## CC MM LTP
Type (A) | Program (B) | Department (C) | Vendor (D) | Equipment (E) | Task Name (F) | Start (G) | Finish (H) | Duration (I) | Period (J) | Work (K) | Group (L) | Group Counter (M) | Maint Item (N) | Component Due Date (O) | Strategy (P) | Function Location (Q) | Annual Estimate | Meas/TotCtrRdg | Counter reading
CC MM MAJOR COMPONENT REPLACEMENT SCHEDULE
| MCORS | All |  |  | MCORS
| MCORS | All |  |  | FY27 - MCORS | 2026-07-01 | 2027-06-30 | 364 days | FY27
| MCORS | Ancillary |  |  | ANCILLARY | 2026-07-01 | 2027-06-30 | 364 days | FY27
854K | MCORS | Ancillary | Force | WD202 | WD202 - MCORS | 2026-08-03 | 2026-09-13 | 41 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Decommissioning & Transport | 2026-08-03 | 2026-08-09 | 6 days | FY27
854K | MCORS | Ancillary | Force | WD202 | WD202 - Baseline Scope | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | DHH Transport Chichester (Site-OEM-Site) | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Opex Variation | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Capex Variation | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Additional Baseline Opex Ancillary Fleet | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Additional Baseline Capex Ancillary Fleet | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Minor Hosing Opex | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Major Hosing Price Variances - Capex | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Baseline Harness (Not on strategy) Capex | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Variation Opex - Corrosions/Repairs | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Capex Variation - Cab Overhaul (if applicable) | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | Site Labour Recovery Per Asset | 2026-08-10 | 2026-09-06 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Brake Accumulator Front | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 4 | 90002955 | B3 | 1000092623 | 26.07.2026 | 22000 | CCK-MP-DOZR-WD202 -BRKSYS-BACCM-BACCF | 6300 | 79930 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Brake Accumulator Rear | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 4 | 90002955 | B3 | 1000092624 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -BRKSYS-BACCM-BACCR | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Replace Brake System Hoses | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 48 | 90013050 | B3 | 1000109626 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -BRKSYS-BRHLF | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Pump Brake | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 4 | 90002957 | B3 | 1000092625 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -BRKSYS-BRPMP | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Sepura SCC Microphone | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 0.5 | 90028996 | B1 | 1000289583 | 20.09.2026 | 12 Monthly | CCK-MP-DOZR-WD202 -COMMUN-RADIO | 6300 | 79903 | 79903
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Engine Cat C32 | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 404 | 90015797 | B1 | 1000286607 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -ENGINE | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Radiator Engine Cooling | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 72 | 90002931 | B3 | 1000092607 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -ENGINE-COSYS-RADTR | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Aftercooler Engine | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 12 | 90010216 | B3 | 1000092639 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -ENGINE-INTEX-AFTER | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Oil Cooler Front Axle Lube | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 6 | 90010219 | B3 | 1000092641 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-AXLEC-OILCF | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Replace Shaft Trans to Rear Diff | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 8 | 90002948 | B3 | 1000268448 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT02 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Replace Shaft Universals Centre | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 6 | 90026668 | B1 | 1000268451 | 01.09.2027 | 11000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT03 | 6300 | 79903 | 3832
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Shaft Centre Brg to Fr Diff | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 8 | 90002950 | B3 | 1000268452 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT04 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Final Drive Position 1 | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 58 | 90002954 | B3 | 1000092619 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-FDRVE-FDR01 | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Final Drive Position 2 | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 58 | 90002954 | B3 | 1000092620 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-FDRVE-FDR02 | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Final Drive Position 4 | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 58 | 90002954 | B3 | 1000092622 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-FDRVE-FDR04 | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Front Differential | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 132 | 90002951 | B3 | 1000092616 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-FRDIF | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Rear Differential | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 134 | 90002952 | B3 | 1000092617 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -FDRSYS-RRDIF | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Overhaul Axle Oscillation Rear | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 64 | 90002953 | B3 | 1000092618 | 26.02.2027 | 15000 | CCK-MP-DOZR-WD202 -FDRSYS-RRDIF-TRNON | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Overhaul Auto Lubrication System | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 96 | 90002971 | B3 | 1000092636 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -GRSYST | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Cylinder Blade Tilt LH | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 14 | 90002967 | B1 | 1000228675 | 24.07.2026 | 22000 | CCK-MP-DOZR-WD202 -HYDSYS-HDCYL-BTCYL | 6300 | 79903 | 21729
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Cylinder Blade Tilt RH | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 14 | 90002968 | B1 | 1000228676 | 24.07.2026 | 22000 | CCK-MP-DOZR-WD202 -HYDSYS-HDCYL-BTCYR | 6300 | 79903 | 21729
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hyd & Steering Oil Cooler | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 24 | 90010218 | B3 | 1000092640 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -HYDSYS-HDOCO | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hyd Motor Fan | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 8 | 90002969 | B3 | 1000092634 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -HYDSYS-HYDMT-HYM01 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hyd Motor & Pump Axle Cooling | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 4 | 90002970 | B3 | 1000092635 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -HYDSYS-HYDMT-HYM02 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hyd Pump Implement | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 12 | 90002962 | B3 | 1000092631 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -HYDSYS-HYDPP-HYP01 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hyd Pump Cooling Fan | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 8 | 90002964 | B3 | 1000092633 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -HYDSYS-HYDPP-HYP03 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Replace Hoses Steering System | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 48 | 90013051 | B3 | 1000109627 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -STRSYS-STHLF | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hyd Pump Steering Main | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 12 | 90002958 | B3 | 1000092626 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -STRSYS-STPMP-STP01 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hyd Pump Steer Secondary | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 4 | 90002960 | B3 | 1000092628 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -STRSYS-STPMP-STP03 | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Overhaul Airconditioner | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 48 | 90013087 | B1 | 1000286613 | 27.07.2026 | 11000 | CCK-MP-DOZR-WD202 -STRUCT-CABIN-AIRCN | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Operators Seat | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 4 | 90002975 | B2 | 1000228703 | 07.01.2027 | 7000 | CCK-MP-DOZR-WD202 -STRUCT-CABIN-SEATS | 6300 | 79903 | 3832
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Transmission Oil Cooler | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 6 | 90002945 | B3 | 1000109668 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -TRNSYS-TROLC | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Pump Transmission | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 8 | 90002946 | B3 | 1000092611 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -TRNSYS-TRPMP | 6300 | 79903 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Replace Hoses Powertrain System | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 48 | 90013049 | B3 | 1000116337 | 27.07.2026 | 22000 | CCK-MP-DOZR-WD202 -TRNSYS-TRHLF | 6300 | 79903 | 21666
854K | MCORS | Ancillary | Force | WD202 | WD202 Replace Hyd Pilot System Hoses | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 24 | 90013052 | B3 | 1000231928 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -HYDSYS-HDHLF-HDHPS | 6300 | 79930 | 10962
854K | MCORS | Ancillary | Force | WD202 | WD202 Repl Hoses Main Hyd-Fan System | 2026-08-10 | 2026-09-06 | 27 days | FY27 | 48 | 90013053 | B3 | 1000231929 | 27.02.2027 | 15000 | CCK-MP-DOZR-WD202 -HYDSYS-HDHLF-HDHMH | 6300 | 79930 | 10962
854K | MCORS | Ancillary | Force | WD202 | Transport & Recommissioning | 2026-09-07 | 2026-09-13 | 6 days | FY27
994H | MCORS | Ancillary | Force | WL021 | WL021 - MCORS | 2026-08-14 | 2026-09-29 | 46 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Decommissioning & Transport | 2026-08-14 | 2026-08-20 | 6 days | FY27
994H | MCORS | Ancillary | Force | WL021 | WL021 - Baseline Scope | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | DHH Transport Chichester (Site-OEM-Site) | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Opex Variation | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Capex Variation | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Additional Baseline Opex Ancillary Fleet | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Additional Baseline Capex Ancillary Fleet | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Minor Hosing Opex | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Major Hosing Price Variances - Capex | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Baseline Harness (Not on strategy) Capex | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Variation Opex - Corrosions/Repairs | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Capex Variation - Cab Overhaul (if applicable) | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | Site Labour Recovery Per Asset | 2026-08-21 | 2026-09-22 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Engine Cat 3516B | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 500 | 90021152 | B1 | 1000222347 | 13.08.2026 | 20000 | CCK-MP-LOAD-WL021 -ENGINE | 6000 | 79997 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Overhaul Engine Prelube | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 10 | 90021219 | B1 | 1000222348 | 13.08.2026 | 20000 | CCK-MP-LOAD-WL021 -ENGINE-LUBSY-PREPP | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Radiator Engine Cooling | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 102 | 90002682 | B2 | 1000028792 | 27.09.2025 | 20000 | CCK-MP-LOAD-WL021 -ENGINE-COSYS-RADTR | 6000 | 79997 | 61894
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Electrical Harness | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 36 | 90010123 | B2 | 1000081869 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -ELCTLV-HARNS | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Transmission Charge Pump | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 12 | 90002694 | B2 | 1000028796 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-TRPMP | 6000 | 79997 | 9602
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Gearbox Pump Drive Rear | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 326 | 90002706 | B2 | 1000028808 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-PMPDR-RRPDR | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Front Drive Shaft | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 16 | 90033175 | B1 | 1000333461 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT04 | 6000 | 79997 | 9602
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Shaft Rear PD To Cntr Brng | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 24 | 90033191 | B1 | 1000333463 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT05 | 6000 | 79997 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Front Pump Drv Drive Shaft | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 16 | 90033189 | B1 | 1000333465 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT06 | 6000 | 79997 | 9602
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Centre Bearing Upper Shaft | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 24 | 90002702 | B2 | 1000028804 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-UCTRB | 6000 | 79997 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Rear Differential | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 114 | 90002708 | B2 | 1000028810 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -FDRSYS-RRDIF | 6000 | 38502 | 38502
994H | MCORS | Ancillary | Force | WL021 | WL021 Overhaul Rear Axle Trunnion | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 112 | 90002709 | B2 | 1000028811 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -FDRSYS-RRDIF-TRNON | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Overhaul Park Brake & Centre Brg | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 36 | 90002711 | B2 | 1000087664 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -BRKSYS-BRPRK | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Pump Brake Cooling | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 8 | 90002713 | B2 | 1000028817 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -BRKSYS-BRPMP-BRP02 | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Brake Accumulator Front | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 12 | 90002714 | B2 | 1000028818 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -BRKSYS-BRACC-BACCF | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Brake Accumulator Rear | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 12 | 90002714 | B2 | 1000089004 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -BRKSYS-BRACC-BACCR | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Brake Oil Cooler | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 72 | 90002715 | B2 | 1000103786 | 22.07.2026 | 20000 | CCK-MP-LOAD-WL021 -BRKSYS-BROCC | 6000 | 79974 | 19658
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Pump Steering LH | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 36 | 90002716 | B2 | 1000028821 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP01 | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Pump Steering RH | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 36 | 90002717 | B2 | 1000028822 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP02 | 6000 | 38502 | 38502
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Steer & Brake Oil Cooler Pump | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 8 | 90002718 | B2 | 1000028823 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP03 | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Reseal Steering & Brake Tank | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 36 | 90010963 | B2 | 1000090047 | 18.08.2026 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STTNK | 6000 | 79914 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Pump Implement LH | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 24 | 90002723 | B2 | 1000028828 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP01 | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Pump Pilot & Cooling | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 12 | 90002726 | B2 | 1000028831 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP04 | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Cyl Lift RH Ext High Lift | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 54 | 90002728 | B2 | 1000028833 | 11.01.2027 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-HCYLR | 6000 | 79974 | 6827
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Cyl Bucket LH Ext High Lift | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 38 | 90015438 | B2 | 1000028834 | 06.12.2026 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-BUCYL | 6000 | 79974 | 7368
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Cyl Bucket RH Ext High Lift | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 36 | 90015437 | B2 | 1000028835 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-BUCYR | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Reseal Tank Hyd | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 12 | 90010623 | B2 | 1000087655 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -HYDSYS-HDTNK-HYT01 | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Oil Cooler | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 96 | 90002733 | B2 | 1000028836 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -HYDSYS-HDOCO | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Valve Implement Ctrl LH | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 24 | 90010965 | B2 | 1000090057 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -HYDSYS-HDVLV-HYV01 | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hyd Valve Implement Ctrl RH | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 24 | 90010966 | B2 | 1000090058 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -HYDSYS-HDVLV-HYV02 | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Main Airhoses & Valves | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 18 | 90011137 | B2 | 1000093191 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -PNEUMC-PNHLF
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Auto Lube Pump | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 6 | 90002737 | B2 | 1000028839 | 26.07.2026 | 10000 | CCK-MP-LOAD-WL021 -GRSYST-ALBPP | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Overhaul Air Conditioner | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 48 | 90021132 | B1 | 1000222345 | 13.08.2026 | 10000 | CCK-MP-LOAD-WL021 -STRUCT-CABIN-AIRCN | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Operators Seat | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 4 | 90002741 | B2 | 1000028841 | 24.10.2026 | 7000 | CCK-MP-LOAD-WL021 -STRUCT-CABIN-SEATS | 6000 | 79974 | 5126
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Sepura SCC Microphone | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 0.5 | 90028998 | B1 | 1000289595 | 12.11.2026 | 12 Monthly | CCK-MP-LOAD-WL021 -COMMUN-RADIO
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Brake System Hoses | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 48 | 90026921 | B1 | 1000271528 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -BRKSYS-BRHLF-BRKHO | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Hydraulic System Hoses | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 96 | 90026922 | B1 | 1000271530 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-HYDHO | 6000 | 79974 | 9601
994H | MCORS | Ancillary | Force | WL021 | WL021 Replace Pilot System Hoses | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 96 | 90009731 | B1 | 1000076462 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-PILHO | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Replace Steering System Hoses | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 96 | 90009732 | B2 | 1000076463 | 15.08.2026 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STHLF-STRHO | 6000 | 79974 | 19277
994H | MCORS | Ancillary | Force | WL021 | WL021 Replace Artic Area Hyd Hosing | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 6 | 90020831 | B1 | 1000220494 | 10.11.2026 | 8 Monthly | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-ARTHO
994H | MCORS | Ancillary | Force | WL021 | WL021 12 Monthly Hydraulic Tune Up | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 24 | 90015111 | B1 | 1000266797 | 29.06.2025 | 52 Weekly | CCK-MP-LOAD-WL021 -HYDSYS
994H | MCORS | Ancillary | Force | WL021 | WL021 Repl Transmission Oil Cooler | 2026-08-21 | 2026-09-22 | 32 days | FY27 | 36 | 90002695 | B2 | 1000028797 | 27.09.2025 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-TROLC | 6000 | 79997 | 24580
994H | MCORS | Ancillary | Force | WL021 | Transport & Recommissioning | 2026-09-23 | 2026-09-29 | 6 days | FY27
994H | MCORS | Ancillary | Force | WL261 | WL261 - MCORS | 2026-11-06 | 2026-12-22 | 46 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Decommissioning & Transport | 2026-11-06 | 2026-11-12 | 6 days | FY27
994H | MCORS | Ancillary | Force | WL261 | WL261 - Baseline Scope | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | DHH Transport Chichester (Site-OEM-Site) | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Opex Variation | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Capex Variation | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Additional Baseline Opex Ancillary Fleet | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Additional Baseline Capex Ancillary Fleet | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Minor Hosing Opex | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Major Hosing Price Variances - Capex | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Baseline Harness (Not on strategy) Capex | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Variation Opex - Corrosions/Repairs | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Capex Variation - Cab Overhaul (if applicable) | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | Site Labour Recovery Per Asset | 2026-11-13 | 2026-12-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Brake System Hoses Midlife | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 4 | 90026908 | B1 | 1000271587 | 14.07.2026 | 10000 | CCK-MP-LOAD-WL261 -BRKSYS-BRHLF-BRKHO | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Overhaul Park Brake & Centre Brg | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 36 | 90002711 | B2 | 1000090343 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -BRKSYS-BRPRK | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Sepura SCC Microphone | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 0.5 | 90028998 | B1 | 1000289599 | 19.09.2026 | 12 Monthly | CCK-MP-LOAD-WL261 -COMMUN-RADIO | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Engine Midlife complete | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 170 | 90021253 | B1 | 1000222530 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -ENGINE | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Radiator Engine Cooling | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 102 | 90002682 | B2 | 1000090289 | 08.03.2026 | 20000 | CCK-MP-LOAD-WL261 -ENGINE-COSYS-RADTR | 6000 | 76567 | 22498
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Final Drive Position 1 | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 83 | 90002710 | B2 | 1000090308 | 01.03.2027 | 16000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR01 | 6000 | 77065 | 12939
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Final Drive Position 4 | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 83 | 90002710 | B2 | 1000090311 | 01.03.2027 | 16000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR04 | 6000 | 77065 | 12939
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Front Differential | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 114 | 90002707 | B2 | 1000090305 | 07.10.2026 | 20000 | CCK-MP-LOAD-WL261 -FDRSYS-FRDIF | 6000 | 77065 | 19291
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Rear Differential | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 114 | 90002708 | B2 | 1000090306 | 07.10.2026 | 20000 | CCK-MP-LOAD-WL261 -FDRSYS-RRDIF | 6000 | 77065 | 19291
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Auto Lube Pump | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 6 | 90002737 | B2 | 1000090330 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -GRSYST-ALBPP | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 12 Monthly Hydraulic Tune Up | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 24 | 90015111 | B1 | 1000126197 | 23.09.2026 | 52 Weekly | CCK-MP-LOAD-WL261 -HYDSYS | 6000 | 77065 | 30681
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Cyl Bucket LH Ext High Lift | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 38 | 90015438 | B2 | 1000131508 | 26.04.2026 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-BUCYL | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Cyl Bucket RH Ext High Lift | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 36 | 90015437 | B2 | 1000131509 | 26.04.2026 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-BUCYR | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Cyl Lift RH Ext High Lift | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 54 | 90002728 | B2 | 1000112666 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-HCYLR | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Hyd System Hoses Midlife | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 24 | 90026914 | B1 | 1000271589 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-HYDHO | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Main Airhoses & Valves | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 18 | 90011137 | B2 | 1000112602 | 03.04.2026 | 20000 | CCK-MP-LOAD-WL261 -PNEUMC-PNHLF | 6000 | 77065 | 43701
994H | MCORS | Ancillary | Force | WL261 | WL261 Replace Steering System Hoses | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 96 | 90009732 | B2 | 1000090339 | 07.10.2026 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STHLF-STRHO | 6000 | 77065 | 19291
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Steering STIC Pilot Valve | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 12 | 90026110 | B1 | 1000257366 | 17.12.2026 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STIPV | 6000 | 77065 | 36172
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Hyd Pump Steering RH | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 36 | 90002717 | B2 | 1000090318 | 07.10.2026 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP02 | 6000 | 77065 | 19291
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Cyl Steering LH | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 26 | 90002721 | B2 | 1000090321 | 10.09.2026 | 12000 | CCK-MP-LOAD-WL261 -STRSYS-STRCY-STCYL | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Cyl Steering RH | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 28 | 90002722 | B2 | 1000090322 | 27.05.2026 | 12000 | CCK-MP-LOAD-WL261 -STRSYS-STRCY-STCYR | 6000 | 77065 | 13476
994H | MCORS | Ancillary | Force | WL261 | WL261 Overhaul Air Conditioner | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 48 | 90021132 | B1 | 1000222521 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -STRUCT-CABIN-AIRCN | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Operators Seat | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 4 | 90002741 | B2 | 1000090331 | 17.02.2027 | 7000 | CCK-MP-LOAD-WL261 -STRUCT-CABIN-SEATS | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Articulation Overhaul | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 360 | 90032991 | B1 | 1000329971 | 26.01.2027 | 16000 | CCK-MP-LOAD-WL261 -STRUCT-CHASS-ARTIC | 6000 | 77065 | 13461
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Centre Output Drive Shaft | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 14 | 90033171 | B1 | 1000333495 | 07.10.2026 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT03 | 6000 | 77065 | 19291
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Front Drive Shaft Unis | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 8 | 90033188 | B1 | 1000333498 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT04 | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Rr PDrv Drive Shaft Ctr Brg | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 8 | 90033193 | B1 | 1000333500 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT05 | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Fr Pump Drv Shaft Unis | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 8 | 90033190 | B1 | 1000333502 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT06 | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Centre Bearing Upper Shaft | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 24 | 90002702 | B2 | 1000090300 | 15.05.2026 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-UCTRB | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Gearbox Pump Drive Front | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 74 | 90002705 | B2 | 1000090303 | 25.01.2027 | 16000 | CCK-MP-LOAD-WL261 -TRNSYS-PMPDR-FRPDR | 6000 | 77065 | 13476
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Transmission | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 74 | 90002692 | B2 | 1000090291 | 25.01.2027 | 16000 | CCK-MP-LOAD-WL261 -TRNSYS-TRANS | 6000 | 77065 | 13476
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Transmission System Hoses | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 96 | 90026923 | B2 | 1000271590 | 15.02.2027 | 16000 | CCK-MP-LOAD-WL261 -TRNSYS-TRHLF-TRNHO | 6000 | 77065 | 13476
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Transmission Charge Pump | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 12 | 90002694 | B2 | 1000090292 | 11.05.2026 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-TRPMP | 6000 | 77065 | 11736
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Torque Converter | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 48 | 90002693 | B2 | 1000090290 | 17.03.2027 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-TRQUE | 6000 | 77065 | 16650
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Axle Shaft Position 1 | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 12 | 90012242 | B2 | 1000112615 | 13.11.2026 | 32000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP1 | 6000 | 77065 | 30681
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Axle Shaft Position 2 | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 12 | 90012242 | B2 | 1000112616 | 13.11.2026 | 32000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP2 | 6000 | 77065 | 30681
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Axle Shaft Position 3 | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 12 | 90012242 | B2 | 1000112617 | 13.11.2026 | 32000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP3 | 6000 | 77065 | 30681
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Axle Shaft Position 4 | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 12 | 90012242 | B2 | 1000112618 | 13.11.2026 | 32000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP4 | 6000 | 77065 | 30681
994H | MCORS | Ancillary | Force | WL261 | WL261 Repl Transmission Transfer Case | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 74 | 90017029 | B2 | 1000153215 | 25.01.2027 | 16000 | CCK-MP-LOAD-WL261 -TRNSYS-TRTRF | 6000 | 77065 | 13476
994H | MCORS | Ancillary | Force | WL261 | WL261 Replace Artic Area Hyd Hosing | 2026-11-13 | 2026-12-15 | 32 days | FY27 | 6 | 90020831 | B1 | 1000220498 | 23.10.2026 | 8 Monthly | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-ARTHO
994H | MCORS | Ancillary | Force | WL261 | Transport & Recommissioning | 2026-12-16 | 2026-12-22 | 6 days | FY27
854K | MCORS | Ancillary | Force | WD201 | WD201 - MCORS | 2027-02-09 | 2027-03-22 | 41 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Decommissioning & Transport | 2027-02-09 | 2027-02-15 | 6 days | FY27
854K | MCORS | Ancillary | Force | WD201 | WD201 - Baseline Scope | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | DHH Transport Chichester (Site-OEM-Site) | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Opex Variation | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Capex Variation | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Additional Baseline Opex Ancillary Fleet | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Additional Baseline Capex Ancillary Fleet | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Minor Hosing Opex | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Major Hosing Price Variances - Capex | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Baseline Harness (Not on strategy) Capex | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Variation Opex - Corrosions/Repairs | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Capex Variation - Cab Overhaul (if applicable) | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | Site Labour Recovery Per Asset | 2027-02-16 | 2027-03-15 | 27 days | FY27
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Brake Accumulator Front | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 4 | 90002955 | B3 | 1000092573 | 02.06.2027 | 22000 | CCK-MP-DOZR-WD201 -BRKSYS-BACCM-BACCF | 6300 | 81082 | 39870
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Brake Accumulator Rear | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 4 | 90002955 | B3 | 1000092574 | 02.06.2027 | 22000 | CCK-MP-DOZR-WD201 -BRKSYS-BACCM-BACCR | 6300 | 81082 | 39870
854K | MCORS | Ancillary | Force | WD201 | WD201 Replace Brake System Hoses | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 48 | 90013050 | B3 | 1000109598 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -BRKSYS-BRHLF | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Pump Brake | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 4 | 90002957 | B3 | 1000092575 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -BRKSYS-BRPMP | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Radiator Engine Cooling | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 72 | 90002931 | B3 | 1000092557 | 27.03.2027 | 22000 | CCK-MP-DOZR-WD201 -ENGINE-COSYS-RADTR | 6300 | 81082 | 17929
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Aftercooler Engine | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 12 | 90010216 | B3 | 1000092589 | 27.03.2027 | 22000 | CCK-MP-DOZR-WD201 -ENGINE-INTEX-AFTER | 6300 | 81082 | 17929
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Oil Cooler Front Axle Lube | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 6 | 90010219 | B3 | 1000092591 | 27.03.2027 | 22000 | CCK-MP-DOZR-WD201 -FDRSYS-AXLEC-OILCF | 6300 | 81082 | 17929
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Final Drive Position 2 | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 58 | 90002954 | B3 | 1000092570 | 01.05.2027 | 22000 | CCK-MP-DOZR-WD201 -FDRSYS-FDRVE-FDR02 | 6300 | 81082 | 17330
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Final Drive Position 4 | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 58 | 90002954 | B3 | 1000092572 | 27.03.2027 | 22000 | CCK-MP-DOZR-WD201 -FDRSYS-FDRVE-FDR04 | 6300 | 81082 | 17929
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Front Differential | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 132 | 90002951 | B3 | 1000092566 | 01.05.2027 | 22000 | CCK-MP-DOZR-WD201 -FDRSYS-FRDIF | 6300 | 81082 | 17330
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Rear Differential | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 134 | 90002952 | B3 | 1000092567 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -FDRSYS-RRDIF | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Overhaul Axle Oscillation Rear | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 64 | 90002953 | B3 | 1000092568 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -FDRSYS-RRDIF-TRNON | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Hyd Motor Fan | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 8 | 90002969 | B3 | 1000092584 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDMT-HYM01 | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Hyd Motor & Pump Axle Cooling | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 4 | 90002970 | B3 | 1000092585 | 26.08.2026 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDMT-HYM02 | 6300 | 81082 | 14552
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Hyd Pump Implement | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 12 | 90002962 | B3 | 1000092581 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDPP-HYP01 | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Hyd Pump Cooling Fan | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 8 | 90002964 | B3 | 1000092583 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDPP-HYP03 | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Replace Hoses Steering System | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 48 | 90013051 | B3 | 1000109599 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STHLF | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Hyd Pump Steering Main | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 12 | 90002958 | B3 | 1000092576 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP01 | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Pump Str Pilot & Str Cooling | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 4 | 90002959 | B3 | 1000092577 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP02 | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Hyd Pump Steer Secondary | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 4 | 90002960 | B3 | 1000092578 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP03 | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Cyl Steering LH | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 22 | 90002961 | B3 | 1000092579 | 27.03.2027 | 22000 | CCK-MP-DOZR-WD201 -STRSYS-STRCY-STCYL | 6300 | 81082 | 17929
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Transmission Oil Cooler | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 6 | 90002945 | B3 | 1000109666 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -TRNSYS-TROLC | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Torque Converter | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 164 | 90002943 | B3 | 1000092559 | 27.03.2027 | 22000 | CCK-MP-DOZR-WD201 -TRNSYS-TRQUE | 6300 | 81082 | 17929
854K | MCORS | Ancillary | Force | WD201 | WD201 Replace Hyd Pilot System Hoses | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 24 | 90013052 | B3 | 1000231926 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HDHLF-HDHPS | 6300 | 81106 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Repl Hoses Main Hyd-Fan System | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 48 | 90013053 | B3 | 1000231927 | 13.12.2026 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HDHLF-HDHMH | 6300 | 81106 | 12720
854K | MCORS | Ancillary | Force | WD201 | WD201 Clean Engine Pre Cleaners | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 6 | 90015808 | B1 | 1000286601 | 13.12.2026 | 5500 | CCK-MP-DOZR-WD201 -ENGINE-INTEX-AIRFL | 6300 | 81082 | 28558
854K | MCORS | Ancillary | Force | WD201 | WD201 Service Airconditioner | 2027-02-16 | 2027-03-15 | 27 days | FY27 | 24 | 90003915 | B1 | 1000286605 | 13.12.2026 | 5500 | CCK-MP-DOZR-WD201 -STRUCT-CABIN-AIRCN | 6300 | 81082 | 12720
854K | MCORS | Ancillary | Force | WD201 | Transport & Recommissioning | 2027-03-16 | 2027-03-22 | 6 days | FY27
994H | MCORS | Ancillary | Force | WL022 | WL022 - MCORS | 2027-04-06 | 2027-05-22 | 46 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Decommissioning & Transport | 2027-04-06 | 2027-04-12 | 6 days | FY27
994H | MCORS | Ancillary | Force | WL022 | WL022 - Baseline Scope | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | DHH Transport Chichester (Site-OEM-Site) | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Opex Variation | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Capex Variation | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Additional Baseline Opex Ancillary Fleet | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Additional Baseline Capex Ancillary Fleet | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Minor Hosing Opex | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Major Hosing Price Variances - Capex | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Baseline Harness (Not on strategy) Capex | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Variation Opex - Corrosions/Repairs | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Capex Variation - Cab Overhaul (if applicable) | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | Site Labour Recovery Per Asset | 2027-04-13 | 2027-05-15 | 32 days | FY27
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Cyl Steering RH | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 28 | 90002722 | B2 | 1000028892 | 14.10.2026 | 12000 | CCK-MP-LOAD-WL022 -STRSYS-STRCY-STCYR | 6000 | 80515 | 10370
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Transmission Charge Pump | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 12 | 90002694 | B2 | 1000028861 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-TRPMP | 6000 | 80537 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Centre Bearing Upper Shaft | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 24 | 90002702 | B2 | 1000028869 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-UCTRB | 6000 | 80537 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Overhaul Park Brake & Centre Brg | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 36 | 90002711 | B2 | 1000087665 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -BRKSYS-BRPRK | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Pump Implement LH | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 24 | 90002723 | B2 | 1000028893 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP01 | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Pump Implement RH | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 24 | 90002724 | B2 | 1000028894 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP02 | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Pump Implement Centre | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 24 | 90002725 | B2 | 1000028895 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP03 | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Pump Pilot & Cooling | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 12 | 90002726 | B2 | 1000028896 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP04 | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Cyl Lift LH Ext High Lift | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 54 | 90002728 | B2 | 1000028897 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-HCYLL | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Cyl Bucket LH Ext High Lift | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 38 | 90015438 | B2 | 1000131514 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-BUCYL | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Cyl Bucket RH Ext High Lift | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 36 | 90015437 | B2 | 1000131515 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-BUCYR | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Engine Cat 3516B | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 500 | 90021152 | B1 | 1000222369 | 18.03.2027 | 20000 | CCK-MP-LOAD-WL022 -ENGINE | 6000 | 80537 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Overhaul Engine Prelube | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 10 | 90021219 | B1 | 1000222370 | 18.03.2027 | 20000 | CCK-MP-LOAD-WL022 -ENGINE-LUBSY-PREPP | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Radiator Engine Cooling | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 102 | 90002682 | B2 | 1000028857 | 18.03.2027 | 20000 | CCK-MP-LOAD-WL022 -ENGINE-COSYS-RADTR | 6000 | 80537 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Torque Converter | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 48 | 90002693 | B2 | 1000028859 | 18.03.2027 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-TRQUE | 6000 | 80537 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Overhaul Air Conditioner | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 48 | 90021132 | B1 | 1000222367 | 18.03.2027 | 10000 | CCK-MP-LOAD-WL022 -STRUCT-CABIN-AIRCN | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Electrical Harness | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 36 | 90010123 | B2 | 1000081871 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -ELCTLV-HARNS | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Front Drive Shaft | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 16 | 90033175 | B1 | 1000333473 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT04 | 6000 | 80537 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Front Pump Drv Drive Shaft | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 16 | 90033189 | B1 | 1000333477 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT06 | 6000 | 80537 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Rear Differential | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 114 | 90002708 | B2 | 1000028875 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -FDRSYS-RRDIF | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Overhaul Rear Axle Trunnion | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 112 | 90002709 | B2 | 1000028876 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -FDRSYS-RRDIF-TRNON | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Pump Brake | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 12 | 90002712 | B2 | 1000028881 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -BRKSYS-BRPMP-BRP01 | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Brake Oil Cooler | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 72 | 90002715 | B2 | 1000028885 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -BRKSYS-BROCC | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Steer & Brake Oil Cooler Pump | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 8 | 90002718 | B2 | 1000028888 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -STRSYS-STPMP-STP03 | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Reseal Tank Hyd | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 12 | 90010623 | B2 | 1000087656 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -HYDSYS-HDTNK-HYT01 | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Oil Cooler | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 96 | 90002733 | B2 | 1000028901 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -HYDSYS-HDOCO | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Valve Implement Ctrl LH | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 24 | 90010965 | B2 | 1000090059 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -HYDSYS-HDVLV-HYV01 | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Valve Implement Ctrl RH | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 24 | 90010966 | B2 | 1000090180 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -HYDSYS-HDVLV-HYV02 | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hyd Pilot Accumulator | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 4 | 90012174 | B2 | 1000100308 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -HYDSYS-PACCM | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Main Airhoses & Valves | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 18 | 90011137 | B2 | 1000093192 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -PNEUMC-PNHLF
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Auto Lube Pump | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 6 | 90002737 | B2 | 1000116256 | 19.03.2027 | 10000 | CCK-MP-LOAD-WL022 -GRSYST-ALBPP | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Steering Neutralizer Valves | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 6 | 90002720 | B2 | 1000076052 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -STRSYS-STNVS | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Brake System Hoses | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 48 | 90026921 | B1 | 1000271534 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -BRKSYS-BRHLF-BRKHO | 6000 | 80515 | 7474
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Hydraulic System Hoses | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 96 | 90026922 | B1 | 1000271536 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-HYDHO | 6000 | 80515 | 7474
994H | MCORS | Ancillary | Force | WL022 | WL022 Replace Pilot System Hoses | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 96 | 90009731 | B1 | 1000076467 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-PILHO | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Replace Steering System Hoses | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 96 | 90009732 | B2 | 1000076468 | 19.03.2027 | 20000 | CCK-MP-LOAD-WL022 -STRSYS-STHLF-STRHO | 6000 | 80515 | 15801
994H | MCORS | Ancillary | Force | WL022 | WL022 Replace Artic Area Hyd Hosing | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 6 | 90020831 | B1 | 1000220496 | 22.03.2027 | 8 Monthly | CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-ARTHO
994H | MCORS | Ancillary | Force | WL022 | WL022 12 Monthly Hydraulic Tune Up | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 24 | 90015111 | B1 | 1000126743 | 31.03.2027 | 52 Weekly | CCK-MP-LOAD-WL022 -HYDSYS
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Trans System Hoses Midlife | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 4 | 90026915 | B1 | 1000271539 | 01.04.2027 | 8000 | CCK-MP-LOAD-WL022 -TRNSYS-TRHLF-TRNHO | 6000 | 80515 | 35795
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Cyl Steering LH | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 26 | 90002721 | B2 | 1000028891 | 08.04.2027 | 12000 | CCK-MP-LOAD-WL022 -STRSYS-STRCY-STCYL | 6000 | 80515 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Reseal Steering & Brake Tank | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 36 | 90010963 | B2 | 1000090048 | 16.07.2026 | 20000 | CCK-MP-LOAD-WL022 -STRSYS-STTNK | 6000 | 80515 | 57915
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Axle Shaft Position 2 | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 12 | 90012242 | B2 | 1000101203 | 11.06.2027 | 32000 | CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP2 | 6000 | 80515 | 26409
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Axle Shaft Position 3 | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 12 | 90012242 | B2 | 1000101204 | 11.06.2027 | 32000 | CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP3 | 6000 | 80515 | 26409
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Axle Shaft Position 4 | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 12 | 90012242 | B2 | 1000101205 | 11.06.2027 | 32000 | CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP4 | 6000 | 80515 | 26409
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Rear Output Drive Shaft Unis | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 8 | 90033167 | B1 | 1000333470 | 20.06.2027 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT02 | 6000 | 80537 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Input Shaft Unis | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 8 | 90033167 | B1 | 1000333468 | 23.06.2027 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT01 | 6000 | 80537 | 7470
994H | MCORS | Ancillary | Force | WL022 | WL022 Repl Ctr Output Drive Shaft Unis | 2027-04-13 | 2027-05-15 | 32 days | FY27 | 8 | 90033173 | B1 | 1000333472 | 24.06.2027 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT03 | 6000 | 80537 | 7470
994H | MCORS | Ancillary | Force | WL022 | Transport & Recommissioning | 2027-05-16 | 2027-05-22 | 6 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | GR7107 - MCORS | 2027-05-10 | 2027-06-08 | 29 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Decommissioning & Transport | 2027-05-10 | 2027-05-13 | 3 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | GR7107 - Baseline Scope | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | DHH Transport Chichester (Site-OEM-Site) | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Opex Variation | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Capex Variation | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Additional Baseline Opex Ancillary Fleet | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Additional Baseline Capex Ancillary Fleet | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Minor Hosing Opex | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Major Hosing Price Variances - Capex | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Baseline Harness (Not on strategy) Capex | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Variation Opex - Corrosions/Repairs | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Capex Variation - Cab Overhaul (if applicable) | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | Site Labour Recovery Per Asset | 2027-05-14 | 2027-06-04 | 21 days | FY27
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Service Brake LHF | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019593 | B1 | 1000201893 | 25.09.2026 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBLF | 5500 | 24399 | 13118
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Service Brake LHR | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019611 | B1 | 1000201895 | 25.09.2026 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBLR | 5500 | 24399 | 13118
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Service Brake RHF | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019593 | B1 | 1000201894 | 25.09.2026 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBRF | 5500 | 24399 | 13118
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Service Brake RHR | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019611 | B1 | 1000201896 | 25.09.2026 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBRR | 5500 | 24399 | 13118
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Articulation RH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021512 | B1 | 1000225882 | 01.11.2026 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYR | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Wheel Lean LH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021515 | B1 | 1000225890 | 05.01.2027 | 6000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYL | 5500 | 24399 | 3609
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Wheel Lean RH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021515 | B1 | 1000225891 | 05.01.2027 | 6000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYR | 5500 | 24399 | 3609
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Overhaul Cabin | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 12 | 90019617 | B1 | 1000201933 | 24.03.2027 | 28000 | CCK-MP-GRDR-GR7107-STRUCT-CABIN | 5500 | 24399 | 24399
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Chassis Articulation | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 362 | 90021517 | B1 | 1000225893 | 09.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-CHASS-ARTIC | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Fuel Cooler | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 6 | 90021516 | B1 | 1000225880 | 09.05.2027 | 14000 | CCK-MP-GRDR-GR7107-ENGINE-FUSYS-FULCO | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Replace Brake System Hoses | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019613 | B1 | 1000201915 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-BRHLF | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Brake Slack Adjuster LH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 1 | 90019594 | B1 | 1000201920 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SLACK-SLACL | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Brake Slack Adjuster Rear | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 1 | 90019594 | B1 | 1000201921 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SLACK-SLACR | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Electrical Harness | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019616 | B1 | 1000201914 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-ELCTLV-HARNS | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Engine Cat C27 | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 296 | 90019620 | B1 | 1000201867 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-ENGINE | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Radiator Engine Cooling | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 96 | 90019579 | B1 | 1000201883 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-ENGINE-COSYS-RADTR | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Aftercooler Engine | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 24 | 90019580 | B1 | 1000201919 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-ENGINE-INTEX-AFTER | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Rear Axle Assembly | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 96 | 90030388 | B1 | 1000303443 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-FDRSYS-DIFFL | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Overhaul Auto Lube System | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019605 | B1 | 1000201906 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-GRSYST-ALBPP | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Articulation LH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021512 | B1 | 1000225881 | 10.05.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYL | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Blade Lift RH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021509 | B1 | 1000225884 | 10.05.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BLCYR | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Blade Tilt LH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021511 | B1 | 1000225885 | 10.05.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYL | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Blade Tilt RH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021511 | B1 | 1000225886 | 10.05.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYR | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Centre Shift | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021510 | B1 | 1000225887 | 10.05.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-CSCYL | 5500 | 24399 | 173
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Ripper Lift | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021514 | B1 | 1000225888 | 10.05.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-RICYL | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Replace Hydraulic System Hoses | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019614 | B1 | 1000201916 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-HYDSYS-HDHLF | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Hyd Fan Motor | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 6 | 90019604 | B1 | 1000201905 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-HYDSYS-HDMOT-MOT03 | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Hyd Oil Cooler | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 6 | 90021519 | B1 | 1000225892 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-HYDSYS-HDOCO | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Hyd Pump Differential Lock | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 8 | 90019603 | B1 | 1000201904 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-DIFFL | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Hyd Pump Brake & Fan | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 8 | 90019601 | B1 | 1000201903 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-FANPP | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Hyd Pump Implement | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 8 | 90019599 | B1 | 1000201901 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-HYIMP | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Hyd Pump Steering Main | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 8 | 90019600 | B1 | 1000201902 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-HYSTP | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Hyd Pump Secondary Steering | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 6 | 90019598 | B1 | 1000201900 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRSYS-STEMG-SESPP | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Replace Steering System Hoses | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019612 | B1 | 1000201918 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRSYS-STHLF | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Front Axle Assembly | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 96 | 90019637 | B1 | 1000201930 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-AXLES | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Overhaul Blade | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019610 | B1 | 1000201913 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-BLADE | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Overhaul Air Condtioner System | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019635 | B1 | 1000201882 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-CABIN-AIRCN | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Blade Mounting Bracket LH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 24 | 90019608 | B1 | 1000201909 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-CIRCL-BLMBL | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Blade Mounting Bracket RH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 24 | 90019608 | B1 | 1000201910 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-CIRCL-BLMBR | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Overhaul Drawbar Group | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 72 | 90019607 | B1 | 1000201908 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-DRWBR | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Transmission Oil Cooler | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 6 | 90019584 | B1 | 1000201886 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-TRNSYS-TROLC | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Pump Transmission | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 8 | 90019586 | B1 | 1000201887 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-TRNSYS-TRPMP | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Torque Converter | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 96 | 90019582 | B1 | 1000201884 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-TRNSYS-TRQUE | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Replace Powertrain System Hoses | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 48 | 90019615 | B1 | 1000201917 | 10.05.2027 | 14000 | CCK-MP-GRDR-GR7107-TRNSYS-POHLF | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Drive Shaft TCon to Trans | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 3 | 90019588 | B1 | 1000201889 | 27.06.2027 | 7000 | CCK-MP-GRDR-GR7107-FDRSYS-DRSHT-SHT02 | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Drive Shaft Trans to Rr Diff | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 6 | 90019587 | B1 | 1000201888 | 29.06.2027 | 7000 | CCK-MP-GRDR-GR7107-FDRSYS-DRSHT-SHT01 | 5500 | 24399 | 9687
24 | MCORS | Ancillary | Force | GR7107 | GR7107 Repl Cyl Blade Lift LH | 2027-05-14 | 2027-06-04 | 21 days | FY27 | 4 | 90021509 | B1 | 1000225883 | 29.06.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BLCYL | 5500 | 24399 | 1941
24 | MCORS | Ancillary | Force | GR7107 | Transport & Recommissioning | 2027-06-05 | 2027-06-08 | 3 days | FY27
| MCORS | Haul |  |  | HAUL | 2026-07-01 | 2027-06-30 | 364 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | DT5314 - MCORS | 2026-11-02 | 2026-12-16 | 44 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Decommissioning & Transport | 2026-11-02 | 2026-11-08 | 6 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | DT5314 - Baseline scope | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | DHH Transport Chichester (Site-OEM-Site) | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Opex Variation | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Capex Variation | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Additional Baseline Opex Truck Fleet | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Additional Baseline Capex Truck Fleet | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Capex Variation - Steer Box (if applicable) | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Minor Hosing Opex | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Baseline Harness (Not on strategy) Capex | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Variation Opex - Corrosions/Repairs | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | Site Labour Recovery Per Asset | 2026-11-09 | 2026-12-08 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Engine Cat C175-16 LMR | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 137 | 90018364 | B1 | 1000167058 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-ENGINE | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Radiator Engine Cooling | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 62 | 90031072 | B1 | 1000307688 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-ENGINE-COSYS-RADTR | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Pump Drive | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 39 | 90002365 | B1 | 1000166993 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-ENGINE-PMPDR | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Transmisson Calibration | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 8 | 90029836 | B1 | 1000298814 | 10.08.2026 | 4500 | CCK-MP-HAUL-DT5314-TRNSYS-TRANS | 7400 | 45898 | 950
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Spider Trans Driveshaft | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 12 | 90017211 | B1 | 1000167056 | 04.01.2027 | 6000 | CCK-MP-HAUL-DT5314-FDRSYS-DRSHT-UNVSL | 7400 | 45898 | 950
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Drive Line Axle LH | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 4 | 90014919 | B2 | 1000167044 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-FDRSYS-DRLAX-AXLLH | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Drive Line Axle RH | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 4 | 90014943 | B2 | 1000167045 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-FDRSYS-DRLAX-AXLRH | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Wheel End RH | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 54.5 | 90017425 | B1 | 1000167001 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-FDRSYS-FDRVE-FDRRH | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Motor Lube Axle Rear & Hoses | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 8 | 90026943 | B1 | 1000272185 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYM01 | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl AOC Fan Motor Rear | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 6 | 90002376 | B1 | 1000167003 | 06.12.2026 | 12000 | CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYM02 | 7400 | 45898 | 9592
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Axle Lube Hyd Pump | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 4 | 90010102 | B1 | 1000167055 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYPUM | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Overhaul Accumulator Brake LHF | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167004 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BACCM-FRLFT | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Overhaul Accumulator Brake RHF | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167005 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BACCM-FRRGT | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Overhaul Accumulator Brake Rear | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167006 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BACCM-BACCR | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Pump Brake Cooling | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 17 | 90002379 | B1 | 1000167007 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-HYFPP | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Overhaul Valve Control Brake | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 20 | 90002380 | B2 | 1000167008 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BRVLV | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Brake Oil Cooler Front | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 13 | 90010109 | B1 | 1000167033 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BROCO-BROCF | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Brake Oil Cooler Rear | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 13 | 90010108 | B1 | 1000167032 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BROCO-BROCR | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Motor Brake Oil Cooling | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 3 | 90002381 | B1 | 1000167043 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BROCO-HYMO1 | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Replace Brake System Hoses | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 90 | 90010129 | B1 | 1000167034 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BRHLF-BRHOS | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Brake Cooling System Hoses | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 60 | 90010130 | B2 | 1000167035 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-BRKSYS-BRHLF-CBRHO | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Steering Hyd Oil Cooler | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 9 | 90012866 | B2 | 1000167042 | 09.05.2027 | 15000 | CCK-MP-HAUL-DT5314-STRSYS-STOCO | 7400 | 45898 | 9592
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Hyd Pump Steering Main & Fan | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 17 | 90002383 | B1 | 1000167011 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-STRSYS-STPMP | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Steering HMU | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 8 | 90002384 | B1 | 1000167012 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-STRSYS-STHMU | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Ovhl Accumulator Steering Front | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167015 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-STRSYS-STACC-SACCF | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Ovhl Accumulator Steering Middle | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167016 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-STRSYS-STACC-SACCM | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Replace Steering System Hoses | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 106 | 90010133 | B2 | 1000167036 | 09.05.2027 | 15000 | CCK-MP-HAUL-DT5314-STRSYS-STHLF-STRHO | 7400 | 45898 | 9592
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Pump Hoist & Brake | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 15 | 90002388 | B1 | 1000167019 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-HYDSYS-HOPMP | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Valve Hoist | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 8 | 90018607 | B1 | 1000183601 | 27.11.2026 | 48000 | CCK-MP-HAUL-DT5314-HYDSYS-HOVLV | 7400 | 45898 | 45898
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Cyl Hoist LH | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 33 | 90015130 | B1 | 1000167047 | 06.06.2027 | 28000 | CCK-MP-HAUL-DT5314-HYDSYS-HOCYL-HCYLL | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Cyl Hoist RH | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 33 | 90015131 | B1 | 1000167048 | 06.06.2027 | 28000 | CCK-MP-HAUL-DT5314-HYDSYS-HOCYL-HCYLR | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Replace Hoses Hoist System | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 40 | 90010105 | B2 | 1000167031 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-HYDSYS-HDHLF-HSTHO | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Auto Lube Pump | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 3 | 90002391 | B1 | 1000285806 | 16.11.2026 | 8000 | CCK-MP-HAUL-DT5314-GRSYST-ALBPP | 7400 | 45898 | 14121
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Service Air Conditioner 12M | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 18 | 90018230 | B1 | 1000174193 | 07.11.2026 | 12 Monthly | CCK-MP-HAUL-DT5314-STRUCT-CABIN-AIRCN | 7400 | 45898 | 45898
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Operators Seat | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 6 | 90002395 | B1 | 1000167021 | 03.05.2027 | 15000 | CCK-MP-HAUL-DT5314-STRUCT-CABIN-SEATS | 7400 | 45898 | 13481
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Rear Axle Linkages | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 113 | 90002396 | B1 | 1000167022 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-STRUCT-CHASS-AXLIK | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Wheel Group Front LH XLF | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167065 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-STRUCT-AXLES-HUBLH | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Wheel Group Front RH XLF | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167067 | 21.11.2026 | 24000 | CCK-MP-HAUL-DT5314-STRUCT-AXLES-HUBRH | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Cyl Suspension LHF | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 84 | 90002408 | B1 | 1000167026 | 06.06.2027 | 28000 | CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYLF | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Cyl Suspension RHF | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 84 | 90002408 | B2 | 1000167027 | 28.09.2026 | 28000 | CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYRF | 7400 | 45898 | 27054
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Cyl Suspension LHR | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 39 | 90002409 | B1 | 1000167024 | 06.06.2027 | 28000 | CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYLR | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | DT5314 Repl Cyl Suspension RHR | 2026-11-09 | 2026-12-08 | 29 days | FY27 | 39 | 90002409 | B2 | 1000167025 | 06.06.2027 | 28000 | CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYRR | 7400 | 45898 | 22018
793F | MCORS | Haul | Thiess | DT5314 | Transport & Recommissioning | 2026-12-09 | 2026-12-16 | 7 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | DT5318 - MCORS | 2027-01-02 | 2027-02-15 | 44 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Decommissioning & Transport | 2027-01-02 | 2027-01-08 | 6 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | DT5318 - Baseline scope | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | DHH Transport Chichester (Site-OEM-Site) | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Opex Variation | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Capex Variation | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Additional Baseline Opex Truck Fleet | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Additional Baseline Capex Truck Fleet | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Capex Variation - Steer Box (if applicable) | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Minor Hosing Opex | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Baseline Harness (Not on strategy) Capex | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Variation Opex - Corrosions/Repairs | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | Site Labour Recovery Per Asset | 2027-01-09 | 2027-02-07 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Radiator Fan Hoses | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 11 | 90031073 | B1 | 1000307697 | 15.02.2027 | 12000 | CCK-MP-HAUL-DT5318-ENGINE-COSYS-RADTR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Pump Drive | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 39 | 90002365 | B1 | 1000167313 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-ENGINE-PMPDR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Transmisson Calibration | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 8 | 90029836 | B1 | 1000298818 | 20.09.2026 | 4500 | CCK-MP-HAUL-DT5318-TRNSYS-TRANS | 7400 | 45240 | 9085
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Spider Trans Driveshaft | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 12 | 90017211 | B1 | 1000167376 | 26.12.2026 | 6000 | CCK-MP-HAUL-DT5318-FDRSYS-DRSHT-UNVSL | 7400 | 45240 | 9085
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Drive Line Axle LH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 4 | 90014919 | B2 | 1000167364 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-FDRSYS-DRLAX-AXLLH | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Drive Line Axle RH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 4 | 90014943 | B2 | 1000167365 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-FDRSYS-DRLAX-AXLRH | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Wheel End LH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 58.5 | 90030708 | B1 | 1000167320 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-FDRSYS-FDRVE-FDRLH | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Wheel End RH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 54.5 | 90017425 | B1 | 1000167321 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-FDRSYS-FDRVE-FDRRH | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Motor Lube Axle Rear & Hoses | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 8 | 90026943 | B1 | 1000272193 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYM01 | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl AOC Fan Motor Rear | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 6 | 90002376 | B1 | 1000167323 | 30.12.2026 | 12000 | CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYM02 | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Axle Lube Hyd Pump | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 4 | 90010102 | B1 | 1000167375 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYPUM | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Overhaul Accumulator Brake LHF | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167324 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BACCM-FRLFT | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Overhaul Accumulator Brake RHF | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167325 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BACCM-FRRGT | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Overhaul Accumulator Brake Rear | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167326 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BACCM-BACCR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Pump Brake Cooling | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 17 | 90002379 | B1 | 1000167327 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-HYFPP | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Overhaul Valve Control Brake | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 20 | 90002380 | B2 | 1000167328 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BRVLV | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Brake Oil Cooler Front | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 13 | 90010109 | B1 | 1000167353 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BROCO-BROCF | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Brake Oil Cooler Rear | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 13 | 90010108 | B1 | 1000167352 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BROCO-BROCR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Motor Brake Oil Cooling | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 3 | 90002381 | B1 | 1000167363 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BROCO-HYMO1 | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Replace Brake System Hoses | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 90 | 90010129 | B1 | 1000167354 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BRHLF-BRHOS | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Brake Cooling System Hoses | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 60 | 90010130 | B2 | 1000167355 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-BRKSYS-BRHLF-CBRHO | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Steering Hyd Oil Cooler | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 9 | 90012866 | B2 | 1000167362 | 02.06.2027 | 15000 | CCK-MP-HAUL-DT5318-STRSYS-STOCO | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Hyd Pump Steering Main & Fan | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 17 | 90002383 | B1 | 1000167331 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRSYS-STPMP | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Steering HMU | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 8 | 90002384 | B1 | 1000167332 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRSYS-STHMU | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Steering LH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 20 | 90002385 | B1 | 1000167333 | 13.07.2027 | 15000 | CCK-MP-HAUL-DT5318-STRSYS-STRCY-STCYL | 7400 | 45240 | 9085
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Steering RH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 20 | 90002385 | B2 | 1000167334 | 13.07.2027 | 15000 | CCK-MP-HAUL-DT5318-STRSYS-STRCY-STCYR | 7400 | 45240 | 9085
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Ovhl Accumulator Steering Front | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167335 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRSYS-STACC-SACCF | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Ovhl Accumulator Steering Middle | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167336 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRSYS-STACC-SACCM | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Ovhl Accumulator Steering Rear | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167337 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRSYS-STACC-SACCR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Steering Linkages | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 28 | 90028568 | B1 | 1000317675 | 13.07.2027 | 15000 | CCK-MP-HAUL-DT5318-STRSYS-STLTR | 7400 | 45240 | 45240
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Replace Steering System Hoses | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 106 | 90010133 | B2 | 1000167356 | 02.06.2027 | 15000 | CCK-MP-HAUL-DT5318-STRSYS-STHLF-STRHO | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Pump Hoist & Brake | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 15 | 90002388 | B1 | 1000167339 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-HYDSYS-HOPMP | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Valve Hoist | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 8 | 90018607 | B1 | 1000183609 | 23.12.2026 | 48000 | CCK-MP-HAUL-DT5318-HYDSYS-HOVLV | 7400 | 45240 | 45240
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Hoist LH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 33 | 90015130 | B1 | 1000167367 | 12.07.2027 | 28000 | CCK-MP-HAUL-DT5318-HYDSYS-HOCYL-HCYLL | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Hoist RH | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 33 | 90015131 | B1 | 1000167368 | 12.07.2027 | 28000 | CCK-MP-HAUL-DT5318-HYDSYS-HOCYL-HCYLR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Replace Hoses Hoist System | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 40 | 90010105 | B2 | 1000167351 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-HYDSYS-HDHLF-HSTHO | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Auto Lube Pump | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 3 | 90002391 | B1 | 1000285810 | 03.08.2026 | 8000 | CCK-MP-HAUL-DT5318-GRSYST-ALBPP | 7400 | 45240 | 9085
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Service Air Conditioner 12M | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 18 | 90018230 | B1 | 1000174195 | 16.07.2026 | 12 Monthly | CCK-MP-HAUL-DT5318-STRUCT-CABIN-AIRCN | 7400 | 45240 | 9085
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Operators Seat | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 6 | 90002395 | B1 | 1000167341 | 13.07.2027 | 15000 | CCK-MP-HAUL-DT5318-STRUCT-CABIN-SEATS | 7400 | 45240 | 9085
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Rear Axle Linkages | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 113 | 90002396 | B1 | 1000167342 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRUCT-CHASS-AXLIK | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Wheel Group Front LH XLF | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167385 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRUCT-AXLES-HUBLH | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Wheel Group Front RH XLF | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167387 | 26.12.2026 | 24000 | CCK-MP-HAUL-DT5318-STRUCT-AXLES-HUBRH | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Suspension LHF | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 84 | 90002408 | B1 | 1000167346 | 12.07.2027 | 28000 | CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYLF | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Suspension RHF | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 84 | 90002408 | B2 | 1000167347 | 12.07.2027 | 28000 | CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYRF | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Suspension LHR | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 39 | 90002409 | B1 | 1000167344 | 12.07.2027 | 28000 | CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYLR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | DT5318 Repl Cyl Suspension RHR | 2027-01-09 | 2027-02-07 | 29 days | FY27 | 39 | 90002409 | B2 | 1000167345 | 12.07.2027 | 28000 | CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYRR | 7400 | 45240 | 21163
793F | MCORS | Haul | Thiess | DT5318 | Transport & Recommissioning | 2027-02-08 | 2027-02-15 | 7 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | DT5317 - MCORS | 2027-02-22 | 2027-04-07 | 44 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Decommissioning & Transport | 2027-02-22 | 2027-02-28 | 6 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | DT5317 - Baseline scope | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | DHH Transport Chichester (Site-OEM-Site) | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Opex Variation | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Capex Variation | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Additional Baseline Opex Truck Fleet | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Additional Baseline Capex Truck Fleet | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Capex Variation - Steer Box (if applicable) | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Minor Hosing Opex | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Baseline Harness (Not on strategy) Capex | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Variation Opex - Corrosions/Repairs | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | Site Labour Recovery Per Asset | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Engine Cat C175-16 LMR | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 137 | 90018364 | B1 | 1000167298 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-ENGINE | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Radiator Engine Cooling | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 62 | 90031072 | B1 | 1000307694 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-ENGINE-COSYS-RADTR | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Pump Drive | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 39 | 90002365 | B1 | 1000167233 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-ENGINE-PMPDR | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Torque Converter | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 53 | 90002369 | B1 | 1000167237 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-TRNSYS-TRQUE | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Transmisson Calibration | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 8 | 90029836 | B1 | 1000298817 | 05.05.2027 | 4500 | CCK-MP-HAUL-DT5317-TRNSYS-TRANS | 7400 | 45576 | 9163
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Drive Line Axle LH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 4 | 90014919 | B2 | 1000167284 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-FDRSYS-DRLAX-AXLLH | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Drive Line Axle RH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 4 | 90014943 | B2 | 1000167285 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-FDRSYS-DRLAX-AXLRH | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Wheel End LH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 58.5 | 90030708 | B1 | 1000167240 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-FDRSYS-FDRVE-FDRLH | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Wheel End RH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 54.5 | 90017425 | B1 | 1000167241 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-FDRSYS-FDRVE-FDRRH | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Motor Lube Axle Rear & Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 8 | 90026943 | B1 | 1000272191 | 21.01.2027 | 24000 | CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYM01 | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl AOC Fan Motor Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 6 | 90002376 | B1 | 1000167243 | 21.01.2027 | 12000 | CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYM02 | 7400 | 45576 | 8696
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Axle Lube Hyd Pump | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 4 | 90010102 | B1 | 1000167295 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYPUM | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Overhaul Accumulator Brake LHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167244 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BACCM-FRLFT | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Overhaul Accumulator Brake RHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167245 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BACCM-FRRGT | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Overhaul Accumulator Brake Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167246 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BACCM-BACCR | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Pump Brake Cooling | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 17 | 90002379 | B1 | 1000167247 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-HYFPP | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Overhaul Valve Control Brake | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 20 | 90002380 | B2 | 1000167248 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BRVLV | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Brake Oil Cooler Front | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 13 | 90010109 | B1 | 1000167273 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BROCO-BROCF | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Brake Oil Cooler Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 13 | 90010108 | B1 | 1000167272 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BROCO-BROCR | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Motor Brake Oil Cooling | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 3 | 90002381 | B1 | 1000167283 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BROCO-HYMO1 | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Replace Brake System Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 90 | 90010129 | B1 | 1000167274 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BRHLF-BRHOS | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Brake Cooling System Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 60 | 90010130 | B2 | 1000167275 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-BRKSYS-BRHLF-CBRHO | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Steering Hyd Oil Cooler | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 9 | 90012866 | B2 | 1000167282 | 17.06.2027 | 15000 | CCK-MP-HAUL-DT5317-STRSYS-STOCO | 7400 | 45576 | 8696
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Hyd Pump Steering Main & Fan | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 17 | 90002383 | B1 | 1000167251 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-STRSYS-STPMP | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Steering HMU | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 8 | 90002384 | B1 | 1000167252 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-STRSYS-STHMU | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Ovhl Accumulator Steering Front | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167255 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-STRSYS-STACC-SACCF | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Ovhl Accumulator Steering Middle | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167256 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-STRSYS-STACC-SACCM | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Ovhl Accumulator Steering Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167257 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-STRSYS-STACC-SACCR | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Replace Steering System Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 106 | 90010133 | B2 | 1000167276 | 17.06.2027 | 15000 | CCK-MP-HAUL-DT5317-STRSYS-STHLF-STRHO | 7400 | 45576 | 8696
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Pump Hoist & Brake | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 15 | 90002388 | B1 | 1000167259 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-HYDSYS-HOPMP | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Valve Hoist | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 8 | 90018607 | B1 | 1000183607 | 08.12.2026 | 48000 | CCK-MP-HAUL-DT5317-HYDSYS-HOVLV | 7400 | 45576 | 45576
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Cyl Hoist LH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 33 | 90015130 | B1 | 1000167287 | 17.08.2027 | 28000 | CCK-MP-HAUL-DT5317-HYDSYS-HOCYL-HCYLL | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Cyl Hoist RH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 33 | 90015131 | B1 | 1000167288 | 17.08.2027 | 28000 | CCK-MP-HAUL-DT5317-HYDSYS-HOCYL-HCYLR | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Replace Hoses Hoist System | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 40 | 90010105 | B2 | 1000167271 | 01.02.2027 | 24000 | CCK-MP-HAUL-DT5317-HYDSYS-HDHLF-HSTHO | 7400 | 45556 | 20460
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Service Air Conditioner 12M | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 18 | 90018230 | B1 | 1000174194 | 18.06.2027 | 12 Monthly | CCK-MP-HAUL-DT5317-STRUCT-CABIN-AIRCN | 7400 | 45576 | 32701
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Rear Axle Linkages | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 113 | 90002396 | B1 | 1000167262 | 27.02.2027 | 24000 | CCK-MP-HAUL-DT5317-STRUCT-CHASS-AXLIK | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Wheel Group Front LH XLF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167305 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-STRUCT-AXLES-HUBLH | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Wheel Group Front RH XLF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167307 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT5317-STRUCT-AXLES-HUBRH | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Cyl Suspension LHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 84 | 90002408 | B1 | 1000167266 | 17.08.2027 | 28000 | CCK-MP-HAUL-DT5317-STRUCT-SUSPN-SCYLF | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Cyl Suspension RHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 84 | 90002408 | B2 | 1000167267 | 17.08.2027 | 28000 | CCK-MP-HAUL-DT5317-STRUCT-SUSPN-SCYRF | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | DT5317 Repl Cyl Suspension LHR | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 39 | 90002409 | B1 | 1000167264 | 17.08.2027 | 28000 | CCK-MP-HAUL-DT5317-STRUCT-SUSPN-SCYLR | 7400 | 45576 | 20480
793F | MCORS | Haul | Thiess | DT5317 | Transport & Recommissioning | 2027-03-31 | 2027-04-07 | 7 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | DT5315 - MCORS | 2027-02-22 | 2027-04-07 | 44 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Decommissioning & Transport | 2027-02-22 | 2027-02-28 | 6 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | DT5315 - Baseline scope | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | DHH Transport Chichester (Site-OEM-Site) | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Opex Variation | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Capex Variation | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Additional Baseline Opex Truck Fleet | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Additional Baseline Capex Truck Fleet | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Capex Variation - Steer Box (if applicable) | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Minor Hosing Opex | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Baseline Harness (Not on strategy) Capex | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Variation Opex - Corrosions/Repairs | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | Site Labour Recovery Per Asset | 2027-03-01 | 2027-03-30 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Engine Cat C175-16 LMR | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 137 | 90018364 | B1 | 1000167138 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-ENGINE | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Radiator Engine Cooling | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 62 | 90031072 | B1 | 1000307690 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-ENGINE-COSYS-RADTR | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Pump Drive | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 39 | 90002365 | B1 | 1000167073 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-ENGINE-PMPDR | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Spiders Pump Drive Shaft | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 4 | 90002366 | B1 | 1000167074 | 24.11.2027 | 18000 | CCK-MP-HAUL-DT5315-ENGINE-PMPDR-DRSHT | 7400 | 45392 | 8351
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Torque Converter | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 53 | 90002369 | B1 | 1000167077 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-TRNSYS-TRQUE | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Transmission | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 39 | 90026996 | B1 | 1000272513 | 24.11.2027 | 18000 | CCK-MP-HAUL-DT5315-TRNSYS-TRANS | 7400 | 45392 | 8391
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Replace Trans TCon System Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 20 | 90010099 | B3 | 1000167117 | 26.11.2027 | 18000 | CCK-MP-HAUL-DT5315-TRNSYS-TRANS-TRNHO | 7400 | 45392 | 25826
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Transmission Oil Cooler | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 12 | 90010097 | B1 | 1000167108 | 26.11.2027 | 18000 | CCK-MP-HAUL-DT5315-TRNSYS-TROLC | 7400 | 45392 | 8391
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Drive Shaft Transmission | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 16 | 90017195 | B1 | 1000167137 | 24.11.2027 | 18000 | CCK-MP-HAUL-DT5315-FDRSYS-DRSHT | 7400 | 45392 | 8391
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Differential | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 66 | 90014504 | B1 | 1000167079 | 24.11.2027 | 18000 | CCK-MP-HAUL-DT5315-FDRSYS-DIFFL | 7400 | 45392 | 8391
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Replace Hoses Differential System | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 5 | 90010101 | B3 | 1000167118 | 24.11.2027 | 18000 | CCK-MP-HAUL-DT5315-FDRSYS-DIFFL-DIFHO | 7400 | 45392 | 25826
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Drive Line Axle LH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 4 | 90014919 | B2 | 1000167124 | 19.08.2027 | 24000 | CCK-MP-HAUL-DT5315-FDRSYS-DRLAX-AXLLH | 7400 | 45392 | 16359
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Drive Line Axle RH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 4 | 90014943 | B2 | 1000167125 | 19.08.2027 | 24000 | CCK-MP-HAUL-DT5315-FDRSYS-DRLAX-AXLRH | 7400 | 45392 | 16418
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Wheel End LH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 58.5 | 90030708 | B1 | 1000167080 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-FDRSYS-FDRVE-FDRLH | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Wheel End RH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 54.5 | 90017425 | B1 | 1000167081 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-FDRSYS-FDRVE-FDRRH | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Motor Lube Axle Rear & Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 8 | 90026943 | B1 | 1000272187 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYM01 | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl AOC Fan Motor Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 6 | 90002376 | B1 | 1000167083 | 01.02.2027 | 12000 | CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYM02 | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Axle Lube Hyd Pump | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 4 | 90010102 | B1 | 1000167135 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYPUM | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Overhaul Accumulator Brake LHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167084 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BACCM-FRLFT | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Overhaul Accumulator Brake RHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167085 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BACCM-FRRGT | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Overhaul Accumulator Brake Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167086 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BACCM-BACCR | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Pump Brake Cooling | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 17 | 90002379 | B1 | 1000167087 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-HYFPP | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Overhaul Valve Control Brake | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 20 | 90002380 | B2 | 1000167088 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BRVLV | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Brake Oil Cooler Front | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 13 | 90010109 | B1 | 1000167113 | 19.08.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BROCO-BROCF | 7400 | 45392 | 16359
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Brake Oil Cooler Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 13 | 90010108 | B1 | 1000167112 | 19.08.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BROCO-BROCR | 7400 | 45392 | 16359
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Motor Brake Oil Cooling | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 3 | 90002381 | B1 | 1000167123 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BROCO-HYMO1 | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Replace Brake System Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 90 | 90010129 | B1 | 1000167114 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BRHLF-BRHOS | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Brake Cooling System Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 60 | 90010130 | B2 | 1000167115 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-BRKSYS-BRHLF-CBRHO | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Steering Hyd Oil Cooler | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 9 | 90012866 | B2 | 1000167122 | 01.07.2027 | 15000 | CCK-MP-HAUL-DT5315-STRSYS-STOCO | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Hyd Pump Steering Main & Fan | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 17 | 90002383 | B1 | 1000167091 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRSYS-STPMP | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Steering HMU | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 8 | 90002384 | B1 | 1000167092 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRSYS-STHMU | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Steering LH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 20 | 90002385 | B1 | 1000167093 | 09.08.2027 | 15000 | CCK-MP-HAUL-DT5315-STRSYS-STRCY-STCYL | 7400 | 45392 | 8391
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Steering RH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 20 | 90002385 | B2 | 1000167094 | 29.06.2027 | 15000 | CCK-MP-HAUL-DT5315-STRSYS-STRCY-STCYR | 7400 | 45392 | 8391
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Ovhl Accumulator Steering Front | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167095 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRSYS-STACC-SACCF | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Ovhl Accumulator Steering Middle | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167096 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRSYS-STACC-SACCM | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Ovhl Accumulator Steering Rear | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167097 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRSYS-STACC-SACCR | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Steering Linkages | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 28 | 90028568 | B1 | 1000317669 | 21.07.2026 | 15000 | CCK-MP-HAUL-DT5315-STRSYS-STLTR | 7400 | 45392 | 30138
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Replace Steering System Hoses | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 106 | 90010133 | B2 | 1000167116 | 01.07.2027 | 15000 | CCK-MP-HAUL-DT5315-STRSYS-STHLF-STRHO | 7400 | 45392 | 8351
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Pump Hoist & Brake | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 15 | 90002388 | B1 | 1000167099 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-HYDSYS-HOPMP | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Valve Hoist | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 8 | 90018607 | B1 | 1000183603 | 14.12.2026 | 48000 | CCK-MP-HAUL-DT5315-HYDSYS-HOVLV | 7400 | 45392 | 45392
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Hoist LH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 33 | 90015130 | B1 | 1000167127 | 10.08.2027 | 28000 | CCK-MP-HAUL-DT5315-HYDSYS-HOCYL-HCYLL | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Hoist RH | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 33 | 90015131 | B1 | 1000167128 | 10.08.2027 | 28000 | CCK-MP-HAUL-DT5315-HYDSYS-HOCYL-HCYLR | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Replace Hoses Hoist System | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 40 | 90010105 | B2 | 1000167111 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-HYDSYS-HDHLF-HSTHO | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Auto Lube Pump | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 3 | 90002391 | B1 | 1000285807 | 15.11.2026 | 8000 | CCK-MP-HAUL-DT5315-GRSYST-ALBPP | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Service Air Conditioner 12M | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 18 | 90018230 | B1 | 1000172994 | 02.07.2027 | 12 Monthly | CCK-MP-HAUL-DT5315-STRUCT-CABIN-AIRCN | 7400 | 45392 | 45392
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Rear Axle Linkages | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 113 | 90002396 | B1 | 1000167102 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRUCT-CHASS-AXLIK | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Wheel Group Front LH XLF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167145 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRUCT-AXLES-HUBLH | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Wheel Group Front RH XLF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167147 | 25.01.2027 | 24000 | CCK-MP-HAUL-DT5315-STRUCT-AXLES-HUBRH | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Suspension LHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 84 | 90002408 | B1 | 1000167106 | 10.08.2027 | 28000 | CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYLF | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Suspension RHF | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 84 | 90002408 | B2 | 1000167107 | 10.08.2027 | 28000 | CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYRF | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Suspension LHR | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 39 | 90002409 | B1 | 1000167104 | 10.08.2027 | 28000 | CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYLR | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | DT5315 Repl Cyl Suspension RHR | 2027-03-01 | 2027-03-30 | 29 days | FY27 | 39 | 90002409 | B2 | 1000167105 | 10.08.2027 | 28000 | CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYRR | 7400 | 45392 | 20546
793F | MCORS | Haul | Thiess | DT5315 | Transport & Recommissioning | 2027-03-31 | 2027-04-07 | 7 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | DT5316 - MCORS | 2027-04-07 | 2027-05-21 | 44 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Decommissioning & Transport | 2027-04-07 | 2027-04-13 | 6 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | DT5316 - Baseline scope | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | DHH Transport Chichester (Site-OEM-Site) | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Opex Variation | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Capex Variation | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Additional Baseline Opex Truck Fleet | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Additional Baseline Capex Truck Fleet | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Capex Variation - Steer Box (if applicable) | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Minor Hosing Opex | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Baseline Harness (Not on strategy) Capex | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Variation Opex - Corrosions/Repairs | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | Site Labour Recovery Per Asset | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Engine Cat C175-16 LMR | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 137 | 90018364 | B1 | 1000167218 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-ENGINE | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Radiator Engine Cooling | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 62 | 90031072 | B1 | 1000307692 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-ENGINE-COSYS-RADTR | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Pump Drive | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 39 | 90002365 | B1 | 1000167153 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-ENGINE-PMPDR | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Spiders Pump Drive Shaft | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 4 | 90002366 | B1 | 1000167154 | 21.12.2027 | 18000 | CCK-MP-HAUL-DT5316-ENGINE-PMPDR-DRSHT | 7400 | 45108 | 27566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Torque Converter | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 53 | 90002369 | B1 | 1000167157 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-TRNSYS-TRQUE | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Replace Trans TCon System Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 20 | 90010099 | B3 | 1000167197 | 22.02.2027 | 18000 | CCK-MP-HAUL-DT5316-TRNSYS-TRANS-TRNHO | 7400 | 45108 | 45108
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Transmission Oil Cooler | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90010097 | B1 | 1000167188 | 24.12.2027 | 18000 | CCK-MP-HAUL-DT5316-TRNSYS-TROLC | 7400 | 45108 | 25317
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Differential | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 66 | 90014504 | B1 | 1000167159 | 24.12.2027 | 18000 | CCK-MP-HAUL-DT5316-FDRSYS-DIFFL | 7400 | 45108 | 7861
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Replace Hoses Differential System | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 5 | 90010101 | B3 | 1000167198 | 27.12.2026 | 18000 | CCK-MP-HAUL-DT5316-FDRSYS-DIFFL-DIFHO | 7400 | 45108 | 45108
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Drive Line Axle LH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 4 | 90014919 | B2 | 1000167204 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-FDRSYS-DRLAX-AXLLH | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Drive Line Axle RH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 4 | 90014943 | B2 | 1000167205 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-FDRSYS-DRLAX-AXLRH | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Wheel End RH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 54.5 | 90017425 | B1 | 1000167161 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-FDRSYS-FDRVE-FDRRH | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Motor Lube Axle Rear & Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 8 | 90026943 | B1 | 1000272189 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYM01 | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl AOC Fan Motor Rear | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 6 | 90002376 | B1 | 1000167163 | 28.02.2027 | 12000 | CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYM02 | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Axle Lube Hyd Pump | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 4 | 90010102 | B1 | 1000167215 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYPUM | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Overhaul Accumulator Brake LHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167164 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BACCM-FRLFT | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Overhaul Accumulator Brake RHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167165 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BACCM-FRRGT | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Overhaul Accumulator Brake Rear | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 11 | 90002378 | B1 | 1000167166 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BACCM-BACCR | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Pump Brake Cooling | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 17 | 90002379 | B1 | 1000167167 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-HYFPP | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Overhaul Valve Control Brake | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 20 | 90002380 | B2 | 1000167168 | 18.12.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BRVLV | 7400 | 45108 | 13925
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Motor Brake Oil Cooling | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 3 | 90002381 | B1 | 1000167203 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BROCO-HYMO1 | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Replace Brake System Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 90 | 90010129 | B1 | 1000167194 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BRHLF-BRHOS | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Brake Cooling System Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 60 | 90010130 | B2 | 1000167195 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BRHLF-CBRHO | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Steering Hyd Oil Cooler | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 9 | 90012866 | B2 | 1000167202 | 04.01.2028 | 15000 | CCK-MP-HAUL-DT5316-STRSYS-STOCO | 7400 | 45108 | 7861
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Hyd Pump Steering Main & Fan | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 17 | 90002383 | B1 | 1000167171 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRSYS-STPMP | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Steering HMU | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 8 | 90002384 | B1 | 1000167172 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRSYS-STHMU | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Cyl Steering LH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 20 | 90002385 | B1 | 1000167173 | 30.07.2027 | 15000 | CCK-MP-HAUL-DT5316-STRSYS-STRCY-STCYL | 7400 | 45108 | 7788
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Cyl Steering RH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 20 | 90002385 | B2 | 1000167174 | 30.07.2027 | 15000 | CCK-MP-HAUL-DT5316-STRSYS-STRCY-STCYR | 7400 | 45108 | 7788
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Ovhl Accumulator Steering Front | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167175 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRSYS-STACC-SACCF | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Ovhl Accumulator Steering Middle | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167176 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRSYS-STACC-SACCM | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Ovhl Accumulator Steering Rear | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90002386 | B1 | 1000167177 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRSYS-STACC-SACCR | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Replace Steering System Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 106 | 90010133 | B2 | 1000167196 | 04.01.2028 | 15000 | CCK-MP-HAUL-DT5316-STRSYS-STHLF-STRHO | 7400 | 45108 | 7861
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Pump Hoist & Brake | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 15 | 90002388 | B1 | 1000167179 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-HYDSYS-HOPMP | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Valve Hoist | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 8 | 90018607 | B1 | 1000183605 | 28.12.2026 | 48000 | CCK-MP-HAUL-DT5316-HYDSYS-HOVLV | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Cyl Hoist LH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 33 | 90015130 | B1 | 1000167207 | 28.09.2027 | 28000 | CCK-MP-HAUL-DT5316-HYDSYS-HOCYL-HCYLL | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Replace Hoses Hoist System | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 40 | 90010105 | B2 | 1000167191 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-HYDSYS-HDHLF-HSTHO | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Operators Seat | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 6 | 90002395 | B1 | 1000167181 | 19.03.2027 | 15000 | CCK-MP-HAUL-DT5316-STRUCT-CABIN-SEATS | 7400 | 45108 | 10479
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Rear Axle Linkages | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 113 | 90002396 | B1 | 1000167182 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRUCT-CHASS-AXLIK | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Wheel Group Front LH XLF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167225 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRUCT-AXLES-HUBLH | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Wheel Group Front RH XLF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 54 | 90018999 | B1 | 1000167227 | 14.03.2027 | 24000 | CCK-MP-HAUL-DT5316-STRUCT-AXLES-HUBRH | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Cyl Suspension LHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 84 | 90002408 | B1 | 1000167186 | 11.02.2027 | 28000 | CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYLF | 7400 | 45108 | 24198
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Cyl Suspension RHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 84 | 90002408 | B2 | 1000167187 | 28.09.2027 | 28000 | CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYRF | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Cyl Suspension LHR | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 39 | 90002409 | B1 | 1000167184 | 28.09.2027 | 28000 | CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYLR | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | DT5316 Repl Cyl Suspension RHR | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 39 | 90002409 | B2 | 1000167185 | 28.09.2027 | 28000 | CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYRR | 7400 | 45108 | 19566
793F | MCORS | Haul | Thiess | DT5316 | Transport & Recommissioning | 2027-05-14 | 2027-05-21 | 7 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | DT5313 - MCORS | 2027-04-07 | 2027-05-21 | 44 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Decommissioning & Transport | 2027-04-07 | 2027-04-13 | 6 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | DT5313 - Baseline scope | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | DHH Transport Chichester (Site-OEM-Site) | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Opex Variation | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Capex Variation | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Additional Baseline Opex Truck Fleet | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Additional Baseline Capex Truck Fleet | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Capex Variation - Steer Box (if applicable) | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Minor Hosing Opex | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Baseline Harness (Not on strategy) Capex | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Variation Opex - Corrosions/Repairs | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | Site Labour Recovery Per Asset | 2027-04-14 | 2027-05-13 | 29 days | FY27
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Engine Cat C175-16 LMR | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 137 | 90018364 | B1 | 1000166978 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-ENGINE | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Radiator Engine Cooling | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 62 | 90031072 | B1 | 1000307686 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-ENGINE-COSYS-RADTR | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Pump Drive | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 39 | 90002365 | B1 | 1000166913 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-ENGINE-PMPDR | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Torque Converter | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 53 | 90002369 | B1 | 1000166917 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-TRNSYS-TRQUE | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Transmisson Calibration | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 8 | 90029836 | B1 | 1000298813 | 06.07.2027 | 4500 | CCK-MP-HAUL-DT5313-TRNSYS-TRANS | 7400 | 44693 | 6773
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Spider Trans Driveshaft | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90017211 | B1 | 1000166976 | 27.04.2027 | 6000 | CCK-MP-HAUL-DT5313-FDRSYS-DRSHT-UNVSL | 7400 | 44693 | 6773
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Differential | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 66 | 90014504 | B1 | 1000166919 | 01.11.2026 | 18000 | CCK-MP-HAUL-DT5313-FDRSYS-DIFFL | 7400 | 44693 | 17171
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Replace Hoses Differential System | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 5 | 90010101 | B3 | 1000166958 | 08.02.2028 | 18000 | CCK-MP-HAUL-DT5313-FDRSYS-DIFFL-DIFHO | 7400 | 44693 | 25140
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Drive Line Axle LH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 4 | 90014919 | B2 | 1000166964 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-FDRSYS-DRLAX-AXLLH | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Drive Line Axle RH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 4 | 90014943 | B2 | 1000166965 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-FDRSYS-DRLAX-AXLRH | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Wheel End LH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 58.5 | 90030708 | B1 | 1000166920 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-FDRSYS-FDRVE-FDRLH | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Wheel End RH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 54.5 | 90017425 | B1 | 1000166921 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-FDRSYS-FDRVE-FDRRH | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Motor Lube Axle Rear & Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 8 | 90026943 | B1 | 1000272183 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYM01 | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl AOC Fan Motor Rear | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 6 | 90002376 | B1 | 1000166923 | 23.04.2027 | 12000 | CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYM02 | 7400 | 44693 | 6773
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Axle Lube Hyd Pump | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 4 | 90010102 | B1 | 1000166975 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYPUM | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Overhaul Accumulator Brake LHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 11 | 90002378 | B1 | 1000166924 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BACCM-FRLFT | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Overhaul Accumulator Brake RHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 11 | 90002378 | B1 | 1000166925 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BACCM-FRRGT | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Pump Brake Cooling | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 17 | 90002379 | B1 | 1000166927 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-HYFPP | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Overhaul Valve Control Brake | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 20 | 90002380 | B2 | 1000166928 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BRVLV | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Motor Brake Oil Cooling | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 3 | 90002381 | B1 | 1000166963 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BROCO-HYMO1 | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Replace Brake System Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 90 | 90010129 | B1 | 1000166954 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BRHLF-BRHOS | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Brake Cooling System Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 60 | 90010130 | B2 | 1000166955 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BRHLF-CBRHO | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Steering Hyd Oil Cooler | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 9 | 90012866 | B2 | 1000166962 | 18.09.2027 | 15000 | CCK-MP-HAUL-DT5313-STRSYS-STOCO | 7400 | 44693 | 6773
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Hyd Pump Steering Main & Fan | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 17 | 90002383 | B1 | 1000166931 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRSYS-STPMP | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Steering HMU | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 8 | 90002384 | B1 | 1000166932 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRSYS-STHMU | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Cyl Steering LH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 20 | 90002385 | B1 | 1000166933 | 25.08.2026 | 15000 | CCK-MP-HAUL-DT5313-STRSYS-STRCY-STCYL | 7400 | 44693 | 14543
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Ovhl Accumulator Steering Front | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90002386 | B1 | 1000166935 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRSYS-STACC-SACCF | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Ovhl Accumulator Steering Middle | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90002386 | B1 | 1000166936 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRSYS-STACC-SACCM | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Ovhl Accumulator Steering Rear | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 12 | 90002386 | B1 | 1000166937 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRSYS-STACC-SACCR | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Steering Linkages | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 28 | 90028568 | B1 | 1000317665 | 25.08.2026 | 15000 | CCK-MP-HAUL-DT5313-STRSYS-STLTR | 7400 | 44693 | 14543
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Replace Steering System Hoses | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 106 | 90010133 | B2 | 1000166956 | 08.01.2028 | 15000 | CCK-MP-HAUL-DT5313-STRSYS-STHLF-STRHO | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Pump Hoist & Brake | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 15 | 90002388 | B1 | 1000166939 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-HYDSYS-HOPMP | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Valve Hoist | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 8 | 90018607 | B1 | 1000183599 | 13.01.2027 | 48000 | CCK-MP-HAUL-DT5313-HYDSYS-HOVLV | 7400 | 44693 | 44693
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Cyl Hoist LH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 33 | 90015130 | B1 | 1000166967 | 04.08.2026 | 28000 | CCK-MP-HAUL-DT5313-HYDSYS-HOCYL-HCYLL | 7400 | 44693 | 27967
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Cyl Hoist RH | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 33 | 90015131 | B1 | 1000166968 | 04.08.2026 | 28000 | CCK-MP-HAUL-DT5313-HYDSYS-HOCYL-HCYLR | 7400 | 44693 | 27967
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Replace Hoses Hoist System | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 40 | 90010105 | B2 | 1000166951 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-HYDSYS-HDHLF-HSTHO | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Service Air Conditioner 12M | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 18 | 90018230 | B1 | 1000172995 | 23.12.2026 | 12 Monthly | CCK-MP-HAUL-DT5313-STRUCT-CABIN-AIRCN | 7400 | 44693 | 44693
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Operators Seat | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 6 | 90002395 | B1 | 1000166941 | 25.10.2026 | 15000 | CCK-MP-HAUL-DT5313-STRUCT-CABIN-SEATS | 7400 | 44693 | 13322
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Rear Axle Linkages | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 113 | 90002396 | B1 | 1000166942 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRUCT-CHASS-AXLIK | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Wheel Group Front LH XLF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 54 | 90018999 | B1 | 1000166985 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRUCT-AXLES-HUBLH | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Wheel Group Front RH XLF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 54 | 90018999 | B1 | 1000166987 | 18.03.2027 | 24000 | CCK-MP-HAUL-DT5313-STRUCT-AXLES-HUBRH | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Cyl Suspension LHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 84 | 90002408 | B1 | 1000166946 | 01.10.2027 | 28000 | CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYLF | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Cyl Suspension RHF | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 84 | 90002408 | B2 | 1000166947 | 01.10.2027 | 28000 | CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYRF | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | DT5313 Repl Cyl Suspension RHR | 2027-04-14 | 2027-05-13 | 29 days | FY27 | 39 | 90002409 | B2 | 1000166945 | 01.10.2027 | 28000 | CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYRR | 7400 | 44693 | 19408
793F | MCORS | Haul | Thiess | DT5313 | Transport & Recommissioning | 2027-05-14 | 2027-05-21 | 7 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | WC220 - MCORS | 2027-04-27 | 2027-07-07 | 71 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Decommissioning & Transport | 2027-04-27 | 2027-05-04 | 7 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | WC220 - Baseline Scope | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | DHH Transport Chichester (Site-OEM-Site) | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Opex Variation | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Capex Variation | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Additional Baseline Opex Truck Fleet | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Additional Baseline Capex Truck Fleet | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Minor Hosing Opex | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Baseline Harness (Not on strategy) Capex | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Variation Opex - Corrosions/Repairs | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | MCORS Watercart Module Refurbishment CAPEX | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | Site Labour Recovery Per Asset | 2027-05-05 | 2027-06-13 | 39 days | FY27
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace C32 Engine | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 386 | 90015753 | B1 | 1000269911 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -ENGINE | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Repl Engine Radiator | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 50 | 90011532 | B1 | 1000098057 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -ENGINE-COSYS-RADTR | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Engine Aftercooler | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 6 | 90011533 | B1 | 1000098058 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -ENGINE-INTEX-AFTER | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Drive Shaft | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 2 | 90011540 | B1 | 1000098064 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -FDRSYS-DRSHT | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Differential | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 38 | 90011541 | B1 | 1000098065 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -FDRSYS-DIFFL | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Final Drive LH | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 50 | 90011542 | B1 | 1000098066 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -FDRSYS-FDRVE-FDRLH | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Final Drive RH | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 50 | 90011543 | B1 | 1000098067 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -FDRSYS-FDRVE-FDRRH | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Hydraulic Oil Cooler | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 12 | 90011563 | B1 | 1000098085 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -HYDSYS-HDOCO | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Valve Hoist | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 36 | 90011564 | B1 | 1000098086 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -HYDSYS-HOVLV | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Pump Hoist Lines | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 8 | 90011562 | B1 | 1000098084 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -HYDSYS-HDHLF | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Auto Lube Pump | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 2 | 90011565 | B1 | 1000098087 | 07.04.2027 | 9000 | CCK-MP-SUPP-WC220 -GRSYST-ALBPP | 4300 | 58137 | 5434
777G WC | MCORS | Haul | Mader | WC220 | WC220 Overhaul Airconditioner | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 24 | 90011566 | B2 | 1000269914 | 28.04.2027 | 9000 | CCK-MP-SUPP-WC220 -STRUCT-CABIN-AIRCN | 4300 | 58137 | 18617
777G WC | MCORS | Haul | Mader | WC220 | WC220 Refurbish A Frame | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 36 | 90011568 | B1 | 1000098090 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-CHASS-AFRME | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Tag Link | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 6 | 90011569 | B1 | 1000098091 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-CHASS-TAGLK | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Hub and Spindle LH | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 22 | 90011570 | B1 | 1000098092 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-AXLES-HUBLH | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Hub and Spindle RH | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 22 | 90011571 | B1 | 1000098093 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-AXLES-HUBRH | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Overhaul Water Tank Module | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 1 | 90028969 | B1 | 1000288994 | 18.06.2029 | 36000 | CCK-MP-SUPP-WC220 -STRUCT-WTANK | 4300 | 58137 | 58137
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Cylinder Suspension LHF | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 26 | 90011572 | B1 | 1000098094 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-SUSPN-SCYLF | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Cylinder Suspension RHF | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 44 | 90011573 | B1 | 1000098095 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-SUSPN-SCYRF | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Cylinder Suspension LHR | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 10 | 90011574 | B1 | 1000098096 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-SUSPN-SCYLR | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Cylinder Suspension RHR | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 10 | 90011575 | B1 | 1000098097 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -STRUCT-SUSPN-SCYRR | 4300 | 58137 | 14252
777G WC | MCORS | Haul | Mader | WC220 | WC220 Brake Slack Adjuster Front | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 6 | 90036701 | B1 | 1000368013 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -BRKSYS-SLACK-SLACF | 4300 | 58137 | 58137
777G WC | MCORS | Haul | Mader | WC220 | WC220 Brake Slack Adjuster Rear Left | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 6 | 90036703 | B1 | 1000368014 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -BRKSYS-SLACK-SLARL | 4300 | 58137 | 58137
777G WC | MCORS | Haul | Mader | WC220 | WC220 Brake Slack Adjuster Rear Right | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 6 | 90036703 | B1 | 1000368015 | 28.04.2027 | 18000 | CCK-MP-SUPP-WC220 -BRKSYS-SLACK-SLARR | 4300 | 58137 | 58137
777G WC | MCORS | Haul | Mader | WC220 | WC220 Replace Valve Brake | 2027-05-05 | 2027-06-13 | 39 days | FY27 | 12 | 90011548 | B1 | 1000098072 | 26.02.2027 | 18000 | CCK-MP-SUPP-WC220 -BRKSYS-BRVLV | 4300 | 58137 | 14971
777G WC | MCORS | Haul | Mader | WC220 | Transport & Recommissioning | 2027-06-14 | 2027-07-07 | 23 days | FY27
| MCORS | All |  |  | FY28 - MCORS | 2027-07-01 | 2028-06-30 | 365 days | FY28
| MCORS | Ancillary |  |  | ANCILLARY | 2027-07-01 | 2028-06-30 | 365 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | WD204 - MCORS | 2027-08-07 | 2027-09-15 | 39 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Decommissioning & Transport | 2027-08-07 | 2027-08-12 | 5 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | WD204 - Baseline Scope | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | DHH Transport Chichester (Site-OEM-Site) | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Opex Variation | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Capex Variation | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Additional Baseline Opex Ancillary Fleet | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Additional Baseline Capex Ancillary Fleet | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Minor Hosing Opex | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Major Hosing Price Variances - Capex | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Baseline Harness (Not on strategy) Capex | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Variation Opex - Corrosions/Repairs | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Capex Variation - Cab Overhaul (if applicable) | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | Site Labour Recovery Per Asset | 2027-08-13 | 2027-09-09 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Shaft Universals TC - Trans | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 3 | 90026669 | B1 | 1000268463 | 19.05.2027 | 11000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT01 | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Replace Shaft Universals Front | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 6 | 90026667 | B1 | 1000268469 | 19.05.2027 | 11000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT04 | 6300 | 83628 | 19866
854K | MCORS | Ancillary | TBA | WD204 | WD204 Replace Shaft Universals Rear | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 6 | 90026666 | B1 | 1000268465 | 22.05.2027 | 11000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT02 | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Shaft Trans to Cntr Bearing | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 8 | 90002949 | B3 | 1000268466 | 10.06.2027 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT03 | 6300 | 83628 | 2002
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Operators Seat | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 4 | 90002975 | B2 | 1000228705 | 22.06.2027 | 7000 | CCK-MP-DOZR-WD204 -STRUCT-CABIN-SEATS | 6300 | 83628 | 854
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Final Drive Position 4 | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 58 | 90002954 | B3 | 1000092726 | 09.07.2027 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR04 | 6300 | 83628 | 16224
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Transmission Oil Cooler | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 6 | 90002945 | B3 | 1000116340 | 07.08.2027 | 15000 | CCK-MP-DOZR-WD204 -TRNSYS-TROLC | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Brake Accumulator Front | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 4 | 90002955 | B3 | 1000092727 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -BRKSYS-BACCM-BACCF | 6300 | 83628 | 38735
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Brake Accumulator Rear | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 4 | 90002955 | B3 | 1000092728 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -BRKSYS-BACCM-BACCR | 6300 | 83628 | 38735
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Engine Cat C32 | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 404 | 90015797 | B1 | 1000286621 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -ENGINE | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Radiator Engine Cooling | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 72 | 90002931 | B3 | 1000092711 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -ENGINE-COSYS-RADTR | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Aftercooler Engine | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 12 | 90010216 | B3 | 1000092743 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -ENGINE-INTEX-AFTER | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Oil Cooler Front Axle Lube | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 6 | 90010219 | B3 | 1000092745 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-AXLEC-OILCF | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Final Drive Position 1 | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 58 | 90002954 | B3 | 1000092723 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR01 | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Final Drive Position 2 | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 58 | 90002954 | B3 | 1000092724 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR02 | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Final Drive Position 3 | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 58 | 90002954 | B3 | 1000092725 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR03 | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Cylinder Blade Lift RH | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 12 | 90002966 | B1 | 1000228682 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -HYDSYS-HDCYL-BLCYR | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Cylinder Blade Tilt LH | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 14 | 90002967 | B1 | 1000228683 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -HYDSYS-HDCYL-BTCYL | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Cylinder Blade Tilt RH | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 14 | 90002968 | B1 | 1000228684 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -HYDSYS-HDCYL-BTCYR | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Overhaul Airconditioner | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 48 | 90013087 | B1 | 1000286627 | 22.08.2027 | 11000 | CCK-MP-DOZR-WD204 -STRUCT-CABIN-AIRCN | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Replace Hoses Powertrain System | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 48 | 90013049 | B3 | 1000116339 | 22.08.2027 | 22000 | CCK-MP-DOZR-WD204 -TRNSYS-TRHLF | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Hyd & Steering Oil Cooler | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 24 | 90010218 | B3 | 1000092744 | 04.09.2027 | 22000 | CCK-MP-DOZR-WD204 -HYDSYS-HDOCO | 6300 | 83628 | 15298
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Sepura SCC Microphone | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 0.5 | 90028996 | B1 | 1000289585 | 30.09.2027 | 12 Monthly | CCK-MP-DOZR-WD204 -COMMUN-RADIO | 6300 | 83628 | 83628
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Hyd Motor Fan | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 8 | 90002969 | B3 | 1000092738 | 24.10.2027 | 15000 | CCK-MP-DOZR-WD204 -HYDSYS-HYDMT-HYM01 | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Replace Brake System Hoses | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 48 | 90013050 | B3 | 1000109638 | 25.10.2027 | 15000 | CCK-MP-DOZR-WD204 -BRKSYS-BRHLF | 6300 | 83583 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Pump Brake | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 4 | 90002957 | B3 | 1000092729 | 25.10.2027 | 15000 | CCK-MP-DOZR-WD204 -BRKSYS-BRPMP | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Hyd Motor & Pump Axle Cooling | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 4 | 90002970 | B3 | 1000092739 | 25.10.2027 | 15000 | CCK-MP-DOZR-WD204 -HYDSYS-HYDMT-HYM02 | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Replace Hoses Steering System | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 48 | 90013051 | B3 | 1000109639 | 25.10.2027 | 15000 | CCK-MP-DOZR-WD204 -STRSYS-STHLF | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Replace Hyd Pilot System Hoses | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 24 | 90013052 | B3 | 1000231932 | 25.10.2027 | 15000 | CCK-MP-DOZR-WD204 -HYDSYS-HDHLF-HDHPS | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Hoses Main Hyd-Fan System | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 48 | 90013053 | B3 | 1000231933 | 25.10.2027 | 15000 | CCK-MP-DOZR-WD204 -HYDSYS-HDHLF-HDHMH | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Hyd Pump Implement | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 12 | 90002962 | B3 | 1000092735 | 29.10.2027 | 15000 | CCK-MP-DOZR-WD204 -HYDSYS-HYDPP-HYP01 | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Hyd Pump Steering Main | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 12 | 90002958 | B3 | 1000092730 | 29.10.2027 | 15000 | CCK-MP-DOZR-WD204 -STRSYS-STPMP-STP01 | 6300 | 83628 | 7365
854K | MCORS | Ancillary | TBA | WD204 | WD204 Repl Rear Differential | 2027-08-13 | 2027-09-09 | 27 days | FY28 | 134 | 90002952 | B3 | 1000092721 | 29.03.2028 | 15000 | CCK-MP-DOZR-WD204 -FDRSYS-RRDIF | 6300 | 83628 | 4677
854K | MCORS | Ancillary | TBA | WD204 | Transport & Recommissioning | 2027-09-10 | 2027-09-15 | 5 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 - MCORS | 2027-11-01 | 2027-12-17 | 46 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Decommissioning & Transport | 2027-11-01 | 2027-11-07 | 6 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 - Baseline Scope | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | DHH Transport Chichester (Site-OEM-Site) | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Opex Variation | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Capex Variation | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Additional Baseline Opex Ancillary Fleet | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Additional Baseline Capex Ancillary Fleet | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Minor Hosing Opex | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Major Hosing Price Variances - Capex | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Baseline Harness (Not on strategy) Capex | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Variation Opex - Corrosions/Repairs | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Capex Variation - Cab Overhaul (if applicable) | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | Site Labour Recovery Per Asset | 2027-11-08 | 2027-12-10 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Hydraulic Oil Cooler | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 96 | 90002733 | B2 | 1000138179 | 03.09.2027 | 20000 | CCK-MP-LOAD-WL7103-HYDSYS-HDOCO | 6000 | 72865 | 13547
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Implement Pump LH | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 24 | 90002723 | B2 | 1000138173 | 03.10.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP01 | 6000 | 72865 | 3040
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Implement Pump Centre | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 24 | 90002725 | B2 | 1000138175 | 03.10.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP03 | 6000 | 72865 | 3047
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Centre Bearing Upper Shaft | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 24 | 90002702 | B2 | 1000138152 | 03.10.2027 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-UCTRB | 6000 | 72865 | 3040
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Overhaul Park Brake & Centre Brg | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90002711 | B2 | 1000138193 | 04.10.2027 | 10000 | CCK-MP-LOAD-WL7103-BRKSYS-BRPRK | 6000 | 72865 | 3040
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Implement Pump RH | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 24 | 90002724 | B2 | 1000138174 | 04.10.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP02 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Overhaul Boom | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 96 | 90021334 | B1 | 1000223863 | 14.10.2027 | 40000 | CCK-MP-LOAD-WL7103-STRUCT-CHASS-LIARM | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Steering Cylinder RH | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 28 | 90002722 | B2 | 1000138172 | 26.10.2027 | 12000 | CCK-MP-LOAD-WL7103-STRSYS-STRCY-STCYR | 6000 | 72865 | 4648
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Cyl Bucket LH High Lift | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90017978 | B1 | 1000184467 | 31.10.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-BUCYL | 6000 | 72865 | 2579
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Cyl Bucket RH High Lift | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90017977 | B1 | 1000184468 | 31.10.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-BUCYR | 6000 | 72865 | 2579
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Cyl Lift RH High Lift | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 48 | 90002727 | B2 | 1000138178 | 31.10.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-HCYLR | 6000 | 72865 | 13547
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Engine Midlife complete | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 170 | 90021253 | B1 | 1000222748 | 01.11.2027 | 10000 | CCK-MP-LOAD-WL7103-ENGINE | 6000 | 72865 | 2571
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Overhaul Air Conditioner | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 48 | 90021132 | B1 | 1000222741 | 01.11.2027 | 10000 | CCK-MP-LOAD-WL7103-STRUCT-CABIN-AIRCN | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Input Drive Shaft | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 12 | 90033166 | B1 | 1000333563 | 01.12.2027 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT01 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Rear Output Drive Shaft | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 14 | 90033168 | B1 | 1000333565 | 01.12.2027 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT02 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Center Output Drive Shaft | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 14 | 90033171 | B1 | 1000333567 | 01.12.2027 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT03 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Brake Accumulator Front | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 12 | 90002714 | B2 | 1000138165 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-BRKSYS-BRACC-BACCF | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Brake Accumulator Rear | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 12 | 90002714 | B2 | 1000138194 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-BRKSYS-BRACC-BACCR | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Brake System Hoses | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 48 | 90026921 | B1 | 1000271657 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-BRKSYS-BRHLF-BRKHO | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Steering & Brake Oil Coolers | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 72 | 90002715 | B2 | 1000138203 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-BRKSYS-BROCC | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Wiring Harness | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90010123 | B2 | 1000138191 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-ELCTLV-HARNS | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Engine Radiator | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 102 | 90002682 | B2 | 1000138141 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-ENGINE-COSYS-RADTR | 6300 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Differential Front | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 114 | 90002707 | B2 | 1000138156 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-FDRSYS-FRDIF | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Differential Rear | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 114 | 90002708 | B2 | 1000138157 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-FDRSYS-RRDIF | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Overhaul Rear Axle Trunnion | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 112 | 90002709 | B2 | 1000138158 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-FDRSYS-RRDIF-TRNON | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Cyl Lift LH High Lift | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 48 | 90002727 | B2 | 1000138177 | 02.12.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-HCYLL | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Hydraulic System Hoses | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 96 | 90026922 | B1 | 1000271659 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-HYDHO | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Pilot System Hoses | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 96 | 90009731 | B2 | 1000138188 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-PILHO | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Reseal Hydraulic Tank | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 12 | 90010623 | B2 | 1000138192 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-HYDSYS-HDTNK-HYT01 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Implement Valve LH | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 24 | 90010965 | B2 | 1000138196 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-HYDSYS-HDVLV-HYV01 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Implement Valve RH | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 24 | 90010966 | B2 | 1000138197 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-HYDSYS-HDVLV-HYV02 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Hydraulic Pilot Accumulator | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 4 | 90012174 | B2 | 1000138198 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-HYDSYS-PACCM | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Main Airhoses & Valves | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 18 | 90011137 | B2 | 1000321322 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-PNEUMC-PNHLF | 6000 | 72865 | 72865
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Steering System Hoses | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 96 | 90009732 | B2 | 1000138189 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STHLF-STRHO | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Steering Neutralizer Valves | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 6 | 90002720 | B2 | 1000138185 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STNVS | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Steering Pump LH | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90002716 | B2 | 1000138167 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP01 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Steering Pump RH | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90002717 | B2 | 1000138168 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP02 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Steer Brake Tank Cooler Pump | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 8 | 90002718 | B2 | 1000138169 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP03 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Secondary Steering Pump | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 8 | 90002719 | B2 | 1000138170 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP04 | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Reseal Steering & Brake Tank | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90010963 | B2 | 1000138195 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STTNK | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Pump Drive Gearbox Rear | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 326 | 90002706 | B2 | 1000138155 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-PMPDR-RRPDR | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Transmission Oil Cooler | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 36 | 90002695 | B2 | 1000138145 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-TROLC | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Serv Front Frame Grease Sys | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 24 | 90010326 | B1 | 1000138205 | 02.12.2027 | 20000 | CCK-MP-LOAD-WL7103-GRSYST-FFGHO | 6000 | 72865 | 12069
994H | MCORS | Ancillary | TBA | WL7103 | WL7103 Repl Artic Area Hyd Hosing | 2027-11-08 | 2027-12-10 | 32 days | FY28 | 6 | 90020831 | B1 | 1000321324 | 08.12.2027 | 8 Monthly | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-ARTHO
994H | MCORS | Ancillary | TBA | WL7103 | Transport & Recommissioning | 2027-12-11 | 2027-12-17 | 6 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | WL266 - MCORS | 2027-11-02 | 2027-12-18 | 46 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Decommissioning & Transport | 2027-11-02 | 2027-11-08 | 6 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | WL266 - Baseline Scope | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | DHH Transport Chichester (Site-OEM-Site) | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Opex Variation | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Capex Variation | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Additional Baseline Opex Ancillary Fleet | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Additional Baseline Capex Ancillary Fleet | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Minor Hosing Opex | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Major Hosing Price Variances - Capex | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Baseline Harness (Not on strategy) Capex | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Variation Opex - Corrosions/Repairs | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Capex Variation - Cab Overhaul (if applicable) | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | Site Labour Recovery Per Asset | 2027-11-09 | 2027-12-11 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL266 | WL266 Replace Artic Area Hyd Hosing | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 6 | 90020831 | B1 | 1000220501 | 11.07.2027 | 8 Monthly | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-ARTHO
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Centre Output Drive Shaft | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 14 | 90033171 | B1 | 1000333519 | 22.07.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT03 | 6000 | 74342 | 14189
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Cyl Bucket LH High Lift | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 36 | 90017978 | B1 | 1000131518 | 06.08.2027 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-BUCYL | 6000 | 74342 | 3995
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Cyl Steering LH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 26 | 90002721 | B2 | 1000090617 | 25.08.2027 | 12000 | CCK-MP-LOAD-WL266 -STRSYS-STRCY-STCYL | 6000 | 74342 | 18157
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Cyl Steering RH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 28 | 90002722 | B2 | 1000090618 | 25.08.2027 | 12000 | CCK-MP-LOAD-WL266 -STRSYS-STRCY-STCYR | 6000 | 74342 | 5601
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Pump Implement LH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 24 | 90002723 | B2 | 1000090619 | 30.10.2027 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP01 | 6000 | 74342 | 2546
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Pump Implement RH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 24 | 90002724 | B2 | 1000090620 | 30.10.2027 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP02 | 6000 | 74342 | 2546
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Brake Accumulator Front | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 12 | 90002714 | B2 | 1000090610 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -BRKSYS-BRACC-BACCF | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Brake Accumulator Rear | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 12 | 90002714 | B2 | 1000090611 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -BRKSYS-BRACC-BACCR | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Brake Oil Cooler | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 72 | 90002715 | B2 | 1000116287 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -BRKSYS-BROCC | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Pump Brake | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 12 | 90002712 | B2 | 1000090608 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -BRKSYS-BRPMP-BRP01 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Electrical Harness | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 36 | 90010123 | B2 | 1000090637 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -ELCTLV-HARNS | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Engine Cat 3516B | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 500 | 90021152 | B1 | 1000222611 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -ENGINE | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Radiator Engine Cooling | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 102 | 90002682 | B2 | 1000090585 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -ENGINE-COSYS-RADTR | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Overhaul Engine Prelube | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 10 | 90021219 | B1 | 1000222612 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -ENGINE-LUBSY-PREPP | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Front Differential | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 114 | 90002707 | B2 | 1000090601 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -FDRSYS-FRDIF | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Rear Differential | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 114 | 90002708 | B2 | 1000090602 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -FDRSYS-RRDIF | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Cyl Lift LH High Lift | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 48 | 90002727 | B2 | 1000112685 | 13.11.2027 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-HCYLL | 6000 | 74342 | 1243
994H | MCORS | Ancillary | TBA | WL266 | WL266 Replace Pilot System Hoses | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 96 | 90009731 | B2 | 1000090634 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-PILHO | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Oil Cooler | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 96 | 90002733 | B2 | 1000090623 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -HYDSYS-HDOCO | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Reseal Tank Hyd | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 12 | 90010623 | B2 | 1000090638 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -HYDSYS-HDTNK-HYT01 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Valve Implement Ctrl LH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 24 | 90010965 | B2 | 1000112590 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -HYDSYS-HDVLV-HYV01 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Valve Implement Ctrl RH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 24 | 90010966 | B2 | 1000112597 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -HYDSYS-HDVLV-HYV02 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Replace Steering System Hoses | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 96 | 90009732 | B2 | 1000090635 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -STRSYS-STHLF-STRHO | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Steering Neutralizer Valves | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 6 | 90002720 | B2 | 1000090631 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -STRSYS-STNVS | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Pump Steering LH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 36 | 90002716 | B2 | 1000090613 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP01 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Pump Steering RH | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 36 | 90002717 | B2 | 1000090614 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP02 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Steer & Brake Oil Cooler Pump | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 8 | 90002718 | B2 | 1000090615 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP03 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Steering Hyd Pump Secondary | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 8 | 90002719 | B2 | 1000090616 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP04 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Overhaul Air Conditioner | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 48 | 90021132 | B1 | 1000222609 | 13.11.2027 | 10000 | CCK-MP-LOAD-WL266 -STRUCT-CABIN-AIRCN | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Input Drive Shaft | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 12 | 90033166 | B1 | 1000333515 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT01 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Rear Output Drive Shaft | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 14 | 90033168 | B1 | 1000333517 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT02 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Front Drive Shaft | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 16 | 90033175 | B1 | 1000333521 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT04 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Front Pump Drv Drive Shaft | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 16 | 90033189 | B1 | 1000333525 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT06 | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Gearbox Pump Drive Rear | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 326 | 90002706 | B2 | 1000090600 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-PMPDR-RRPDR | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Transmission Oil Cooler | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 36 | 90002695 | B2 | 1000090589 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-TROLC | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Torque Converter | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 48 | 90002693 | B2 | 1000090586 | 13.11.2027 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-TRQUE | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Pump Implement Centre | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 24 | 90002725 | B2 | 1000090621 | 24.11.2027 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP03 | 6000 | 74342 | 2546
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hyd Pump Brake Cooling | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 8 | 90002713 | B2 | 1000090609 | 25.11.2027 | 10000 | CCK-MP-LOAD-WL266 -BRKSYS-BRPMP-BRP02 | 6000 | 74342 | 16796
994H | MCORS | Ancillary | TBA | WL266 | WL266 Overhaul Park Brake & Centre Brg | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 36 | 90002711 | B2 | 1000090639 | 25.11.2027 | 10000 | CCK-MP-LOAD-WL266 -BRKSYS-BRPRK | 6000 | 74342 | 24646
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Auto Lube Pump | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 6 | 90002737 | B2 | 1000090626 | 25.11.2027 | 10000 | CCK-MP-LOAD-WL266 -GRSYST-ALBPP | 6000 | 74342 | 12308
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Sepura SCC Microphone | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 0.5 | 90028998 | B1 | 1000289601 | 12.12.2027 | 12 Monthly | CCK-MP-LOAD-WL266 -COMMUN-RADIO | 6000 | 74342 | 74342
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Final Drive Position 2 | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 83 | 90002710 | B2 | 1000090605 | 12.01.2028 | 16000 | CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR02 | 6000 | 74342 | 7305
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Operators Seat | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 4 | 90002741 | B2 | 1000090627 | 16.01.2028 | 7000 | CCK-MP-LOAD-WL266 -STRUCT-CABIN-SEATS | 6000 | 74342 | 5199
994H | MCORS | Ancillary | TBA | WL266 | WL266 12 Monthly Hydraulic Tune Up | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 24 | 90015111 | B1 | 1000126199 | 15.02.2028 | 52 Weekly | CCK-MP-LOAD-WL266 -HYDSYS | 6000 | 74342 | 31864
994H | MCORS | Ancillary | TBA | WL266 | WL266 Replace Artic Area Hyd Hosing | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 6 | 90020831 | B1 | 1000220501 | 07.03.2028 | 8 Monthly | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-ARTHO
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Cyl Lift RH High Lift | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 48 | 90002727 | B2 | 1000112686 | 20.03.2028 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-HCYLR | 6000 | 74342 | 1243
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Brake System Hoses | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 48 | 90026921 | B1 | 1000271597 | 24.03.2028 | 20000 | CCK-MP-LOAD-WL266 -BRKSYS-BRHLF-BRKHO | 6000 | 74342 | 30142
994H | MCORS | Ancillary | TBA | WL266 | WL266 Repl Hydraulic System Hoses | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 96 | 90026922 | B1 | 1000271599 | 24.03.2028 | 20000 | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-HYDHO | 6000 | 74342 | 30142
994H | MCORS | Ancillary | TBA | WL266 | WL266 Overhaul Boom | 2027-11-09 | 2027-12-11 | 32 days | FY28 | 96 | 90021334 | B1 | 1000223819 | 24.03.2028 | 40000 | CCK-MP-LOAD-WL266 -STRUCT-CHASS-LIARM | 6000 | 74342 | 74342
994H | MCORS | Ancillary | TBA | WL266 | Transport & Recommissioning | 2027-12-12 | 2027-12-18 | 6 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | WD007 - MCORS | 2028-01-22 | 2028-03-01 | 39 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Decommissioning & Transport | 2028-01-22 | 2028-01-27 | 5 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | WD007 - Baseline Scope | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | DHH Transport Chichester (Site-OEM-Site) | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Opex Variation | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Capex Variation | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Additional Baseline Opex Ancillary Fleet | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Additional Baseline Capex Ancillary Fleet | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Minor Hosing Opex | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Major Hosing Price Variances - Capex | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Baseline Harness (Not on strategy) Capex | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Variation Opex - Corrosions/Repairs | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Capex Variation - Cab Overhaul (if applicable) | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | Site Labour Recovery Per Asset | 2028-01-28 | 2028-02-24 | 27 days | FY28
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Operators Seat | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 4 | 90002975 | B2 | 1000033656 | 11.07.2027 | 7000 | CCK-MP-DOZR-WD007 -STRUCT-CABIN-SEATS | 6300 | 76489 | 892
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Hyd Pump Steer Secondary | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 4 | 90002960 | B3 | 1000033640 | 06.09.2027 | 15000 | CCK-MP-DOZR-WD007 -STRSYS-STPMP-STP03 | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Transmission | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 167 | 90002944 | B3 | 1000033621 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -TRNSYS-TRANS | 6300 | 76513 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Transmission Oil Cooler | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 6 | 90002945 | B3 | 1000033622 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -TRNSYS-TROLC | 6300 | 76513 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Pump Transmission | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 8 | 90002946 | B3 | 1000033623 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -TRNSYS-TRPMP | 6300 | 76513 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Pump Brake | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 4 | 90002957 | B3 | 1000033637 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -BRKSYS-BRPMP | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Replace Brake System Hoses | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 48 | 90013050 | B3 | 1000109652 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -BRKSYS-BRHLF | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Hyd Pump Steering Main | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 12 | 90002958 | B3 | 1000033638 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -STRSYS-STPMP-STP01 | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Pump Str Pilot & Str Cooling | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 4 | 90002959 | B3 | 1000033639 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -STRSYS-STPMP-STP02 | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Replace Hoses Steering System | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 48 | 90013051 | B3 | 1000109653 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -STRSYS-STHLF | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Hyd Pump Implement | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 12 | 90002962 | B3 | 1000033643 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -HYDSYS-HYDPP-HYP01 | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Hyd Pump Cooling Fan | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 8 | 90002964 | B3 | 1000033645 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -HYDSYS-HYDPP-HYP03 | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Hyd Motor Fan | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 8 | 90002969 | B3 | 1000033650 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -HYDSYS-HYDMT-HYM01 | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Hyd Motor & Pump Axle Cooling | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 4 | 90002970 | B3 | 1000033651 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -HYDSYS-HYDMT-HYM02 | 6300 | 76489 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Replace Hyd Pilot System Hoses | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 24 | 90013052 | B3 | 1000231936 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -HYDSYS-HDHLF-HDHPS | 6300 | 76513 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Hoses Main Hyd-Fan System | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 48 | 90013053 | B3 | 1000231937 | 07.09.2027 | 15000 | CCK-MP-DOZR-WD007 -HYDSYS-HDHLF-HDHMH | 6300 | 76513 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Rear Differential | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 134 | 90002952 | B3 | 1000033629 | 17.09.2027 | 15000 | CCK-MP-DOZR-WD007 -FDRSYS-RRDIF | 6300 | 76513 | 8036
854K | MCORS | Ancillary | TBA | WD007 | WD007 Replace Shaft Trans to Rear Diff | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 8 | 90002948 | B3 | 1000268432 | 27.11.2027 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT02 | 6300 | 76513 | 8208
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Final Drive Position 2 | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 58 | 90002954 | B3 | 1000033632 | 28.11.2027 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR02 | 6300 | 76489 | 13800
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Final Drive Position 3 | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 58 | 90002954 | B3 | 1000033633 | 14.12.2027 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR03 | 6300 | 76489 | 13479
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Final Drive Position 4 | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 58 | 90002954 | B3 | 1000033634 | 16.12.2027 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR04 | 6300 | 76489 | 13479
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Engine Cat C32 | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 404 | 90015797 | B1 | 1000286593 | 31.01.2028 | 22000 | CCK-MP-DOZR-WD007 -ENGINE | 6300 | 76513 | 12682
854K | MCORS | Ancillary | TBA | WD007 | WD007 Overhaul Airconditioner | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 48 | 90013087 | B1 | 1000286599 | 31.01.2028 | 11000 | CCK-MP-DOZR-WD007 -STRUCT-CABIN-AIRCN | 6300 | 76489 | 20596
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Brake Accumulator Front | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 4 | 90002955 | B3 | 1000033635 | 19.02.2028 | 22000 | CCK-MP-DOZR-WD007 -BRKSYS-BACCM-BACCF | 6300 | 76489 | 35779
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Brake Accumulator Rear | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 4 | 90002955 | B3 | 1000033636 | 19.02.2028 | 22000 | CCK-MP-DOZR-WD007 -BRKSYS-BACCM-BACCR | 6300 | 76489 | 35779
854K | MCORS | Ancillary | TBA | WD007 | WD007 Repl Sepura SCC Microphone | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 0.5 | 90028996 | B1 | 1000289581 | 23.02.2028 | 12 Monthly | CCK-MP-DOZR-WD007 -COMMUN-RADIO
854K | MCORS | Ancillary | TBA | WD007 | WD007 Replace Hoses Powertrain System | 2028-01-28 | 2028-02-24 | 27 days | FY28 | 48 | 90013049 | B3 | 1000109651 | 16.06.2028 | 22000 | CCK-MP-DOZR-WD007 -TRNSYS-TRHLF
854K | MCORS | Ancillary | TBA | WD007 | Transport & Recommissioning | 2028-02-25 | 2028-03-01 | 5 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | WL260 - MCORS | 2028-02-09 | 2028-03-26 | 46 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Decommissioning & Transport | 2028-02-09 | 2028-02-15 | 6 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | WL260 - Baseline Scope | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | DHH Transport Chichester (Site-OEM-Site) | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Opex Variation | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Capex Variation | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Additional Baseline Opex Ancillary Fleet | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Additional Baseline Capex Ancillary Fleet | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Minor Hosing Opex | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Major Hosing Price Variances - Capex | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Baseline Harness (Not on strategy) Capex | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Variation Opex - Corrosions/Repairs | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Capex Variation - Cab Overhaul (if applicable) | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | Site Labour Recovery Per Asset | 2028-02-16 | 2028-03-19 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Gearbox Pump Drive Front | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 74 | 90002705 | B2 | 1000090229 | 22.08.2027 | 16000 | CCK-MP-LOAD-WL260 -TRNSYS-PMPDR-FRPDR | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Transmission Transfer Case | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 74 | 90017029 | B2 | 1000153214 | 22.08.2027 | 16000 | CCK-MP-LOAD-WL260 -TRNSYS-TRTRF | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Final Drive Position 1 | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 83 | 90002710 | B2 | 1000090234 | 13.09.2027 | 16000 | CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR01 | 6000 | 75558 | 9452
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Pump Brake Cooling | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 8 | 90002713 | B2 | 1000090239 | 15.09.2027 | 10000 | CCK-MP-LOAD-WL260 -BRKSYS-BRPMP-BRP02 | 6000 | 75566 | 3411
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Pump Implement LH | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 24 | 90002723 | B2 | 1000090249 | 15.09.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP01 | 6000 | 75558 | 12904
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Centre Bearing Upper Shaft | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 24 | 90002702 | B2 | 1000090226 | 15.09.2027 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-UCTRB | 6000 | 75558 | 12904
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Auto Lube Pump | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 6 | 90002737 | B2 | 1000090256 | 16.09.2027 | 10000 | CCK-MP-LOAD-WL260 -GRSYST-ALBPP | 6000 | 75553 | 3406
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Cyl Bucket LH Ext High Lift | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 38 | 90015438 | B2 | 1000131506 | 16.09.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-BUCYL | 6000 | 75558 | 3411
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Cyl Lift LH Ext High Lift | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 54 | 90002728 | B2 | 1000112695 | 16.09.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-HCYLL | 6000 | 75558 | 814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Cyl Lift RH Ext High Lift | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 54 | 90002728 | B2 | 1000112664 | 16.09.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-HCYLR | 6000 | 75558 | 3411
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Pump Implement RH | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 24 | 90002724 | B2 | 1000090250 | 16.09.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP02 | 6000 | 75558 | 3411
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Pump Implement Centre | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 24 | 90002725 | B2 | 1000090251 | 16.09.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP03 | 6000 | 75558 | 3411
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Pump Pilot & Cooling | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 12 | 90002726 | B2 | 1000090252 | 17.09.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP04 | 6000 | 75542 | 3411
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Input Drive Shaft | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 12 | 90033166 | B1 | 1000333479 | 16.10.2027 | 20000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT01 | 6000 | 75558 | 12904
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Centre Output Drive Shaft | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 14 | 90033171 | B1 | 1000333483 | 16.10.2027 | 20000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT03 | 6000 | 75558 | 12904
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Cyl Steering LH | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 26 | 90002721 | B2 | 1000090247 | 21.10.2027 | 12000 | CCK-MP-LOAD-WL260 -STRSYS-STRCY-STCYL | 6000 | 75558 | 4819
994H | MCORS | Ancillary | TBA | WL260 | WL260 Replace Artic Area Hyd Hosing | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 6 | 90020831 | B1 | 1000220497 | 28.12.2027 | 8 Monthly | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-ARTHO
994H | MCORS | Ancillary | TBA | WL260 | WL260 12 Monthly Hydraulic Tune Up | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 24 | 90015111 | B1 | 1000126196 | 14.01.2028 | 52 Weekly | CCK-MP-LOAD-WL260 -HYDSYS | 6000 | 75558 | 75558
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Pump Brake | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 12 | 90002712 | B2 | 1000090238 | 14.02.2028 | 20000 | CCK-MP-LOAD-WL260 -BRKSYS-BRPMP-BRP01 | 6000 | 75566 | 10899
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Transmission System Hoses | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 96 | 90026923 | B2 | 1000271584 | 26.03.2028 | 16000 | CCK-MP-LOAD-WL260 -TRNSYS-TRHLF-TRNHO | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Brake Accumulator Front | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 12 | 90002714 | B2 | 1000090240 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -BRKSYS-BRACC-BACCF | 6000 | 75566 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Brake Accumulator Rear | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 12 | 90002714 | B2 | 1000090241 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -BRKSYS-BRACC-BACCR | 6000 | 75566 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Electrical Harness | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 36 | 90010123 | B2 | 1000090267 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -ELCTLV-HARNS | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Engine Cat 3516B | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 500 | 90021152 | B1 | 1000222501 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -ENGINE | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Overhaul Engine Prelube | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 10 | 90021219 | B1 | 1000222502 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -ENGINE-LUBSY-PREPP | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Front Differential | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 114 | 90002707 | B2 | 1000090231 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -FDRSYS-FRDIF | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Rear Differential | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 114 | 90002708 | B2 | 1000090232 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -FDRSYS-RRDIF | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Overhaul Rear Axle Trunnion | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 112 | 90002709 | B2 | 1000090233 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -FDRSYS-RRDIF-TRNON | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Replace Pilot System Hoses | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 96 | 90009731 | B1 | 1000090264 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-PILHO | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Reseal Tank Hyd | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 12 | 90010623 | B2 | 1000090268 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -HYDSYS-HDTNK-HYT01 | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Valve Implement Ctrl LH | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 24 | 90010965 | B2 | 1000112587 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -HYDSYS-HDVLV-HYV01 | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Hyd Valve Implement Ctrl RH | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 24 | 90010966 | B2 | 1000112594 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -HYDSYS-HDVLV-HYV02 | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Replace Steering System Hoses | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 96 | 90009732 | B2 | 1000090265 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STHLF-STRHO | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Steering Neutralizer Valves | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 6 | 90002720 | B2 | 1000090261 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STNVS | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Steer & Brake Oil Cooler Pump | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 8 | 90002718 | B2 | 1000090245 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP03 | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Overhaul Air Conditioner | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 48 | 90021132 | B1 | 1000222499 | 21.04.2028 | 10000 | CCK-MP-LOAD-WL260 -STRUCT-CABIN-AIRCN | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Rear Output Drive Shaft | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 14 | 90033168 | B1 | 1000333481 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT02 | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Transmission Oil Cooler | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 36 | 90002695 | B2 | 1000090219 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -TRNSYS-TROLC | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Transmission Charge Pump | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 12 | 90002694 | B2 | 1000090218 | 21.04.2028 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-TRPMP | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Torque Converter | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 48 | 90002693 | B2 | 1000090216 | 21.04.2028 | 20000 | CCK-MP-LOAD-WL260 -TRNSYS-TRQUE | 6000 | 75558 | 9814
994H | MCORS | Ancillary | TBA | WL260 | WL260 Repl Operators Seat | 2028-02-16 | 2028-03-19 | 32 days | FY28 | 4 | 90002741 | B2 | 1000090257 | 16.05.2028 | 7000 | CCK-MP-LOAD-WL260 -STRUCT-CABIN-SEATS | 6000 | 75558 | 3411
994H | MCORS | Ancillary | TBA | WL260 | Transport & Recommissioning | 2028-03-20 | 2028-03-26 | 6 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 - MCORS | 2028-05-04 | 2028-06-19 | 46 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Decommissioning & Transport | 2028-05-04 | 2028-05-10 | 6 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 - Baseline Scope | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | DHH Transport Chichester (Site-OEM-Site) | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Opex Variation | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Capex Variation | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Additional Baseline Opex Ancillary Fleet | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Additional Baseline Capex Ancillary Fleet | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Minor Hosing Opex | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Major Hosing Price Variances - Capex | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Baseline Harness (Not on strategy) Capex | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Variation Opex - Corrosions/Repairs | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Capex Variation - Cab Overhaul (if applicable) | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | Site Labour Recovery Per Asset | 2028-05-11 | 2028-06-12 | 32 days | FY28
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Cyl Bucket Tilt LH | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 56 | 90016387 | B1 | 1000257047 | 14.03.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-BUCYL | 6100 | 25829 | 2515
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Cyl Bucket Tilt RH | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 56 | 90016388 | B1 | 1000257048 | 14.03.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-BUCYR | 6100 | 25829 | 2515
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Cyl Lift RH Lift | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 62 | 90016386 | B1 | 1000257046 | 21.03.2028 | 10000 | CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-HCYLR | 6100 | 25829 | 10405
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Brake Park Assembly | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 36 | 90016364 | B1 | 1000257024 | 03.04.2028 | 12000 | CCK-MP-LOAD-WL7162-BRKSYS-BRPRK | 6100 | 25829 | 2179
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pump Cooling Fan | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 24 | 90016382 | B1 | 1000257042 | 03.04.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYFPP | 6100 | 25829 | 2268
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pump Implement LH | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 24 | 90016376 | B1 | 1000257036 | 03.04.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP01 | 6100 | 25829 | 2179
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pump Implement RH | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 24 | 90016377 | B1 | 1000257037 | 03.04.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP02 | 6100 | 25829 | 2179
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pump Pilot & Axl Cooling | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016380 | B1 | 1000257040 | 03.04.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP05 | 6100 | 25829 | 2179
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pump AOC Fan & Imp Cool | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016381 | B1 | 1000257041 | 03.04.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP06 | 6100 | 25829 | 2192
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Uni T/C to Input Gears | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 20 | 90016338 | B1 | 1000256986 | 24.04.2028 | 12000 | CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT01 | 6100 | 25829 | 2179
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Uni Trans to Rear Diff | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 20 | 90016340 | B1 | 1000256988 | 24.04.2028 | 12000 | CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT02 | 6100 | 25829 | 9393
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Uni Trsfr GBox to Brake | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 20 | 90016342 | B1 | 1000256990 | 24.04.2028 | 12000 | CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT03 | 6100 | 25829 | 2088
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Uni Park Brake to Front Diff | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 20 | 90016344 | B1 | 1000256992 | 24.04.2028 | 12000 | CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT04 | 6100 | 25829 | 2179
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Uni Rear PD - Fr PD | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 20 | 90016346 | B1 | 1000256994 | 24.04.2028 | 12000 | CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT05 | 6100 | 25829 | 2192
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Gearbox Pump Drive Rear | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 386 | 90016348 | B1 | 1000256996 | 24.04.2028 | 18000 | CCK-MP-LOAD-WL7162-TRNSYS-PMPDR-RRPDR | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Brake Accumulator Front | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016361 | B1 | 1000257020 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-BRKSYS-BRACC-BACCF | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Brake Accumulator Rear | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016361 | B1 | 1000257021 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-BRKSYS-BRACC-BACCR | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Brake System Hoses | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 48 | 90016366 | B1 | 1000257025 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-BRKSYS-BRHLF-BRKHO | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pump Brake | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016363 | B1 | 1000257023 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-BRKSYS-BRPMP-BRP01 | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hydraulic System Hoses | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 96 | 90016393 | B1 | 1000257053 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-HYDHO | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Pilot System hoses | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 96 | 90016394 | B1 | 1000257054 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-PILHO | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Pump AOC Rear | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016379 | B1 | 1000257039 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP04 | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Steering System Hoses | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 96 | 90016375 | B1 | 1000257035 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-STRSYS-STHLF-STRHO | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Steering STIC Pilot Valve | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016372 | B1 | 1000257031 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-STRSYS-STIPV | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Steering Neutralizer Valves | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 6 | 90016367 | B1 | 1000257026 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-STRSYS-STNVS | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pump Steering | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 24 | 90016368 | B1 | 1000257027 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-STRSYS-STPMP-STP01 | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Steer & Brake Oil Cool Pump | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 8 | 90016369 | B1 | 1000257028 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-STRSYS-STPMP-STP02 | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Steering Hyd Pump Secondary | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 8 | 90016370 | B1 | 1000257029 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-STRSYS-STPMP-STP03 | 6100 | 25829 | 2443
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Steering Valve | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 16 | 90016371 | B1 | 1000257030 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-STRSYS-STVLV | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Service Minor Air Conditioner | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 24 | 90019465 | B1 | 1000256938 | 16.05.2028 | 6000 | CCK-MP-LOAD-WL7162-STRUCT-CABIN-AIRCN | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Gearbox Pump Drive Front | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 74 | 90016347 | B1 | 1000256995 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-TRNSYS-PMPDR-FRPDR | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Transmission | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 80 | 90016349 | B1 | 1000256998 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-TRNSYS-TRANS | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Replace Transmission System Hoses | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 96 | 90016350 | B1 | 1000256999 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-TRNSYS-TRHLF-TRNHO | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Transmission Charge Pump | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 12 | 90016352 | B1 | 1000257001 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-TRNSYS-TRPMP | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Torque Converter | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 50 | 90016353 | B1 | 1000257002 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-TRNSYS-TRQUE | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Transmission Transfer Case | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 72 | 90019528 | B1 | 1000289363 | 16.05.2028 | 18000 | CCK-MP-LOAD-WL7162-TRNSYS-TRTRF | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Hyd Pilot Accumulator | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 4 | 90016392 | B1 | 1000257052 | 07.07.2028 | 12000 | CCK-MP-LOAD-WL7162-HYDSYS-PACCM | 6100 | 25829 | 25829
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Operators Seat | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 4 | 90016397 | B1 | 1000257056 | 12.07.2028 | 7000 | CCK-MP-LOAD-WL7162-STRUCT-CABIN-SEATS | 6100 | 25829 | 2515
994K | MCORS | Ancillary | TBA | WL7162 | WL7162 Repl Cooler Module | 2028-05-11 | 2028-06-12 | 32 days | FY28 | 68 | 90034406 | B1 | 1000350364 | 16.07.2028 | 24000 | CCK-MP-LOAD-WL7162-ENGINE-COSYS-RADTR | 6100 | 25829 | 7473
994K | MCORS | Ancillary | TBA | WL7162 | Transport & Recommissioning | 2028-06-13 | 2028-06-19 | 6 days | FY28
| MCORS | Haul |  |  | HAUL | 2027-07-01 | 2028-06-30 | 365 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 - MCORS | 2027-08-02 | 2027-10-12 | 71 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Decommissioning & Transport | 2027-08-02 | 2027-08-09 | 7 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 - Baseline Scope | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | DHH Transport Chichester (Site-OEM-Site) | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Opex Variation | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Capex Variation | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Additional Baseline Opex Truck Fleet | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Additional Baseline Capex Truck Fleet | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Minor Hosing Opex | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Baseline Harness (Not on strategy) Capex | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Variation Opex - Corrosions/Repairs | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | MCORS Watercart Module Refurbishment CAPEX | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | Site Labour Recovery Per Asset | 2027-08-10 | 2027-09-18 | 39 days | FY28
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl C32 Engine | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 386 | 90015753 | B1 | 1000136132 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-ENGINE | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Engine Radiator | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 50 | 90011532 | B1 | 1000136147 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-ENGINE-COSYS-RADTR | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Engine Aftercooler | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 6 | 90011533 | B1 | 1000136148 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-ENGINE-INTEX-AFTER | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Differential | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 38 | 90011541 | B1 | 1000136155 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-FDRSYS-DIFFL | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Drive Shaft | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 2 | 90011540 | B1 | 1000136154 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-FDRSYS-DRSHT | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Pump & Motor Sec Str | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 6 | 90011558 | B1 | 1000136168 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STEMG-SESPP | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Steering Hoses & Lines | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 8 | 90011560 | B1 | 1000136170 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STHLF | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Steering HMU | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 12 | 90011553 | B1 | 1000136163 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STHMU | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Steering Linkages | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 24 | 90011557 | B1 | 1000136167 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STLTR | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Pump Steering | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 6 | 90011552 | B1 | 1000136162 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STPMP | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Cylinder Steering LH | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 10 | 90011555 | B1 | 1000136165 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STRCY-STCYL | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Cylinder Steering RH | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 12 | 90011556 | B1 | 1000136166 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STRCY-STCYR | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Valve Steering | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 12 | 90011554 | B1 | 1000136164 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRSYS-STVLV | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Overhaul Airconditioner | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 24 | 90011566 | B2 | 1000229149 | 09.07.2027 | 9000 | CCK-MP-SUPP-WC2501-STRUCT-CABIN-AIRCN | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Refurbish A Frame | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 36 | 90011568 | B1 | 1000136178 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRUCT-CHASS-AFRME | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Tag Link | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 6 | 90011569 | B1 | 1000136179 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRUCT-CHASS-TAGLK | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Cylinder Suspension LHF | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 26 | 90011572 | B1 | 1000136182 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRUCT-SUSPN-SCYLF | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Cylinder Suspension RHF | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 44 | 90011573 | B1 | 1000136183 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-STRUCT-SUSPN-SCYRF | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Trans & TCon Charge Pump | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 4 | 90011536 | B1 | 1000136152 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-TRNSYS-TRPMP-TCCPP | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Torque Converter | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 26 | 90011534 | B1 | 1000136149 | 09.07.2027 | 18000 | CCK-MP-SUPP-WC2501-TRNSYS-TRQUE | 2000 | 56945 | 15935
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Overhaul Water Tank Module | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 1 | 90028969 | B1 | 1000288998 | 04.08.2027 | 36000 | CCK-MP-SUPP-WC2501-STRUCT-WTANK | 2000 | 56945 | 56945
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Brake Slack Adjuster Front | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 6 | 90036701 | B1 | 1000368019 | 10.08.2027 | 18000 | CCK-MP-SUPP-WC2501-BRKSYS-SLACK-SLACF | 2000 | 56765 | 56765
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Brake Slack Adjuster LHR | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 6 | 90036703 | B1 | 1000368040 | 10.08.2027 | 18000 | CCK-MP-SUPP-WC2501-BRKSYS-SLACK-SLARL | 2000 | 56765 | 56765
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Brake Slack Adjuster RHR | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 6 | 90036703 | B1 | 1000368041 | 10.08.2027 | 18000 | CCK-MP-SUPP-WC2501-BRKSYS-SLACK-SLARR | 2000 | 56765 | 56765
777G WC | MCORS | Haul | TBA | WC2501 | WC2501 Repl Transmission | 2027-08-10 | 2027-09-18 | 39 days | FY28 | 50 | 90011535 | B1 | 1000136150 | 25.09.2027 | 18000 | CCK-MP-SUPP-WC2501-TRNSYS-TRANS | 2000 | 56945 | 15507
777G WC | MCORS | Haul | TBA | WC2501 | Transport & Recommissioning | 2027-09-19 | 2027-10-12 | 23 days | FY28
793F | MCORS | Haul | TBA | DT138 | DT138 - MCORS | 2028-01-10 | 2028-02-23 | 44 days | FY28
793F | MCORS | Haul | TBA | DT138 | Decommissioning & Transport | 2028-01-10 | 2028-01-16 | 6 days | FY28
793F | MCORS | Haul | TBA | DT138 | DT138 - Baseline scope | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | DHH Transport Chichester (Site-OEM-Site) | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Opex Variation | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Capex Variation | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Additional Baseline Opex Truck Fleet | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Additional Baseline Capex Truck Fleet | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Capex Variation - Steer Box (if applicable) | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Minor Hosing Opex | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Baseline Harness (Not on strategy) Capex | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Variation Opex - Corrosions/Repairs | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | Site Labour Recovery Per Asset | 2028-01-17 | 2028-02-15 | 29 days | FY28
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Operators Seat | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 6 | 90002395 | B1 | 1000025646 | 29.08.2027 | 15000 | CCK-MP-HAUL-DT138 -STRUCT-CABIN-SEATS | 7400 | 82982 | 7134
793F | MCORS | Haul | TBA | DT138 | DT138 Service Air Conditioner 12M | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 18 | 90018230 | B1 | 1000174171 | 14.10.2027 | 12 Monthly | CCK-MP-HAUL-DT138 -STRUCT-CABIN-AIRCN | 7400 | 82982 | 35790
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Tyre Sense Battery | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 2 | 90017022 | B1 | 1000153154 | 16.10.2027 | 24 Monthly | CCK-MP-HAUL-DT138 -MANGMT-TYRSN
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Auto Lube Pump | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 3 | 90002391 | B1 | 1000285783 | 13.12.2027 | 8000 | CCK-MP-HAUL-DT138 -GRSYST-ALBPP | 7400 | 82982 | 5976
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Transmission | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 39 | 90026996 | B2 | 1000272329 | 03.01.2028 | 18000 | CCK-MP-HAUL-DT138 -TRNSYS-TRANS | 7400 | 82982 | 6438
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Engine Cat C175-16 | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 137 | 90015881 | B1 | 1000155985 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -ENGINE | 7400 | 82982 | 35790
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Radiator Engine Cooling | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 62 | 90031072 | B1 | 1000307510 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -ENGINE-COSYS-RADTR | 7400 | 82982 | 35790
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Pump Drive | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 39 | 90002365 | B1 | 1000025607 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -ENGINE-PMPDR | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Torque Converter | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 53 | 90002369 | B1 | 1000025612 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -TRNSYS-TRQUE | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Wheel End LH | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 58.5 | 90002374 | B1 | 1000025617 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -FDRSYS-FDRVE-FDRLH | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Wheel End RH | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 58.5 | 90007352 | B1 | 1000025618 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -FDRSYS-FDRVE-FDRRH | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Motor Lube Axle Rear & Hoses | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 8 | 90026943 | B1 | 1000272003 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -FDRSYS-AXLEC-HYM01 | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl AOC Fan Motor Rear | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 6 | 90002376 | B1 | 1000025620 | 10.01.2028 | 12000 | CCK-MP-HAUL-DT138 -FDRSYS-AXLEC-HYM02 | 7400 | 82982 | 431
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Axle Lube Hyd Pump | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 4 | 90010102 | B1 | 1000083242 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -FDRSYS-AXLEC-HYPUM | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Overhaul Accumulator Brake LHF | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 11 | 90002378 | B1 | 1000025621 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BACCM-FRLFT | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Overhaul Accumulator Brake RHF | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 11 | 90002378 | B1 | 1000025622 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BACCM-FRRGT | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Overhaul Accumulator Brake Rear | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 11 | 90002378 | B1 | 1000025623 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BACCM-BACCR | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Pump Brake Cooling | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 17 | 90002379 | B1 | 1000025624 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-HYFPP | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Overhaul Valve Control Brake | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 20 | 90002380 | B2 | 1000025625 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BRVLV | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Brake Oil Cooler Front | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 13 | 90010109 | B1 | 1000083249 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BROCO-BROCF | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Brake Oil Cooler Rear | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 13 | 90010108 | B1 | 1000083248 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BROCO-BROCR | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Motor Brake Oil Cooling | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 3 | 90002381 | B1 | 1000025626 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BROCO-HYMO1 | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Hyd Pump Steering Main & Fan | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 17 | 90002383 | B1 | 1000025629 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -STRSYS-STPMP | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Ovhl Accumulator Steering Front | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 12 | 90002386 | B1 | 1000025633 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -STRSYS-STACC-SACCF | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Ovhl Accumulator Steering Middle | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 12 | 90002386 | B1 | 1000025634 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -STRSYS-STACC-SACCM | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Pump Hoist & Brake | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 15 | 90002388 | B1 | 1000025638 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -HYDSYS-HOPMP | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Rear Axle Linkages | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 113 | 90002396 | B1 | 1000025647 | 10.01.2028 | 24000 | CCK-MP-HAUL-DT138 -STRUCT-CHASS-AXLIK | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Spider Trans Driveshaft | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 12 | 90017211 | B1 | 1000154962 | 18.02.2028 | 6000 | CCK-MP-HAUL-DT138 -FDRSYS-DRSHT-UNVSL | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Differential | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 66 | 90014504 | B1 | 1000025616 | 27.02.2028 | 18000 | CCK-MP-HAUL-DT138 -FDRSYS-DIFFL | 7400 | 82982 | 6438
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Front Wheel Bearings LH | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 44 | 90017284 | B1 | 1000157148 | 11.03.2028 | 16000 | CCK-MP-HAUL-DT138 -STRUCT-AXLES-FWBLH | 7400 | 82982 | 5976
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Spiders Pump Drive Shaft | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 4 | 90002366 | B1 | 1000025608 | 21.03.2028 | 18000 | CCK-MP-HAUL-DT138 -ENGINE-PMPDR-DRSHT | 7400 | 82982 | 6028
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Transmission Oil Cooler | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 12 | 90010097 | B1 | 1000083240 | 21.03.2028 | 18000 | CCK-MP-HAUL-DT138 -TRNSYS-TROLC | 7400 | 82982 | 5976
793F | MCORS | Haul | TBA | DT138 | DT138 Repl Steering Linkages | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 28 | 90028568 | B1 | 1000317621 | 21.03.2028 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STLTR | 7400 | 82982 | 13427
793F | MCORS | Haul | TBA | DT138 | DT138 Replace Trans TCon System Hoses | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 20 | 90010099 | B1 | 1000090121 | 21.03.2028 | 18000 | CCK-MP-HAUL-DT138 -TRNSYS-TRANS-TRNHO | 7400 | 82982 | 23396
793F | MCORS | Haul | TBA | DT138 | DT138 Replace Hoses Differential System | 2028-01-17 | 2028-02-15 | 29 days | FY28 | 5 | 90010101 | B2 | 1000090122 | 21.03.2028 | 18000 | CCK-MP-HAUL-DT138 -FDRSYS-DIFFL-DIFHO | 7400 | 82982 | 23314
793F | MCORS | Haul | TBA | DT138 | Transport & Recommissioning | 2028-02-16 | 2028-02-23 | 7 days | FY28
| MCORS | All |  |  | FY29 - MCORS | 2028-07-01 | 2029-06-30 | 364 days | FY29
| MCORS | Ancillary |  |  | ANCILLARY | 2028-07-01 | 2029-06-30 | 364 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | WL017 - MCORS | 2029-01-08 | 2029-02-23 | 46 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Decommissioning & Transport | 2029-01-08 | 2029-01-14 | 6 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | WL017 - Baseline Scope | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | DHH Transport Chichester (Site-OEM-Site) | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Opex Variation | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Capex Variation | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Additional Baseline Opex Ancillary Fleet | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Additional Baseline Capex Ancillary Fleet | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Major Hosing Price Variances - Capex | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Variation Opex - Corrosions/Repairs | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Capex Variation - Cab Overhaul (if applicable) | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | Site Labour Recovery Per Asset | 2029-01-15 | 2029-02-16 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Rear Differential | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 126 | 90002768 | B2 | 1000030629 | 18.08.2028 | 24000 | CCK-MP-LOAD-WL017 -FDRSYS-RRDIF | 3100 | 56923 | 17424
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Front Differential | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 126 | 90002767 | B2 | 1000030628 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -FDRSYS-FRDIF | 3100 | 56923 | 17413
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Final Drive Position 1 | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 56 | 90002771 | B2 | 1000030633 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -FDRSYS-FDRVE-FDR01 | 3100 | 56923 | 17413
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Final Drive Position 3 | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 56 | 90002771 | B2 | 1000030635 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -FDRSYS-FDRVE-FDR03 | 3100 | 56923 | 17424
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Final Drive Position 4 | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 56 | 90002771 | B2 | 1000030636 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -FDRSYS-FDRVE-FDR04 | 3100 | 56923 | 17424
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Service Brake LHF | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 48 | 90002772 | B2 | 1000030637 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBLF | 3100 | 56923 | 17413
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Service Brake RHF | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 48 | 90002772 | B2 | 1000030638 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBRF | 3100 | 56923 | 17413
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Service Brake LHR | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 48 | 90002772 | B2 | 1000030639 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBLR | 3100 | 56923 | 17424
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Service Brake RHR | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 48 | 90002772 | B2 | 1000030640 | 19.08.2028 | 24000 | CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBRR | 3100 | 56923 | 17424
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Pump Transmission | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002760 | B2 | 1000030621 | 21.09.2028 | 8000 | CCK-MP-LOAD-WL017 -TRNSYS-TRPMP | 3100 | 56923 | 1114
993K | MCORS | Ancillary | TBA | WL017 | WL017 Engine Midlife Complete | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 80 | 90015824 | B1 | 1000291902 | 12.11.2028 | 8000 | CCK-MP-LOAD-WL017 -ENGINE | 3100 | 56923 | 689
993K | MCORS | Ancillary | TBA | WL017 | WL017 Replace High Risk Hoses | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90021799 | B2 | 1000291905 | 12.11.2028 | 8000 | CCK-MP-LOAD-WL017 -ENGINE | 3100 | 56923 | 689
993K | MCORS | Ancillary | TBA | WL017 | WL017 Wash Engine Pre Cleaners | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 2 | 90017388 | B1 | 1000291759 | 12.11.2028 | 8000 | CCK-MP-LOAD-WL017 -ENGINE-INTEX-AIRFL
993K | MCORS | Ancillary | TBA | WL017 | WL017 Air Conditioning Overhaul | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 48 | 90017479 | B1 | 1000291904 | 12.11.2028 | 8000 | CCK-MP-LOAD-WL017 -STRUCT-CABIN-AIRCN | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Bucket Cyl Tilt LH | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 28 | 90002788 | B2 | 1000052490 | 17.12.2028 | 12000 | CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-BUCYL | 3100 | 56923 | 7268
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Radiator Engine Cooling | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 72 | 90002751 | B2 | 1000030615 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -ENGINE-COSYS-RADTR | 3700 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Fan Cooling System | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002753 | B2 | 1000030617 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -ENGINE-COSYS-COFAN | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Transmission | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 167 | 90002758 | B2 | 1000030619 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -TRNSYS-TRANS | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Torque Converter | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 144 | 90002759 | B2 | 1000030620 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -TRNSYS-TRQUE | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Transmission Oil Cooler | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 6 | 90002761 | B2 | 1000030622 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -TRNSYS-TROLC | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Drive Shaft TCon to Trans | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 4 | 90002762 | B2 | 1000030623 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT01 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Drive Shaft Trans to Rr Diff | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002763 | B2 | 1000030624 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT02 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Shaft Ctr Bearing to Fr Diff | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002765 | B2 | 1000030626 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT04 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Drive Shaft Centre Bearing | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002766 | B2 | 1000030627 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-CTRBR | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Replace Brake Hoses | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 72 | 90010151 | B1 | 1000081963 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -BRKSYS-BRHLF | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Pumps Steering Centre | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002776 | B2 | 1000030642 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -STRSYS-STPMP | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Valve Steering | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 24 | 90002778 | B2 | 1000087691 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -STRSYS-STVLV | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Steering Hyd Oil Cooler | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 36 | 90002779 | B2 | 1000030644 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -STRSYS-STOCO | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Replace Steering Hoses | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 72 | 90010150 | B1 | 1000081964 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -STRSYS-STHLF | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Replace Pump Pilot & Axle Cooling | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 4 | 90002783 | B2 | 1000030648 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP02 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Hyd Pump Steering & Fan | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 24 | 90002784 | B2 | 1000030649 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP03 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Hyd Motor Fan | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002790 | B2 | 1000030650 | 17.02.2029 | 8000 | CCK-MP-LOAD-WL017 -HYDSYS-HYDMT-HYM01 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Hyd Motor Axle Cooler Front | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 2 | 90002791 | B2 | 1000030651 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HYDMT-HYM02 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Hyd Motor Axle Cooler Rear | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 2 | 90002791 | B2 | 1000030652 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HYDMT-HYM03 | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Overhaul Auto Lubrication System | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 96 | 90002794 | B2 | 1000030654 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -GRSYST | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Replace Powertrain Hoses | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 72 | 90010149 | B1 | 1000081960 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -TRNSYS-TRHLF | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Replace Pilot Hoses | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 72 | 90010153 | B1 | 1000081969 | 17.02.2029 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HDHLF-PILHO | 3100 | 56923 | 7866
993K | MCORS | Ancillary | TBA | WL017 | WL017 Repl Shaft Trans to Ctr Bearing | 2029-01-15 | 2029-02-16 | 32 days | FY29 | 8 | 90002764 | B2 | 1000030625 | 01.05.2029 | 12000 | CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT03 | 3100 | 56923 | 3247
993K | MCORS | Ancillary | TBA | WL017 | Transport & Recommissioning | 2029-02-17 | 2029-02-23 | 6 days | FY29
| MCORS | Haul |  |  | HAUL | 2028-07-01 | 2029-06-30 | 364 days | FY29
793F | MCORS | Haul | TBA | DT221 | DT221 - MCORS | 2028-08-14 | 2028-09-27 | 44 days | FY29
793F | MCORS | Haul | TBA | DT221 | Decommissioning & Transport | 2028-08-14 | 2028-08-20 | 6 days | FY29
793F | MCORS | Haul | TBA | DT221 | DT221 - Baseline scope | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | DHH Transport Chichester (Site-OEM-Site) | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Opex Variation | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Capex Variation | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Additional Baseline Opex Truck Fleet | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Additional Baseline Capex Truck Fleet | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Capex Variation - Steer Box (if applicable) | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Minor Hosing Opex | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Baseline Harness (Not on strategy) Capex | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Variation Opex - Corrosions/Repairs | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | Site Labour Recovery Per Asset | 2028-08-21 | 2028-09-19 | 29 days | FY29
793F | MCORS | Haul | TBA | DT221 | DT221 Service Air Conditioner 12M | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 18 | 90018230 | B1 | 1000174188 | 04.04.2028 | 12 Monthly | CCK-MP-HAUL-DT221 -STRUCT-CABIN-AIRCN | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Tyre Sense Battery | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 2 | 90017022 | B1 | 1000153171 | 21.04.2028 | 24 Monthly | CCK-MP-HAUL-DT221 -MANGMT-TYRSN
793F | MCORS | Haul | TBA | DT221 | DT221 Overhaul Accumulator Brake Rear | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 11 | 90002378 | B1 | 1000127971 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BACCM-BACCR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Overhaul Accumulator Brake LHF | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 11 | 90002378 | B1 | 1000127969 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BACCM-FRLFT | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Replace Brake System Hoses | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 90 | 90010129 | B1 | 1000128010 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BRHLF-BRHOS | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Brake Cooling System Hoses | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 60 | 90010130 | B2 | 1000128011 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BRHLF-CBRHO | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Brake Oil Cooler Front | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 13 | 90010109 | B1 | 1000128009 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BROCO-BROCF | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Brake Oil Cooler Rear | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 13 | 90010108 | B1 | 1000128008 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BROCO-BROCR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Motor Brake Oil Cooling | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 3 | 90002381 | B1 | 1000127974 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BROCO-HYMO1 | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Overhaul Valve Control Brake | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 20 | 90002380 | B2 | 1000127973 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BRVLV | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Pump Brake Cooling | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 17 | 90002379 | B1 | 1000127972 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-HYFPP | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Engine Cat C175-16 | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 137 | 90015881 | B1 | 1000156081 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -ENGINE | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Radiator Engine Cooling | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 62 | 90031072 | B1 | 1000307552 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -ENGINE-COSYS-RADTR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Pump Drive | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 39 | 90002365 | B1 | 1000127919 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -ENGINE-PMPDR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Motor Lube Axle Rear & Hoses | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 8 | 90026943 | B1 | 1000272037 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYM01 | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl AOC Fan Motor Rear | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 6 | 90002376 | B1 | 1000127968 | 09.06.2028 | 12000 | CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYM02 | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Axle Lube Hyd Pump | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 4 | 90010102 | B1 | 1000128002 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYPUM | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Drive Line Axle LH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 4 | 90014919 | B2 | 1000128020 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -FDRSYS-DRLAX-AXLLH | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Drive Line Axle RH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 4 | 90014943 | B2 | 1000128021 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -FDRSYS-DRLAX-AXLRH | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Wheel End LH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 58.5 | 90030708 | B1 | 1000127965 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -FDRSYS-FDRVE-FDRLH | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Wheel End RH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 54.5 | 90017425 | B1 | 1000127966 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -FDRSYS-FDRVE-FDRRH | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Replace Hoses Hoist System | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 40 | 90010105 | B2 | 1000128004 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -HYDSYS-HDHLF-HSTHO | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Pump Hoist & Brake | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 15 | 90002388 | B1 | 1000127985 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -HYDSYS-HOPMP | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Ovhl Accumulator Steering Front | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 12 | 90002386 | B1 | 1000127981 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRSYS-STACC-SACCF | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Ovhl Accumulator Steering Middle | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 12 | 90002386 | B1 | 1000127982 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRSYS-STACC-SACCM | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Ovhl Accumulator Steering Rear | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 12 | 90002386 | B1 | 1000127983 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRSYS-STACC-SACCR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Steering HMU | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 8 | 90002384 | B1 | 1000127978 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRSYS-STHMU | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Hyd Pump Steering Main & Fan | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 17 | 90002383 | B1 | 1000127977 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRSYS-STPMP | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Wheel Group Front LH XLF | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 54 | 90018999 | B1 | 1000157183 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRUCT-AXLES-HUBLH | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Wheel Group Front RH XLF | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 54 | 90018999 | B1 | 1000157271 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRUCT-AXLES-HUBRH | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Rear Axle Linkages | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 113 | 90002396 | B1 | 1000127988 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -STRUCT-CHASS-AXLIK | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Torque Converter | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 53 | 90002369 | B1 | 1000127961 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT221 -TRNSYS-TRQUE | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Auto Lube Pump | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 3 | 90002391 | B1 | 1000285800 | 14.06.2028 | 8000 | CCK-MP-HAUL-DT221 -GRSYST-ALBPP | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Steering Linkages | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 28 | 90028568 | B1 | 1000317655 | 31.07.2028 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STLTR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Replace Hoses Differential System | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 5 | 90010101 | B4 | 1000127999 | 13.09.2028 | 18000 | CCK-MP-HAUL-DT221 -FDRSYS-DIFFL-DIFHO | 7400 | 57237 | 20442
793F | MCORS | Haul | TBA | DT221 | DT221 Replace Trans TCon System Hoses | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 20 | 90010099 | B2 | 1000127997 | 13.09.2028 | 18000 | CCK-MP-HAUL-DT221 -TRNSYS-TRANS-TRNHO | 7400 | 57237 | 20442
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Spiders Pump Drive Shaft | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 4 | 90002366 | B1 | 1000127960 | 24.09.2028 | 18000 | CCK-MP-HAUL-DT221 -ENGINE-PMPDR-DRSHT | 7400 | 57237 | 2222
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Cyl Steering LH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 20 | 90002385 | B1 | 1000127979 | 13.11.2028 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STRCY-STCYL | 7400 | 57237 | 13199
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Cyl Steering RH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 20 | 90002385 | B2 | 1000127980 | 13.11.2028 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STRCY-STCYR | 7400 | 57237 | 13199
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Drive Shaft Transmission | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 16 | 90017195 | B1 | 1000154997 | 07.12.2028 | 18000 | CCK-MP-HAUL-DT221 -FDRSYS-DRSHT | 7400 | 57237 | 17825
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Cyl Hoist LH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 33 | 90015130 | B1 | 1000128875 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT221 -HYDSYS-HOCYL-HCYLL | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Cyl Hoist RH | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 33 | 90015131 | B1 | 1000128876 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT221 -HYDSYS-HOCYL-HCYLR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Cyl Suspension LHR | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 39 | 90002409 | B1 | 1000127992 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT221 -STRUCT-SUSPN-SCYLR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Cyl Suspension RHF | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 84 | 90002408 | B2 | 1000127995 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT221 -STRUCT-SUSPN-SCYRF | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Cyl Suspension RHR | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 39 | 90002409 | B2 | 1000127993 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT221 -STRUCT-SUSPN-SCYRR | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Differential | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 66 | 90014504 | B1 | 1000127964 | 13.03.2029 | 18000 | CCK-MP-HAUL-DT221 -FDRSYS-DIFFL | 7400 | 57237 | 16760
793F | MCORS | Haul | TBA | DT221 | DT221 Replace Steering System Hoses | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 106 | 90010133 | B2 | 1000128014 | 01.04.2029 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STHLF-STRHO | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | DT221 Repl Steering Hyd Oil Cooler | 2028-08-21 | 2028-09-19 | 29 days | FY29 | 9 | 90012866 | B2 | 1000128018 | 01.04.2029 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STOCO | 7400 | 57237 | 10386
793F | MCORS | Haul | TBA | DT221 | Transport & Recommissioning | 2028-09-20 | 2028-09-27 | 7 days | FY29
793F | MCORS | Haul | TBA | DT222 | DT222 - MCORS | 2029-01-15 | 2029-02-28 | 44 days | FY29
793F | MCORS | Haul | TBA | DT222 | Decommissioning & Transport | 2029-01-15 | 2029-01-21 | 6 days | FY29
793F | MCORS | Haul | TBA | DT222 | DT222 - Baseline scope | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | DHH Transport Chichester (Site-OEM-Site) | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Opex Variation | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Capex Variation | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Additional Baseline Opex Truck Fleet | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Additional Baseline Capex Truck Fleet | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Capex Variation - Steer Box (if applicable) | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Minor Hosing Opex | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Baseline Harness (Not on strategy) Capex | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Variation Opex - Corrosions/Repairs | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | Site Labour Recovery Per Asset | 2029-01-22 | 2029-02-20 | 29 days | FY29
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Differential | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 66 | 90014504 | B1 | 1000128033 | 22.06.2028 | 18000 | CCK-MP-HAUL-DT222 -FDRSYS-DIFFL | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Replace Hoses Differential System | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 5 | 90010101 | B4 | 1000128068 | 22.06.2028 | 18000 | CCK-MP-HAUL-DT222 -FDRSYS-DIFFL-DIFHO | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Transmission | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 39 | 90026996 | B1 | 1000272365 | 22.06.2028 | 18000 | CCK-MP-HAUL-DT222 -TRNSYS-TRANS | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Replace Trans TCon System Hoses | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 20 | 90010099 | B2 | 1000128066 | 22.06.2028 | 18000 | CCK-MP-HAUL-DT222 -TRNSYS-TRANS-TRNHO | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Transmission Oil Cooler | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 12 | 90010097 | B1 | 1000128069 | 22.06.2028 | 18000 | CCK-MP-HAUL-DT222 -TRNSYS-TROLC | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Wheel End RH | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 54.5 | 90017425 | B1 | 1000128035 | 10.08.2028 | 24000 | CCK-MP-HAUL-DT222 -FDRSYS-FDRVE-FDRRH | 7400 | 55735 | 9011
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Brake Slack Adjuster Front | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 4 | 90002382 | B1 | 1000128044 | 28.09.2028 | 20000 | CCK-MP-HAUL-DT222 -BRKSYS-SLACK-SLACF | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Brake Slack Adjuster Rear | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 4 | 90002382 | B1 | 1000128045 | 28.09.2028 | 20000 | CCK-MP-HAUL-DT222 -BRKSYS-SLACK-SLACR | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Steering Linkages | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 28 | 90028568 | B1 | 1000317657 | 30.09.2028 | 15000 | CCK-MP-HAUL-DT222 -STRSYS-STLTR | 7400 | 55735 | 28978
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Cyl Steering LH | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 20 | 90002385 | B1 | 1000128048 | 01.01.2029 | 15000 | CCK-MP-HAUL-DT222 -STRSYS-STRCY-STCYL | 7400 | 55735 | 12092
793F | MCORS | Haul | TBA | DT222 | DT222 Service Air Conditioner 12M | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 18 | 90018230 | B1 | 1000174189 | 10.01.2029 | 12 Monthly | CCK-MP-HAUL-DT222 -STRUCT-CABIN-AIRCN | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Overhaul Accumulator Brake Rear | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 11 | 90002378 | B1 | 1000128040 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BACCM-BACCR | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Overhaul Accumulator Brake LHF | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 11 | 90002378 | B1 | 1000128038 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BACCM-FRLFT | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Overhaul Accumulator Brake RHF | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 11 | 90002378 | B1 | 1000128039 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BACCM-FRRGT | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Replace Brake System Hoses | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 90 | 90010129 | B1 | 1000128079 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BRHLF-BRHOS | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Brake Cooling System Hoses | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 60 | 90010130 | B2 | 1000128080 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BRHLF-CBRHO | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Brake Oil Cooler Front | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 13 | 90010109 | B1 | 1000128078 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BROCO-BROCF | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Brake Oil Cooler Rear | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 13 | 90010108 | B1 | 1000128077 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BROCO-BROCR | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Motor Brake Oil Cooling | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 3 | 90002381 | B1 | 1000128043 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BROCO-HYMO1 | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Overhaul Valve Control Brake | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 20 | 90002380 | B2 | 1000128042 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-BRVLV | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Pump Brake Cooling | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 17 | 90002379 | B1 | 1000128041 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -BRKSYS-HYFPP | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Engine Cat C175-16 | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 137 | 90015881 | B1 | 1000156087 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -ENGINE | 7400 | 55735 | 3987
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Radiator Engine Cooling | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 62 | 90031072 | B1 | 1000307554 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -ENGINE-COSYS-RADTR | 7400 | 55735 | 3987
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Pump Drive | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 39 | 90002365 | B1 | 1000128028 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -ENGINE-PMPDR | 7400 | 55735 | 3987
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Motor Lube Axle Rear & Hoses | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 8 | 90026943 | B1 | 1000272039 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYM01 | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl AOC Fan Motor Rear | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 6 | 90002376 | B1 | 1000128037 | 14.04.2029 | 12000 | CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYM02 | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Axle Lube Hyd Pump | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 4 | 90010102 | B1 | 1000128071 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYPUM | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Drive Line Axle LH | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 4 | 90014919 | B2 | 1000128089 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -FDRSYS-DRLAX-AXLLH | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Drive Line Axle RH | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 4 | 90014943 | B2 | 1000128090 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -FDRSYS-DRLAX-AXLRH | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Auto Lube Pump | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 3 | 90002391 | B1 | 1000285801 | 14.04.2029 | 8000 | CCK-MP-HAUL-DT222 -GRSYST-ALBPP | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Replace Hoses Hoist System | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 40 | 90010105 | B2 | 1000128073 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -HYDSYS-HDHLF-HSTHO | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Ovhl Accumulator Steering Front | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 12 | 90002386 | B1 | 1000128050 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -STRSYS-STACC-SACCF | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Ovhl Accumulator Steering Middle | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 12 | 90002386 | B1 | 1000128051 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -STRSYS-STACC-SACCM | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Ovhl Accumulator Steering Rear | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 12 | 90002386 | B1 | 1000128052 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -STRSYS-STACC-SACCR | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Steering HMU | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 8 | 90002384 | B1 | 1000128047 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -STRSYS-STHMU | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Hyd Pump Steering Main & Fan | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 17 | 90002383 | B1 | 1000128046 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -STRSYS-STPMP | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Wheel Group Front LH XLF | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 54 | 90018999 | B1 | 1000157185 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -STRUCT-AXLES-HUBLH | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Rear Axle Linkages | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 113 | 90002396 | B1 | 1000128057 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -STRUCT-CHASS-AXLIK | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Torque Converter | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 53 | 90002369 | B1 | 1000128030 | 14.04.2029 | 24000 | CCK-MP-HAUL-DT222 -TRNSYS-TRQUE | 7400 | 55735 | 4006
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Drive Shaft Transmission | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 16 | 90017195 | B1 | 1000154999 | 20.04.2029 | 18000 | CCK-MP-HAUL-DT222 -FDRSYS-DRSHT | 7400 | 55735 | 15829
793F | MCORS | Haul | TBA | DT222 | DT222 Repl Operators Seat | 2029-01-22 | 2029-02-20 | 29 days | FY29 | 6 | 90002395 | B1 | 1000128056 | 11.05.2029 | 15000 | CCK-MP-HAUL-DT222 -STRUCT-CABIN-SEATS | 7400 | 55735 | 9457
793F | MCORS | Haul | TBA | DT222 | Transport & Recommissioning | 2029-02-21 | 2029-02-28 | 7 days | FY29
793F | MCORS | Haul | TBA | DT223 | DT223 - MCORS | 2029-02-19 | 2029-04-04 | 44 days | FY29
793F | MCORS | Haul | TBA | DT223 | Decommissioning & Transport | 2029-02-19 | 2029-02-25 | 6 days | FY29
793F | MCORS | Haul | TBA | DT223 | DT223 - Baseline scope | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | DHH Transport Chichester (Site-OEM-Site) | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Opex Variation | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Capex Variation | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Additional Baseline Opex Truck Fleet | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Additional Baseline Capex Truck Fleet | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Capex Variation - Steer Box (if applicable) | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Minor Hosing Opex | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Baseline Harness (Not on strategy) Capex | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Variation Opex - Corrosions/Repairs | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | Site Labour Recovery Per Asset | 2029-02-26 | 2029-03-27 | 29 days | FY29
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Spiders Pump Drive Shaft | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 4 | 90002366 | B1 | 1000128098 | 15.07.2028 | 18000 | CCK-MP-HAUL-DT223 -ENGINE-PMPDR-DRSHT | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Differential | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 66 | 90014504 | B1 | 1000128102 | 15.07.2028 | 18000 | CCK-MP-HAUL-DT223 -FDRSYS-DIFFL | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Replace Hoses Differential System | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 5 | 90010101 | B4 | 1000128137 | 15.07.2028 | 18000 | CCK-MP-HAUL-DT223 -FDRSYS-DIFFL-DIFHO | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Transmission | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 39 | 90026996 | B1 | 1000272367 | 15.07.2028 | 18000 | CCK-MP-HAUL-DT223 -TRNSYS-TRANS | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl AOC Fan Motor Rear | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 6 | 90002376 | B1 | 1000128106 | 03.09.2028 | 12000 | CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYM02 | 7400 | 54920 | 19069
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Drive Shaft Transmission | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 16 | 90017195 | B1 | 1000155001 | 29.09.2028 | 18000 | CCK-MP-HAUL-DT223 -FDRSYS-DRSHT | 7400 | 54920 | 19882
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Steering Linkages | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 28 | 90028568 | B1 | 1000317659 | 04.10.2028 | 15000 | CCK-MP-HAUL-DT223 -STRSYS-STLTR | 7400 | 54920 | 12085
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Brake Slack Adjuster Front | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 4 | 90002382 | B1 | 1000128113 | 22.10.2028 | 20000 | CCK-MP-HAUL-DT223 -BRKSYS-SLACK-SLACF | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Brake Slack Adjuster Rear | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 4 | 90002382 | B1 | 1000128114 | 22.10.2028 | 20000 | CCK-MP-HAUL-DT223 -BRKSYS-SLACK-SLACR | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Wheel End LH | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 58.5 | 90030708 | B1 | 1000128103 | 29.12.2028 | 24000 | CCK-MP-HAUL-DT223 -FDRSYS-FDRVE-FDRLH | 7400 | 54920 | 6323
793F | MCORS | Haul | TBA | DT223 | DT223 Service Air Conditioner 12M | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 18 | 90018230 | B1 | 1000174190 | 06.02.2029 | 12 Monthly | CCK-MP-HAUL-DT223 -STRUCT-CABIN-AIRCN | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Transmisson Calibration | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 8 | 90029836 | B1 | 1000298742 | 22.02.2029 | 4500 | CCK-MP-HAUL-DT223 -TRNSYS-TRANS | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Motor Lube Axle Rear & Hoses | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 8 | 90026943 | B1 | 1000272041 | 01.03.2029 | 24000 | CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYM01 | 7400 | 54920 | 29074
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Cyl Steering LH | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 20 | 90002385 | B1 | 1000128117 | 05.03.2029 | 15000 | CCK-MP-HAUL-DT223 -STRSYS-STRCY-STCYL | 7400 | 54920 | 10976
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Cyl Steering RH | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 20 | 90002385 | B2 | 1000128118 | 05.03.2029 | 15000 | CCK-MP-HAUL-DT223 -STRSYS-STRCY-STCYR | 7400 | 54920 | 10976
793F | MCORS | Haul | TBA | DT223 | DT223 Overhaul Accumulator Brake Rear | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 11 | 90002378 | B1 | 1000128109 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BACCM-BACCR | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Overhaul Accumulator Brake LHF | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 11 | 90002378 | B1 | 1000128107 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BACCM-FRLFT | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Overhaul Accumulator Brake RHF | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 11 | 90002378 | B1 | 1000128108 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BACCM-FRRGT | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Replace Brake System Hoses | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 90 | 90010129 | B1 | 1000128148 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BRHLF-BRHOS | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Brake Cooling System Hoses | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 60 | 90010130 | B2 | 1000128149 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BRHLF-CBRHO | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Brake Oil Cooler Front | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 13 | 90010109 | B1 | 1000128147 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BROCO-BROCF | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Brake Oil Cooler Rear | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 13 | 90010108 | B1 | 1000128146 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BROCO-BROCR | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Motor Brake Oil Cooling | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 3 | 90002381 | B1 | 1000128112 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BROCO-HYMO1 | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Overhaul Valve Control Brake | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 20 | 90002380 | B2 | 1000128111 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-BRVLV | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Pump Brake Cooling | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 17 | 90002379 | B1 | 1000128110 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -BRKSYS-HYFPP | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Engine Cat C175-16 | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 137 | 90015881 | B1 | 1000156093 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -ENGINE | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Radiator Engine Cooling | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 62 | 90031072 | B1 | 1000307556 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -ENGINE-COSYS-RADTR | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Pump Drive | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 39 | 90002365 | B1 | 1000128097 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -ENGINE-PMPDR | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Axle Lube Hyd Pump | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 4 | 90010102 | B1 | 1000128140 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYPUM | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Drive Line Axle LH | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 4 | 90014919 | B2 | 1000128158 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -FDRSYS-DRLAX-AXLLH | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Drive Line Axle RH | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 4 | 90014943 | B2 | 1000128159 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -FDRSYS-DRLAX-AXLRH | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Auto Lube Pump | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 3 | 90002391 | B1 | 1000285802 | 07.05.2029 | 8000 | CCK-MP-HAUL-DT223 -GRSYST-ALBPP | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Replace Hoses Hoist System | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 40 | 90010105 | B2 | 1000128142 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -HYDSYS-HDHLF-HSTHO | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Pump Hoist & Brake | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 15 | 90002388 | B1 | 1000128123 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -HYDSYS-HOPMP | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Ovhl Accumulator Steering Front | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 12 | 90002386 | B1 | 1000128119 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRSYS-STACC-SACCF | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Ovhl Accumulator Steering Middle | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 12 | 90002386 | B1 | 1000128120 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRSYS-STACC-SACCM | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Ovhl Accumulator Steering Rear | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 12 | 90002386 | B1 | 1000128121 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRSYS-STACC-SACCR | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Steering HMU | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 8 | 90002384 | B1 | 1000128116 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRSYS-STHMU | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Hyd Pump Steering Main & Fan | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 17 | 90002383 | B1 | 1000128115 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRSYS-STPMP | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Wheel Group Front LH XLF | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 54 | 90018999 | B1 | 1000157187 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRUCT-AXLES-HUBLH | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Wheel Group Front RH XLF | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 54 | 90018999 | B1 | 1000157275 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRUCT-AXLES-HUBRH | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Rear Axle Linkages | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 113 | 90002396 | B1 | 1000128126 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -STRUCT-CHASS-AXLIK | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Torque Converter | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 53 | 90002369 | B1 | 1000128099 | 07.05.2029 | 24000 | CCK-MP-HAUL-DT223 -TRNSYS-TRQUE | 7400 | 54920 | 3706
793F | MCORS | Haul | TBA | DT223 | DT223 Repl Wheel End RH | 2029-02-26 | 2029-03-27 | 29 days | FY29 | 54.5 | 90017425 | B1 | 1000128104 | 01.07.2029 | 24000 | CCK-MP-HAUL-DT223 -FDRSYS-FDRVE-FDRRH | 7400 | 54920 | 2595
793F | MCORS | Haul | TBA | DT223 | Transport & Recommissioning | 2029-03-28 | 2029-04-04 | 7 days | FY29
| Onsite Shut | All | Fortescue |  | ONSITE SHUTDOWNS |  |  |  | FY27
| Onsite Shut | All | Fortescue |  | FY27 - ONSITE SHUTDOWNS | 2026-07-01 | 2027-06-30 | 8736 hrs | FY27
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 - BOTH ENGINES & MAJOR COMPONENTS | 2026-07-23 | 2026-08-04 | 290 hrs | FY27
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Auto Lube Pump | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 6 | 90027592 | B1 | 1000296999 | 08.07.2026 | 6000 | CCK-MP-EXCV-EX7125-GRSYST-ALBPP | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic Oil Replacement | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90016793 | B1 | 1000296988 | 09.07.2026 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic System Tune Up | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 24 | 90017865 | B1 | 1000296998 | 05.07.2026 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cyl Boom LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 138 | 90027497 | B1 | 1000296943 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BMCYL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cyl Boom RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 138 | 90027497 | B1 | 1000296944 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BMCYR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Boom Arch Hoses | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 24 | 90027558 | B1 | 1000296966 | 21.07.2026 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-BMARH | 6900 | 18844 | 12306
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Boom Stick Bucket Cyl Hoses | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 136 | 90027560 | B1 | 1000296967 | 13.10.2026 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-HBSBC | 6900 | 18844 | 10809
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Boom & MCV Hoses | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 136 | 90032593 | B1 | 1000325063 | 13.10.2026 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-HBSBC | 6900 | 18844 | 10809
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Pump to Rotor Hose | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 48 | 90027567 | B1 | 1000296972 | 21.07.2026 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-MPRCH | 6900 | 18844 | 12306
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl PTO Cooling Hoses | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90027569 | B1 | 1000296974 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-PTOCL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Servo Hose Bulkhead to MCV | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 16 | 90027574 | B1 | 1000296978 | 21.07.2026 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SHMCV | 6900 | 18844 | 12306
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Swing Circuit Hoses | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 16 | 90027576 | B1 | 1000296980 | 20.12.2026 | 9000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SWCRT | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Fan Hyd Cool Front | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90027504 | B1 | 1000296955 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-FMCHF | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Fan Hyd Cool Rear | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90027504 | B1 | 1000296956 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-FMCHR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Fan Engine Cool LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90027494 | B1 | 1000296937 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-HECPL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Fan Engine Cool RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90027494 | B1 | 1000296938 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-HECPR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Drive Gearbox LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 116 | 90027489 | B1 | 1000296929 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-PPDRL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Drive Gearbox RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 116 | 90027489 | B1 | 1000296930 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-PPDRR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Engine Cat C32 LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 244 | 90027533 | B1 | 1000296914 | 21.06.2026 | 18000 | CCK-MP-EXCV-EX7125-LHENGN | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Radiator LH Engine Cooling | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90027552 | B1 | 1000296918 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-LHENGN-COSYS-RADTR | 6500 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl LH Aftercooler | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 24 | 90023361 | B1 | 1000309282 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-LHENGN-INTEX-AFTER | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Minestar Harness | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 43.5 | 90031708 | B1 | 1000369998 | 20.06.2026 | 4000 | CCK-MP-EXCV-EX7125-MANGMT-UMMMC | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Engine Cat C32 RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 244 | 90027534 | B1 | 1000296919 | 21.06.2026 | 18000 | CCK-MP-EXCV-EX7125-RHENGN | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Radiator RH Engine Cooling | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90027553 | B1 | 1000296923 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-RHENGN-COSYS-RADTR | 6500 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl RH Aftercooler | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 24 | 90023360 | B1 | 1000309283 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-RHENGN-INTEX-AFTER | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Wiper Blades | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 1 | 90027557 | B1 | 1000296994 | 04.09.2026 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Annual Air Con Service LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 13 | 90027615 | B1 | 1000297023 | 25.07.2026 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN-AIRCL
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Annual Air Con Service RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 13 | 90027615 | B1 | 1000296993 | 26.07.2026 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN-AIRCR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Operators Seat | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 2 | 90027613 | B1 | 1000296964 | 23.09.2026 | 10000 | CCK-MP-EXCV-EX7125-STRUCT-CABIN-SEATS | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Track Tensioner RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 72 | 90027527 | B1 | 1000296991 | 20.06.2026 | 18000 | CCK-MP-EXCV-EX7125-STRUCT-TKFRR-TENSR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Gearbox Swing LHR | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 82 | 90027580 | B1 | 1000296926 | 11.10.2026 | 20000 | CCK-MP-EXCV-EX7125-SWGSYS-SWBOX-SGBLR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Gearbox Swing RHF | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 82 | 90027580 | B1 | 1000296927 | 11.10.2026 | 20000 | CCK-MP-EXCV-EX7125-SWGSYS-SWBOX-SGBRF | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Gearbox Swing RHR | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 82 | 90027580 | B1 | 1000296928 | 11.10.2026 | 20000 | CCK-MP-EXCV-EX7125-SWGSYS-SWBOX-SGBRR | 6900 | 18844 | 18844
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 - ENGINE & MAJOR COMPONENTS | 2026-07-23 | 2026-08-04 | 290 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Engine Cat C175-16 | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 137 | 90015881 | B1 | 1000155901 | 08.07.2026 | 24000 | CCK-MP-HAUL-DT088 -ENGINE | 7400 | 89037 | 50219
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Torque Converter | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 53 | 90002369 | B1 | 1000024155 | 17.06.2026 | 24000 | CCK-MP-HAUL-DT088 -TRNSYS-TRQUE | 7400 | 89037 | 24979
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Motor Lube Axle Hoses | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 4 | 90026944 | B1 | 1000271956 | 24.03.2026 | 12000 | CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM01 | 7400 | 89037 | 14711
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl AOC Fan Motor Rear | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 6 | 90002376 | B1 | 1000024163 | 24.03.2026 | 12000 | CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM02 | 7400 | 89037 | 14711
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Steering Linkages | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 28 | 90028568 | B1 | 1000317593 | 24.04.2026 | 15000 | CCK-MP-HAUL-DT088 -STRSYS-STLTR | 7400 | 89037 | 25027
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Cyl Hoist LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 33 | 90015130 | B1 | 1000128547 | 19.12.2026 | 28000 | CCK-MP-HAUL-DT088 -HYDSYS-HOCYL-HCYLL | 7400 | 89037 | 24979
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Cyl Hoist RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 33 | 90015131 | B1 | 1000128548 | 19.12.2026 | 28000 | CCK-MP-HAUL-DT088 -HYDSYS-HOCYL-HCYLR | 7400 | 89037 | 24979
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Service Air Conditioner 12M | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 18 | 90018230 | B1 | 1000174116 | 24.08.2026 | 12 Monthly | CCK-MP-HAUL-DT088 -STRUCT-CABIN-AIRCN | 7400 | 89037 | 14711
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Replace Hoses Hoist System | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 40 | 90010105 | B1 | 1000082921 | 05.03.2027 | 24000 | CCK-MP-HAUL-DT088 -HYDSYS-HDHLF-HSTHO | 7400 | 89037 | 50219
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Brake Cooling System Hoses | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 60 | 90010130 | B1 | 1000082928 | 14.06.2026 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BRHLF-CBRHO | 7400 | 89037 | 25051
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Steering Hyd Oil Cooler | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 9 | 90012866 | B2 | 1000107019 | 19.08.2026 | 15000 | CCK-MP-HAUL-DT088 -STRSYS-STOCO | 7400 | 89037 | 14711
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Drive Line Axle LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 4 | 90014919 | B1 | 1000124559 | 18.06.2026 | 24000 | CCK-MP-HAUL-DT088 -FDRSYS-DRLAX-AXLLH | 7400 | 89037 | 24979
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Drive Line Axle RH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 4 | 90014943 | B1 | 1000124561 | 18.06.2026 | 24000 | CCK-MP-HAUL-DT088 -FDRSYS-DRLAX-AXLRH | 7400 | 89037 | 24979
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Front Wheel Bearings LH | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 44 | 90017284 | B1 | 1000157118 | 29.09.2026 | 16000 | CCK-MP-HAUL-DT088 -STRUCT-AXLES-FWBLH | 7400 | 89037 | 14711
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Transmission Oil Cooler | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 12 | 90010097 | B1 | 1000082917 | 06.01.2027 | 18000 | CCK-MP-HAUL-DT088 -TRNSYS-TROLC | 7400 | 89037 | 14711
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Differential | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 66 | 90014504 | B1 | 1000024159 | 19.09.2026 | 18000 | CCK-MP-HAUL-DT088 -FDRSYS-DIFFL | 7400 | 89037 | 17080
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Replace Hoses Differential System | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 5 | 90010101 | B1 | 1000090074 | 15.09.2026 | 18000 | CCK-MP-HAUL-DT088 -FDRSYS-DIFFL-DIFHO | 7400 | 89037 | 36530
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Pump Brake Cooling | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 17 | 90002379 | B1 | 1000024167 | 28.02.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-HYFPP | 7400 | 89037 | 19390
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Brake Slack Adjuster Front | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 4 | 90002382 | B1 | 1000024170 | 02.04.2027 | 20000 | CCK-MP-HAUL-DT088 -BRKSYS-SLACK-SLACF | 7400 | 89037 | 14711
793F | Onsite Shut | Haul | Fortescue | DT088 | DT088 Repl Brake Slack Adjuster Rear | 2026-07-23 | 2026-08-04 | 290 hrs | FY27 | 4 | 90002382 | B1 | 1000024171 | 02.04.2027 | 20000 | CCK-MP-HAUL-DT088 -BRKSYS-SLACK-SLACR | 7400 | 89037 | 14711
994H | Onsite Shut | Ancillary | Fortescue | WL260 | WL260 - ARTIC OVERHAUL & COMPONENTS | 2026-07-27 | 2026-08-04 | 204 hrs | FY27
994H | Onsite Shut | Ancillary | Fortescue | WL260 | WL260 Articulation Overhaul | 2026-07-27 | 2026-08-04 | 204 hrs | FY27 | 360 | 90032991 | B1 | 1000329970 | 05.03.2026 | 16000 | CCK-MP-LOAD-WL260 -STRUCT-CHASS-ARTIC | 6000 | 75558 | 18081
994H | Onsite Shut | Ancillary | Fortescue | WL260 | WL260 Repl Sepura SCC Microphone | 2026-07-27 | 2026-08-04 | 204 hrs | FY27 | 0.5 | 90028998 | B1 | 1000289598 | 23.07.2026 | 12 Monthly | CCK-MP-LOAD-WL260 -COMMUN-RADIO | 6000 | 75558 | 75558
994H | Onsite Shut | Ancillary | Fortescue | WL260 | WL260 Replace Artic Area Hyd Hosing | 2026-07-27 | 2026-08-04 | 204 hrs | FY27 | 6 | 90020831 | B1 | 1000220497 | 04.09.2026 | 8 Monthly | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL260 | WL260 Engine Midlife complete | 2026-07-27 | 2026-08-04 | 204 hrs | FY27 | 170 | 90021253 | B1 | 1000222508 | 22.08.2026 | 10000 | CCK-MP-LOAD-WL260 -ENGINE | 6000 | 75558 | 9814
994H | Onsite Shut | Ancillary | Fortescue | WL260 | WL260 Overhaul Air Conditioner | 2026-07-27 | 2026-08-04 | 204 hrs | FY27 | 48 | 90021132 | B1 | 1000222499 | 22.08.2026 | 10000 | CCK-MP-LOAD-WL260 -STRUCT-CABIN-AIRCN | 6000 | 75558 | 9814
994H | Onsite Shut | Ancillary | Fortescue | WL260 | WL260 Repl Rear Output Drive Shaft Unis | 2026-07-27 | 2026-08-04 | 204 hrs | FY27 | 8 | 90033167 | B1 | 1000333482 | 22.08.2026 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT02 | 6000 | 75558 | 9814
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 - POWER PACK MODULE & TRACK ASSEMBLIES | 2026-08-10 | 2026-08-20 | 255 hrs | FY27
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Power Pack Module | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 172 | 90030914 | B1 | 1000307004 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Grease Tank Level Valve | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 2 | 90015003 | B2 | 1000306963 | 12.11.2026 | 12 Monthly | CCK-MP-EXCV-EX7136-GRSYST-AUTLU-GRTNK | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Grease Block & Injectors | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 84 | 90030749 | B1 | 1000306959 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-GRSYST-GRINJ | 7200 | 19274 | 6872
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 12M Hydraulic Service & Repairs | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 30 | 90014448 | B2 | 1000306961 | 31.12.2026 | 12 Monthly | CCK-MP-EXCV-EX7136-HYDSYS | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Accumulator Track Hyd LH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 3 | 90030729 | B1 | 1000306942 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDACC-HACCL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Accumulator Track Hyd RH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 3 | 90030729 | B1 | 1000306943 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDACC-HACCR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Bucket RH Lift | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 54 | 90030726 | B1 | 1000306991 | 29.05.2026 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-BUCYR | 7200 | 19274 | 11264
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Ladder Raise Cyl | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 24 | 90030750 | B1 | 1000307003 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-LACYL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Bucket Cyl | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 54 | 90030738 | B1 | 1000306946 | 04.01.2027 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HBKCL | 7200 | 19274 | 6848
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Boom Cyl | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 72 | 90030735 | B1 | 1000306944 | 04.01.2027 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HBMCL | 7200 | 19274 | 6872
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Stick Cyl | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 48 | 90030737 | B1 | 1000306945 | 15.12.2026 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HSTCL | 7200 | 19274 | 7384
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Swing Front | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 24 | 90030727 | B1 | 1000306917 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-SWMOF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Swing Rear | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 24 | 90030727 | B1 | 1000306916 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-SWMOR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel LHF | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 8 | 90030728 | B1 | 1000306918 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMLF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel LHR | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 8 | 90030728 | B1 | 1000306919 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMLR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel RHF | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 8 | 90030728 | B1 | 1000306940 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMRF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel RHR | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 8 | 90030728 | B1 | 1000306941 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMRR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Hyd Vlve Bank Module Quarter Life | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 15 | 90027371 | B1 | 1000307009 | 08.09.2026 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDVLV-MCVLU | 7200 | 19274 | 8502
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Rotary Connection & Hoses | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 168 | 90030430 | B1 | 1000307014 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-ROTRY | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Minestar Harness | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 43.5 | 90030746 | B1 | 1000307013 | 04.01.2027 | 5000 | CCK-MP-EXCV-EX7136-MANGMT-UMMMC | 7200 | 19274 | 6848
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Boom Module Quarter Life | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 48 | 90027377 | B1 | 1000307011 | 13.08.2026 | 10000 | CCK-MP-EXCV-EX7136-STRUCT-BOOMS | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Svc 12M Air Conditioner Sys1 Eng | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 12 | 90035241 | B1 | 1000359789 | 20.09.2026 | 12 Monthly | CCK-MP-EXCV-EX7136-STRUCT-CABIN-AIRC1
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Tank Module | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 86 | 90036464 | B1 | 1000307012 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-STRUCT-HDTNK | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Service Module Hosing | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 24 | 90030753 | B1 | 1000307001 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-STRUCT-SRVCT-SHHLF
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Gearbox Swing P1 | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 109 | 90030720 | B1 | 1000306914 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-SWGSYS-SWBOX-SGBPF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Gearbox Swing P2 | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 109 | 90030720 | B1 | 1000306915 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-SWGSYS-SWBOX-SGBPR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Track Tension Tuning-Adjust | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 9 | 90020545 | B1 | 1000306996 | 13.11.2026 | 6 Monthly | CCK-MP-EXCV-EX7136-UNDERC | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Idler LH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 36 | 90030740 | B1 | 1000306956 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-IDLLH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Sprocket LH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 72 | 90030718 | B1 | 1000306952 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-SPRKL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Hyd Tensioner LH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 74 | 90024277 | B1 | 1000306948 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-TENSL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Assembly LH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 36 | 90030719 | B1 | 1000306953 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-TRKLH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Idler RH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 36 | 90030740 | B1 | 1000306957 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-IDLRH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Sprocket RH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 72 | 90030718 | B1 | 1000306954 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-SPRKR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Hyd Tensioner RH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 74 | 90024277 | B1 | 1000306949 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-TENSL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Assembly RH | 2026-08-10 | 2026-08-20 | 255 hrs | FY27 | 36 | 90030719 | B1 | 1000306955 | 08.09.2026 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-TRKRH | 7200 | 19274 | 19274
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 - ENGINE MODULE & MAJOR COMPONENTS | 2026-08-18 | 2026-08-29 | 276 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Engine Module | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 226 | 90011318 | B1 | 1000095155 | 24.05.2026 | 25000 | CCK-MP-HAUL-DT768 -ENGINE | 6800 | 79837 | 27373
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Grid Box Blower Motor LH | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 10 | 90011331 | B1 | 1000095171 | 27.05.2026 | 25000 | CCK-MP-HAUL-DT768 -ELCTHV-HVGBM-GBMLH | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Grid Box Blower Motor RH | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 10 | 90011332 | B1 | 1000095172 | 27.05.2026 | 25000 | CCK-MP-HAUL-DT768 -ELCTHV-HVGBM-GBMRH | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Wheel Motor RH | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 83.5 | 90011336 | B1 | 1000095176 | 27.05.2026 | 25000 | CCK-MP-HAUL-DT768 -FDRSYS-WLMTR-WHMRH | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Valve Retard & Brake Treadle | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 5.5 | 90011345 | B1 | 1000095181 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -BRKSYS-BRVTR | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Replace Brake Cooling Hoses | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223888 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -BRKSYS-BRHLF | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Replace Brake Cabinet Hoses | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126515 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -BRKSYS-BRHLF | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Valve Flow Amplifier | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 13.5 | 90011348 | B1 | 1000095184 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -STRSYS-STVLV | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Steering Brake Pump Compensator | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 7 | 90019922 | B1 | 1000204772 | 26.09.2026 | 6000 | CCK-MP-HAUL-DT768 -STRSYS-STPMP | 6800 | 79837 | 4916
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Pump Hoist | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 12 | 90011355 | B1 | 1000095191 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -HYDSYS-HOPMP | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Cyl Hoist RH | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 33 | 90011358 | B1 | 1000095194 | 27.05.2026 | 25000 | CCK-MP-HAUL-DT768 -HYDSYS-HOCYL-HCYLR | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Drive Shaft | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 2 | 90011359 | B1 | 1000095195 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -HYDSYS-DRSHT | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Replace Pump Module Hosing | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 27 | 90021389 | B1 | 1000223912 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -HYDSYS-HDHLF | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Replace Operator Cabin Dash Bulbs | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 2 | 90017265 | B1 | 1000158233 | 18.04.2026 | 3000 | CCK-MP-HAUL-DT768 -STRUCT-CABIN | 6800 | 79837 | 18344
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Air Con Service & Overhaul | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 36 | 90013265 | B1 | 1000110637 | 17.01.2027 | 12 Monthly | CCK-MP-HAUL-DT768 -STRUCT-CABIN-AIRCN | 6800 | 79837 | 79837
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Cyl Suspension LHR | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 50 | 90011367 | B1 | 1000095204 | 27.05.2026 | 25000 | CCK-MP-HAUL-DT768 -STRUCT-SUSPN-SCYLR | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Cyl Suspension RHR | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 50 | 90011368 | B1 | 1000095205 | 27.05.2026 | 25000 | CCK-MP-HAUL-DT768 -STRUCT-SUSPN-SCYRR | 6800 | 79837 | 26332
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Tyre Sense Battery | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 1 | 90017025 | B1 | 1000153193 | 22.12.2026 | 24 Monthly | CCK-MP-HAUL-DT768 -MANGMT-TYRSN
930E | Onsite Shut | Haul | Fortescue | DT768 | DT768 Repl Brake Dual Relay Valves | 2026-08-18 | 2026-08-29 | 276 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223768 | 21.05.2026 | 25000 | CCK-MP-HAUL-DT768 -BRKSYS-BRVRL | 6800 | 79837 | 26332
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 - MAJOR COMPONENTS | 2026-08-23 | 2026-09-03 | 276 hrs | FY27
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Annual Air Con Service RH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 13 | 90027615 | B1 | 1000288563 | 20.07.2026 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN-AIRCR | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Idler Track LH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 18 | 90027507 | B1 | 1000288573 | 27.07.2026 | 1500 | CCK-MP-EXCV-EX7121-STRUCT-TKFRL-IDLLH | 490 | 1377 | 1377
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Idler Track RH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 18 | 90027507 | B1 | 1000288584 | 27.07.2026 | 1500 | CCK-MP-EXCV-EX7121-STRUCT-TKFRR-IDLRH | 490 | 1377 | 1377
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Sprocket LH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 24 | 90027486 | B1 | 1000288581 | 27.07.2026 | 1500 | CCK-MP-EXCV-EX7121-TRAVEL-SPRKL | 490 | 1377 | 1377
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Sprocket RH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 24 | 90027486 | B1 | 1000288592 | 27.07.2026 | 1500 | CCK-MP-EXCV-EX7121-TRAVEL-SPRKR | 490 | 1377 | 1377
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Minestar Harness | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 43.5 | 90031708 | B1 | 1000369996 | 11.08.2026 | 4000 | CCK-MP-EXCV-EX7121-MANGMT-UMMMC | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Annual Air Con Service LH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 13 | 90027615 | B1 | 1000288593 | 25.08.2026 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN-AIRCL
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Fan Drive Hyd Cooling Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 36 | 90027565 | B1 | 1000288539 | 08.10.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-FDHCH | 6900 | 21434 | 10797
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Fan Drive Eng Cooling Hose | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 36 | 90027564 | B1 | 1000288538 | 09.10.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-FDECH | 6900 | 21434 | 10785
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hydraulic Cooling Circ Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 36 | 90031704 | B1 | 1000288540 | 09.10.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-HCCHH | 6900 | 21434 | 10785
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Rotor to Drive Motor Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 40 | 90027570 | B1 | 1000288545 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-RCDMH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Servo Hoses Cascade to Bulkhead | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 16 | 90027572 | B1 | 1000288547 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SHBLK | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Servo Hoses Cascade to Trvl Valve | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 12 | 90027575 | B1 | 1000288549 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SHTRV | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 2nd Speed Trvl Brake Release Hose | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 10 | 90027559 | B1 | 1000288535 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SSTBR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Swing Motor Case Drain Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 12 | 90027577 | B1 | 1000288551 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SWMCD | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Travel Motor Case Drain Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 10 | 90027578 | B1 | 1000288552 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-TMCDH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel LHF | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000288529 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMLF | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel RHF | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000288531 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMRF | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel RHR | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000288532 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMRR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Hyd Pump Pos1 | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 64 | 90027490 | B1 | 1000288501 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-MNPP1 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Hyd Pump Pos2 | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 64 | 90027490 | B1 | 1000288502 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-MNPP2 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Pos1 & Pos2 | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 42 | 90027492 | B1 | 1000288505 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SP1P2 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Pos3 & Pos4 | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 42 | 90027492 | B1 | 1000288506 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SP3P4 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Replenish LH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 2 | 90027495 | B1 | 1000288511 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SRPPL | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Replenish RH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 2 | 90027495 | B1 | 1000288512 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SRPPR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Pump Servo LH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 2 | 90027496 | B1 | 1000288509 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SVPPL | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Pump Servo RH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 2 | 90027496 | B1 | 1000288510 | 16.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SVPPR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Boom Arch Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 24 | 90027558 | B1 | 1000288536 | 17.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-BMARH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Boom & MCV Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 136 | 90032593 | B1 | 1000324957 | 17.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-HBSBC | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Boom Stick Bucket Cyl Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 136 | 90027560 | B1 | 1000288537 | 17.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-HBSBC | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Rotor & Logic Valve Hp Hoses | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 36 | 90027571 | B1 | 1000288546 | 17.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-RCLVH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Servo Hose Bulkhead to MCV | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 16 | 90027574 | B1 | 1000288548 | 17.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SHMCV | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel LHR | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000288530 | 17.12.2026 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMLR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Rotary Joint | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 48 | 90027501 | B1 | 1000288521 | 19.12.2026 | 24000 | CCK-MP-EXCV-EX7121-HYDSYS-ROTRY | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Final Drive LH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 144 | 90027485 | B1 | 1000288454 | 19.12.2026 | 24000 | CCK-MP-EXCV-EX7121-TRAVEL-FDRLH | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Final Drive RH | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 144 | 90027485 | B1 | 1000288455 | 19.12.2026 | 24000 | CCK-MP-EXCV-EX7121-TRAVEL-FDRRH | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Auto Lube Pump | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 6 | 90027592 | B1 | 1000288569 | 14.01.2027 | 6000 | CCK-MP-EXCV-EX7121-GRSYST-ALBPP | 6900 | 21434 | 9780
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Grease Control Valving | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 14 | 90027612 | B1 | 1000288570 | 14.01.2027 | 12000 | CCK-MP-EXCV-EX7121-GRSYST-ALCON
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Hydraulic System Tune Up | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 24 | 90017865 | B1 | 1000288568 | 14.01.2027 | 6000 | CCK-MP-EXCV-EX7121-HYDSYS | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Hydraulic Oil Replacement | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 12 | 90016793 | B1 | 1000288558 | 14.01.2027 | 6000 | CCK-MP-EXCV-EX7121-HYDSYS | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Hyd Pump Pos3 | 2026-08-23 | 2026-09-03 | 276 hrs | FY27 | 64 | 90027490 | B1 | 1000288503 | 26.01.2027 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-MNPP3 | 6900 | 21434 | 8484
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 - ENGINE & MAJOR COMPONENTS | 2026-09-03 | 2026-09-12 | 228 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Engine Cat C175-16 | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 137 | 90015881 | B1 | 1000155895 | 20.07.2026 | 24000 | CCK-MP-HAUL-DT086 -ENGINE | 7400 | 86822 | 24006
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Transmission | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 39 | 90026996 | B2 | 1000271879 | 22.01.2027 | 18000 | CCK-MP-HAUL-DT086 -TRNSYS-TRANS | 7400 | 86822 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Transmission Oil Cooler | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 12 | 90010097 | B1 | 1000082898 | 22.01.2027 | 18000 | CCK-MP-HAUL-DT086 -TRNSYS-TROLC | 7400 | 86822 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Drive Shaft Transmission | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 16 | 90017195 | B1 | 1000154931 | 21.01.2027 | 18000 | CCK-MP-HAUL-DT086 -FDRSYS-DRSHT | 7400 | 86846 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Differential | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 66 | 90014504 | B1 | 1000024033 | 21.01.2027 | 18000 | CCK-MP-HAUL-DT086 -FDRSYS-DIFFL | 7400 | 86846 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Cyl Steering LH | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 20 | 90002385 | B1 | 1000024048 | 26.08.2026 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STRCY-STCYL | 7400 | 86846 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Steering Linkages | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 28 | 90028568 | B1 | 1000317591 | 27.08.2026 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STLTR | 7400 | 86846 | 23853
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Auto Lube Pump | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 3 | 90002391 | B1 | 1000285628 | 15.12.2026 | 8000 | CCK-MP-HAUL-DT086 -GRSYST-ALBPP | 7400 | 86846 | 5030
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Service Air Conditioner 12M | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 18 | 90018230 | B1 | 1000174115 | 27.08.2026 | 12 Monthly | CCK-MP-HAUL-DT086 -STRUCT-CABIN-AIRCN | 7400 | 86822 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Operators Seat | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 6 | 90002395 | B1 | 1000024062 | 02.08.2026 | 15000 | CCK-MP-HAUL-DT086 -STRUCT-CABIN-SEATS | 7400 | 86822 | 14768
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Replace Steering System Hoses | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 106 | 90010133 | B1 | 1000082912 | 27.08.2026 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STHLF-STRHO | 7400 | 86822 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Replace Trans TCon System Hoses | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 20 | 90010099 | B1 | 1000090070 | 22.01.2027 | 18000 | CCK-MP-HAUL-DT086 -TRNSYS-TRANS-TRNHO | 7400 | 86822 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Replace Hoses Differential System | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 5 | 90010101 | B1 | 1000090071 | 22.01.2027 | 18000 | CCK-MP-HAUL-DT086 -FDRSYS-DIFFL-DIFHO | 7400 | 86822 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Steering Hyd Oil Cooler | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 9 | 90012866 | B2 | 1000107018 | 27.08.2026 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STOCO | 7400 | 86822 | 14283
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Drive Line Axle LH | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 4 | 90014919 | B1 | 1000124400 | 30.07.2026 | 24000 | CCK-MP-HAUL-DT086 -FDRSYS-DRLAX-AXLLH | 7400 | 86822 | 23853
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Drive Line Axle RH | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 4 | 90014943 | B1 | 1000124401 | 30.07.2026 | 24000 | CCK-MP-HAUL-DT086 -FDRSYS-DRLAX-AXLRH | 7400 | 86822 | 23853
793F | Onsite Shut | Haul | Fortescue | DT086 | DT086 Repl Front Wheel Bearings LH | 2026-09-03 | 2026-09-12 | 228 hrs | FY27 | 44 | 90017284 | B1 | 1000157116 | 23.11.2026 | 16000 | CCK-MP-HAUL-DT086 -STRUCT-AXLES-FWBLH | 7400 | 86822 | 13482
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 - POWER PACKS & MAJOR COMPONENTS | 2026-09-08 | 2026-09-19 | 276 hrs | FY27
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Power Pack Module 1 | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 190 | 90026630 | B1 | 1000267713 | 30.10.2026 | 16000 | CCK-MP-EXCV-EX8106-FRENGN | 7200 | 46150 | 15799
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Grease System Audit | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 36 | 90019204 | B1 | 1000213677 | 28.06.2026 | 4000 | CCK-MP-EXCV-EX8106-GRSYST-GRINJ | 7200 | 40923 | 7881
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Boom LH | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 76 | 90015686 | B1 | 1000162069 | 05.02.2027 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-BMCYL | 7200 | 46150 | 12222
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Boom RH | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 76 | 90015686 | B1 | 1000162070 | 27.12.2026 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-BMCYR | 7200 | 46150 | 13003
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Bucket LH Lift | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 46 | 90015688 | B1 | 1000162073 | 19.02.2027 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-BUCYL | 7200 | 46150 | 5656
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Stick LH | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 48 | 90015687 | B1 | 1000162071 | 05.02.2027 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-STCLL | 7200 | 46150 | 12222
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Stick RH | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 48 | 90015687 | B1 | 1000162072 | 05.02.2027 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-STCLR | 7200 | 46150 | 12222
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Mono-Block C/Over - Repl | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 12 | 90015706 | B1 | 1000162106 | 02.01.2027 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HMBCO | 7200 | 46150 | 8894
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing RHF P1 | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 18 | 90015695 | B1 | 1000162086 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMF1 | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing LHF P2 | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 18 | 90015695 | B1 | 1000162087 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMF2 | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing RHR P1 | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 18 | 90015695 | B1 | 1000162084 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMR1 | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing LHR P2 | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 18 | 90015695 | B1 | 1000162085 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMR2 | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hydraulic Tank Module | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 108 | 90026632 | B1 | 1000267597 | 30.10.2026 | 24000 | CCK-MP-EXCV-EX8106-HYDSYS-HDTNK | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Power Pack Module 2 | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 190 | 90026631 | B1 | 1000267716 | 30.10.2026 | 16000 | CCK-MP-EXCV-EX8106-RRENGN | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing LHF | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 60 | 90015674 | B1 | 1000162038 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBLF | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing LHR | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 60 | 90015674 | B4 | 1000162039 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBLR | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing RHF | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 60 | 90015674 | B2 | 1000162040 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBRF | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing RHR | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 60 | 90015674 | B3 | 1000162041 | 23.06.2026 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBRR | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Service Trap & Ladder Harns | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 12 | 90019319 | B1 | 1000245270 | 03.12.2026 | 24000 | CCK-MP-EXCV-EX8106-ELCTLV-HARNS-HARLA | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Elec Harness Cabin-Cabinet | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 1 | 90019317 | B1 | 1000196705 | 03.12.2026 | 24000 | CCK-MP-EXCV-EX8106-ELCTLV-MCCEL-MCCHR | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Bucket Cylinders - Repl | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 54 | 90015703 | B1 | 1000222964 | 19.02.2027 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HBKCL | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Auto Lube Pump P3 Slew Teeth | 2026-09-08 | 2026-09-19 | 276 hrs | FY27 | 2 | 90019422 | B1 | 1000197104 | 19.02.2027 | 10000 | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-ALBP3 | 7200 | 46150 | 5656
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 - ENGINE & MAJOR COMPONENTS | 2026-09-13 | 2026-09-22 | 222 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Engine Cat C175-16 | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 137 | 90015881 | B1 | 1000155913 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -ENGINE | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Radiator Engine Cooling | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 62 | 90031072 | B1 | 1000307484 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -ENGINE-COSYS-RADTR | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Pump Drive | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 39 | 90002365 | B1 | 1000024340 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -ENGINE-PMPDR | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Torque Converter | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 53 | 90002369 | B1 | 1000024345 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -TRNSYS-TRQUE | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Motor Lube Axle Rear & Hoses | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 8 | 90026943 | B1 | 1000271959 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYM01 | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Axle Lube Hyd Pump | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 4 | 90010102 | B1 | 1000154009 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYPUM | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Overhaul Accumulator Brake LHF | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 11 | 90002378 | B1 | 1000024354 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BACCM-FRLFT | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Overhaul Accumulator Brake RHF | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 11 | 90002378 | B1 | 1000024355 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BACCM-FRRGT | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Overhaul Accumulator Brake Rear | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 11 | 90002378 | B1 | 1000024356 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BACCM-BACCR | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Overhaul Valve Control Brake | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 20 | 90002380 | B2 | 1000024358 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BRVLV | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Motor Brake Oil Cooling | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 3 | 90002381 | B1 | 1000024359 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BROCO-HYMO1 | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Hyd Pump Steering Main & Fan | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 17 | 90002383 | B1 | 1000024362 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -STRSYS-STPMP | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Steering HMU | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 8 | 90002384 | B1 | 1000024363 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -STRSYS-STHMU | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Ovhl Accumulator Steering Front | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 12 | 90002386 | B1 | 1000024366 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -STRSYS-STACC-SACCF | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Ovhl Accumulator Steering Middle | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 12 | 90002386 | B1 | 1000024367 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -STRSYS-STACC-SACCM | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Ovhl Accumulator Steering Rear | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 12 | 90002386 | B1 | 1000024368 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -STRSYS-STACC-SACCR | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Auto Lube Pump | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 3 | 90002391 | B1 | 1000285631 | 26.12.2026 | 8000 | CCK-MP-HAUL-DT091 -GRSYST-ALBPP | 7400 | 83859 | 5241
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Rear Axle Linkages | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 113 | 90002396 | B1 | 1000024379 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -STRUCT-CHASS-AXLIK | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Replace Hoses Hoist System | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 40 | 90010105 | B1 | 1000091384 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -HYDSYS-HDHLF-HSTHO | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Replace Brake System Hoses | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 90 | 90010129 | B3 | 1000091390 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BRHLF-BRHOS | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Brake Cooling System Hoses | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 60 | 90010130 | B1 | 1000091391 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BRHLF-CBRHO | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Drive Line Axle LH | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 4 | 90014919 | B1 | 1000124567 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -FDRSYS-DRLAX-AXLLH | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Drive Line Axle RH | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 4 | 90014943 | B1 | 1000124569 | 21.08.2026 | 24000 | CCK-MP-HAUL-DT091 -FDRSYS-DRLAX-AXLRH | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Wheel End LH | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 58.5 | 90002374 | B1 | 1000024350 | 24.02.2028 | 24000 | CCK-MP-HAUL-DT091 -FDRSYS-FDRVE-FDRLH | 7400 | 83859 | 12431
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Cyl Hoist LH | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 33 | 90015130 | B1 | 1000128551 | 28.02.2027 | 28000 | CCK-MP-HAUL-DT091 -HYDSYS-HOCYL-HCYLL | 7400 | 83859 | 23814
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Drive Shaft Transmission | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 16 | 90017195 | B1 | 1000154937 | 07.06.2027 | 18000 | CCK-MP-HAUL-DT091 -FDRSYS-DRSHT | 7400 | 83859 | 11975
793F | Onsite Shut | Haul | Fortescue | DT091 | DT091 Repl Front Wheel Bearings RH | 2026-09-13 | 2026-09-22 | 222 hrs | FY27 | 44 | 90017285 | B1 | 1000157210 | 30.09.2029 | 16000 | CCK-MP-HAUL-DT091 -STRUCT-AXLES-FWBRH | 7400 | 83859 | 16663
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 - ENGINE MODULE & MAJOR COMPONENTS | 2026-09-23 | 2026-10-10 | 414 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Engine Module | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 226 | 90011318 | B1 | 1000094572 | 02.07.2026 | 25000 | CCK-MP-HAUL-DT757 -ENGINE | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Wheel Motor LH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 83.5 | 90011335 | B1 | 1000094592 | 25.06.2026 | 25000 | CCK-MP-HAUL-DT757 -FDRSYS-WLMTR-WHMLH | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Wheel Motor Oil LH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 1 | 90033606 | B1 | 1000338210 | 25.06.2026 | 25000 | CCK-MP-HAUL-DT757 -FDRSYS-WLMTR-WHMLH | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Wheel Motor RH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 83.5 | 90011336 | B1 | 1000094593 | 25.06.2026 | 25000 | CCK-MP-HAUL-DT757 -FDRSYS-WLMTR-WHMRH | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Wheel Motor Oil RH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 1 | 90033606 | B1 | 1000338211 | 25.06.2026 | 25000 | CCK-MP-HAUL-DT757 -FDRSYS-WLMTR-WHMRH | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Replace Brake Cabinet Hoses | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126504 | 01.07.2026 | 25000 | CCK-MP-HAUL-DT757 -BRKSYS-BRHLF | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Replace Brake Cooling Hoses | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223877 | 01.07.2026 | 25000 | CCK-MP-HAUL-DT757 -BRKSYS-BRHLF | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Cyl Steering LH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 16 | 90011350 | B1 | 1000094603 | 07.05.2026 | 15000 | CCK-MP-HAUL-DT757 -STRSYS-STRCY-STCYL | 6800 | 80700 | 16936
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Cyl Steering RH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 15 | 90011351 | B1 | 1000094604 | 07.05.2026 | 15000 | CCK-MP-HAUL-DT757 -STRSYS-STRCY-STCYR | 6800 | 80700 | 16936
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Hyd Pump Steering & Brake | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 38 | 90019919 | B1 | 1000204437 | 08.04.2026 | 12000 | CCK-MP-HAUL-DT757 -STRSYS-STPMP | 6800 | 80700 | 14601
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Pump Hoist | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 12 | 90011355 | B1 | 1000094608 | 01.07.2026 | 25000 | CCK-MP-HAUL-DT757 -HYDSYS-HOPMP | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Cyl Hoist LH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 33 | 90011357 | B1 | 1000094610 | 25.06.2026 | 25000 | CCK-MP-HAUL-DT757 -HYDSYS-HOCYL-HCYLL | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Replace Pump Module Hosing | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 27 | 90021389 | B1 | 1000223901 | 01.07.2026 | 25000 | CCK-MP-HAUL-DT757 -HYDSYS-HDHLF | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Replace Operator Cabin Dash Bulbs | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 2 | 90017265 | B1 | 1000158222 | 19.07.2026 | 3000 | CCK-MP-HAUL-DT757 -STRUCT-CABIN | 6800 | 80700 | 80700
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Hub & Spindle RH | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 60 | 90011364 | B1 | 1000094618 | 11.10.2026 | 18000 | CCK-MP-HAUL-DT757 -STRUCT-AXLES-HUBRH | 6800 | 80700 | 16936
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Cyl Suspension RHF | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 112 | 90011366 | B1 | 1000094620 | 11.10.2026 | 18000 | CCK-MP-HAUL-DT757 -STRUCT-SUSPN-SCYRF | 6800 | 80700 | 16936
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Cyl Suspension LHR | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 50 | 90011367 | B1 | 1000094621 | 25.06.2026 | 25000 | CCK-MP-HAUL-DT757 -STRUCT-SUSPN-SCYLR | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Cyl Suspension RHR | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 50 | 90011368 | B1 | 1000094622 | 25.06.2026 | 25000 | CCK-MP-HAUL-DT757 -STRUCT-SUSPN-SCYRR | 6800 | 80700 | 25834
930E | Onsite Shut | Haul | Fortescue | DT757 | DT757 Repl Brake Dual Relay Valves | 2026-09-23 | 2026-10-10 | 414 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223477 | 01.07.2026 | 25000 | CCK-MP-HAUL-DT757 -BRKSYS-BRVRL | 6800 | 80700 | 25834
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 - ENGINE MIDLIFE & COMPONENTS | 2026-10-07 | 2026-10-17 | 246 hrs | FY27
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Centre Bearing Upper Shaft | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90002702 | B2 | 1000090374 | 29.07.2026 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-UCTRB | 6000 | 74441 | 9732
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Front Drive Shaft Unis | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 8 | 90033188 | B1 | 1000333534 | 31.07.2026 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT04 | 6000 | 74441 | 9741
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Replace Artic Area Hyd Hosing | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 6 | 90020831 | B1 | 1000220503 | 21.08.2026 | 8 Monthly | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Final Drive Position 2 | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 83 | 90002710 | B2 | 1000090383 | 27.08.2026 | 16000 | CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR02 | 6000 | 74441 | 15269
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Sepura SCC Microphone | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 0.5 | 90028998 | B1 | 1000289602 | 18.09.2026 | 12 Monthly | CCK-MP-LOAD-WL267 -COMMUN-RADIO | 6000 | 74441 | 74441
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Brake Accumulator Front | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 12 | 90002714 | B2 | 1000090388 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -BRKSYS-BRACC-BACCF | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Brake Accumulator Rear | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 12 | 90002714 | B2 | 1000090389 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -BRKSYS-BRACC-BACCR | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Auto Lube Pump | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 6 | 90002737 | B2 | 1000090404 | 10.06.2026 | 10000 | CCK-MP-LOAD-WL267 -GRSYST-ALBPP | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Valve Implement Ctrl LH | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90010965 | B2 | 1000112591 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -HYDSYS-HDVLV-HYV01 | 6000 | 74441 | 14181
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Valve Implement Ctrl RH | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90010966 | B2 | 1000112598 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -HYDSYS-HDVLV-HYV02 | 6000 | 74441 | 11777
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Implement LH | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90002723 | B2 | 1000090397 | 05.07.2026 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP01 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Implement RH | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90002724 | B2 | 1000090398 | 10.07.2026 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP02 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Implement Centre | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90002725 | B2 | 1000090399 | 10.07.2026 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP03 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Pilot & Cooling | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 12 | 90002726 | B2 | 1000090400 | 12.06.2026 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP04 | 6000 | 74441 | 10738
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pilot Accumulator | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 4 | 90012174 | B2 | 1000112612 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -HYDSYS-PACCM | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Main Airhoses & Valves | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 18 | 90011137 | B2 | 1000112605 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -PNEUMC-PNHLF | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Steering Hyd Pump Secondary | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 8 | 90002719 | B2 | 1000090394 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP04 | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Reseal Steering & Brake Tank | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 36 | 90010963 | B2 | 1000112584 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STTNK | 6000 | 74441 | 42578
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Shaft Rear PD To Cntr Brng | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90033191 | B1 | 1000333535 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT05 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Front Pump Drv Drive Shaft | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 16 | 90033189 | B1 | 1000333537 | 24.05.2026 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT06 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Trans System Hoses Midlife | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 4 | 90026915 | B1 | 1000271608 | 03.07.2026 | 8000 | CCK-MP-LOAD-WL267 -TRNSYS-TRHLF-TRNHO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Transmission Charge Pump | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 12 | 90002694 | B2 | 1000090366 | 10.06.2026 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-TRPMP | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Transmission Transfer Case | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 74 | 90017029 | B2 | 1000153218 | 08.10.2026 | 16000 | CCK-MP-LOAD-WL267 -TRNSYS-TRTRF | 6000 | 74441 | 14588
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Brake System Hoses Midlife | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 4 | 90026908 | B1 | 1000271604 | 28.10.2026 | 10000 | CCK-MP-LOAD-WL267 -BRKSYS-BRHLF-BRKHO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Engine Midlife complete | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 170 | 90021253 | B1 | 1000222640 | 28.10.2026 | 10000 | CCK-MP-LOAD-WL267 -ENGINE | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd System Hoses Midlife | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90026914 | B1 | 1000271606 | 28.10.2026 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-HYDHO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Overhaul Air Conditioner | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 48 | 90021132 | B1 | 1000222631 | 28.10.2026 | 10000 | CCK-MP-LOAD-WL267 -STRUCT-CABIN-AIRCN | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Input Shaft Unis | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 8 | 90033167 | B1 | 1000333528 | 28.10.2026 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT01 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Rear Output Drive Shaft Unis | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 8 | 90033167 | B1 | 1000333530 | 28.10.2026 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT02 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Ctr Output Drive Shaft Unis | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 8 | 90033173 | B1 | 1000333532 | 28.10.2026 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT03 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Brake Cooling | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 8 | 90002713 | B2 | 1000090387 | 12.01.2027 | 10000 | CCK-MP-LOAD-WL267 -BRKSYS-BRPMP-BRP02 | 6000 | 74441 | 19742
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Overhaul Park Brake & Centre Brg | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 36 | 90002711 | B2 | 1000090417 | 07.02.2027 | 10000 | CCK-MP-LOAD-WL267 -BRKSYS-BRPRK | 6000 | 74441 | 21055
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Steering LH | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 26 | 90002721 | B2 | 1000090395 | 26.02.2027 | 12000 | CCK-MP-LOAD-WL267 -STRSYS-STRCY-STCYL | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Steering RH | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 28 | 90002722 | B2 | 1000090396 | 26.02.2027 | 12000 | CCK-MP-LOAD-WL267 -STRSYS-STRCY-STCYR | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 12 Monthly Hydraulic Tune Up | 2026-10-07 | 2026-10-17 | 246 hrs | FY27 | 24 | 90015111 | B1 | 1000126740 | 15.03.2027 | 52 Weekly | CCK-MP-LOAD-WL267 -HYDSYS | 6000 | 74441 | 8258
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 - LH ENGINE & MAJOR COMPONENTS | 2026-10-11 | 2026-10-22 | 276 hrs | FY27
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Engine Midlife Complete RH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 66 | 90027554 | B1 | 1000297433 | 13.09.2026 | 9000 | CCK-MP-EXCV-EX7123-RHENGN | 6900 | 15607 | 7903
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Annual Air Con Service RH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 13 | 90027615 | B1 | 1000297544 | 19.09.2026 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN-AIRCR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Hydraulic System Tune Up | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 24 | 90017865 | B1 | 1000297549 | 21.10.2026 | 6000 | CCK-MP-EXCV-EX7123-HYDSYS | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Hydraulic Oil Replacement | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90016793 | B1 | 1000297539 | 21.10.2026 | 6000 | CCK-MP-EXCV-EX7123-HYDSYS | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cyl Boom LH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 138 | 90027497 | B1 | 1000297494 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BMCYL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cyl Boom RH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 138 | 90027497 | B1 | 1000297495 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BMCYR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Oil Suction Hoses | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 48 | 90027568 | B1 | 1000297524 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-OILSC | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl PTO Cooling Hoses | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90027569 | B1 | 1000297525 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-PTOCL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Hyd Cool Front | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90027504 | B1 | 1000297506 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMCHF | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Hyd Cool Rear | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90027504 | B1 | 1000297507 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMCHR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Engine Cool LH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 18 | 90027505 | B1 | 1000297508 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMECL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Engine Cool RH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 18 | 90027505 | B1 | 1000297509 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMECR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Fan Engine Cool LH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90027494 | B1 | 1000297488 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-HECPL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Fan Engine Cool RH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90027494 | B1 | 1000297489 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-HECPR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Pump Drive Gearbox LH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 116 | 90027489 | B1 | 1000297480 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-PPDRL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Pump Drive Gearbox RH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 116 | 90027489 | B1 | 1000297481 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-PPDRR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Engine Cat C32 | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 244 | 90027533 | B1 | 1000297425 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-LHENGN | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Radiator LH Engine Cooling | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90027552 | B1 | 1000297429 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-LHENGN-COSYS-RADTR | 7100 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl LH Aftercooler | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 24 | 90023361 | B1 | 1000309290 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-LHENGN-INTEX-AFTER | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Minestar Harness | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 43.5 | 90031708 | B1 | 1000369997 | 04.12.2026 | 4000 | CCK-MP-EXCV-EX7123-MANGMT-UMMMC | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Radiator RH Engine Cooling | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 12 | 90027553 | B1 | 1000297434 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-RHENGN-COSYS-RADTR | 7100 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl RH Aftercooler | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 24 | 90023360 | B1 | 1000309291 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-RHENGN-INTEX-AFTER | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Track Tensioner LH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 72 | 90027527 | B1 | 1000297541 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-STRUCT-TKFRL-TENSR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Track Tensioner RH | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 72 | 90027527 | B1 | 1000297542 | 04.12.2026 | 18000 | CCK-MP-EXCV-EX7123-STRUCT-TKFRR-TENSR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Travel RHR | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000297513 | 27.01.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-TRMRR | 6900 | 15607 | 8493
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Wiper Blades | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 1 | 90027557 | B1 | 1000297545 | 24.02.2027 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Travel LHR | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000297511 | 26.02.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-TRMLR | 6900 | 15607 | 8020
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Travel LHF | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000297510 | 04.03.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-TRMLF | 6900 | 15607 | 7903
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Gearbox Swing LHR | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 82 | 90027580 | B1 | 1000297437 | 20.03.2027 | 20000 | CCK-MP-EXCV-EX7123-SWGSYS-SWBOX-SGBLR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Gearbox Swing RHF | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 82 | 90027580 | B1 | 1000297438 | 20.03.2027 | 20000 | CCK-MP-EXCV-EX7123-SWGSYS-SWBOX-SGBRF | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Gearbox Swing RHR | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 82 | 90027580 | B1 | 1000297439 | 20.03.2027 | 20000 | CCK-MP-EXCV-EX7123-SWGSYS-SWBOX-SGBRR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Swing Circuit Hoses | 2026-10-11 | 2026-10-22 | 276 hrs | FY27 | 16 | 90027576 | B1 | 1000297531 | 28.03.2027 | 9000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SWCRT | 6900 | 15607 | 4439
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2026-10-12 | 2026-10-21 | 222 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Engine Midlife Complete | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 62 | 90015886 | B1 | 1000155894 | 14.06.2026 | 12000 | CCK-MP-HAUL-DT082 -ENGINE | 7400 | 84374 | 35900
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Radiator Fan Hoses | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 11 | 90031073 | B1 | 1000307475 | 14.06.2026 | 12000 | CCK-MP-HAUL-DT082 -ENGINE-COSYS-RADTR | 7400 | 84374 | 35900
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Drive Shaft Transmission | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 16 | 90017195 | B1 | 1000154929 | 16.08.2026 | 18000 | CCK-MP-HAUL-DT082 -FDRSYS-DRSHT | 7400 | 84374 | 17432
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Differential | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 66 | 90014504 | B1 | 1000023970 | 02.09.2026 | 18000 | CCK-MP-HAUL-DT082 -FDRSYS-DIFFL | 7400 | 84374 | 17432
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Wheel End LH | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 58.5 | 90002374 | B1 | 1000023971 | 09.05.2026 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-FDRVE-FDRLH | 7400 | 84374 | 25964
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Wheel End RH | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 58.5 | 90007352 | B1 | 1000023972 | 09.05.2026 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-FDRVE-FDRRH | 7400 | 84374 | 25964
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Motor Lube Axle Hoses | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 4 | 90026944 | B1 | 1000271952 | 14.06.2026 | 12000 | CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYM01 | 7400 | 84374 | 13167
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl AOC Fan Motor Rear | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 6 | 90002376 | B1 | 1000023974 | 14.06.2026 | 12000 | CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYM02 | 7400 | 84374 | 13167
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Brake Oil Cooler Front | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 13 | 90010109 | B1 | 1000082888 | 09.05.2026 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BROCO-BROCF | 7400 | 84374 | 25919
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Brake Oil Cooler Rear | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 13 | 90010108 | B1 | 1000082887 | 09.05.2026 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BROCO-BROCR | 7400 | 84374 | 25919
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Brake Slack Adjuster Front | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 4 | 90002382 | B1 | 1000023981 | 14.07.2027 | 20000 | CCK-MP-HAUL-DT082 -BRKSYS-SLACK-SLACF | 7400 | 84374 | 13167
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Brake Slack Adjuster Rear | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 4 | 90002382 | B1 | 1000023982 | 14.07.2027 | 20000 | CCK-MP-HAUL-DT082 -BRKSYS-SLACK-SLACR | 7400 | 84374 | 13167
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Wheel Group Front LH | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 54 | 90017286 | B1 | 1000157115 | 06.06.2026 | 24000 | CCK-MP-HAUL-DT082 -STRUCT-AXLES-HUBLH | 7400 | 84375 | 29
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Replace Hoses Differential System | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 5 | 90010101 | B1 | 1000090068 | 02.09.2026 | 18000 | CCK-MP-HAUL-DT082 -FDRSYS-DIFFL-DIFHO | 7400 | 84374 | 35900
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Drive Line Axle LH | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 4 | 90014919 | B1 | 1000124318 | 25.03.2026 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-DRLAX-AXLLH | 7400 | 84374 | 26984
793F | Onsite Shut | Haul | Fortescue | DT082 | DT082 Repl Drive Line Axle RH | 2026-10-12 | 2026-10-21 | 222 hrs | FY27 | 4 | 90014943 | B1 | 1000124319 | 25.03.2026 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-DRLAX-AXLRH | 7400 | 84374 | 26984
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 - MAJOR COMPONENTS | 2026-10-23 | 2026-11-01 | 216 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Wheel Motor RH | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 83.5 | 90011336 | B1 | 1000095282 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -FDRSYS-WLMTR-WHMRH | 6800 | 79305 | 24535
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Valve Retard & Brake Treadle | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 5.5 | 90011345 | B1 | 1000095287 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -BRKSYS-BRVTR | 6800 | 79305 | 24535
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Replace Brake Cabinet Hoses | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126517 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -BRKSYS-BRHLF | 6800 | 79305 | 24535
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Cyl Steering LH | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 16 | 90011350 | B1 | 1000095292 | 09.07.2026 | 15000 | CCK-MP-HAUL-DT770 -STRSYS-STRCY-STCYL | 6800 | 79305 | 15443
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Cyl Steering RH | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 15 | 90011351 | B1 | 1000095293 | 14.10.2026 | 15000 | CCK-MP-HAUL-DT770 -STRSYS-STRCY-STCYR | 6800 | 79305 | 13622
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Hyd Pump Steering & Brake | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 38 | 90019919 | B1 | 1000204750 | 18.07.2026 | 12000 | CCK-MP-HAUL-DT770 -STRSYS-STPMP | 6800 | 79305 | 24817
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Pump Hoist | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 12 | 90011355 | B1 | 1000095297 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -HYDSYS-HOPMP | 6800 | 79305 | 24535
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Replace Pump Module Hosing | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 27 | 90021389 | B1 | 1000223914 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -HYDSYS-HDHLF | 6800 | 79305 | 24535
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Replace Operator Cabin Dash Bulbs | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 2 | 90017265 | B1 | 1000158235 | 09.07.2026 | 3000 | CCK-MP-HAUL-DT770 -STRUCT-CABIN | 6800 | 79305 | 79305
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Cyl Suspension LHR | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 50 | 90011367 | B1 | 1000095310 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -STRUCT-SUSPN-SCYLR | 6800 | 79305 | 24535
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Cyl Suspension RHR | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 50 | 90011368 | B1 | 1000095311 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -STRUCT-SUSPN-SCYRR | 6800 | 79305 | 24535
930E | Onsite Shut | Haul | Fortescue | DT770 | DT770 Repl Brake Dual Relay Valves | 2026-10-23 | 2026-11-01 | 216 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223770 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -BRKSYS-BRVRL | 6800 | 79305 | 24535
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 - UNDERCARRIAGE & MINOR COMPONENTS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Final Drive & Sprocket RH | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 26 | 90020182 | B1 | 1000278377 | 23.07.2026 | 20000 | CCK-MP-DRLL-DR2129-TRAVEL-FDRRH | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Pump Water Inj | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 4 | 90031899 | B1 | 1000315427 | 08.08.2026 | 7500 | CCK-MP-DRLL-DR2129-DSTSUP-WTRPP | 6800 | 18062 | 7100
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Drive Shaft Pump Drive | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 12 | 90028862 | B1 | 1000287881 | 19.10.2026 | 5000 | CCK-MP-DRLL-DR2129-HYDSYS-PMPDG-DRSHT | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Mast ADS Hardware | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 49 | 90029071 | B1 | 1000292812 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-ADSYST-ADSHW | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Deck ADS Elec Hardware | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 10 | 90029060 | B1 | 1000292813 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-ADSYST-ADSHW-ADSMF | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cabin ADS Components | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 58.5 | 90029058 | B1 | 1000293015 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-ADSYST-ADSHW-HMIJK | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl ADS Field Instruments | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 7.5 | 90029064 | B1 | 1000293016 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-ADSYST-ADSIS | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl ADS 3D Sensor Harness | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 2 | 90029068 | B1 | 1000293019 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-ADSYST-ADSPR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl ADS LiDAR | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 4 | 90029065 | B1 | 1000293041 | 27.10.2026 | 5000 | CCK-MP-DRLL-DR2129-ADSYST-ADSPR-LIDAR | 6800 | 18062 | 13815
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl ADS Harnesses | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 43.5 | 90029073 | B1 | 1000293042 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-ADSYST-HARNC | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Hyd Motor Propel NCS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 12 | 90020190 | B1 | 1000278388 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-MPRPL | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Hyd Motor Propel CS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 12 | 90020190 | B1 | 1000278387 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-MPRPR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Seat Operators | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020200 | B2 | 1000278447 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-CABIN-SEATS | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Mast Module Midlife | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 253 | 90030336 | B1 | 1000302806 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-DMAST | 6800 | 18062 | 4985
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Carrier NCS NDE | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020189 | B1 | 1000278418 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-CARLF | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Carrier NCS Middle | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020189 | B1 | 1000278419 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-CARLM | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Carrier NCS DE | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020189 | B1 | 1000278420 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-CARLR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Idler & Recoil Gp NCS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90030377 | B1 | 1000303490 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-IDLLH | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos1 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278422 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF01 | 6800 | 18062 | 15983
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos2 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278432 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF02 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos3 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278434 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF03 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos4 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278436 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF04 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos5 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278438 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF05 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos6 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278440 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF06 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos7 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278442 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF07 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos8 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278444 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF08 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos9 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278446 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF09 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos10 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278424 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF10 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos11 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278426 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF11 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos12 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278428 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF12 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos13 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278430 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF13 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Carrier CS NDE | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020189 | B1 | 1000278417 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-CARRF | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Carrier CS Middle | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020189 | B1 | 1000278416 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-CARRM | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Carrier CS DE | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020189 | B1 | 1000278415 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-CARRR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Idler & Recoil Gp CS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90030377 | B1 | 1000303506 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-IDLRH | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos1 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278421 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF01 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos2 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278431 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF02 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos3 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278433 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF03 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos4 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278435 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF04 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos5 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278437 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF05 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos6 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278439 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF06 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos7 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278441 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF07 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos8 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278443 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF08 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos9 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278445 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF09 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos10 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278423 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF10 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos11 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278425 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF11 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos12 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278427 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF12 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos13 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000278429 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF13 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Final Drive & Sprocket LH | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 26 | 90020182 | B1 | 1000278376 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-TRAVEL-FDRLH | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Track Assembly NCS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 24 | 90020187 | B1 | 1000278451 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-TRAVEL-TRKLH | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Track Assembly CS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 24 | 90020187 | B1 | 1000278450 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-TRAVEL-TRKRH | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load NCS Pos14 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000313286 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF14 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Roller Load CS Pos14 | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 8 | 90020188 | B1 | 1000313285 | 27.10.2026 | 20000 | CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF14 | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl ADS Vibration Sensors | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 1 | 90029062 | B1 | 1000293017 | 16.12.2026 | 10000 | CCK-MP-DRLL-DR2129-ADSYST-ADSIS-DSVSN | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack RHF NDE CS | 2026-10-24 | 2026-10-31 | 180 hrs | FY27 | 24 | 90030670 | B1 | 1000278358 | 22.12.2026 | 6000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYRF | 6800 | 18057 | 1556
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 - MAJOR COMPONENTS | 2026-10-28 | 2026-11-04 | 180 hrs | FY27
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Cyl Blade Lift LH | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 16 | 90000287 | B1 | 1000255646 | 30.08.2026 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BLCYL | 5000 | 69680 | 8485
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Cyl Blade Lift RH | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 16 | 90000287 | B1 | 1000255647 | 26.07.2026 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BLCYR | 5000 | 69680 | 4914
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Steer Clutch & Brake Assm RH | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 28 | 90000313 | B2 | 1000091221 | 04.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -BRKSTR-SCABR | 5000 | 69693 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Rad Engine Cooling SN 529 UP | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 48 | 90000307 | B2 | 1000091212 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -ENGINE-COSYS-RADTR | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Aftercooler Engine | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 8 | 90010841 | B1 | 1000108464 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -ENGINE-INTEX-AFTER | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Final Drive LH | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 28 | 90000312 | B2 | 1000091218 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -FDRSYS-FDRLH | 5000 | 69680 | 7159
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Final Drive RH | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 28 | 90000312 | B2 | 1000091219 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -FDRSYS-FDRRH | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Fan Cooling Motor Hyd | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 16 | 90002094 | B2 | 1000108462 | 05.11.2026 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDCFM | 5000 | 69680 | 1080
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Hyd Oil Cooler | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 10 | 90009664 | B2 | 1000091227 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDOCO | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Ovhl Hydraulic & Fuel Tank | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 48 | 90010842 | B1 | 1000108466 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDTNK | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Overhaul Air Conditioner | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 48 | 90017468 | B1 | 1000196633 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -STRUCT-CABIN-AIRCN | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Drive Shaft | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 6 | 90033296 | B1 | 1000334113 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -TRNSYS | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Pump Trans & TCon Charge | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 10 | 90000302 | B2 | 1000091217 | 05.11.2026 | 18000 | CCK-MP-DOZR-DZ176 -TRNSYS-TRPMP | 5000 | 69680 | 16621
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Sepura SCC Microphone | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289551 | 13.11.2026 | 12 Monthly | CCK-MP-DOZR-DZ176 -COMMUN-RADIO | 5000 | 69693 | 69693
D10T | Onsite Shut | Ancillary | Fortescue | DZ176 | DZ176 Repl Hyd Pump Implement | 2026-10-28 | 2026-11-04 | 180 hrs | FY27 | 10 | 90000301 | B2 | 1000091222 | 09.03.2027 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HYDPP-HYIPP | 5000 | 69680 | 5908
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 - POWER PACK MIDLIFE & MINOR COMPONENTS | 2026-11-02 | 2026-11-13 | 276 hrs | FY27
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Gearbox Swing P1 | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 109 | 90030720 | B1 | 1000250210 | 13.07.2026 | 20000 | CCK-MP-EXCV-EX7120-SWGSYS-SWBOX-SGBPF | 7200 | 28725 | 20457
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Boom LH | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 78 | 90030723 | B1 | 1000250299 | 14.09.2026 | 16000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BMCYL | 7200 | 28725 | 15249
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Motor Swing Front | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 24 | 90030727 | B1 | 1000250229 | 14.09.2026 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDMOT-SWMOF | 7200 | 28725 | 19245
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Boom Module Quarter Life | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 48 | 90027377 | B1 | 1000279090 | 21.09.2026 | 10000 | CCK-MP-EXCV-EX7120-STRUCT-BOOMS | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Hyd Vlve Bank Module Quarter Life | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 15 | 90027371 | B1 | 1000279084 | 10.10.2026 | 10000 | CCK-MP-EXCV-EX7120-HYDSYS-HDVLV-MCVLU | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Ovhl 24M Air Conditioner Sys2 Hyd | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 36 | 90035446 | B1 | 1000359788 | 27.05.2026 | 24 Monthly | CCK-MP-EXCV-EX7120-STRUCT-CABIN-AIRC2
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Boom RH | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 78 | 90030723 | B1 | 1000250300 | 18.10.2026 | 16000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BMCYR | 7200 | 28725 | 14582
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Minestar Harness | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 43.5 | 90030746 | B1 | 1000281594 | 27.11.2026 | 5000 | CCK-MP-EXCV-EX7120-MANGMT-UMMMC | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Power Pack Module Midlife | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 343.5 | 90026485 | B1 | 1000279051 | 30.11.2026 | 10000 | CCK-MP-EXCV-EX7120-ENGINE | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Bucket LH Lift | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 54 | 90030725 | B1 | 1000250303 | 30.11.2026 | 10000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BUCYL | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Rotary Connection Hoses | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 96 | 90030432 | B1 | 1000303745 | 30.11.2026 | 10000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Track Tension Tuning-Adjust | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 9 | 90020545 | B1 | 1000250313 | 02.12.2026 | 6 Monthly | CCK-MP-EXCV-EX7120-UNDERC | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Grease System Audit | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 36 | 90030748 | B1 | 1000250272 | 03.03.2027 | 5000 | CCK-MP-EXCV-EX7120-GRSYST-GRINJ | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Gearbox Swing P2 | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 109 | 90030720 | B1 | 1000250211 | 08.03.2027 | 20000 | CCK-MP-EXCV-EX7120-SWGSYS-SWBOX-SGBPR | 7200 | 28725 | 15802
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Bucket RH Lift | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 54 | 90030726 | B1 | 1000250304 | 09.04.2027 | 10000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BUCYR | 7200 | 28725 | 5217
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Hose Bucket Cyl | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 54 | 90030738 | B1 | 1000250251 | 28.04.2027 | 8000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF-HBKCL | 7200 | 28725 | 2793
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Hose Stick Cyl | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 48 | 90030737 | B1 | 1000250250 | 06.05.2027 | 8000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF-HSTCL | 7200 | 28725 | 2629
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Hose Boom Cyl | 2026-11-02 | 2026-11-13 | 276 hrs | FY27 | 72 | 90030735 | B1 | 1000250249 | 30.04.2026 | 8000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF-HBMCL | 7200 | 28725 | 12234
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2026-11-03 | 2026-11-10 | 180 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Engine Midlife Complete | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 62 | 90015886 | B1 | 1000155936 | 17.08.2026 | 12000 | CCK-MP-HAUL-DT097 -ENGINE | 7400 | 83732 | 33462
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Radiator Fan Hoses | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 11 | 90031073 | B1 | 1000307493 | 15.08.2026 | 12000 | CCK-MP-HAUL-DT097 -ENGINE-COSYS-RADTR | 7400 | 83804 | 33534
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Pump Drive | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 39 | 90002365 | B1 | 1000024718 | 25.10.2026 | 24000 | CCK-MP-HAUL-DT097 -ENGINE-PMPDR | 7400 | 83804 | 22315
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Transmission | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 39 | 90026996 | B2 | 1000272311 | 26.08.2026 | 18000 | CCK-MP-HAUL-DT097 -TRNSYS-TRANS | 7400 | 83804 | 17427
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Drive Shaft Transmission | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 16 | 90017195 | B1 | 1000154943 | 20.11.2026 | 18000 | CCK-MP-HAUL-DT097 -FDRSYS-DRSHT | 7400 | 83804 | 15765
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Differential | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 66 | 90014504 | B1 | 1000024727 | 26.08.2026 | 18000 | CCK-MP-HAUL-DT097 -FDRSYS-DIFFL | 7400 | 83804 | 17427
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Motor Lube Axle Hoses | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 4 | 90026944 | B1 | 1000271986 | 13.08.2026 | 12000 | CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYM01 | 7400 | 83804 | 11742
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl AOC Fan Motor Rear | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 6 | 90002376 | B1 | 1000024731 | 13.08.2026 | 12000 | CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYM02 | 7400 | 83804 | 11742
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Steering Linkages | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 28 | 90028568 | B1 | 1000317603 | 11.01.2027 | 15000 | CCK-MP-HAUL-DT097 -STRSYS-STLTR | 7400 | 83804 | 22315
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Service Air Conditioner 12M | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 18 | 90018230 | B1 | 1000174161 | 06.01.2027 | 12 Monthly | CCK-MP-HAUL-DT097 -STRUCT-CABIN-AIRCN | 7400 | 83804 | 33534
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Replace Steering System Hoses | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 106 | 90010133 | B1 | 1000083026 | 11.01.2027 | 15000 | CCK-MP-HAUL-DT097 -STRSYS-STHLF-STRHO | 7400 | 83804 | 11742
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Replace Trans TCon System Hoses | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 20 | 90010099 | B1 | 1000090088 | 26.08.2026 | 18000 | CCK-MP-HAUL-DT097 -TRNSYS-TRANS-TRNHO | 7400 | 83804 | 17427
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Replace Hoses Differential System | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 5 | 90010101 | B1 | 1000090089 | 26.08.2026 | 18000 | CCK-MP-HAUL-DT097 -FDRSYS-DIFFL-DIFHO | 7400 | 83804 | 17425
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Steering Hyd Oil Cooler | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 9 | 90012866 | B2 | 1000107022 | 11.01.2027 | 15000 | CCK-MP-HAUL-DT097 -STRSYS-STOCO | 7400 | 83804 | 11742
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Tyre Sense Battery | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 2 | 90017022 | B1 | 1000153144 | 06.01.2027 | 24 Monthly | CCK-MP-HAUL-DT097 -MANGMT-TYRSN
793F | Onsite Shut | Haul | Fortescue | DT097 | DT097 Repl Front Wheel Bearings LH | 2026-11-03 | 2026-11-10 | 180 hrs | FY27 | 44 | 90017284 | B1 | 1000157128 | 01.03.2027 | 16000 | CCK-MP-HAUL-DT097 -STRUCT-AXLES-FWBLH | 7400 | 83804 | 11742
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 - ENGINE & MINOR COMPONENTS | 2026-11-11 | 2026-11-18 | 180 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl Engine Cat C175-16 | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 137 | 90015881 | B1 | 1000155979 | 23.09.2026 | 24000 | CCK-MP-HAUL-DT137 -ENGINE | 7400 | 84196 | 49397
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl Radiator Fan Hoses | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 11 | 90031073 | B1 | 1000307509 | 27.10.2026 | 12000 | CCK-MP-HAUL-DT137 -ENGINE-COSYS-RADTR | 7400 | 84196 | 32285
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl Motor Lube Axle Hoses | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 4 | 90026944 | B1 | 1000272002 | 27.10.2026 | 12000 | CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYM01 | 7400 | 84196 | 9757
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl AOC Fan Motor Rear | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 6 | 90002376 | B1 | 1000025556 | 27.10.2026 | 12000 | CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYM02 | 7400 | 84196 | 9757
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl Cyl Steering RH | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 20 | 90002385 | B2 | 1000025568 | 04.09.2026 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STRCY-STCYR | 7400 | 84196 | 13819
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl Steering Linkages | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 28 | 90028568 | B1 | 1000317619 | 24.03.2027 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STLTR | 7400 | 84196 | 32285
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Service Air Conditioner 12M | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 18 | 90018230 | B1 | 1000174170 | 31.03.2027 | 12 Monthly | CCK-MP-HAUL-DT137 -STRUCT-CABIN-AIRCN | 7400 | 84196 | 9757
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl Operators Seat | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 6 | 90002395 | B1 | 1000025581 | 29.10.2026 | 15000 | CCK-MP-HAUL-DT137 -STRUCT-CABIN-SEATS | 7400 | 84196 | 18714
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Replace Steering System Hoses | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 106 | 90010133 | B1 | 1000083235 | 24.03.2027 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STHLF-STRHO | 7400 | 84196 | 9757
793F | Onsite Shut | Haul | Fortescue | DT137 | DT137 Repl Steering Hyd Oil Cooler | 2026-11-11 | 2026-11-18 | 180 hrs | FY27 | 9 | 90012866 | B2 | 1000106995 | 24.03.2027 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STOCO | 7400 | 84196 | 9757
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 - POWER PACK MIDLIFE & MAJOR COMPONENTS | 2026-11-15 | 2026-11-22 | 180 hrs | FY27
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Engine Valve Set | 2026-10-01 | 2026-10-01 | 8 hrs | FY27 | 16 | 90021723 | B1 | 1000295094 | 01.10.2026 | 3000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Service Airconditioning System | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 12 | 90023281 | B1 | 1000295091 | 28.08.2026 | 12 Monthly | CCK-MP-DRLL-DR3134-STRUCT-CABIN-ACCOM | 5400 | 16590 | 16590
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Power Pack Module Midlife | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 129 | 90026035 | B1 | 1000295095 | 24.09.2026 | 6000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 1 | 90020876 | B1 | 1000295060 | 26.09.2026 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Pump Air Lubrication | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 2 | 90021656 | B1 | 1000295071 | 30.09.2026 | 6000 | CCK-MP-DRLL-DR3134-AIRSYS-COMPR-PALUB | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Pump Water Injection | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 4 | 90021716 | B1 | 1000295073 | 30.09.2026 | 6000 | CCK-MP-DRLL-DR3134-DSTSUP-WTRPP | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Pump Rod Thread Lube | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 2 | 90021715 | B1 | 1000295083 | 30.09.2026 | 6000 | CCK-MP-DRLL-DR3134-GRSYST-RTLPP | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Operators Seat | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 4 | 90021702 | B1 | 1000295069 | 30.09.2026 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-CABIN-SEATS | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Electrical Harness | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 30 | 90021727 | B1 | 1000295089 | 31.10.2026 | 18000 | CCK-MP-DRLL-DR3134-ELCTLV-HARNS | 5400 | 16590 | 16590
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 XLF Repl Main Feed Chain | 2026-11-15 | 2026-11-22 | 180 hrs | FY27 | 16 | 90021711 | B1 | 1000295065 | 04.12.2026 | 2500 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHH | 5400 | 16590 | 3175
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 - ENGINE MODULE & MAJOR COMPONENTS | 2026-11-22 | 2026-12-01 | 222 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Air Con Service & Overhaul | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 36 | 90013265 | B1 | 1000110631 | 09.10.2026 | 12 Monthly | CCK-MP-HAUL-DT762 -STRUCT-CABIN-AIRCN | 6800 | 76486 | 43303
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Cyl Hoist RH | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 33 | 90011358 | B1 | 1000094876 | 15.11.2026 | 25000 | CCK-MP-HAUL-DT762 -HYDSYS-HOCYL-HCYLR | 6800 | 76486 | 22853
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Engine Module | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 226 | 90011318 | B1 | 1000094837 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -ENGINE | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Grid Box Blower Motor LH | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 10 | 90011331 | B1 | 1000094853 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -ELCTHV-HVGBM-GBMLH | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Wheel Motor LH | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 83.5 | 90011335 | B1 | 1000094857 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -FDRSYS-WLMTR-WHMLH | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Wheel Motor RH | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 83.5 | 90011336 | B1 | 1000094858 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -FDRSYS-WLMTR-WHMRH | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Valve Retard & Brake Treadle | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 5.5 | 90011345 | B1 | 1000094863 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -BRKSYS-BRVTR | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Replace Brake Cabinet Hoses | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126509 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -BRKSYS-BRHLF | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Replace Brake Cooling Hoses | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223882 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -BRKSYS-BRHLF | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Valve Flow Amplifier | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 13.5 | 90011348 | B1 | 1000094866 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -STRSYS-STVLV | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Accumulator Hyd Steer Front | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 11.5 | 90011352 | B1 | 1000094870 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -STRSYS-STACC-SACCF | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Drive Shaft | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 2 | 90011359 | B1 | 1000094877 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -HYDSYS-DRSHT | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Replace Pump Module Hosing | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 27 | 90021389 | B1 | 1000223906 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -HYDSYS-HDHLF | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Cyl Suspension LHR | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 50 | 90011367 | B1 | 1000094886 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -STRUCT-SUSPN-SCYLR | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Cyl Suspension RHR | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 50 | 90011368 | B1 | 1000094887 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -STRUCT-SUSPN-SCYRR | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Brake Dual Relay Valves | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223762 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -BRKSYS-BRVRL | 6800 | 76486 | 22280
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Steering Brake Pump Compensator | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 7 | 90019922 | B1 | 1000204766 | 20.02.2027 | 6000 | CCK-MP-HAUL-DT762 -STRSYS-STPMP | 6800 | 76486 | 2043
930E | Onsite Shut | Haul | Fortescue | DT762 | DT762 Repl Pressure Reducing Valve | 2026-11-22 | 2026-12-01 | 222 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204794 | 27.03.2027 | 12000 | CCK-MP-HAUL-DT762 -BRKSYS-BRVLV-VVPRV | 6800 | 76486 | 10392
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 - MAJOR COMPONENTS | 2026-11-25 | 2026-12-02 | 168 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Radiator Engine Cooling | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 62 | 90031072 | B1 | 1000307488 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -ENGINE-COSYS-RADTR | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Pump Drive | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 39 | 90002365 | B1 | 1000024592 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -ENGINE-PMPDR | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Torque Converter | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 53 | 90002369 | B1 | 1000024597 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -TRNSYS-TRQUE | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl AOC Fan Motor Rear | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 6 | 90002376 | B1 | 1000024605 | 08.12.2026 | 12000 | CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYM02 | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Overhaul Accumulator Brake LHF | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 11 | 90002378 | B1 | 1000024606 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BACCM-FRLFT | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Overhaul Accumulator Brake RHF | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 11 | 90002378 | B1 | 1000024607 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BACCM-FRRGT | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Overhaul Accumulator Brake Rear | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 11 | 90002378 | B1 | 1000024608 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BACCM-BACCR | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Pump Brake Cooling | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 17 | 90002379 | B1 | 1000024609 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-HYFPP | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Overhaul Valve Control Brake | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 20 | 90002380 | B2 | 1000024610 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BRVLV | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Motor Brake Oil Cooling | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 3 | 90002381 | B1 | 1000024611 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BROCO-HYMO1 | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Hyd Pump Steering Main & Fan | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 17 | 90002383 | B1 | 1000024614 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -STRSYS-STPMP | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Steering HMU | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 8 | 90002384 | B1 | 1000024615 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -STRSYS-STHMU | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Cyl Steering LH | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 20 | 90002385 | B1 | 1000024616 | 29.11.2026 | 15000 | CCK-MP-HAUL-DT095 -STRSYS-STRCY-STCYL | 7400 | 88921 | 12649
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Cyl Steering RH | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 20 | 90002385 | B2 | 1000024617 | 29.11.2026 | 15000 | CCK-MP-HAUL-DT095 -STRSYS-STRCY-STCYR | 7400 | 88921 | 12649
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Ovhl Accumulator Steering Front | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 12 | 90002386 | B1 | 1000024618 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -STRSYS-STACC-SACCF | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Ovhl Accumulator Steering Middle | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 12 | 90002386 | B1 | 1000024619 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -STRSYS-STACC-SACCM | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Ovhl Accumulator Steering Rear | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 12 | 90002386 | B1 | 1000024620 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -STRSYS-STACC-SACCR | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Service Air Conditioner 12M | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 18 | 90018230 | B1 | 1000174160 | 10.10.2026 | 12 Monthly | CCK-MP-HAUL-DT095 -STRUCT-CABIN-AIRCN | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Rear Axle Linkages | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 113 | 90002396 | B1 | 1000024631 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -STRUCT-CHASS-AXLIK | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Wheel Group Front RH | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 54 | 90017287 | B1 | 1000157215 | 10.09.2026 | 24000 | CCK-MP-HAUL-DT095 -STRUCT-AXLES-HUBRH | 7400 | 88921 | 23253
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Replace Hoses Hoist System | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 40 | 90010105 | B1 | 1000082997 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -HYDSYS-HDHLF-HSTHO | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Replace Brake System Hoses | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 90 | 90010129 | B3 | 1000083003 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BRHLF-BRHOS | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Brake Cooling System Hoses | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 60 | 90010130 | B1 | 1000083004 | 17.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BRHLF-CBRHO | 7400 | 88921 | 21880
793F | Onsite Shut | Haul | Fortescue | DT095 | DT095 Repl Spider Trans Driveshaft | 2026-11-25 | 2026-12-02 | 168 hrs | FY27 | 12 | 90017211 | B1 | 1000154940 | 13.11.2026 | 6000 | CCK-MP-HAUL-DT095 -FDRSYS-DRSHT-UNVSL | 7400 | 88921 | 3967
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 - ENGINE MIDLIFE & COMPONENTS | 2026-11-26 | 2026-12-06 | 244 hrs | FY27
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 12 Monthly Hydraulic Tune Up | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 24 | 90015111 | B1 | 1000126742 | 04.09.2026 | 52 Weekly | CCK-MP-LOAD-WL269 -HYDSYS | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Bucket RH Ext High Lift | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 36 | 90015437 | B2 | 1000131513 | 16.10.2026 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-BUCYR | 6000 | 74583 | 8680
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Engine Midlife complete | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 170 | 90021253 | B1 | 1000222684 | 17.10.2026 | 10000 | CCK-MP-LOAD-WL269 -ENGINE | 6000 | 74583 | 8436
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Overhaul Air Conditioner | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 48 | 90021132 | B1 | 1000222675 | 17.10.2026 | 10000 | CCK-MP-LOAD-WL269 -STRUCT-CABIN-AIRCN | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Operators Seat | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 4 | 90002741 | B2 | 1000090553 | 22.10.2026 | 7000 | CCK-MP-LOAD-WL269 -STRUCT-CABIN-SEATS | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Bucket LH Ext High Lift | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 38 | 90015438 | B2 | 1000131512 | 01.11.2026 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-BUCYL | 6000 | 74583 | 8459
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Overhaul Park Brake & Centre Brg | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 36 | 90002711 | B2 | 1000090565 | 25.11.2026 | 10000 | CCK-MP-LOAD-WL269 -BRKSYS-BRPRK | 6000 | 74561 | 8060
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Auto Lube Pump | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 6 | 90002737 | B2 | 1000090552 | 25.11.2026 | 10000 | CCK-MP-LOAD-WL269 -GRSYST-ALBPP | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Pilot & Cooling | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 12 | 90002726 | B2 | 1000090548 | 25.11.2026 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP04 | 6000 | 74583 | 8060
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Centre Bearing Upper Shaft | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 24 | 90002702 | B2 | 1000090522 | 25.11.2026 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-UCTRB | 6000 | 74583 | 8437
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Replace Artic Area Hyd Hosing | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 6 | 90020831 | B1 | 1000220507 | 25.11.2026 | 8 Monthly | CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Lift RH Ext High Lift | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 54 | 90002728 | B2 | 1000112693 | 17.12.2026 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-HCYLR | 6000 | 74583 | 7630
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Trans System Hoses Midlife | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 4 | 90026915 | B1 | 1000271620 | 21.12.2026 | 8000 | CCK-MP-LOAD-WL269 -TRNSYS-TRHLF-TRNHO | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Final Drive Position 4 | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 83 | 90002710 | B2 | 1000090533 | 09.01.2027 | 16000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR04 | 6000 | 74583 | 13398
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Brake Accumulator Rear | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 12 | 90002714 | B2 | 1000090537 | 01.02.2027 | 20000 | CCK-MP-LOAD-WL269 -BRKSYS-BRACC-BACCR | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Replace Pilot System Hoses | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 96 | 90009731 | B2 | 1000090560 | 01.02.2027 | 20000 | CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-PILHO | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Steering Hyd Pump Secondary | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 8 | 90002719 | B2 | 1000090542 | 01.02.2027 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP04 | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Rear Output Drive Shaft | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 14 | 90033168 | B1 | 1000333553 | 01.02.2027 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT02 | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Centre Output Drive Shaft | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 14 | 90033171 | B1 | 1000333555 | 01.02.2027 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT03 | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Front Drive Shaft | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 16 | 90033175 | B1 | 1000333557 | 01.02.2027 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT04 | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Shaft Rear PD To Cntr Brng | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 24 | 90033191 | B1 | 1000333559 | 01.02.2027 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT05 | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Brake Accumulator Front | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 12 | 90002714 | B2 | 1000223014 | 06.03.2027 | 20000 | CCK-MP-LOAD-WL269 -BRKSYS-BRACC-BACCF | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Brake System Hoses Midlife | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 4 | 90026908 | B1 | 1000271616 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -BRKSYS-BRHLF-BRKHO | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Brake Cooling | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 8 | 90002713 | B2 | 1000090535 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -BRKSYS-BRPMP-BRP02 | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd System Hoses Midlife | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 24 | 90026914 | B1 | 1000271618 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-HYDHO | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Implement LH | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 24 | 90002723 | B2 | 1000090545 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP01 | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Implement RH | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 24 | 90002724 | B2 | 1000090546 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP02 | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Implement Centre | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 24 | 90002725 | B2 | 1000090547 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP03 | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Input Shaft Unis | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 8 | 90033167 | B1 | 1000333552 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT01 | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Transmission Charge Pump | 2026-11-26 | 2026-12-06 | 244 hrs | FY27 | 12 | 90002694 | B2 | 1000090514 | 22.04.2027 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-TRPMP | 6000 | 74583 | 5623
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 - ENGINE MODULE & MAJOR COMPONENTS | 2026-12-04 | 2026-12-13 | 222 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Hub & Spindle RH | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 60 | 90011364 | B1 | 1000095466 | 14.08.2026 | 18000 | CCK-MP-HAUL-DT773 -STRUCT-AXLES-HUBRH | 6800 | 75884 | 17674
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Cyl Steering RH | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 15 | 90011351 | B1 | 1000095452 | 13.09.2026 | 15000 | CCK-MP-HAUL-DT773 -STRSYS-STRCY-STCYR | 6800 | 75884 | 14026
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Brake Manifold | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 13.5 | 90029265 | B1 | 1000292181 | 22.10.2026 | 25000 | CCK-MP-HAUL-DT773 -BRKSYS-BRVLV | 6800 | 75884 | 23421
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Hyd Pump Steering & Brake | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 38 | 90019919 | B1 | 1000204753 | 25.10.2026 | 12000 | CCK-MP-HAUL-DT773 -STRSYS-STPMP | 6800 | 75884 | 10573
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Engine Module | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 226 | 90011318 | B1 | 1000095420 | 07.12.2026 | 25000 | CCK-MP-HAUL-DT773 -ENGINE | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Wheel Motor LH | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 83.5 | 90011335 | B1 | 1000095440 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -FDRSYS-WLMTR-WHMLH | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Wheel Motor RH | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 83.5 | 90011336 | B1 | 1000095441 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -FDRSYS-WLMTR-WHMRH | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Brake Accumulator Rear | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 11 | 90011339 | B1 | 1000095444 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -BRKSYS-BRACC-BACCR | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Replace Brake Cabinet Hoses | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126520 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -BRKSYS-BRHLF | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Replace Brake Cooling Hoses | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223893 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -BRKSYS-BRHLF | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Cyl Hoist LH | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 33 | 90011357 | B1 | 1000095458 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -HYDSYS-HOCYL-HCYLL | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Cyl Hoist RH | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 33 | 90011358 | B1 | 1000095459 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -HYDSYS-HOCYL-HCYLR | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Replace Pump Module Hosing | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 27 | 90021389 | B1 | 1000223917 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -HYDSYS-HDHLF | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Replace Operator Cabin Dash Bulbs | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 2 | 90017265 | B1 | 1000158238 | 15.12.2026 | 3000 | CCK-MP-HAUL-DT773 -STRUCT-CABIN | 6800 | 75884 | 75884
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Cyl Suspension LHF | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 112 | 90011365 | B1 | 1000095467 | 15.12.2026 | 18000 | CCK-MP-HAUL-DT773 -STRUCT-SUSPN-SCYLF | 6800 | 75884 | 13213
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Cyl Suspension LHR | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 50 | 90011367 | B1 | 1000095469 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -STRUCT-SUSPN-SCYLR | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Cyl Suspension RHR | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 50 | 90011368 | B1 | 1000095470 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -STRUCT-SUSPN-SCYRR | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Brake Dual Relay Valves | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223773 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -BRKSYS-BRVRL | 6800 | 75884 | 22415
930E | Onsite Shut | Haul | Fortescue | DT773 | DT773 Repl Cyl Steering LH | 2026-12-04 | 2026-12-13 | 222 hrs | FY27 | 16 | 90011350 | B1 | 1000095451 | 16.03.2027 | 15000 | CCK-MP-HAUL-DT773 -STRSYS-STRCY-STCYL | 6800 | 75884 | 10573
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2026-12-15 | 2026-12-22 | 180 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Pump Drive | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 39 | 90002365 | B1 | 1000026462 | 12.11.2026 | 24000 | CCK-MP-HAUL-DT151 -ENGINE-PMPDR | 7400 | 84301 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Wheel End LH | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 58.5 | 90002374 | B1 | 1000026472 | 12.11.2026 | 24000 | CCK-MP-HAUL-DT151 -FDRSYS-FDRVE-FDRLH | 7400 | 84301 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Wheel End RH | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 58.5 | 90007352 | B1 | 1000026473 | 12.11.2026 | 24000 | CCK-MP-HAUL-DT151 -FDRSYS-FDRVE-FDRRH | 7400 | 84301 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Overhaul Valve Control Brake | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 20 | 90002380 | B2 | 1000026480 | 12.11.2026 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BRVLV | 7400 | 84301 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Wheel Group Front LH | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 54 | 90017286 | B1 | 1000157167 | 14.11.2026 | 24000 | CCK-MP-HAUL-DT151 -STRUCT-AXLES-HUBLH | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Wheel Group Front RH | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 54 | 90017287 | B1 | 1000157255 | 14.11.2026 | 24000 | CCK-MP-HAUL-DT151 -STRUCT-AXLES-HUBRH | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Replace Hoses Hoist System | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 40 | 90010105 | B1 | 1000083453 | 14.11.2026 | 24000 | CCK-MP-HAUL-DT151 -HYDSYS-HDHLF-HSTHO | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Replace Brake System Hoses | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 90 | 90010129 | B4 | 1000083459 | 14.11.2026 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BRHLF-BRHOS | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Brake Cooling System Hoses | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 60 | 90010130 | B1 | 1000083460 | 14.11.2026 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BRHLF-CBRHO | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Motor Lube Axle Hoses | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 4 | 90026944 | B1 | 1000272022 | 01.12.2026 | 12000 | CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYM01 | 7400 | 84301 | 9530
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl AOC Fan Motor Rear | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 6 | 90002376 | B1 | 1000026475 | 01.12.2026 | 12000 | CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYM02 | 7400 | 84301 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Operators Seat | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 6 | 90002395 | B1 | 1000026501 | 15.12.2026 | 15000 | CCK-MP-HAUL-DT151 -STRUCT-CABIN-SEATS | 7400 | 84253 | 12192
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Engine Midlife Complete | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 62 | 90015886 | B1 | 1000156044 | 30.12.2026 | 12000 | CCK-MP-HAUL-DT151 -ENGINE | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Axle Lube Hyd Pump | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 4 | 90010102 | B1 | 1000083451 | 20.01.2027 | 24000 | CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYPUM | 7400 | 84301 | 20384
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Auto Lube Pump | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 3 | 90002391 | B1 | 1000285792 | 29.01.2027 | 8000 | CCK-MP-HAUL-DT151 -GRSYST-ALBPP | 7400 | 84301 | 13358
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Drive Shaft Transmission | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 16 | 90017195 | B1 | 1000154981 | 14.02.2027 | 18000 | CCK-MP-HAUL-DT151 -FDRSYS-DRSHT | 7400 | 84301 | 9530
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Replace Steering System Hoses | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 106 | 90010133 | B1 | 1000083463 | 28.04.2027 | 15000 | CCK-MP-HAUL-DT151 -STRSYS-STHLF-STRHO | 7400 | 84253 | 9530
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Steering Hyd Oil Cooler | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 9 | 90012866 | B2 | 1000107006 | 30.04.2027 | 15000 | CCK-MP-HAUL-DT151 -STRSYS-STOCO | 7400 | 84253 | 9530
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Cyl Suspension LHF | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 84 | 90002408 | B1 | 1000067605 | 31.05.2027 | 28000 | CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYLF | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Cyl Suspension LHR | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 39 | 90002409 | B1 | 1000026509 | 31.05.2027 | 28000 | CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYLR | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Cyl Suspension RHR | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 39 | 90002409 | B2 | 1000026510 | 31.05.2027 | 28000 | CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYRR | 7400 | 84253 | 21869
793F | Onsite Shut | Haul | Fortescue | DT151 | DT151 Repl Cyl Suspension RHF | 2026-12-15 | 2026-12-22 | 180 hrs | FY27 | 84 | 90002408 | B2 | 1000067607 | 04.06.2027 | 28000 | CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYRF | 7400 | 84253 | 21869
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 - POWER PACK MODULES & MAJOR COMPONENTS | 2027-01-04 | 2027-01-15 | 276 hrs | FY27
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Power Pack Module 1 | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 190 | 90026630 | B1 | 1000267760 | 02.11.2026 | 16000 | CCK-MP-EXCV-EX8107-FRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Boom RH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 76 | 90015686 | B1 | 1000162219 | 13.04.2027 | 16000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-BMCYR | 7200 | 46126 | 10939
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Stick LH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 48 | 90015687 | B1 | 1000162220 | 06.03.2027 | 16000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-STCLL | 7200 | 46126 | 11696
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Stick RH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 48 | 90015687 | B1 | 1000162221 | 16.03.2027 | 16000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-STCLR | 7200 | 46126 | 11696
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Mono-Block C/Over - Repl | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 12 | 90015706 | B1 | 1000162255 | 07.12.2026 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HMBCO | 7200 | 46126 | 9438
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Valve-Travel Mtrs - Repl | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 72 | 90015707 | B1 | 1000162256 | 19.01.2027 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HVVTM | 7200 | 46126 | 8376
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel RHF | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 14 | 90015697 | B1 | 1000162243 | 08.11.2026 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMRF | 7200 | 46126 | 10005
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel RHR | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 14 | 90015697 | B1 | 1000162244 | 08.11.2026 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMRR | 7200 | 46126 | 10005
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hydraulic Tank Module | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 108 | 90026632 | B1 | 1000268042 | 02.11.2026 | 24000 | CCK-MP-EXCV-EX8107-HYDSYS-HDTNK | 7200 | 46126 | 21919
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Power Pack Module 2 | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 190 | 90026631 | B1 | 1000267768 | 02.11.2026 | 16000 | CCK-MP-EXCV-EX8107-RRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Operators Seat | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 17 | 90015711 | B1 | 1000162261 | 29.09.2026 | 8000 | CCK-MP-EXCV-EX8107-STRUCT-CABIN-SEATO | 7200 | 46126 | 6810
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Track Tension Tuning - Adjust | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 9 | 90020546 | B1 | 1000213055 | 28.07.2026 | 6 Monthly | CCK-MP-EXCV-EX8107-UNDERC
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Track Idler LH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 38 | 90015669 | B1 | 1000162275 | 14.08.2026 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRL-IDLLH | 500 | 2526 | 1073
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Track Assembly LH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 36 | 90015666 | B1 | 1000162273 | 14.08.2026 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRL-TRKLH | 500 | 2526 | 1073
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Track Idler RH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 38 | 90015669 | B1 | 1000162288 | 14.08.2026 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRR-IDLRH | 500 | 2526 | 1073
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Track Hyd Tensioner RH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 28 | 90015670 | B1 | 1000162186 | 30.05.2027 | 16000 | CCK-MP-EXCV-EX8107-UNDERC-TKFRR-TENSR | 7200 | 46126 | 10005
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Track Assembly RH | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 36 | 90015666 | B1 | 1000162286 | 14.08.2026 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRR-TRKRH | 500 | 2526 | 1073
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Valve pressure Limiting Y4 | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 4 | 90019283 | B1 | 1000196179 | 17.09.2026 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDVLV-VVPLV | 7200 | 46126 | 7049
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Elec Harness Cabin-Cabinet | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 1 | 90019317 | B1 | 1000196706 | 13.11.2026 | 24000 | CCK-MP-EXCV-EX8107-ELCTLV-MCCEL-MCCHR | 7200 | 46126 | 21919
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Grease Block & Injectors Repl | 2027-01-04 | 2027-01-15 | 276 hrs | FY27 | 84 | 90020364 | B1 | 1000213678 | 13.04.2027 | 16000 | CCK-MP-EXCV-EX8107-GRSYST-GRINJ | 7200 | 41901 | 548
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 - ENGINE & MAJOR COMPONENTS | 2027-01-04 | 2027-01-14 | 240 hrs | FY27
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Sepura SCC Microphone | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 0.5 | 90028997 | B1 | 1000289593 | 12.12.2026 | 12 Monthly | CCK-MP-LOAD-WL004 -COMMUN-RADIO
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Pump Brake | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 4 | 90002774 | B2 | 1000030479 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -BRKSYS-BRPMP | 3100 | 64006 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Electrical Harness | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 108 | 90002153 | B2 | 1000110136 | 11.06.2026 | 16000 | CCK-MP-LOAD-WL004 -ELCTLV-HARNS | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Replace High Risk Hoses | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 8 | 90021799 | B2 | 1000291756 | 05.06.2026 | 8000 | CCK-MP-LOAD-WL004 -ENGINE | 3100 | 64006 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Engine Cat C32 | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 304 | 90015812 | B1 | 1000291748 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -ENGINE | 3100 | 64006 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Radiator Engine Cooling | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 72 | 90002751 | B2 | 1000030453 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -ENGINE-COSYS-RADTR | 3700 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Wash Engine Pre Cleaners | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 2 | 90017388 | B1 | 1000291750 | 05.06.2026 | 8000 | CCK-MP-LOAD-WL004 -ENGINE-INTEX-AIRFL
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Overhaul Auto Lubrication System | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 96 | 90002794 | B2 | 1000030492 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -GRSYST | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Bucket Cyl Tilt LH | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 28 | 90002788 | B2 | 1000080566 | 16.06.2025 | 12000 | CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-BUCYL | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Bucket Cyl Tilt RH | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 28 | 90002789 | B2 | 1000080567 | 16.06.2025 | 12000 | CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-BUCYR | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Cyl Lift LH | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 56 | 90002786 | B2 | 1000131360 | 30.11.2026 | 10000 | CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-HCYLL | 3100 | 64003 | 7915
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Hyd Oil Cooler | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 6 | 90002792 | B2 | 1000030491 | 21.03.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HDOCO | 3100 | 64003 | 16510
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Reseal Tank Hyd | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 24 | 90021393 | B1 | 1000224273 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HDTNK | 3100 | 64003 | 64003
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Hyd Motor Axle Cooler Front | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 2 | 90002791 | B2 | 1000030489 | 06.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HYDMT-HYM02 | 3100 | 63992 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Hyd Motor Axle Cooler Rear | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 2 | 90002791 | B2 | 1000030490 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HYDMT-HYM03 | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Hyd Pump Implement | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 24 | 90002782 | B2 | 1000030485 | 06.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP01 | 3100 | 63992 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Hyd Pump Pilot & Axle Cooling | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 4 | 90002783 | B2 | 1000030486 | 06.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP02 | 3100 | 63992 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Hyd Pump Steering & Fan | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 24 | 90002784 | B2 | 1000030487 | 01.02.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP03 | 3100 | 63992 | 16994
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Replace Steering Hoses | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 72 | 90010157 | B1 | 1000081923 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -STRSYS-STHLF | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Pumps Steering Centre | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 8 | 90002776 | B2 | 1000030480 | 06.06.2026 | 16000 | CCK-MP-LOAD-WL004 -STRSYS-STPMP | 3100 | 63992 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Cyl Steering LH | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 22 | 90002781 | B2 | 1000030483 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -STRSYS-STRCY-STCYL | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Overhaul Air Conditioner | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 48 | 90017479 | B1 | 1000291755 | 05.06.2026 | 8000 | CCK-MP-LOAD-WL004 -STRUCT-CABIN-AIRCN | 3100 | 64003 | 8684
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Transmission | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 167 | 90002758 | B2 | 1000030457 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -TRNSYS-TRANS | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Transmission Oil Cooler | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 6 | 90002761 | B2 | 1000030460 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -TRNSYS-TROLC | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Torque Converter | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 144 | 90002759 | B2 | 1000030458 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -TRNSYS-TRQUE | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Drive Shaft Centre Bearing | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 8 | 90002766 | B2 | 1000030465 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-CTRBR | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Drive Shaft TCon to Trans | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 4 | 90002762 | B2 | 1000030461 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT01 | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Drive Shaft Trans to Rr Diff | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 8 | 90002763 | B2 | 1000030462 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT02 | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Shaft Ctr Bearing to Fr Diff | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 8 | 90002765 | B2 | 1000030464 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT04 | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Steering Hyd Oil Cooler | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 36 | 90002779 | B2 | 1000030482 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -STRSYS-STOCO | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Pump Hyd Impliment Tandem | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 24 | 90005123 | B2 | 1000074966 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP06 | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Replace Hydraulic Hoses | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 96 | 90010159 | B1 | 1000081926 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HDHLF-HYDHO | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Replace Pilot Hoses | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 72 | 90010160 | B1 | 1000081928 | 05.06.2026 | 16000 | CCK-MP-LOAD-WL004 -HYDSYS-HDHLF-PILHO | 3100 | 64003 | 15676
993K | Onsite Shut | Ancillary | Fortescue | WL004 | WL004 Repl Operators Seat | 2027-01-04 | 2027-01-14 | 240 hrs | FY27 | 2 | 90002797 | B2 | 1000110129 | 20.02.2027 | 6000 | CCK-MP-LOAD-WL004 -STRUCT-CABIN-SEATS | 3100 | 64003 | 4210
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 - ARTIC & MAJOR COMPONENTS | 2027-01-04 | 2027-01-14 | 246 hrs | FY27
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Brake Pump | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90002712 | B2 | 1000138163 | 02.09.2027 | 20000 | CCK-MP-LOAD-WL7103-BRKSYS-BRPMP-BRP01 | 6000 | 72865 | 16267
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Brake Cooling Pump | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 8 | 90002713 | B2 | 1000138164 | 26.02.2028 | 10000 | CCK-MP-LOAD-WL7103-BRKSYS-BRPMP-BRP02 | 6000 | 72865 | 12306
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Engine Thermostats | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 6 | 90021139 | B1 | 1000222750 | 06.05.2027 | 5000 | CCK-MP-LOAD-WL7103-ENGINE-COSYS-THERM | 6000 | 72865 | 2571
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Axle Shaft Pos1 | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90012242 | B2 | 1000138199 | 10.03.2027 | 32000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP1 | 6000 | 72865 | 30393
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Axle Shaft Pos2 | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90012242 | B2 | 1000138200 | 10.03.2027 | 32000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP2 | 6000 | 72865 | 30393
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Axle Shaft Pos3 | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90012242 | B2 | 1000138201 | 10.03.2027 | 32000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP3 | 6000 | 72865 | 30393
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Axle Shaft Pos4 | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90012242 | B2 | 1000138202 | 10.03.2027 | 32000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP4 | 6000 | 72865 | 30393
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Final Drive & Brake LHF | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 83 | 90002710 | B2 | 1000138159 | 21.09.2027 | 16000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR01 | 6000 | 72865 | 12069
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Final Drive & Brake RHR | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 83 | 90002710 | B2 | 1000138162 | 21.09.2027 | 16000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR04 | 6000 | 33806 | 33806
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Auto Lube Pump | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 6 | 90002737 | B2 | 1000138180 | 19.11.2027 | 10000 | CCK-MP-LOAD-WL7103-GRSYST-ALBPP | 6000 | 72865 | 15227
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Pilot Hyd Cooling Pump | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90002726 | B2 | 1000138176 | 20.11.2027 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP04 | 6000 | 72865 | 16811
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl STIC Steering Valve | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90026110 | B1 | 1000257374 | 14.07.2027 | 20000 | CCK-MP-LOAD-WL7103-STRSYS-STIPV | 6000 | 72865 | 16811
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Steering Cylinder LH | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 26 | 90002721 | B2 | 1000138171 | 25.07.2027 | 12000 | CCK-MP-LOAD-WL7103-STRSYS-STRCY-STCYL | 6000 | 72865 | 8691
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Service Air Conditioner | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 24 | 90021130 | B1 | 1000222742 | 06.05.2027 | 5000 | CCK-MP-LOAD-WL7103-STRUCT-CABIN-AIRCN | 6000 | 72865 | 12069
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Ohaul Articulation Point | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 360 | 90032991 | B1 | 1000329977 | 17.10.2027 | 16000 | CCK-MP-LOAD-WL7103-STRUCT-CHASS-ARTIC | 6000 | 72865 | 11776
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Front Drive Shaft | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 16 | 90033175 | B1 | 1000333569 | 14.07.2027 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT04 | 6000 | 72865 | 6385
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Shaft Rear PD To Cntr Brng | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 24 | 90033191 | B1 | 1000333571 | 14.07.2027 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT05 | 6000 | 72865 | 16811
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Fr Pump Drv Shaft Unis | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 8 | 90033190 | B1 | 1000333574 | 20.11.2027 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT06 | 6000 | 72865 | 5406
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Transmission | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 74 | 90002692 | B2 | 1000138143 | 15.10.2027 | 16000 | CCK-MP-LOAD-WL7103-TRNSYS-TRANS | 6000 | 72865 | 11793
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Transmission System Hoses | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 96 | 90026923 | B1 | 1000271661 | 27.03.2027 | 16000 | CCK-MP-LOAD-WL7103-TRNSYS-TRHLF-TRNHO | 6000 | 72865 | 14006
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Transmission Pump | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 12 | 90002694 | B2 | 1000138144 | 26.07.2027 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-TRPMP | 6000 | 72865 | 6666
994H | Onsite Shut | Ancillary | Fortescue | WL7103 | WL7103 Repl Artic Area Hyd Hosing | 2027-01-04 | 2027-01-14 | 246 hrs | FY27 | 6 | 90020831 | B1 | 1000321324 | 15.08.2026 | 8 Monthly | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-ARTHO
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 - ENGINE MODULE & MAJOR COMPONENTS | 2027-01-07 | 2027-01-16 | 222 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Cyl Steering LH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 16 | 90011350 | B1 | 1000094815 | 22.06.2026 | 15000 | CCK-MP-HAUL-DT761 -STRSYS-STRCY-STCYL | 6800 | 78336 | 16076
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Hyd Pump Steering & Brake | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 38 | 90019919 | B1 | 1000204741 | 30.09.2026 | 12000 | CCK-MP-HAUL-DT761 -STRSYS-STPMP | 6800 | 78336 | 10559
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Cyl Steering RH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 15 | 90011351 | B1 | 1000094816 | 03.10.2026 | 15000 | CCK-MP-HAUL-DT761 -STRSYS-STRCY-STCYR | 6800 | 78336 | 13970
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Valve Retard & Brake Treadle | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 5.5 | 90011345 | B1 | 1000094810 | 08.11.2026 | 25000 | CCK-MP-HAUL-DT761 -BRKSYS-BRVTR | 6800 | 78336 | 23353
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Engine Module | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 226 | 90011318 | B1 | 1000094784 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -ENGINE | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Grid Box Blower Motor LH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 10 | 90011331 | B1 | 1000094800 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -ELCTHV-HVGBM-GBMLH | 6800 | 78336 | 22645
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Wheel Motor LH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 83.5 | 90011335 | B1 | 1000094804 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -FDRSYS-WLMTR-WHMLH | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Wheel Motor RH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 83.5 | 90011336 | B1 | 1000094805 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -FDRSYS-WLMTR-WHMRH | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Replace Brake Cabinet Hoses | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126508 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -BRKSYS-BRHLF | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Replace Brake Cooling Hoses | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223881 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -BRKSYS-BRHLF | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Valve Flow Amplifier | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 13.5 | 90011348 | B1 | 1000094813 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -STRSYS-STVLV | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Cyl Hoist LH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 33 | 90011357 | B1 | 1000094822 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -HYDSYS-HOCYL-HCYLL | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Cyl Hoist RH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 33 | 90011358 | B1 | 1000094823 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -HYDSYS-HOCYL-HCYLR | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Drive Shaft | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 2 | 90011359 | B1 | 1000094824 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -HYDSYS-DRSHT | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Replace Pump Module Hosing | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 27 | 90021389 | B1 | 1000223905 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -HYDSYS-HDHLF | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Cyl Suspension LHR | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 50 | 90011367 | B1 | 1000094833 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -STRUCT-SUSPN-SCYLR | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Cyl Suspension RHR | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 50 | 90011368 | B1 | 1000094834 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -STRUCT-SUSPN-SCYRR | 6800 | 78336 | 23274
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Hub & Spindle LH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 60 | 90011363 | B1 | 1000094829 | 23.02.2027 | 18000 | CCK-MP-HAUL-DT761 -STRUCT-AXLES-HUBLH | 6800 | 78336 | 14347
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Hub & Spindle RH | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 60 | 90011364 | B1 | 1000094830 | 23.02.2027 | 18000 | CCK-MP-HAUL-DT761 -STRUCT-AXLES-HUBRH | 6800 | 78336 | 14347
930E | Onsite Shut | Haul | Fortescue | DT761 | DT761 Repl Cyl Suspension RHF | 2027-01-07 | 2027-01-16 | 222 hrs | FY27 | 112 | 90011366 | B1 | 1000094832 | 23.02.2027 | 18000 | CCK-MP-HAUL-DT761 -STRUCT-SUSPN-SCYRF | 6800 | 78336 | 14347
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 - ENGINE & MAJOR COMPONENTS | 2027-01-18 | 2027-01-27 | 222 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Service Air Conditioner 12M | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 18 | 90018230 | B1 | 1000174109 | 08.10.2026 | 12 Monthly | CCK-MP-HAUL-DT054 -STRUCT-CABIN-AIRCN | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Torque Converter | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 53 | 90002369 | B1 | 1000023588 | 04.11.2026 | 24000 | CCK-MP-HAUL-DT054 -TRNSYS-TRQUE | 7400 | 88111 | 22331
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Auto Lube Pump | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 3 | 90002391 | B1 | 1000285622 | 13.11.2026 | 8000 | CCK-MP-HAUL-DT054 -GRSYST-ALBPP | 7400 | 88111 | 5197
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Spiders Pump Drive Shaft | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 4 | 90002366 | B1 | 1000023584 | 06.12.2026 | 18000 | CCK-MP-HAUL-DT054 -ENGINE-PMPDR-DRSHT | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Transmission | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 39 | 90026996 | B2 | 1000271867 | 06.12.2026 | 18000 | CCK-MP-HAUL-DT054 -TRNSYS-TRANS | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Transmission Oil Cooler | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 12 | 90010097 | B1 | 1000082841 | 06.12.2026 | 18000 | CCK-MP-HAUL-DT054 -TRNSYS-TROLC | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Differential | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 66 | 90014504 | B1 | 1000023592 | 06.12.2026 | 18000 | CCK-MP-HAUL-DT054 -FDRSYS-DIFFL | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Replace Trans TCon System Hoses | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 20 | 90010099 | B1 | 1000090061 | 06.12.2026 | 18000 | CCK-MP-HAUL-DT054 -TRNSYS-TRANS-TRNHO | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Replace Hoses Differential System | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 5 | 90010101 | B1 | 1000090062 | 06.12.2026 | 18000 | CCK-MP-HAUL-DT054 -FDRSYS-DIFFL-DIFHO | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Pump Hoist & Brake | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 15 | 90002388 | B1 | 1000023613 | 28.12.2026 | 24000 | CCK-MP-HAUL-DT054 -HYDSYS-HOPMP | 7400 | 88111 | 21219
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Engine Cat C175-16 | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 137 | 90015881 | B1 | 1000155759 | 06.01.2027 | 24000 | CCK-MP-HAUL-DT054 -ENGINE | 7400 | 88111 | 21034
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Wheel Group Front LH | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 54 | 90017286 | B1 | 1000157105 | 28.02.2027 | 24000 | CCK-MP-HAUL-DT054 -STRUCT-AXLES-HUBLH | 7400 | 88111 | 18865
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Drive Shaft Transmission | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 16 | 90017195 | B1 | 1000155237 | 08.03.2027 | 18000 | CCK-MP-HAUL-DT054 -FDRSYS-DRSHT | 7400 | 88111 | 15675
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Pump Drive | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 39 | 90002365 | B1 | 1000023583 | 22.04.2027 | 24000 | CCK-MP-HAUL-DT054 -ENGINE-PMPDR | 7400 | 88111 | 18897
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Radiator Fan Hoses | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 11 | 90031073 | B1 | 1000307465 | 29.05.2027 | 12000 | CCK-MP-HAUL-DT054 -ENGINE-COSYS-RADTR | 7400 | 88111 | 31799
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl Motor Lube Axle Hoses | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 4 | 90026944 | B1 | 1000271942 | 29.05.2027 | 12000 | CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYM01 | 7400 | 88111 | 6138
793F | Onsite Shut | Haul | Fortescue | DT054 | DT054 Repl AOC Fan Motor Rear | 2027-01-18 | 2027-01-27 | 222 hrs | FY27 | 6 | 90002376 | B1 | 1000023596 | 29.05.2027 | 12000 | CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYM02 | 7400 | 88111 | 6138
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 - MINOR COMPONENTS | 2027-01-18 | 2027-01-29 | 276 hrs | FY27
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Boom Cyl | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 72 | 90029908 | B1 | 1000352459 | 13.08.2026 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HBMCL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Bucket Cyl | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 54 | 90029911 | B1 | 1000352461 | 13.08.2026 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HBKCL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Minestar Harness | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 43.5 | 90029998 | B1 | 1000352528 | 04.08.2026 | 4000 | CCK-MP-EXCV-EX7147-MANGMT-UMMMC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Pump Swing Combination | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 36 | 90030252 | B1 | 1000352533 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-SWPP1 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Bucket LH Lift | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 52 | 90029964 | B1 | 1000352507 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-BUCYL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Bucket RH Lift | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 52 | 90029967 | B1 | 1000352508 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-BUCYR | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Vlve Bank Module Quarter Life | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 12 | 90029987 | B1 | 1000352523 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDVLV-MCVLU | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Valve pressure Limiting Y4 | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 6 | 90030321 | B1 | 1000352541 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDVLV-VVPLV | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Accumulator Servo Hyd | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 3 | 90030487 | B1 | 1000352524 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDACC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Accumulator Ladder Hyd | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 4 | 90030685 | B1 | 1000352550 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDACC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Track Tensioning Hoses | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 24 | 90030538 | B1 | 1000352549 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HHTTL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hyd Hose Work Pumps to Valves | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 10.5 | 90030287 | B1 | 1000352538 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HWPVV | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hyd Hose Swing Pump Swing Motor | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 24 | 90030288 | B1 | 1000352539 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HSPSM | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hyd Hose Rotary Con to Valve Bank | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 24 | 90029912 | B1 | 1000352462 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HRCVV | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hoses Rotary Conn to Travel Motor | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 48 | 90029914 | B1 | 1000352463 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HRCTM | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Operators Seat | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 16 | 90029915 | B1 | 1000352464 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-STRUCT-CABIN-SEATO | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Auto Lube Pump P3 | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 2 | 90035351 | B1 | 1000358641 | 21.12.2026 | 10000 | CCK-MP-EXCV-EX7147-GRSYST-AUTLU-ALBP3 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Boom Module Quarter Life | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 48 | 90029992 | B1 | 1000352526 | 16.01.2027 | 10000 | CCK-MP-EXCV-EX7147-STRUCT-BOOMS | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Track Tension Tuning-Adjust | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 9 | 90029977 | B1 | 1000352515 | 28.01.2027 | 6 Monthly | CCK-MP-EXCV-EX7147-UNDERC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Grease Injectors | 2027-01-18 | 2027-01-29 | 276 hrs | FY27 | 84 | 90029932 | B1 | 1000352475 | 03.02.2027 | 10000 | CCK-MP-EXCV-EX7147-GRSYST-GRINJ | 6200 | 7547 | 7547
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 - POWER PACK MIDLIFE | 2027-01-20 | 2027-01-27 | 180 hrs | FY27
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Service Airconditioning System | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 12 | 90023281 | B1 | 1000295051 | 26.09.2026 | 12 Monthly | CCK-MP-DRLL-DR3133-STRUCT-CABIN-ACCOM | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Pump Air Lubrication | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 2 | 90021656 | B1 | 1000295031 | 07.11.2026 | 6000 | CCK-MP-DRLL-DR3133-AIRSYS-COMPR-PALUB | 5400 | 16251 | 10110
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Pump Water Injection | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 4 | 90021716 | B1 | 1000295033 | 07.11.2026 | 6000 | CCK-MP-DRLL-DR3133-DSTSUP-WTRPP | 5400 | 16251 | 1685
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Engine Valve Set | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 16 | 90021723 | B1 | 1000295054 | 07.11.2026 | 3000 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Power Pack Module Midlife | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 129 | 90026035 | B1 | 1000295055 | 07.11.2026 | 6000 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 1 | 90020876 | B1 | 1000295020 | 07.11.2026 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Pump Rod Thread Lube | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 2 | 90021715 | B1 | 1000295043 | 07.11.2026 | 6000 | CCK-MP-DRLL-DR3133-GRSYST-RTLPP | 5400 | 16251 | 10110
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Operators Seat | 2027-01-20 | 2027-01-27 | 180 hrs | FY27 | 4 | 90021702 | B1 | 1000295029 | 07.11.2026 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-CABIN-SEATS | 5400 | 16251 | 10110
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 - MAJOR COMPONENTS | 2027-01-21 | 2027-01-30 | 222 hrs | FY27
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Repl Engine Radiator | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 50 | 90011532 | B1 | 1000092959 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -ENGINE-COSYS-RADTR | 5100 | 58303 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Engine Aftercooler | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 6 | 90011533 | B1 | 1000093040 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -ENGINE-INTEX-AFTER | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Torque Converter | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 26 | 90011534 | B1 | 1000093041 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -TRNSYS-TRQUE | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Transmission | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 50 | 90011535 | B1 | 1000093042 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -TRNSYS-TRANS | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Repl Trans & TCon Charge Pump | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 4 | 90011536 | B1 | 1000093043 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -TRNSYS-TRPMP | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Drive Shaft | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 2 | 90011540 | B1 | 1000093047 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -FDRSYS-DRSHT | 5100 | 58303 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Differential | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 38 | 90011541 | B1 | 1000093048 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -FDRSYS-DIFFL | 5100 | 58303 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Pump Steering | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 6 | 90011552 | B1 | 1000093056 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STPMP | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Steering HMU | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 12 | 90011553 | B1 | 1000093057 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STHMU | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Steering Hoses & Lines | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 8 | 90011560 | B1 | 1000093064 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STHLF | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Hydraulic Oil Cooler | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 12 | 90011563 | B1 | 1000093067 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -HYDSYS-HDOCO | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Pump Hoist Lines | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 8 | 90011562 | B1 | 1000093066 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -HYDSYS-HDHLF | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Refurbish A Frame | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 36 | 90011568 | B1 | 1000093071 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-CHASS-AFRME | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Tag Link | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 6 | 90011569 | B1 | 1000093072 | 06.11.2026 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-CHASS-TAGLK | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 HP Grease Gun, Hose & Burst Sleeve | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 4 | 90022836 | B1 | 1000238750 | 04.12.2026 | 12 Monthly | CCK-MP-SUPP-SV220 -GRSYST-ALHLF | 5100 | 58259 | 58259
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Repl Bulk Grease Tank Breather | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 1 | 90022533 | B1 | 1000236909 | 30.12.2026 | 6 Monthly | CCK-MP-SUPP-SV220 -GRSYST-GRTNK | 5100 | 58259 | 58259
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Auto Lube Pump | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 2 | 90011565 | B1 | 1000093069 | 03.07.2026 | 9000 | CCK-MP-SUPP-SV220 -GRSYST-ALBPP | 5100 | 58259 | 8034
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Repl Sepura SCC Microphone | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289611 | 04.02.2027 | 12 Monthly | CCK-MP-SUPP-SV220 -COMMUN-RADIO | 5100 | 58303 | 58303
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Repl Pump Brake Charge & Cooling | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 6 | 90037883 | B1 | 1000379414 | 07.03.2027 | 9000 | CCK-MP-SUPP-SV220 -BRKSYS-BRPMP | 5100 | 58303 | 23399
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Final Drive LH | 2027-01-21 | 2027-01-30 | 222 hrs | FY27 | 50 | 90011542 | B1 | 1000093049 | 29.04.2027 | 18000 | CCK-MP-SUPP-SV220 -FDRSYS-FDRVE-FDRLH | 5100 | 58303 | 13500
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 - ENGINE MODULE & MAJOR COMPONENTS | 2027-02-04 | 2027-02-13 | 222 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Engine Module | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 226 | 90011318 | B1 | 1000094996 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -ENGINE | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Grid Box Blower Motor LH | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 10 | 90011331 | B1 | 1000095012 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -ELCTHV-HVGBM-GBMLH | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Wheel Motor LH | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 83.5 | 90011335 | B1 | 1000095016 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -FDRSYS-WLMTR-WHMLH | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Wheel Motor RH | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 83.5 | 90011336 | B1 | 1000095017 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -FDRSYS-WLMTR-WHMRH | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Valve Retard & Brake Treadle | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 5.5 | 90011345 | B1 | 1000095022 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -BRKSYS-BRVTR | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Replace Brake Cooling Hoses | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223885 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -BRKSYS-BRHLF | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Replace Brake Cabinet Hoses | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126512 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -BRKSYS-BRHLF | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Valve Flow Amplifier | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 13.5 | 90011348 | B1 | 1000095025 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -STRSYS-STVLV | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Cyl Hoist LH | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 33 | 90011357 | B1 | 1000095034 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -HYDSYS-HOCYL-HCYLL | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Cyl Hoist RH | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 33 | 90011358 | B1 | 1000095035 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -HYDSYS-HOCYL-HCYLR | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Drive Shaft | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 2 | 90011359 | B1 | 1000095036 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -HYDSYS-DRSHT | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Replace Pump Module Hosing | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 27 | 90021389 | B1 | 1000223909 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -HYDSYS-HDHLF | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Cyl Suspension LHR | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 50 | 90011367 | B1 | 1000095045 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -STRUCT-SUSPN-SCYLR | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Cyl Suspension RHR | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 50 | 90011368 | B1 | 1000095046 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -STRUCT-SUSPN-SCYRR | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Brake Dual Relay Valves | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223765 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -BRKSYS-BRVRL | 6800 | 78429 | 23008
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Air Con Service & Overhaul | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 36 | 90013265 | B1 | 1000110634 | 24.12.2026 | 12 Monthly | CCK-MP-HAUL-DT765 -STRUCT-CABIN-AIRCN | 6800 | 78429 | 78429
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Brake Accumulator Front | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 11 | 90011338 | B1 | 1000095019 | 21.01.2027 | 25000 | CCK-MP-HAUL-DT765 -BRKSYS-BRACC-BACCF | 6800 | 78429 | 22047
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Auto Lube Pump | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095037 | 13.02.2027 | 8000 | CCK-MP-HAUL-DT765 -GRSYST-ALBPP | 6800 | 78429 | 13600
930E | Onsite Shut | Haul | Fortescue | DT765 | DT765 Repl Hyd Pump Steering & Brake | 2027-02-04 | 2027-02-13 | 222 hrs | FY27 | 38 | 90019919 | B1 | 1000204745 | 20.02.2027 | 12000 | CCK-MP-HAUL-DT765 -STRSYS-STPMP | 6800 | 78429 | 4626
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 - BOOM & MAST MODULES & POWER PACK MIDLIFE | 2027-02-09 | 2027-02-17 | 186 hrs | FY27
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 XLF Repl Main Feed Chain | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 16 | 90021711 | B1 | 1000305041 | 25.12.2026 | 2500 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | 5400 | 14356 | 943
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Service Airconditioning System | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 12 | 90023281 | B1 | 1000305067 | 08.01.2027 | 12 Monthly | CCK-MP-DRLL-DR3138-STRUCT-CABIN-ACCOM | 5400 | 14414 | 7858
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Pump Rod Thread Lube | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 2 | 90021715 | B1 | 1000305059 | 10.01.2027 | 6000 | CCK-MP-DRLL-DR3138-GRSYST-RTLPP | 5400 | 14414 | 2620
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Engine Valve Set | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 16 | 90021723 | B1 | 1000305070 | 30.01.2027 | 3000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Power Pack Module Midlife | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 129 | 90026035 | B1 | 1000305071 | 30.01.2027 | 6000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Boom Module Assembly | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 48 | 90022011 | B1 | 1000305050 | 30.01.2027 | 18000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BMASY | 5400 | 14414 | 14414
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Mast Beam Module | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 96 | 90020447 | B1 | 1000361316 | 30.01.2027 | 18000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-DMAST | 5400 | 14414 | 14414
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Pump Air Lubrication | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 2 | 90021656 | B1 | 1000305047 | 05.03.2027 | 6000 | CCK-MP-DRLL-DR3138-AIRSYS-COMPR-PALUB | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Pump Water Injection | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 4 | 90021716 | B1 | 1000305049 | 05.03.2027 | 6000 | CCK-MP-DRLL-DR3138-DSTSUP-WTRPP | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Operators Seat | 2027-02-09 | 2027-02-17 | 186 hrs | FY27 | 4 | 90021702 | B1 | 1000305045 | 05.03.2027 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-CABIN-SEATS | 5400 | 14414 | 7858
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 - WHEEL MOTORS & MAJOR COMPONENTS | 2027-03-04 | 2027-03-13 | 216 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Air Con Service & Overhaul | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 36 | 90013265 | B1 | 1000110632 | 07.01.2027 | 12 Monthly | CCK-MP-HAUL-DT763 -STRUCT-CABIN-AIRCN | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Wheel Motor LH | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 83.5 | 90011335 | B1 | 1000094910 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -FDRSYS-WLMTR-WHMLH | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Wheel Motor RH | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 83.5 | 90011336 | B1 | 1000094911 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -FDRSYS-WLMTR-WHMRH | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Valve Retard & Brake Treadle | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 5.5 | 90011345 | B1 | 1000094916 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -BRKSYS-BRVTR | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Replace Brake Cabinet Hoses | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126510 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -BRKSYS-BRHLF | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Valve Flow Amplifier | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 13.5 | 90011348 | B1 | 1000094919 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -STRSYS-STVLV | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Pump Hoist | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 12 | 90011355 | B1 | 1000094926 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -HYDSYS-HOPMP | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Cyl Hoist LH | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 33 | 90011357 | B1 | 1000094928 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -HYDSYS-HOCYL-HCYLL | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Cyl Hoist RH | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 33 | 90011358 | B1 | 1000094929 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -HYDSYS-HOCYL-HCYLR | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Drive Shaft | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 2 | 90011359 | B1 | 1000094930 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -HYDSYS-DRSHT | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Cyl Suspension LHR | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 50 | 90011367 | B1 | 1000094939 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -STRUCT-SUSPN-SCYLR | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Cyl Suspension RHR | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 50 | 90011368 | B1 | 1000094940 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -STRUCT-SUSPN-SCYRR | 6800 | 74143 | 21626
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Auto Lube Pump | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094931 | 11.02.2027 | 8000 | CCK-MP-HAUL-DT763 -GRSYST-ALBPP | 6800 | 74143 | 14657
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Hyd Pump Steering & Brake | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 38 | 90019919 | B1 | 1000204743 | 09.03.2027 | 12000 | CCK-MP-HAUL-DT763 -STRSYS-STPMP | 6800 | 74143 | 14657
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Pressure Reducing Valve | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204795 | 28.03.2027 | 12000 | CCK-MP-HAUL-DT763 -BRKSYS-BRVLV-VVPRV | 6800 | 74143 | 11011
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Cyl Suspension LHF | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 112 | 90011365 | B1 | 1000094937 | 22.04.2027 | 18000 | CCK-MP-HAUL-DT763 -STRUCT-SUSPN-SCYLF | 6800 | 74143 | 13238
930E | Onsite Shut | Haul | Fortescue | DT763 | DT763 Repl Grid Box Blower Motor LH | 2027-03-04 | 2027-03-13 | 216 hrs | FY27 | 10 | 90011331 | B1 | 1000094906 | 16.05.2027 | 25000 | CCK-MP-HAUL-DT763 -ELCTHV-HVGBM-GBMLH | 6800 | 74143 | 19790
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 - POWER PACK MODULE & COMPONENTS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Operators Seat | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 6 | 90011710 | B2 | 1000144815 | 16.12.2026 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-CABIN-SEATS | 6800 | 54883 | 16796
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 PV271 Hydraulic Tune | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 31.5 | 90017118 | B1 | 1000153015 | 12.01.2027 | 3000 | CCK-MP-DRLL-DR2110-HYDSYS | 6800 | 54883 | 22468
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Jack Leg NDE NCS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 8 | 90015956 | B1 | 1000144793 | 16.01.2027 | 15000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYLF | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Jack Leg DE NCS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 8 | 90015958 | B1 | 1000144795 | 16.01.2027 | 15000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYLR | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Pump Water Injection | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 2 | 90016011 | B1 | 1000144840 | 22.01.2027 | 5000 | CCK-MP-DRLL-DR2110-DSTSUP-WTRPP | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Tower Raise NCS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 8 | 90011666 | B1 | 1000233303 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TRCYL | 6800 | 54883 | 1949
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Tower Raise CS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 8 | 90011667 | B1 | 1000233302 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TRCYR | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Hyd Motor Fan Hyd Cooler | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 6 | 90011697 | B1 | 1000144782 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MFMCA | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Hyd Motor Screw Jack NCS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 1 | 90022221 | B1 | 1000232714 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MSJTL | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Hyd Motor Screw Jack CS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 1 | 90022221 | B1 | 1000232713 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MSJTR | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Sheaves & Cables | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 140 | 90029857 | B1 | 1000303754 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Tower Cylinders | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 58 | 90029866 | B1 | 1000303756 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Grbx Powerhead Midlife | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 6 | 90029861 | B1 | 1000303755 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-PWRHD | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Rod Support | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 20 | 90022208 | B1 | 1000232704 | 01.03.2027 | 10000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-RDSPT | 6800 | 54883 | 1072
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl ADS PTZ Camera & LIDAR | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 10 | 90029206 | B1 | 1000294202 | 02.03.2027 | 10000 | CCK-MP-DRLL-DR2110-ADSYST-ADSPR-HTCAM | 6800 | 54907 | 14238
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Power Pack Module | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 294 | 90029571 | B1 | 1000295326 | 15.03.2027 | 20000 | CCK-MP-DRLL-DR2110-ENGINE | 6800 | 54907 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Jack Leg NDE CS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 8 | 90015957 | B1 | 1000144794 | 29.03.2027 | 15000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYRF | 6800 | 54883 | 9679
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Counter Balance | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 1 | 90015976 | B1 | 1000144804 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVCNB | 6800 | 54883 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Diverter NCS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 4 | 90015977 | B1 | 1000144805 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDVL | 6800 | 54883 | 14238
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Diverter CS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 4 | 90015978 | B1 | 1000144806 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDVR | 6800 | 54883 | 14238
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Drill & Propel Control | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 6 | 90015979 | B1 | 1000144807 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDPC | 6800 | 54883 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Track Frame Module-NCS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 72 | 90022185 | B1 | 1000206435 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-TKFRL | 6800 | 54883 | 14238
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Track Frame Module CS | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 72 | 90022183 | B1 | 1000206453 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-TKFRR | 6800 | 54883 | 14238
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cabin ADS Components | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 31.5 | 90029189 | B1 | 1000294139 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-ADSYST-ADSHW-HMIJK | 6800 | 54907 | 54751
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl ADS Ace Cabinet Components | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 44.5 | 90029187 | B1 | 1000294138 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-ADSYST-ADSHW-CLXEN | 6800 | 54907 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl ADS Harnesses | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 131.5 | 90029210 | B1 | 1000294204 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-ADSYST-HARNC | 6800 | 54907 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl ADS IO Modules | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 4 | 90029208 | B1 | 1000294137 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-ADSYST-ADSHW-ARDIO | 6800 | 54907 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Deck ADS Elec Hardware | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 9.5 | 90029190 | B1 | 1000294136 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-ADSYST-ADSHW-ADSMF | 6800 | 54907 | 54751
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl ADS 3D sensor | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 1 | 90029207 | B1 | 1000294201 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-ADSYST-ADSPR | 6800 | 54907 | 54751
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Control Harnesses Chassis | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 39 | 90029952 | B1 | 1000303816 | 20.04.2027 | 20000 | CCK-MP-DRLL-DR2110-ELCTLV-HARNS-HARCO | 6800 | 54907 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl LiDAR Sensor | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 24 | 90023242 | B1 | 1000240813 | 02.05.2027 | 12 Monthly | CCK-MP-DRLL-DR2110-ADSYST-ADSPR-LIDAR | 6800 | 54907 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Water & Fuel Tank Mounts | 2027-03-16 | 2027-03-24 | 186 hrs | FY27 | 20 | 90017453 | B1 | 1000160344 | 07.06.2027 | 6000 | CCK-MP-DRLL-DR2110-ENGINE-FUSYS-FULTK | 6800 | 54883 | 5228
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 - MAJOR COMPONENTS | 2027-03-18 | 2027-03-27 | 222 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl 50A Aux Cabinet Relays | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 0.5 | 90029280 | B1 | 1000292267 | 20.02.2027 | 25000 | CCK-MP-HAUL-DT764 -ELCTLV-AUCAB | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Air Con Service & Overhaul | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 36 | 90013265 | B1 | 1000110633 | 31.12.2026 | 12 Monthly | CCK-MP-HAUL-DT764 -STRUCT-CABIN-AIRCN | 6800 | 75315 | 9805
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Grid Box Blower Motor RH | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 10 | 90011332 | B1 | 1000094960 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -ELCTHV-HVGBM-GBMRH | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Valve Retard & Brake Treadle | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 5.5 | 90011345 | B1 | 1000094969 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -BRKSYS-BRVTR | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Replace Brake Cabinet Hoses | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126511 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -BRKSYS-BRHLF | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Replace Brake Cooling Hoses | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223884 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -BRKSYS-BRHLF | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Valve Flow Amplifier | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 13.5 | 90011348 | B1 | 1000094972 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -STRSYS-STVLV | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Drive Shaft | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 2 | 90011359 | B1 | 1000094983 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -HYDSYS-DRSHT | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Replace Pump Module Hosing | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 27 | 90021389 | B1 | 1000223908 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -HYDSYS-HDHLF | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Cyl Suspension LHR | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 50 | 90011367 | B1 | 1000094992 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -STRUCT-SUSPN-SCYLR | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Cyl Suspension RHR | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 50 | 90011368 | B1 | 1000094993 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -STRUCT-SUSPN-SCYRR | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Replace Operator Cabin Dash Bulbs | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 2 | 90017265 | B1 | 1000158229 | 02.05.2027 | 3000 | CCK-MP-HAUL-DT764 -STRUCT-CABIN | 6800 | 75315 | 21117
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Pressure Reducing Valve | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204796 | 03.05.2027 | 12000 | CCK-MP-HAUL-DT764 -BRKSYS-BRVLV-VVPRV | 6800 | 75315 | 6502
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Cyl Hoist LH | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 33 | 90011357 | B1 | 1000094981 | 13.05.2027 | 25000 | CCK-MP-HAUL-DT764 -HYDSYS-HOCYL-HCYLL | 6800 | 75315 | 19467
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Cyl Hoist RH | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 33 | 90011358 | B1 | 1000094982 | 13.05.2027 | 25000 | CCK-MP-HAUL-DT764 -HYDSYS-HOCYL-HCYLR | 6800 | 75315 | 19467
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Hub & Spindle LH | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 60 | 90011363 | B1 | 1000094988 | 13.06.2027 | 18000 | CCK-MP-HAUL-DT764 -STRUCT-AXLES-HUBLH | 6800 | 75315 | 11874
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Cyl Suspension LHF | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 112 | 90011365 | B1 | 1000094990 | 13.06.2027 | 18000 | CCK-MP-HAUL-DT764 -STRUCT-SUSPN-SCYLF | 6800 | 75315 | 11874
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Cyl Suspension RHF | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 112 | 90011366 | B1 | 1000094991 | 13.06.2027 | 18000 | CCK-MP-HAUL-DT764 -STRUCT-SUSPN-SCYRF | 6800 | 75315 | 11874
930E | Onsite Shut | Haul | Fortescue | DT764 | DT764 Repl Auto Lube Pump | 2027-03-18 | 2027-03-27 | 222 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094984 | 21.06.2027 | 8000 | CCK-MP-HAUL-DT764 -GRSYST-ALBPP | 6800 | 75315 | 9805
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 - MAJOR COMPONENTS | 2027-03-24 | 2027-04-03 | 240 hrs | FY27
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Cyl Blade Lift LH | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 16 | 90000287 | B1 | 1000255598 | 18.01.2027 | 9000 | CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BLCYL | 5000 | 54263 | 6767
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Steer Clutch & Brake Assm LH | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 28 | 90000313 | B2 | 1000091100 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -BRKSTR-SCABL | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Steer Clutch & Brake Assm RH | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 28 | 90000313 | B2 | 1000091101 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -BRKSTR-SCABR | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Rad Engine Cooling SN 529 UP | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 48 | 90000307 | B2 | 1000091092 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -ENGINE-COSYS-RADTR | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Aftercooler Engine | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 8 | 90010841 | B1 | 1000108392 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -ENGINE-INTEX-AFTER | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Final Drive RH | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 28 | 90000312 | B2 | 1000091099 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -FDRSYS-FDRRH | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Hyd Oil Cooler | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 10 | 90009664 | B2 | 1000091107 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -HYDSYS-HDOCO | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Ovhl Hydraulic & Fuel Tank | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 48 | 90010842 | B1 | 1000108394 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -HYDSYS-HDTNK | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Equaliser Bar | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 110 | 90002097 | B1 | 1000108396 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -STRUCT-CHASS-EQUAL | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Minor Overhaul Track Frame LH | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 98 | 90002098 | B1 | 1000108397 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -STRUCT-UNDER-TKFRL | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Minor Overhaul Track Frame RH | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 98 | 90010766 | B1 | 1000108399 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -STRUCT-UNDER-TKFRR | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Drive Shaft | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 6 | 90033296 | B1 | 1000334101 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -TRNSYS | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Transmission | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 48 | 90000308 | B2 | 1000091095 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -TRNSYS-TRANS | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Pump Trans & TCon Charge | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 10 | 90000302 | B2 | 1000091097 | 05.03.2027 | 18000 | CCK-MP-DOZR-DZ170 -TRNSYS-TRPMP | 5000 | 54263 | 15137
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Repl Hyd Pump Implement | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 10 | 90000301 | B2 | 1000091102 | 30.04.2027 | 9000 | CCK-MP-DOZR-DZ170 -HYDSYS-HYDPP-HYIPP | 5000 | 54263 | 5339
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Engine Midlife Complete | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 103 | 90015859 | B1 | 1000160121 | 01.05.2027 | 9000 | CCK-MP-DOZR-DZ170 -ENGINE | 5000 | 54263 | 5287
D10T | Onsite Shut | Ancillary | Fortescue | DZ170 | DZ170 Major Service Air Conditioner | 2027-03-24 | 2027-04-03 | 240 hrs | FY27 | 24 | 90017469 | B1 | 1000196613 | 01.05.2027 | 9000 | CCK-MP-DOZR-DZ170 -STRUCT-CABIN-AIRCN | 5000 | 54263 | 15137
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 - BOOM MODULE & POWERPACK MIDLIFE | 2027-03-31 | 2027-04-08 | 186 hrs | FY27
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Pump Rod Thread Lube | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 2 | 90021715 | B1 | 1000295739 | 02.12.2026 | 6000 | CCK-MP-DRLL-DR3137-GRSYST-RTLPP | 5400 | 14232 | 2559
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 XLF Repl Main Feed Chain | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 16 | 90021711 | B1 | 1000295721 | 26.05.2027 | 2500 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHH | 5400 | 14232 | 1011
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 1 | 90020876 | B1 | 1000295716 | 29.01.2027 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Pump Air Lubrication | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 2 | 90021656 | B1 | 1000295727 | 19.02.2027 | 6000 | CCK-MP-DRLL-DR3137-AIRSYS-COMPR-PALUB | 5400 | 14232 | 8625
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Operators Seat | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 4 | 90021702 | B1 | 1000295725 | 19.02.2027 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-CABIN-SEATS | 5400 | 14232 | 4056
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Pressure Safety Valve Cert | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 3 | 90021719 | B1 | 1000295740 | 20.02.2027 | 48 Monthly | CCK-MP-DRLL-DR3137-AIRSYS-COMPR-VCSRL | 5400 | 14232 | 2835
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Engine Valve Set | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 16 | 90021723 | B1 | 1000295750 | 17.03.2027 | 3000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Power Pack Module Midlife | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 129 | 90026035 | B1 | 1000295751 | 17.03.2027 | 6000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Boom Module Assembly | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 48 | 90022011 | B1 | 1000295730 | 17.03.2027 | 18000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BMASY | 5400 | 14232 | 14232
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Mast Beam Module | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 96 | 90020447 | B1 | 1000361309 | 17.03.2027 | 18000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-DMAST | 5400 | 14232 | 14232
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Pump Water Injection | 2027-03-31 | 2027-04-08 | 186 hrs | FY27 | 4 | 90021716 | B1 | 1000295729 | 11.05.2027 | 6000 | CCK-MP-DRLL-DR3137-DSTSUP-WTRPP | 5400 | 14232 | 7384
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2027-04-06 | 2027-04-15 | 216 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Drive Shaft Transmission | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 16 | 90017195 | B1 | 1000154993 | 18.01.2027 | 18000 | CCK-MP-HAUL-DT160 -FDRSYS-DRSHT | 7400 | 85085 | 18309
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Axle Lube Hyd Pump | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 4 | 90010102 | B1 | 1000154019 | 18.01.2027 | 24000 | CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYPUM | 7400 | 85085 | 20607
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Wheel End RH | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 58.5 | 90007352 | B1 | 1000027067 | 13.02.2027 | 24000 | CCK-MP-HAUL-DT160 -FDRSYS-FDRVE-FDRRH | 7400 | 85085 | 20089
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Cyl Hoist LH | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 33 | 90015130 | B1 | 1000128607 | 02.03.2027 | 28000 | CCK-MP-HAUL-DT160 -HYDSYS-HOCYL-HCYLL | 7400 | 85085 | 23750
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Cyl Hoist RH | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 33 | 90015131 | B1 | 1000128608 | 02.03.2027 | 28000 | CCK-MP-HAUL-DT160 -HYDSYS-HOCYL-HCYLR | 7400 | 85085 | 23750
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Differential | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 66 | 90014504 | B1 | 1000027065 | 07.03.2027 | 18000 | CCK-MP-HAUL-DT160 -FDRSYS-DIFFL | 7400 | 85085 | 13594
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Replace Hoses Differential System | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 5 | 90010101 | B2 | 1000091576 | 09.03.2027 | 18000 | CCK-MP-HAUL-DT160 -FDRSYS-DIFFL-DIFHO | 7400 | 85085 | 57996
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Brake Oil Cooler Front | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 13 | 90010109 | B1 | 1000091565 | 12.03.2027 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BROCO-BROCF | 7400 | 85085 | 19556
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Brake Oil Cooler Rear | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 13 | 90010108 | B1 | 1000091564 | 12.03.2027 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BROCO-BROCR | 7400 | 85085 | 19556
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Engine Midlife Complete | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 62 | 90015886 | B1 | 1000156074 | 28.03.2027 | 12000 | CCK-MP-HAUL-DT160 -ENGINE | 7400 | 85085 | 7211
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Radiator Fan Hoses | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 11 | 90031073 | B1 | 1000307547 | 28.03.2027 | 12000 | CCK-MP-HAUL-DT160 -ENGINE-COSYS-RADTR | 7400 | 85085 | 32389
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl Motor Lube Axle Hoses | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 4 | 90026944 | B1 | 1000272034 | 28.03.2027 | 12000 | CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYM01 | 7400 | 85085 | 7211
793F | Onsite Shut | Haul | Fortescue | DT160 | DT160 Repl AOC Fan Motor Rear | 2027-04-06 | 2027-04-15 | 216 hrs | FY27 | 6 | 90002376 | B1 | 1000027069 | 28.03.2027 | 12000 | CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYM02 | 7400 | 85085 | 7211
PV271 | Onsite Shut | Drills | Fortescue | DR2104 | DR2104 - MAST MODULE & POWER PACK MIDLIFE | 2027-04-07 | 2027-04-15 | 186 hrs | FY27
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 - MAJOR COMPONENTS | 2027-04-12 | 2027-04-21 | 222 hrs | FY27
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Cabin Refurbishment | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 12 | 90010318 | B2 | 1000090944 | 23.01.2027 | 28000 | CCK-MP-GRDR-GR122 -STRUCT-CABIN | 5200 | 68036 | 25631
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Brake Slack Adjuster LH | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 1 | 90002641 | B2 | 1000090942 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -BRKSYS-SLACK-SLACL | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Brake Slack Adjuster Rear | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 1 | 90002641 | B2 | 1000090943 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -BRKSYS-SLACK-SLACR | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Electrical Harness | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 48 | 90010000 | B2 | 1000090936 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -ELCTLV-HARNS | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Radiator Engine Cooling | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 98 | 90002618 | B3 | 1000090897 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -ENGINE-COSYS-RADTR | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Rear Axel Assembly | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 128 | 90030396 | B1 | 1000303521 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -FDRSYS-DIFFL | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Drive Shaft Trans to Rr Diff | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 6 | 90033262 | B1 | 1000333912 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -FDRSYS-DRSHT-SHT01 | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Drive Shaft TCon to Trans | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 4 | 90033265 | B1 | 1000333914 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -FDRSYS-DRSHT-SHT02 | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Overhaul Auto Lubrication System | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 2 | 90002660 | B2 | 1000090923 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -GRSYST-ALBPP | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Brake System Hoses | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 48 | 90009997 | B2 | 1000090937 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-BRKS | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Hydraulic System Hoses | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 48 | 90009998 | B2 | 1000090938 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-HYDSH | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Power Train System Hoses | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 48 | 90009999 | B2 | 1000090939 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-PWTRN | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Steering System Hoses | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 48 | 90009996 | B2 | 1000090940 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-STRNG | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Hyd Fan Motor | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 6 | 90002651 | B2 | 1000090922 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HDMOT-MOT03 | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Hyd Pump Brake & Fan | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 8 | 90002648 | B2 | 1000090918 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-FANPP | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Hyd Pump Secondary Steering | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 6 | 90002645 | B2 | 1000090915 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -STRSYS-STEMG-SESPP | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Axle Assembly Front | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 98 | 90002666 | B1 | 1000180098 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-AXLES | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Operators Seat | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 4 | 90002663 | B2 | 1000090924 | 04.04.2027 | 7000 | CCK-MP-GRDR-GR122 -STRUCT-CABIN-SEATS | 5200 | 68036 | 924
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Blade Mounting Bracket LH | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 48 | 90002671 | B2 | 1000090929 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CIRCL-BLMBL | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Blade Mounting Bracket RH | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 48 | 90002671 | B2 | 1000090930 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CIRCL-BLMBR | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Overhaul Drawbar Group | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 72 | 90002668 | B2 | 1000090928 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-DRWBR | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Transmission | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 146 | 90002631 | B2 | 1000090900 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -TRNSYS-TRANS | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Pump Transmission | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 8 | 90002633 | B2 | 1000090902 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -TRNSYS-TRPMP | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Torque Converter | 2027-04-12 | 2027-04-21 | 222 hrs | FY27 | 98 | 90002630 | B2 | 1000090899 | 04.04.2027 | 14000 | CCK-MP-GRDR-GR122 -TRNSYS-TRQUE | 5200 | 68036 | 10615
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 - ENGINE MODULE & MAJOR COMPONENTS | 2027-04-15 | 2027-04-24 | 222 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Grid Box Blower Motor LH | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 10 | 90011331 | B1 | 1000095118 | 18.11.2026 | 25000 | CCK-MP-HAUL-DT767 -ELCTHV-HVGBM-GBMLH | 6800 | 74312 | 22671
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Brake Accumulator Front | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 11 | 90011338 | B1 | 1000095125 | 17.03.2027 | 25000 | CCK-MP-HAUL-DT767 -BRKSYS-BRACC-BACCF | 6800 | 74312 | 20457
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Brake Accumulator Rear | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 11 | 90011339 | B1 | 1000095126 | 17.03.2027 | 25000 | CCK-MP-HAUL-DT767 -BRKSYS-BRACC-BACCR | 6800 | 74312 | 20457
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Air Con Service & Overhaul | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 36 | 90013265 | B1 | 1000110636 | 05.04.2027 | 12 Monthly | CCK-MP-HAUL-DT767 -STRUCT-CABIN-AIRCN | 6800 | 74312 | 74312
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Pressure Reducing Valve | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204799 | 06.04.2027 | 12000 | CCK-MP-HAUL-DT767 -BRKSYS-BRVLV-VVPRV | 6800 | 74312 | 9613
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Engine Module | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 226 | 90011318 | B1 | 1000095102 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -ENGINE | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Grid Box Blower Motor RH | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 10 | 90011332 | B1 | 1000095119 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -ELCTHV-HVGBM-GBMRH | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Wheel Motor LH | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 83.5 | 90011335 | B1 | 1000095122 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -FDRSYS-WLMTR-WHMLH | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Valve Retard & Brake Treadle | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 5.5 | 90011345 | B1 | 1000095128 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -BRKSYS-BRVTR | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Replace Brake Cooling Hoses | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223887 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -BRKSYS-BRHLF | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Replace Brake Cabinet Hoses | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126514 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -BRKSYS-BRHLF | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Valve Flow Amplifier | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 13.5 | 90011348 | B1 | 1000095131 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -STRSYS-STVLV | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Pump Hoist | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 12 | 90011355 | B1 | 1000095138 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -HYDSYS-HOPMP | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Cyl Hoist LH | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 33 | 90011357 | B1 | 1000095140 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -HYDSYS-HOCYL-HCYLL | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Cyl Hoist RH | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 33 | 90011358 | B1 | 1000095141 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -HYDSYS-HOCYL-HCYLR | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Drive Shaft | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 2 | 90011359 | B1 | 1000095142 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -HYDSYS-DRSHT | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Replace Pump Module Hosing | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 27 | 90021389 | B1 | 1000223911 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -HYDSYS-HDHLF | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Cyl Suspension LHR | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 50 | 90011367 | B1 | 1000095151 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -STRUCT-SUSPN-SCYLR | 6800 | 74312 | 19669
930E | Onsite Shut | Haul | Fortescue | DT767 | DT767 Repl Cyl Suspension RHR | 2027-04-15 | 2027-04-24 | 222 hrs | FY27 | 50 | 90011368 | B1 | 1000095152 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -STRUCT-SUSPN-SCYRR | 6800 | 74312 | 19669
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 - ENGINE & MAJOR COMPONENTS | 2027-04-19 | 2027-05-05 | 384 hrs | FY27
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Engine Cat C27 | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 82 | 90018843 | B1 | 1000225424 | 11.04.2027 | 18000 | CCK-MP-DOZR-DZ8234-ENGINE | 5000 | 26641 | 14816
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Wash Engine Pre Cleaners | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 2 | 90018848 | B1 | 1000225428 | 11.04.2027 | 9000 | CCK-MP-DOZR-DZ8234-ENGINE-INTEX-AIRFL
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Air Conditioner Overhaul | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 48 | 90018854 | B1 | 1000225399 | 11.04.2027 | 18000 | CCK-MP-DOZR-DZ8234-STRUCT-CABIN-AIRCN | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Torque Converter | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 60 | 90018826 | B1 | 1000225453 | 14.04.2027 | 18000 | CCK-MP-DOZR-DZ8234-TRNSYS-TRQUE | 5000 | 26629 | 14816
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Cyl Blade Lift LH | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 14 | 90031953 | B1 | 1000225389 | 29.04.2027 | 9000 | CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BLCYL | 5000 | 26629 | 5612
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Operators Seat | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 8 | 90018835 | B1 | 1000225444 | 05.05.2027 | 6000 | CCK-MP-DOZR-DZ8234-STRUCT-CABIN-SEATS | 5000 | 26629 | 8321
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Cyl Blade Lift RH | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 14 | 90031953 | B1 | 1000225390 | 29.07.2027 | 9000 | CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BLCYR | 5000 | 26629 | 4367
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Steer Clutch & Brake Assm LH | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 32 | 90018830 | B1 | 1000225450 | 27.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-BRKSTR-SCABL | 5000 | 26641 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Steer Clutch & Brake Assm RH | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 32 | 90018830 | B1 | 1000225451 | 27.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-BRKSTR-SCABR | 5000 | 26641 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Radiator Engine Cooling | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 48 | 90018824 | B1 | 1000225446 | 27.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-ENGINE-COSYS-RADTR | 5000 | 26641 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Aftercooler Engine | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 8 | 90018836 | B1 | 1000225386 | 27.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-ENGINE-INTEX-AFTER | 5000 | 26641 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Drive Shaft | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 6 | 90033311 | B1 | 1000334043 | 27.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-TRNSYS-DRSHT | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Final Drive LH | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 48 | 90018829 | B1 | 1000225434 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-FDRSYS-FDRLH | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Final Drive RH | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 48 | 90018829 | B1 | 1000225435 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-FDRSYS-FDRRH | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Hyd Oil Cooler | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 10 | 90018834 | B1 | 1000225440 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-HYDSYS-HDOCO | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Reseal Hydraulic Tank | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 48 | 90018838 | B1 | 1000225441 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-HYDSYS-HDTNK | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Hyd Pump Cooling Fan | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 16 | 90018832 | B1 | 1000225438 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYFPP | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Pump Hyd Implement 1 | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 10 | 90018831 | B1 | 1000225439 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYIP1 | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Equaliser Bar | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 96 | 90018840 | B1 | 1000225433 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-STRUCT-CHASS-EQUAL | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Transmission | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 48 | 90018827 | B1 | 1000225454 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-TRNSYS-TRANS | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Pump Trans & TCon Charge | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 10 | 90018828 | B1 | 1000225452 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-TRNSYS-TRPMP | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Pump Hyd Variable Charge | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 4 | 90021620 | B1 | 1000226598 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYDVC | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Pump Hyd Implement 2 | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 6 | 90021621 | B1 | 1000226708 | 28.08.2027 | 18000 | CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYIP2 | 5000 | 26629 | 12967
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Actuator Brake HaulX Shield | 2027-04-19 | 2027-05-05 | 384 hrs | FY27 | 50 | 90033499 | B1 | 1000337808 | 20.09.2027 | 14000 | CCK-MP-DOZR-DZ8234-MANGMT-CASYS-ACTBK
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 - FRONT CORNERS & WHEEL MOTORS | 2027-05-04 | 2027-05-13 | 222 hrs | FY27
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Hub & Spindle LH | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 60 | 90011363 | B1 | 1000095359 | 11.04.2027 | 18000 | CCK-MP-HAUL-DT771 -STRUCT-AXLES-HUBLH | 6800 | 84423 | 13551
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Hub & Spindle RH | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 60 | 90011364 | B1 | 1000095360 | 11.04.2027 | 18000 | CCK-MP-HAUL-DT771 -STRUCT-AXLES-HUBRH | 6800 | 84423 | 13551
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Cyl Suspension LHF | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 112 | 90011365 | B1 | 1000095361 | 11.04.2027 | 18000 | CCK-MP-HAUL-DT771 -STRUCT-SUSPN-SCYLF | 6800 | 84423 | 13551
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Cyl Suspension RHF | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 112 | 90011366 | B1 | 1000095362 | 11.04.2027 | 18000 | CCK-MP-HAUL-DT771 -STRUCT-SUSPN-SCYRF | 6800 | 84423 | 13551
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Wheel Motor LH | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 83.5 | 90011335 | B1 | 1000095334 | 12.05.2027 | 25000 | CCK-MP-HAUL-DT771 -FDRSYS-WLMTR-WHMLH | 6800 | 84423 | 19973
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Wheel Motor RH | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 83.5 | 90011336 | B1 | 1000095335 | 12.05.2027 | 25000 | CCK-MP-HAUL-DT771 -FDRSYS-WLMTR-WHMRH | 6800 | 84423 | 19973
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Cyl Steering RH | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 15 | 90011351 | B1 | 1000095346 | 16.06.2027 | 15000 | CCK-MP-HAUL-DT771 -STRSYS-STRCY-STCYR | 6800 | 84423 | 9331
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Repl Hyd Pump Steering & Brake | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 38 | 90019919 | B1 | 1000204751 | 14.07.2027 | 12000 | CCK-MP-HAUL-DT771 -STRSYS-STPMP | 6800 | 84423 | 18016
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Replace Operator Cabin Dash Bulbs | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 2 | 90017265 | B1 | 1000158236 | 14.07.2027 | 3000 | CCK-MP-HAUL-DT771 -STRUCT-CABIN | 6800 | 84423 | 84423
930E | Onsite Shut | Haul | Fortescue | DT771 | DT771 Engine Midlife Complete | 2027-05-04 | 2027-05-13 | 222 hrs | FY27 | 76 | 90028571 | B1 | 1000285529 | 24.07.2027 | 12500 | CCK-MP-HAUL-DT771 -ENGINE | 6800 | 84423 | 5826
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 - MAST MODULE, ENG MIDLIFE & COMPONENTS | 2027-05-06 | 2027-05-14 | 186 hrs | FY27
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS LiDAR | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 4 | 90029065 | B1 | 1000290890 | 11.10.2026 | 5000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR-LIDAR | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack LHR DE NCS | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 24 | 90020204 | B1 | 1000213908 | 22.11.2026 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYLR | 6800 | 34249 | 1270
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Mast Cables | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 64 | 90030334 | B1 | 1000302720 | 16.12.2026 | 2500 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Pump Water Inj | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 4 | 90031899 | B1 | 1000315424 | 07.01.2027 | 7500 | CCK-MP-DRLL-DR2112-DSTSUP-WTRPP | 6800 | 34249 | 11324
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack LHF NDE NCS | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 24 | 90020196 | B1 | 1000213907 | 16.01.2027 | 6000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYLF | 6800 | 34249 | 2981
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Hyd Pump Auxiliary | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 4 | 90020236 | B1 | 1000213927 | 20.01.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-PPAUX | 6800 | 34249 | 11048
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Washdown Pump | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 8 | 90030681 | B1 | 1000305723 | 25.01.2027 | 7500 | CCK-MP-DRLL-DR2112-DSTSUP-WSHPP | 6800 | 34249 | 9455
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos8 | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 8 | 90020188 | B1 | 1000213636 | 26.01.2027 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF08 | 6800 | 34249 | 15978
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Drive Shaft Pump Drive | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 12 | 90028862 | B1 | 1000287873 | 07.03.2027 | 5000 | CCK-MP-DRLL-DR2112-HYDSYS-PMPDG-DRSHT | 6800 | 34249 | 2406
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Overhaul 24M Air Conditioner | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 24 | 90028299 | B1 | 1000283156 | 27.03.2027 | 24 Monthly | CCK-MP-DRLL-DR2112-STRUCT-CABIN-AIRCN | 6800 | 34249 | 34249
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Adjust 3750Hr Valve Set | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 24 | 90020402 | B1 | 1000213713 | 30.03.2027 | 3750 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Engine Midlife Complete | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 54 | 90029233 | B1 | 1000293338 | 30.03.2027 | 7500 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Hyd Motor Propel NCS | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 12 | 90020190 | B1 | 1000213900 | 26.04.2027 | 20000 | CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-MPRPL | 6800 | 34249 | 14251
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Hyd Motor Propel CS | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 12 | 90020190 | B1 | 1000213901 | 26.04.2027 | 20000 | CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-MPRPR | 6800 | 34249 | 34249
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Mast Module | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 384 | 90020218 | B1 | 1000302723 | 26.04.2027 | 40000 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS Harnesses | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 43.5 | 90029073 | B1 | 1000290891 | 26.04.2027 | 20000 | CCK-MP-DRLL-DR2112-ADSYST-HARNC | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Mast ADS Hardware | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 49 | 90029071 | B1 | 1000290880 | 26.04.2027 | 20000 | CCK-MP-DRLL-DR2112-ADSYST-ADSHW | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Equaliser Bar TRL | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 32 | 90030390 | B1 | 1000303369 | 27.04.2027 | 40000 | CCK-MP-DRLL-DR2112-STRUCT-UNDER-EQUAL | 6800 | 34230 | 34230
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS Field Instruments | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 7.5 | 90029064 | B1 | 1000290885 | 28.06.2027 | 20000 | CCK-MP-DRLL-DR2112-ADSYST-ADSIS | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cabin ADS Components | 2027-05-06 | 2027-05-14 | 186 hrs | FY27 | 58.5 | 90029058 | B1 | 1000290884 | 28.06.2027 | 20000 | CCK-MP-DRLL-DR2112-ADSYST-ADSHW-HMIJK | 6800 | 34252 | 34252
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 - MAJOR COMPONENTS | 2027-05-15 | 2027-05-26 | 276 hrs | FY27
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Idler Track LH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 18 | 90027507 | B1 | 1000297003 | 19.02.2027 | 1500 | CCK-MP-EXCV-EX7125-STRUCT-TKFRL-IDLLH | 490 | 1211 | 1211
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Idler Track RH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 18 | 90027507 | B1 | 1000297014 | 19.02.2027 | 1500 | CCK-MP-EXCV-EX7125-STRUCT-TKFRR-IDLRH | 490 | 1211 | 1211
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Sprocket LH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 24 | 90027486 | B1 | 1000297011 | 19.02.2027 | 1500 | CCK-MP-EXCV-EX7125-TRAVEL-SPRKL | 490 | 1211 | 1211
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Sprocket RH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 24 | 90027486 | B1 | 1000297022 | 19.02.2027 | 1500 | CCK-MP-EXCV-EX7125-TRAVEL-SPRKR | 490 | 1211 | 1211
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Batteries | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 4 | 90027525 | B1 | 1000296989 | 04.04.2027 | 10000 | CCK-MP-EXCV-EX7125-ELCTLV-CHARG-BATTY | 6900 | 18815 | 5438
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Fan Engine Cool RH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 18 | 90027505 | B1 | 1000296958 | 22.04.2027 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-FMECR | 6900 | 18844 | 12979
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Oil Cooler Rear | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 48 | 90027500 | B1 | 1000296950 | 29.04.2027 | 24000 | CCK-MP-EXCV-EX7125-HYDSYS-HDOCO-OCHYR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Rotary Joint | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 48 | 90027501 | B1 | 1000296951 | 29.04.2027 | 24000 | CCK-MP-EXCV-EX7125-HYDSYS-ROTRY | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Final Drive LH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 144 | 90027485 | B1 | 1000296924 | 29.04.2027 | 24000 | CCK-MP-EXCV-EX7125-TRAVEL-FDRLH | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Final Drive RH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 144 | 90027485 | B1 | 1000296925 | 29.04.2027 | 24000 | CCK-MP-EXCV-EX7125-TRAVEL-FDRRH | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic System Tune Up | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 24 | 90017865 | B1 | 1000296998 | 13.05.2027 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Fan Drive Eng Cooling Hose | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 36 | 90027564 | B1 | 1000296968 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-FDECH | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Fan Drive Hyd Cooling Hoses | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 36 | 90027565 | B1 | 1000296969 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-FDHCH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hydraulic Cooling Circ Hoses | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 36 | 90031704 | B1 | 1000296970 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-HCCHH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Rotor to Drive Motor Hoses | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 40 | 90027570 | B1 | 1000296975 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-RCDMH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Rotor & Logic Valve Hp Hoses | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 36 | 90027571 | B1 | 1000296976 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-RCLVH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Servo Hoses Cascade to Bulkhead | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 16 | 90027572 | B1 | 1000296977 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SHBLK | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Servo Hoses Cascade to Trvl Valve | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 12 | 90027575 | B1 | 1000296979 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SHTRV | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 2nd Speed Trvl Brake Release Hose | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 10 | 90027559 | B1 | 1000296965 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SSTBR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Swing Motor Case Drain Hoses | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 12 | 90027577 | B1 | 1000296981 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SWMCD | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Travel Motor Case Drain Hoses | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 10 | 90027578 | B1 | 1000296982 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-TMCDH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Track Tensioning Hoses | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 3 | 90027579 | B1 | 1000296983 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-TRTNH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel LHF | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000296959 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMLF | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel RHF | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000296961 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMRF | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel RHR | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000296962 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMRR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Replenish LH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 2 | 90027495 | B1 | 1000296941 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SRPPL | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Replenish RH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 2 | 90027495 | B1 | 1000296942 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SRPPR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Servo LH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 2 | 90027496 | B1 | 1000296939 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SVPPL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Servo RH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 2 | 90027496 | B1 | 1000296940 | 13.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SVPPR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Auto Lube Pump | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 6 | 90027592 | B1 | 1000296999 | 16.05.2027 | 6000 | CCK-MP-EXCV-EX7125-GRSYST-ALBPP | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Grease Control Valving | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 14 | 90027612 | B1 | 1000297000 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-GRSYST-ALCON
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Stick LH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 54 | 90027498 | B1 | 1000296945 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-STCLL | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Stick RH | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 54 | 90027498 | B1 | 1000296946 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-STCLR | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos1 | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 64 | 90027490 | B1 | 1000296931 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP1 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos2 | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 64 | 90027490 | B1 | 1000296932 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP2 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos3 | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 64 | 90027490 | B1 | 1000296933 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP3 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos4 | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 64 | 90027490 | B1 | 1000296934 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP4 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Pos1 & Pos2 | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 42 | 90027492 | B1 | 1000296935 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SP1P2 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Pos3 & Pos4 | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 42 | 90027492 | B1 | 1000296936 | 16.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SP3P4 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic Oil Replacement | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 12 | 90016793 | B1 | 1000296988 | 17.05.2027 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel LHR | 2027-05-15 | 2027-05-26 | 276 hrs | FY27 | 14 | 90027506 | B1 | 1000296960 | 25.05.2027 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMLR | 6900 | 18844 | 6369
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2027-05-25 | 2027-06-03 | 216 hrs | FY27
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Spider Trans Driveshaft | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 12 | 90017211 | B1 | 1000154974 | 06.03.2027 | 6000 | CCK-MP-HAUL-DT148 -FDRSYS-DRSHT-UNVSL | 7400 | 85451 | 1970
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Engine Midlife Complete | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 62 | 90015886 | B1 | 1000156026 | 23.04.2027 | 12000 | CCK-MP-HAUL-DT148 -ENGINE | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Radiator Engine Cooling | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 62 | 90031072 | B1 | 1000307526 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -ENGINE-COSYS-RADTR | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Pump Drive | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 39 | 90002365 | B1 | 1000026264 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -ENGINE-PMPDR | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Torque Converter | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 53 | 90002369 | B1 | 1000026269 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -TRNSYS-TRQUE | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Wheel End RH | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 58.5 | 90007352 | B1 | 1000026275 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -FDRSYS-FDRVE-FDRRH | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Motor Lube Axle Rear & Hoses | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 8 | 90026943 | B1 | 1000272015 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYM01 | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Axle Lube Hyd Pump | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 4 | 90010102 | B1 | 1000154014 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYPUM | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Overhaul Accumulator Brake LHF | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 11 | 90002378 | B1 | 1000026278 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BACCM-FRLFT | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Overhaul Accumulator Brake RHF | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 11 | 90002378 | B1 | 1000026279 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BACCM-FRRGT | 7400 | 85452 | 258
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Overhaul Accumulator Brake Rear | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 11 | 90002378 | B1 | 1000026280 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BACCM-BACCR | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Pump Brake Cooling | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 17 | 90002379 | B1 | 1000026281 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-HYFPP | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Overhaul Valve Control Brake | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 20 | 90002380 | B2 | 1000026282 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BRVLV | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Motor Brake Oil Cooling | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 3 | 90002381 | B1 | 1000026283 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BROCO-HYMO1 | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Hyd Pump Steering Main & Fan | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 17 | 90002383 | B1 | 1000026286 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -STRSYS-STPMP | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Steering HMU | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 8 | 90002384 | B1 | 1000026287 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -STRSYS-STHMU | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Ovhl Accumulator Steering Front | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 12 | 90002386 | B1 | 1000026290 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -STRSYS-STACC-SACCF | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Ovhl Accumulator Steering Middle | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 12 | 90002386 | B1 | 1000026291 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -STRSYS-STACC-SACCM | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Ovhl Accumulator Steering Rear | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 12 | 90002386 | B1 | 1000026292 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -STRSYS-STACC-SACCR | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Pump Hoist & Brake | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 15 | 90002388 | B1 | 1000026295 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -HYDSYS-HOPMP | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Rear Axle Linkages | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 113 | 90002396 | B1 | 1000026304 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -STRUCT-CHASS-AXLIK | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Wheel Group Front LH | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 54 | 90017286 | B1 | 1000157161 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -STRUCT-AXLES-HUBLH | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Repl Cyl Suspension RHF | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 84 | 90002408 | B2 | 1000067595 | 25.05.2027 | 28000 | CCK-MP-HAUL-DT148 -STRUCT-SUSPN-SCYRF | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Replace Brake System Hoses | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 90 | 90010129 | B4 | 1000091456 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BRHLF-BRHOS | 7400 | 85451 | 18023
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Replace Torque Conv System Hoses | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 12 | 90010100 | B2 | 1000091467 | 25.05.2027 | 24000 | CCK-MP-HAUL-DT148 -TRNSYS-TRQUE-TRQHO | 7400 | 85452 | 18024
793F | Onsite Shut | Haul | Fortescue | DT148 | DT148 Service Air Conditioner 12M | 2027-05-25 | 2027-06-03 | 216 hrs | FY27 | 18 | 90018230 | B1 | 1000174177 | 01.06.2027 | 12 Monthly | CCK-MP-HAUL-DT148 -STRUCT-CABIN-AIRCN | 7400 | 85451 | 18023
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 - ENGINE & MAJOR COMPONENTS | 2027-05-31 | 2027-06-09 | 222 hrs | FY27
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Axle Assembly Front | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 98 | 90002666 | B1 | 1000180099 | 15.11.2026 | 14000 | CCK-MP-GRDR-GR123 -STRUCT-AXLES | 5200 | 50884 | 6392
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Brake System Hoses | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 48 | 90009997 | B2 | 1000105662 | 22.02.2027 | 14000 | CCK-MP-GRDR-GR123 -BRKSYS-BRHLF | 5200 | 50884 | 10664
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Hydraulic System Hoses | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 48 | 90009998 | B2 | 1000105663 | 22.02.2027 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HDHLF-HYDSH | 5200 | 50884 | 10664
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Steering System Hoses | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 48 | 90009996 | B2 | 1000105665 | 22.02.2027 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HDHLF-STRNG | 5200 | 50884 | 10664
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Gearbox Circle Drive Front | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 14 | 90002672 | B2 | 1000105638 | 22.02.2027 | 14000 | CCK-MP-GRDR-GR123 -STRUCT-CIRCL-CDBXF | 5200 | 50884 | 10664
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Overhaul Drawbar Group | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 72 | 90002668 | B2 | 1000105635 | 22.02.2027 | 14000 | CCK-MP-GRDR-GR123 -STRUCT-DRWBR | 5200 | 50884 | 10664
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Operators Seat | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 4 | 90002663 | B2 | 1000105631 | 30.03.2027 | 7000 | CCK-MP-GRDR-GR123 -STRUCT-CABIN-SEATS | 5200 | 50884 | 6392
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Engine Cat C18 | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 310 | 90015771 | B1 | 1000290316 | 02.06.2027 | 14000 | CCK-MP-GRDR-GR123 -ENGINE | 5200 | 50884 | 9251
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Overhaul Air Condtioner System | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 48 | 90017475 | B1 | 1000290322 | 02.06.2027 | 14000 | CCK-MP-GRDR-GR123 -STRUCT-CABIN-AIRCN
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Blade Mounting Bracket LH | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 48 | 90002671 | B2 | 1000105636 | 27.07.2027 | 14000 | CCK-MP-GRDR-GR123 -STRUCT-CIRCL-BLMBL | 5200 | 50884 | 26071
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Blade Mounting Bracket RH | 2027-05-31 | 2027-06-09 | 222 hrs | FY27 | 48 | 90002671 | B2 | 1000105637 | 27.07.2027 | 14000 | CCK-MP-GRDR-GR123 -STRUCT-CIRCL-BLMBR | 5200 | 50884 | 26071
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2027-06-21 | 2027-06-30 | 222 hrs | FY27
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Drive Shaft Trans to Rr Diff | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 6 | 90033262 | B1 | 1000333908 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -FDRSYS-DRSHT-SHT01 | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Drive Shaft TCon to Trans | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 4 | 90033265 | B1 | 1000333910 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -FDRSYS-DRSHT-SHT02 | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Brake System Hoses | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 48 | 90009997 | B2 | 1000090876 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-BRKS | 5200 | 67029 | 10194
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Hydraulic System Hoses | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 48 | 90009998 | B2 | 1000090877 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-HYDSH | 5200 | 67029 | 10194
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Power Train System Hoses | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 48 | 90009999 | B2 | 1000090878 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-PWTRN | 5200 | 67029 | 10194
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Steering System Hoses | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 48 | 90009996 | B2 | 1000090879 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-STRNG | 5200 | 67029 | 10194
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Hyd Fan Motor | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 6 | 90002651 | B2 | 1000090861 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HDMOT-MOT03 | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Hyd Pump Brake & Fan | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 8 | 90002648 | B2 | 1000090857 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-FANPP | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Hyd Pump Implement | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 8 | 90002646 | B2 | 1000090855 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-HYIMP | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Hyd Pump Steering Main | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 8 | 90002647 | B2 | 1000090856 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-HYSTP | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Overhaul Drawbar Group | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 72 | 90002668 | B2 | 1000090867 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -STRUCT-DRWBR | 5200 | 67029 | 10194
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Transmission Oil Cooler | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 6 | 90002632 | B2 | 1000090840 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -TRNSYS-TROLC | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Pump Transmission | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 8 | 90002633 | B2 | 1000090841 | 04.05.2027 | 14000 | CCK-MP-GRDR-GR121 -TRNSYS-TRPMP | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Engine Midlife complete | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 72 | 90015782 | B1 | 1000290302 | 14.05.2027 | 7000 | CCK-MP-GRDR-GR121 -ENGINE | 5200 | 67029 | 5487
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Service Major Air Conditioner | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 24 | 90017472 | B1 | 1000290306 | 14.05.2027 | 7000 | CCK-MP-GRDR-GR121 -STRUCT-CABIN-AIRCN | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Service Brake LHF | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 52 | 90002640 | B2 | 1000090847 | 13.09.2027 | 14000 | CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBLF | 5200 | 67029 | 8307
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Rear Axel Assembly | 2027-06-21 | 2027-06-30 | 222 hrs | FY27 | 128 | 90030396 | B1 | 1000303437 | 13.09.2027 | 14000 | CCK-MP-GRDR-GR121 -FDRSYS-DIFFL | 5200 | 67029 | 8307
| Onsite Shut | All | Fortescue |  | FY28 - ONSITE SHUTDOWNS | 2027-07-01 | 2028-06-30 | 8760 hrs | FY28
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 - POWER PACK MODULE & MAJOR COMPONENTS | 2027-07-14 | 2027-07-22 | 186 hrs | FY28
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 EncoderHarness Cab to Aframe Repl | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 6 | 90036144 | B1 | 1000365254 | 19.04.2027 | 5000 | CCK-MP-DRLL-DR2111-ADSYST-HARNC | 6800 | 49417 | 4564
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cables & Hoses | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 100 | 90029843 | B1 | 1000303760 | 20.04.2027 | 5000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Water & Fuel Tank Mounts | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 20 | 90017453 | B1 | 1000160345 | 19.05.2027 | 6000 | CCK-MP-DRLL-DR2111-ENGINE-FUSYS-FULTK | 6800 | 49393 | 11797
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Power Pack Module | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 294 | 90029571 | B1 | 1000295330 | 24.05.2027 | 20000 | CCK-MP-DRLL-DR2111-ENGINE | 6800 | 49411 | 11797
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cooler Module Assembly | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 22 | 90011659 | B1 | 1000144866 | 24.05.2027 | 20000 | CCK-MP-DRLL-DR2111-COOLER | 6800 | 49417 | 11797
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Jack Leg DE CS | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 8 | 90015959 | B1 | 1000144881 | 09.06.2027 | 15000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYRR | 6800 | 49393 | 8373
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Auto Lube Pump | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 2 | 90016009 | B1 | 1000144923 | 17.06.2027 | 12000 | CCK-MP-DRLL-DR2111-GRSYST-ALBPP | 6800 | 49393 | 5207
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 24M Air Cond Rencool Overhaul | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 24 | 90018580 | B1 | 1000180990 | 12.07.2027 | 24 Monthly | CCK-MP-DRLL-DR2111-STRUCT-CABIN-AIRCN
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 24M Air Conditioner Overhaul | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 180 | 90018566 | B1 | 1000180541 | 12.07.2027 | 24 Monthly | CCK-MP-DRLL-DR2111-STRUCT-CABIN-AIRCN
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Jack Leg DE NCS | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 8 | 90015958 | B1 | 1000144880 | 15.07.2027 | 15000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYLR | 6800 | 49393 | 7634
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 PV271 Hydraulic Tune | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 31.5 | 90017118 | B1 | 1000153016 | 16.07.2027 | 3000 | CCK-MP-DRLL-DR2111-HYDSYS | 6800 | 49393 | 8364
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Counter Balance | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 1 | 90015976 | B1 | 1000144889 | 26.08.2027 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVCNB | 6800 | 49393 | 11797
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Rod Thread lube Pump | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 2 | 90016010 | B1 | 1000207194 | 26.08.2027 | 10000 | CCK-MP-DRLL-DR2111-GRSYST-RTLPP | 6800 | 49393 | 4564
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Pump Water Injection | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 2 | 90016011 | B1 | 1000144924 | 26.08.2027 | 5000 | CCK-MP-DRLL-DR2111-DSTSUP-WTRPP | 6800 | 49393 | 4564
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Operators Seat | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 6 | 90011710 | B2 | 1000144900 | 27.08.2027 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-CABIN-SEATS | 6800 | 49393 | 11797
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl LiDAR Sensor | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 24 | 90023242 | B1 | 1000240814 | 14.09.2027 | 12 Monthly | CCK-MP-DRLL-DR2111-ADSYST-ADSPR-LIDAR | 6800 | 49417 | 6939
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Control Harnesses Chassis | 2027-07-14 | 2027-07-22 | 186 hrs | FY28 | 39 | 90029952 | B1 | 1000303817 | 10.10.2027 | 20000 | CCK-MP-DRLL-DR2111-ELCTLV-HARNS-HARCO | 6800 | 49417 | 49417
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2027-08-09 | 2027-08-19 | 240 hrs | FY28
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Motor & Pump Axle Cooling | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 4 | 90002970 | B3 | 1000033597 | 14.05.2027 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HYDMT-HYM02 | 6300 | 69386 | 10327
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Transmission | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 167 | 90002944 | B3 | 1000033567 | 18.05.2027 | 15000 | CCK-MP-DOZR-WD006 -TRNSYS-TRANS | 6300 | 69386 | 10255
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Transmission Oil Cooler | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 6 | 90002945 | B3 | 1000033568 | 18.05.2027 | 15000 | CCK-MP-DOZR-WD006 -TRNSYS-TROLC | 6300 | 69386 | 10255
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Rear Differential | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 134 | 90002952 | B3 | 1000033575 | 18.05.2027 | 15000 | CCK-MP-DOZR-WD006 -FDRSYS-RRDIF | 6300 | 69386 | 10255
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Brake System Hoses | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 48 | 90013050 | B3 | 1000109644 | 18.05.2027 | 15000 | CCK-MP-DOZR-WD006 -BRKSYS-BRHLF | 6300 | 69386 | 10255
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Pump Steer Secondary | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 4 | 90002960 | B3 | 1000033586 | 18.05.2027 | 15000 | CCK-MP-DOZR-WD006 -STRSYS-STPMP-STP03 | 6300 | 69386 | 10255
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Hoses Steering System | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 48 | 90013051 | B3 | 1000109646 | 18.05.2027 | 15000 | CCK-MP-DOZR-WD006 -STRSYS-STHLF | 6300 | 69386 | 10255
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Sepura SCC Microphone | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 0.5 | 90028996 | B1 | 1000289580 | 16.08.2027 | 12 Monthly | CCK-MP-DOZR-WD006 -COMMUN-RADIO
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Pump Transmission | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 8 | 90002946 | B3 | 1000033569 | 01.09.2027 | 15000 | CCK-MP-DOZR-WD006 -TRNSYS-TRPMP | 6300 | 69386 | 8416
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Engine Midlife complete | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 84 | 90015811 | B1 | 1000286590 | 18.09.2027 | 11000 | CCK-MP-DOZR-WD006 -ENGINE | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Shaft Universals TC - Trans | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 3 | 90026669 | B1 | 1000268423 | 18.09.2027 | 11000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT01 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Shaft Universals Rear | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 6 | 90026666 | B1 | 1000268425 | 18.09.2027 | 11000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT02 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Shaft Universals Centre | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 6 | 90026668 | B1 | 1000268427 | 18.09.2027 | 11000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT03 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Shaft Universals Front | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 6 | 90026667 | B1 | 1000268429 | 18.09.2027 | 11000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT04 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Overhaul Airconditioner | 2027-08-09 | 2027-08-19 | 240 hrs | FY28 | 48 | 90013087 | B1 | 1000286592 | 18.09.2027 | 11000 | CCK-MP-DOZR-WD006 -STRUCT-CABIN-AIRCN | 6300 | 69386 | 4123
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 - SLEW BEARING, ATTACHMENTS & POWER PACK | 2027-08-25 | 2027-09-14 | 480 hrs | FY28
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Grease System Audit | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 36 | 90030748 | B1 | 1000232084 | 25.07.2027 | 5000 | CCK-MP-EXCV-EX7117-GRSYST-GRINJ | 7200 | 32281 | 7621
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Auto Lube Pump P3 | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 2 | 90035368 | B1 | 1000358742 | 01.08.2027 | 10000 | CCK-MP-EXCV-EX7117-GRSYST-AUTLU-ALBP3 | 7200 | 32281 | 2918
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Operators Seat | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 17 | 90030739 | B1 | 1000232069 | 01.08.2027 | 10000 | CCK-MP-EXCV-EX7117-STRUCT-CABIN-SEATO | 7200 | 32281 | 2918
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Accumulator Track Hyd LH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 3 | 90030729 | B1 | 1000232058 | 09.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDACC-HACCL | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Accumulator Track Hyd RH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 3 | 90030729 | B1 | 1000232059 | 09.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDACC-HACCR | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Ladder Raise Cyl | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 24 | 90030750 | B1 | 1000245085 | 09.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-LACYL | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Motor Swing Front | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 24 | 90030727 | B1 | 1000232041 | 09.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDMOT-SWMOF | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Motor Swing Rear | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 24 | 90030727 | B1 | 1000232040 | 09.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDMOT-SWMOR | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Gearbox Swing P1 | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 109 | 90030720 | B1 | 1000232022 | 09.08.2027 | 20000 | CCK-MP-EXCV-EX7117-SWGSYS-SWBOX-SGBPF | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Motor Travel RHF | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000232050 | 14.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDMOT-TRMRF | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Auto Lube Pump P1 | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 2 | 90035369 | B1 | 1000232073 | 15.08.2027 | 10000 | CCK-MP-EXCV-EX7117-GRSYST-AUTLU-ALBPP | 7200 | 32281 | 2607
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Motor Travel LHF | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000232048 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDMOT-TRMLF | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Motor Travel LHR | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000232049 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDMOT-TRMLR | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Motor Travel RHR | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000232051 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-HDMOT-TRMRR | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Track Idler LH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 36 | 90030740 | B1 | 1000232080 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRL-IDLLH | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Sprocket LH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 72 | 90030718 | B1 | 1000232076 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRL-SPRKL | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Track Hyd Tensioner LH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 74 | 90024277 | B1 | 1000232070 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRL-TENSL | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Track Assembly LH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 36 | 90030719 | B1 | 1000232077 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRL-TRKLH | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Track Idler RH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 36 | 90030740 | B1 | 1000232081 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRR-IDLRH | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Sprocket RH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 72 | 90030718 | B1 | 1000232078 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRR-SPRKR | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Track Hyd Tensioner RH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 74 | 90024277 | B1 | 1000232071 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRR-TENSL | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Track Assembly RH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 36 | 90030719 | B1 | 1000232079 | 18.08.2027 | 20000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRR-TRKRH | 7200 | 32281 | 12581
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Boom Module | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 276 | 90027376 | B1 | 1000279087 | 19.08.2027 | 40000 | CCK-MP-EXCV-EX7117-STRUCT-BOOMS | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Stick Assembly | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 332 | 90017828 | B2 | 1000232118 | 19.08.2027 | 40000 | CCK-MP-EXCV-EX7117-STRUCT-STICK | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Batteries | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 9 | 90017122 | B1 | 1000232126 | 24.08.2027 | 12 Monthly | CCK-MP-EXCV-EX7117-ELCTLV-CHARG-BATST | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Power Pack Module | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 172 | 90026482 | B1 | 1000279045 | 02.09.2027 | 20000 | CCK-MP-EXCV-EX7117-ENGINE | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Valve Bank Module | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 122 | 90027370 | B1 | 1000279081 | 02.09.2027 | 40000 | CCK-MP-EXCV-EX7117-HYDSYS-HDVLV-MCVLU | 7200 | 32281 | 2639
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Rotary Connection & Hoses | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 168 | 90030430 | B1 | 1000303742 | 02.09.2027 | 20000 | CCK-MP-EXCV-EX7117-HYDSYS-ROTRY | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Tank Module | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 72 | 90027374 | B1 | 1000279990 | 02.09.2027 | 20000 | CCK-MP-EXCV-EX7117-STRUCT-HDTNK | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Service Module | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 18 | 90030754 | B1 | 1000243455 | 02.09.2027 | 40000 | CCK-MP-EXCV-EX7117-STRUCT-SRVCT | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Slew Bearing | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 288 | 90030743 | B1 | 1000232072 | 02.09.2027 | 40000 | CCK-MP-EXCV-EX7117-UNDERC-SLEWB | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Final Drive LH | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 141 | 90030716 | B1 | 1000232020 | 02.09.2027 | 40000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRL-FDRLH | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Final Drive RH Side | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 141 | 90030716 | B1 | 1000232021 | 02.09.2027 | 40000 | CCK-MP-EXCV-EX7117-UNDERC-TKFRR-FDRRH | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Minestar Harness | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 43.5 | 90030746 | B1 | 1000281593 | 05.09.2027 | 5000 | CCK-MP-EXCV-EX7117-MANGMT-UMMMC | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Ovhl 24M Air Conditioner Sys1 Eng | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 49 | 90035445 | B1 | 1000359782 | 06.09.2027 | 24 Monthly | CCK-MP-EXCV-EX7117-STRUCT-CABIN-AIRC1
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Track Tension Tuning - Adjust | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 9 | 90020545 | B1 | 1000232125 | 12.09.2027 | 6 Monthly | CCK-MP-EXCV-EX7117-UNDERC | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Svc 12M Air Conditioner Sys2 Hyd | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 12 | 90035237 | B1 | 1000359783 | 20.02.2028 | 12 Monthly | CCK-MP-EXCV-EX7117-STRUCT-CABIN-AIRC2
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Grease Tank Level Valve | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 2 | 90015003 | B2 | 1000232088 | 08.03.2028 | 12 Monthly | CCK-MP-EXCV-EX7117-GRSYST-AUTLU-GRTNK | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 12M Hydraulic Service & Repairs | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 30 | 90014448 | B2 | 1000232086 | 10.03.2028 | 12 Monthly | CCK-MP-EXCV-EX7117-HYDSYS | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Track Tension Tuning - Adjust | 2027-08-25 | 2027-09-14 | 480 hrs | FY28 | 9 | 90020545 | B1 | 1000232125 | 10.03.2028 | 6 Monthly | CCK-MP-EXCV-EX7117-UNDERC | 7200 | 32281 | 32281
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 - ENGINE & MAJOR COMPONENTS | 2027-09-06 | 2027-09-15 | 222 hrs | FY28
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Engine Cat C18 | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 310 | 90015771 | B1 | 1000290260 | 07.08.2027 | 14000 | CCK-MP-GRDR-GR120 -ENGINE | 5200 | 60265 | 8767
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Overhaul Air Condtioner System | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 48 | 90017475 | B1 | 1000290266 | 07.08.2027 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-CABIN-AIRCN | 5200 | 60265 | 18931
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Brake Slack Adjuster LH | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 1 | 90002641 | B2 | 1000090820 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -BRKSYS-SLACK-SLACL | 5200 | 60265 | 8770
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Brake Slack Adjuster Rear | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 1 | 90002641 | B2 | 1000090821 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -BRKSYS-SLACK-SLACR | 5200 | 60265 | 8768
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Service Brake LHF | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 52 | 90002640 | B2 | 1000090786 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBLF | 5200 | 60265 | 8767
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Electrical Harness | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 48 | 90010000 | B2 | 1000090814 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -ELCTLV-HARNS | 5200 | 60265 | 8768
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Steering System Hoses | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 48 | 90009996 | B2 | 1000090818 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-STRNG | 5200 | 60265 | 8770
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Hyd Fan Motor | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 6 | 90002651 | B2 | 1000090800 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HDMOT-MOT03 | 5200 | 60265 | 8770
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Hyd Pump Differential Lock | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 8 | 90002649 | B2 | 1000090797 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-DIFFL | 5200 | 60265 | 8768
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Operators Seat | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 4 | 90002663 | B2 | 1000090802 | 11.08.2027 | 7000 | CCK-MP-GRDR-GR120 -STRUCT-CABIN-SEATS | 5200 | 60265 | 8768
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Overhaul Drawbar Group | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 72 | 90002668 | B2 | 1000090806 | 11.08.2027 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-DRWBR | 5200 | 60265 | 8767
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Torque Converter | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 98 | 90002630 | B2 | 1000090757 | 03.12.2027 | 14000 | CCK-MP-GRDR-GR120 -TRNSYS-TRQUE | 5200 | 60265 | 7142
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Service Brake RHR | 2027-09-06 | 2027-09-15 | 222 hrs | FY28 | 54 | 90004548 | B2 | 1000090789 | 10.12.2027 | 14000 | CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBRR | 5200 | 60265 | 7045
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 - ENGINE & MAJOR COMPONENTS | 2027-09-13 | 2027-09-19 | 144 hrs | FY28
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Operators Seat | 2027-09-13 | 2027-09-19 | 144 hrs | FY28 | 8 | 90000318 | B1 | 1000108439 | 13.08.2027 | 6000 | CCK-MP-DOZR-DZ174 -STRUCT-CABIN-SEATS | 5000 | 65414 | 534
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Engine Cat C27 | 2027-09-13 | 2027-09-19 | 144 hrs | FY28 | 114 | 90015849 | B1 | 1000160158 | 02.09.2027 | 18000 | CCK-MP-DOZR-DZ174 -ENGINE | 5000 | 65414 | 12899
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Overhaul Air Conditioner | 2027-09-13 | 2027-09-19 | 144 hrs | FY28 | 48 | 90017468 | B1 | 1000196627 | 02.09.2027 | 18000 | CCK-MP-DOZR-DZ174 -STRUCT-CABIN-AIRCN | 5000 | 65414 | 20488
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Fan Cooling Motor Hyd | 2027-09-13 | 2027-09-19 | 144 hrs | FY28 | 16 | 90002094 | B2 | 1000108438 | 27.09.2027 | 9000 | CCK-MP-DOZR-DZ174 -HYDSYS-HDCFM | 5000 | 65414 | 1172
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Drive Shaft Unis | 2027-09-13 | 2027-09-19 | 144 hrs | FY28 | 6 | 90033292 | B1 | 1000334110 | 15.12.2027 | 9000 | CCK-MP-DOZR-DZ174 -TRNSYS | 5000 | 65414 | 20488
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Cyl Blade Lift RH | 2027-09-13 | 2027-09-19 | 144 hrs | FY28 | 16 | 90000287 | B1 | 1000255631 | 30.03.2028 | 9000 | CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-BLCYR | 5000 | 65414 | 538
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Transmission | 2027-09-13 | 2027-09-19 | 144 hrs | FY28 | 48 | 90000308 | B2 | 1000091167 | 30.03.2028 | 18000 | CCK-MP-DOZR-DZ174 -TRNSYS-TRANS | 5000 | 65414 | 10038
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 - MAJOR COMPONENTS | 2027-09-18 | 2027-09-30 | 282 hrs | FY28
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Hose Boom Cyl | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 72 | 90029908 | B1 | 1000378369 | 19.07.2027 | 8000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HBMCL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Hose Stick Cyl | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 48 | 90029909 | B1 | 1000378370 | 19.07.2027 | 8000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HSTCL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Hose Bucket Cyl | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 54 | 90029911 | B1 | 1000378371 | 19.07.2027 | 8000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HBKCL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Minestar Harness | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 43.5 | 90029998 | B1 | 1000378437 | 19.07.2027 | 4000 | CCK-MP-EXCV-EX7153-MANGMT-UMMMC | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Boom Module Quarter Life | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 48 | 90029992 | B1 | 1000378435 | 18.09.2027 | 10000 | CCK-MP-EXCV-EX7153-STRUCT-BOOMS | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Track Tension Tuning-Adjust | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 9 | 90029977 | B1 | 1000378425 | 20.09.2027 | 6 Monthly | CCK-MP-EXCV-EX7153-UNDERC | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Pump Swing Combination | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 36 | 90030252 | B1 | 1000378442 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-SWPP1 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Bucket LH Lift | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 52 | 90029964 | B1 | 1000378417 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-BUCYL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Bucket RH Lift | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 52 | 90029967 | B1 | 1000378418 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-BUCYR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Vlve Bank Module Quarter Life | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 12 | 90029987 | B1 | 1000378432 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDVLV-MCVLU | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Valve pressure Limiting Y4 | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 6 | 90030321 | B1 | 1000378450 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDVLV-VVPLV | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Accumulator Servo Hyd | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 3 | 90030487 | B1 | 1000378433 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDACC-HACCS | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Accumulator Ladder Hyd | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 4 | 90030685 | B1 | 1000378459 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDACC-HACCB | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Track Tensioning Hoses | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 24 | 90030538 | B1 | 1000378458 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HHTTL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hyd Hose Work Pumps to Valves | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 10.5 | 90030287 | B1 | 1000378447 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HWPVV | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hyd Hose Swing Pump Swing Motor | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 24 | 90030288 | B1 | 1000378448 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HSPSM | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hyd Hose Rotary Con to Valve Bank | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 24 | 90029912 | B1 | 1000378372 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HRCVV | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hoses Rotary Conn to Travel Motor | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 48 | 90029914 | B1 | 1000378373 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HRCTM | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Operators Seat | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 16 | 90029915 | B1 | 1000378374 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-STRUCT-CABIN-SEATO | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl P1 Auto Lube Pump | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 2 | 90030312 | B1 | 1000378378 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-GRSYST-AUTLU-ALBPP | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl P3 Auto Lube Pump | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 2 | 90035351 | B1 | 1000378465 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-GRSYST-AUTLU-ALBP3 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Grease Injectors | 2027-09-18 | 2027-09-30 | 282 hrs | FY28 | 84 | 90029932 | B1 | 1000378385 | 14.11.2027 | 10000 | CCK-MP-EXCV-EX7153-GRSYST-GRINJ | 6200 | 2136 | 2136
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2027-09-21 | 2027-09-30 | 216 hrs | FY28
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Service Air Conditioner 12M | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 18 | 90018230 | B1 | 1000174185 | 26.08.2027 | 12 Monthly | CCK-MP-HAUL-DT159 -STRUCT-CABIN-AIRCN | 7400 | 90235 | 41100
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Radiator Engine Cooling | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 62 | 90031072 | B1 | 1000307544 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -ENGINE-COSYS-RADTR | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Pump Drive | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 39 | 90002365 | B1 | 1000026990 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -ENGINE-PMPDR | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Torque Converter | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 53 | 90002369 | B1 | 1000026995 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -TRNSYS-TRQUE | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Motor Lube Axle Rear & Hoses | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 8 | 90026943 | B1 | 1000272031 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYM01 | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Overhaul Accumulator Brake LHF | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000027004 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-BACCM-FRLFT | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Overhaul Accumulator Brake RHF | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000027005 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-BACCM-FRRGT | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Overhaul Accumulator Brake Rear | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000027006 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-BACCM-BACCR | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Pump Brake Cooling | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 17 | 90002379 | B1 | 1000027007 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-HYFPP | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Overhaul Valve Control Brake | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 20 | 90002380 | B2 | 1000027008 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-BRVLV | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Motor Brake Oil Cooling | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 3 | 90002381 | B1 | 1000027009 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-BROCO-HYMO1 | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Hyd Pump Steering Main & Fan | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 17 | 90002383 | B1 | 1000027012 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -STRSYS-STPMP | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Steering HMU | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 8 | 90002384 | B1 | 1000027013 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -STRSYS-STHMU | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Ovhl Accumulator Steering Front | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000027016 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -STRSYS-STACC-SACCF | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Ovhl Accumulator Steering Middle | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000027017 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -STRSYS-STACC-SACCM | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Ovhl Accumulator Steering Rear | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000027018 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -STRSYS-STACC-SACCR | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Pump Hoist & Brake | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 15 | 90002388 | B1 | 1000027021 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -HYDSYS-HOPMP | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Rear Axle Linkages | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 113 | 90002396 | B1 | 1000027030 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -STRUCT-CHASS-AXLIK | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Replace Hoses Hoist System | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 40 | 90010105 | B1 | 1000083529 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -HYDSYS-HDHLF-HSTHO | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Replace Brake System Hoses | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 90 | 90010129 | B4 | 1000083535 | 25.09.2027 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-BRHLF-BRHOS | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Engine Midlife Complete | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 62 | 90015886 | B1 | 1000156068 | 03.11.2027 | 12000 | CCK-MP-HAUL-DT159 -ENGINE | 7400 | 90235 | 26732
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Auto Lube Pump | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 3 | 90002391 | B1 | 1000285797 | 15.11.2027 | 8000 | CCK-MP-HAUL-DT159 -GRSYST-ALBPP | 7400 | 90235 | 15586
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Spider Trans Driveshaft | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 12 | 90017211 | B1 | 1000154990 | 27.11.2027 | 6000 | CCK-MP-HAUL-DT159 -FDRSYS-DRSHT-UNVSL | 7400 | 90235 | 7642
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Differential | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 66 | 90014504 | B1 | 1000026999 | 30.12.2027 | 18000 | CCK-MP-HAUL-DT159 -FDRSYS-DIFFL | 7400 | 90235 | 7642
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Brake Slack Adjuster Front | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 4 | 90002382 | B1 | 1000027010 | 12.02.2028 | 20000 | CCK-MP-HAUL-DT159 -BRKSYS-SLACK-SLACF | 7400 | 90235 | 8738
793F | Onsite Shut | Haul | Fortescue | DT159 | DT159 Repl Brake Slack Adjuster Rear | 2027-09-21 | 2027-09-30 | 216 hrs | FY28 | 4 | 90002382 | B1 | 1000027011 | 12.02.2028 | 20000 | CCK-MP-HAUL-DT159 -BRKSYS-SLACK-SLACR | 7400 | 90235 | 8738
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2027-09-27 | 2027-10-06 | 222 hrs | FY28
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Engine Midlife complete | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 49 | 90015737 | B1 | 1000269597 | 19.10.2027 | 7000 | CCK-MP-GRDR-GR015 -ENGINE | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Replace High Risk Hoses | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 6 | 90021797 | B2 | 1000269601 | 19.10.2027 | 7000 | CCK-MP-GRDR-GR015 -ENGINE | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Drive Shaft Uni | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 6 | 90033281 | B1 | 1000333749 | 19.10.2027 | 7000 | CCK-MP-GRDR-GR015 -TRNSYS | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Hyd Pump Secondary Steering | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 6 | 90002459 | B1 | 1000027429 | 19.10.2027 | 7000 | CCK-MP-GRDR-GR015 -STRSYS-STEMG-SESPP | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Air Conditioner Major Service | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 24 | 90017476 | B1 | 1000269598 | 19.10.2027 | 7000 | CCK-MP-GRDR-GR015 -STRUCT-CABIN-AIRCN | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Operators Seat | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 8 | 90002475 | B1 | 1000027446 | 19.10.2027 | 7000 | CCK-MP-GRDR-GR015 -STRUCT-CABIN-SEATS | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Front Axle Assembly Midlife | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 66 | 90026004 | B1 | 1000256255 | 19.10.2027 | 7000 | CCK-MP-GRDR-GR015 -STRUCT-AXLES | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Brake Assy LHF | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 40 | 90002455 | B1 | 1000027422 | 11.02.2028 | 8000 | CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBLF | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Brake Assy RHF | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 40 | 90002455 | B1 | 1000027423 | 11.02.2028 | 8000 | CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBRF | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Brake Assy LHR | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 40 | 90002456 | B1 | 1000027424 | 11.02.2028 | 8000 | CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBLR | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Brake Assy RHR | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 40 | 90002456 | B1 | 1000027425 | 11.02.2028 | 8000 | CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBRR | 3200 | 42638 | 2788
16M | Onsite Shut | Ancillary | Fortescue | GR015 | GR015 Repl Tandem Chain LHF | 2027-09-27 | 2027-10-06 | 222 hrs | FY28 | 26 | 90015334 | B2 | 1000129920 | 22.02.2028 | 14000 | CCK-MP-GRDR-GR015 -FDRSYS-CHAIN-CHNLF | 3200 | 42638 | 12705
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2027-10-19 | 2027-10-28 | 216 hrs | FY28
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Cyl Hoist RH | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 33 | 90015131 | B1 | 1000128582 | 09.07.2027 | 28000 | CCK-MP-HAUL-DT142 -HYDSYS-HOCYL-HCYLR | 7400 | 87027 | 21177
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Spiders Pump Drive Shaft | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 4 | 90002366 | B1 | 1000025869 | 18.07.2027 | 18000 | CCK-MP-HAUL-DT142 -ENGINE-PMPDR-DRSHT | 7400 | 87027 | 27424
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Transmission Oil Cooler | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 12 | 90010097 | B1 | 1000083316 | 13.09.2027 | 18000 | CCK-MP-HAUL-DT142 -TRNSYS-TROLC | 7400 | 87027 | 9824
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Wheel End LH | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 58.5 | 90002374 | B1 | 1000025878 | 21.09.2027 | 24000 | CCK-MP-HAUL-DT142 -FDRSYS-FDRVE-FDRLH | 7400 | 87027 | 15622
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Wheel End RH | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 58.5 | 90007352 | B1 | 1000025879 | 21.09.2027 | 24000 | CCK-MP-HAUL-DT142 -FDRSYS-FDRVE-FDRRH | 7400 | 87027 | 15647
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Engine Midlife Complete | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 62 | 90015886 | B1 | 1000156002 | 23.10.2027 | 12000 | CCK-MP-HAUL-DT142 -ENGINE | 7400 | 87027 | 27424
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Radiator Fan Hoses | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 11 | 90031073 | B1 | 1000307515 | 23.10.2027 | 12000 | CCK-MP-HAUL-DT142 -ENGINE-COSYS-RADTR | 7400 | 87027 | 27424
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Motor Lube Axle Hoses | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 4 | 90026944 | B1 | 1000272008 | 23.10.2027 | 12000 | CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYM01 | 7400 | 87027 | 18705
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl AOC Fan Motor Rear | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 6 | 90002376 | B1 | 1000025881 | 23.10.2027 | 12000 | CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYM02 | 7400 | 87027 | 13221
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Replace Trans TCon System Hoses | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 20 | 90010099 | B1 | 1000090133 | 30.10.2027 | 18000 | CCK-MP-HAUL-DT142 -TRNSYS-TRANS-TRNHO | 7400 | 87027 | 27424
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Transmisson Calibration | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 8 | 90029836 | B1 | 1000298725 | 05.01.2028 | 4500 | CCK-MP-HAUL-DT142 -TRNSYS-TRANS | 7400 | 87027 | 9824
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Service Air Conditioner 12M | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 18 | 90018230 | B1 | 1000174173 | 26.01.2028 | 12 Monthly | CCK-MP-HAUL-DT142 -STRUCT-CABIN-AIRCN | 7400 | 87027 | 27424
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Tyre Sense Battery | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 2 | 90017022 | B1 | 1000153156 | 26.01.2028 | 24 Monthly | CCK-MP-HAUL-DT142 -MANGMT-TYRSN
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Cyl Steering LH | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 20 | 90002385 | B1 | 1000025892 | 19.03.2028 | 15000 | CCK-MP-HAUL-DT142 -STRSYS-STRCY-STCYL | 7400 | 87027 | 872
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Cyl Steering RH | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 20 | 90002385 | B2 | 1000025893 | 19.03.2028 | 15000 | CCK-MP-HAUL-DT142 -STRSYS-STRCY-STCYR | 7400 | 87027 | 3010
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Operators Seat | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 6 | 90002395 | B1 | 1000025907 | 19.03.2028 | 15000 | CCK-MP-HAUL-DT142 -STRUCT-CABIN-SEATS | 7400 | 87027 | 32847
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Replace Steering System Hoses | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 106 | 90010133 | B1 | 1000083330 | 19.03.2028 | 15000 | CCK-MP-HAUL-DT142 -STRSYS-STHLF-STRHO | 7400 | 87027 | 27424
793F | Onsite Shut | Haul | Fortescue | DT142 | DT142 Repl Spider Trans Driveshaft | 2027-10-19 | 2027-10-28 | 216 hrs | FY28 | 12 | 90017211 | B1 | 1000154966 | 19.03.2028 | 6000 | CCK-MP-HAUL-DT142 -FDRSYS-DRSHT-UNVSL | 7400 | 87027 | 11970
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 - ENGINE & MAJOR COMPONENTS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack RHR DE CS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90030672 | B1 | 1000278171 | 24.07.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYRR | 6800 | 21646 | 7977
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS Vibration Sensors | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 1 | 90029062 | B1 | 1000291545 | 19.09.2027 | 10000 | CCK-MP-DRLL-DR2128-ADSYST-ADSIS-DSVSN | 6800 | 21646 | 11827
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS GPS Components | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 3 | 90029061 | B1 | 1000291546 | 28.09.2027 | 30000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPO | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Hydraulic Cooler Module | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90020220 | B1 | 1000278201 | 28.09.2027 | 30000 | CCK-MP-DRLL-DR2128-COOLER | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Engine Assy Caterpillar C32 | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 154 | 90020393 | B1 | 1000278176 | 28.09.2027 | 15000 | CCK-MP-DRLL-DR2128-ENGINE | 6800 | 21646 | 3367
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Radiator Cooler Module | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90021617 | B1 | 1000278202 | 28.09.2027 | 30000 | CCK-MP-DRLL-DR2128-ENGINE-COSYS-RADTR | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack LHR DE NCS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90020204 | B1 | 1000278168 | 28.09.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYLR | 6800 | 21646 | 4602
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Mast Module Qtr Life | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 201 | 90030335 | B1 | 1000302801 | 28.09.2027 | 10000 | CCK-MP-DRLL-DR2128-STRUCT-DMAST | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Sprocket LH | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90020186 | B1 | 1000303007 | 28.09.2027 | 10000 | CCK-MP-DRLL-DR2128-TRAVEL-SPRKL | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Sprocket RH | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90020186 | B1 | 1000303008 | 28.09.2027 | 10000 | CCK-MP-DRLL-DR2128-TRAVEL-SPRKR | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Mast Harnesses | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 112 | 90028949 | B1 | 1000289035 | 28.09.2027 | 30000 | CCK-MP-DRLL-DR2128-ELCTLV-HARNS | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Fish Eye Camera | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 16 | 90029067 | B1 | 1000291548 | 11.10.2027 | 10000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPR-HTCAM | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Main Air Compressor LP | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 50 | 90020192 | B1 | 1000278197 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-AIRSYS-COMPR | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Pump Water Inj | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 4 | 90031899 | B1 | 1000315426 | 13.10.2027 | 7500 | CCK-MP-DRLL-DR2128-DSTSUP-WTRPP | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cyl Mast Locking NCS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90020197 | B1 | 1000278173 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MLCYL | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cyl Mast Locking CS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90030657 | B1 | 1000278172 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MLCYR | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Hyd Pump Fan Oil Cooler LH | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 2 | 90020239 | B1 | 1000278208 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-FANP1 | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Hyd Pump Fan Engine Cool RH | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 2 | 90020240 | B1 | 1000278209 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-FANP2 | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Pump Main Hyd NCS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 6 | 90020235 | B1 | 1000278210 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-MNPP1 | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Pump Charge | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 2 | 90020232 | B1 | 1000278206 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-MNPP3 | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Hyd Pump Auxiliary | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 4 | 90020236 | B1 | 1000278205 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-PPAUX | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Pump Drive Gearbox | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 78 | 90020181 | B1 | 1000278207 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-PMPDG | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Compressor Harnesses | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 12 | 90028948 | B1 | 1000289034 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-ELCTLV-HARNS | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cab Harnesses | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 14 | 90028947 | B1 | 1000289033 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-ELCTLV-HARNS | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Chassis Harnesses | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 208 | 90028944 | B1 | 1000289032 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-ELCTLV-HARNS | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Battery Cables | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90028942 | B1 | 1000289031 | 13.10.2027 | 15000 | CCK-MP-DRLL-DR2128-ELCTLV-HARNS | 6800 | 21646 | 6363
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Washdown Pump | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 8 | 90030681 | B1 | 1000305733 | 27.01.2028 | 7500 | CCK-MP-DRLL-DR2128-DSTSUP-WSHPP | 6800 | 21646 | 3234
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Service 12M Air Conditioner | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 12 | 90028298 | B1 | 1000283159 | 27.01.2028 | 12 Monthly | CCK-MP-DRLL-DR2128-STRUCT-CABIN-AIRCN | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Mast Cables | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 64 | 90030334 | B1 | 1000302800 | 06.02.2028 | 2500 | CCK-MP-DRLL-DR2128-STRUCT-DMAST | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS LiDAR | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 4 | 90029065 | B1 | 1000291549 | 26.02.2028 | 5000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPR-LIDAR | 6800 | 21646 | 6175
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack RHF NDE CS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90030670 | B1 | 1000278170 | 13.03.2028 | 6000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYRF | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack LHF NDE NCS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 24 | 90020196 | B1 | 1000278169 | 17.03.2028 | 6000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYLF | 6800 | 21646 | 2309
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cyl Mast Raise NCS | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 32 | 90030659 | B1 | 1000278175 | 06.04.2028 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MRCYL | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Seat Operators | 2027-10-19 | 2027-10-27 | 186 hrs | FY28 | 8 | 90020200 | B2 | 1000278259 | 07.04.2028 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-CABIN-SEATS | 6800 | 21646 | 6363
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 - ENGINE & MAJOR COMPONENTS | 2027-10-27 | 2027-11-05 | 216 hrs | FY28
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Valve Steering | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 12 | 90011554 | B1 | 1000098130 | 16.07.2027 | 18000 | CCK-MP-SUPP-WC221 -STRSYS-STVLV | 4000 | 56923 | 13811
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Auto Lube Pump | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 2 | 90011565 | B1 | 1000098141 | 01.09.2027 | 9000 | CCK-MP-SUPP-WC221 -GRSYST-ALBPP | 4000 | 56923 | 4771
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace C32 Engine | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 386 | 90015753 | B1 | 1000269917 | 17.09.2027 | 18000 | CCK-MP-SUPP-WC221 -ENGINE | 4300 | 56923 | 12761
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Overhaul Airconditioner | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 24 | 90011566 | B2 | 1000269920 | 17.09.2027 | 9000 | CCK-MP-SUPP-WC221 -STRUCT-CABIN-AIRCN | 4000 | 56923 | 4347
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Engine Aftercooler | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 6 | 90011533 | B1 | 1000098112 | 25.10.2027 | 18000 | CCK-MP-SUPP-WC221 -ENGINE-INTEX-AFTER | 4000 | 56923 | 12761
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Drive Shaft | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 2 | 90011540 | B1 | 1000098118 | 25.10.2027 | 18000 | CCK-MP-SUPP-WC221 -FDRSYS-DRSHT | 4000 | 56923 | 12761
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Differential | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 38 | 90011541 | B1 | 1000098119 | 25.10.2027 | 18000 | CCK-MP-SUPP-WC221 -FDRSYS-DIFFL | 4000 | 56923 | 12761
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Steering Linkages | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 24 | 90011557 | B1 | 1000098133 | 25.10.2027 | 18000 | CCK-MP-SUPP-WC221 -STRSYS-STLTR | 4000 | 56923 | 12775
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Valve Hoist | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 36 | 90011564 | B1 | 1000098140 | 25.10.2027 | 18000 | CCK-MP-SUPP-WC221 -HYDSYS-HOVLV | 4000 | 56923 | 12761
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Replace Pump Hoist Lines | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 8 | 90011562 | B1 | 1000098138 | 25.10.2027 | 18000 | CCK-MP-SUPP-WC221 -HYDSYS-HDHLF | 4000 | 56923 | 12761
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Repl Sepura SCC Microphone | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289621 | 07.11.2027 | 12 Monthly | CCK-MP-SUPP-WC221 -COMMUN-RADIO
777G WC | Onsite Shut | Haul | Fortescue | WC221 | WC221 Refurbish A Frame | 2027-10-27 | 2027-11-05 | 216 hrs | FY28 | 36 | 90011568 | B1 | 1000098144 | 20.01.2028 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-CHASS-AFRME | 4000 | 56923 | 30341
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 - ENGINE & MAJOR COMPONENTS | 2027-11-01 | 2027-11-11 | 240 hrs | FY28
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Cyl Blade Lift RH | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 16 | 90000287 | B1 | 1000255623 | 02.11.2027 | 9000 | CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-BLCYR | 5000 | 68711 | 433
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Steer Clutch & Brake Assm LH | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000079432 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -BRKSTR-SCABL | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Engine Cat C27 | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 114 | 90015849 | B1 | 1000160146 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -ENGINE | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Rad Engine Cooling SN 529 UP | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 48 | 90000307 | B2 | 1000079424 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -ENGINE-COSYS-RADTR | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Final Drive RH | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 28 | 90000312 | B2 | 1000079431 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -FDRSYS-FDRRH | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Hyd Oil Cooler | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 10 | 90009664 | B2 | 1000079441 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -HYDSYS-HDOCO | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Ovhl Hydraulic & Fuel Tank | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 48 | 90010842 | B1 | 1000108430 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -HYDSYS-HDTNK | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Overhaul Air Conditioner | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 48 | 90017468 | B1 | 1000196626 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -STRUCT-CABIN-AIRCN | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Minor Overhaul Track Frame LH | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 98 | 90002098 | B1 | 1000108433 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -STRUCT-UNDER-TKFRL | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Minor Overhaul Track Frame RH | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 98 | 90010766 | B1 | 1000108435 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -STRUCT-UNDER-TKFRR | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Drive Shaft | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 6 | 90033296 | B1 | 1000334107 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -TRNSYS | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Transmission | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 48 | 90000308 | B2 | 1000079427 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -TRNSYS-TRANS | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Pump Trans & TCon Charge | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 10 | 90000302 | B2 | 1000079429 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -TRNSYS-TRPMP | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Torque Converter | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 60 | 90000309 | B2 | 1000079426 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -TRNSYS-TRQUE | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Steer Clutch & Brake Assm RH | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000079433 | 04.11.2027 | 18000 | CCK-MP-DOZR-DZ173 -BRKSTR-SCABR | 5000 | 68788 | 11848
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Operators Seat | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 8 | 90000318 | B1 | 1000108427 | 11.11.2027 | 6000 | CCK-MP-DOZR-DZ173 -STRUCT-CABIN-SEATS | 5000 | 68788 | 11495
D10T | Onsite Shut | Ancillary | Fortescue | DZ173 | DZ173 Repl Hyd Pump Implement | 2027-11-01 | 2027-11-11 | 240 hrs | FY28 | 10 | 90000301 | B2 | 1000079434 | 27.01.2028 | 9000 | CCK-MP-DOZR-DZ173 -HYDSYS-HYDPP-HYIPP | 5000 | 68788 | 1691
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181- ENGINE & MAJOR COMPONENTS | 2027-11-08 | 2027-11-18 | 240 hrs | FY28
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Sepura SCC Microphone | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289555 | 24.08.2027 | 12 Monthly | CCK-MP-DOZR-DZ181 -COMMUN-RADIO | 5000 | 66297 | 66297
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Actuator Brake HaulX Shield | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 50 | 90033498 | B1 | 1000337798 | 25.08.2027 | 14000 | CCK-MP-DOZR-DZ181 -MANGMT-CASYS-ACTBK
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Operators Seat | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 8 | 90000318 | B1 | 1000108523 | 30.08.2027 | 6000 | CCK-MP-DOZR-DZ181 -STRUCT-CABIN-SEATS | 5000 | 66297 | 691
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Steer Clutch & Brake Assm LH | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000091292 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -BRKSTR-SCABL | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Steer Clutch & Brake Assm RH | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000091293 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -BRKSTR-SCABR | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Engine Cat C27 | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 114 | 90015849 | B1 | 1000160242 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -ENGINE | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Aftercooler Engine | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 8 | 90010841 | B1 | 1000108524 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -ENGINE-INTEX-AFTER | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Final Drive LH | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 28 | 90000312 | B2 | 1000091290 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -FDRSYS-FDRLH | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Final Drive RH | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 28 | 90000312 | B2 | 1000091291 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -FDRSYS-FDRRH | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Cyl Blade Lift LH | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 16 | 90000287 | B1 | 1000255678 | 23.10.2027 | 9000 | CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-BLCYL | 5000 | 66297 | 11065
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Hyd Oil Cooler | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 10 | 90009664 | B2 | 1000091299 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -HYDSYS-HDOCO | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Ovhl Hydraulic & Fuel Tank | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 48 | 90010842 | B1 | 1000108526 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -HYDSYS-HDTNK | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Hyd Pump Cooling Fan | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 16 | 90004952 | B2 | 1000091297 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -HYDSYS-HYDPP-HYFPP | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Overhaul Air Conditioner | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 48 | 90017468 | B1 | 1000196650 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -STRUCT-CABIN-AIRCN | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Drive Shaft | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 6 | 90033296 | B1 | 1000334121 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -TRNSYS | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Transmission | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 48 | 90000308 | B2 | 1000091287 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -TRNSYS-TRANS | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Torque Converter | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 60 | 90000309 | B2 | 1000091286 | 23.10.2027 | 18000 | CCK-MP-DOZR-DZ181 -TRNSYS-TRQUE | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Hyd Pump Implement | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 10 | 90000301 | B2 | 1000091294 | 07.01.2028 | 9000 | CCK-MP-DOZR-DZ181 -HYDSYS-HYDPP-HYIPP | 5000 | 66297 | 1907
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Equaliser Bar | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 110 | 90002097 | B1 | 1000108528 | 27.03.2028 | 18000 | CCK-MP-DOZR-DZ181 -STRUCT-CHASS-EQUAL | 5000 | 66297 | 9861
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Track Frame LH | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 40 | 90002099 | B1 | 1000108530 | 23.06.2028 | 36000 | CCK-MP-DOZR-DZ181 -STRUCT-UNDER-TKFRL | 5000 | 66297 | 12007
D10T | Onsite Shut | Ancillary | Fortescue | DZ181 | DZ181 Repl Track Frame RH | 2027-11-08 | 2027-11-18 | 240 hrs | FY28 | 40 | 90002102 | B1 | 1000108532 | 23.06.2028 | 36000 | CCK-MP-DOZR-DZ181 -STRUCT-UNDER-TKFRR | 5000 | 66297 | 12007
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 - POWER PACK MODULE | 2027-11-08 | 2027-11-16 | 186 hrs | FY28
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Cylinder Oscillation LH | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 8 | 90021662 | B1 | 1000295063 | 09.05.2027 | 12000 | CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-TFCOL | 5400 | 16590 | 7605
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Cylinder Oscillation RH | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 8 | 90021663 | B1 | 1000295064 | 09.05.2027 | 12000 | CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-TFCOR | 5400 | 16590 | 7605
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Track Frame Module LH | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 28 | 90021739 | B1 | 1000295085 | 13.05.2027 | 12000 | CCK-MP-DRLL-DR3134-STRUCT-TKFRL | 5400 | 16590 | 7605
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Track Frame Module RH | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 28 | 90021741 | B1 | 1000295086 | 13.05.2027 | 12000 | CCK-MP-DRLL-DR3134-STRUCT-TKFRR | 5400 | 16590 | 7605
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Pressure Safety Valve Cert | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 3 | 90021719 | B1 | 1000295084 | 19.08.2027 | 48 Monthly | CCK-MP-DRLL-DR3134-AIRSYS-COMPR-VCSRL | 5400 | 16590 | 5149
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Overhaul Airconditioning System | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 18 | 90023285 | B1 | 1000295090 | 23.08.2027 | 24 Monthly | CCK-MP-DRLL-DR3134-STRUCT-CABIN-ACCOM | 5400 | 16590 | 16590
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Power Pack Module | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 88 | 90026030 | B1 | 1000295092 | 20.10.2027 | 12000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 2 | 90020875 | B1 | 1000295059 | 22.10.2027 | 8000 | CCK-MP-DRLL-DR3134-GRSYST-ALBPP | 5400 | 16590 | 970
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 1 | 90020876 | B1 | 1000295060 | 22.10.2027 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Pump Air Lubrication | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 2 | 90021656 | B1 | 1000295071 | 26.10.2027 | 6000 | CCK-MP-DRLL-DR3134-AIRSYS-COMPR-PALUB | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Pump Water Injection | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 4 | 90021716 | B1 | 1000295073 | 26.10.2027 | 6000 | CCK-MP-DRLL-DR3134-DSTSUP-WTRPP | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Pump Rod Thread Lube | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 2 | 90021715 | B1 | 1000295083 | 26.10.2027 | 6000 | CCK-MP-DRLL-DR3134-GRSYST-RTLPP | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Cyl Jack levelling Rear | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 6 | 90021661 | B1 | 1000295062 | 26.10.2027 | 12000 | CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-JLCYR | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Valve Main Block | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 18 | 90021692 | B1 | 1000295087 | 26.10.2027 | 12000 | CCK-MP-DRLL-DR3134-HYDSYS-HDVLV-VVMBK | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Oscillation Valve | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 4 | 90021664 | B1 | 1000295088 | 26.10.2027 | 12000 | CCK-MP-DRLL-DR3134-HYDSYS-HDVLV-VVOST | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Operators Seat | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 4 | 90021702 | B1 | 1000295069 | 26.10.2027 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-CABIN-SEATS | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Hyd Feed Motor | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 6 | 90022025 | B1 | 1000361305 | 26.11.2027 | 6000 | CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MFEED | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 XLF Timing Chain Maintenance | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 14 | 90022023 | B1 | 1000361303 | 26.11.2027 | 3000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHP | 5400 | 16590 | 567
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Feed Chain Sprockets | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 24 | 90022030 | B1 | 1000361304 | 26.11.2027 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHS | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Hose Drum Sprocket | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 6 | 90022032 | B1 | 1000361308 | 26.11.2027 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDHDS | 5400 | 16590 | 5065
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 Repl Gearbox Powerhead | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 32 | 90021707 | B1 | 1000361306 | 26.11.2027 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-PWRHD | 5400 | 16590 | 5716
D65 | Onsite Shut | Drills | Fortescue | DR3134 | DR3134 XLF Repl Main Feed Chain | 2027-11-08 | 2027-11-16 | 186 hrs | FY28 | 16 | 90021711 | B1 | 1000295065 | 26.10.2027 | 2500 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHH | 5400 | 16590 | 3175
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 - ENGINE MIDLIFES & MINOR COMPONENTS | 2027-11-17 | 2027-11-29 | 282 hrs | FY28
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Annual Air Con Service LH | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 13 | 90027615 | B1 | 1000297023 | 20.07.2027 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN-AIRCL
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Annual Air Con Service RH | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 13 | 90027615 | B1 | 1000296993 | 21.07.2027 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN-AIRCR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Engine Midlife Complete LH | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 66 | 90027554 | B1 | 1000296917 | 05.10.2027 | 9000 | CCK-MP-EXCV-EX7125-LHENGN | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Engine Midlife Complete RH | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 66 | 90027554 | B1 | 1000296922 | 05.10.2027 | 9000 | CCK-MP-EXCV-EX7125-RHENGN | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Case Drain Hoses | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 16 | 90027566 | B1 | 1000296971 | 19.10.2027 | 15000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-HPCDL | 6900 | 18844 | 6502
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Swing LHR | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 27 | 90027503 | B1 | 1000296952 | 19.10.2027 | 15000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-SWMLR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Swing RHF | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 27 | 90027503 | B1 | 1000296953 | 19.10.2027 | 15000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-SWMRF | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Swing RHR | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 27 | 90027503 | B1 | 1000296954 | 19.10.2027 | 15000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-SWMRR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Operators Seat | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 2 | 90027613 | B1 | 1000296964 | 24.02.2028 | 10000 | CCK-MP-EXCV-EX7125-STRUCT-CABIN-SEATS | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Minestar Harness | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 43.5 | 90031708 | B1 | 1000369998 | 12.03.2028 | 4000 | CCK-MP-EXCV-EX7125-MANGMT-UMMMC | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic System Tune Up | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 24 | 90017865 | B1 | 1000296998 | 25.03.2028 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Swing Circuit Hoses | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 16 | 90027576 | B1 | 1000296980 | 25.03.2028 | 9000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SWCRT | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Auto Lube Pump | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 6 | 90027592 | B1 | 1000296999 | 29.03.2028 | 6000 | CCK-MP-EXCV-EX7125-GRSYST-ALBPP | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic Oil Replacement | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 12 | 90016793 | B1 | 1000296988 | 29.03.2028 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Boom Arch Hoses | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 24 | 90027558 | B1 | 1000296966 | 09.04.2028 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-BMARH | 6900 | 18844 | 12306
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Pump to Rotor Hose | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 48 | 90027567 | B1 | 1000296972 | 09.04.2028 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-MPRCH | 6900 | 18844 | 12306
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Servo Hose Bulkhead to MCV | 2027-11-17 | 2027-11-29 | 282 hrs | FY28 | 16 | 90027574 | B1 | 1000296978 | 09.04.2028 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SHMCV | 6900 | 18844 | 12306
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 - ENGINE & TANK MODULE MIDLIFE | 2027-12-04 | 2027-12-13 | 216 hrs | FY28
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Service Tank Module Midlife | 2027-12-04 | 2027-12-13 | 216 hrs | FY28 | 1 | 90028958 | B1 | 1000288851 | 24.01.2025 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-SVTNK | 5100 | 58259 | 58259
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace C32 Engine | 2027-12-04 | 2027-12-13 | 216 hrs | FY28 | 386 | 90015632 | B1 | 1000269772 | 13.08.2027 | 18000 | CCK-MP-SUPP-SV220 -ENGINE | 5100 | 58303 | 11037
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Overhaul Airconditioner | 2027-12-04 | 2027-12-13 | 216 hrs | FY28 | 24 | 90011566 | B2 | 1000269775 | 13.08.2027 | 9000 | CCK-MP-SUPP-SV220 -STRUCT-CABIN-AIRCN | 5100 | 58259 | 16547
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Brake Oil Cooler | 2027-12-04 | 2027-12-13 | 216 hrs | FY28 | 6 | 90011549 | B1 | 1000093055 | 01.10.2027 | 15000 | CCK-MP-SUPP-SV220 -BRKSYS-BROCO | 5100 | 58303 | 23536
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Replace Operator Seat | 2027-12-04 | 2027-12-13 | 216 hrs | FY28 | 6 | 90011567 | B1 | 1000098152 | 07.10.2027 | 6000 | CCK-MP-SUPP-SV220 -STRUCT-CABIN-SEATS | 5100 | 58259 | 5249
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 HP Grease Gun, Hose & Burst Sleeve | 2027-12-04 | 2027-12-13 | 216 hrs | FY28 | 4 | 90022836 | B1 | 1000238750 | 29.11.2027 | 12 Monthly | CCK-MP-SUPP-SV220 -GRSYST-ALHLF | 5100 | 58259 | 58259
777G SV | Onsite Shut | Haul | Fortescue | SV220 | SV220 Repl Bulk Grease Tank Breather | 2027-12-04 | 2027-12-13 | 216 hrs | FY28 | 1 | 90022533 | B1 | 1000236909 | 25.12.2027 | 6 Monthly | CCK-MP-SUPP-SV220 -GRSYST-GRTNK | 5100 | 58259 | 58259
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 - RH ENGINE & MAJOR COMPONENTS | 2027-12-08 | 2027-12-20 | 282 hrs | FY28
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Annual Air Con Service LH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 13 | 90027615 | B1 | 1000297574 | 09.07.2027 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN-AIRCL
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Idler Track LH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 18 | 90027507 | B1 | 1000297554 | 28.07.2027 | 1500 | CCK-MP-EXCV-EX7123-STRUCT-TKFRL-IDLLH | 490 | 1007 | 1007
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Idler Track RH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 18 | 90027507 | B1 | 1000297565 | 28.07.2027 | 1500 | CCK-MP-EXCV-EX7123-STRUCT-TKFRR-IDLRH | 490 | 1007 | 1007
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Sprocket LH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 24 | 90027486 | B1 | 1000297562 | 28.07.2027 | 1500 | CCK-MP-EXCV-EX7123-TRAVEL-SPRKL | 490 | 1007 | 1007
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Sprocket RH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 24 | 90027486 | B1 | 1000297573 | 28.07.2027 | 1500 | CCK-MP-EXCV-EX7123-TRAVEL-SPRKR | 490 | 1007 | 1007
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Adjust 4500hr Valve Set | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 20 | 90027549 | B1 | 1000297427 | 30.07.2027 | 4500 | CCK-MP-EXCV-EX7123-LHENGN | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos2 | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 64 | 90027490 | B1 | 1000297483 | 02.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP2 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Auto Lube Pump | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 6 | 90027592 | B1 | 1000297550 | 03.09.2027 | 6000 | CCK-MP-EXCV-EX7123-GRSYST-ALBPP | 6900 | 15681 | 503
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Grease Control Valving | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 14 | 90027612 | B1 | 1000297551 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-GRSYST-ALCON
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Hydraulic System Tune Up | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 24 | 90017865 | B1 | 1000297549 | 03.09.2027 | 6000 | CCK-MP-EXCV-EX7123-HYDSYS | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Hydraulic Oil Replacement | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 12 | 90016793 | B1 | 1000297539 | 03.09.2027 | 6000 | CCK-MP-EXCV-EX7123-HYDSYS | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Stick LH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 54 | 90027498 | B1 | 1000297496 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-STCLL | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Boom Arch Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 24 | 90027558 | B1 | 1000297517 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-BMARH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Fan Drive Eng Cooling Hose | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 36 | 90027564 | B1 | 1000297519 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-FDECH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Fan Drive Hyd Cooling Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 36 | 90027565 | B1 | 1000297520 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-FDHCH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hydraulic Cooling Circ Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 36 | 90031704 | B1 | 1000297521 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-HCCHH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Pump to Rotor Hose | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 48 | 90027567 | B1 | 1000297523 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-MPRCH | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Rotor to Drive Motor Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 40 | 90027570 | B1 | 1000297526 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-RCDMH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Rotor & Logic Valve Hp Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 36 | 90027571 | B1 | 1000297527 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-RCLVH | 6900 | 15607 | 4281
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Servo Hoses Cascade to Bulkhead | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 16 | 90027572 | B1 | 1000297528 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SHBLK | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Servo Hose Bulkhead to MCV | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 16 | 90027574 | B1 | 1000297529 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SHMCV | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Servo Hoses Cascade to Trvl Valve | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 12 | 90027575 | B1 | 1000297530 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SHTRV | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 2nd Speed Trvl Brake Release Hose | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 10 | 90027559 | B1 | 1000297516 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SSTBR | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Swing Motor Case Drain Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 12 | 90027577 | B1 | 1000297532 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SWMCD | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Travel Motor Case Drain Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 10 | 90027578 | B1 | 1000297533 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-TMCDH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Track Tensioning Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 3 | 90027579 | B1 | 1000297534 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-TRTNH | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos1 | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 64 | 90027490 | B1 | 1000297482 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP1 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos3 | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 64 | 90027490 | B1 | 1000297484 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP3 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos4 | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 64 | 90027490 | B1 | 1000297485 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP4 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Pos1 & Pos2 | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 42 | 90027492 | B1 | 1000297486 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SP1P2 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Pos3 & Pos4 | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 42 | 90027492 | B1 | 1000297487 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SP3P4 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Replenish LH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 2 | 90027495 | B1 | 1000297492 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SRPPL | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Replenish RH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 2 | 90027495 | B1 | 1000297493 | 03.09.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SRPPR | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Annual Air Con Service RH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 13 | 90027615 | B1 | 1000297544 | 14.09.2027 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN-AIRCR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Boom Stick Bucket Cyl Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 136 | 90027560 | B1 | 1000297518 | 17.10.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-HBSBC | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Boom & MCV Hoses | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 136 | 90032593 | B1 | 1000325061 | 17.10.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-HBSBC | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Oil Cooler Front | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 48 | 90027500 | B1 | 1000297500 | 17.10.2027 | 24000 | CCK-MP-EXCV-EX7123-HYDSYS-HDOCO-OCHYF | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Oil Cooler Rear | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 48 | 90027500 | B1 | 1000297501 | 17.10.2027 | 24000 | CCK-MP-EXCV-EX7123-HYDSYS-HDOCO-OCHYR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Rotary Joint | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 48 | 90027501 | B1 | 1000297502 | 17.10.2027 | 24000 | CCK-MP-EXCV-EX7123-HYDSYS-ROTRY | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Final Drive RH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 144 | 90027485 | B1 | 1000297436 | 17.10.2027 | 24000 | CCK-MP-EXCV-EX7123-TRAVEL-FDRRH | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Stick RH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 54 | 90027498 | B1 | 1000297497 | 20.10.2027 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-STCLR | 6900 | 15607 | 3559
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Bucket LH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 32 | 90027499 | B1 | 1000297498 | 26.11.2027 | 10000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BUCYL | 6900 | 15607 | 10846
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Engine Cat C32 | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 244 | 90027534 | B1 | 1000297430 | 15.01.2028 | 18000 | CCK-MP-EXCV-EX7123-RHENGN | 6900 | 15607 | 7903
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Bucket RH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 32 | 90027499 | B1 | 1000297499 | 27.01.2028 | 10000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BUCYR | 6900 | 15607 | 9683
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Minestar Harness | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 43.5 | 90031708 | B1 | 1000369997 | 31.01.2028 | 4000 | CCK-MP-EXCV-EX7123-MANGMT-UMMMC | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Wiper Blades | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 1 | 90027557 | B1 | 1000297545 | 19.02.2028 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Engine Midlife Complete LH | 2027-12-08 | 2027-12-20 | 282 hrs | FY28 | 66 | 90027554 | B1 | 1000297428 | 24.03.2028 | 9000 | CCK-MP-EXCV-EX7123-LHENGN | 6900 | 15607 | 15607
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 - MAJOR COMPONENTS | 2027-12-08 | 2027-12-17 | 216 hrs | FY28
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Auto Lube Pump | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 3 | 90002391 | B1 | 1000285810 | 29.08.2027 | 8000 | CCK-MP-HAUL-DT5318-GRSYST-ALBPP | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Spider Trans Driveshaft | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 12 | 90017211 | B1 | 1000167376 | 16.10.2027 | 6000 | CCK-MP-HAUL-DT5318-FDRSYS-DRSHT-UNVSL | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Spiders Pump Drive Shaft | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 4 | 90002366 | B1 | 1000167314 | 20.10.2027 | 18000 | CCK-MP-HAUL-DT5318-ENGINE-PMPDR-DRSHT | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Replace Hoses Differential System | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 5 | 90010101 | B3 | 1000167358 | 20.10.2027 | 18000 | CCK-MP-HAUL-DT5318-FDRSYS-DIFFL-DIFHO | 7400 | 45240 | 25711
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Torque Converter | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 53 | 90002369 | B1 | 1000167317 | 06.12.2027 | 24000 | CCK-MP-HAUL-DT5318-TRNSYS-TRQUE | 7400 | 45240 | 14125
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Transmission | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 39 | 90026996 | B1 | 1000272519 | 06.12.2027 | 18000 | CCK-MP-HAUL-DT5318-TRNSYS-TRANS | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Replace Trans TCon System Hoses | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 20 | 90010099 | B3 | 1000167357 | 06.12.2027 | 18000 | CCK-MP-HAUL-DT5318-TRNSYS-TRANS-TRNHO | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Transmission Oil Cooler | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 12 | 90010097 | B1 | 1000167348 | 06.12.2027 | 18000 | CCK-MP-HAUL-DT5318-TRNSYS-TROLC | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Differential | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 66 | 90014504 | B1 | 1000167319 | 06.12.2027 | 18000 | CCK-MP-HAUL-DT5318-FDRSYS-DIFFL | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Brake Slack Adjuster Front | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 4 | 90002382 | B1 | 1000167329 | 02.02.2028 | 20000 | CCK-MP-HAUL-DT5318-BRKSYS-SLACK-SLACF | 7400 | 45240 | 9085
793F | Onsite Shut | Haul | Fortescue | DT5318 | DT5318 Repl Brake Slack Adjuster Rear | 2027-12-08 | 2027-12-17 | 216 hrs | FY28 | 4 | 90002382 | B1 | 1000167330 | 02.02.2028 | 20000 | CCK-MP-HAUL-DT5318-BRKSYS-SLACK-SLACR | 7400 | 45240 | 9085
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 - POWER PACK MODULE & MAJOR COMPONENTS | 2027-12-08 | 2027-12-16 | 186 hrs | FY28
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Cylinder Oscillation LH | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 8 | 90021662 | B1 | 1000295023 | 22.08.2027 | 12000 | CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-TFCOL | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Cylinder Oscillation RH | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 8 | 90021663 | B1 | 1000295024 | 22.08.2027 | 12000 | CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-TFCOR | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Track Frame Module LH | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 28 | 90021739 | B1 | 1000295045 | 22.08.2027 | 12000 | CCK-MP-DRLL-DR3133-STRUCT-TKFRL | 5400 | 16251 | 6175
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Track Frame Module RH | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 28 | 90021741 | B1 | 1000295046 | 22.08.2027 | 12000 | CCK-MP-DRLL-DR3133-STRUCT-TKFRR | 5400 | 16251 | 6175
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Pressure Safety Valve Cert | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 3 | 90021719 | B1 | 1000295044 | 20.09.2027 | 48 Monthly | CCK-MP-DRLL-DR3133-AIRSYS-COMPR-VCSRL | 5400 | 16251 | 10110
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Overhaul Air Condtioner System | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 18 | 90023285 | B1 | 1000295050 | 21.09.2027 | 24 Monthly | CCK-MP-DRLL-DR3133-STRUCT-CABIN-ACCOM | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Pump Air Lubrication | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 2 | 90021656 | B1 | 1000295031 | 03.12.2027 | 6000 | CCK-MP-DRLL-DR3133-AIRSYS-COMPR-PALUB | 5400 | 16251 | 10110
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Pump Water Injection | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 4 | 90021716 | B1 | 1000295033 | 03.12.2027 | 6000 | CCK-MP-DRLL-DR3133-DSTSUP-WTRPP | 5400 | 16251 | 1685
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 2 | 90020875 | B1 | 1000294979 | 03.12.2027 | 8000 | CCK-MP-DRLL-DR3133-GRSYST-ALBPP | 5400 | 16251 | 8583
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 1 | 90020876 | B1 | 1000295020 | 03.12.2027 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Pump Rod Thread Lube | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 2 | 90021715 | B1 | 1000295043 | 03.12.2027 | 6000 | CCK-MP-DRLL-DR3133-GRSYST-RTLPP | 5400 | 16251 | 10110
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Cyl Jack levelling Rear | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 6 | 90021661 | B1 | 1000295022 | 03.12.2027 | 12000 | CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-JLCYR | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Valve Main Block | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 18 | 90021692 | B1 | 1000295047 | 03.12.2027 | 12000 | CCK-MP-DRLL-DR3133-HYDSYS-HDVLV-VVMBK | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Oscillation Valve | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 4 | 90021664 | B1 | 1000295048 | 03.12.2027 | 12000 | CCK-MP-DRLL-DR3133-HYDSYS-HDVLV-VVOST | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Operators Seat | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 4 | 90021702 | B1 | 1000295029 | 03.12.2027 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-CABIN-SEATS | 5400 | 16251 | 10110
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Power Pack Module | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 88 | 90026030 | B1 | 1000295052 | 04.12.2027 | 12000 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Hyd Motor Feed | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 6 | 90022025 | B1 | 1000361230 | 25.12.2027 | 6000 | CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MFEED | 5400 | 16251 | 10609
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Timing Chain Maintenance | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 14 | 90022023 | B1 | 1000361228 | 25.12.2027 | 3000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHP | 5400 | 16251 | 1197
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Feed Chain Sprockets | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 24 | 90022030 | B1 | 1000361229 | 25.12.2027 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHS | 5400 | 16251 | 2448
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Hose Drum Sprocket | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 6 | 90022032 | B1 | 1000361233 | 25.12.2027 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDHDS | 5400 | 16251 | 16251
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 Repl Gearbox Power Head | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 32 | 90021707 | B1 | 1000361231 | 25.12.2027 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-PWRHD | 5400 | 16251 | 7735
D65 | Onsite Shut | Drills | Fortescue | DR3133 | DR3133 XLF Repl Main Feed Chain | 2027-12-08 | 2027-12-16 | 186 hrs | FY28 | 16 | 90021711 | B1 | 1000295025 | 12.11.2027 | 2500 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHH | 5400 | 16251 | 1197
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 - ENGINE & MAJOR COMPONENTS | 2027-12-13 | 2027-12-23 | 240 hrs | FY28
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Actuator Brake HaulX Shield | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 50 | 90033498 | B1 | 1000337797 | 09.08.2027 | 14000 | CCK-MP-DOZR-DZ171 -MANGMT-CASYS-ACTBK
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Cyl Blade Lift RH | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 16 | 90000287 | B1 | 1000255607 | 16.09.2027 | 9000 | CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-BLCYR | 5000 | 67979 | 3604
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Fan Cooling Motor Hyd | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 16 | 90002094 | B2 | 1000108402 | 08.10.2027 | 9000 | CCK-MP-DOZR-DZ171 -HYDSYS-HDCFM | 5000 | 67979 | 850
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Equaliser Bar | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 110 | 90002097 | B1 | 1000108408 | 08.10.2027 | 18000 | CCK-MP-DOZR-DZ171 -STRUCT-CHASS-EQUAL | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Sepura SCC Microphone | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289546 | 21.12.2027 | 12 Monthly | CCK-MP-DOZR-DZ171 -COMMUN-RADIO | 5000 | 67979 | 67979
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Steer Clutch & Brake Assm LH | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000091124 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -BRKSTR-SCABL | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Steer Clutch & Brake Assm RH | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000091125 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -BRKSTR-SCABR | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Engine Cat C27 | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 114 | 90015849 | B1 | 1000160122 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -ENGINE | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Rad Engine Cooling SN 529 UP | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 48 | 90000307 | B2 | 1000091116 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -ENGINE-COSYS-RADTR | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Aftercooler Engine | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 8 | 90010841 | B1 | 1000108404 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -ENGINE-INTEX-AFTER | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Ovhl Hydraulic & Fuel Tank | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 48 | 90010842 | B1 | 1000108406 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -HYDSYS-HDTNK | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Hyd Pump Cooling Fan | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 16 | 90004952 | B2 | 1000091129 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -HYDSYS-HYDPP-HYFPP | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Overhaul Air Conditioner | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 48 | 90017468 | B1 | 1000196616 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -STRUCT-CABIN-AIRCN | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Transmission | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 48 | 90000308 | B2 | 1000091119 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -TRNSYS-TRANS | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Torque Converter | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 60 | 90000309 | B2 | 1000091118 | 25.12.2027 | 18000 | CCK-MP-DOZR-DZ171 -TRNSYS-TRQUE | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Cyl Blade Lift LH | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 16 | 90000287 | B1 | 1000255606 | 08.01.2028 | 9000 | CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-BLCYL | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Hyd Pump Implement | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 10 | 90000301 | B2 | 1000091126 | 08.01.2028 | 9000 | CCK-MP-DOZR-DZ171 -HYDSYS-HYDPP-HYIPP | 5000 | 67979 | 11227
D10T | Onsite Shut | Ancillary | Fortescue | DZ171 | DZ171 Repl Operators Seat | 2027-12-13 | 2027-12-23 | 240 hrs | FY28 | 8 | 90000318 | B1 | 1000108403 | 20.02.2028 | 6000 | CCK-MP-DOZR-DZ171 -STRUCT-CABIN-SEATS | 5000 | 67979 | 11227
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 - POWER PACK MIDLIFES & MINOR COMPONENTS | 2028-01-05 | 2028-01-17 | 282 hrs | FY28
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel LHF | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 14 | 90015697 | B1 | 1000162092 | 02.07.2027 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMLF | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel LHR | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 14 | 90015697 | B1 | 1000162093 | 02.07.2027 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMLR | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel RHF | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 14 | 90015697 | B1 | 1000162094 | 02.07.2027 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMRF | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Rotary Connection | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 50 | 90015692 | B1 | 1000162079 | 02.07.2027 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-ROTRY | 7200 | 46150 | 13003
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel RHR | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 14 | 90015697 | B1 | 1000162095 | 03.07.2027 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMRR | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Auto Lube Pump P1 Slew | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 2 | 90015715 | B1 | 1000162113 | 24.07.2027 | 10000 | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-ALBP1 | 7200 | 46150 | 2898
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Grease System Audit | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 36 | 90019204 | B1 | 1000213677 | 08.08.2027 | 4000 | CCK-MP-EXCV-EX8106-GRSYST-GRINJ | 7200 | 40923 | 7881
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Operators Seat | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 17 | 90015711 | B1 | 1000162112 | 17.09.2027 | 8000 | CCK-MP-EXCV-EX8106-STRUCT-CABIN-SEATS | 7200 | 46150 | 1397
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Swing Pmp Swg Mtr - Repl | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 144 | 90015705 | B1 | 1000162105 | 22.09.2027 | 8000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HSPSM | 7200 | 46150 | 1397
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Work Pumps-Valves - Repl | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 48 | 90015704 | B1 | 1000162104 | 22.09.2027 | 8000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HWPVV | 7200 | 46150 | 1373
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Replace Minestar Harness | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 43.5 | 90018769 | B2 | 1000281581 | 22.09.2027 | 4000 | CCK-MP-EXCV-EX8106-MANGMT-UMMMC | 7200 | 46150 | 15686
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Valve pressure Limiting Y4 | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 4 | 90019283 | B1 | 1000196178 | 22.09.2027 | 8000 | CCK-MP-EXCV-EX8106-HYDSYS-HDVLV-VVPLV | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Track Tension Tuning - Adjust | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 9 | 90020546 | B1 | 1000213054 | 22.10.2027 | 6 Monthly | CCK-MP-EXCV-EX8106-UNDERC
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Power Pack Module 1 Midlife | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 94 | 90026626 | B1 | 1000267714 | 10.12.2027 | 8000 | CCK-MP-EXCV-EX8106-FRENGN | 7200 | 46150 | 15799
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Power Pack Module 2 Midlife | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 94 | 90026626 | B1 | 1000267717 | 10.12.2027 | 8000 | CCK-MP-EXCV-EX8106-RRENGN | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Track Hyd Tensioner RH | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 28 | 90015670 | B1 | 1000162037 | 22.01.2028 | 16000 | CCK-MP-EXCV-EX8106-UNDERC-TKFRR-TENSR | 7200 | 46150 | 24979
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Track Hyd Tensioner LH | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 28 | 90015670 | B1 | 1000162035 | 25.01.2028 | 16000 | CCK-MP-EXCV-EX8106-UNDERC-TKFRL-TENSL | 7200 | 46150 | 24236
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 12M Hydraulic Service & Repairs | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 30 | 90019301 | B1 | 1000196308 | 19.02.2028 | 12 Monthly | CCK-MP-EXCV-EX8106-HYDSYS
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Grease Block & Injectors Repl | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 84 | 90020364 | B1 | 1000213676 | 27.02.2028 | 16000 | CCK-MP-EXCV-EX8106-GRSYST-GRINJ | 7200 | 40923 | 7881
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Air Conditioner Unit Rear | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 20 | 90019235 | B1 | 1000195718 | 29.02.2028 | 24 Monthly | CCK-MP-EXCV-EX8106-STRUCT-CABIN-AIRC2
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Air Conditioner Unit Front | 2028-01-05 | 2028-01-17 | 282 hrs | FY28 | 21 | 90019234 | B1 | 1000195717 | 03.03.2028 | 24 Monthly | CCK-MP-EXCV-EX8106-STRUCT-CABIN-AIRC1
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 - ENGINE & MAJOR COMPONENTS | 2028-01-10 | 2028-01-20 | 240 hrs | FY28
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Operators Seat | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 8 | 90018835 | B1 | 1000225852 | 20.11.2027 | 6000 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN-SEATS | 5000 | 23802 | 5679
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Steer Clutch & Brake Assm LH | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 32 | 90018830 | B1 | 1000225858 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-BRKSTR-SCABL | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Steer Clutch & Brake Assm RH | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 32 | 90018830 | B1 | 1000225859 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-BRKSTR-SCABR | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Engine Cat C27 | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 82 | 90018843 | B1 | 1000225832 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-ENGINE | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Radiator Engine Cooling | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 48 | 90018824 | B1 | 1000225854 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-ENGINE-COSYS-RADTR | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Aftercooler Engine | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 8 | 90018836 | B1 | 1000225814 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-ENGINE-INTEX-AFTER | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Wash Engine Pre Cleaners | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 2 | 90018848 | B1 | 1000225836 | 17.02.2028 | 9000 | CCK-MP-DOZR-DZ8235-ENGINE-INTEX-AIRFL
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Final Drive LH | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 48 | 90018829 | B1 | 1000225842 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-FDRSYS-FDRLH | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Final Drive RH | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 48 | 90018829 | B1 | 1000225843 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-FDRSYS-FDRRH | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Cyl Blade Lift LH | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 14 | 90018821 | B1 | 1000225817 | 17.02.2028 | 9000 | CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-BLCYL | 5000 | 23802 | 1067
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Hyd Oil Cooler | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 10 | 90018834 | B1 | 1000225848 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-HYDSYS-HDOCO | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Reseal Hydraulic Tank | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 48 | 90018838 | B1 | 1000225849 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-HYDSYS-HDTNK | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Hyd Pump Cooling Fan | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 16 | 90018832 | B1 | 1000225846 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYFPP | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Air Conditioner Overhaul | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 48 | 90018854 | B1 | 1000225827 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN-AIRCN | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Equaliser Bar | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 96 | 90018840 | B1 | 1000225841 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-STRUCT-CHASS-EQUAL | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Drive Shaft | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 6 | 90033311 | B1 | 1000334047 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-TRNSYS-DRSHT | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Transmission | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 48 | 90018827 | B1 | 1000225862 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-TRNSYS-TRANS | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Pump Trans & TCon Charge | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 10 | 90018828 | B1 | 1000225860 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-TRNSYS-TRPMP | 5000 | 23802 | 10459
D10T2 | Onsite Shut | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Torque Converter | 2028-01-10 | 2028-01-20 | 240 hrs | FY28 | 60 | 90018826 | B1 | 1000225861 | 17.02.2028 | 18000 | CCK-MP-DOZR-DZ8235-TRNSYS-TRQUE | 5000 | 23802 | 10459
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 - ENGINE & MAJOR COMPONENTS | 2028-01-13 | 2028-01-23 | 240 hrs | FY28
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Steering Hyd Pump Secondary | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 8 | 90002719 | B2 | 1000090320 | 18.09.2027 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP04 | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Input Drive Shaft | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 12 | 90033166 | B1 | 1000333491 | 18.09.2027 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT01 | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Rear Output Drive Shaft | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 14 | 90033168 | B1 | 1000333493 | 18.09.2027 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT02 | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 12 Monthly Hydraulic Tune Up | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90015111 | B1 | 1000126197 | 22.09.2027 | 52 Weekly | CCK-MP-LOAD-WL261 -HYDSYS | 6000 | 77065 | 30681
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Brake Cooling | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 8 | 90002713 | B2 | 1000090313 | 23.09.2027 | 10000 | CCK-MP-LOAD-WL261 -BRKSYS-BRPMP-BRP02 | 6000 | 77065 | 3344
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Implement LH | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90002723 | B2 | 1000090323 | 01.10.2027 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP01 | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Implement RH | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90002724 | B2 | 1000090324 | 01.10.2027 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP02 | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Implement Centre | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90002725 | B2 | 1000090325 | 01.10.2027 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP03 | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Pilot & Cooling | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 12 | 90002726 | B2 | 1000090326 | 01.10.2027 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP04 | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Brake Accumulator Front | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 12 | 90002714 | B2 | 1000090314 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -BRKSYS-BRACC-BACCF | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Brake Accumulator Rear | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 12 | 90002714 | B2 | 1000090315 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -BRKSYS-BRACC-BACCR | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Brake | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 12 | 90002712 | B2 | 1000090312 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -BRKSYS-BRPMP-BRP01 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Overhaul Park Brake & Centre Brg | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 36 | 90002711 | B2 | 1000090343 | 02.01.2028 | 10000 | CCK-MP-LOAD-WL261 -BRKSYS-BRPRK | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Electrical Harness | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 36 | 90010123 | B2 | 1000090341 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -ELCTLV-HARNS | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Engine Cat 3516B | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 500 | 90021152 | B1 | 1000222523 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -ENGINE | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Overhaul Engine Prelube | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 10 | 90021219 | B1 | 1000222524 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -ENGINE-LUBSY-PREPP | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Overhaul Rear Axle Trunnion | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 112 | 90002709 | B2 | 1000090307 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -FDRSYS-RRDIF-TRNON | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Auto Lube Pump | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 6 | 90002737 | B2 | 1000090330 | 02.01.2028 | 10000 | CCK-MP-LOAD-WL261 -GRSYST-ALBPP | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Cyl Bucket LH Ext High Lift | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 38 | 90015438 | B2 | 1000131508 | 02.01.2028 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-BUCYL | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Cyl Bucket RH Ext High Lift | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 36 | 90015437 | B2 | 1000131509 | 02.01.2028 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-BUCYR | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Cyl Lift RH Ext High Lift | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 54 | 90002728 | B2 | 1000112666 | 02.01.2028 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-HCYLR | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hydraulic System Hoses | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 96 | 90026922 | B1 | 1000271588 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-HYDHO | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Replace Pilot System Hoses | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 96 | 90009731 | B1 | 1000090338 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-PILHO | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Oil Cooler | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 96 | 90002733 | B2 | 1000090327 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -HYDSYS-HDOCO | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Reseal Tank Hyd | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 12 | 90010623 | B2 | 1000090342 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -HYDSYS-HDTNK-HYT01 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Valve Implement Ctrl LH | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90010965 | B2 | 1000112588 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -HYDSYS-HDVLV-HYV01 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Valve Implement Ctrl RH | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90010966 | B2 | 1000112595 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -HYDSYS-HDVLV-HYV02 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pilot Accumulator | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 4 | 90012174 | B2 | 1000112609 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -HYDSYS-PACCM | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Steering Neutralizer Valves | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 6 | 90002720 | B2 | 1000090335 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STNVS | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Steer & Brake Oil Cooler Pump | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 8 | 90002718 | B2 | 1000090319 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP03 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Reseal Steering & Brake Tank | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 36 | 90010963 | B2 | 1000112581 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STTNK | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Overhaul Air Conditioner | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 48 | 90021132 | B1 | 1000222521 | 02.01.2028 | 10000 | CCK-MP-LOAD-WL261 -STRUCT-CABIN-AIRCN | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Front Drive Shaft | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 16 | 90033175 | B1 | 1000333497 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT04 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Shaft Rear PD To Cntr Brng | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90033191 | B1 | 1000333499 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT05 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Front Pump Drv Drive Shaft | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 16 | 90033189 | B1 | 1000333501 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT06 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Gearbox Pump Drive Rear | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 326 | 90002706 | B2 | 1000090304 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-PMPDR-RRPDR | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Transmission Oil Cooler | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 36 | 90002695 | B2 | 1000090293 | 02.01.2028 | 20000 | CCK-MP-LOAD-WL261 -TRNSYS-TROLC | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Transmission Charge Pump | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 12 | 90002694 | B2 | 1000090292 | 02.01.2028 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-TRPMP | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Brake Oil Cooler | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 72 | 90002715 | B2 | 1000090316 | 06.01.2028 | 20000 | CCK-MP-LOAD-WL261 -BRKSYS-BROCC | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Steering LH | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 36 | 90002716 | B2 | 1000090317 | 06.01.2028 | 20000 | CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP01 | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Centre Bearing Upper Shaft | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 24 | 90002702 | B2 | 1000090300 | 06.01.2028 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-UCTRB | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Replace Artic Area Hyd Hosing | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 6 | 90020831 | B1 | 1000220498 | 15.02.2028 | 8 Monthly | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Brake System Hoses | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 48 | 90026921 | B1 | 1000271586 | 06.03.2028 | 20000 | CCK-MP-LOAD-WL261 -BRKSYS-BRHLF-BRKHO | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Overhaul Boom | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 96 | 90021334 | B1 | 1000223817 | 08.03.2028 | 40000 | CCK-MP-LOAD-WL261 -STRUCT-CHASS-LIARM | 6000 | 77065 | 77065
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Final Drive Position 2 | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 83 | 90002710 | B2 | 1000090309 | 12.03.2028 | 16000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR02 | 6000 | 77065 | 6591
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Operators Seat | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 4 | 90002741 | B2 | 1000090331 | 10.04.2028 | 7000 | CCK-MP-LOAD-WL261 -STRUCT-CABIN-SEATS | 6000 | 77065 | 11736
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Cyl Steering RH | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 28 | 90002722 | B2 | 1000090322 | 19.05.2028 | 12000 | CCK-MP-LOAD-WL261 -STRSYS-STRCY-STCYR | 6000 | 77065 | 13476
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Ctr Output Drive Shaft Unis | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 8 | 90033173 | B1 | 1000333496 | 30.05.2028 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT03 | 6000 | 77065 | 19291
994H | Onsite Shut | Ancillary | Fortescue | WL261 | WL261 Repl Trans System Hoses Midlife | 2028-01-13 | 2028-01-23 | 240 hrs | FY28 | 4 | 90026915 | B1 | 1000271591 | 08.06.2028 | 8000 | CCK-MP-LOAD-WL261 -TRNSYS-TRHLF-TRNHO | 6000 | 77065 | 13476
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 - SLEW BEARING, BOOM & STICK & RH ENGINE | 2028-01-19 | 2028-02-08 | 480 hrs | FY28
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Boom Arch Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 24 | 90022724 | B1 | 1000206869 | 31.12.2027 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-BMARH | 6900 | 25928 | 15977
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Boom Stick Bucket Cyl Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 136 | 90009468 | B1 | 1000344110 | 31.12.2027 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-HBSBC | 6900 | 25928 | 14431
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Cyl Boom LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 138 | 90003167 | B1 | 1000206846 | 06.01.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-BMCYL | 6900 | 25928 | 8332
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Cyl Boom RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 138 | 90003167 | B1 | 1000206847 | 06.01.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-BMCYR | 6900 | 25928 | 8332
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Engine Cool Fan LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90003164 | B1 | 1000206840 | 27.01.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-HECPL | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Boom Assembly | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 292 | 90003181 | B1 | 1000231154 | 27.01.2028 | 36000 | CCK-MP-EXCV-EX7110-STRUCT-BOOMS | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Stick Assembly | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 291 | 90003183 | B1 | 1000231304 | 27.01.2028 | 36000 | CCK-MP-EXCV-EX7110-STRUCT-STICK | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Slew Gear Bearing | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 288 | 90003193 | B1 | 1000206866 | 27.01.2028 | 36000 | CCK-MP-EXCV-EX7110-STRUCT-UNDER-SLEWB | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Radiator LH Engine | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 24 | 90017956 | B1 | 1000206811 | 29.01.2028 | 18000 | CCK-MP-EXCV-EX7110-LHENGN-COSYS-RADTR | 7100 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Fan Drive Eng Cooling Hose | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 36 | 90009469 | B2 | 1000344109 | 04.02.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-FDECH | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hydraulic Cooling Circ Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 72 | 90009471 | B2 | 1000344107 | 04.02.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-HCCHH | 6900 | 25928 | 13784
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Fan Hyd Cool Rear | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90003176 | B1 | 1000206859 | 18.03.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-FMCHR | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Auto Lube SStructure | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90018988 | B1 | 1000206903 | 21.03.2028 | 6000 | CCK-MP-EXCV-EX7110-GRSYST-ALBPP | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Grease Control Valving | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 18 | 90018990 | B1 | 1000206905 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-GRSYST-ALCON | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Hydraulic Oil Replacement | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90016793 | B1 | 1000206891 | 21.03.2028 | 6000 | CCK-MP-EXCV-EX7110-HYDSYS | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 2nd Speed Trvl Brake Release Hose | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 10 | 90022723 | B1 | 1000344112 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SSTBR | 6900 | 25928 | 12913
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Main Pump to Rotor Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 48 | 90009473 | B1 | 1000344105 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-MPRCH | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Rotor to Drive Motor Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 20 | 90022733 | B1 | 1000344102 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-RCDMH | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Rotor & Logic Valve Hp Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 36 | 90009477 | B1 | 1000344100 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-RCLVH | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Servo Hoses Cascade to Bulkhead | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 16 | 90009478 | B1 | 1000343099 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SHBLK | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Servo Hoses Cascade to Trvl Valve | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90009480 | B1 | 1000343097 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SHTRV | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Swing Motor Case Drain Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90022739 | B1 | 1000206884 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SWMCD | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Travel Motor Case Drain Hose | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 10 | 90022740 | B1 | 1000206885 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-TMCDH | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Travel LHF | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90022657 | B1 | 1000206862 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-TRMLF | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Travel LHR | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90022657 | B1 | 1000206863 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-TRMLR | 6900 | 25928 | 12913
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Main Hyd Pump Pos1 | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 54 | 90003162 | B1 | 1000206834 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-MNPP1 | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Main Hyd Pump Pos2 | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 54 | 90003162 | B1 | 1000206835 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-MNPP2 | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Main Hyd Pump Pos3 | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 54 | 90003162 | B1 | 1000206836 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-MNPP3 | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Main Hyd Pump Pos4 | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 54 | 90003162 | B1 | 1000206837 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-MNPP4 | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Swing Pos1 & Pos2 | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 42 | 90003163 | B1 | 1000206838 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-SP1P2 | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Swing Pos3 & Pos4 | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 42 | 90003163 | B1 | 1000206839 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-SP3P4 | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Swing Replenish LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 2 | 90022643 | B1 | 1000206844 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-SRPPL | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Swing Replenish RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 2 | 90022643 | B1 | 1000206845 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-SRPPR | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Pump Servo LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 2 | 90010935 | B1 | 1000206842 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-SVPPL | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Pump Servo RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 2 | 90010935 | B1 | 1000206843 | 21.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-SVPPR | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Hydraulic System Tune Up | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 24 | 90017865 | B1 | 1000206902 | 22.03.2028 | 6000 | CCK-MP-EXCV-EX7110-HYDSYS | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Stick LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 54 | 90003168 | B1 | 1000206848 | 22.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-STCLL | 6900 | 25928 | 12889
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Stick RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 54 | 90003168 | B1 | 1000206849 | 22.03.2028 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-STCLR | 6900 | 25928 | 12889
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Annual Air Con Service LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 13 | 90004141 | B1 | 1000287617 | 26.03.2028 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN-AIRCL
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Minestar Harness | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 43.5 | 90027626 | B2 | 1000281596 | 10.04.2028 | 4000 | CCK-MP-EXCV-EX7110-MANGMT-UMMMC | 6900 | 25928 | 12535
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Wiper Blades | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 2 | 90004684 | B1 | 1000206897 | 13.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Oil Suction Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 48 | 90009474 | B2 | 1000344104 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-OILSC | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl PTO Cooling Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90009475 | B2 | 1000344103 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-PTOCL | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Swing Circuit Hoses | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 16 | 90009481 | B1 | 1000206883 | 07.05.2028 | 9000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SWCRT | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Fan Hyd Cool Front | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90003176 | B1 | 1000206858 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-FMCHF | 6900 | 25928 | 6158
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Fan Engine Cool RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 18 | 90003177 | B1 | 1000206861 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-FMECR | 6900 | 25928 | 6138
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Engine Cool Fan RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 12 | 90003164 | B1 | 1000206841 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HYDPP-HECPR | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Pump Drive Gearbox LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 108 | 90003161 | B1 | 1000206832 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-PPDRL | 6900 | 25928 | 6138
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Pump Drive Gearbox RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 108 | 90003161 | B1 | 1000206833 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-PPDRR | 6900 | 25928 | 6158
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Engine Cat C32 RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 250 | 90017914 | B1 | 1000206812 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-RHENGN | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Radiator RH Engine | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 24 | 90017957 | B1 | 1000206825 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-RHENGN-COSYS-RADTR | 7100 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Track Tension Cyl LH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 60 | 90032648 | B1 | 1000206893 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-STRUCT-TKFRL-TENSR | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Track Tension Cyl RH | 2028-01-19 | 2028-02-08 | 480 hrs | FY28 | 60 | 90032648 | B1 | 1000206894 | 07.05.2028 | 18000 | CCK-MP-EXCV-EX7110-STRUCT-TKFRR-TENSR | 6900 | 25928 | 6158
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 - TRACK FRAMES & MAJOR COMPONENTS | 2028-01-24 | 2028-02-03 | 240 hrs | FY28
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Aftercooler Engine | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 8 | 90010841 | B1 | 1000108548 | 16.09.2027 | 18000 | CCK-MP-DOZR-DZ183 -ENGINE-INTEX-AFTER | 5000 | 65794 | 12584
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Final Drive LH | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 28 | 90000312 | B2 | 1000091338 | 16.09.2027 | 18000 | CCK-MP-DOZR-DZ183 -FDRSYS-FDRLH | 5000 | 65794 | 12144
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Transmission | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 48 | 90000308 | B2 | 1000091335 | 16.09.2027 | 18000 | CCK-MP-DOZR-DZ183 -TRNSYS-TRANS | 5000 | 65794 | 12584
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Actuator Brake HaulX Shield | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 50 | 90033498 | B1 | 1000337807 | 18.09.2027 | 14000 | CCK-MP-DOZR-DZ183 -MANGMT-CASYS-ACTBK
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Steer Clutch & Brake Assm LH | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000091340 | 16.10.2027 | 18000 | CCK-MP-DOZR-DZ183 -BRKSTR-SCABL | 5000 | 65807 | 12144
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Steer Clutch & Brake Assm RH | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000091341 | 16.10.2027 | 18000 | CCK-MP-DOZR-DZ183 -BRKSTR-SCABR | 5000 | 65807 | 12144
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Hyd Pump Implement | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 10 | 90000301 | B2 | 1000091342 | 16.10.2027 | 9000 | CCK-MP-DOZR-DZ183 -HYDSYS-HYDPP-HYIPP | 5000 | 65794 | 3119
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Final Drive RH | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 28 | 90000312 | B2 | 1000091339 | 17.10.2027 | 18000 | CCK-MP-DOZR-DZ183 -FDRSYS-FDRRH | 5000 | 65794 | 12144
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Minor Overhaul Track Frame LH | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 98 | 90002098 | B1 | 1000108553 | 10.11.2027 | 18000 | CCK-MP-DOZR-DZ183 -STRUCT-UNDER-TKFRL | 5000 | 65794 | 11778
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Minor Overhaul Track Frame RH | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 98 | 90010766 | B1 | 1000108555 | 10.11.2027 | 18000 | CCK-MP-DOZR-DZ183 -STRUCT-UNDER-TKFRR | 5000 | 65794 | 11778
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Fan Cooling Motor Hyd | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 16 | 90002094 | B2 | 1000108546 | 13.12.2027 | 9000 | CCK-MP-DOZR-DZ183 -HYDSYS-HDCFM | 5000 | 65794 | 2328
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Cyl Blade Lift RH | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 16 | 90000287 | B1 | 1000255695 | 13.12.2027 | 9000 | CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-BLCYR | 5000 | 65794 | 2328
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Engine Midlife Complete | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 103 | 90015859 | B1 | 1000160277 | 13.03.2028 | 9000 | CCK-MP-DOZR-DZ183 -ENGINE | 5000 | 65794 | 1433
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Major Service Air Conditioner | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 24 | 90017469 | B1 | 1000196654 | 13.03.2028 | 9000 | CCK-MP-DOZR-DZ183 -STRUCT-CABIN-AIRCN | 5000 | 65794 | 25789
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Operators Seat | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 8 | 90000318 | B1 | 1000108547 | 18.03.2028 | 6000 | CCK-MP-DOZR-DZ183 -STRUCT-CABIN-SEATS | 5000 | 65794 | 4209
D10T | Onsite Shut | Ancillary | Fortescue | DZ183 | DZ183 Repl Pump Trans & TCon Charge | 2028-01-24 | 2028-02-03 | 240 hrs | FY28 | 10 | 90000302 | B2 | 1000091337 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ183 -TRNSYS-TRPMP | 5000 | 65794 | 9873
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2028-01-25 | 2028-02-03 | 216 hrs | FY28
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Transmission Oil Cooler | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 12 | 90010097 | B1 | 1000083487 | 06.08.2027 | 18000 | CCK-MP-HAUL-DT153 -TRNSYS-TROLC | 7400 | 84230 | 21949
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Auto Lube Pump | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 3 | 90002391 | B1 | 1000285793 | 03.10.2027 | 8000 | CCK-MP-HAUL-DT153 -GRSYST-ALBPP | 7400 | 84230 | 7415
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Engine Midlife Complete | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 62 | 90015886 | B1 | 1000161156 | 06.10.2027 | 12000 | CCK-MP-HAUL-DT153 -ENGINE | 7400 | 84181 | 51293
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Tyre Sense Battery | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 2 | 90017022 | B1 | 1000153164 | 13.10.2027 | 24 Monthly | CCK-MP-HAUL-DT153 -MANGMT-TYRSN
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Service Air Conditioner 12M | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 18 | 90018230 | B1 | 1000174181 | 14.10.2027 | 12 Monthly | CCK-MP-HAUL-DT153 -STRUCT-CABIN-AIRCN | 7400 | 84230 | 34787
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Transmisson Calibration | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 8 | 90029836 | B1 | 1000298733 | 15.11.2027 | 4500 | CCK-MP-HAUL-DT153 -TRNSYS-TRANS | 7400 | 84230 | 2506
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Wheel Group Front RH | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 54 | 90017287 | B1 | 1000157257 | 21.11.2027 | 24000 | CCK-MP-HAUL-DT153 -STRUCT-AXLES-HUBRH | 7400 | 84181 | 14402
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl AOC Fan Motor Rear | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 6 | 90002376 | B1 | 1000026607 | 23.12.2027 | 12000 | CCK-MP-HAUL-DT153 -FDRSYS-AXLEC-HYM02 | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Radiator Engine Cooling | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 62 | 90031072 | B1 | 1000307534 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -ENGINE-COSYS-RADTR | 7400 | 84230 | 34787
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Pump Drive | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 39 | 90002365 | B1 | 1000026594 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -ENGINE-PMPDR | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Wheel End LH | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 58.5 | 90002374 | B1 | 1000026604 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -FDRSYS-FDRVE-FDRLH | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Motor Lube Axle Rear & Hoses | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 8 | 90026943 | B1 | 1000272023 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -FDRSYS-AXLEC-HYM01 | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Axle Lube Hyd Pump | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 4 | 90010102 | B1 | 1000083489 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -FDRSYS-AXLEC-HYPUM | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Overhaul Accumulator Brake LHF | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000026608 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-BACCM-FRLFT | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Overhaul Accumulator Brake RHF | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000026609 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-BACCM-FRRGT | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Overhaul Accumulator Brake Rear | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000026610 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-BACCM-BACCR | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Overhaul Valve Control Brake | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 20 | 90002380 | B2 | 1000026612 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-BRVLV | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Brake Oil Cooler Front | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 13 | 90010109 | B1 | 1000083496 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-BROCO-BROCF | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Brake Oil Cooler Rear | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 13 | 90010108 | B1 | 1000083495 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-BROCO-BROCR | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Motor Brake Oil Cooling | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 3 | 90002381 | B1 | 1000026613 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-BROCO-HYMO1 | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Hyd Pump Steering Main & Fan | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 17 | 90002383 | B1 | 1000026616 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -STRSYS-STPMP | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Steering HMU | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 8 | 90002384 | B1 | 1000026617 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -STRSYS-STHMU | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Ovhl Accumulator Steering Front | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000026620 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -STRSYS-STACC-SACCF | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Ovhl Accumulator Steering Middle | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000026621 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -STRSYS-STACC-SACCM | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Ovhl Accumulator Steering Rear | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000026622 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -STRSYS-STACC-SACCR | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Pump Hoist & Brake | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 15 | 90002388 | B1 | 1000026625 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -HYDSYS-HOPMP | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Rear Axle Linkages | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 113 | 90002396 | B1 | 1000026634 | 04.01.2028 | 24000 | CCK-MP-HAUL-DT153 -STRUCT-CHASS-AXLIK | 7400 | 84230 | 13523
793F | Onsite Shut | Haul | Fortescue | DT153 | DT153 Repl Spider Trans Driveshaft | 2028-01-25 | 2028-02-03 | 216 hrs | FY28 | 12 | 90017211 | B1 | 1000154982 | 04.01.2028 | 6000 | CCK-MP-HAUL-DT153 -FDRSYS-DRSHT-UNVSL | 7400 | 84230 | 2506
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 - ENGINE, MAST MODULE & MAJOR COMPONENTS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Mast Module | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 384 | 90020218 | B1 | 1000302724 | 04.06.2027 | 40000 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Equaliser Bar TRL | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 32 | 90030390 | B1 | 1000303370 | 04.06.2027 | 40000 | CCK-MP-DRLL-DR2113-STRUCT-UNDER-EQUAL | 6800 | 33986 | 33986
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Battery Cables | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90028942 | B1 | 1000289026 | 14.10.2027 | 15000 | CCK-MP-DRLL-DR2113-ELCTLV-HARNS | 6800 | 34008 | 16998
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl ADS LiDAR | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 4 | 90029065 | B1 | 1000290902 | 25.10.2027 | 5000 | CCK-MP-DRLL-DR2113-ADSYST-ADSPR-LIDAR | 6800 | 34008 | 10800
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack RHF NDE CS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90030670 | B1 | 1000214058 | 27.10.2027 | 6000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYRF | 6800 | 33987 | 306
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl ADS Harnesses | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 43.5 | 90029073 | B1 | 1000290903 | 17.11.2027 | 20000 | CCK-MP-DRLL-DR2113-ADSYST-HARNC | 6800 | 34008 | 10800
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl ADS Field Instruments | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 7.5 | 90029064 | B1 | 1000290897 | 17.11.2027 | 20000 | CCK-MP-DRLL-DR2113-ADSYST-ADSIS | 6800 | 34008 | 34008
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Mast ADS Hardware | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 49 | 90029071 | B1 | 1000290892 | 17.11.2027 | 20000 | CCK-MP-DRLL-DR2113-ADSYST-ADSHW | 6800 | 34008 | 10800
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cabin ADS Components | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 58.5 | 90029058 | B1 | 1000290896 | 17.11.2027 | 20000 | CCK-MP-DRLL-DR2113-ADSYST-ADSHW-HMIJK | 6800 | 34008 | 34008
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl ADS 3D Sensor Harness | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 2 | 90029068 | B1 | 1000290900 | 17.11.2027 | 20000 | CCK-MP-DRLL-DR2113-ADSYST-ADSPR | 6800 | 34008 | 34008
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Idler & Recoil Gp NCS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 8 | 90030377 | B1 | 1000303484 | 18.11.2027 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-IDLLH | 6800 | 33987 | 10801
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Idler & Recoil Gp CS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 8 | 90030377 | B1 | 1000303500 | 18.11.2027 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-IDLRH | 6800 | 33987 | 10801
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Main Air Compressor LP | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 50 | 90020192 | B1 | 1000214055 | 24.11.2027 | 15000 | CCK-MP-DRLL-DR2113-AIRSYS-COMPR | 6800 | 34008 | 548
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cyl Mast Locking NCS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90020197 | B1 | 1000214060 | 24.11.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MLCYL | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cyl Mast Locking CS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90030657 | B1 | 1000214061 | 24.11.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MLCYR | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cyl Mast Raise CS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 32 | 90020198 | B1 | 1000213975 | 24.11.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MRCYR | 6800 | 33987 | 16998
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Hyd Pump Fan Oil Cooler LH | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 2 | 90020239 | B1 | 1000214073 | 24.11.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-FANP1 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Hyd Pump Fan Engine Cool RH | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 2 | 90020240 | B1 | 1000214074 | 24.11.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-FANP2 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Pump Charge | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 2 | 90020232 | B1 | 1000214069 | 24.11.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-MNPP3 | 6800 | 33987 | 2582
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Sprocket LH | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90020186 | B1 | 1000302909 | 24.11.2027 | 10000 | CCK-MP-DRLL-DR2113-TRAVEL-SPRKL | 6800 | 33987 | 2582
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Sprocket RH | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90020186 | B1 | 1000302910 | 24.11.2027 | 10000 | CCK-MP-DRLL-DR2113-TRAVEL-SPRKR | 6800 | 33987 | 2582
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Drive Shaft Pump Drive | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 12 | 90028862 | B1 | 1000287874 | 08.12.2027 | 5000 | CCK-MP-DRLL-DR2113-HYDSYS-PMPDG-DRSHT | 6800 | 33987 | 2582
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Pump Water Inj | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 4 | 90031899 | B1 | 1000315425 | 22.12.2027 | 7500 | CCK-MP-DRLL-DR2113-DSTSUP-WTRPP | 6800 | 33987 | 306
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Washdown Pump | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 8 | 90030681 | B1 | 1000305724 | 13.02.2028 | 7500 | CCK-MP-DRLL-DR2113-DSTSUP-WSHPP | 6800 | 33987 | 9462
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Mast Cables | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 64 | 90030334 | B1 | 1000302727 | 19.02.2028 | 2500 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Engine Assy Caterpillar C32 | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 154 | 90020393 | B1 | 1000214037 | 20.02.2028 | 15000 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Service 12M Air Conditioner | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 12 | 90028298 | B1 | 1000283157 | 21.03.2028 | 12 Monthly | CCK-MP-DRLL-DR2113-STRUCT-CABIN-AIRCN | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Chassis Harnesses | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 208 | 90028946 | B1 | 1000289027 | 22.03.2028 | 15000 | CCK-MP-DRLL-DR2113-ELCTLV-HARNS | 6800 | 34008 | 16998
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cyl Mast Raise NCS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 32 | 90030659 | B1 | 1000214062 | 02.06.2028 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MRCYL | 6800 | 33987 | 1834
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Compressor Harnesses | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 12 | 90028948 | B1 | 1000289029 | 02.06.2028 | 15000 | CCK-MP-DRLL-DR2113-ELCTLV-HARNS | 6800 | 34008 | 16998
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cab Harnesses | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 14 | 90028947 | B1 | 1000289028 | 02.06.2028 | 15000 | CCK-MP-DRLL-DR2113-ELCTLV-HARNS | 6800 | 34008 | 16998
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Radiator Cooler Module | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90021617 | B1 | 1000226509 | 29.06.2028 | 30000 | CCK-MP-DRLL-DR2113-ENGINE-COSYS-RADTR | 6800 | 33987 | 16493
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack LHF NDE NCS | 2028-01-30 | 2028-02-07 | 186 hrs | FY28 | 24 | 90020196 | B1 | 1000214056 | 29.06.2028 | 6000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLF | 6800 | 33987 | 1040
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 - POWER PACK MIDLIFE & MINOR COMPONENTS | 2028-02-02 | 2028-02-14 | 282 hrs | FY28
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Ovhl 24M Air Conditioner Sys1 Eng | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 49 | 90035243 | B1 | 1000359790 | 15.09.2027 | 24 Monthly | CCK-MP-EXCV-EX7136-STRUCT-CABIN-AIRC1
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Stick Cyl | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 48 | 90030737 | B1 | 1000306945 | 10.10.2027 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HSTCL | 7200 | 19274 | 7384
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Bucket RH Lift | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 54 | 90030726 | B1 | 1000306991 | 15.10.2027 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-BUCYR | 7200 | 19274 | 11264
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Boom Cyl | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 72 | 90030735 | B1 | 1000306944 | 04.11.2027 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HBMCL | 7200 | 19274 | 6872
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Bucket Cyl | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 54 | 90030738 | B1 | 1000306946 | 05.11.2027 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HBKCL | 7200 | 19274 | 6848
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Grease Tank Level Valve | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 2 | 90015003 | B2 | 1000306963 | 07.11.2027 | 12 Monthly | CCK-MP-EXCV-EX7136-GRSYST-AUTLU-GRTNK | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Track Tension Tuning-Adjust | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 9 | 90020545 | B1 | 1000306996 | 08.11.2027 | 6 Monthly | CCK-MP-EXCV-EX7136-UNDERC | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 12 | 90035479 | B1 | 1000359911 | 15.11.2027 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 12M Hydraulic Service & Repairs | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 30 | 90014448 | B2 | 1000306961 | 26.12.2027 | 12 Monthly | CCK-MP-EXCV-EX7136-HYDSYS | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Boom Module Quarter Life | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 48 | 90027377 | B1 | 1000307011 | 08.01.2028 | 10000 | CCK-MP-EXCV-EX7136-STRUCT-BOOMS | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Operators Seat | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 17 | 90030739 | B1 | 1000306947 | 19.01.2028 | 10000 | CCK-MP-EXCV-EX7136-STRUCT-CABIN-SEATO | 7200 | 19274 | 9362
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Power Pack Module Midlife | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 307.5 | 90031019 | B1 | 1000307005 | 24.01.2028 | 10000 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Grease Injectors | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 84 | 90030744 | B1 | 1000306958 | 24.01.2028 | 10000 | CCK-MP-EXCV-EX7136-GRSYST-GRINJ | 7200 | 19274 | 6872
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Rotary Connection Hoses | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 96 | 90030432 | B1 | 1000307015 | 24.01.2028 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Hyd Vlve Bank Module Quarter Life | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 15 | 90027371 | B1 | 1000307009 | 24.01.2028 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDVLV-MCVLU | 7200 | 19274 | 8502
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 12 | 90035479 | B1 | 1000359911 | 30.01.2028 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Batteries | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 9 | 90017122 | B1 | 1000306997 | 13.02.2028 | 12 Monthly | CCK-MP-EXCV-EX7136-ELCTLV-CHARG-BATST | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Svc 12M Air Conditioner Sys2 Hyd | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 12 | 90035242 | B1 | 1000359791 | 20.02.2028 | 12 Monthly | CCK-MP-EXCV-EX7136-STRUCT-CABIN-AIRC2
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Stick LH | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 54 | 90030724 | B1 | 1000306988 | 15.04.2028 | 16000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-STCLL | 7200 | 19274 | 3654
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Stick RH | 2028-02-02 | 2028-02-14 | 282 hrs | FY28 | 54 | 90030724 | B1 | 1000306989 | 04.05.2028 | 16000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-STCLR | 7200 | 19274 | 980
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2028-02-07 | 2028-02-17 | 240 hrs | FY28
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Brake System Hoses Midlife | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 4 | 90026908 | B1 | 1000271664 | 26.08.2027 | 10000 | CCK-MP-LOAD-WL7104-BRKSYS-BRHLF-BRKHO | 4000 | 64060 | 8512
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Cyl Lift RH High Lift | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 48 | 90002727 | B2 | 1000138266 | 29.08.2027 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-HCYLR | 4000 | 64060 | 5258
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Artic Area Hyd Hosing | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 6 | 90020831 | B1 | 1000364487 | 29.08.2027 | 8 Monthly | CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 12 Monthly Hydraulic Tune Up | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 24 | 90015111 | B1 | 1000364486 | 06.09.2027 | 52 Weekly | CCK-MP-LOAD-WL7104-HYDSYS
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Auto Lube Pump | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 6 | 90002737 | B2 | 1000138268 | 30.09.2027 | 10000 | CCK-MP-LOAD-WL7104-GRSYST-ALBPP | 4000 | 64060 | 15309
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Implement Pump Centre | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 24 | 90002725 | B2 | 1000138263 | 15.10.2027 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP03 | 4000 | 64060 | 3297
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Implement Pump RH | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 24 | 90002724 | B2 | 1000138262 | 04.11.2027 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP02 | 4000 | 64060 | 3297
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Transmission Pump | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 12 | 90002694 | B2 | 1000138232 | 08.11.2027 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-TRPMP | 4000 | 64060 | 4736
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Pump Drive Gearbox Front | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 74 | 90002705 | B2 | 1000138242 | 05.01.2028 | 16000 | CCK-MP-LOAD-WL7104-TRNSYS-PMPDR-FRPDR | 4000 | 64060 | 9837
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Differential Front | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 114 | 90002707 | B2 | 1000138244 | 17.01.2028 | 20000 | CCK-MP-LOAD-WL7104-FDRSYS-FRDIF | 4000 | 64060 | 14276
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Fr Pump Drv Shaft Unis | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 8 | 90033190 | B1 | 1000333658 | 09.02.2028 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT06 | 4000 | 64060 | 3453
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Implement Pump LH | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 24 | 90002723 | B2 | 1000138261 | 23.02.2028 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP01 | 4000 | 64060 | 3297
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Pilot Hyd Cooling Pump | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 12 | 90002726 | B2 | 1000138264 | 23.02.2028 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP04 | 4000 | 64060 | 3297
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Brake Cooling Pump | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 8 | 90002713 | B2 | 1000138252 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-BRKSYS-BRPMP-BRP02 | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Engine Midlife complete | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 170 | 90021253 | B1 | 1000222770 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-ENGINE | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Cyl Bucket LH High Lift | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 36 | 90017978 | B1 | 1000184469 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-BUCYL | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Cyl Bucket RH High Lift | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 36 | 90017977 | B1 | 1000184470 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-BUCYR | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Cyl Lift LH High Lift | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 48 | 90002727 | B2 | 1000138265 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-HCYLL | 4000 | 64060 | 5258
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Overhaul Air Conditioner | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 48 | 90021132 | B1 | 1000222763 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-STRUCT-CABIN-AIRCN | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Front Drive Shaft Unis | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 8 | 90033188 | B1 | 1000333654 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT04 | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 8 | 90033193 | B1 | 1000333656 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT05 | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Centre Bearing Upper Shaft | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 24 | 90002702 | B2 | 1000138240 | 08.03.2028 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-UCTRB | 4000 | 64060 | 3143
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Torque Converter | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 48 | 90002693 | B2 | 1000138230 | 13.03.2028 | 20000 | CCK-MP-LOAD-WL7104-TRNSYS-TRQUE | 4000 | 64060 | 13091
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Artic Area Hyd Hosing | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 6 | 90020831 | B1 | 1000364487 | 25.04.2028 | 8 Monthly | CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL7104 | WL7104 Repl Transmission System Hoses | 2028-02-07 | 2028-02-17 | 240 hrs | FY28 | 96 | 90026923 | B1 | 1000271667 | 21.05.2028 | 16000 | CCK-MP-LOAD-WL7104-TRNSYS-TRHLF-TRNHO | 4000 | 64060 | 7889
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2028-02-07 | 2028-02-16 | 216 hrs | FY28
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Front Wheel Bearings RH | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 44 | 90017285 | B1 | 1000157268 | 07.08.2027 | 16000 | CCK-MP-HAUL-DT161 -STRUCT-AXLES-FWBRH | 7400 | 80609 | 10780
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Brake Slack Adjuster Rear | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 4 | 90002382 | B1 | 1000027143 | 16.09.2027 | 20000 | CCK-MP-HAUL-DT161 -BRKSYS-SLACK-SLACR | 7400 | 80609 | 11737
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Hyd Pump Steering Main & Fan | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 17 | 90002383 | B1 | 1000027144 | 12.12.2027 | 24000 | CCK-MP-HAUL-DT161 -STRSYS-STPMP | 7400 | 80609 | 13960
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Spider Trans Driveshaft | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 12 | 90017211 | B1 | 1000154994 | 12.12.2027 | 6000 | CCK-MP-HAUL-DT161 -FDRSYS-DRSHT-UNVSL | 7400 | 80609 | 1574
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Front Wheel Bearings LH | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 44 | 90017284 | B1 | 1000157180 | 30.12.2027 | 16000 | CCK-MP-HAUL-DT161 -STRUCT-AXLES-FWBLH | 7400 | 80609 | 12749
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Engine Midlife Complete | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 62 | 90015886 | B1 | 1000156080 | 31.12.2027 | 12000 | CCK-MP-HAUL-DT161 -ENGINE | 7400 | 80609 | 1574
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Motor Lube Axle Hoses | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 4 | 90026944 | B1 | 1000272036 | 31.12.2027 | 12000 | CCK-MP-HAUL-DT161 -FDRSYS-AXLEC-HYM01 | 7400 | 80609 | 1574
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl AOC Fan Motor Rear | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 6 | 90002376 | B1 | 1000027135 | 31.12.2027 | 12000 | CCK-MP-HAUL-DT161 -FDRSYS-AXLEC-HYM02 | 7400 | 80609 | 1574
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Cyl Suspension LHR | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 39 | 90002409 | B1 | 1000027169 | 03.01.2028 | 28000 | CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYLR | 7400 | 80609 | 17509
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Transmission | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 39 | 90026996 | B2 | 1000272361 | 20.02.2028 | 18000 | CCK-MP-HAUL-DT161 -TRNSYS-TRANS | 7400 | 80609 | 12241
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Wheel End RH | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 58.5 | 90007352 | B1 | 1000027133 | 06.03.2028 | 24000 | CCK-MP-HAUL-DT161 -FDRSYS-FDRVE-FDRRH | 7400 | 80609 | 12221
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Repl Pump Brake Cooling | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 17 | 90002379 | B1 | 1000027139 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT161 -BRKSYS-HYFPP | 7400 | 80609 | 11737
793F | Onsite Shut | Haul | Fortescue | DT161 | DT161 Service Air Conditioner 12M | 2028-02-07 | 2028-02-16 | 216 hrs | FY28 | 18 | 90018230 | B1 | 1000174186 | 14.05.2028 | 12 Monthly | CCK-MP-HAUL-DT161 -STRUCT-CABIN-AIRCN | 7400 | 80609 | 1574
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 - ENGINE & MAJOR COMPONENTS | 2028-02-16 | 2028-02-25 | 216 hrs | FY28
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Wheel Group Front LH | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 54 | 90017286 | B1 | 1000157189 | 04.09.2027 | 24000 | CCK-MP-HAUL-DT5202-STRUCT-AXLES-HUBLH | 7400 | 84333 | 15833
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Wheel Group Front RH | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 54 | 90017287 | B1 | 1000157277 | 04.09.2027 | 24000 | CCK-MP-HAUL-DT5202-STRUCT-AXLES-HUBRH | 7400 | 84333 | 15833
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Transmisson Calibration | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 8 | 90029836 | B1 | 1000298744 | 06.10.2027 | 4500 | CCK-MP-HAUL-DT5202-TRNSYS-TRANS | 7400 | 84333 | 975
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Auto Lube Pump | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 3 | 90002391 | B1 | 1000285803 | 09.11.2027 | 8000 | CCK-MP-HAUL-DT5202-GRSYST-ALBPP | 7400 | 84333 | 6577
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Spider Trans Driveshaft | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 12 | 90017211 | B1 | 1000155002 | 03.12.2027 | 6000 | CCK-MP-HAUL-DT5202-FDRSYS-DRSHT-UNVSL | 7400 | 84333 | 7715
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Pump Brake Cooling | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 17 | 90002379 | B1 | 1000111929 | 06.01.2028 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-HYFPP | 7400 | 84333 | 16149
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Overhaul Accumulator Brake Rear | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000111928 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-BACCM-BACCR | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Overhaul Accumulator Brake LHF | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000111926 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-BACCM-FRLFT | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Overhaul Accumulator Brake RHF | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 11 | 90002378 | B1 | 1000111927 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-BACCM-FRRGT | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Replace Brake System Hoses | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 90 | 90010129 | B4 | 1000111971 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-BRHLF-BRHOS | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Motor Brake Oil Cooling | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 3 | 90002381 | B1 | 1000111931 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-BROCO-HYMO1 | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Overhaul Valve Control Brake | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 20 | 90002380 | B2 | 1000111930 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-BRVLV | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Engine Cat C175-16 | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 137 | 90015881 | B1 | 1000156099 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-ENGINE | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Radiator Engine Cooling | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 62 | 90031072 | B1 | 1000307550 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-ENGINE-COSYS-RADTR | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Motor Lube Axle Rear & Hoses | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 8 | 90026943 | B1 | 1000272045 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYM01 | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl AOC Fan Motor Rear | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 6 | 90002376 | B1 | 1000111925 | 09.01.2028 | 12000 | CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYM02 | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Axle Lube Hyd Pump | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 4 | 90010102 | B1 | 1000111963 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYPUM | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Wheel End LH | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 58.5 | 90002374 | B1 | 1000111922 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-FDRSYS-FDRVE-FDRLH | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Wheel End RH | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 58.5 | 90007352 | B1 | 1000111923 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-FDRSYS-FDRVE-FDRRH | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Replace Hoses Hoist System | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 40 | 90010105 | B1 | 1000111965 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-HYDSYS-HDHLF-HSTHO | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Ovhl Accumulator Steering Front | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000111938 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-STRSYS-STACC-SACCF | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Ovhl Accumulator Steering Middle | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000111939 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-STRSYS-STACC-SACCM | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Ovhl Accumulator Steering Rear | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 12 | 90002386 | B1 | 1000111940 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-STRSYS-STACC-SACCR | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Steering HMU | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 8 | 90002384 | B1 | 1000111935 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-STRSYS-STHMU | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Rear Axle Linkages | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 113 | 90002396 | B1 | 1000111948 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-STRUCT-CHASS-AXLIK | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Drive Line Axle LH | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 4 | 90014919 | B1 | 1000124633 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-FDRSYS-DRLAX-AXLLH | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Drive Line Axle RH | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 4 | 90014943 | B1 | 1000124634 | 09.01.2028 | 24000 | CCK-MP-HAUL-DT5202-FDRSYS-DRLAX-AXLRH | 7400 | 84333 | 13327
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Repl Steering Bell Crank & Links | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 36 | 90028566 | B1 | 1000317662 | 14.02.2028 | 30000 | CCK-MP-HAUL-DT5202-STRSYS-STLTR-STLAC | 7400 | 84333 | 7715
793F | Onsite Shut | Haul | Fortescue | DT5202 | DT5202 Service Air Conditioner 12M | 2028-02-16 | 2028-02-25 | 216 hrs | FY28 | 18 | 90018230 | B1 | 1000174191 | 19.02.2028 | 12 Monthly | CCK-MP-HAUL-DT5202-STRUCT-CABIN-AIRCN | 7400 | 84333 | 13327
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 - POWER PACK MIDLIFES & MINOR COMPONENTS | 2028-02-16 | 2028-02-28 | 282 hrs | FY28
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Grease System Audit | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 36 | 90019204 | B1 | 1000213679 | 02.11.2027 | 4000 | CCK-MP-EXCV-EX8107-GRSYST-GRINJ | 7200 | 41901 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Bucket RH Lift | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 48 | 90015689 | B1 | 1000162223 | 02.11.2027 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-BUCYR | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Operators Seat | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 17 | 90015711 | B1 | 1000162261 | 09.11.2027 | 8000 | CCK-MP-EXCV-EX8107-STRUCT-CABIN-SEATO | 7200 | 46126 | 6810
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Work Pumps-Valves - Repl | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 48 | 90015704 | B1 | 1000162253 | 28.11.2027 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HWPVV | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Rotary Connection | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 50 | 90015692 | B1 | 1000162228 | 28.11.2027 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-ROTRY | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Power Pack Module 1 Midlife | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 94 | 90026626 | B1 | 1000267761 | 13.12.2027 | 8000 | CCK-MP-EXCV-EX8107-FRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Power Pack Module 2 Midlife | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 94 | 90026626 | B1 | 1000267769 | 13.12.2027 | 8000 | CCK-MP-EXCV-EX8107-RRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Batteries | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 5 | 90019334 | 1 | 1000195274 | 10.01.2028 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-CHARG-BATRR
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Grease Tank Level Valve | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 2 | 90015003 | B4 | 1000162271 | 10.01.2028 | 12 Monthly | CCK-MP-EXCV-EX8107-GRSYST-GRTNK
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Replace Minestar Harness | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 43.5 | 90018769 | B2 | 1000281586 | 11.01.2028 | 4000 | CCK-MP-EXCV-EX8107-MANGMT-UMMMC | 7200 | 46126 | 46126
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Track Tension Tuning - Adjust | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 9 | 90020546 | B1 | 1000213055 | 19.01.2028 | 6 Monthly | CCK-MP-EXCV-EX8107-UNDERC
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel LHF | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 14 | 90015697 | B1 | 1000162241 | 19.03.2028 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMLF | 7200 | 46126 | 12211
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel LHR | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 14 | 90015697 | B1 | 1000162242 | 19.03.2028 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMLR | 7200 | 46126 | 12211
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Boom LH | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 76 | 90015686 | B1 | 1000162218 | 02.05.2028 | 16000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-BMCYL | 7200 | 46126 | 3487
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Track Hyd Tensioner LH | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 28 | 90015670 | B1 | 1000162184 | 02.05.2028 | 16000 | CCK-MP-EXCV-EX8107-UNDERC-TKFRL-TENSL | 7200 | 46126 | 3487
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Replace Grease Injectors | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 84 | 90019202 | B1 | 1000195348 | 22.05.2028 | 8000 | CCK-MP-EXCV-EX8107-GRSYST-GRINJ | 7200 | 41901 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Gearbox Swing LHR | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 60 | 90015674 | B4 | 1000162188 | 25.05.2028 | 15000 | CCK-MP-EXCV-EX8107-SWGSYS-SWBOX-SGBLR | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Air Conditioner Unit Front | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 21 | 90019234 | B1 | 1000195719 | 25.06.2028 | 24 Monthly | CCK-MP-EXCV-EX8107-STRUCT-CABIN-AIRC1
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Air Conditioner Unit Rear | 2028-02-16 | 2028-02-28 | 282 hrs | FY28 | 20 | 90019235 | B1 | 1000195760 | 25.06.2028 | 24 Monthly | CCK-MP-EXCV-EX8107-STRUCT-CABIN-AIRC2
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 - POWER PACK MODULE & MAJOR COMPONENTS | 2028-02-29 | 2028-03-08 | 186 hrs | FY28
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Track Frame Module LH | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 28 | 90021739 | B1 | 1000305061 | 11.07.2027 | 12000 | CCK-MP-DRLL-DR3138-STRUCT-TKFRL | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Track Frame Module RH | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 28 | 90021741 | B1 | 1000305062 | 11.07.2027 | 12000 | CCK-MP-DRLL-DR3138-STRUCT-TKFRR | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Cylinder Oscillation LH | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 8 | 90021662 | B1 | 1000304879 | 01.10.2027 | 12000 | CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-TFCOL | 5400 | 14414 | 4335
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Cylinder Oscillation RH | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 8 | 90021663 | B1 | 1000305040 | 02.10.2027 | 12000 | CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-TFCOR | 5400 | 14403 | 4335
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 XLF Repl Main Feed Chain | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 16 | 90021711 | B1 | 1000305041 | 26.10.2027 | 2500 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | 5400 | 14356 | 943
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 2 | 90020875 | B1 | 1000304875 | 16.12.2027 | 8000 | CCK-MP-DRLL-DR3138-GRSYST-ALBPP | 5400 | 14414 | 14414
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Pressure Safety Valve Cert | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 3 | 90021719 | B1 | 1000305060 | 03.01.2028 | 48 Monthly | CCK-MP-DRLL-DR3138-AIRSYS-COMPR-VCSRL | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Overhaul Air Condtioner System | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 18 | 90023285 | B1 | 1000305066 | 03.01.2028 | 24 Monthly | CCK-MP-DRLL-DR3138-STRUCT-CABIN-ACCOM | 5400 | 14414 | 7858
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Pump Rod Thread Lube | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 2 | 90021715 | B1 | 1000305059 | 10.01.2028 | 6000 | CCK-MP-DRLL-DR3138-GRSYST-RTLPP | 5400 | 14414 | 2620
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Power Pack Module | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 88 | 90026030 | B1 | 1000305068 | 30.01.2028 | 12000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Cyl Jack levelling Rear | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 6 | 90021661 | B1 | 1000304878 | 30.01.2028 | 12000 | CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-JLCYR | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Hyd Motor Feed | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 6 | 90022025 | B1 | 1000361319 | 30.01.2028 | 6000 | CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MFEED | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Valve Main Block | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 18 | 90021692 | B1 | 1000305063 | 30.01.2028 | 12000 | CCK-MP-DRLL-DR3138-HYDSYS-HDVLV-VVMBK | 5400 | 14414 | 14414
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Oscillation Valve | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 4 | 90021664 | B1 | 1000305064 | 30.01.2028 | 12000 | CCK-MP-DRLL-DR3138-HYDSYS-HDVLV-VVOST | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Timing Chain Maintenance | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 14 | 90022023 | B1 | 1000361317 | 30.01.2028 | 3000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHP | 5400 | 14414 | 7858
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Feed Chain Sprockets | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 24 | 90022030 | B1 | 1000361318 | 30.01.2028 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHS | 5400 | 14414 | 7858
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Hose Drum Sprocket | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 6 | 90022032 | B1 | 1000361482 | 30.01.2028 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDHDS | 5400 | 14414 | 7858
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Gearbox Power Head | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 32 | 90021707 | B1 | 1000361480 | 30.01.2028 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-PWRHD | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Pump Air Lubrication | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 2 | 90021656 | B1 | 1000305047 | 04.03.2028 | 6000 | CCK-MP-DRLL-DR3138-AIRSYS-COMPR-PALUB | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Pump Water Injection | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 4 | 90021716 | B1 | 1000305049 | 04.03.2028 | 6000 | CCK-MP-DRLL-DR3138-DSTSUP-WTRPP | 5400 | 14414 | 3216
D65 | Onsite Shut | Drills | Fortescue | DR3138 | DR3138 Repl Operators Seat | 2028-02-29 | 2028-03-08 | 186 hrs | FY28 | 4 | 90021702 | B1 | 1000305045 | 04.03.2028 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-CABIN-SEATS | 5400 | 14414 | 7858
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 - MAJOR COMPONENTS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cabin ADS Components | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 31.5 | 90029189 | B1 | 1000294208 | 21.12.2027 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSHW-HMIJK | 6800 | 49417 | 45632
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl ADS Ace Cabinet Components | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 44.5 | 90029187 | B1 | 1000294207 | 21.12.2027 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSHW-CLXEN | 6800 | 49417 | 45632
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 EncoderHarness Cab to Aframe Repl | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 6 | 90036144 | B1 | 1000365254 | 21.12.2027 | 5000 | CCK-MP-DRLL-DR2111-ADSYST-HARNC | 6800 | 49417 | 4564
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl ADS IO Modules | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 4 | 90029208 | B1 | 1000294206 | 21.12.2027 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSHW-ARDIO | 6800 | 49417 | 45632
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Deck ADS Elec Hardware | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 9.5 | 90029190 | B1 | 1000294205 | 21.12.2027 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSHW-ADSMF | 6800 | 49417 | 45632
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl ADS 3D sensor | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 1 | 90029207 | B1 | 1000294210 | 21.12.2027 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSPR | 6800 | 49417 | 45632
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Raise NCS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 8 | 90011666 | B1 | 1000233276 | 22.12.2027 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYL | 6800 | 49393 | 8364
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Raise CS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 8 | 90011667 | B1 | 1000233275 | 22.12.2027 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYR | 6800 | 49393 | 8364
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Angle Locking NCS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 4 | 90011670 | B1 | 1000242416 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TACYL | 6800 | 49393 | 16543
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Angle Locking CS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 4 | 90011670 | B1 | 1000242415 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TACYR | 6800 | 49393 | 16543
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Stacking 8 Spool | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 8 | 90011688 | B1 | 1000233271 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVS8S | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Stacking 11 spool | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 10 | 90011689 | B1 | 1000233272 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VV11S | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Tension Cable | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 2 | 90022224 | B1 | 1000232726 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVTNC | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Hyd Motor Screw Jack NCS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 1 | 90022221 | B1 | 1000232742 | 22.12.2027 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTL | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Hyd Motor Screw Jack CS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 1 | 90022221 | B1 | 1000232741 | 22.12.2027 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTR | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Sheaves & Cables | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 140 | 90029857 | B1 | 1000303761 | 22.12.2027 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Tower Cylinders | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 58 | 90029866 | B1 | 1000303763 | 22.12.2027 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Gearbox Power Head | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 52 | 90011716 | B1 | 1000232720 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-PWRHD | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Screw Jack Cable Tension NCS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 12 | 90022222 | B1 | 1000232724 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-SCBTL | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Screw Jack Cable Tension CS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 12 | 90022222 | B1 | 1000232725 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-SCBTR | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Rod Support | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 20 | 90022208 | B1 | 1000232732 | 22.12.2027 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-RDSPT | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Overhaul Rod Changer & Carousel | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 8 | 90029755 | B1 | 1000303765 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-CARAS | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Brkout Wrench & Fork Assy | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 38 | 90029873 | B1 | 1000303764 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-BOWRH | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Mast & A-Frame Harnesses | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 70.5 | 90030429 | B1 | 1000303766 | 22.12.2027 | 20000 | CCK-MP-DRLL-DR2111-ELCTLV-HARNS-HARCO | 6800 | 49417 | 49417
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Power Pack Quarter Life | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 68 | 90029574 | B1 | 1000295333 | 26.01.2028 | 5000 | CCK-MP-DRLL-DR2111-ENGINE | 6800 | 49411 | 11797
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Dual Counter Balance | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 2 | 90015975 | B1 | 1000144888 | 09.02.2028 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDCB | 6800 | 49393 | 16543
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Drill & Propel Control | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 6 | 90015979 | B1 | 1000144892 | 09.02.2028 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDPC | 6800 | 49393 | 26969
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl ADS PTZ Camera & LIDAR | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 10 | 90029206 | B1 | 1000294211 | 09.02.2028 | 10000 | CCK-MP-DRLL-DR2111-ADSYST-ADSPR-HTCAM | 6800 | 49417 | 19408
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Yoke Oscillation | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 24 | 90016004 | B1 | 1000144921 | 11.02.2028 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-UNDER-YKOSC | 6800 | 49393 | 8374
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Diverter NCS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 4 | 90015977 | B1 | 1000144890 | 12.02.2028 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDVL | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Valve Diverter CS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 4 | 90015978 | B1 | 1000144891 | 12.02.2028 | 20000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDVR | 6800 | 49393 | 8353
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Track Frame Module-NCS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 72 | 90022185 | B1 | 1000206475 | 12.02.2028 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-TKFRL | 6800 | 49393 | 8338
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Track Frame Module CS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 72 | 90022183 | B1 | 1000206493 | 12.02.2028 | 20000 | CCK-MP-DRLL-DR2111-STRUCT-TKFRR | 6800 | 49393 | 8364
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Jack Leg NDE NCS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 8 | 90015956 | B1 | 1000144878 | 04.03.2028 | 15000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYLF | 6800 | 49393 | 17919
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Jack Leg NDE CS | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 8 | 90015957 | B1 | 1000144879 | 04.03.2028 | 15000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYRF | 6800 | 49393 | 4564
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Water & Fuel Tank Mounts | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 20 | 90017453 | B1 | 1000160345 | 10.03.2028 | 6000 | CCK-MP-DRLL-DR2111-ENGINE-FUSYS-FULTK | 6800 | 49393 | 11797
PV271 | Onsite Shut | Drills | Fortescue | DR2111 | DR2111 Repl Pump Water Injection | 2028-03-15 | 2028-03-23 | 186 hrs | FY28 | 2 | 90016011 | B1 | 1000144924 | 28.04.2028 | 5000 | CCK-MP-DRLL-DR2111-DSTSUP-WTRPP | 6800 | 49393 | 4564
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2028-03-27 | 2028-04-06 | 240 hrs | FY28
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pilot Accumulator | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 4 | 90012174 | B2 | 1000100307 | 03.12.2027 | 20000 | CCK-MP-LOAD-WL021 -HYDSYS-PACCM | 6000 | 79974 | 32530
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Input Drive Shaft | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 12 | 90033166 | B1 | 1000332555 | 06.12.2027 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT01 | 6000 | 79997 | 11410
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pump Brake | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 12 | 90002712 | B2 | 1000028816 | 06.12.2027 | 20000 | CCK-MP-LOAD-WL021 -BRKSYS-BRPMP-BRP01 | 6000 | 79974 | 11410
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Cyl Lift LH Ext High Lift | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 54 | 90002728 | B2 | 1000028832 | 09.12.2027 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-HCYLL | 6000 | 79974 | 1272
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Cyl Steering LH | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 26 | 90002721 | B2 | 1000028826 | 18.12.2027 | 12000 | CCK-MP-LOAD-WL021 -STRSYS-STRCY-STCYL | 6000 | 41674 | 41674
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Cyl Steering RH | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 28 | 90002722 | B2 | 1000028827 | 18.12.2027 | 12000 | CCK-MP-LOAD-WL021 -STRSYS-STRCY-STCYR | 6000 | 38502 | 38502
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Operators Seat | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 4 | 90002741 | B2 | 1000028841 | 23.12.2027 | 7000 | CCK-MP-LOAD-WL021 -STRUCT-CABIN-SEATS | 6000 | 79974 | 5126
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Ctr Output Drive Shaft Unis | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 8 | 90033173 | B1 | 1000333460 | 25.12.2027 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT03 | 6000 | 79997 | 3457
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Rear Output Drive Shaft Unis | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 8 | 90033167 | B1 | 1000332558 | 27.12.2027 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT02 | 6000 | 79997 | 3457
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Replace Artic Area Hyd Hosing | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 6 | 90020831 | B1 | 1000220494 | 04.03.2028 | 8 Monthly | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Transmission Charge Pump | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 12 | 90002694 | B2 | 1000028796 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-TRPMP | 6000 | 79997 | 9602
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Centre Bearing Upper Shaft | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 24 | 90002702 | B2 | 1000028804 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-UCTRB | 6000 | 79997 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Overhaul Park Brake & Centre Brg | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 36 | 90002711 | B2 | 1000087664 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -BRKSYS-BRPRK | 6000 | 79974 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pump Brake Cooling | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 8 | 90002713 | B2 | 1000028817 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -BRKSYS-BRPMP-BRP02 | 6000 | 79974 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Steering Hyd Pump Secondary | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 8 | 90002719 | B2 | 1000028824 | 25.03.2028 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP04 | 6000 | 79974 | 9602
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Steering STIC Pilot Valve | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 12 | 90026110 | B1 | 1000028825 | 25.03.2028 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STIPV | 6000 | 79974 | 9602
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pump Implement LH | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 24 | 90002723 | B2 | 1000028828 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP01 | 6000 | 79974 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pump Implement Centre | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 24 | 90002725 | B2 | 1000028830 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP03 | 6000 | 38502 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pump Pilot & Cooling | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 12 | 90002726 | B2 | 1000028831 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP04 | 6000 | 79974 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Cyl Bucket RH Ext High Lift | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 36 | 90015437 | B2 | 1000028835 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-BUCYR | 6000 | 79974 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Auto Lube Pump | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 6 | 90002737 | B2 | 1000028839 | 25.03.2028 | 10000 | CCK-MP-LOAD-WL021 -GRSYST-ALBPP | 6000 | 79974 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Engine Midlife complete | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 170 | 90021253 | B1 | 1000222354 | 12.04.2028 | 10000 | CCK-MP-LOAD-WL021 -ENGINE | 6000 | 79997 | 19277
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Overhaul Air Conditioner | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 48 | 90021132 | B1 | 1000222345 | 12.04.2028 | 10000 | CCK-MP-LOAD-WL021 -STRUCT-CABIN-AIRCN | 6000 | 79974 | 19277
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Front Drive Shaft Unis | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 8 | 90033188 | B1 | 1000333462 | 13.04.2028 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT04 | 6000 | 79997 | 9602
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 8 | 90033193 | B1 | 1000333464 | 13.04.2028 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT05 | 6000 | 79997 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Fr Pump Drv Shaft Unis | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 8 | 90033190 | B1 | 1000333466 | 13.04.2028 | 10000 | CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT06 | 6000 | 79997 | 9602
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Brake System Hoses Midlife | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 4 | 90026908 | B1 | 1000271529 | 13.04.2028 | 10000 | CCK-MP-LOAD-WL021 -BRKSYS-BRHLF-BRKHO | 6000 | 79974 | 9601
994H | Onsite Shut | Ancillary | Fortescue | WL021 | WL021 Repl Hyd System Hoses Midlife | 2028-03-27 | 2028-04-06 | 240 hrs | FY28 | 24 | 90026914 | B1 | 1000271531 | 13.04.2028 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-HYDHO | 6000 | 79974 | 9601
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 - ENGINE & MAJOR COMPONENTS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Sprocket RH | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90020186 | B1 | 1000303010 | 27.12.2027 | 10000 | CCK-MP-DRLL-DR2129-TRAVEL-SPRKR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack LHF NDE NCS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90020196 | B1 | 1000278357 | 07.01.2028 | 6000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYLF | 6800 | 18062 | 1556
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Washdown Pump | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 8 | 90030681 | B1 | 1000305734 | 24.01.2028 | 7500 | CCK-MP-DRLL-DR2129-DSTSUP-WSHPP | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Service 12M Air Conditioner | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 12 | 90028298 | B1 | 1000283241 | 27.01.2028 | 12 Monthly | CCK-MP-DRLL-DR2129-STRUCT-CABIN-AIRCN | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Pump Drive Gearbox | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 78 | 90020181 | B1 | 1000278395 | 24.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-PMPDG | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Engine Assy Caterpillar C32 | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 154 | 90020393 | B1 | 1000278364 | 26.03.2028 | 15000 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl ADS GPS Components | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 3 | 90029061 | B1 | 1000293018 | 31.03.2028 | 30000 | CCK-MP-DRLL-DR2129-ADSYST-ADSPO | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Fish Eye Camera | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 16 | 90029067 | B1 | 1000293040 | 31.03.2028 | 10000 | CCK-MP-DRLL-DR2129-ADSYST-ADSPR-HTCAM | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl ADS LiDAR | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 4 | 90029065 | B1 | 1000293041 | 31.03.2028 | 5000 | CCK-MP-DRLL-DR2129-ADSYST-ADSPR-LIDAR | 6800 | 18062 | 13815
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Main Air Compressor LP | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 50 | 90020192 | B1 | 1000278385 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-AIRSYS-COMPR | 6800 | 18062 | 320
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Hydraulic Cooler Module | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90020220 | B1 | 1000278389 | 31.03.2028 | 30000 | CCK-MP-DRLL-DR2129-COOLER | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Radiator Cooler Module | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90021617 | B1 | 1000278390 | 31.03.2028 | 30000 | CCK-MP-DRLL-DR2129-ENGINE-COSYS-RADTR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack LHR DE NCS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90020204 | B1 | 1000278356 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYLR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack RHR DE CS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90030672 | B1 | 1000278359 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYRR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cyl Mast Locking NCS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90020197 | B1 | 1000278361 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MLCYL | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cyl Mast Locking CS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90030657 | B1 | 1000278360 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MLCYR | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cyl Mast Raise NCS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 32 | 90030659 | B1 | 1000278363 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MRCYL | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cyl Mast Raise CS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 32 | 90020198 | B1 | 1000278362 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MRCYR | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Hyd Pump Fan Oil Cooler LH | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 2 | 90020239 | B1 | 1000278396 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-FANP1 | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Hyd Pump Fan Engine Cool RH | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 2 | 90020240 | B1 | 1000278397 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-FANP2 | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Pump Main Hyd NCS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 6 | 90020235 | B1 | 1000278398 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-MNPP1 | 6800 | 18062 | 4291
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Pump Main Hyd CS | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 6 | 90020234 | B1 | 1000278399 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-MNPP2 | 6800 | 18062 | 3589
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Pump Charge | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 2 | 90020232 | B1 | 1000278394 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-MNPP3 | 6800 | 18062 | 3449
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Hyd Pump Auxiliary | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 4 | 90020236 | B1 | 1000278393 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-PPAUX | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Mast Module Qtr Life | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 201 | 90030335 | B1 | 1000302805 | 31.03.2028 | 10000 | CCK-MP-DRLL-DR2129-STRUCT-DMAST | 6800 | 18062 | 4985
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Sprocket LH | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 24 | 90020186 | B1 | 1000303009 | 31.03.2028 | 10000 | CCK-MP-DRLL-DR2129-TRAVEL-SPRKL | 6800 | 18062 | 9347
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Mast Harnesses | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 112 | 90028949 | B1 | 1000289060 | 31.03.2028 | 30000 | CCK-MP-DRLL-DR2129-ELCTLV-HARNS | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Compressor Harnesses | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 12 | 90028948 | B1 | 1000289039 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-ELCTLV-HARNS | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Cab Harnesses | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 14 | 90028947 | B1 | 1000289038 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-ELCTLV-HARNS | 6800 | 18062 | 18062
MD6310 | Onsite Shut | Drills | Fortescue | DR2129 | DR2129 Repl Chassis Harnesses | 2028-03-28 | 2028-04-05 | 186 hrs | FY28 | 208 | 90028944 | B1 | 1000289037 | 31.03.2028 | 15000 | CCK-MP-DRLL-DR2129-ELCTLV-HARNS | 6800 | 18062 | 18062
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 - POWERPACK MODULE & MINOR COMPONENTS | 2028-03-29 | 2028-04-06 | 186 hrs | FY28
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 PV271 Hydraulic Tune | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 31.5 | 90017118 | B1 | 1000345149 | 04.11.2027 | 3000 | CCK-MP-DRLL-DR055 -HYDSYS | 6800 | 64569 | 64569
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Rod Thread lube Pump | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 2 | 90011732 | B1 | 1000102875 | 16.02.2028 | 10000 | CCK-MP-DRLL-DR055 -GRSYST-RTLPP | 6800 | 64569 | 6663
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Valve Counter Balance | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 1 | 90011691 | B1 | 1000102836 | 17.02.2028 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVCNB | 6800 | 64569 | 9560
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Power Pack Module | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 294 | 90029571 | B1 | 1000295334 | 11.04.2028 | 20000 | CCK-MP-DRLL-DR055 -ENGINE | 6800 | 64593 | 10155
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 PV271 Hydraulic Tune | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 31.5 | 90017118 | B1 | 1000345149 | 13.04.2028 | 3000 | CCK-MP-DRLL-DR055 -HYDSYS | 6800 | 64569 | 64569
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Cables & Hoses | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 100 | 90029843 | B1 | 1000303655 | 13.04.2028 | 5000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Pump Water Injection | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 2 | 90011733 | B1 | 1000102876 | 13.04.2028 | 5000 | CCK-MP-DRLL-DR055 -DSTSUP-WTRPP | 6800 | 64569 | 14276
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 EncoderHarness Cab to Aframe Repl | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 6 | 90036144 | B1 | 1000365255 | 13.04.2028 | 5000 | CCK-MP-DRLL-DR055 -ADSYST-HARNC | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Auto Lube Pump | 2028-03-29 | 2028-04-06 | 186 hrs | FY28 | 2 | 90011731 | B1 | 1000102874 | 08.06.2028 | 12000 | CCK-MP-DRLL-DR055 -GRSYST-ALBPP | 6800 | 64569 | 11474
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 - POWER PACK MODULE & MAJOR COMPONENTS | 2028-04-25 | 2028-05-03 | 186 hrs | FY28
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Track Frame Module LH | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 28 | 90021739 | B1 | 1000295741 | 08.09.2027 | 12000 | CCK-MP-DRLL-DR3137-STRUCT-TKFRL | 5400 | 14232 | 4968
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Track Frame Module RH | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 28 | 90021741 | B1 | 1000295742 | 08.09.2027 | 12000 | CCK-MP-DRLL-DR3137-STRUCT-TKFRR | 5400 | 14232 | 4968
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Cylinder Oscillation LH | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 8 | 90021662 | B1 | 1000295719 | 08.10.2027 | 12000 | CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-TFCOL | 5400 | 14232 | 4968
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Cylinder Oscillation RH | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 8 | 90021663 | B1 | 1000295720 | 08.10.2027 | 12000 | CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-TFCOR | 5400 | 14232 | 14232
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Overhaul Air Condtioner System | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 18 | 90023285 | B1 | 1000295746 | 02.11.2027 | 24 Monthly | CCK-MP-DRLL-DR3137-STRUCT-CABIN-ACCOM | 5400 | 14232 | 8625
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Pump Rod Thread Lube | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 2 | 90021715 | B1 | 1000295739 | 28.12.2027 | 6000 | CCK-MP-DRLL-DR3137-GRSYST-RTLPP | 5400 | 14232 | 2559
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 1 | 90020876 | B1 | 1000295716 | 24.02.2028 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Pump Air Lubrication | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 2 | 90021656 | B1 | 1000295727 | 16.03.2028 | 6000 | CCK-MP-DRLL-DR3137-AIRSYS-COMPR-PALUB | 5400 | 14232 | 8625
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Operators Seat | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 4 | 90021702 | B1 | 1000295725 | 16.03.2028 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-CABIN-SEATS | 5400 | 14232 | 4056
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Power Pack Module | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 88 | 90026030 | B1 | 1000295748 | 11.04.2028 | 12000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Cyl Jack levelling Rear | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 6 | 90021661 | B1 | 1000295718 | 11.04.2028 | 12000 | CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-JLCYR | 5400 | 14232 | 2835
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Hyd Motor Feed | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 6 | 90022025 | B1 | 1000361312 | 11.04.2028 | 6000 | CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MFEED | 5400 | 14232 | 4926
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Valve Main Block | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 18 | 90021692 | B1 | 1000295743 | 11.04.2028 | 12000 | CCK-MP-DRLL-DR3137-HYDSYS-HDVLV-VVMBK | 5400 | 14232 | 1891
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Oscillation Valve | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 4 | 90021664 | B1 | 1000295744 | 11.04.2028 | 12000 | CCK-MP-DRLL-DR3137-HYDSYS-HDVLV-VVOST | 5400 | 14232 | 14232
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Timing Chain Maintenance | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 14 | 90022023 | B1 | 1000361310 | 11.04.2028 | 3000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHP | 5400 | 14232 | 14232
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Feed Chain Sprockets | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 24 | 90022030 | B1 | 1000361311 | 11.04.2028 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHS | 5400 | 14232 | 8625
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Hose Drum Sprocket | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 6 | 90022032 | B1 | 1000361315 | 11.04.2028 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDHDS | 5400 | 14232 | 8625
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Gearbox Power Head | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 32 | 90021707 | B1 | 1000361313 | 11.04.2028 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-PWRHD | 5400 | 14232 | 7186
D65 | Onsite Shut | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump | 2028-04-25 | 2028-05-03 | 186 hrs | FY28 | 2 | 90020875 | B1 | 1000295715 | 02.05.2028 | 8000 | CCK-MP-DRLL-DR3137-GRSYST-ALBPP | 5400 | 14232 | 14232
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 - ENGINE & MAJOR COMPONENTS | 2028-05-04 | 2028-05-12 | 186 hrs | FY28
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack RHR DE CS | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 24 | 90030672 | B1 | 1000213911 | 18.09.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYRR | 6800 | 34249 | 22114
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Idler & Recoil Gp NCS | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 8 | 90030377 | B1 | 1000303483 | 25.09.2027 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-IDLLH | 6800 | 34249 | 11326
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Idler & Recoil Gp CS | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 8 | 90030377 | B1 | 1000303499 | 25.09.2027 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-IDLRH | 6800 | 34249 | 11324
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS Vibration Sensors | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 1 | 90029062 | B1 | 1000290886 | 25.09.2027 | 10000 | CCK-MP-DRLL-DR2112-ADSYST-ADSIS-DSVSN | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS 3D Sensor Harness | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 2 | 90029068 | B1 | 1000290888 | 25.09.2027 | 20000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cyl Mast Locking NCS | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 24 | 90020197 | B1 | 1000213913 | 08.10.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MLCYL | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Adjust 3750Hr Valve Set | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 24 | 90020402 | B1 | 1000213713 | 11.10.2027 | 3750 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Compressor Coupling | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 24 | 90030404 | B1 | 1000303532 | 12.10.2027 | 7500 | CCK-MP-DRLL-DR2112-AIRSYS-COMPR-COUPL | 6800 | 34252 | 3236
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Deck ADS Elec Hardware | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 10 | 90029060 | B1 | 1000290881 | 25.10.2027 | 20000 | CCK-MP-DRLL-DR2112-ADSYST-ADSHW-ADSMF | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Pump Drive Gearbox | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 78 | 90020181 | B1 | 1000213620 | 23.11.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-PMPDG | 6800 | 34249 | 2739
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack LHF NDE NCS | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 24 | 90020196 | B1 | 1000213907 | 25.11.2027 | 6000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYLF | 6800 | 34249 | 2981
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Chassis Harnesses | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 208 | 90028946 | B1 | 1000289022 | 05.12.2027 | 15000 | CCK-MP-DRLL-DR2112-ELCTLV-HARNS | 6800 | 34252 | 34228
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Fish Eye Camera | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 16 | 90029067 | B1 | 1000290889 | 01.01.2028 | 10000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR-HTCAM | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Mast Cables | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 64 | 90030334 | B1 | 1000302720 | 11.01.2028 | 2500 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Pump Water Inj | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 4 | 90031899 | B1 | 1000315424 | 02.02.2028 | 7500 | CCK-MP-DRLL-DR2112-DSTSUP-WTRPP | 6800 | 34249 | 11324
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Washdown Pump | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 8 | 90030681 | B1 | 1000305723 | 20.02.2028 | 7500 | CCK-MP-DRLL-DR2112-DSTSUP-WSHPP | 6800 | 34249 | 9455
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS LiDAR | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 4 | 90029065 | B1 | 1000290890 | 15.03.2028 | 5000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR-LIDAR | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Service 12M Air Conditioner | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 12 | 90028298 | B1 | 1000283155 | 21.03.2028 | 12 Monthly | CCK-MP-DRLL-DR2112-STRUCT-CABIN-AIRCN | 6800 | 34249 | 34249
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Compressor Harnesses | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 12 | 90028948 | B1 | 1000289024 | 23.04.2028 | 15000 | CCK-MP-DRLL-DR2112-ELCTLV-HARNS | 6800 | 34252 | 34228
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Engine Assy Caterpillar C32 | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 154 | 90020393 | B1 | 1000213705 | 24.04.2028 | 15000 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack RHF NDE CS | 2028-05-04 | 2028-05-12 | 186 hrs | FY28 | 24 | 90030670 | B1 | 1000213910 | 10.05.2028 | 6000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYRF | 6800 | 34249 | 2739
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 - SLEW BEARING, ATTACHMENTS & POWER PACK | 2028-05-10 | 2028-05-30 | 480 hrs | FY28
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Boom Module | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 276 | 90027376 | B1 | 1000279089 | 09.02.2028 | 40000 | CCK-MP-EXCV-EX7120-STRUCT-BOOMS | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Stick Assembly | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 332 | 90017828 | B2 | 1000250306 | 09.02.2028 | 40000 | CCK-MP-EXCV-EX7120-STRUCT-STICK | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Valve Bank Module | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 122 | 90027370 | B1 | 1000279083 | 29.02.2028 | 40000 | CCK-MP-EXCV-EX7120-HYDSYS-HDVLV-MCVLU | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Service Module | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 18 | 90030754 | B1 | 1000250317 | 29.02.2028 | 40000 | CCK-MP-EXCV-EX7120-STRUCT-SRVCT | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Slew Bearing | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 288 | 90030743 | B1 | 1000250260 | 29.02.2028 | 40000 | CCK-MP-EXCV-EX7120-UNDERC-SLEWB | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Final Drive LH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 141 | 90030716 | B1 | 1000250208 | 29.02.2028 | 40000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRL-FDRLH | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Final Drive RH Side | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 141 | 90030716 | B1 | 1000250209 | 29.02.2028 | 40000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRR-FDRRH | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Hose Boom Cyl | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 72 | 90030735 | B1 | 1000250249 | 25.03.2028 | 8000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF-HBMCL | 7200 | 28725 | 12234
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Stick RH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 54 | 90030724 | B1 | 1000250302 | 02.04.2028 | 16000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-STCLR | 7200 | 28725 | 4087
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Minestar Harness | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 43.5 | 90030746 | B1 | 1000281594 | 17.04.2028 | 5000 | CCK-MP-EXCV-EX7120-MANGMT-UMMMC | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Power Pack Module | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 172 | 90026482 | B1 | 1000279050 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-ENGINE | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Accumulator Track Hyd LH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 3 | 90030729 | B1 | 1000250246 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDACC-HACCL | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Accumulator Track Hyd RH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 3 | 90030729 | B1 | 1000250247 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDACC-HACCR | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Bucket LH Lift | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 54 | 90030725 | B1 | 1000250303 | 20.04.2028 | 10000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BUCYL | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Ladder Raise Cyl | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 24 | 90030750 | B1 | 1000250320 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-LACYL | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Motor Swing Rear | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 24 | 90030727 | B1 | 1000250228 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDMOT-SWMOR | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Motor Travel LHF | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000250236 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDMOT-TRMLF | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Motor Travel LHR | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000250237 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDMOT-TRMLR | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Motor Travel RHF | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000250238 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDMOT-TRMRF | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Motor Travel RHR | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 8 | 90030728 | B1 | 1000250239 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDMOT-TRMRR | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Rotary Connection & Hoses | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 168 | 90030430 | B1 | 1000303744 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-ROTRY | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Tank Module | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 72 | 90027374 | B1 | 1000279991 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-STRUCT-HDTNK | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Track Idler LH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 36 | 90030740 | B1 | 1000250268 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRL-IDLLH | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Sprocket LH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 72 | 90030718 | B1 | 1000250264 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRL-SPRKL | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Track Hyd Tensioner LH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 74 | 90024277 | B1 | 1000250258 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRL-TENSL | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Track Assembly LH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 36 | 90030719 | B1 | 1000250265 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRL-TRKLH | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Track Idler RH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 36 | 90030740 | B1 | 1000250269 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRR-IDLRH | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Sprocket RH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 72 | 90030718 | B1 | 1000250266 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRR-SPRKR | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Track Hyd Tensioner RH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 74 | 90024277 | B1 | 1000250259 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRR-TENSL | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Track Assembly RH | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 36 | 90030719 | B1 | 1000250267 | 20.04.2028 | 20000 | CCK-MP-EXCV-EX7120-UNDERC-TKFRR-TRKRH | 7200 | 28725 | 8287
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Batteries | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 9 | 90017122 | B1 | 1000250314 | 05.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7120-ELCTLV-CHARG-BATST | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Grease Tank Level Valve | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 2 | 90015003 | B2 | 1000250276 | 05.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7120-GRSYST-AUTLU-GRTNK | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 12M Hydraulic Service & Repairs | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 30 | 90014448 | B2 | 1000250274 | 05.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7120-HYDSYS | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Ovhl 24M Air Conditioner Sys1 Eng | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 49 | 90035445 | B1 | 1000359786 | 16.05.2028 | 24 Monthly | CCK-MP-EXCV-EX7120-STRUCT-CABIN-AIRC1
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Track Tension Tuning-Adjust | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 9 | 90020545 | B1 | 1000250313 | 25.05.2028 | 6 Monthly | CCK-MP-EXCV-EX7120-UNDERC | 7200 | 28725 | 28725
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Hose Bucket Cyl | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 54 | 90030738 | B1 | 1000250251 | 06.06.2028 | 8000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF-HBKCL | 7200 | 28725 | 2793
R9400 | Onsite Shut | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Hose Stick Cyl | 2028-05-10 | 2028-05-30 | 480 hrs | FY28 | 48 | 90030737 | B1 | 1000250250 | 15.06.2028 | 8000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF-HSTCL | 7200 | 28725 | 2629
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 - ENGINE & MAJOR COMPONENTS | 2028-05-15 | 2028-05-25 | 240 hrs | FY28
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 12 Monthly Hydraulic Tune Up | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 24 | 90015111 | B1 | 1000126742 | 03.09.2027 | 52 Weekly | CCK-MP-LOAD-WL269 -HYDSYS | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Torque Converter | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 48 | 90002693 | B2 | 1000090512 | 28.09.2027 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-TRQUE | 6000 | 74583 | 13004
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Axle Shaft Position 1 | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 12 | 90012242 | B2 | 1000112659 | 26.10.2027 | 32000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP1 | 6000 | 74583 | 24556
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Axle Shaft Position 2 | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 12 | 90012242 | B2 | 1000112660 | 26.10.2027 | 32000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP2 | 6000 | 74583 | 24556
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Axle Shaft Position 3 | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 12 | 90012242 | B2 | 1000112661 | 26.10.2027 | 32000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP3 | 6000 | 74583 | 24556
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Axle Shaft Position 4 | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 12 | 90012242 | B2 | 1000112662 | 26.10.2027 | 32000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP4 | 6000 | 74583 | 24556
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Final Drive Position 2 | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 83 | 90002710 | B2 | 1000090531 | 20.11.2027 | 16000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR02 | 6000 | 74583 | 8142
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Articulation Overhaul | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 360 | 90032991 | B1 | 1000329976 | 25.11.2027 | 16000 | CCK-MP-LOAD-WL269 -STRUCT-CHASS-ARTIC | 6000 | 74583 | 8058
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Transmission | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 74 | 90002692 | B2 | 1000090513 | 25.11.2027 | 16000 | CCK-MP-LOAD-WL269 -TRNSYS-TRANS | 6000 | 74583 | 8060
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Transmission Transfer Case | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 74 | 90017029 | B2 | 1000153360 | 25.11.2027 | 16000 | CCK-MP-LOAD-WL269 -TRNSYS-TRTRF | 6000 | 74583 | 8060
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Operators Seat | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 4 | 90002741 | B2 | 1000090553 | 21.12.2027 | 7000 | CCK-MP-LOAD-WL269 -STRUCT-CABIN-SEATS | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Replace Artic Area Hyd Hosing | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 6 | 90020831 | B1 | 1000220507 | 19.03.2028 | 8 Monthly | CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-ARTHO
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Gearbox Pump Drive Front | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 74 | 90002705 | B2 | 1000090525 | 21.04.2028 | 16000 | CCK-MP-LOAD-WL269 -TRNSYS-PMPDR-FRPDR | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Transmission System Hoses | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 96 | 90026923 | B1 | 1000271619 | 21.04.2028 | 16000 | CCK-MP-LOAD-WL269 -TRNSYS-TRHLF-TRNHO | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Final Drive Position 1 | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 83 | 90002710 | B2 | 1000090530 | 29.05.2028 | 16000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR01 | 6000 | 74583 | 5000
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Bucket RH Ext High Lift | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 36 | 90015437 | B2 | 1000131513 | 15.06.2028 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-BUCYR | 6000 | 74583 | 8680
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Brake | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 12 | 90002712 | B2 | 1000090534 | 17.06.2028 | 20000 | CCK-MP-LOAD-WL269 -BRKSYS-BRPMP-BRP01 | 6000 | 74583 | 8437
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Engine Cat 3516B | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 500 | 90021152 | B1 | 1000222677 | 17.06.2028 | 20000 | CCK-MP-LOAD-WL269 -ENGINE | 6000 | 74583 | 8436
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Overhaul Engine Prelube | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 10 | 90021219 | B1 | 1000222678 | 17.06.2028 | 20000 | CCK-MP-LOAD-WL269 -ENGINE-LUBSY-PREPP | 6000 | 74583 | 8436
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Overhaul Air Conditioner | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 48 | 90021132 | B1 | 1000222675 | 17.06.2028 | 10000 | CCK-MP-LOAD-WL269 -STRUCT-CABIN-AIRCN | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Bucket LH Ext High Lift | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 38 | 90015438 | B2 | 1000131512 | 01.07.2028 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-BUCYL | 6000 | 74583 | 8459
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Gearbox Pump Drive Rear | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 326 | 90002706 | B2 | 1000090526 | 02.07.2028 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-PMPDR-RRPDR | 6000 | 74583 | 8437
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Sepura SCC Microphone | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289604 | 17.07.2028 | 12 Monthly | CCK-MP-LOAD-WL269 -COMMUN-RADIO | 6000 | 74583 | 5623
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Overhaul Park Brake & Centre Brg | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 36 | 90002711 | B2 | 1000090565 | 25.07.2028 | 10000 | CCK-MP-LOAD-WL269 -BRKSYS-BRPRK | 6000 | 74561 | 8060
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Auto Lube Pump | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 6 | 90002737 | B2 | 1000090552 | 25.07.2028 | 10000 | CCK-MP-LOAD-WL269 -GRSYST-ALBPP | 6000 | 74583 | 16942
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Pilot & Cooling | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 12 | 90002726 | B2 | 1000090548 | 25.07.2028 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP04 | 6000 | 74583 | 8060
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Centre Bearing Upper Shaft | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 24 | 90002702 | B2 | 1000090522 | 25.07.2028 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-UCTRB | 6000 | 74583 | 8437
994H | Onsite Shut | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Lift RH Ext High Lift | 2028-05-15 | 2028-05-25 | 240 hrs | FY28 | 54 | 90002728 | B2 | 1000112693 | 16.08.2028 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-HCYLR | 6000 | 74583 | 7630
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 - AXLES & MAJOR COMPONENTS | 2028-06-05 | 2028-06-14 | 222 hrs | FY28
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Sepura SCC Microphone | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 0.5 | 90028989 | B1 | 1000289371 | 10.02.2028 | 12 Monthly | CCK-MP-GRDR-GR120 -COMMUN-RADIO | 5200 | 60265 | 60265
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Axle Assembly Front | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 98 | 90002666 | B1 | 1000180096 | 06.04.2028 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-AXLES | 5200 | 60265 | 4188
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Service Minor Air Conditioner | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 12 | 90019542 | B1 | 1000290264 | 08.04.2028 | 3500 | CCK-MP-GRDR-GR120 -STRUCT-CABIN-AIRCN | 5200 | 60265 | 18931
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Service Brake RHF | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 52 | 90002640 | B2 | 1000090787 | 25.04.2028 | 14000 | CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBRF | 5200 | 60265 | 5097
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Blade Mounting Bracket LH | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 48 | 90002671 | B2 | 1000090807 | 06.05.2028 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-CIRCL-BLMBL | 5200 | 60265 | 18931
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Blade Mounting Bracket RH | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 48 | 90002671 | B2 | 1000090808 | 06.05.2028 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-CIRCL-BLMBR | 5200 | 60265 | 18931
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Service Brake LHR | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 54 | 90004548 | B2 | 1000090788 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBLR | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Rear Axel Assembly | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 128 | 90030396 | B1 | 1000303436 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -FDRSYS-DIFFL | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Drive Shaft Trans to Rr Diff | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 6 | 90033262 | B1 | 1000333904 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -FDRSYS-DRSHT-SHT01 | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Drive Shaft TCon to Trans | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 4 | 90033265 | B1 | 1000333906 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -FDRSYS-DRSHT-SHT02 | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Brake System Hoses | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 48 | 90009997 | B2 | 1000090815 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-BRKS | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Hydraulic System Hoses | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 48 | 90009998 | B2 | 1000090816 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-HYDSH | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Power Train System Hoses | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 48 | 90009999 | B2 | 1000090817 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-PWTRN | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Hyd Pump Implement | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 8 | 90002646 | B2 | 1000090794 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-HYIMP | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Hyd Pump Steering Main | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 8 | 90002647 | B2 | 1000090795 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-HYSTP | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Hyd Pump Secondary Steering | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 6 | 90002645 | B2 | 1000090793 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -STRSYS-STEMG-SESPP | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Gearbox Circle Drive Front | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 14 | 90002672 | B2 | 1000090809 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-CIRCL-CDBXF | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Transmission | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 146 | 90002631 | B2 | 1000090758 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -TRNSYS-TRANS | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Transmission Oil Cooler | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 6 | 90002632 | B2 | 1000090759 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -TRNSYS-TROLC | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Repl Pump Transmission | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 8 | 90002633 | B2 | 1000090780 | 24.05.2028 | 14000 | CCK-MP-GRDR-GR120 -TRNSYS-TRPMP | 5200 | 60265 | 4679
24M | Onsite Shut | Ancillary | Fortescue | GR120 | GR120 Overhaul Auto Lubrication System | 2028-06-05 | 2028-06-14 | 222 hrs | FY28 | 2 | 90002660 | B2 | 1000090801 | 31.05.2028 | 14000 | CCK-MP-GRDR-GR120 -GRSYST-ALBPP | 5200 | 60265 | 4760
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2028-06-12 | 2028-06-21 | 222 hrs | FY28
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Hyd Pump Implement & Steer | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 16 | 90002460 | B1 | 1000027372 | 14.04.2028 | 14000 | CCK-MP-GRDR-GR014 -HYDSYS-HYDPP-HYISP | 3200 | 44181 | 8489
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Differential | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 106 | 90002451 | B1 | 1000027359 | 15.04.2028 | 14000 | CCK-MP-GRDR-GR014 -FDRSYS-DIFFL | 3200 | 44181 | 8479
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Hyd Pump Secondary Steering | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 6 | 90002459 | B1 | 1000027371 | 15.04.2028 | 7000 | CCK-MP-GRDR-GR014 -STRSYS-STEMG-SESPP | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Implement Ctrl Valve Front | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 12 | 90002461 | B1 | 1000027373 | 15.04.2028 | 14000 | CCK-MP-GRDR-GR014 -HYDSYS-HDCVL-FRONT | 3200 | 44181 | 8479
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Implement Control Valve Rear | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 12 | 90002462 | B1 | 1000027374 | 15.04.2028 | 14000 | CCK-MP-GRDR-GR014 -HYDSYS-HDCVL-REAR1 | 3200 | 44181 | 8479
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Hyd Motor Fan Hyd Cooler | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 8 | 90002464 | B1 | 1000027376 | 15.04.2028 | 14000 | CCK-MP-GRDR-GR014 -HYDSYS-HDMOT-MOFAN | 3200 | 44181 | 8489
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Operators Seat | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 8 | 90002475 | B1 | 1000027388 | 15.04.2028 | 7000 | CCK-MP-GRDR-GR014 -STRUCT-CABIN-SEATS | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Gearbox Circle Drive | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 14 | 90002481 | B1 | 1000027395 | 15.04.2028 | 14000 | CCK-MP-GRDR-GR014 -STRUCT-CIRCL-CDRBX | 3200 | 44181 | 8479
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Brake Assy LHF | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 40 | 90002455 | B1 | 1000027364 | 05.07.2028 | 8000 | CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBLF | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Brake Assy RHF | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 40 | 90002455 | B1 | 1000027365 | 05.07.2028 | 8000 | CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBRF | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Brake Assy RHR | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 40 | 90002456 | B1 | 1000027367 | 07.07.2028 | 8000 | CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBRR | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Engine Midlife complete | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 49 | 90015737 | B1 | 1000269558 | 29.07.2028 | 7000 | CCK-MP-GRDR-GR014 -ENGINE | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Replace High Risk Hoses | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 6 | 90021797 | B2 | 1000269582 | 29.07.2028 | 7000 | CCK-MP-GRDR-GR014 -ENGINE | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Repl Drive Shaft Uni | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 6 | 90033281 | B1 | 1000333747 | 29.07.2028 | 7000 | CCK-MP-GRDR-GR014 -TRNSYS | 3200 | 44181 | 297
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Air Conditioner Major Service | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 24 | 90017476 | B1 | 1000269559 | 29.07.2028 | 7000 | CCK-MP-GRDR-GR014 -STRUCT-CABIN-AIRCN | 3200 | 44181 | 8479
16M | Onsite Shut | Ancillary | Fortescue | GR014 | GR014 Front Axle Assembly Midlife | 2028-06-12 | 2028-06-21 | 222 hrs | FY28 | 66 | 90026004 | B1 | 1000256253 | 01.08.2028 | 7000 | CCK-MP-GRDR-GR014 -STRUCT-AXLES | 3200 | 44181 | 297
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 - ENGINE & TRACK FRAMES | 2028-06-19 | 2028-06-29 | 240 hrs | FY28
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Equaliser Bar | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 110 | 90002097 | B1 | 1000108384 | 04.02.2028 | 18000 | CCK-MP-DOZR-DZ169 -STRUCT-CHASS-EQUAL | 5000 | 62015 | 10301
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Cyl Blade Lift RH | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 16 | 90000287 | B1 | 1000255591 | 07.02.2028 | 9000 | CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-BLCYR | 5000 | 62015 | 10794
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Transmission | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 48 | 90000308 | B2 | 1000091071 | 27.04.2028 | 18000 | CCK-MP-DOZR-DZ169 -TRNSYS-TRANS | 5000 | 62015 | 836
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Pump Trans & TCon Charge | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 10 | 90000302 | B2 | 1000091073 | 27.04.2028 | 18000 | CCK-MP-DOZR-DZ169 -TRNSYS-TRPMP | 5000 | 62015 | 9171
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Torque Converter | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 60 | 90000309 | B2 | 1000091070 | 27.04.2028 | 18000 | CCK-MP-DOZR-DZ169 -TRNSYS-TRQUE | 5000 | 62015 | 9171
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Cyl Blade Lift LH | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 16 | 90000287 | B1 | 1000255590 | 15.05.2028 | 9000 | CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-BLCYL | 5000 | 62015 | 8908
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Sepura SCC Microphone | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289544 | 21.05.2028 | 12 Monthly | CCK-MP-DOZR-DZ169 -COMMUN-RADIO | 5000 | 62015 | 62015
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Steer Clutch & Brake Assm RH | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 28 | 90000313 | B2 | 1000091077 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -BRKSTR-SCABR | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Engine Cat C27 | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 114 | 90015849 | B1 | 1000160078 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -ENGINE | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Rad Engine Cooling SN 529 UP | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 48 | 90000307 | B2 | 1000091068 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -ENGINE-COSYS-RADTR | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Aftercooler Engine | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 8 | 90010841 | B1 | 1000108380 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -ENGINE-INTEX-AFTER | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Final Drive RH | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 28 | 90000312 | B2 | 1000091075 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -FDRSYS-FDRRH | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Hyd Oil Cooler | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 10 | 90009664 | B2 | 1000091083 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -HYDSYS-HDOCO | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Ovhl Hydraulic & Fuel Tank | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 48 | 90010842 | B1 | 1000108382 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -HYDSYS-HDTNK | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Hyd Pump Cooling Fan | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 16 | 90004952 | B2 | 1000091081 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -HYDSYS-HYDPP-HYFPP | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Overhaul Air Conditioner | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 48 | 90017468 | B1 | 1000196610 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN-AIRCN | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Minor Overhaul Track Frame LH | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 98 | 90002098 | B1 | 1000108385 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -STRUCT-UNDER-TKFRL | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Minor Overhaul Track Frame RH | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 98 | 90010766 | B1 | 1000108387 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -STRUCT-UNDER-TKFRR | 5000 | 62015 | 8044
D10T | Onsite Shut | Ancillary | Fortescue | DZ169 | DZ169 Repl Drive Shaft | 2028-06-19 | 2028-06-29 | 240 hrs | FY28 | 6 | 90033296 | B1 | 1000334099 | 18.07.2028 | 18000 | CCK-MP-DOZR-DZ169 -TRNSYS | 5000 | 62015 | 8044
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 - ENGINE & MAJOR COMPONENTS | 2028-06-19 | 2028-06-28 | 222 hrs | FY28
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Front Axle Assembly Midlife | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 42 | 90025907 | B1 | 1000255886 | 19.01.2028 | 7000 | CCK-MP-GRDR-GR121 -STRUCT-AXLES | 5200 | 67029 | 50
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Transmission | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 146 | 90002631 | B2 | 1000090839 | 09.02.2028 | 14000 | CCK-MP-GRDR-GR121 -TRNSYS-TRANS | 5200 | 67029 | 6190
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Torque Converter | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 98 | 90002630 | B2 | 1000090838 | 22.02.2028 | 14000 | CCK-MP-GRDR-GR121 -TRNSYS-TRQUE | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Service Brake LHR | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 54 | 90004548 | B2 | 1000090849 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBLR | 5200 | 67029 | 16173
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Service Brake RHR | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 54 | 90004548 | B2 | 1000090850 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBRR | 5200 | 67029 | 19812
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Electrical Harness | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 48 | 90010000 | B2 | 1000090875 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -ELCTLV-HARNS | 5200 | 67029 | 5487
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Radiator Engine Cooling | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 98 | 90002618 | B3 | 1000090836 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -ENGINE-COSYS-RADTR | 5200 | 67029 | 5487
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Aftercooler Engine | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 24 | 90002623 | B2 | 1000090880 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -ENGINE-INTEX-AFTER | 5200 | 67029 | 5487
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Hyd Pump Differential Lock | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 8 | 90002649 | B2 | 1000090858 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-DIFFL | 5200 | 67029 | 16173
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Gearbox Circle Drive Front | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 14 | 90002672 | B2 | 1000090870 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -STRUCT-CIRCL-CDBXF | 5200 | 67029 | 5487
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Gearbox Circle Drive Rear | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 14 | 90011066 | B2 | 1000090871 | 29.03.2028 | 14000 | CCK-MP-GRDR-GR121 -STRUCT-CIRCL-CDBXR | 5200 | 67029 | 5487
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Hyd Pump Secondary Steering | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 6 | 90002645 | B2 | 1000090854 | 30.04.2028 | 14000 | CCK-MP-GRDR-GR121 -STRSYS-STEMG-SESPP | 5200 | 67029 | 35586
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Operators Seat | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 4 | 90002663 | B2 | 1000090863 | 30.04.2028 | 7000 | CCK-MP-GRDR-GR121 -STRUCT-CABIN-SEATS | 5200 | 67029 | 12377
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Brake Slack Adjuster LH | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 1 | 90002641 | B2 | 1000090881 | 01.05.2028 | 14000 | CCK-MP-GRDR-GR121 -BRKSYS-SLACK-SLACL | 5200 | 67029 | 16101
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Brake Slack Adjuster Rear | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 1 | 90002641 | B2 | 1000090882 | 01.05.2028 | 14000 | CCK-MP-GRDR-GR121 -BRKSYS-SLACK-SLACR | 5200 | 67029 | 16173
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Service Brake RHF | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 52 | 90002640 | B2 | 1000090848 | 01.05.2028 | 14000 | CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBRF | 5200 | 67029 | 19812
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Overhaul Auto Lubrication System | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 2 | 90002660 | B2 | 1000090862 | 01.05.2028 | 14000 | CCK-MP-GRDR-GR121 -GRSYST-ALBPP | 5200 | 67029 | 25162
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Output Drive Shaft Unis | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 8 | 90033264 | B1 | 1000333909 | 06.09.2028 | 7000 | CCK-MP-GRDR-GR121 -FDRSYS-DRSHT-SHT01 | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Trans Input Drive Shaft Unis | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 8 | 90033267 | B1 | 1000333911 | 06.09.2028 | 7000 | CCK-MP-GRDR-GR121 -FDRSYS-DRSHT-SHT02 | 5200 | 67029 | 10195
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Repl Engine Cat C18 | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 310 | 90015771 | B1 | 1000290301 | 16.09.2028 | 14000 | CCK-MP-GRDR-GR121 -ENGINE | 5200 | 67029 | 5487
24M | Onsite Shut | Ancillary | Fortescue | GR121 | GR121 Overhaul Air Condtioner System | 2028-06-19 | 2028-06-28 | 222 hrs | FY28 | 48 | 90017475 | B1 | 1000290307 | 16.09.2028 | 14000 | CCK-MP-GRDR-GR121 -STRUCT-CABIN-AIRCN | 5200 | 67029 | 10195
| Onsite Shut | All | Fortescue |  | FY29 - ONSITE SHUTDOWNS | 2028-07-01 | 2029-06-30 | 8736 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 - MAJOR COMPONENTS | 2028-07-01 | 2028-07-13 | 282 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 24M Ovhl Air Con Side Unit | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 36 | 90030500 | B1 | 1000349851 | 20.05.2028 | 24 Monthly | CCK-MP-EXCV-EX7144-STRUCT-AIRC1 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 24M Ovhl Air Con Rear Unit | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 36 | 90030537 | B1 | 1000349853 | 20.05.2028 | 24 Monthly | CCK-MP-EXCV-EX7144-STRUCT-AIRC2 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Boom Module Quarter Life | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 48 | 90029992 | B1 | 1000349865 | 17.06.2028 | 10000 | CCK-MP-EXCV-EX7144-STRUCT-BOOMS | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl HV Motor Coupling | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 30 | 90030128 | B1 | 1000349889 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-ELCTHV-HVMOT-COUPL | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Gearbox Swing P1 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000349787 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-SWGSYS-SWBOX-SGBPF | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Gearbox Swing P2 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000349788 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-SWGSYS-SWBOX-SGBPR | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Splitter Gearbox | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 240 | 90030087 | B1 | 1000349870 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-PMPDR | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Pump Hyd Work Pos1 & Pos2 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 54 | 90030234 | B1 | 1000349871 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-WPPP1 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Pump Hyd Work Pos3 & Pos4 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 54 | 90030286 | B1 | 1000349879 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-WPPP2 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Pump Swing Combination | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 36 | 90030252 | B1 | 1000349872 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-SWPP1 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Pump Fan Hyd Oil Cooler | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 24 | 90030278 | B1 | 1000349873 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-HECP1 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Pump Servo Bearing Lube | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 4 | 90030280 | B1 | 1000349874 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-SVPP1 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Lube Pump Splitter Gear Box | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 4 | 90030281 | B1 | 1000349875 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-PTOLU | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Pump Oil Replenishing | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 4 | 90030285 | B1 | 1000349876 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-RPPP1 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Ladder Raise Cylinder | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 6 | 90030320 | B1 | 1000349882 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-LACYL | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Bucket LH Lift | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 52 | 90029964 | B1 | 1000349846 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-BUCYL | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Bucket RH Lift | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 52 | 90029967 | B1 | 1000349847 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-BUCYR | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Rotary Connection | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 72 | 90029901 | B1 | 1000349789 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-ROTRY | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Vlve Bank Module Quarter Life | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 12 | 90029987 | B1 | 1000349862 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDVLV-MCVLU | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Valve Pressure Reducing Y3 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 6 | 90030294 | B1 | 1000349881 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDVLV-VVPRV | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Valve Pressure Limiting Y4 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 6 | 90030321 | B1 | 1000349880 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDVLV-VVPLV | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Motor Swing Front | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000349791 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDMOT-SWMOF | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Motor Swing Rear | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000349790 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDMOT-SWMOR | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Motor Travel LHF | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000349792 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDMOT-TRMLF | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Motor Travel LHR | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000349793 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDMOT-TRMLR | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Motor Travel RHF | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000349794 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDMOT-TRMRF | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Motor Travel RHR | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000349795 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDMOT-TRMRR | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Accumulator Track Hyd LH | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000349796 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDACC | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Accumulator Track Hyd RH | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000349797 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-HYDSYS-HDACC | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Accumulator Servo Hyd | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 3 | 90030487 | B1 | 1000349863 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDACC | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Accumulator Ladder Hyd | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 4 | 90030685 | B1 | 1000349891 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDACC | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Track Tensioning Hoses | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 24 | 90030538 | B1 | 1000349890 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HHTTL | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Hyd Hose Work Pumps to Valves | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 10.5 | 90030287 | B1 | 1000349877 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HWPVV | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Hyd Hose Swing Pump Swing Motor | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 24 | 90030288 | B1 | 1000349878 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HSPSM | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Hyd Hose Rotary Con to Valve Bank | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 24 | 90029912 | B1 | 1000349801 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HRCVV | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Hoses Rotary Conn to Travel Motor | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 48 | 90029914 | B1 | 1000349802 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HRCTM | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Operators Seat | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 16 | 90029915 | B1 | 1000349803 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-STRUCT-CABIN-SEATO | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Tank Module | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 84 | 90030313 | B1 | 1000349866 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-STRUCT-HDTNK | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Service Module Hosing | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 24 | 90029982 | B1 | 1000349859 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-STRUCT-SRVCT | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Service Arm Locking Cyl | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 20 | 90029983 | B1 | 1000349860 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-STRUCT-SRVCT | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Bucket Assembly | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 78 | 90029975 | B1 | 1000349849 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-STRUCT-BUCKT | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Auto Lube Pump P1 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 2 | 90030312 | B1 | 1000349807 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-GRSYST-AUTLU-ALBPP | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Auto Lube Pump P3 | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 2 | 90035351 | B1 | 1000358635 | 28.07.2028 | 10000 | CCK-MP-EXCV-EX7144-GRSYST-AUTLU-ALBP3 | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Motor Side ACon Comp Drive | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000349892 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-STRUCT-AIRC1-ACONM | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Motor Rear ACon Comp Drive | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000349893 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-STRUCT-AIRC2-ACONM | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Minestar Harness | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 43.5 | 90029998 | B1 | 1000349867 | 02.08.2028 | 4000 | CCK-MP-EXCV-EX7144-MANGMT-UMMMC | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Grease Block & Injectors | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 84 | 90029933 | B1 | 1000349815 | 13.08.2028 | 20000 | CCK-MP-EXCV-EX7144-GRSYST-GRINJ | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Hose Boom Cyl | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 72 | 90029908 | B1 | 1000349798 | 09.11.2028 | 8000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HBMCL | 6200 | 8005 | 8005
R9400E | Onsite Shut | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Hose Stick Cyl | 2028-07-01 | 2028-07-13 | 282 hrs | FY29 | 48 | 90029909 | B1 | 1000349799 | 09.11.2028 | 8000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HSTCL | 6200 | 8005 | 8005
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 - ENGINE & MAJOR COMPONENTS | 2028-07-03 | 2028-07-13 | 246 hrs | FY29
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Bucket LH High Lift | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 36 | 90017978 | B1 | 1000131520 | 09.02.2028 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-BUCYL | 6000 | 74441 | 719
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Bucket RH High Lift | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 36 | 90017977 | B1 | 1000131521 | 09.02.2028 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-BUCYR | 6000 | 74441 | 719
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Implement LH | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 24 | 90002723 | B2 | 1000090397 | 28.02.2028 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP01 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Implement RH | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 24 | 90002724 | B2 | 1000090398 | 03.03.2028 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP02 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Implement Centre | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 24 | 90002725 | B2 | 1000090399 | 03.03.2028 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP03 | 6000 | 74441 | 10237
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 12 Monthly Hydraulic Tune Up | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 24 | 90015111 | B1 | 1000126740 | 13.03.2028 | 52 Weekly | CCK-MP-LOAD-WL267 -HYDSYS | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Centre Bearing Upper Shaft | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 24 | 90002702 | B2 | 1000090374 | 27.03.2028 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-UCTRB | 6000 | 74441 | 9732
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Steering LH | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 36 | 90002716 | B2 | 1000090391 | 29.03.2028 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP01 | 6000 | 74441 | 9741
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Steering RH | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 36 | 90002717 | B2 | 1000090392 | 29.03.2028 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP02 | 6000 | 74441 | 31558
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Front Drive Shaft | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 16 | 90033175 | B1 | 1000333533 | 29.03.2028 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT04 | 6000 | 74441 | 9741
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Brake System Hoses | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 48 | 90026921 | B1 | 1000271603 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -BRKSYS-BRHLF-BRKHO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Brake Oil Cooler | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 72 | 90002715 | B2 | 1000090390 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -BRKSYS-BROCC | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Electrical Harness | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 36 | 90010123 | B2 | 1000090415 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -ELCTLV-HARNS | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Engine Cat 3516B | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 500 | 90021152 | B1 | 1000222633 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -ENGINE | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Radiator Engine Cooling | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 102 | 90002682 | B2 | 1000090363 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -ENGINE-COSYS-RADTR | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Overhaul Engine Prelube | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 10 | 90021219 | B1 | 1000222634 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -ENGINE-LUBSY-PREPP | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Rear Differential | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 114 | 90002708 | B2 | 1000090380 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -FDRSYS-RRDIF | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Overhaul Rear Axle Trunnion | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 112 | 90002709 | B2 | 1000090381 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -FDRSYS-RRDIF-TRNON | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hydraulic System Hoses | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 96 | 90026922 | B1 | 1000271605 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-HYDHO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Replace Pilot System Hoses | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 96 | 90009731 | B2 | 1000090412 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-PILHO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Oil Cooler | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 96 | 90002733 | B2 | 1000090401 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -HYDSYS-HDOCO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Reseal Tank Hyd | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 12 | 90010623 | B2 | 1000090416 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -HYDSYS-HDTNK-HYT01 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Replace Steering System Hoses | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 96 | 90009732 | B2 | 1000090413 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STHLF-STRHO | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Steering Neutralizer Valves | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 6 | 90002720 | B2 | 1000090409 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STNVS | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Steer & Brake Oil Cooler Pump | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 8 | 90002718 | B2 | 1000090393 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP03 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Overhaul Air Conditioner | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 48 | 90021132 | B1 | 1000222631 | 27.06.2028 | 10000 | CCK-MP-LOAD-WL267 -STRUCT-CABIN-AIRCN | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Input Drive Shaft | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 12 | 90033166 | B1 | 1000333527 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT01 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Rear Output Drive Shaft | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 14 | 90033168 | B1 | 1000333529 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT02 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Centre Output Drive Shaft | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 14 | 90033171 | B1 | 1000333531 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT03 | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Gearbox Pump Drive Rear | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 326 | 90002706 | B2 | 1000090378 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-PMPDR-RRPDR | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Transmission Oil Cooler | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 36 | 90002695 | B2 | 1000090367 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-TROLC | 6000 | 74441 | 8258
994H | Onsite Shut | Ancillary | Fortescue | WL267 | WL267 Repl Torque Converter | 2028-07-03 | 2028-07-13 | 246 hrs | FY29 | 48 | 90002693 | B2 | 1000090364 | 27.06.2028 | 20000 | CCK-MP-LOAD-WL267 -TRNSYS-TRQUE | 6000 | 74441 | 8258
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 - ENGINE & MAJOR COMPONENTS | 2028-07-12 | 2028-07-22 | 240 hrs | FY29
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Track Frame LH | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 40 | 90002099 | B1 | 1000108566 | 01.07.2028 | 36000 | CCK-MP-DOZR-DZ184 -STRUCT-UNDER-TKFRL | 5000 | 67674 | 12208
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Track Frame RH | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 40 | 90002102 | B1 | 1000108568 | 01.07.2028 | 36000 | CCK-MP-DOZR-DZ184 -STRUCT-UNDER-TKFRR | 5000 | 67674 | 12208
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Steer Clutch & Brake Assm LH | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091364 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -BRKSTR-SCABL | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Steer Clutch & Brake Assm RH | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091365 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -BRKSTR-SCABR | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Engine Cat C27 | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 114 | 90015849 | B1 | 1000160278 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -ENGINE | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Rad Engine Cooling SN 529 UP | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 48 | 90000307 | B2 | 1000091356 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -ENGINE-COSYS-RADTR | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Aftercooler Engine | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 8 | 90010841 | B1 | 1000108560 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -ENGINE-INTEX-AFTER | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Final Drive LH | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091362 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -FDRSYS-FDRLH | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Final Drive RH | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091363 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -FDRSYS-FDRRH | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Hyd Oil Cooler | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 10 | 90009664 | B2 | 1000091371 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -HYDSYS-HDOCO | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Ovhl Hydraulic & Fuel Tank | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 48 | 90010842 | B1 | 1000108562 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -HYDSYS-HDTNK | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Hyd Pump Cooling Fan | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 16 | 90004952 | B2 | 1000091369 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -HYDSYS-HYDPP-HYFPP | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Hyd Pump Implement | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 10 | 90000301 | B2 | 1000091366 | 11.07.2028 | 9000 | CCK-MP-DOZR-DZ184 -HYDSYS-HYDPP-HYIPP | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Overhaul Air Conditioner | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 48 | 90017468 | B1 | 1000196657 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN-AIRCN | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Drive Shaft | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 6 | 90033296 | B1 | 1000334127 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -TRNSYS | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Transmission | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 48 | 90000308 | B2 | 1000091359 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -TRNSYS-TRANS | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Pump Trans & TCon Charge | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 10 | 90000302 | B2 | 1000091361 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -TRNSYS-TRPMP | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Repl Torque Converter | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 60 | 90000309 | B2 | 1000091358 | 11.07.2028 | 18000 | CCK-MP-DOZR-DZ184 -TRNSYS-TRQUE | 5000 | 67674 | 8628
D10T | Onsite Shut | Ancillary | Fortescue | DZ184 | DZ184 Refurbish Cabin | 2028-07-12 | 2028-07-22 | 240 hrs | FY29 | 18 | 90010844 | B1 | 1000108563 | 20.05.2029 | 36000 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN | 5000 | 67674 | 22343
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 - ENGINE & MAJOR COMPONENTS | 2028-07-26 | 2028-08-05 | 240 hrs | FY29
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Final Drive LH | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091266 | 01.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -FDRSYS-FDRLH | 5000 | 63195 | 8038
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Engine Cat C27 | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 114 | 90015849 | B1 | 1000160230 | 08.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -ENGINE | 5000 | 63195 | 7949
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Aftercooler Engine | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 8 | 90010841 | B1 | 1000108512 | 08.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -ENGINE-INTEX-AFTER | 5000 | 63195 | 7949
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Overhaul Air Conditioner | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 48 | 90017468 | B1 | 1000196645 | 08.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -STRUCT-CABIN-AIRCN | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Sepura SCC Microphone | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289554 | 25.08.2028 | 12 Monthly | CCK-MP-DOZR-DZ180 -COMMUN-RADIO | 5000 | 63195 | 63195
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Steer Clutch & Brake Assm LH | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091268 | 31.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -BRKSTR-SCABL | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Hyd Oil Cooler | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 10 | 90009664 | B2 | 1000091275 | 31.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -HYDSYS-HDOCO | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Ovhl Hydraulic & Fuel Tank | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 48 | 90010842 | B1 | 1000108514 | 31.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -HYDSYS-HDTNK | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Hyd Pump Cooling Fan | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 16 | 90004952 | B2 | 1000091273 | 31.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -HYDSYS-HYDPP-HYFPP | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Hyd Pump Implement | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 10 | 90000301 | B2 | 1000091270 | 31.08.2028 | 9000 | CCK-MP-DOZR-DZ180 -HYDSYS-HYDPP-HYIPP | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Operators Seat | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 8 | 90000318 | B1 | 1000108511 | 31.08.2028 | 6000 | CCK-MP-DOZR-DZ180 -STRUCT-CABIN-SEATS | 5000 | 63195 | 1342
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Drive Shaft | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 6 | 90033296 | B1 | 1000334119 | 31.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -TRNSYS | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Transmission | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 48 | 90000308 | B2 | 1000091263 | 31.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -TRNSYS-TRANS | 5000 | 63195 | 7626
D10T | Onsite Shut | Ancillary | Fortescue | DZ180 | DZ180 Repl Pump Trans & TCon Charge | 2028-07-26 | 2028-08-05 | 240 hrs | FY29 | 10 | 90000302 | B2 | 1000091265 | 31.08.2028 | 18000 | CCK-MP-DOZR-DZ180 -TRNSYS-TRPMP | 5000 | 63195 | 7626
PV271 | Onsite Shut | Drills | Fortescue | DR2104 | DR2104 - POWER PACK MODULE & COMPONENTS | 2028-08-16 | 2028-08-24 | 186 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 - MAJOR COMPONENTS | 2028-08-23 | 2028-09-04 | 282 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Track Tension Tuning-Adjust | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 9 | 90029977 | B1 | 1000352515 | 21.07.2028 | 6 Monthly | CCK-MP-EXCV-EX7147-UNDERC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl HV Motor Coupling | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 30 | 90030128 | B1 | 1000352548 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-ELCTHV-HVMOT-COUPL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Gearbox Swing P1 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000352448 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-SWGSYS-SWBOX-SGBPF | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Gearbox Swing P2 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000352449 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-SWGSYS-SWBOX-SGBPR | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Splitter Gearbox | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 240 | 90030087 | B1 | 1000352531 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-PMPDR | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Pump Hyd Work Pos1 & Pos2 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 54 | 90030234 | B1 | 1000352532 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-WPPP1 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Pump Hyd Work Pos3 & Pos4 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 54 | 90030286 | B1 | 1000352540 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-WPPP2 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Pump Swing Combination | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 36 | 90030252 | B1 | 1000352533 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-SWPP1 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Pump Fan Hyd Oil Cooler | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90030278 | B1 | 1000352534 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-HECP1 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Pump Servo Bearing Lube | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030280 | B1 | 1000352535 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-SVPP1 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Lube Pump Splitter Gear Box | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030281 | B1 | 1000352536 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-PTOLU | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Pump Oil Replenishing | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030285 | B1 | 1000352537 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HYDPP-RPPP1 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Ladder Raise Cylinder | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 6 | 90030320 | B1 | 1000352543 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-LACYL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Bucket LH Lift | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 52 | 90029964 | B1 | 1000352507 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-BUCYL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Bucket RH Lift | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 52 | 90029967 | B1 | 1000352508 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-BUCYR | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Rotary Connection | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 72 | 90029901 | B1 | 1000352450 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-ROTRY | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Vlve Bank Module Quarter Life | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 12 | 90029987 | B1 | 1000352523 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDVLV-MCVLU | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Valve Pressure Reducing Y3 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 6 | 90030294 | B1 | 1000352542 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDVLV-VVPRV | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Valve pressure Limiting Y4 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 6 | 90030321 | B1 | 1000352541 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDVLV-VVPLV | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Motor Swing Front | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000352452 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDMOT-SWMOF | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Motor Swing Rear | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000352451 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDMOT-SWMOR | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Motor Travel LHF | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000352453 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDMOT-TRMLF | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Motor Travel LHR | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000352454 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDMOT-TRMLR | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Motor Travel RHF | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000352455 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDMOT-TRMRF | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Motor Travel RHR | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000352456 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDMOT-TRMRR | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Accumulator Track Hyd LH | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000352457 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDACC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Accumulator Track Hyd RH | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000352458 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-HYDSYS-HDACC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Accumulator Servo Hyd | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 3 | 90030487 | B1 | 1000352524 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDACC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Accumulator Ladder Hyd | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030685 | B1 | 1000352550 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDACC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Track Tensioning Hoses | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90030538 | B1 | 1000352549 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HHTTL | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hyd Hose Work Pumps to Valves | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 10.5 | 90030287 | B1 | 1000352538 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HWPVV | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hyd Hose Swing Pump Swing Motor | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90030288 | B1 | 1000352539 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HSPSM | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hyd Hose Rotary Con to Valve Bank | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029912 | B1 | 1000352462 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HRCVV | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Hoses Rotary Conn to Travel Motor | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 48 | 90029914 | B1 | 1000352463 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HRCTM | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Operators Seat | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 16 | 90029915 | B1 | 1000352464 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-STRUCT-CABIN-SEATO | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Motor ACon Comp Drive | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000352551 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-STRUCT-AIRC1-ACONM | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Motor ACon Comp Drive | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000352552 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-STRUCT-AIRC2-ACONM | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Tank Module | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 84 | 90030313 | B1 | 1000352527 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-STRUCT-HDTNK | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Service Arm Locking Cyl | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 20 | 90029983 | B1 | 1000352521 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-STRUCT-SRVCT | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Service Module Hosing | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029982 | B1 | 1000352520 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-STRUCT-SRVCT | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Bucket Assembly | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 78 | 90029975 | B1 | 1000352510 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-STRUCT-BUCKT | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Auto Lube Pump P3 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 2 | 90035351 | B1 | 1000358641 | 31.07.2028 | 10000 | CCK-MP-EXCV-EX7147-GRSYST-AUTLU-ALBP3 | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Minestar Harness | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 43.5 | 90029998 | B1 | 1000352528 | 31.07.2028 | 4000 | CCK-MP-EXCV-EX7147-MANGMT-UMMMC | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7147 | EX7147 Repl Grease Block & Injectors | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 84 | 90029933 | B1 | 1000352476 | 14.09.2028 | 20000 | CCK-MP-EXCV-EX7147-GRSYST-GRINJ | 6200 | 7547 | 7547
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 - MAJOR COMPONENTS | 2028-08-23 | 2028-09-04 | 282 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Grease Block & Injectors | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 84 | 90029933 | B1 | 1000350866 | 13.08.2028 | 20000 | CCK-MP-EXCV-EX7145-GRSYST-GRINJ | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl HV Motor Coupling | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 30 | 90030128 | B1 | 1000350938 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-ELCTHV-HVMOT-COUPL | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Gearbox Swing P1 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000350758 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-SWGSYS-SWBOX-SGBPF | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Gearbox Swing P2 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000350759 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-SWGSYS-SWBOX-SGBPR | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Splitter Gearbox | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 240 | 90030087 | B1 | 1000350921 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-PMPDR | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Pump Hyd Work Pos1 & Pos2 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 54 | 90030234 | B1 | 1000350922 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-WPPP1 | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Pump Hyd Work Pos3 & Pos4 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 54 | 90030286 | B1 | 1000350930 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-WPPP2 | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Pump Swing Combination | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 36 | 90030252 | B1 | 1000350923 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-SWPP1 | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Pump Fan Hyd Oil Cooler | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90030278 | B1 | 1000350924 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-HECP1 | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Pump Servo Bearing Lube | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030280 | B1 | 1000350925 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-SVPP1 | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Lube Pump Splitter Gear Box | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030281 | B1 | 1000350926 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-PTOLU | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Pump Oil Replenishing | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030285 | B1 | 1000350927 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-RPPP1 | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Ladder Raise Cylinder | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 6 | 90030320 | B1 | 1000350933 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-LACYL | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Cyl Bucket RH Lift | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 52 | 90029967 | B1 | 1000350898 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-BUCYR | 6200 | 7526 | 544
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Rotary Connection | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 72 | 90029901 | B1 | 1000350840 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-ROTRY | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Vlve Bank Module Quarter Life | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 12 | 90029987 | B1 | 1000350913 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDVLV-MCVLU | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Valve Pressure Reducing Y3 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 6 | 90030294 | B1 | 1000350932 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDVLV-VVPRV | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Valve Pressure Limiting Y4 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 6 | 90030321 | B1 | 1000350931 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDVLV-VVPLV | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Motor Swing Front | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000350842 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDMOT-SWMOF | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Motor Swing Rear | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000350841 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDMOT-SWMOR | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Motor Travel LHF | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000350843 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDMOT-TRMLF | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Motor Travel LHR | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000350844 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDMOT-TRMLR | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Motor Travel RHF | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000350845 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDMOT-TRMRF | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Motor Travel RHR | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000350846 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDMOT-TRMRR | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Accumulator Track Hyd LH | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000350847 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDACC | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Accumulator Track Hyd RH | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000350848 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-HYDSYS-HDACC | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Accumulator Servo Hyd | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 3 | 90030487 | B1 | 1000350914 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDACC | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Accumulator Ladder Hyd | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 4 | 90030685 | B1 | 1000350940 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDACC | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Track Tensioning Hoses | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90030538 | B1 | 1000350939 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HHTTL | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Hyd Hose Work Pumps to Valves | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 10.5 | 90030287 | B1 | 1000350928 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HWPVV | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Hyd Hose Swing Pump Swing Motor | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90030288 | B1 | 1000350929 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HSPSM | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Hyd Hose Rotary Con to Valve Bank | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029912 | B1 | 1000350852 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HRCVV | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Hoses Rotary Conn to Travel Motor | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 48 | 90029914 | B1 | 1000350853 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HRCTM | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Operators Seat | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 16 | 90029915 | B1 | 1000350854 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-STRUCT-CABIN-SEATO | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Motor A/C Comp Drive | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000350941 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-STRUCT-AIRC1-ACONM | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Motor A/C Comp Drive | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000350942 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-STRUCT-AIRC2-ACONM | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Tank Module | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 84 | 90030313 | B1 | 1000350917 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-STRUCT-HDTNK | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Boom Module Quarter Life | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 48 | 90029992 | B1 | 1000350916 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-STRUCT-BOOMS | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Service Arm Locking Cyl | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 20 | 90029983 | B1 | 1000350911 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-STRUCT-SRVCT | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Service Module Hosing | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 24 | 90029982 | B1 | 1000350910 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-STRUCT-SRVCT | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Bucket Assembly | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 78 | 90029975 | B1 | 1000350900 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-STRUCT-BUCKT | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Auto Lube Pump P1 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 2 | 90030312 | B1 | 1000350858 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-GRSYST-AUTLU-ALBPP | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Auto Lube Pump P3 | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 2 | 90035351 | B1 | 1000358636 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-GRSYST-AUTLU-ALBP3 | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Air Compressor Unit | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 15 | 90030086 | B1 | 1000350920 | 28.08.2028 | 20000 | CCK-MP-EXCV-EX7145-PNEUMC-COMPR | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Minestar Harness | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 43.5 | 90029998 | B1 | 1000350918 | 28.08.2028 | 4000 | CCK-MP-EXCV-EX7145-MANGMT-UMMMC | 6200 | 7526 | 7526
R9400E | Onsite Shut | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Boom Cyl | 2028-08-23 | 2028-09-04 | 282 hrs | FY29 | 72 | 90029908 | B1 | 1000350849 | 02.11.2028 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HBMCL | 6200 | 7526 | 7526
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 - POWER PACK MIDLIFE & MAJOR COMPONENTS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cooler Module Assembly | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 22 | 90011659 | B1 | 1000144781 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-COOLER | 6800 | 54883 | 1945
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Tower Raise NCS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 8 | 90011666 | B1 | 1000233303 | 06.07.2028 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TRCYL | 6800 | 54883 | 1949
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Tower Raise CS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 8 | 90011667 | B1 | 1000233302 | 06.07.2028 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TRCYR | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Tower Angle Locking NCS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 4 | 90011670 | B1 | 1000242413 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TACYL | 6800 | 54883 | 18195
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Tower Angle Locking CS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 4 | 90011670 | B1 | 1000242414 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TACYR | 6800 | 54883 | 16796
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Stacking 8 Spool | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 8 | 90011688 | B1 | 1000233278 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVS8S | 6800 | 54883 | 11133
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Stacking 11 spool | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 10 | 90011689 | B1 | 1000233279 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VV11S | 6800 | 54907 | 11133
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Tension Cable | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 2 | 90022224 | B1 | 1000232698 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVTNC | 6800 | 54883 | 11133
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Hyd Motor Screw Jack NCS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 1 | 90022221 | B1 | 1000232714 | 06.07.2028 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MSJTL | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Hyd Motor Screw Jack CS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 1 | 90022221 | B1 | 1000232713 | 06.07.2028 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MSJTR | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Sheaves & Cables | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 140 | 90029857 | B1 | 1000303754 | 06.07.2028 | 10000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Tower Cylinders | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 58 | 90029866 | B1 | 1000303756 | 06.07.2028 | 10000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Gearbox Power Head | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 52 | 90011716 | B1 | 1000232692 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-PWRHD | 6800 | 54883 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Screw Jack Cable Tension NCS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 12 | 90022222 | B1 | 1000232696 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-SCBTL | 6800 | 54883 | 11133
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Screw Jack Cable Tension CS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 12 | 90022222 | B1 | 1000232697 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-SCBTR | 6800 | 54883 | 11133
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Rod Support | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 20 | 90022208 | B1 | 1000232704 | 06.07.2028 | 10000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-RDSPT | 6800 | 54883 | 1072
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Overhaul Rod Changer & Carousel | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 8 | 90029755 | B1 | 1000303758 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-CARAS | 6800 | 54883 | 11133
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Brkout Wrench & Fork Assy | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 38 | 90029873 | B1 | 1000303757 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER-BOWRH | 6800 | 54883 | 11133
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Mast & A-Frame Harnesses | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 70.5 | 90030429 | B1 | 1000303759 | 06.07.2028 | 20000 | CCK-MP-DRLL-DR2110-ELCTLV-HARNS-HARCO | 6800 | 54907 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl ADS PTZ Camera & LIDAR | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 10 | 90029206 | B1 | 1000294202 | 07.07.2028 | 10000 | CCK-MP-DRLL-DR2110-ADSYST-ADSPR-HTCAM | 6800 | 54907 | 14238
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Power Pack Midlife | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 197 | 90029572 | B1 | 1000295328 | 20.07.2028 | 10000 | CCK-MP-DRLL-DR2110-ENGINE | 6800 | 54907 | 5228
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 EncoderHarness Cab to Aframe Repl | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 6 | 90036144 | B1 | 1000365253 | 26.08.2028 | 5000 | CCK-MP-DRLL-DR2110-ADSYST-HARNC | 6800 | 54907 | 14230
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 12M Air Cond Rencool Service | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 16 | 90018579 | B1 | 1000180987 | 19.09.2028 | 12 Monthly | CCK-MP-DRLL-DR2110-STRUCT-CABIN-AIRCN
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 12M Air Conditioner Service | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 36 | 90018564 | B1 | 1000180528 | 19.09.2028 | 12 Monthly | CCK-MP-DRLL-DR2110-STRUCT-CABIN-AIRCN
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Jack Leg NDE NCS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 8 | 90015956 | B1 | 1000144793 | 25.01.2029 | 15000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYLF | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Jack Leg DE NCS | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 8 | 90015958 | B1 | 1000144795 | 25.01.2029 | 15000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYLR | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Valve Dual Counter Balance | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 2 | 90015975 | B1 | 1000144803 | 25.01.2029 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDCB | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Rod Thread lube Pump | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 2 | 90011732 | B1 | 1000207193 | 25.01.2029 | 10000 | CCK-MP-DRLL-DR2110-GRSYST-RTLPP | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Pump Water Injection | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 2 | 90016011 | B1 | 1000144840 | 31.01.2029 | 5000 | CCK-MP-DRLL-DR2110-DSTSUP-WTRPP | 6800 | 54883 | 11134
PV271 | Onsite Shut | Drills | Fortescue | DR2110 | DR2110 Repl Yoke Oscillation | 2028-09-05 | 2028-09-13 | 186 hrs | FY29 | 24 | 90016004 | B1 | 1000144836 | 20.02.2029 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-UNDER-YKOSC | 6800 | 54883 | 20610
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 - MAJOR COMPONENTS | 2028-09-13 | 2028-09-25 | 282 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl HV Motor Coupling | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 30 | 90030128 | B1 | 1000351985 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-ELCTHV-HVMOT-COUPL | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Gearbox Swing P1 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000351885 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-SWGSYS-SWBOX-SGBPF | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Gearbox Swing P2 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000351886 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-SWGSYS-SWBOX-SGBPR | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Splitter Gearbox | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 240 | 90030087 | B1 | 1000351968 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-PMPDR | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Pump Hyd Work Pos1 & Pos2 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 54 | 90030234 | B1 | 1000351969 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-WPPP1 | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Pump Hyd Work Pos3 & Pos4 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 54 | 90030286 | B1 | 1000351977 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-WPPP2 | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Pump Swing Combination | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 36 | 90030252 | B1 | 1000351970 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-SWPP1 | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Pump Fan Hyd Oil Cooler | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 24 | 90030278 | B1 | 1000351971 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-HECP1 | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Pump Servo Bearing Lube | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 4 | 90030280 | B1 | 1000351972 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-SVPP1 | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Lube Pump Splitter Gear Box | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 4 | 90030281 | B1 | 1000351973 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-PTOLU | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Pump Oil Replenishing | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 4 | 90030285 | B1 | 1000351974 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-RPPP1 | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Ladder Raise Cylinder | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 6 | 90030320 | B1 | 1000351980 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-LACYL | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Bucket LH Lift | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 52 | 90029964 | B1 | 1000351944 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-BUCYL | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Bucket RH Lift | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 52 | 90029967 | B1 | 1000351945 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-BUCYR | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Rotary Connection | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 72 | 90029901 | B1 | 1000351887 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-ROTRY | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Vlve Bank Module Quarter Life | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 12 | 90029987 | B1 | 1000351960 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDVLV-MCVLU | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Valve Pressure Reducing Y3 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 6 | 90030294 | B1 | 1000351979 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDVLV-VVPRV | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Valve Pressure Limiting Y4 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 6 | 90030321 | B1 | 1000351978 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDVLV-VVPLV | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Motor Swing Front | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000351889 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDMOT-SWMOF | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Motor Swing Rear | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000351888 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDMOT-SWMOR | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Motor Travel LHF | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000351890 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDMOT-TRMLF | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Motor Travel LHR | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000351891 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDMOT-TRMLR | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Motor Travel RHF | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000351892 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDMOT-TRMRF | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Motor Travel RHR | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000351893 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDMOT-TRMRR | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Accumulator Track Hyd LH | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000351894 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDACC | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Accumulator Track Hyd RH | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000351895 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-HYDSYS-HDACC | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Accumulator Servo Hyd | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 3 | 90030487 | B1 | 1000351961 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDACC | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Accumulator Ladder Hyd | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 4 | 90030685 | B1 | 1000351987 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDACC | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Track Tensioning Hoses | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 24 | 90030538 | B1 | 1000351986 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HHTTL | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Hyd Hose Work Pumps to Valves | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 10.5 | 90030287 | B1 | 1000351975 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HWPVV | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Hyd Hose Swing Pump Swing Motor | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 24 | 90030288 | B1 | 1000351976 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HSPSM | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Hyd Hose Rotary Con to Valve Bank | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 24 | 90029912 | B1 | 1000351899 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HRCVV | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Hoses Rotary Conn to Travel Motor | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 48 | 90029914 | B1 | 1000351900 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HRCTM | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Operators Seat | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 16 | 90029915 | B1 | 1000351901 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-STRUCT-CABIN-SEATO | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Motor A/C Comp Drive | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000351988 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-STRUCT-AIRC1-ACONM | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Motor A/C Comp Drive | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000351989 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-STRUCT-AIRC2-ACONM | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Tank Module | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 84 | 90030313 | B1 | 1000351964 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-STRUCT-HDTNK | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Boom Module Quarter Life | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 48 | 90029992 | B1 | 1000351963 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-STRUCT-BOOMS | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Service Module Hosing | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 24 | 90029982 | B1 | 1000351957 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-STRUCT-SRVCT | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Service Arm Locking Cyl | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 20 | 90029983 | B1 | 1000351958 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-STRUCT-SRVCT | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Bucket Assembly | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 78 | 90029975 | B1 | 1000351947 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-STRUCT-BUCKT | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Auto Lube Pump P1 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 2 | 90030312 | B1 | 1000351905 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-GRSYST-AUTLU-ALBPP | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Auto Lube Pump P3 | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 2 | 90035351 | B1 | 1000358640 | 06.09.2028 | 10000 | CCK-MP-EXCV-EX7146-GRSYST-AUTLU-ALBP3 | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Grease Block & Injectors | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 84 | 90029933 | B1 | 1000351913 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-GRSYST-GRINJ | 6200 | 7286 | 7286
R9400E | Onsite Shut | Excavators | Fortescue | EX7146 | EX7146 Repl Air Compressor Unit | 2028-09-13 | 2028-09-25 | 282 hrs | FY29 | 15 | 90030086 | B1 | 1000351967 | 06.09.2028 | 20000 | CCK-MP-EXCV-EX7146-PNEUMC-COMPR | 6200 | 7286 | 7286
16M | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 - ENGINE MIDLIFE & MAJOR COMPONENTS | 2028-09-18 | 2028-09-27 | 222 hrs | FY29
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Engine Midlife Complete | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 77 | 90019632 | B1 | 1000201878 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-ENGINE | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Articulation LH | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 4 | 90021512 | B1 | 1000225881 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYL | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Blade Lift RH | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 4 | 90021509 | B1 | 1000225884 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BLCYR | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Blade Tilt LH | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 4 | 90021511 | B1 | 1000225885 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYL | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Blade Tilt RH | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 4 | 90021511 | B1 | 1000225886 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYR | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Centre Shift | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 4 | 90021510 | B1 | 1000225887 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-CSCYL | 5500 | 24399 | 173
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Ripper Lift | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 4 | 90021514 | B1 | 1000225888 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-RICYL | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Front Axle Assembly Midlife | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 56 | 90030394 | B1 | 1000303390 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-STRUCT-AXLES | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Major Service Air Conditioner | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 24 | 90019634 | B1 | 1000201881 | 17.08.2028 | 7000 | CCK-MP-GRDR-GR7107-STRUCT-CABIN-AIRCN | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Gearbox Circle Drive Front | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 14 | 90019609 | B1 | 1000201911 | 03.09.2028 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-CIRCL-CDBXF | 5500 | 24399 | 820
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Gearbox Circle Drive Rear | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 14 | 90019609 | B1 | 1000201912 | 19.09.2028 | 14000 | CCK-MP-GRDR-GR7107-STRUCT-CIRCL-CDBXR | 5500 | 24399 | 820
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Drive Shaft TCon to Trans | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 3 | 90019588 | B1 | 1000201889 | 03.10.2028 | 7000 | CCK-MP-GRDR-GR7107-FDRSYS-DRSHT-SHT02 | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Drive Shaft Trans to Rr Diff | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 6 | 90019587 | B1 | 1000201888 | 05.10.2028 | 7000 | CCK-MP-GRDR-GR7107-FDRSYS-DRSHT-SHT01 | 5500 | 24399 | 9687
24 | Onsite Shut | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Blade Lift LH | 2028-09-18 | 2028-09-27 | 222 hrs | FY29 | 4 | 90021509 | B1 | 1000225883 | 05.10.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BLCYL | 5500 | 24399 | 1941
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 - ENGINE & MAJOR COMPONENTS | 2028-10-25 | 2028-11-04 | 240 hrs | FY29
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Torque Converter | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 60 | 90000309 | B2 | 1000091142 | 21.10.2028 | 18000 | CCK-MP-DOZR-DZ172 -TRNSYS-TRQUE | 5000 | 68264 | 7030
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Steer Clutch & Brake Assm LH | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091148 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -BRKSTR-SCABL | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Steer Clutch & Brake Assm RH | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091149 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -BRKSTR-SCABR | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Engine Cat C27 | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 114 | 90015849 | B1 | 1000160134 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -ENGINE | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Rad Engine Cooling SN 529 UP | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 48 | 90000307 | B2 | 1000091140 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -ENGINE-COSYS-RADTR | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Aftercooler Engine | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 8 | 90010841 | B1 | 1000108416 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -ENGINE-INTEX-AFTER | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Fan Cooling Motor Hyd | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 16 | 90002094 | B2 | 1000108414 | 05.11.2028 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDCFM | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Hyd Oil Cooler | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 10 | 90009664 | B2 | 1000091155 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDOCO | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Ovhl Hydraulic & Fuel Tank | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 48 | 90010842 | B1 | 1000108418 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDTNK | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Hyd Pump Cooling Fan | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 16 | 90004952 | B2 | 1000091153 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -HYDSYS-HYDPP-HYFPP | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Hyd Pump Implement | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 10 | 90000301 | B2 | 1000091150 | 05.11.2028 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HYDPP-HYIPP | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Overhaul Air Conditioner | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 48 | 90017468 | B1 | 1000196621 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -STRUCT-CABIN-AIRCN | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Operators Seat | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 8 | 90000318 | B1 | 1000108415 | 05.11.2028 | 6000 | CCK-MP-DOZR-DZ172 -STRUCT-CABIN-SEATS | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Equaliser Bar | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 110 | 90002097 | B1 | 1000108420 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -STRUCT-CHASS-EQUAL | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Minor Overhaul Track Frame LH | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 98 | 90002098 | B1 | 1000108421 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -STRUCT-UNDER-TKFRL | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Minor Overhaul Track Frame RH | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 98 | 90010766 | B1 | 1000108423 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -STRUCT-UNDER-TKFRR | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Drive Shaft | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 6 | 90033296 | B1 | 1000334105 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -TRNSYS | 5000 | 68264 | 16489
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Transmission | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 48 | 90000308 | B2 | 1000091143 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -TRNSYS-TRANS | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Pump Trans & TCon Charge | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 10 | 90000302 | B2 | 1000091145 | 05.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -TRNSYS-TRPMP | 5000 | 68264 | 6824
D10T | Onsite Shut | Ancillary | Fortescue | DZ172 | DZ172 Repl Final Drive LH | 2028-10-25 | 2028-11-04 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091146 | 06.11.2028 | 18000 | CCK-MP-DOZR-DZ172 -FDRSYS-FDRLH | 5000 | 68245 | 6824
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 - SLEW BEARING, BOOM, STICK & BOTH ENGINES | 2028-10-25 | 2028-11-14 | 480 hrs | FY29
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Fan Drive Eng Cooling Hose | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 36 | 90027564 | B1 | 1000288538 | 04.07.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-FDECH | 6900 | 21434 | 10785
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Fan Drive Hyd Cooling Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 36 | 90027565 | B1 | 1000288539 | 04.07.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-FDHCH | 6900 | 21434 | 10797
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hydraulic Cooling Circ Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 36 | 90031704 | B1 | 1000288540 | 04.07.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-HCCHH | 6900 | 21434 | 10785
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Annual Air Con Service RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 13 | 90027615 | B1 | 1000288563 | 09.07.2028 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN-AIRCR | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Annual Air Con Service LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 13 | 90027615 | B1 | 1000288593 | 14.08.2028 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN-AIRCL
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Batteries | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 4 | 90027525 | B1 | 1000288559 | 09.09.2028 | 10000 | CCK-MP-EXCV-EX7121-ELCTLV-CHARG-BATTY | 6900 | 21434 | 5556
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Rotor to Drive Motor Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 40 | 90027570 | B1 | 1000288545 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-RCDMH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Servo Hoses Cascade to Bulkhead | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 16 | 90027572 | B1 | 1000288547 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SHBLK | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Servo Hoses Cascade to Trvl Valve | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90027575 | B1 | 1000288549 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SHTRV | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 2nd Speed Trvl Brake Release Hose | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 10 | 90027559 | B1 | 1000288535 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SSTBR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Swing Motor Case Drain Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90027577 | B1 | 1000288551 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SWMCD | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Travel Motor Case Drain Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 10 | 90027578 | B1 | 1000288552 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-TMCDH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel LHF | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000288529 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMLF | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel RHF | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000288531 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMRF | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel RHR | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000288532 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMRR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Hyd Pump Pos1 | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000288501 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-MNPP1 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Hyd Pump Pos2 | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000288502 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-MNPP2 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Hyd Pump Pos4 | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000288504 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-MNPP4 | 6900 | 21434 | 228
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Pos1 & Pos2 | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 42 | 90027492 | B1 | 1000288505 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SP1P2 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Pos3 & Pos4 | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 42 | 90027492 | B1 | 1000288506 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SP3P4 | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Replenish LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 2 | 90027495 | B1 | 1000288511 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SRPPL | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Swing Replenish RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 2 | 90027495 | B1 | 1000288512 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SRPPR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Pump Servo LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 2 | 90027496 | B1 | 1000288509 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SVPPL | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Pump Servo RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 2 | 90027496 | B1 | 1000288510 | 11.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-SVPPR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Boom Arch Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 24 | 90027558 | B1 | 1000288536 | 12.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-BMARH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Boom & MCV Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 136 | 90032593 | B1 | 1000324957 | 12.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-HBSBC | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Boom Stick Bucket Cyl Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 136 | 90027560 | B1 | 1000288537 | 12.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-HBSBC | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Rotor & Logic Valve Hp Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 36 | 90027571 | B1 | 1000288546 | 12.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-RCLVH | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Servo Hose Bulkhead to MCV | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 16 | 90027574 | B1 | 1000288548 | 12.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SHMCV | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Travel LHR | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000288530 | 12.09.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-TRMLR | 6900 | 21434 | 9486
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Control Valve Block LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 50 | 90027502 | B1 | 1000288554 | 14.09.2028 | 36000 | CCK-MP-EXCV-EX7121-HYDSYS-HDVLV-MCVVL | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Control Valve Block RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 50 | 90027502 | B1 | 1000288555 | 14.09.2028 | 36000 | CCK-MP-EXCV-EX7121-HYDSYS-HDVLV-MCVVR | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Boom Assy Dressed | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 324 | 90031798 | B1 | 1000314054 | 14.09.2028 | 36000 | CCK-MP-EXCV-EX7121-STRUCT-BOOMS | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Stick Assy Dressed | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 192 | 90031801 | B1 | 1000314250 | 14.09.2028 | 36000 | CCK-MP-EXCV-EX7121-STRUCT-STICK | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Track Tensioner LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 72 | 90027527 | B1 | 1000288560 | 14.09.2028 | 18000 | CCK-MP-EXCV-EX7121-STRUCT-TKFRL-TENSR | 6900 | 21434 | 1769
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Track Tensioner RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 72 | 90027527 | B1 | 1000288561 | 14.09.2028 | 18000 | CCK-MP-EXCV-EX7121-STRUCT-TKFRR-TENSR | 6900 | 21434 | 521
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Slew Gear Bearing | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 288 | 90027508 | B1 | 1000288533 | 14.09.2028 | 36000 | CCK-MP-EXCV-EX7121-STRUCT-UNDER-SLEWB | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Auto Lube Pump | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 6 | 90027592 | B1 | 1000288569 | 09.10.2028 | 6000 | CCK-MP-EXCV-EX7121-GRSYST-ALBPP | 6900 | 21434 | 9780
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Grease Control Valving | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 14 | 90027612 | B1 | 1000288570 | 09.10.2028 | 12000 | CCK-MP-EXCV-EX7121-GRSYST-ALCON
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Hydraulic System Tune Up | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 24 | 90017865 | B1 | 1000288568 | 09.10.2028 | 6000 | CCK-MP-EXCV-EX7121-HYDSYS | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Hydraulic Oil Replacement | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90016793 | B1 | 1000288558 | 09.10.2028 | 6000 | CCK-MP-EXCV-EX7121-HYDSYS | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Cyl Boom LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 138 | 90027497 | B1 | 1000288513 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-BMCYL | 6900 | 21434 | 2948
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Oil Suction Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 48 | 90027568 | B1 | 1000288543 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-OILSC | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl PTO Cooling Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90027569 | B1 | 1000288544 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-PTOCL | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Swing Circuit Hoses | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 16 | 90027576 | B1 | 1000288550 | 09.10.2028 | 9000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SWCRT | 6900 | 21434 | 13568
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Fan Hyd Cool Front | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90027504 | B1 | 1000288525 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-FMCHF | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Fan Hyd Cool Rear | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90027504 | B1 | 1000288526 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-FMCHR | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Fan Engine Cool LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 18 | 90027505 | B1 | 1000288527 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-FMECL | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Fan Engine Cool RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 18 | 90027505 | B1 | 1000288528 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-FMECR | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Pump Drive Gearbox LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 116 | 90027489 | B1 | 1000288459 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-PPDRL | 6900 | 21434 | 2948
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Pump Drive Gearbox RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 116 | 90027489 | B1 | 1000288500 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-PPDRR | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Engine Cat C32 LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 244 | 90027533 | B1 | 1000288442 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-LHENGN | 6900 | 21434 | 2948
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Radiator LH Engine Cooling | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90027552 | B1 | 1000288446 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-LHENGN-COSYS-RADTR | 7100 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl LH Aftercooler | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 24 | 90023361 | B1 | 1000309254 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-LHENGN-INTEX-AFTER | 6900 | 21434 | 2948
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Engine Cat C32 RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 244 | 90027534 | B1 | 1000288448 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-RHENGN | 6900 | 21434 | 2948
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Radiator RH Engine Cooling | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 12 | 90027553 | B1 | 1000288452 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-RHENGN-COSYS-RADTR | 7100 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl RH Aftercooler | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 24 | 90023360 | B1 | 1000309255 | 09.10.2028 | 18000 | CCK-MP-EXCV-EX7121-RHENGN-INTEX-AFTER | 6900 | 21434 | 2948
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Main Hyd Pump Pos3 | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000288503 | 22.10.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-MNPP3 | 6900 | 21434 | 8484
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Cyl Boom RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 138 | 90027497 | B1 | 1000288514 | 28.10.2028 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-BMCYR | 6900 | 21434 | 2604
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Minestar Harness | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 43.5 | 90031708 | B1 | 1000369996 | 29.12.2028 | 4000 | CCK-MP-EXCV-EX7121-MANGMT-UMMMC | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Bucket LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 32 | 90027499 | B1 | 1000288517 | 23.01.2029 | 10000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-BUCYL | 6900 | 21434 | 2948
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Bucket RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 32 | 90027499 | B1 | 1000288518 | 23.01.2029 | 10000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-BUCYR | 6900 | 21434 | 11598
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Operators Seat | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 2 | 90027613 | B1 | 1000288534 | 23.01.2029 | 10000 | CCK-MP-EXCV-EX7121-STRUCT-CABIN-SEATS | 6900 | 21434 | 21434
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Gearbox Swing LHR | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 82 | 90027580 | B1 | 1000288456 | 23.01.2029 | 20000 | CCK-MP-EXCV-EX7121-SWGSYS-SWBOX-SGBLR | 6900 | 21434 | 2846
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Gearbox Swing RHF | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 82 | 90027580 | B1 | 1000288457 | 23.01.2029 | 20000 | CCK-MP-EXCV-EX7121-SWGSYS-SWBOX-SGBRF | 6900 | 21434 | 2846
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Gearbox Swing RHR | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 82 | 90027580 | B1 | 1000288458 | 23.01.2029 | 20000 | CCK-MP-EXCV-EX7121-SWGSYS-SWBOX-SGBRR | 6900 | 21434 | 2846
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Stick LH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 54 | 90027498 | B1 | 1000288515 | 22.02.2029 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-STCLL | 6900 | 21434 | 6378
6040 | Onsite Shut | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Stick RH | 2028-10-25 | 2028-11-14 | 480 hrs | FY29 | 54 | 90027498 | B1 | 1000288516 | 22.02.2029 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-STCLR | 6900 | 21434 | 6378
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 - MAJOR COMPONENTS | 2028-11-20 | 2028-11-29 | 222 hrs | FY29
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Brake Slack Adjuster LH | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 1 | 90002641 | B2 | 1000105667 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -BRKSYS-SLACK-SLACL | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Brake Slack Adjuster Rear | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 1 | 90002641 | B2 | 1000105668 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -BRKSYS-SLACK-SLACR | 5200 | 50884 | 13188
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Service Brake LHR | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 54 | 90004548 | B2 | 1000105597 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -BRKSYS-SRVBK-SVBLR | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Electrical Harness | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 48 | 90010000 | B2 | 1000105661 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -ELCTLV-HARNS | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Radiator Engine Cooling | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 98 | 90002618 | B3 | 1000105430 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -ENGINE-COSYS-RADTR | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Rear Axel Assembly | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 128 | 90030396 | B1 | 1000303529 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -FDRSYS-DIFFL | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Hyd Pump Steering Main | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 8 | 90002647 | B2 | 1000105624 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-HYSTP | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Operators Seat | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 4 | 90002663 | B2 | 1000105631 | 03.08.2028 | 7000 | CCK-MP-GRDR-GR123 -STRUCT-CABIN-SEATS | 5200 | 50884 | 6392
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Torque Converter | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 98 | 90002630 | B2 | 1000105432 | 03.08.2028 | 14000 | CCK-MP-GRDR-GR123 -TRNSYS-TRQUE | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Hyd Pump Differential Lock | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 8 | 90002649 | B2 | 1000105626 | 10.09.2028 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-DIFFL | 5200 | 50884 | 3151
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Sepura SCC Microphone | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 0.5 | 90028989 | B1 | 1000289374 | 01.10.2028 | 12 Monthly | CCK-MP-GRDR-GR123 -COMMUN-RADIO
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Engine Midlife complete | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 72 | 90015782 | B1 | 1000290317 | 05.10.2028 | 7000 | CCK-MP-GRDR-GR123 -ENGINE | 5200 | 50884 | 9251
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Service Major Air Conditioner | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 24 | 90017472 | B1 | 1000290321 | 05.10.2028 | 7000 | CCK-MP-GRDR-GR123 -STRUCT-CABIN-AIRCN
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Transmission | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 146 | 90002631 | B2 | 1000105433 | 14.12.2028 | 14000 | CCK-MP-GRDR-GR123 -TRNSYS-TRANS | 5200 | 50884 | 1244
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Transmission Oil Cooler | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 6 | 90002632 | B2 | 1000105434 | 14.12.2028 | 14000 | CCK-MP-GRDR-GR123 -TRNSYS-TROLC | 5200 | 50884 | 1244
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Pump Transmission | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 8 | 90002633 | B2 | 1000105435 | 14.12.2028 | 14000 | CCK-MP-GRDR-GR123 -TRNSYS-TRPMP | 5200 | 50884 | 1244
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Service Brake RHF | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 52 | 90002640 | B2 | 1000105596 | 16.12.2028 | 14000 | CCK-MP-GRDR-GR123 -BRKSYS-SRVBK-SVBRF | 5200 | 50884 | 6392
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Output Drive Shaft Unis | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 8 | 90033264 | B1 | 1000333917 | 23.04.2029 | 7000 | CCK-MP-GRDR-GR123 -FDRSYS-DRSHT-SHT01 | 5200 | 50884 | 6392
24M | Onsite Shut | Ancillary | Fortescue | GR123 | GR123 Repl Trans Input Drive Shaft Unis | 2028-11-20 | 2028-11-29 | 222 hrs | FY29 | 8 | 90033267 | B1 | 1000333919 | 23.04.2029 | 7000 | CCK-MP-GRDR-GR123 -FDRSYS-DRSHT-SHT02 | 5200 | 50884 | 6392
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 - LH ENGINE & MAJOR COMPONENTS | 2028-12-04 | 2028-12-15 | 276 hrs | FY29
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Operators Seat | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 2 | 90003180 | B1 | 1000206867 | 20.08.2028 | 10000 | CCK-MP-EXCV-EX7110-STRUCT-CABIN-SEATS | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Gearbox Swing LHR | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 80 | 90012369 | B1 | 1000206829 | 20.08.2028 | 20000 | CCK-MP-EXCV-EX7110-SWINGS-SWBOX-SGBLR | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Gearbox Swing RHF | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 80 | 90012369 | B1 | 1000206830 | 20.08.2028 | 20000 | CCK-MP-EXCV-EX7110-SWINGS-SWBOX-SGBRF | 6900 | 25928 | 6138
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Gearbox Swing RHR | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 80 | 90012369 | B1 | 1000206831 | 20.08.2028 | 20000 | CCK-MP-EXCV-EX7110-SWINGS-SWBOX-SGBRR | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Annual Air Con Service RH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 13 | 90004141 | B1 | 1000206896 | 18.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN-AIRCR | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Idler Track RH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 18 | 90003189 | B1 | 1000206919 | 14.10.2028 | 1500 | CCK-MP-EXCV-EX7110-STRUCT-TKFRR-IDLRH | 490 | 1733 | 346
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Fan Engine Cool LH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 18 | 90003177 | B1 | 1000206860 | 27.10.2028 | 18000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-FMECL | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Engine Cat C32 LH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 250 | 90017913 | B1 | 1000206798 | 27.10.2028 | 18000 | CCK-MP-EXCV-EX7110-LHENGN | 6900 | 25928 | 1337
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Minestar Harness | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 43.5 | 90027626 | B2 | 1000281596 | 07.11.2028 | 4000 | CCK-MP-EXCV-EX7110-MANGMT-UMMMC | 6900 | 25928 | 12535
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Bucket LH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 32 | 90003169 | B1 | 1000206850 | 05.12.2028 | 10000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-BUCYL | 6900 | 25928 | 4012
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Bucket RH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 32 | 90003169 | B1 | 1000206851 | 05.12.2028 | 10000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-BUCYR | 6900 | 25928 | 4012
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Sprocket LH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 24 | 90003156 | B1 | 1000206916 | 06.01.2029 | 1500 | CCK-MP-EXCV-EX7110-TRAVEL-SPRKL | 490 | 1733 | 1733
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Sprocket RH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 24 | 90003156 | B1 | 1000206927 | 06.01.2029 | 1500 | CCK-MP-EXCV-EX7110-TRAVEL-SPRKR | 490 | 1733 | 1733
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Travel RHR | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 12 | 90022657 | B1 | 1000206865 | 01.02.2029 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-TRMRR | 6900 | 25928 | 6943
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Auto Lube SStructure | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 12 | 90018988 | B1 | 1000206903 | 02.02.2029 | 6000 | CCK-MP-EXCV-EX7110-GRSYST-ALBPP | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Hydraulic Oil Replacement | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 12 | 90016793 | B1 | 1000206891 | 02.02.2029 | 6000 | CCK-MP-EXCV-EX7110-HYDSYS | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Hydraulic System Tune Up | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 24 | 90017865 | B1 | 1000206902 | 02.02.2029 | 6000 | CCK-MP-EXCV-EX7110-HYDSYS | 6900 | 25928 | 25928
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Case Drain Hoses | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 16 | 90009472 | B2 | 1000344106 | 02.02.2029 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-HPCDL | 6900 | 25928 | 12901
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Fan Drive Hyd Cooling Hoses | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 36 | 90009470 | B2 | 1000344108 | 20.03.2029 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-FDHCH | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Servo Hoses Bulkhead to MCV | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 16 | 90009479 | B1 | 1000343096 | 20.03.2029 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SHMCV | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Repl Track Tensioning Hoses | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 3 | 90022741 | B1 | 1000206886 | 20.03.2029 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-TRTNH | 6900 | 25928 | 6025
6040 | Onsite Shut | Excavators | Fortescue | EX7110 | EX7110 Annual Air Con Service LH | 2028-12-04 | 2028-12-15 | 276 hrs | FY29 | 13 | 90004141 | B1 | 1000287617 | 21.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN-AIRCL
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 - ENGINE & MAJOR COMPONENTS | 2028-12-11 | 2028-12-20 | 222 hrs | FY29
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Output Drive Shaft Unis | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 8 | 90033264 | B1 | 1000333913 | 08.08.2028 | 7000 | CCK-MP-GRDR-GR122 -FDRSYS-DRSHT-SHT01 | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Trans Input Drive Shaft Unis | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 8 | 90033267 | B1 | 1000333915 | 08.08.2028 | 7000 | CCK-MP-GRDR-GR122 -FDRSYS-DRSHT-SHT02 | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Front Axle Assembly Midlife | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 42 | 90025907 | B1 | 1000255887 | 08.08.2028 | 7000 | CCK-MP-GRDR-GR122 -STRUCT-AXLES | 5200 | 68036 | 10615
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Operators Seat | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 4 | 90002663 | B2 | 1000090924 | 08.08.2028 | 7000 | CCK-MP-GRDR-GR122 -STRUCT-CABIN-SEATS | 5200 | 68036 | 924
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Sepura SCC Microphone | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 0.5 | 90028989 | B1 | 1000289373 | 11.08.2028 | 12 Monthly | CCK-MP-GRDR-GR122 -COMMUN-RADIO | 5200 | 68036 | 68036
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Service Brake RHR | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 54 | 90004548 | B2 | 1000090911 | 01.11.2028 | 14000 | CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBRR | 5200 | 68036 | 575
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Engine Cat C18 | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 310 | 90015771 | B1 | 1000290308 | 15.12.2028 | 14000 | CCK-MP-GRDR-GR122 -ENGINE | 5200 | 68036 | 1754
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Overhaul Air Condtioner System | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 48 | 90017475 | B1 | 1000290314 | 15.12.2028 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CABIN-AIRCN | 5200 | 68036 | 15776
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Aftercooler Engine | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 24 | 90002623 | B2 | 1000090941 | 16.12.2028 | 14000 | CCK-MP-GRDR-GR122 -ENGINE-INTEX-AFTER | 5200 | 68036 | 1749
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Service Brake LHF | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 52 | 90002640 | B2 | 1000090908 | 17.12.2028 | 14000 | CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBLF | 5200 | 68036 | 924
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Service Brake LHR | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 54 | 90004548 | B2 | 1000090910 | 17.12.2028 | 14000 | CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBLR | 5200 | 68036 | 924
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Service Brake RHF | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 52 | 90002640 | B2 | 1000090909 | 17.12.2028 | 14000 | CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBRF | 5200 | 68036 | 15776
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Hyd Pump Differential Lock | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 8 | 90002649 | B2 | 1000090919 | 17.12.2028 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-DIFFL | 5200 | 68036 | 1749
24M | Onsite Shut | Ancillary | Fortescue | GR122 | GR122 Repl Transmission Oil Cooler | 2028-12-11 | 2028-12-20 | 222 hrs | FY29 | 6 | 90002632 | B2 | 1000090901 | 17.12.2028 | 14000 | CCK-MP-GRDR-GR122 -TRNSYS-TROLC | 5200 | 68036 | 1749
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 - POWER PACK MODULES & SLEW BEARING & ATTACHMENT | 2029-02-06 | 2029-02-18 | 282 hrs | FY29
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Gearbox Swing RHF | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 60 | 90015674 | B2 | 1000162189 | 05.08.2028 | 15000 | CCK-MP-EXCV-EX8107-SWGSYS-SWBOX-SGBRF | 7200 | 46126 | 15483
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Mono-Block C/Over - Repl | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 12 | 90015706 | B1 | 1000162255 | 07.08.2028 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HMBCO | 7200 | 46126 | 9438
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Final Drive LH | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 218 | 90015667 | B1 | 1000162183 | 11.08.2028 | 18000 | CCK-MP-EXCV-EX8107-UNDERC-TKFRL-FDRLH | 7200 | 46126 | 3487
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Final Drive RH Side | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 218 | 90015667 | B1 | 1000162185 | 11.08.2028 | 18000 | CCK-MP-EXCV-EX8107-UNDERC-TKFRR-FDRRH | 7200 | 46126 | 3188
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Valve-Travel Mtrs - Repl | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 72 | 90015707 | B1 | 1000162256 | 19.09.2028 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HVVTM | 7200 | 46126 | 8376
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Boom Cylinder - Replace | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 16 | 90015701 | B1 | 1000162250 | 28.09.2028 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HBCYL | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Stick Cylinder - Replace | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 44 | 90015702 | B1 | 1000162251 | 28.09.2028 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HSCYL | 7200 | 46126 | 571
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Swing RHF P1 | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 18 | 90015695 | B1 | 1000162235 | 28.09.2028 | 15000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-SWMF1 | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Swing LHF P2 | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 18 | 90015695 | B1 | 1000162236 | 28.09.2028 | 15000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-SWMF2 | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Swing RHR P1 | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 18 | 90015695 | B1 | 1000162233 | 28.09.2028 | 15000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-SWMR1 | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Swing LHR P2 | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 18 | 90015695 | B1 | 1000162234 | 28.09.2028 | 15000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-SWMR2 | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Gearbox Swing LHF | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 60 | 90015674 | B1 | 1000162187 | 28.09.2028 | 15000 | CCK-MP-EXCV-EX8107-SWGSYS-SWBOX-SGBLF | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Gearbox Swing RHR | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 60 | 90015674 | B3 | 1000162190 | 28.09.2028 | 15000 | CCK-MP-EXCV-EX8107-SWGSYS-SWBOX-SGBRR | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P2 Slew | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 2 | 90019421 | B1 | 1000197106 | 28.09.2028 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP2 | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P3 Slew Teeth | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 2 | 90019422 | B1 | 1000197107 | 28.09.2028 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP3 | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P1 Slew | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 2 | 90015715 | B1 | 1000197105 | 28.09.2028 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP1 | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Bucket Cylinder - Repl | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 54 | 90015703 | B1 | 1000162252 | 02.10.2028 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HBKCL | 7200 | 46126 | 571
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Sprocket LH | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 72 | 90015668 | B1 | 1000162274 | 17.11.2028 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRL-SPRKL | 500 | 2526 | 51
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Sprocket RH | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 72 | 90015668 | B1 | 1000162287 | 17.11.2028 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRR-SPRKR | 500 | 2526 | 51
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Valve pressure Limiting Y4 | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 4 | 90019283 | B1 | 1000196179 | 06.12.2028 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDVLV-VVPLV | 7200 | 46126 | 7049
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Grease System Audit | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 36 | 90019204 | B1 | 1000213679 | 11.12.2028 | 4000 | CCK-MP-EXCV-EX8107-GRSYST-GRINJ | 7200 | 41901 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Operators Seat | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 17 | 90015711 | B1 | 1000162261 | 18.12.2028 | 8000 | CCK-MP-EXCV-EX8107-STRUCT-CABIN-SEATO | 7200 | 46126 | 6810
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Batteries | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 5 | 90019334 | 1 | 1000195274 | 04.01.2029 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-CHARG-BATRR
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Grease Tank Level Valve | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 2 | 90015003 | B4 | 1000162271 | 04.01.2029 | 12 Monthly | CCK-MP-EXCV-EX8107-GRSYST-GRTNK
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Accumulator Track Hyd RH | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 2 | 90015699 | B1 | 1000162248 | 06.01.2029 | 32000 | CCK-MP-EXCV-EX8107-HYDSYS-HDACC-HACCR | 7200 | 46126 | 14442
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Work Pumps-Valves - Repl | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 48 | 90015704 | B1 | 1000162253 | 07.01.2029 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HWPVV | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Slew Bearing | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 264 | 90015665 | B1 | 1000162182 | 07.01.2029 | 32000 | CCK-MP-EXCV-EX8107-UNDERC-SLEWB | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Accumulator Servo Hyd | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 2 | 90019193 | B1 | 1000195416 | 07.01.2029 | 32000 | CCK-MP-EXCV-EX8107-HYDSYS-HDACC-HACCS | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Electrical Harness Swing | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 12 | 90019212 | B1 | 1000196182 | 07.01.2029 | 32000 | CCK-MP-EXCV-EX8107-ELCTLV-HARNS-SWGSY | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Accumulator Track Hyd LH | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 2 | 90015699 | B1 | 1000162247 | 11.01.2029 | 32000 | CCK-MP-EXCV-EX8107-HYDSYS-HDACC-HACCL | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Bucket LH Lift | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 46 | 90015688 | B1 | 1000162222 | 13.01.2029 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-BUCYL | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Power Pack Module 1 | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 190 | 90026630 | B1 | 1000267760 | 22.01.2029 | 16000 | CCK-MP-EXCV-EX8107-FRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Power Pack Module 2 | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 190 | 90026631 | B1 | 1000267768 | 22.01.2029 | 16000 | CCK-MP-EXCV-EX8107-RRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Bucket | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 78 | 90017654 | B1 | 1000162300 | 22.01.2029 | 16000 | CCK-MP-EXCV-EX8107-STRUCT-BUCKT | 7200 | 46126 | 35888
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Stick Assembly | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 96 | 90017651 | B2 | 1000162301 | 22.01.2029 | 32000 | CCK-MP-EXCV-EX8107-STRUCT-STICK | 7200 | 46126 | 571
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Valve Bank Module | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 144 | 90026634 | B1 | 1000268044 | 22.01.2029 | 32000 | CCK-MP-EXCV-EX8107-HYDSYS-HDVLV-MCVMD | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Power Pack Module 2 Valve Set | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 16 | 90015717 | B1 | 1000267762 | 14.03.2029 | 1000 | CCK-MP-EXCV-EX8107-FRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Power Pack Module 2 Valve set | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 16 | 90015717 | B1 | 1000267770 | 14.03.2029 | 1000 | CCK-MP-EXCV-EX8107-RRENGN | 7200 | 46126 | 14421
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Bucket RH Lift | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 48 | 90015689 | B1 | 1000162223 | 23.03.2029 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-BUCYR | 7200 | 46126 | 548
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Linkage Stick To Bucket LH | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 6 | 90019109 | B1 | 1000194345 | 29.04.2029 | 32000 | CCK-MP-EXCV-EX8107-STRUCT-STICK-LINKL | 7200 | 46126 | 12187
R996B | Onsite Shut | Excavators | Fortescue | EX8107 | EX8107 Repl Linkage Stick To Bucket RH | 2029-02-06 | 2029-02-18 | 282 hrs | FY29 | 6 | 90019111 | B1 | 1000194346 | 29.04.2029 | 32000 | CCK-MP-EXCV-EX8107-STRUCT-STICK-LINKR | 7200 | 46126 | 12187
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 - POWER PACK MODULES & MAJOR COMPONENTS | 2029-02-13 | 2029-02-25 | 282 hrs | FY29
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Track Idler LH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 38 | 90015669 | B1 | 1000162125 | 14.09.2028 | 1400 | CCK-MP-EXCV-EX8106-UNDERC-TKFRL-IDLLH | 500 | 2459 | 1281
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Sprocket LH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 72 | 90015668 | B1 | 1000162124 | 14.09.2028 | 1400 | CCK-MP-EXCV-EX8106-UNDERC-TKFRL-SPRKL | 500 | 2459 | 1450
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Track Assembly LH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 36 | 90015666 | B1 | 1000162123 | 14.09.2028 | 1400 | CCK-MP-EXCV-EX8106-UNDERC-TKFRL-TRKLH | 500 | 2459 | 1281
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Track Idler RH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 38 | 90015669 | B1 | 1000162138 | 14.09.2028 | 1400 | CCK-MP-EXCV-EX8106-UNDERC-TKFRR-IDLRH | 500 | 2459 | 1322
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Sprocket RH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 72 | 90015668 | B1 | 1000162137 | 14.09.2028 | 1400 | CCK-MP-EXCV-EX8106-UNDERC-TKFRR-SPRKR | 500 | 2459 | 217
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Track Assembly RH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 36 | 90015666 | B1 | 1000162136 | 14.09.2028 | 1400 | CCK-MP-EXCV-EX8106-UNDERC-TKFRR-TRKRH | 500 | 2459 | 1381
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Grease System Audit | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 36 | 90019204 | B1 | 1000213677 | 17.09.2028 | 4000 | CCK-MP-EXCV-EX8106-GRSYST-GRINJ | 7200 | 40923 | 7881
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Track Tension Tuning - Adjust | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 9 | 90020546 | B1 | 1000213054 | 16.10.2028 | 6 Monthly | CCK-MP-EXCV-EX8106-UNDERC
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Accumulator Track Hyd LH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 2 | 90015699 | B1 | 1000162098 | 27.10.2028 | 32000 | CCK-MP-EXCV-EX8106-HYDSYS-HDACC-HACCL | 7200 | 46150 | 15799
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Operators Seat | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 17 | 90015711 | B1 | 1000162112 | 27.10.2028 | 8000 | CCK-MP-EXCV-EX8106-STRUCT-CABIN-SEATS | 7200 | 46150 | 1397
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Slew Bearing | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 264 | 90015665 | B1 | 1000162033 | 27.10.2028 | 32000 | CCK-MP-EXCV-EX8106-UNDERC-SLEWB | 7200 | 46150 | 15792
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Accumulator Track Hyd RH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 2 | 90015699 | B1 | 1000162099 | 01.11.2028 | 32000 | CCK-MP-EXCV-EX8106-HYDSYS-HDACC-HACCR | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Swing Pmp Swg Mtr - Repl | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 144 | 90015705 | B1 | 1000162105 | 01.11.2028 | 8000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HSPSM | 7200 | 46150 | 1397
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Work Pumps-Valves - Repl | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 48 | 90015704 | B1 | 1000162104 | 01.11.2028 | 8000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HWPVV | 7200 | 46150 | 1373
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Replace Minestar Harness | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 43.5 | 90018769 | B2 | 1000281581 | 01.11.2028 | 4000 | CCK-MP-EXCV-EX8106-MANGMT-UMMMC | 7200 | 46150 | 15686
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Bucket | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 78 | 90017654 | B1 | 1000162150 | 01.11.2028 | 16000 | CCK-MP-EXCV-EX8106-STRUCT-BUCKT | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Linkage Stick To Bucket LH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 6 | 90019109 | B1 | 1000194343 | 01.11.2028 | 32000 | CCK-MP-EXCV-EX8106-STRUCT-STICK-LINKL | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Linkage Stick To Bucket RH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 6 | 90019111 | B1 | 1000194344 | 01.11.2028 | 32000 | CCK-MP-EXCV-EX8106-STRUCT-STICK-LINKR | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Valve pressure Limiting Y4 | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 4 | 90019283 | B1 | 1000196178 | 01.11.2028 | 8000 | CCK-MP-EXCV-EX8106-HYDSYS-HDVLV-VVPLV | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Accumulator Servo Hyd | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 2 | 90019193 | B1 | 1000195415 | 01.11.2028 | 32000 | CCK-MP-EXCV-EX8106-HYDSYS-HDACC-HACCS | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Electrical Harness Swing | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 12 | 90019212 | B1 | 1000196181 | 01.11.2028 | 32000 | CCK-MP-EXCV-EX8106-ELCTLV-HARNS-SWGSY | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Auto Lube Pump P1 Slew | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 2 | 90015715 | B1 | 1000162113 | 12.12.2028 | 10000 | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-ALBP1 | 7200 | 46150 | 2898
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Power Pack Module 1 | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 190 | 90026630 | B1 | 1000267713 | 18.01.2029 | 16000 | CCK-MP-EXCV-EX8106-FRENGN | 7200 | 46150 | 15799
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Power Pack Module 2 | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 190 | 90026631 | B1 | 1000267716 | 18.01.2029 | 16000 | CCK-MP-EXCV-EX8106-RRENGN | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Boom Assy Module Dressed | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 240 | 90026635 | B1 | 1000268040 | 18.01.2029 | 32000 | CCK-MP-EXCV-EX8106-STRUCT-BOOMS | 7200 | 46150 | 1397
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Stick Assembly | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 96 | 90017651 | B2 | 1000162151 | 18.01.2029 | 32000 | CCK-MP-EXCV-EX8106-STRUCT-STICK | 7200 | 46150 | 1373
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Valve Bank Module | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 144 | 90026634 | B1 | 1000267599 | 18.01.2029 | 32000 | CCK-MP-EXCV-EX8106-HYDSYS-HDVLV-MCVMD | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 12M Hydraulic Service & Repairs | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 30 | 90019301 | B1 | 1000196308 | 13.02.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-HYDSYS
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Air Con System | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 4 | 90019239 | B1 | 1000195764 | 23.02.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-ACONR | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Air Condtioner Compr Rear | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 4 | 90019237 | B1 | 1000195762 | 23.02.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-STRUCT-CABIN-ACCN2 | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Air Con System | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 5 | 90019238 | B1 | 1000195763 | 26.02.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-ACONF | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Air Condtioner Compr Front | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 5 | 90019236 | B1 | 1000195761 | 26.02.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-STRUCT-CABIN-ACCN1 | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel LHF | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 14 | 90015697 | B1 | 1000162092 | 01.03.2029 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMLF | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel LHR | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 14 | 90015697 | B1 | 1000162093 | 01.03.2029 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMLR | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel RHF | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 14 | 90015697 | B1 | 1000162094 | 01.03.2029 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMRF | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Rotary Connection | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 50 | 90015692 | B1 | 1000162079 | 01.03.2029 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-ROTRY | 7200 | 46150 | 13003
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Travel RHR | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 14 | 90015697 | B1 | 1000162095 | 02.03.2029 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-TRMRR | 7200 | 46150 | 21475
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Power Pack Module 1 Valve set | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 16 | 90015717 | B1 | 1000267715 | 10.03.2029 | 1000 | CCK-MP-EXCV-EX8106-FRENGN | 7200 | 46150 | 15799
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Power Pack Module 2 Valve set | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 16 | 90015717 | B1 | 1000267718 | 10.03.2029 | 1000 | CCK-MP-EXCV-EX8106-RRENGN | 7200 | 46150 | 15698
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Boom RH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 76 | 90015686 | B1 | 1000162070 | 18.03.2029 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-BMCYR | 7200 | 46150 | 13003
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Replace Grease Injectors | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 84 | 90019202 | B1 | 1000195347 | 08.04.2029 | 8000 | CCK-MP-EXCV-EX8106-GRSYST-GRINJ | 7200 | 40923 | 7881
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Start Batteries | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 9 | 90019192 | B1 | 1000195266 | 26.04.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-CHARG
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Maintenance Batteries | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 5 | 90019334 | 1 | 1000195273 | 26.04.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-CHARG
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Boom LH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 76 | 90015686 | B1 | 1000162069 | 26.04.2029 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-BMCYL | 7200 | 46150 | 12222
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Stick LH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 48 | 90015687 | B1 | 1000162071 | 26.04.2029 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-STCLL | 7200 | 46150 | 12222
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Stick RH | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 48 | 90015687 | B1 | 1000162072 | 26.04.2029 | 16000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-STCLR | 7200 | 46150 | 12222
R996B | Onsite Shut | Excavators | Fortescue | EX8106 | EX8106 Repl Grease Tank Level Valve | 2029-02-13 | 2029-02-25 | 282 hrs | FY29 | 2 | 90015003 | B4 | 1000162121 | 27.04.2029 | 12 Monthly | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-GRTNK
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 - ENGINE & TRACK FRAMES | 2029-02-14 | 2029-02-24 | 240 hrs | FY29
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Repl Track Frame LH | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 40 | 90002099 | B1 | 1000089451 | 06.11.2028 | 36000 | CCK-MP-DOZR-DZ014 -STRUCT-UNDER-TKFRL | 5000 | 64687 | 9227
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Repl Track Frame RH | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 40 | 90002102 | B1 | 1000089471 | 06.11.2028 | 36000 | CCK-MP-DOZR-DZ014 -STRUCT-UNDER-TKFRR | 5000 | 64687 | 9227
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Repl Cylinder Blade Lift RH | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 16 | 90000287 | B1 | 1000255551 | 12.11.2028 | 9000 | CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BLCYR | 5000 | 28779 | 28779
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Repl Steer Clutch & Brake Assm RH | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000020500 | 07.02.2029 | 18000 | CCK-MP-DOZR-DZ014 -BRKSTR-SCABR | 5000 | 64687 | 23459
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Repl Final Drive RH | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000020498 | 07.02.2029 | 18000 | CCK-MP-DOZR-DZ014 -FDRSYS-FDRRH | 5000 | 32278 | 32278
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Repl Final Drive LH | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000020497 | 15.03.2029 | 18000 | CCK-MP-DOZR-DZ014 -FDRSYS-FDRLH | 5000 | 30111 | 30111
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Repl Engine Cat C27 | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 114 | 90015849 | B1 | 1000159523 | 28.04.2029 | 18000 | CCK-MP-DOZR-DZ014 -ENGINE | 5000 | 64687 | 3801
D10T | Onsite Shut | Ancillary | Fortescue | DZ014 | DZ014 Overhaul Air Conditioner | 2029-02-14 | 2029-02-24 | 240 hrs | FY29 | 48 | 90017468 | B1 | 1000160691 | 28.04.2029 | 18000 | CCK-MP-DOZR-DZ014 -STRUCT-CABIN-AIRCN | 5000 | 64687 | 16308
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 - SLEW BEARING, BOOM, STICK & BOTH ENGINES | 2029-02-21 | 2029-03-13 | 480 hrs | FY29
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cyl Boom LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 138 | 90027497 | B1 | 1000296943 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BMCYL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cyl Boom RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 138 | 90027497 | B1 | 1000296944 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BMCYR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Oil Suction Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 48 | 90027568 | B1 | 1000296973 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-OILSC | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl PTO Cooling Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027569 | B1 | 1000296974 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-PTOCL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Fan Hyd Cool Front | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027504 | B1 | 1000296955 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-FMCHF | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Fan Hyd Cool Rear | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027504 | B1 | 1000296956 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-FMCHR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Control Valve Block LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 50 | 90027502 | B1 | 1000296984 | 23.01.2029 | 36000 | CCK-MP-EXCV-EX7125-HYDSYS-HDVLV-MCVVL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Control Valve Block RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 50 | 90027502 | B1 | 1000296985 | 23.01.2029 | 36000 | CCK-MP-EXCV-EX7125-HYDSYS-HDVLV-MCVVR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Fan Engine Cool LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027494 | B1 | 1000296937 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-HECPL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Fan Engine Cool RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027494 | B1 | 1000296938 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-HECPR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Drive Gearbox LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 116 | 90027489 | B1 | 1000296929 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-PPDRL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Drive Gearbox RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 116 | 90027489 | B1 | 1000296930 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-PPDRR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Engine Cat C32 LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 244 | 90027533 | B1 | 1000296914 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-LHENGN | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Radiator LH Engine Cooling | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027552 | B1 | 1000296918 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-LHENGN-COSYS-RADTR | 6500 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl LH Aftercooler | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 24 | 90023361 | B1 | 1000309282 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-LHENGN-INTEX-AFTER | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Engine Cat C32 RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 244 | 90027534 | B1 | 1000296919 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-RHENGN | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Radiator RH Engine Cooling | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027553 | B1 | 1000296923 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-RHENGN-COSYS-RADTR | 6500 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl RH Aftercooler | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 24 | 90023360 | B1 | 1000309283 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-RHENGN-INTEX-AFTER | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Boom Assy Dressed | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 324 | 90031798 | B1 | 1000314056 | 23.01.2029 | 36000 | CCK-MP-EXCV-EX7125-STRUCT-BOOMS | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Stick Assy Dressed | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 192 | 90031801 | B1 | 1000314252 | 23.01.2029 | 36000 | CCK-MP-EXCV-EX7125-STRUCT-STICK | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Track Tensioner RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 72 | 90027527 | B1 | 1000296991 | 23.01.2029 | 18000 | CCK-MP-EXCV-EX7125-STRUCT-TKFRR-TENSR | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Slew Gear Bearing | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 288 | 90027508 | B1 | 1000296963 | 23.01.2029 | 36000 | CCK-MP-EXCV-EX7125-STRUCT-UNDER-SLEWB | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic System Tune Up | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 24 | 90017865 | B1 | 1000296998 | 06.02.2029 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Fan Drive Eng Cooling Hose | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 36 | 90027564 | B1 | 1000296968 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-FDECH | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Fan Drive Hyd Cooling Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 36 | 90027565 | B1 | 1000296969 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-FDHCH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hydraulic Cooling Circ Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 36 | 90031704 | B1 | 1000296970 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-HCCHH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Rotor to Drive Motor Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 40 | 90027570 | B1 | 1000296975 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-RCDMH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Rotor & Logic Valve Hp Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 36 | 90027571 | B1 | 1000296976 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-RCLVH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Servo Hoses Cascade to Bulkhead | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 16 | 90027572 | B1 | 1000296977 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SHBLK | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Servo Hoses Cascade to Trvl Valve | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027575 | B1 | 1000296979 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SHTRV | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 2nd Speed Trvl Brake Release Hose | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 10 | 90027559 | B1 | 1000296965 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SSTBR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Swing Motor Case Drain Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90027577 | B1 | 1000296981 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-SWMCD | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Travel Motor Case Drain Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 10 | 90027578 | B1 | 1000296982 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-TMCDH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Track Tensioning Hoses | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 3 | 90027579 | B1 | 1000296983 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-TRTNH | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel LHF | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000296959 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMLF | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel RHF | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000296961 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMRF | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel RHR | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000296962 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMRR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Replenish LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 2 | 90027495 | B1 | 1000296941 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SRPPL | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Replenish RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 2 | 90027495 | B1 | 1000296942 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SRPPR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Servo LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 2 | 90027496 | B1 | 1000296939 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SVPPL | 6900 | 18844 | 18844
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Pump Servo RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 2 | 90027496 | B1 | 1000296940 | 06.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SVPPR | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Auto Lube Pump | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 6 | 90027592 | B1 | 1000296999 | 09.02.2029 | 6000 | CCK-MP-EXCV-EX7125-GRSYST-ALBPP | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Grease Control Valving | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 14 | 90027612 | B1 | 1000297000 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-GRSYST-ALCON
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Stick LH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 54 | 90027498 | B1 | 1000296945 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-STCLL | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Stick RH | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 54 | 90027498 | B1 | 1000296946 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-STCLR | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos1 | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000296931 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP1 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos2 | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000296932 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP2 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos3 | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000296933 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP3 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Main Hyd Pump Pos4 | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000296934 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-MNPP4 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Pos1 & Pos2 | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 42 | 90027492 | B1 | 1000296935 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SP1P2 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Pump Swing Pos3 & Pos4 | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 42 | 90027492 | B1 | 1000296936 | 09.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HYDPP-SP3P4 | 6900 | 18844 | 6591
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Hydraulic Oil Replacement | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 12 | 90016793 | B1 | 1000296988 | 10.02.2029 | 6000 | CCK-MP-EXCV-EX7125-HYDSYS | 6900 | 18844 | 6514
6040 | Onsite Shut | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Travel LHR | 2029-02-21 | 2029-03-13 | 480 hrs | FY29 | 14 | 90027506 | B1 | 1000296960 | 17.02.2029 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-TRMLR | 6900 | 18844 | 6369
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 - UNDERCARRIAGE & MAJOR COMPONENTS | 2029-02-22 | 2029-03-02 | 186 hrs | FY29
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS LiDAR | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 4 | 90029065 | B1 | 1000290890 | 01.12.2028 | 5000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR-LIDAR | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack LHR DE NCS | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 24 | 90020204 | B1 | 1000213908 | 13.01.2029 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYLR | 6800 | 34249 | 1270
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier NCS NDE | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000213655 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLF | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier NCS Middle | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000213656 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLM | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier NCS DE | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000213657 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLR | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos1 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213629 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF01 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos2 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213630 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF02 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos3 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213631 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF03 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos4 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213632 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF04 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos5 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213633 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF05 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos6 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213634 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF06 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos7 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213635 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF07 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos9 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213637 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF09 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos10 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213638 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF10 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos11 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213639 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF11 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos12 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213640 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF12 | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos13 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213641 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF13 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier CS NDE | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000213658 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRF | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier CS Middle | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000213661 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRM | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier CS DE | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000213662 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRR | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos1 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213642 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF01 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos2 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213643 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF02 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos3 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213644 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF03 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos4 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213645 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF04 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos5 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213646 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF05 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos6 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213647 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF06 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos7 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213648 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF07 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos8 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213649 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF08 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos9 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213650 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF09 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos10 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213651 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF10 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos11 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213652 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF11 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos12 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213653 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF12 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos13 | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000213654 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF13 | 6800 | 34249 | 22131
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Final Drive & Sprocket RH | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 26 | 90020182 | B1 | 1000213622 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-TRAVEL-FDRRH | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Track Assembly NCS | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 24 | 90020187 | B1 | 1000213627 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-TRAVEL-TRKLH | 6800 | 34249 | 22114
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Track Assembly CS | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 24 | 90020187 | B1 | 1000213628 | 17.01.2029 | 20000 | CCK-MP-DRLL-DR2112-TRAVEL-TRKRH | 6800 | 34249 | 22118
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Sprocket LH | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 24 | 90020186 | B1 | 1000302907 | 27.01.2029 | 10000 | CCK-MP-DRLL-DR2112-TRAVEL-SPRKL | 6800 | 34249 | 4197
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Mast Cables | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 64 | 90030334 | B1 | 1000302720 | 05.02.2029 | 2500 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Pump Water Inj | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 4 | 90031899 | B1 | 1000315424 | 27.02.2029 | 7500 | CCK-MP-DRLL-DR2112-DSTSUP-WTRPP | 6800 | 34249 | 11324
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl ADS Vibration Sensors | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 1 | 90029062 | B1 | 1000290886 | 27.02.2029 | 10000 | CCK-MP-DRLL-DR2112-ADSYST-ADSIS-DSVSN | 6800 | 34252 | 34252
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Hyd Pump Auxiliary | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 4 | 90020236 | B1 | 1000213927 | 12.03.2029 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-PPAUX | 6800 | 34249 | 11048
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Main Air Compressor LP | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 50 | 90020192 | B1 | 1000213906 | 16.03.2029 | 15000 | CCK-MP-DRLL-DR2112-AIRSYS-COMPR | 6800 | 34252 | 10999
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Overhaul 24M Air Conditioner | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 24 | 90028299 | B1 | 1000283156 | 16.03.2029 | 24 Monthly | CCK-MP-DRLL-DR2112-STRUCT-CABIN-AIRCN | 6800 | 34249 | 34249
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Washdown Pump | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 8 | 90030681 | B1 | 1000305723 | 17.03.2029 | 7500 | CCK-MP-DRLL-DR2112-DSTSUP-WSHPP | 6800 | 34249 | 9455
MD6310 | Onsite Shut | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack RHF NDE CS | 2029-02-22 | 2029-03-02 | 186 hrs | FY29 | 24 | 90030670 | B1 | 1000213910 | 19.03.2029 | 6000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYRF | 6800 | 34249 | 2739
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 - POWER PACK MIDLIFE & MINOR COMPONENTS | 2029-03-07 | 2029-03-19 | 282 hrs | FY29
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Gearbox Swing P2 | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 109 | 90030720 | B1 | 1000232023 | 11.11.2028 | 20000 | CCK-MP-EXCV-EX7117-SWGSYS-SWBOX-SGBPR | 7200 | 32281 | 3683
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Stick LH | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 54 | 90030724 | B1 | 1000232113 | 24.11.2028 | 16000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-STCLL | 7200 | 32281 | 1776
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Grease System Audit | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 36 | 90030748 | B1 | 1000232084 | 13.12.2028 | 5000 | CCK-MP-EXCV-EX7117-GRSYST-GRINJ | 7200 | 32281 | 7621
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Auto Lube Pump P3 | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 2 | 90035368 | B1 | 1000358742 | 20.12.2028 | 10000 | CCK-MP-EXCV-EX7117-GRSYST-AUTLU-ALBP3 | 7200 | 32281 | 2918
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Operators Seat | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 17 | 90030739 | B1 | 1000232069 | 20.12.2028 | 10000 | CCK-MP-EXCV-EX7117-STRUCT-CABIN-SEATO | 7200 | 32281 | 2918
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Auto Lube Pump P1 | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 2 | 90035369 | B1 | 1000232073 | 03.01.2029 | 10000 | CCK-MP-EXCV-EX7117-GRSYST-AUTLU-ALBPP | 7200 | 32281 | 2607
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Power Pack Module Midlife | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 343.5 | 90026485 | B1 | 1000279046 | 21.01.2029 | 10000 | CCK-MP-EXCV-EX7117-ENGINE | 7200 | 32281 | 12760
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Rotary Connection Hoses | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 96 | 90030432 | B1 | 1000303743 | 21.01.2029 | 10000 | CCK-MP-EXCV-EX7117-HYDSYS-HDHLF
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Hyd Vlve Bank Module Quarter Life | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 15 | 90027371 | B1 | 1000279082 | 21.01.2029 | 10000 | CCK-MP-EXCV-EX7117-HYDSYS-HDVLV-MCVLU | 7200 | 32281 | 2639
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Boom Module Quarter Life | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 48 | 90027377 | B1 | 1000279088 | 21.01.2029 | 10000 | CCK-MP-EXCV-EX7117-STRUCT-BOOMS | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Minestar Harness | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 43.5 | 90030746 | B1 | 1000281593 | 24.01.2029 | 5000 | CCK-MP-EXCV-EX7117-MANGMT-UMMMC | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Ovhl 24M Air Conditioner Sys2 Hyd | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 36 | 90035446 | B1 | 1000359784 | 14.02.2029 | 24 Monthly | CCK-MP-EXCV-EX7117-STRUCT-CABIN-AIRC2
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Repl Grease Tank Level Valve | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 2 | 90015003 | B2 | 1000232088 | 03.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7117-GRSYST-AUTLU-GRTNK | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 12M Hydraulic Service & Repairs | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 30 | 90014448 | B2 | 1000232086 | 05.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7117-HYDSYS | 7200 | 32281 | 32281
R9400 | Onsite Shut | Excavators | Fortescue | EX7117 | EX7117 Track Tension Tuning - Adjust | 2029-03-07 | 2029-03-19 | 282 hrs | FY29 | 9 | 90020545 | B1 | 1000232125 | 05.03.2029 | 6 Monthly | CCK-MP-EXCV-EX7117-UNDERC | 7200 | 32281 | 32281
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 - MAJOR COMPONENTS | 2029-03-14 | 2029-03-26 | 282 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Track Tension Tuning-Adjust | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 9 | 90029977 | B2 | 1000361406 | 11.03.2029 | 6 Monthly | CCK-MP-EXCV-EX7157-UNDERC | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl HV Motor Coupling | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 30 | 90030128 | B2 | 1000361437 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-ELCTHV-HVMOT-COUPL | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Gearbox Swing P1 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 107 | 90029900 | B2 | 1000361337 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-SWGSYS-SWBOX-SGBPF | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Gearbox Swing P2 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 107 | 90029900 | B2 | 1000361338 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-SWGSYS-SWBOX-SGBPR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Pump Drive Splitter Gearbox | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 240 | 90030087 | B2 | 1000361420 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-PMPDR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Pump Hyd Work Pos1 & Pos2 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 54 | 90030234 | B2 | 1000361421 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-WPPP1 | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Pump Hyd Work Pos3 & Pos4 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 54 | 90030286 | B2 | 1000361429 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-WPPP2 | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Pump Swing Combination | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 36 | 90030252 | B2 | 1000361422 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-SWPP1 | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Pump Fan Hyd Oil Cooler | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 24 | 90030278 | B2 | 1000361423 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-HECP1 | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Pump Servo Bearing Lube | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 4 | 90030280 | B2 | 1000361424 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-SVPP1 | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Lube Pump Splitter Gear Box | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 4 | 90030281 | B2 | 1000361425 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-PTOLU | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Pump Oil Replenishing | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 4 | 90030285 | B2 | 1000361426 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-RPPP1 | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Ladder Raise Cylinder | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 6 | 90030320 | B2 | 1000361432 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-LACYL | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Bucket LH Lift | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 52 | 90029964 | B2 | 1000361396 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-BUCYL | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Bucket RH Lift | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 52 | 90029967 | B2 | 1000361397 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-BUCYR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Rotary Connection | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 72 | 90029901 | B2 | 1000361339 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-ROTRY | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Vlve Bank Module Quarter Life | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 12 | 90029987 | B2 | 1000361413 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDVLV-MCVLU | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Valve Pressure Reducing Y3 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 6 | 90030294 | B2 | 1000361431 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDVLV-VVPRV | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Valve pressure Limiting Y4 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 6 | 90030321 | B2 | 1000361430 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDVLV-VVPLV | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Motor Swing Front | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 24 | 90029905 | B2 | 1000361341 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDMOT-SWMOF | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Motor Swing Rear | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 24 | 90029905 | B2 | 1000361340 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDMOT-SWMOR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Motor Travel LHF | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 8 | 90029906 | B2 | 1000361342 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDMOT-TRMLF | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Motor Travel LHR | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 8 | 90029906 | B2 | 1000361343 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDMOT-TRMLR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Motor Travel RHF | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 8 | 90029906 | B2 | 1000361344 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDMOT-TRMRF | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Motor Travel RHR | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 8 | 90029906 | B2 | 1000361345 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDMOT-TRMRR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Accumulator Ladder Hyd | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 4 | 90030685 | B2 | 1000361439 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDACC-HACCB | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Accumulator Track Hyd LH | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 3 | 90029907 | B2 | 1000361346 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDACC-HACCL | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Accumulator Track Hyd RH | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 3 | 90029907 | B2 | 1000361347 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-HYDSYS-HDACC-HACCR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Accumulator Servo Hyd | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 3 | 90030487 | B2 | 1000361414 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDACC-HACCS | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Track Tensioning Hoses | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 24 | 90030538 | B2 | 1000361438 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HHTTL | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Hyd Hose Work Pumps to Valves | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 10.5 | 90030287 | B2 | 1000361427 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HWPVV | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Hyd Hose Swing Pump Swing Motor | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 24 | 90030288 | B2 | 1000361428 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HSPSM | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Hyd Hose Rotary Con to Valve Bank | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 24 | 90029912 | B2 | 1000361351 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HRCVV | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Hoses Rotary Conn to Travel Motor | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 48 | 90029914 | B2 | 1000361352 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HRCTM | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Motor Side ACon Comp Drive | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 2 | 90030714 | B2 | 1000361440 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-STRUCT-AIRC1-ACONM | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Motor Rear ACon Comp Drive | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 2 | 90030714 | B2 | 1000361441 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-STRUCT-AIRC2-ACONM | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Operators Seat | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 17 | 90029915 | B2 | 1000361353 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-STRUCT-CABIN-SEATO | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Tank Module | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 84 | 90030313 | B2 | 1000361417 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-STRUCT-HDTNK | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Boom Module Quarter Life | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 48 | 90029992 | B2 | 1000361416 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-STRUCT-BOOMS | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Service Arm Locking Cyl | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 20 | 90029983 | B2 | 1000361411 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-STRUCT-SRVCT | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Service Module Hosing | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 24 | 90029982 | B2 | 1000361410 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-STRUCT-SRVCT | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Bucket Assembly | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 78 | 90029975 | B2 | 1000361401 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-STRUCT-BUCKT | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Auto Lube Pump P1 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 2 | 90030312 | B2 | 1000361357 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-GRSYST-AUTLU-ALBPP | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Auto Lube Pump P3 | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 2 | 90035351 | B2 | 1000361214 | 14.03.2029 | 10000 | CCK-MP-EXCV-EX7157-GRSYST-AUTLU-ALBP3 | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Grease Block & Injectors | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 84 | 90029933 | B2 | 1000361365 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-GRSYST-GRINJ | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Air Compressor Unit | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 15 | 90030086 | B2 | 1000361419 | 14.03.2029 | 20000 | CCK-MP-EXCV-EX7157-PNEUMC-COMPR | 6000 | 4778 | 4778
R9400E | Onsite Shut | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Clam Cyl | 2029-03-14 | 2029-03-26 | 282 hrs | FY29 | 20 | 90036569 | B2 | 1000366870 | 14.03.2029 | 5000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HCMCL | 6000 | 4778 | 4778
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 - ENGINE & MAJOR COMPONENTS | 2029-03-19 | 2029-03-29 | 240 hrs | FY29
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Operators Seat | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 8 | 90000318 | B1 | 1000108451 | 08.12.2028 | 6000 | CCK-MP-DOZR-DZ175 -STRUCT-CABIN-SEATS | 5000 | 71802 | 6554
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Final Drive RH | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091195 | 07.02.2029 | 18000 | CCK-MP-DOZR-DZ175 -FDRSYS-FDRRH | 5000 | 71802 | 5706
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Steer Clutch & Brake Assm LH | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091196 | 01.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -BRKSTR-SCABL | 5000 | 71827 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Steer Clutch & Brake Assm RH | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091197 | 01.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -BRKSTR-SCABR | 5000 | 71827 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Engine Cat C27 | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 114 | 90015849 | B1 | 1000160170 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -ENGINE | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Rad Engine Cooling SN 529 UP | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 48 | 90000307 | B2 | 1000091188 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -ENGINE-COSYS-RADTR | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Aftercooler Engine | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 8 | 90010841 | B1 | 1000108452 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -ENGINE-INTEX-AFTER | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Final Drive LH | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091194 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -FDRSYS-FDRLH | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Cyl Blade Lift RH | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 16 | 90000287 | B1 | 1000255639 | 03.04.2029 | 9000 | CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-BLCYR | 5000 | 71802 | 24
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Hyd Oil Cooler | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 10 | 90009664 | B2 | 1000091203 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -HYDSYS-HDOCO | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Ovhl Hydraulic & Fuel Tank | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 48 | 90010842 | B1 | 1000108454 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -HYDSYS-HDTNK | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Hyd Pump Implement | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 10 | 90000301 | B2 | 1000091198 | 03.04.2029 | 9000 | CCK-MP-DOZR-DZ175 -HYDSYS-HYDPP-HYIPP | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Overhaul Air Conditioner | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 48 | 90017468 | B1 | 1000196632 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -STRUCT-CABIN-AIRCN | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Equaliser Bar | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 110 | 90002097 | B1 | 1000108456 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -STRUCT-CHASS-EQUAL | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Minor Overhaul Track Frame LH | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 98 | 90002098 | B1 | 1000108457 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -STRUCT-UNDER-TKFRL | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Minor Overhaul Track Frame RH | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 98 | 90010766 | B1 | 1000108459 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -STRUCT-UNDER-TKFRR | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Drive Shaft | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 6 | 90033296 | B1 | 1000334111 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -TRNSYS | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Transmission | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 48 | 90000308 | B2 | 1000091191 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -TRNSYS-TRANS | 5000 | 71802 | 4957
D10T | Onsite Shut | Ancillary | Fortescue | DZ175 | DZ175 Repl Torque Converter | 2029-03-19 | 2029-03-29 | 240 hrs | FY29 | 60 | 90000309 | B2 | 1000091190 | 03.04.2029 | 18000 | CCK-MP-DOZR-DZ175 -TRNSYS-TRQUE | 5000 | 71802 | 4957
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 - ENGINE & MAJOR COMPONENTS | 2029-03-26 | 2029-04-04 | 222 hrs | FY29
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Transmission | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 146 | 90002631 | B2 | 1000028394 | 03.07.2028 | 14000 | CCK-MP-GRDR-GR012 -TRNSYS-TRANS | 5200 | 72353 | 181
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Service Minor Air Conditioner | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 12 | 90019542 | B1 | 1000290217 | 01.08.2028 | 3500 | CCK-MP-GRDR-GR012 -STRUCT-CABIN-AIRCN | 5200 | 72353 | 12098
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Aftercooler Engine | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 24 | 90002623 | B2 | 1000080584 | 14.09.2028 | 14000 | CCK-MP-GRDR-GR012 -ENGINE-INTEX-AFTER | 5200 | 72353 | 27067
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Brake Slack Adjuster LH | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 1 | 90002641 | B2 | 1000085610 | 14.09.2028 | 14000 | CCK-MP-GRDR-GR012 -BRKSYS-SLACK-SLACL | 5200 | 72353 | 176
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Brake Slack Adjuster Rear | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 1 | 90002641 | B2 | 1000085611 | 14.09.2028 | 14000 | CCK-MP-GRDR-GR012 -BRKSYS-SLACK-SLACR | 5200 | 72353 | 348
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Steering System Hoses | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 48 | 90009996 | B2 | 1000080072 | 14.09.2028 | 14000 | CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-STRNG | 5200 | 72353 | 348
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Hydraulic System Hoses | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 48 | 90009998 | B2 | 1000080074 | 14.09.2028 | 14000 | CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-HYDSH | 5200 | 72353 | 348
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Brake System Hoses | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 48 | 90009997 | B2 | 1000080073 | 14.09.2028 | 14000 | CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-BRKS | 5200 | 72353 | 348
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Power Train System Hoses | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 48 | 90009999 | B1 | 1000080075 | 14.09.2028 | 14000 | CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-PWTRN | 5200 | 72353 | 16770
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Blade Mounting Bracket LH | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 48 | 90002671 | B2 | 1000028440 | 16.09.2028 | 14000 | CCK-MP-GRDR-GR012 -STRUCT-CIRCL-BLMBL | 5200 | 72353 | 16770
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Blade Mounting Bracket RH | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 48 | 90002671 | B2 | 1000028441 | 16.09.2028 | 14000 | CCK-MP-GRDR-GR012 -STRUCT-CIRCL-BLMBR | 5200 | 72353 | 16770
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Torque Converter | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 98 | 90002630 | B2 | 1000028393 | 03.10.2028 | 14000 | CCK-MP-GRDR-GR012 -TRNSYS-TRQUE | 5200 | 72353 | 2512
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Hyd Pump Differential Lock | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 8 | 90002649 | B2 | 1000028415 | 22.01.2029 | 14000 | CCK-MP-GRDR-GR012 -HYDSYS-HYDPP-DIFFL | 5200 | 72353 | 348
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Engine Cat C18 | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 310 | 90015771 | B1 | 1000290213 | 04.04.2029 | 14000 | CCK-MP-GRDR-GR012 -ENGINE | 5200 | 72353 | 348
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Overhaul Air Condtioner System | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 48 | 90017475 | B1 | 1000290219 | 04.04.2029 | 14000 | CCK-MP-GRDR-GR012 -STRUCT-CABIN-AIRCN | 5200 | 72353 | 12098
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Overhaul Auto Lubrication System | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 2 | 90002660 | B2 | 1000028431 | 09.04.2029 | 14000 | CCK-MP-GRDR-GR012 -GRSYST-ALBPP | 5200 | 72353 | 27067
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Operators Seat | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 4 | 90002663 | B2 | 1000028433 | 20.04.2029 | 7000 | CCK-MP-GRDR-GR012 -STRUCT-CABIN-SEATS | 5200 | 72353 | 15438
24M | Onsite Shut | Ancillary | Fortescue | GR012 | GR012 Repl Axle Assembly Front | 2029-03-26 | 2029-04-04 | 222 hrs | FY29 | 98 | 90002666 | B1 | 1000180090 | 27.06.2029 | 14000 | CCK-MP-GRDR-GR012 -STRUCT-AXLES | 5200 | 72353 | 348
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 MAST MODULE & UNDERCARRIAGE | 2029-03-29 | 2029-04-06 | 186 hrs | FY29
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack RHF NDE CS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 24 | 90030670 | B1 | 1000278170 | 20.01.2029 | 6000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYRF | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Overhaul 24M Air Conditioner | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 24 | 90028299 | B1 | 1000283240 | 21.01.2029 | 24 Monthly | CCK-MP-DRLL-DR2128-STRUCT-CABIN-AIRCN | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack LHF NDE NCS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 24 | 90020196 | B1 | 1000278169 | 24.01.2029 | 6000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYLF | 6800 | 21646 | 2309
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS Vibration Sensors | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 1 | 90029062 | B1 | 1000291545 | 21.02.2029 | 10000 | CCK-MP-DRLL-DR2128-ADSYST-ADSIS-DSVSN | 6800 | 21646 | 11827
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Washdown Pump | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90030681 | B1 | 1000305733 | 21.02.2029 | 7500 | CCK-MP-DRLL-DR2128-DSTSUP-WSHPP | 6800 | 21646 | 3234
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Mast ADS Hardware | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 49 | 90029071 | B1 | 1000291497 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-ADSYST-ADSHW | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Deck ADS Elec Hardware | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 10 | 90029060 | B1 | 1000291498 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-ADSYST-ADSHW-ADSMF | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS IO Modules | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 6 | 90029069 | B1 | 1000291499 | 03.03.2029 | 40000 | CCK-MP-DRLL-DR2128-ADSYST-ADSHW-ARDIO | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS Ace Cabinet Components | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 101.5 | 90029055 | B1 | 1000291540 | 03.03.2029 | 40000 | CCK-MP-DRLL-DR2128-ADSYST-ADSHW-CLXEN | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Cabin ADS Components | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 58.5 | 90029058 | B1 | 1000291543 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-ADSYST-ADSHW-HMIJK | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS Field Instruments | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 7.5 | 90029064 | B1 | 1000291544 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-ADSYST-ADSIS | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS 3D Sensor Harness | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 2 | 90029068 | B1 | 1000291547 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPR | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl ADS Harnesses | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 43.5 | 90029073 | B1 | 1000291550 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-ADSYST-HARNC | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Hyd Motor Propel NCS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 12 | 90020190 | B1 | 1000278200 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-MPRPL | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Hyd Motor Propel CS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 12 | 90020190 | B1 | 1000278199 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-MPRPR | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Mast Module | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 384 | 90020218 | B1 | 1000302803 | 03.03.2029 | 40000 | CCK-MP-DRLL-DR2128-STRUCT-DMAST | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Carrier NCS NDE | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000278230 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-CARLF | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Carrier NCS Middle | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000278231 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-CARLM | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Carrier NCS DE | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000278232 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-CARLR | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Idler & Recoil Gp NCS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90030377 | B1 | 1000303489 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-IDLLH | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos1 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278234 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF01 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos2 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278244 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF02 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos3 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278246 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF03 | 6800 | 21646 | 1400
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos4 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278248 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF04 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos5 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278250 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF05 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos6 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278252 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF06 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos7 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278254 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF07 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos8 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278256 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF08 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos9 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278258 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF09 | 6800 | 21646 | 1400
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos10 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278236 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF10 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos11 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278238 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF11 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos12 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278240 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF12 | 6800 | 21646 | 1400
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load NCS Pos13 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278242 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF13 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Carrier CS NDE | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000278229 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-CARRF | 6800 | 21646 | 1309
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Carrier CS Middle | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000278228 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-CARRM | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Carrier CS DE | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000278227 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-CARRR | 6800 | 21646 | 1400
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Idler & Recoil Gp CS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90030377 | B1 | 1000303505 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-IDLRH | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos1 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278233 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF01 | 6800 | 21646 | 1400
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos2 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278243 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF02 | 6800 | 21646 | 1400
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos5 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278249 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF05 | 6800 | 21646 | 1400
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos6 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278251 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF06 | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos7 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278253 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF07 | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos8 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278255 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF08 | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos9 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278257 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF09 | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos10 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278235 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF10 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos11 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278237 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF11 | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos12 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278239 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF12 | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Final Drive & Sprocket LH | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 26 | 90020182 | B1 | 1000278188 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-TRAVEL-FDRLH | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Final Drive & Sprocket RH | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 26 | 90020182 | B1 | 1000278189 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-TRAVEL-FDRRH | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Track Assembly NCS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 24 | 90020187 | B1 | 1000278263 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-TRAVEL-TRKLH | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Track Assembly CS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 24 | 90020187 | B1 | 1000278262 | 03.03.2029 | 20000 | CCK-MP-DRLL-DR2128-TRAVEL-TRKRH | 6800 | 21646 | 1516
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Equaliser Bar TRL | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 32 | 90030390 | B1 | 1000303371 | 04.03.2029 | 40000 | CCK-MP-DRLL-DR2128-STRUCT-UNDER-EQUAL | 6800 | 21623 | 21623
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Fish Eye Camera | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 16 | 90029067 | B1 | 1000291548 | 16.03.2029 | 10000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPR-HTCAM | 6800 | 21646 | 21646
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Compressor Coupling | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 24 | 90030404 | B1 | 1000303538 | 17.03.2029 | 7500 | CCK-MP-DRLL-DR2128-AIRSYS-COMPR-COUPL | 6800 | 21646 | 3367
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Drive Shaft Pump Drive | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 12 | 90028862 | B1 | 1000287879 | 17.03.2029 | 5000 | CCK-MP-DRLL-DR2128-HYDSYS-PMPDG-DRSHT | 6800 | 21646 | 1486
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Pump Main Hyd CS | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 6 | 90020234 | B1 | 1000278211 | 30.03.2029 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-MNPP2 | 6800 | 21646 | 79
MD6310 | Onsite Shut | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos13 | 2029-03-29 | 2029-04-06 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000278241 | 13.05.2029 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF13 | 6800 | 21646 | 1486
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 - TRACK FRAMES & MAJOR COMPONENTS | 2029-04-25 | 2029-05-05 | 240 hrs | FY29
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Final Drive RH | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091171 | 02.08.2028 | 18000 | CCK-MP-DOZR-DZ174 -FDRSYS-FDRRH | 5000 | 65414 | 8319
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Minor Overhaul Track Frame LH | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 98 | 90002098 | B1 | 1000108445 | 02.08.2028 | 18000 | CCK-MP-DOZR-DZ174 -STRUCT-UNDER-TKFRL | 5000 | 65414 | 8319
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Minor Overhaul Track Frame RH | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 98 | 90010766 | B1 | 1000108447 | 02.08.2028 | 18000 | CCK-MP-DOZR-DZ174 -STRUCT-UNDER-TKFRR | 5000 | 65414 | 8319
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Cyl Blade Lift LH | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 16 | 90000287 | B1 | 1000255630 | 23.10.2028 | 9000 | CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-BLCYL | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Hyd Oil Cooler | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 10 | 90009664 | B2 | 1000091179 | 23.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -HYDSYS-HDOCO | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Steer Clutch & Brake Assm LH | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091172 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -BRKSTR-SCABL | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Steer Clutch & Brake Assm RH | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000091173 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -BRKSTR-SCABR | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Rad Engine Cooling SN 529 UP | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 48 | 90000307 | B2 | 1000091164 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -ENGINE-COSYS-RADTR | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Aftercooler Engine | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 8 | 90010841 | B1 | 1000108440 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -ENGINE-INTEX-AFTER | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Final Drive LH | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000091170 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -FDRSYS-FDRLH | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Ovhl Hydraulic & Fuel Tank | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 48 | 90010842 | B1 | 1000108442 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -HYDSYS-HDTNK | 5000 | 65414 | 47680
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Hyd Pump Cooling Fan | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 16 | 90004952 | B2 | 1000091177 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -HYDSYS-HYDPP-HYFPP | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Hyd Pump Implement | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 10 | 90000301 | B2 | 1000091174 | 24.10.2028 | 9000 | CCK-MP-DOZR-DZ174 -HYDSYS-HYDPP-HYIPP | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Operators Seat | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 8 | 90000318 | B1 | 1000108439 | 24.10.2028 | 6000 | CCK-MP-DOZR-DZ174 -STRUCT-CABIN-SEATS | 5000 | 65414 | 534
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Pump Trans & TCon Charge | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 10 | 90000302 | B2 | 1000091169 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -TRNSYS-TRPMP | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Torque Converter | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 60 | 90000309 | B2 | 1000091166 | 24.10.2028 | 18000 | CCK-MP-DOZR-DZ174 -TRNSYS-TRQUE | 5000 | 65414 | 7187
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Sepura SCC Microphone | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289549 | 30.03.2029 | 12 Monthly | CCK-MP-DOZR-DZ174 -COMMUN-RADIO | 5000 | 65414 | 65414
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Repl Equaliser Bar | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 110 | 90002097 | B1 | 1000108444 | 08.04.2029 | 18000 | CCK-MP-DOZR-DZ174 -STRUCT-CHASS-EQUAL | 5000 | 65414 | 4916
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Engine Midlife Complete | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 103 | 90015859 | B1 | 1000160169 | 20.06.2029 | 9000 | CCK-MP-DOZR-DZ174 -ENGINE | 5000 | 65414 | 12899
D10T | Onsite Shut | Ancillary | Fortescue | DZ174 | DZ174 Major Service Air Conditioner | 2029-04-25 | 2029-05-05 | 240 hrs | FY29 | 24 | 90017469 | B1 | 1000196629 | 20.06.2029 | 9000 | CCK-MP-DOZR-DZ174 -STRUCT-CABIN-AIRCN | 5000 | 65414 | 20488
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 - UNDERCARRIAGE & MAJOR COMPONENTS | 2029-04-25 | 2029-05-03 | 186 hrs | FY29
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Overhaul 24M Air Conditioner | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90028299 | B1 | 1000283158 | 16.03.2029 | 24 Monthly | CCK-MP-DRLL-DR2113-STRUCT-CABIN-AIRCN | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Mast Cables | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 64 | 90030334 | B1 | 1000302727 | 16.03.2029 | 2500 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Adjust 3750Hr Valve Set | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90020402 | B1 | 1000214045 | 17.03.2029 | 3750 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Engine Midlife Complete | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 54 | 90029233 | B1 | 1000293339 | 17.03.2029 | 7500 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl ADS LiDAR | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 4 | 90029065 | B1 | 1000290902 | 30.03.2029 | 5000 | CCK-MP-DRLL-DR2113-ADSYST-ADSPR-LIDAR | 6800 | 34008 | 10800
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Compressor Coupling | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90030404 | B1 | 1000303533 | 29.04.2029 | 7500 | CCK-MP-DRLL-DR2113-AIRSYS-COMPR-COUPL | 6800 | 34008 | 11590
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Seat Operators | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020200 | B2 | 1000214064 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-CABIN-SEATS | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Carrier NCS NDE | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000214031 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-CARLF | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Carrier NCS Middle | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000214032 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-CARLM | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Carrier NCS DE | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000214033 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-CARLR | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos1 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214005 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF01 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos2 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214006 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF02 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos3 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214007 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF03 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos4 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214008 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF04 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos5 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214009 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF05 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos6 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214010 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF06 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos7 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214011 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF07 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos8 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214012 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF08 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos9 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214013 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF09 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos10 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214014 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF10 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos11 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214015 | 04.08.2028 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF11 | 6800 | 33987 | 10801
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos12 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214016 | 04.08.2028 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF12 | 6800 | 33987 | 10801
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load NCS Pos13 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214017 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF13 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Carrier CS NDE | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000214034 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-CARRF | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Carrier CS Middle | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000214035 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-CARRM | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Carrier CS DE | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020189 | B1 | 1000214036 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-CARRR | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos1 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214018 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF01 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos2 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214019 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF02 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos3 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214020 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF03 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos4 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214021 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF04 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos5 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214022 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF05 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos6 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214023 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF06 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos7 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214024 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF07 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos8 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214025 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF08 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos9 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214026 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF09 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos10 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214027 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF10 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos11 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214028 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF11 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos12 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214029 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF12 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Roller Load CS Pos13 | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 8 | 90020188 | B1 | 1000214030 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF13 | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Final Drive & Sprocket LH | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 26 | 90020182 | B1 | 1000213977 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-TRAVEL-FDRLH | 6800 | 33987 | 2582
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Final Drive & Sprocket RH | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 26 | 90020182 | B1 | 1000213978 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-TRAVEL-FDRRH | 6800 | 33987 | 2582
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Track Assembly NCS | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90020187 | B1 | 1000214003 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-TRAVEL-TRKLH | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Track Assembly CS | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90020187 | B1 | 1000214004 | 29.04.2029 | 20000 | CCK-MP-DRLL-DR2113-TRAVEL-TRKRH | 6800 | 33987 | 20657
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack LHF NDE NCS | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90020196 | B1 | 1000214056 | 08.05.2029 | 6000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLF | 6800 | 33987 | 1040
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Pump Drive Gearbox | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 78 | 90020181 | B1 | 1000213976 | 13.05.2029 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-PMPDG | 6800 | 33987 | 2582
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack LHR DE NCS | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90020204 | B1 | 1000214057 | 23.05.2029 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLR | 6800 | 33987 | 22917
MD6310 | Onsite Shut | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack RHR DE CS | 2029-04-25 | 2029-05-03 | 186 hrs | FY29 | 24 | 90030672 | B1 | 1000214059 | 28.06.2029 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYRR | 6800 | 33987 | 9499
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 - MAST MODULE & MAJOR COMPONENTS | 2029-05-16 | 2029-05-24 | 186 hrs | FY29
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Power Pack Quarter Life | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 68 | 90029574 | B1 | 1000295337 | 04.02.2029 | 5000 | CCK-MP-DRLL-DR055 -ENGINE | 6800 | 64593 | 10155
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl ADS GPS Components | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 3.5 | 90029191 | B1 | 1000294218 | 09.03.2029 | 40000 | CCK-MP-DRLL-DR055 -ADSYST-ADSPO | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Cabin ADS Components | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 31.5 | 90029189 | B1 | 1000294217 | 09.03.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-HMIJK | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl ADS Ace Cabinet Components | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 44.5 | 90029187 | B1 | 1000294216 | 09.03.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-CLXEN | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl ADS Harnesses | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 131.5 | 90029210 | B1 | 1000294222 | 09.03.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-HARNC | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl ADS IO Modules | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 4 | 90029208 | B1 | 1000294215 | 09.03.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-ARDIO | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Deck ADS Elec Hardware | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 9.5 | 90029190 | B1 | 1000294214 | 09.03.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-ADSMF | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl ADS 3D sensor | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 1 | 90029207 | B1 | 1000294219 | 09.03.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSPR | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Control Harnesses Chassis | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 39 | 90029952 | B1 | 1000303818 | 09.03.2029 | 20000 | CCK-MP-DRLL-DR055 -ELCTLV-HARNS-HARCO | 6800 | 64593 | 64593
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl ADS PTZ Camera & LIDAR | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 10 | 90029206 | B1 | 1000294220 | 28.03.2029 | 10000 | CCK-MP-DRLL-DR055 -ADSYST-ADSPR-HTCAM | 6800 | 64593 | 35395
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Pump Water Injection | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 2 | 90011733 | B1 | 1000102876 | 18.04.2029 | 5000 | CCK-MP-DRLL-DR055 -DSTSUP-WTRPP | 6800 | 64569 | 14276
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Raise NCS | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 8 | 90011666 | B1 | 1000233111 | 04.05.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYL | 6800 | 64569 | 13121
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Raise CS | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 8 | 90011667 | B1 | 1000233110 | 04.05.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYR | 6800 | 64569 | 3533
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Valve Diverter NCS | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 9 | 90011692 | B1 | 1000102837 | 04.05.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDVL | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Valve Diverter CS | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 9 | 90011693 | B1 | 1000102838 | 04.05.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDVR | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Valve Drill & Propel Control | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 6 | 90011694 | B1 | 1000102839 | 04.05.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDPC | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Vehicle Loading Crane | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 12 | 90032932 | B1 | 1000331360 | 04.05.2029 | 40000 | CCK-MP-DRLL-DR055 -STRUCT-CRANE | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Track Frame Module-NCS | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 72 | 90022185 | B1 | 1000205855 | 04.05.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TKFRL | 6800 | 64569 | 1827
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Track Frame Module CS | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 72 | 90022183 | B1 | 1000206293 | 04.05.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TKFRR | 6800 | 64569 | 1827
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Mast Module | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 156 | 90022223 | B1 | 1000232407 | 04.05.2029 | 40000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Yoke Oscillation | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 24 | 90011726 | B1 | 1000102869 | 04.05.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-UNDER-YKOSC | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Tower A Frame | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 96 | 90020030 | B1 | 1000233105 | 04.05.2029 | 40000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-AFRME | 6800 | 64569 | 23653
PV271 | Onsite Shut | Drills | Fortescue | DR055 | DR055 Repl Valve Dual Counter Balance | 2029-05-16 | 2029-05-24 | 186 hrs | FY29 | 2 | 90011690 | B1 | 1000102835 | 06.06.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDCB | 6800 | 64569 | 13103
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 - ENGINE & MAJOR COMPONENTS | 2029-05-28 | 2029-06-07 | 240 hrs | FY29
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Actuator Brake HaulX Shield | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 50 | 90033520 | B1 | 1000337790 | 25.03.2029 | 30000 | CCK-MP-DOZR-WD006 -MANGMT-CASYS-ACTBK
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Pump Brake | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 4 | 90002957 | B3 | 1000033583 | 26.03.2029 | 15000 | CCK-MP-DOZR-WD006 -BRKSYS-BRPMP | 6300 | 69386 | 13427
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Pump Str Pilot & Str Cooling | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 4 | 90002959 | B3 | 1000033585 | 26.03.2029 | 15000 | CCK-MP-DOZR-WD006 -STRSYS-STPMP-STP02 | 6300 | 69386 | 13427
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Pump Implement | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 12 | 90002962 | B3 | 1000033589 | 26.03.2029 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HYDPP-HYP01 | 6300 | 69386 | 13427
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Pump Cooling Fan | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 8 | 90002964 | B3 | 1000033591 | 26.03.2029 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HYDPP-HYP03 | 6300 | 69386 | 13427
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Motor Fan | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 8 | 90002969 | B3 | 1000033596 | 26.03.2029 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HYDMT-HYM01 | 6300 | 69386 | 13435
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Operators Seat | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 4 | 90002975 | B2 | 1000033602 | 20.04.2029 | 7000 | CCK-MP-DOZR-WD006 -STRUCT-CABIN-SEATS | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Final Drive Position 1 | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 58 | 90002954 | B3 | 1000033577 | 11.05.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR01 | 6300 | 69386 | 4749
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Engine Cat C32 | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 404 | 90015797 | B1 | 1000286586 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -ENGINE | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Radiator Engine Cooling | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 72 | 90002931 | B3 | 1000033563 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -ENGINE-COSYS-RADTR | 6300 | 69386 | 24173
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Aftercooler Engine | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 12 | 90010216 | B3 | 1000082594 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -ENGINE-INTEX-AFTER | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Shaft TConverter to Trans | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 4 | 90002947 | B3 | 1000268422 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT01 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Shaft Trans to Rear Diff | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 8 | 90002948 | B3 | 1000268424 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT02 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Shaft Trans to Cntr Bearing | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 8 | 90002949 | B3 | 1000268426 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT03 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Shaft Centre Brg to Fr Diff | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 8 | 90002950 | B3 | 1000268428 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT04 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Front Differential | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 132 | 90002951 | B3 | 1000033574 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-FRDIF | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Final Drive Position 2 | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 58 | 90002954 | B3 | 1000033578 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR02 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Final Drive Position 3 | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 58 | 90002954 | B3 | 1000033579 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR03 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Final Drive Position 4 | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 58 | 90002954 | B3 | 1000033580 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR04 | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Oil Cooler Front Axle Lube | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 6 | 90010219 | B3 | 1000082622 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -FDRSYS-AXLEC-OILCF | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Brake Accumulator Front | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 4 | 90002955 | B3 | 1000033581 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -BRKSYS-BACCM-BACCF | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Brake Accumulator Rear | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 4 | 90002955 | B3 | 1000033582 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -BRKSYS-BACCM-BACCR | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Cyl Steering RH | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 22 | 90002961 | B3 | 1000033588 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -STRSYS-STRCY-STCYR | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Cylinder Blade Lift LH | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 12 | 90002965 | B1 | 1000033592 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BLCYL | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Cylinder Blade Tilt LH | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 14 | 90002967 | B1 | 1000033594 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BTCYL | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Cylinder Blade Tilt RH | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 14 | 90002968 | B1 | 1000033595 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BTCYR | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Hyd & Steering Oil Cooler | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 24 | 90010218 | B3 | 1000082598 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -HYDSYS-HDOCO | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Refurbish Operators Cabin | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 32 | 90002972 | B3 | 1000033599 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -STRUCT-CABIN | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Overhaul Airconditioner | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 48 | 90013087 | B1 | 1000286592 | 17.06.2029 | 11000 | CCK-MP-DOZR-WD006 -STRUCT-CABIN-AIRCN | 6300 | 69386 | 4123
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Hoses Powertrain System | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 48 | 90013049 | B3 | 1000109643 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD006 -TRNSYS-TRHLF
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Replace Hyd Pilot System Hoses | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 24 | 90013052 | B3 | 1000231934 | 25.06.2029 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HDHLF-HDHPS | 6300 | 69386 | 69386
854K | Onsite Shut | Ancillary | Fortescue | WD006 | WD006 Repl Hoses Main Hyd-Fan System | 2029-05-28 | 2029-06-07 | 240 hrs | FY29 | 48 | 90013053 | B3 | 1000231935 | 26.06.2029 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HDHLF-HDHMH | 6300 | 69386 | 69386
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 - SLEW BEARING, BOOM, STICK & LH ENGINE | 2029-05-30 | 2029-06-19 | 480 hrs | FY29
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Engine Midlife Complete RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 66 | 90027554 | B1 | 1000297433 | 05.05.2029 | 9000 | CCK-MP-EXCV-EX7123-RHENGN | 6900 | 15607 | 7903
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Bucket LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 32 | 90027499 | B1 | 1000297498 | 08.05.2029 | 10000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BUCYL | 6900 | 15607 | 10846
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Final Drive LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 144 | 90027485 | B1 | 1000297435 | 08.05.2029 | 24000 | CCK-MP-EXCV-EX7123-TRAVEL-FDRLH | 6900 | 15607 | 4847
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos2 | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000297483 | 29.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP2 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Auto Lube Pump | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 6 | 90027592 | B1 | 1000297550 | 30.05.2029 | 6000 | CCK-MP-EXCV-EX7123-GRSYST-ALBPP | 6900 | 15681 | 503
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Grease Control Valving | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 14 | 90027612 | B1 | 1000297551 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-GRSYST-ALCON
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Hydraulic Oil Replacement | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90016793 | B1 | 1000297539 | 30.05.2029 | 6000 | CCK-MP-EXCV-EX7123-HYDSYS | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Stick LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 54 | 90027498 | B1 | 1000297496 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-STCLL | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Boom Arch Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 24 | 90027558 | B1 | 1000297517 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-BMARH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Fan Drive Eng Cooling Hose | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 36 | 90027564 | B1 | 1000297519 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-FDECH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Fan Drive Hyd Cooling Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 36 | 90027565 | B1 | 1000297520 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-FDHCH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hydraulic Cooling Circ Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 36 | 90031704 | B1 | 1000297521 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-HCCHH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Pump to Rotor Hose | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 48 | 90027567 | B1 | 1000297523 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-MPRCH | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Rotor to Drive Motor Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 40 | 90027570 | B1 | 1000297526 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-RCDMH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Rotor & Logic Valve Hp Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 36 | 90027571 | B1 | 1000297527 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-RCLVH | 6900 | 15607 | 4281
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Servo Hoses Cascade to Bulkhead | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 16 | 90027572 | B1 | 1000297528 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SHBLK | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Servo Hose Bulkhead to MCV | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 16 | 90027574 | B1 | 1000297529 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SHMCV | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Servo Hoses Cascade to Trvl Valve | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027575 | B1 | 1000297530 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SHTRV | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 2nd Speed Trvl Brake Release Hose | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 10 | 90027559 | B1 | 1000297516 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SSTBR | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Swing Motor Case Drain Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027577 | B1 | 1000297532 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SWMCD | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Travel Motor Case Drain Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 10 | 90027578 | B1 | 1000297533 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-TMCDH | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Track Tensioning Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 3 | 90027579 | B1 | 1000297534 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-TRTNH | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos1 | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000297482 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP1 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos3 | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000297484 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP3 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Hyd Pump Pos4 | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 64 | 90027490 | B1 | 1000297485 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-MNPP4 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Pos1 & Pos2 | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 42 | 90027492 | B1 | 1000297486 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SP1P2 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Pos3 & Pos4 | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 42 | 90027492 | B1 | 1000297487 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SP3P4 | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Replenish LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 2 | 90027495 | B1 | 1000297492 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SRPPL | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Swing Replenish RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 2 | 90027495 | B1 | 1000297493 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SRPPR | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Pump Servo LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 2 | 90027496 | B1 | 1000297490 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SVPPL | 6900 | 15607 | 181
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Pump Servo RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 2 | 90027496 | B1 | 1000297491 | 30.05.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-SVPPR | 6900 | 15607 | 181
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Annual Air Con Service LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 13 | 90027615 | B1 | 1000297574 | 28.06.2029 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN-AIRCL
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Bucket RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 32 | 90027499 | B1 | 1000297499 | 09.07.2029 | 10000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BUCYR | 6900 | 15607 | 9683
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cyl Boom LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 138 | 90027497 | B1 | 1000297494 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BMCYL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cyl Boom RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 138 | 90027497 | B1 | 1000297495 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BMCYR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Boom Stick Bucket Cyl Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 136 | 90027560 | B1 | 1000297518 | 13.07.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-HBSBC | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Boom & MCV Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 136 | 90032593 | B1 | 1000325061 | 13.07.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-HBSBC | 6900 | 15607 | 4439
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Oil Suction Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 48 | 90027568 | B1 | 1000297524 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-OILSC | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl PTO Cooling Hoses | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027569 | B1 | 1000297525 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-PTOCL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Hyd Cool Front | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027504 | B1 | 1000297506 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMCHF | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Hyd Cool Rear | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027504 | B1 | 1000297507 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMCHR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Engine Cool LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 18 | 90027505 | B1 | 1000297508 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMECL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Fan Engine Cool RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 18 | 90027505 | B1 | 1000297509 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-FMECR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Control Valve Block LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 50 | 90027502 | B1 | 1000297535 | 13.07.2029 | 36000 | CCK-MP-EXCV-EX7123-HYDSYS-HDVLV-MCVVL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Main Control Valve Block RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 50 | 90027502 | B1 | 1000297536 | 13.07.2029 | 36000 | CCK-MP-EXCV-EX7123-HYDSYS-HDVLV-MCVVR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Fan Engine Cool LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027494 | B1 | 1000297488 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-HECPL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Fan Engine Cool RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027494 | B1 | 1000297489 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-HYDPP-HECPR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Pump Drive Gearbox LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 116 | 90027489 | B1 | 1000297480 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-PPDRL | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Pump Drive Gearbox RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 116 | 90027489 | B1 | 1000297481 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-HYDSYS-PPDRR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Engine Cat C32 | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 244 | 90027533 | B1 | 1000297425 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-LHENGN | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Radiator LH Engine Cooling | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027552 | B1 | 1000297429 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-LHENGN-COSYS-RADTR | 7100 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl LH Aftercooler | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 24 | 90023361 | B1 | 1000309290 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-LHENGN-INTEX-AFTER | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Radiator RH Engine Cooling | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 12 | 90027553 | B1 | 1000297434 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-RHENGN-COSYS-RADTR | 7100 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl RH Aftercooler | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 24 | 90023360 | B1 | 1000309291 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-RHENGN-INTEX-AFTER | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Boom Assy Dressed | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 324 | 90031798 | B1 | 1000314055 | 13.07.2029 | 36000 | CCK-MP-EXCV-EX7123-STRUCT-BOOMS | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Stick Assy Dressed | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 192 | 90031801 | B1 | 1000314251 | 13.07.2029 | 36000 | CCK-MP-EXCV-EX7123-STRUCT-STICK | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Track Tensioner LH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 72 | 90027527 | B1 | 1000297541 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-STRUCT-TKFRL-TENSR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Track Tensioner RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 72 | 90027527 | B1 | 1000297542 | 13.07.2029 | 18000 | CCK-MP-EXCV-EX7123-STRUCT-TKFRR-TENSR | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Slew Gear Bearing | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 288 | 90027508 | B1 | 1000297514 | 13.07.2029 | 36000 | CCK-MP-EXCV-EX7123-STRUCT-UNDER-SLEWB | 6900 | 15607 | 15607
6040 | Onsite Shut | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Stick RH | 2029-05-30 | 2029-06-19 | 480 hrs | FY29 | 54 | 90027498 | B1 | 1000297497 | 15.07.2029 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-STCLR | 6900 | 15607 | 3559
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 - MAJOR COMPONENTS | 2029-06-04 | 2029-06-16 | 282 hrs | FY29
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl 24V Batteries | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 9 | 90029978 | B1 | 1000378426 | 13.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7153-ELCTLV-CHARG-BATST | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 12M Hydraulic Service & Repairs | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 30 | 90029940 | B1 | 1000378388 | 13.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7153-HYDSYS
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 12M Service Air Con Side Unit | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 13 | 90030498 | B1 | 1000378421 | 13.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7153-STRUCT-AIRC1 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 12M Service Air Con Rear Unit | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 13 | 90030536 | B1 | 1000378423 | 13.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7153-STRUCT-AIRC2 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Grease Tank Level Valve | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 2 | 90029942 | B1 | 1000378390 | 13.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7153-GRSYST
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl HV Motor Coupling | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 30 | 90030128 | B1 | 1000378457 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-ELCTHV-HVMOT-COUPL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Gearbox Swing P1 | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000378278 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-SWGSYS-SWBOX-SGBPF | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Gearbox Swing P2 | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 107 | 90029900 | B1 | 1000378279 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-SWGSYS-SWBOX-SGBPR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Pump Drive/Splitter Gearbox | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 240 | 90030087 | B1 | 1000378440 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-PMPDR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Pump Hyd Work Pos1 & Pos2 | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 54 | 90030234 | B1 | 1000378441 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-WPPP1 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Pump Hyd Work Pos3 & Pos4 | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 54 | 90030286 | B1 | 1000378449 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-WPPP2 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Pump Swing Combination | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 36 | 90030252 | B1 | 1000378442 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-SWPP1 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Pump Fan Hyd Oil Cooler | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 24 | 90030278 | B1 | 1000378443 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-HECP1 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Pump Servo Bearing Lube | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 4 | 90030280 | B1 | 1000378444 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-SVPP1 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Lube Pump Splitter Gear Box | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 4 | 90030281 | B1 | 1000378445 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-PTOLU | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Pump Oil Replenishing | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 4 | 90030285 | B1 | 1000378446 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HYDPP-RPPP1 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Ladder Raise Cylinder | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 6 | 90030320 | B1 | 1000378452 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-LACYL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Bucket LH Lift | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 52 | 90029964 | B1 | 1000378417 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-BUCYL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Bucket RH Lift | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 52 | 90029967 | B1 | 1000378418 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-BUCYR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Rotary Connection | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 72 | 90029901 | B1 | 1000378360 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-ROTRY | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Vlve Bank Module Quarter Life | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 12 | 90029987 | B1 | 1000378432 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDVLV-MCVLU | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Valve Pressure Reducing Y3 | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 6 | 90030294 | B1 | 1000378451 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDVLV-VVPRV | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Valve pressure Limiting Y4 | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 6 | 90030321 | B1 | 1000378450 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDVLV-VVPLV | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Motor Swing Front | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000378362 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDMOT-SWMOF | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Motor Swing Rear | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 24 | 90029905 | B1 | 1000378361 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDMOT-SWMOR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Motor Travel LHF | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000378363 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDMOT-TRMLF | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Motor Travel LHR | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000378364 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDMOT-TRMLR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Motor Travel RHF | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000378365 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDMOT-TRMRF | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Motor Travel RHR | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 8 | 90029906 | B1 | 1000378366 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDMOT-TRMRR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Accumulator Track Hyd LH | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000378367 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDACC-HACCL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Accumulator Track Hyd RH | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 3 | 90029907 | B1 | 1000378368 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-HYDSYS-HDACC-HACCR | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Accumulator Servo Hyd | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 3 | 90030487 | B1 | 1000378433 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDACC-HACCS | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Accumulator Ladder Hyd | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 4 | 90030685 | B1 | 1000378459 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDACC-HACCB | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Track Tensioning Hoses | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 24 | 90030538 | B1 | 1000378458 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HHTTL | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hyd Hose Work Pumps to Valves | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 10.5 | 90030287 | B1 | 1000378447 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HWPVV | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hyd Hose Swing Pump Swing Motor | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 24 | 90030288 | B1 | 1000378448 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HSPSM | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hyd Hose Rotary Con to Valve Bank | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 24 | 90029912 | B1 | 1000378372 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HRCVV | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Hoses Rotary Conn to Travel Motor | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 48 | 90029914 | B1 | 1000378373 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HRCTM | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Operators Seat | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 16 | 90029915 | B1 | 1000378374 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-STRUCT-CABIN-SEATO | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Motor A/C Comp Drive | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000378460 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-STRUCT-AIRC1-ACONM | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Motor A/C Comp Drive | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 2 | 90030714 | B1 | 1000378461 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-STRUCT-AIRC2-ACONM | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Tank Module | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 84 | 90030313 | B1 | 1000378436 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-STRUCT-HDTNK | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Boom Module Quarter Life | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 48 | 90029992 | B1 | 1000378435 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-STRUCT-BOOMS | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Service Arm Locking Cyl | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 20 | 90029983 | B1 | 1000378430 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-STRUCT-SRVCT | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Service Module Hosing | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 24 | 90029982 | B1 | 1000378429 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-STRUCT-SRVCT | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Bucket Assembly | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 78 | 90029975 | B1 | 1000378420 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-STRUCT-BUCKT | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl P1 Auto Lube Pump | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 2 | 90030312 | B1 | 1000378378 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-GRSYST-AUTLU-ALBPP | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl P3 Auto Lube Pump | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 2 | 90035351 | B1 | 1000378465 | 24.06.2029 | 10000 | CCK-MP-EXCV-EX7153-GRSYST-AUTLU-ALBP3 | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Grease Block & Injectors | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 84 | 90029933 | B1 | 1000378386 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-GRSYST-GRINJ | 6200 | 2136 | 2136
R9400E | Onsite Shut | Excavators | Fortescue | EX7153 | EX7153 Repl Air Compressor Unit | 2029-06-04 | 2029-06-16 | 282 hrs | FY29 | 15 | 90030086 | B1 | 1000378439 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7153-PNEUMC-COMPR | 6200 | 2136 | 2136
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 - ENGINE & MAJOR COMPONENTS | 2029-06-06 | 2029-06-16 | 240 hrs | FY29
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Final Drive LH | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000088969 | 14.02.2029 | 18000 | CCK-MP-DOZR-DZ178 -FDRSYS-FDRLH | 5000 | 54741 | 5886
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Minor Overhaul Track Frame LH | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 98 | 90002098 | B1 | 1000108493 | 29.03.2029 | 18000 | CCK-MP-DOZR-DZ178 -STRUCT-UNDER-TKFRL | 5000 | 54741 | 4806
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Minor Overhaul Track Frame RH | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 98 | 90010766 | B1 | 1000108495 | 29.03.2029 | 18000 | CCK-MP-DOZR-DZ178 -STRUCT-UNDER-TKFRR | 5000 | 54741 | 4806
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Engine Cat C27 | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 114 | 90015849 | B1 | 1000160206 | 11.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -ENGINE | 5000 | 54752 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Rad Engine Cooling SN 529 UP | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 48 | 90000307 | B2 | 1000088964 | 11.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -ENGINE-COSYS-RADTR | 5000 | 54752 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Aftercooler Engine | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 8 | 90010841 | B1 | 1000108488 | 11.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -ENGINE-INTEX-AFTER | 5000 | 54752 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Overhaul Air Conditioner | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 48 | 90017468 | B1 | 1000196639 | 11.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -STRUCT-CABIN-AIRCN | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Drive Shaft | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 6 | 90033296 | B1 | 1000334115 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -TRNSYS | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Torque Converter | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 60 | 90000309 | B2 | 1000088966 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -TRNSYS-TRQUE | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Transmission | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 48 | 90000308 | B2 | 1000088967 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -TRNSYS-TRANS | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Pump Trans & TCon Charge | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 10 | 90000302 | B2 | 1000088968 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -TRNSYS-TRPMP | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Final Drive RH | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 28 | 90000312 | B2 | 1000088970 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -FDRSYS-FDRRH | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Steer Clutch & Brake Assm LH | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000088971 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -BRKSTR-SCABL | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Steer Clutch & Brake Assm RH | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 28 | 90000313 | B2 | 1000088972 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -BRKSTR-SCABR | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Hyd Pump Cooling Fan | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 16 | 90004952 | B2 | 1000088975 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -HYDSYS-HYDPP-HYFPP | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Hyd Pump Implement | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 10 | 90000301 | B2 | 1000088973 | 12.06.2029 | 9000 | CCK-MP-DOZR-DZ178 -HYDSYS-HYDPP-HYIPP | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Cyl Blade Lift LH | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 16 | 90000287 | B1 | 1000255654 | 12.06.2029 | 9000 | CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-BLCYL | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Ovhl Hydraulic & Fuel Tank | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 48 | 90010842 | B1 | 1000108490 | 12.06.2029 | 18000 | CCK-MP-DOZR-DZ178 -HYDSYS-HDTNK | 5000 | 54741 | 3721
D10T | Onsite Shut | Ancillary | Fortescue | DZ178 | DZ178 Repl Operators Seat | 2029-06-06 | 2029-06-16 | 240 hrs | FY29 | 8 | 90000318 | B1 | 1000108487 | 12.06.2029 | 6000 | CCK-MP-DOZR-DZ178 -STRUCT-CABIN-SEATS | 5000 | 54741 | 3721
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 - POWER PACK MODULE & TRACK ASSEMBLIES | 2029-06-06 | 2029-06-18 | 282 hrs | FY29
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Ovhl 24M Air Conditioner Sys2 Hyd | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 37 | 90035267 | B1 | 1000359792 | 14.02.2029 | 24 Monthly | CCK-MP-EXCV-EX7136-STRUCT-CABIN-AIRC2
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Bucket RH Lift | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 54 | 90030726 | B1 | 1000306991 | 05.03.2029 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-BUCYR | 7200 | 19274 | 11264
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Track Tension Tuning-Adjust | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 9 | 90020545 | B1 | 1000306996 | 01.05.2029 | 6 Monthly | CCK-MP-EXCV-EX7136-UNDERC | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Operators Seat | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 17 | 90030739 | B1 | 1000306947 | 09.06.2029 | 10000 | CCK-MP-EXCV-EX7136-STRUCT-CABIN-SEATO | 7200 | 19274 | 9362
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Power Pack Module | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 172 | 90030914 | B1 | 1000307004 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Grease Block & Injectors | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 84 | 90030749 | B1 | 1000306959 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-GRSYST-GRINJ | 7200 | 19274 | 6872
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Accumulator Track Hyd LH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 3 | 90030729 | B1 | 1000306942 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDACC-HACCL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Accumulator Track Hyd RH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 3 | 90030729 | B1 | 1000306943 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDACC-HACCR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Ladder Raise Cyl | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 24 | 90030750 | B1 | 1000307003 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-LACYL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Swing Front | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 24 | 90030727 | B1 | 1000306917 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-SWMOF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Swing Rear | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 24 | 90030727 | B1 | 1000306916 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-SWMOR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel LHF | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 8 | 90030728 | B1 | 1000306918 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMLF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel LHR | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 8 | 90030728 | B1 | 1000306919 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMLR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel RHF | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 8 | 90030728 | B1 | 1000306940 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMRF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Motor Travel RHR | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 8 | 90030728 | B1 | 1000306941 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-HDMOT-TRMRR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Valve Bank Module | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 122 | 90027370 | B1 | 1000307008 | 14.06.2029 | 40000 | CCK-MP-EXCV-EX7136-HYDSYS-HDVLV-MCVLU | 7200 | 19274 | 8502
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Rotary Connection & Hoses | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 168 | 90030430 | B1 | 1000307014 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-HYDSYS-ROTRY | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Boom Module | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 276 | 90027376 | B1 | 1000307010 | 14.06.2029 | 40000 | CCK-MP-EXCV-EX7136-STRUCT-BOOMS | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Tank Module | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 86 | 90036464 | B1 | 1000307012 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-STRUCT-HDTNK | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Service Module | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 18 | 90036466 | B1 | 1000307000 | 14.06.2029 | 40000 | CCK-MP-EXCV-EX7136-STRUCT-SRVCT | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Stick Assembly | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 332 | 90017828 | B2 | 1000306992 | 14.06.2029 | 40000 | CCK-MP-EXCV-EX7136-STRUCT-STICK | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Gearbox Swing P1 | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 109 | 90030720 | B1 | 1000306914 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-SWGSYS-SWBOX-SGBPF | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Gearbox Swing P2 | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 109 | 90030720 | B1 | 1000306915 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-SWGSYS-SWBOX-SGBPR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Slew Bearing | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 288 | 90030743 | B1 | 1000306950 | 14.06.2029 | 40000 | CCK-MP-EXCV-EX7136-UNDERC-SLEWB | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Final Drive LH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 141 | 90030716 | B1 | 1000306912 | 14.06.2029 | 40000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-FDRLH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Idler LH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 36 | 90030740 | B1 | 1000306956 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-IDLLH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Sprocket LH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 72 | 90030718 | B1 | 1000306952 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-SPRKL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Hyd Tensioner LH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 74 | 90024277 | B1 | 1000306948 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-TENSL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Assembly LH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 36 | 90030719 | B1 | 1000306953 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRL-TRKLH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Final Drive RH Side | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 141 | 90030716 | B1 | 1000306913 | 14.06.2029 | 40000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-FDRRH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Idler RH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 36 | 90030740 | B1 | 1000306957 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-IDLRH | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Sprocket RH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 72 | 90030718 | B1 | 1000306954 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-SPRKR | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Hyd Tensioner RH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 74 | 90024277 | B1 | 1000306949 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-TENSL | 7200 | 19274 | 19274
R9400 | Onsite Shut | Excavators | Fortescue | EX7136 | EX7136 Repl Track Assembly RH | 2029-06-06 | 2029-06-18 | 282 hrs | FY29 | 36 | 90030719 | B1 | 1000306955 | 14.06.2029 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-TRKRH | 7200 | 19274 | 19274
| Onsite PM | Ancillary | Fortescue |  | ANCILLARY - COMPONENTS DURING PM
| Onsite PM | Ancillary | Fortescue |  | FY27 - ANCILLARY - COMPONENTS DURING PM | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Ancillary | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Ancillary | Fortescue | MOC | JULY | 2026-07-01 | 2026-07-31 | 30 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Artic Overhaul | 2026-07-01 | 2026-07-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Static Turning - In Cab Warning System | 2026-07-01 | 2026-07-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | Dozer Push Arm Refurbishment | 2026-07-01 | 2026-07-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2026-07-01 | 2026-07-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic overhaul | 2026-08-01 | 2026-08-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Hydraulic Tanks | 2026-08-01 | 2026-08-31 | 30 days | FY27
16M | Onsite PM | Ancillary | Fortescue | All - 16M | 16M Rotable Front Axle | 2026-08-01 | 2026-08-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Air Tanks | 2026-08-01 | 2026-08-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Service Exchange Cab Replacement | 2026-09-01 | 2026-09-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Wheel Loader Bucket Refurbishment | 2026-09-01 | 2026-09-30 | 29 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Repl Gearbox Circle Drive Front - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Cab Replacement | 2026-09-01 | 2026-09-30 | 29 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Blade Refurbishment | 2026-09-01 | 2026-09-30 | 29 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Cab Replacement | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Loaders Fuel Tanks | 2026-10-01 | 2026-10-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Trunnion Support Rear Axle | 2026-10-01 | 2026-10-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Blade Replacement | 2026-10-01 | 2026-10-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Hydraulic Tanks | 2026-10-01 | 2026-10-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic overhaul | 2026-11-01 | 2026-11-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Cab Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Air Tanks | 2026-11-01 | 2026-11-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | Dozer Push Arm Refurbishment | 2026-11-01 | 2026-11-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Wheel Loader Bucket Refurbishment | 2026-12-01 | 2026-12-31 | 30 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Blade Overhaul - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Repl Gearbox Circle Drive Front - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Artic Overhaul | 2027-01-01 | 2027-01-31 | 30 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Cab Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Hydraulic tank | 2027-01-01 | 2027-01-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Blade Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Hydraulic Tanks | 2027-01-01 | 2027-01-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Static Turning - In Cab Warning System | 2027-01-01 | 2027-01-31 | 30 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Repl Gearbox Circle Drive Front - MSR Strategy On Condition | 2027-01-01 | 2027-01-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic overhaul | 2027-02-01 | 2027-02-28 | 27 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Service Exchange Cab Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Blade Refurbishment | 2027-02-01 | 2027-02-28 | 27 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Blade Overhaul - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Chassis Overhaul | 2027-04-01 | 2027-04-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Trunnion Support Rear Axle | 2027-04-01 | 2027-04-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Blade Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Cab Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Wheel Loader Bucket Refurbishment | 2027-04-01 | 2027-04-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Air Tanks | 2027-04-01 | 2027-04-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | Dozer Push Arm Refurbishment | 2027-04-01 | 2027-04-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | MAY | 2027-05-01 | 2027-05-31 | 30 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Cab Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic overhaul | 2027-05-01 | 2027-05-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Hydraulic Tanks | 2027-05-01 | 2027-05-31 | 30 days | FY27
24M | Onsite PM | Ancillary | Fortescue | All - 24M | 24M Service Exchange Cab Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Blade Refurbishment | 2027-05-01 | 2027-05-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | JUNE | 2027-06-01 | 2027-06-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Repl Cylinders (all) - MSR Strategy On Condition | 2027-06-01 | 2027-06-30 | 29 days | FY27
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Front Axle Assembly Midlife | 2026-07-24 | 2026-07-25 | 32 hrs | FY27 | 56 | 90030394 | B1 | 1000303390 | 31.01.2026 | 7000 | CCK-MP-GRDR-GR7107-STRUCT-AXLES | 5500 | 24399 | 9687
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Minor Service Air Conditioner | 2026-07-28 | 2026-07-28 | 10.5 hrs | FY27 | 10.5 | 90017699 | B1 | 1000196631 | 29.07.2026 | 4500 | CCK-MP-DOZR-DZ175 -STRUCT-CABIN-AIRCN | 5000 | 71802 | 4957
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Adjust Engine 500hr Valve Set | 2026-07-30 | 2026-07-30 | 8 hrs | FY27 | 16 | 90015857 | B1 | 1000160191 | 12.12.2026 | 500 | CCK-MP-DOZR-DZ176 -ENGINE | 5000 | 69680 | 784
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Hyd System Hoses Midlife | 2026-08-01 | 2026-08-02 | 24 hrs | FY27 | 24 | 90026914 | B1 | 1000271600 | 16.07.2026 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-HYDHO | 6000 | 74342 | 30142
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Sepura SCC Microphone | 2026-08-03 | 2026-08-03 | 0.5 hrs | FY27 | 0.5 | 90028989 | B1 | 1000289370 | 02.07.2026 | 12 Monthly | CCK-MP-GRDR-GR012 -COMMUN-RADIO | 5200 | 72353 | 72353
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Articulation Overhaul | 2026-08-03 | 2026-08-11 | 194 hrs | FY27 | 360 | 90032991 | B1 | 1000329974 | 22.12.2026 | 16000 | CCK-MP-LOAD-WL267 -STRUCT-CHASS-ARTIC | 6000 | 74441 | 13352
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Adjust 250hr Initial Valve Set | 2026-08-04 | 2026-08-04 | 6 hrs | FY27 | 12 | 90015780 | B1 | 1000290215 | 13.08.2026 | 250 | CCK-MP-GRDR-GR012 -ENGINE | 5200 | 72353 | 348
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Artic Area Hyd Hosing | 2026-08-05 | 2026-08-05 | 6 hrs | FY27 | 6 | 90020831 | B1 | 1000364487 | 06.05.2026 | 8 Monthly | CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-ARTHO
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Air Conditioner Service | 2026-08-07 | 2026-08-08 | 24 hrs | FY27 | 24 | 90018855 | B1 | 1000225828 | 30.04.2026 | 9000 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN-AIRCN | 5000 | 23802 | 10459
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Sepura SCC Microphone | 2026-08-08 | 2026-08-08 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289570 | 08.08.2026 | 12 Monthly | CCK-MP-DOZR-DZ8235-COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Sepura SCC Microphone | 2026-08-09 | 2026-08-09 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289552 | 31.07.2026 | 12 Monthly | CCK-MP-DOZR-DZ178 -COMMUN-RADIO | 5000 | 54741 | 3721
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Minor Service Air Conditioner | 2026-08-09 | 2026-08-09 | 10.5 hrs | FY27 | 10.5 | 90017699 | B1 | 1000196640 | 10.08.2026 | 4500 | CCK-MP-DOZR-DZ178 -STRUCT-CABIN-AIRCN | 5000 | 54741 | 3721
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Sepura SCC Microphone | 2026-08-10 | 2026-08-10 | 0.5 hrs | FY27 | 0.5 | 90028998 | B1 | 1000289604 | 28.07.2026 | 12 Monthly | CCK-MP-LOAD-WL269 -COMMUN-RADIO | 6000 | 74583 | 5623
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Blade Lift RH | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90021509 | B1 | 1000225884 | 31.01.2026 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BLCYR | 5500 | 24399 | 9687
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Blade Tilt LH | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90021511 | B1 | 1000225885 | 31.01.2026 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYL | 5500 | 24399 | 9687
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Blade Tilt RH | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90021511 | B1 | 1000225886 | 31.01.2026 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYR | 5500 | 24399 | 9687
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Side Shift | 2026-08-10 | 2026-08-10 | 5 hrs | FY27 | 6 | 90021513 | B1 | 1000225889 | 07.01.2027 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-SSCYL | 5500 | 24399 | 4589
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Articulation LH | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90021512 | B1 | 1000225881 | 31.01.2026 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYL | 5500 | 24399 | 9687
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Ripper Lift | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90021514 | B1 | 1000225888 | 31.01.2026 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-RICYL | 5500 | 24399 | 9687
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 12 Monthly Hydraulic Tune Up | 2026-08-10 | 2026-08-10 | 12 hrs | FY27 | 24 | 90015111 | B1 | 1000126740 | 16.03.2026 | 52 Weekly | CCK-MP-LOAD-WL267 -HYDSYS | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Cyl Lift RH Ext High Lift | 2026-08-10 | 2026-08-11 | 28 hrs | FY27 | 54 | 90002728 | B2 | 1000028898 | 08.12.2026 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-HCYLR | 6000 | 80515 | 7470
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Cyl Blade Lift LH | 2026-08-10 | 2026-08-10 | 8 hrs | FY27 | 16 | 90000287 | B1 | 1000255590 | 25.07.2026 | 9000 | CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-BLCYL | 5000 | 62015 | 8908
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Operators Seat | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108379 | 21.07.2026 | 6000 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN-SEATS | 5000 | 62015 | 11979
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Blade Mounting Bracket LH | 2026-08-17 | 2026-08-18 | 24 hrs | FY27 | 48 | 90002671 | B2 | 1000090807 | 02.08.2025 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-CIRCL-BLMBL | 5200 | 60265 | 18931
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Blade Mounting Bracket RH | 2026-08-17 | 2026-08-18 | 24 hrs | FY27 | 48 | 90002671 | B2 | 1000090808 | 02.08.2025 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-CIRCL-BLMBR | 5200 | 60265 | 18931
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Sepura SCC Microphone | 2026-08-17 | 2026-08-17 | 0.5 hrs | FY27 | 0.5 | 90028997 | B1 | 1000289594 | 11.08.2026 | 12 Monthly | CCK-MP-LOAD-WL017 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Cyl Blade Lift LH | 2026-08-17 | 2026-08-17 | 8 hrs | FY27 | 16 | 90000287 | B1 | 1000255614 | 03.08.2026 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BLCYL | 5000 | 68264 | 9056
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Cyl Blade Lift RH | 2026-08-17 | 2026-08-17 | 8 hrs | FY27 | 16 | 90000287 | B1 | 1000255615 | 03.08.2026 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BLCYR | 5000 | 68264 | 9054
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Overhaul Air Condtioner System | 2026-08-17 | 2026-08-19 | 48 hrs | FY27 | 48 | 90017475 | B1 | 1000290314 | 16.04.2026 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CABIN-AIRCN | 5200 | 68036 | 15776
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Cyl Bucket LH High Lift | 2026-08-24 | 2026-08-25 | 18 hrs | FY27 | 36 | 90017978 | B1 | 1000131518 | 05.04.2029 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-BUCYL | 6000 | 74342 | 3995
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Sepura SCC Microphone | 2026-08-24 | 2026-08-24 | 0.5 hrs | FY27 | 0.5 | 90028996 | B1 | 1000289580 | 21.08.2026 | 12 Monthly | CCK-MP-DOZR-WD006 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Sepura SCC Microphone | 2026-08-24 | 2026-08-24 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289557 | 31.08.2026 | 12 Monthly | CCK-MP-DOZR-DZ183 -COMMUN-RADIO | 5000 | 65807 | 65807
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Sepura SCC Microphone | 2026-08-24 | 2026-08-24 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289555 | 29.08.2026 | 12 Monthly | CCK-MP-DOZR-DZ181 -COMMUN-RADIO | 5000 | 66297 | 66297
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Hyd Pump Cooling Fan | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 16 | 90004952 | B2 | 1000079438 | 20.03.2027 | 18000 | CCK-MP-DOZR-DZ173 -HYDSYS-HYDPP-HYFPP | 5000 | 68788 | 14973
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Sepura SCC Microphone | 2026-08-24 | 2026-08-24 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289554 | 05.09.2026 | 12 Monthly | CCK-MP-DOZR-DZ180 -COMMUN-RADIO | 5000 | 63195 | 63195
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Sepura SCC Microphone | 2026-08-24 | 2026-08-24 | 0.5 hrs | FY27 | 0.5 | 90028989 | B1 | 1000289373 | 22.08.2026 | 12 Monthly | CCK-MP-GRDR-GR122 -COMMUN-RADIO | 5200 | 68036 | 68036
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Operators Seat | 2026-08-26 | 2026-08-26 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108427 | 30.08.2026 | 6000 | CCK-MP-DOZR-DZ173 -STRUCT-CABIN-SEATS | 5000 | 68788 | 11495
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 6M Anritsu Test Wifi Cables | 2026-08-31 | 2026-08-31 | 2 hrs | FY27 | 2 | 90019046 | B2 | 1000257061 | 30.08.2026 | 6 Monthly | CCK-MP-LOAD-WL7162-COMMUN-FLMGT
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Transmission Charge Pump | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 12 | 90002694 | B2 | 1000090218 | 22.08.2026 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-TRPMP | 6000 | 75558 | 9814
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Air Conditioning Overhaul | 2026-08-31 | 2026-09-02 | 48 hrs | FY27 | 48 | 90017479 | B1 | 1000291904 | 22.05.2026 | 8000 | CCK-MP-LOAD-WL017 -STRUCT-CABIN-AIRCN | 3100 | 56923 | 7866
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Overhaul Air Conditioner | 2026-08-31 | 2026-09-02 | 48 hrs | FY27 | 48 | 90017468 | B1 | 1000196656 | 13.04.2026 | 18000 | CCK-MP-DOZR-DZ183 -STRUCT-CABIN-AIRCN | 5000 | 65794 | 25789
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Overhaul Airconditioner | 2026-08-31 | 2026-09-02 | 48 hrs | FY27 | 48 | 90013087 | B1 | 1000286599 | 28.04.2026 | 11000 | CCK-MP-DOZR-WD007 -STRUCT-CABIN-AIRCN | 6300 | 76489 | 20596
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Operators Seat | 2026-09-02 | 2026-09-02 | 4 hrs | FY27 | 8 | 90018835 | B1 | 1000225852 | 08.09.2026 | 6000 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN-SEATS | 5000 | 23802 | 5679
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Sepura SCC Microphone | 2026-09-07 | 2026-09-07 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289569 | 08.09.2026 | 12 Monthly | CCK-MP-DOZR-DZ8234-COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Cyl Blade Lift LH | 2026-09-07 | 2026-09-07 | 8 hrs | FY27 | 16 | 90000287 | B1 | 1000255694 | 02.09.2026 | 9000 | CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-BLCYL | 5000 | 65794 | 13113
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Gearbox Circle Drive Front | 2026-09-07 | 2026-09-07 | 8 hrs | FY27 | 14 | 90002672 | B2 | 1000090931 | 09.09.2026 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CIRCL-CDBXF | 5200 | 68036 | 15776
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Gearbox Circle Drive Rear | 2026-09-07 | 2026-09-07 | 8 hrs | FY27 | 14 | 90011066 | B2 | 1000090932 | 09.09.2026 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CIRCL-CDBXR | 5200 | 68036 | 10615
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Hyd Pump Implement | 2026-09-12 | 2026-09-12 | 10 hrs | FY27 | 10 | 90000301 | B2 | 1000091366 | 23.09.2026 | 9000 | CCK-MP-DOZR-DZ184 -HYDSYS-HYDPP-HYIPP | 5000 | 67674 | 8628
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Drive Shaft Unis | 2026-09-12 | 2026-09-12 | 3 hrs | FY27 | 6 | 90033292 | B1 | 1000334128 | 23.09.2026 | 9000 | CCK-MP-DOZR-DZ184 -TRNSYS | 5000 | 67674 | 8628
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Sepura SCC Microphone | 2026-09-14 | 2026-09-14 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289550 | 14.09.2026 | 12 Monthly | CCK-MP-DOZR-DZ175 -COMMUN-RADIO | 5000 | 71827 | 4957
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Operators Seat | 2026-09-14 | 2026-09-14 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108391 | 23.09.2026 | 6000 | CCK-MP-DOZR-DZ170 -STRUCT-CABIN-SEATS | 5000 | 54263 | 5339
16M | Onsite PM | Ancillary | Fortescue | GR015 | GR015 Air Conditioner Minor Service | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 12 | 90019351 | B1 | 1000269600 | 15.09.2026 | 3500 | CCK-MP-GRDR-GR015 -STRUCT-CABIN-AIRCN | 3200 | 42638 | 2788
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Operators Seat | 2026-09-14 | 2026-09-14 | 4 hrs | FY27 | 4 | 90019606 | B1 | 1000201907 | 06.09.2026 | 10000 | CCK-MP-GRDR-GR7107-STRUCT-CABIN-SEATS | 5500 | 24399 | 9406
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Minor Service Air Conditioner | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 12 | 90019636 | B1 | 1000201880 | 20.09.2026 | 3500 | CCK-MP-GRDR-GR7107-STRUCT-CABIN-AIRCN | 5500 | 24399 | 9687
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Operators Seat | 2026-09-14 | 2026-09-14 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108559 | 20.10.2026 | 6000 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN-SEATS | 5000 | 67674 | 5213
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Engine Midlife Complete | 2026-09-15 | 2026-09-18 | 71 hrs | FY27 | 103 | 90015859 | B1 | 1000160289 | 15.09.2026 | 9000 | CCK-MP-DOZR-DZ184 -ENGINE | 5000 | 67674 | 8628
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Major Service Air Conditioner | 2026-09-15 | 2026-09-16 | 24 hrs | FY27 | 24 | 90017469 | B1 | 1000196659 | 15.09.2026 | 9000 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN-AIRCN | 5000 | 67674 | 8628
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Sepura SCC Microphone | 2026-09-21 | 2026-09-21 | 0.5 hrs | FY27 | 0.5 | 90028998 | B1 | 1000289610 | 17.09.2026 | 12 Monthly | CCK-MP-LOAD-WL7162-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Sepura SCC Microphone | 2026-09-21 | 2026-09-21 | 0.5 hrs | FY27 | 0.5 | 90028998 | B1 | 1000364484 | 03.09.2026 | 12 Monthly | CCK-MP-LOAD-WL7104-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 12 Monthly Hydraulic Tune Up | 2026-09-21 | 2026-09-21 | 12 hrs | FY27 | 24 | 90015111 | B1 | 1000364486 | 07.09.2026 | 52 Weekly | CCK-MP-LOAD-WL7104-HYDSYS
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Service Minor Air Conditioner | 2026-09-21 | 2026-09-21 | 12 hrs | FY27 | 12 | 90019542 | B1 | 1000290305 | 10.09.2026 | 3500 | CCK-MP-GRDR-GR121 -STRUCT-CABIN-AIRCN | 5200 | 67029 | 10195
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Repl Sepura SCC Microphone | 2026-09-21 | 2026-09-21 | 0.5 hrs | FY27 | 0.5 | 90028989 | B1 | 1000289372 | 29.09.2026 | 12 Monthly | CCK-MP-GRDR-GR121 -COMMUN-RADIO | 5200 | 67029 | 67029
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Operators Seat | 2026-09-21 | 2026-09-21 | 2 hrs | FY27 | 4 | 90002975 | B2 | 1000228704 | 02.09.2026 | 7000 | CCK-MP-DOZR-WD203 -STRUCT-CABIN-SEATS | 6300 | 80875 | 6377
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Engine Midlife Complete | 2026-09-25 | 2026-09-28 | 71 hrs | FY27 | 103 | 90015859 | B1 | 1000160109 | 25.09.2026 | 9000 | CCK-MP-DOZR-DZ169 -ENGINE | 5000 | 62015 | 8044
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Major Service Air Conditioner | 2026-09-25 | 2026-09-26 | 24 hrs | FY27 | 24 | 90017469 | B1 | 1000196608 | 25.09.2026 | 9000 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN-AIRCN | 5000 | 62015 | 8044
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Sepura SCC Microphone | 2026-09-28 | 2026-09-28 | 0.5 hrs | FY27 | 0.5 | 90028996 | B1 | 1000289585 | 05.10.2026 | 12 Monthly | CCK-MP-DOZR-WD204 -COMMUN-RADIO | 6300 | 83628 | 83628
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Drive Shaft Unis | 2026-10-01 | 2026-10-01 | 3 hrs | FY27 | 6 | 90033292 | B1 | 1000334104 | 09.10.2026 | 9000 | CCK-MP-DOZR-DZ171 -TRNSYS | 5000 | 67979 | 8290
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Clean Engine Pre Cleaners | 2026-10-03 | 2026-10-03 | 6 hrs | FY27 | 6 | 90015808 | B1 | 1000286622 | 07.10.2026 | 5500 | CCK-MP-DOZR-WD204 -ENGINE-INTEX-AIRFL | 6300 | 83628 | 28312
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Service Airconditioner | 2026-10-03 | 2026-10-04 | 24 hrs | FY27 | 24 | 90003915 | B1 | 1000286626 | 07.10.2026 | 5500 | CCK-MP-DOZR-WD204 -STRUCT-CABIN-AIRCN | 6300 | 83628 | 15298
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Minor Service Air Conditioner | 2026-10-03 | 2026-10-03 | 10.5 hrs | FY27 | 10.5 | 90017699 | B1 | 1000196628 | 03.10.2026 | 4500 | CCK-MP-DOZR-DZ174 -STRUCT-CABIN-AIRCN | 5000 | 65414 | 20488
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Sepura SCC Microphone | 2026-10-05 | 2026-10-05 | 0.5 hrs | FY27 | 0.5 | 90028998 | B1 | 1000289596 | 01.10.2026 | 12 Monthly | CCK-MP-LOAD-WL022 -COMMUN-RADIO
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 500hr Initial Valve Set | 2026-10-05 | 2026-10-05 | 6 hrs | FY27 | 12 | 90015809 | B1 | 1000286609 | 02.09.2026 | 500 | CCK-MP-DOZR-WD202 -ENGINE | 6300 | 79903 | 21666
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Drive Shaft Unis | 2026-10-05 | 2026-10-05 | 3 hrs | FY27 | 6 | 90033292 | B1 | 1000334100 | 30.09.2026 | 9000 | CCK-MP-DOZR-DZ169 -TRNSYS | 5000 | 62015 | 8044
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Engine Midlife Complete | 2026-10-13 | 2026-10-16 | 71 hrs | FY27 | 103 | 90015859 | B1 | 1000160241 | 13.10.2026 | 9000 | CCK-MP-DOZR-DZ180 -ENGINE | 5000 | 63195 | 7949
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Major Service Air Conditioner | 2026-10-13 | 2026-10-14 | 24 hrs | FY27 | 24 | 90017469 | B1 | 1000196647 | 13.10.2026 | 9000 | CCK-MP-DOZR-DZ180 -STRUCT-CABIN-AIRCN | 5000 | 63195 | 7626
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Adjust 250hr Initial Valve Set | 2026-10-19 | 2026-10-19 | 12 hrs | FY27 | 24 | 90021246 | B1 | 1000222342 | 28.08.2026 | 250 | CCK-MP-LOAD-WL021 -ENGINE | 6000 | 79997 | 19277
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Service Minor Air Conditioner | 2026-10-26 | 2026-10-26 | 12 hrs | FY27 | 12 | 90019542 | B1 | 1000290320 | 29.09.2026 | 3500 | CCK-MP-GRDR-GR123 -STRUCT-CABIN-AIRCN
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Sepura SCC Microphone | 2026-10-26 | 2026-10-26 | 0.5 hrs | FY27 | 0.5 | 90028989 | B1 | 1000289374 | 12.10.2026 | 12 Monthly | CCK-MP-GRDR-GR123 -COMMUN-RADIO
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Replace Articulation Area Hosing | 2026-11-02 | 2026-11-02 | 6 hrs | FY27 | 6 | 90022236 | B1 | 1000257062 | 03.11.2026 | 8 Monthly | CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Cyl Lift LH High Lift | 2026-11-02 | 2026-11-03 | 24 hrs | FY27 | 48 | 90002727 | B2 | 1000138177 | 22.12.2025 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-HCYLL | 6000 | 72865 | 12069
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Brake System Hoses Midlife | 2026-11-02 | 2026-11-02 | 4 hrs | FY27 | 4 | 90026908 | B1 | 1000271581 | 15.11.2026 | 10000 | CCK-MP-LOAD-WL260 -BRKSYS-BRHLF-BRKHO | 6000 | 75566 | 9814
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Torque Converter | 2026-11-02 | 2026-11-04 | 56 hrs | FY27 | 164 | 90002943 | B3 | 1000033620 | 30.10.2026 | 22000 | CCK-MP-DOZR-WD007 -TRNSYS-TRQUE | 6300 | 76513 | 20596
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Cyl Steering RH | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 22 | 90002961 | B3 | 1000033642 | 30.10.2026 | 22000 | CCK-MP-DOZR-WD007 -STRSYS-STRCY-STCYR | 6300 | 76489 | 20596
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Overhaul Auto Lubrication System | 2026-11-02 | 2026-11-04 | 48 hrs | FY27 | 96 | 90002971 | B3 | 1000033652 | 30.10.2026 | 22000 | CCK-MP-DOZR-WD007 -GRSYST | 6300 | 76489 | 20596
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Overhaul Axle Oscillation Rear | 2026-11-02 | 2026-11-03 | 24 hrs | FY27 | 64 | 90002953 | B3 | 1000033630 | 04.11.2026 | 15000 | CCK-MP-DOZR-WD007 -FDRSYS-RRDIF-TRNON | 6300 | 76489 | 13479
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Shaft Trans to Cntr Bearing | 2026-11-02 | 2026-11-02 | 4 hrs | FY27 | 8 | 90002949 | B3 | 1000268434 | 05.11.2026 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT03 | 6300 | 76513 | 20488
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Replace Shaft Universals Front | 2026-11-02 | 2026-11-02 | 3 hrs | FY27 | 6 | 90026667 | B1 | 1000268437 | 21.11.2026 | 11000 | CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT04 | 6300 | 76513 | 9013
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Clean Engine Pre Cleaners | 2026-11-09 | 2026-11-09 | 6 hrs | FY27 | 6 | 90015808 | B1 | 1000286587 | 04.11.2026 | 5500 | CCK-MP-DOZR-WD006 -ENGINE-INTEX-AIRFL
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Service Airconditioner | 2026-11-09 | 2026-11-10 | 24 hrs | FY27 | 24 | 90003915 | B1 | 1000286591 | 04.11.2026 | 5500 | CCK-MP-DOZR-WD006 -STRUCT-CABIN-AIRCN | 6300 | 69386 | 4123
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Pump Brake | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 4 | 90002957 | B3 | 1000033583 | 08.11.2026 | 15000 | CCK-MP-DOZR-WD006 -BRKSYS-BRPMP | 6300 | 69386 | 13427
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Pump Str Pilot & Str Cooling | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 4 | 90002959 | B3 | 1000033585 | 08.11.2026 | 15000 | CCK-MP-DOZR-WD006 -STRSYS-STPMP-STP02 | 6300 | 69386 | 13427
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Pump Implement | 2026-11-09 | 2026-11-09 | 6 hrs | FY27 | 12 | 90002962 | B3 | 1000033589 | 08.11.2026 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HYDPP-HYP01 | 6300 | 69386 | 13427
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Pump Cooling Fan | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 8 | 90002964 | B3 | 1000033591 | 08.11.2026 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HYDPP-HYP03 | 6300 | 69386 | 13427
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Motor Fan | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 8 | 90002969 | B3 | 1000033596 | 08.11.2026 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HYDMT-HYM01 | 6300 | 69386 | 13435
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Aftercooler Engine | 2026-11-09 | 2026-11-09 | 8 hrs | FY27 | 8 | 90010841 | B1 | 1000089373 | 28.10.2026 | 18000 | CCK-MP-DOZR-DZ014 -ENGINE-INTEX-AFTER | 5000 | 64687 | 16308
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Replace Artic Area Hyd Hosing | 2026-11-16 | 2026-11-16 | 6 hrs | FY27 | 6 | 90020831 | B1 | 1000220501 | 13.11.2026 | 8 Monthly | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Operators Seat | 2026-11-16 | 2026-11-16 | 4 hrs | FY27 | 4 | 90002741 | B2 | 1000090627 | 16.11.2026 | 7000 | CCK-MP-LOAD-WL266 -STRUCT-CABIN-SEATS | 6000 | 74342 | 5199
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Shaft Rear PD To Cntr Brng | 2026-11-16 | 2026-11-16 | 12 hrs | FY27 | 24 | 90033191 | B1 | 1000333523 | 22.11.2026 | 20000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT05 | 6000 | 74342 | 18157
16M | Onsite PM | Ancillary | Fortescue | GR015 | GR015 Repl Sepura SCC Microphone | 2026-11-16 | 2026-11-16 | 0.5 hrs | FY27 | 0.5 | 90028988 | B1 | 1000289365 | 16.11.2026 | 12 Monthly | CCK-MP-GRDR-GR015 -COMMUN-RADIO
16M | Onsite PM | Ancillary | Fortescue | GR014 | GR014 Repl Sepura SCC Microphone | 2026-11-16 | 2026-11-16 | 0.5 hrs | FY27 | 0.5 | 90028988 | B1 | 1000289364 | 22.11.2026 | 12 Monthly | CCK-MP-GRDR-GR014 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Minor Service Air Conditioner | 2026-11-23 | 2026-11-23 | 10.5 hrs | FY27 | 10.5 | 90017699 | B1 | 1000196649 | 28.11.2026 | 4500 | CCK-MP-DOZR-DZ181 -STRUCT-CABIN-AIRCN | 5000 | 66297 | 12007
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Hyd Pump Implement | 2026-11-23 | 2026-11-23 | 10 hrs | FY27 | 10 | 90000301 | B2 | 1000091270 | 13.11.2026 | 9000 | CCK-MP-DOZR-DZ180 -HYDSYS-HYDPP-HYIPP | 5000 | 63195 | 7626
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Drive Shaft Unis | 2026-11-23 | 2026-11-23 | 3 hrs | FY27 | 6 | 90033292 | B1 | 1000334120 | 13.11.2026 | 9000 | CCK-MP-DOZR-DZ180 -TRNSYS | 5000 | 63195 | 7626
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Trans System Hoses Midlife | 2026-11-25 | 2026-11-25 | 4 hrs | FY27 | 4 | 90026915 | B1 | 1000271585 | 25.11.2026 | 8000 | CCK-MP-LOAD-WL260 -TRNSYS-TRHLF-TRNHO | 6000 | 75558 | 9814
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Sepura SCC Microphone | 2026-11-27 | 2026-11-27 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289558 | 27.11.2026 | 12 Monthly | CCK-MP-DOZR-DZ184 -COMMUN-RADIO | 5000 | 67674 | 8628
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Front Axle Assembly Midlife | 2026-12-01 | 2026-12-02 | 41 hrs | FY27 | 42 | 90025907 | B1 | 1000255885 | 01.12.2026 | 7000 | CCK-MP-GRDR-GR120 -STRUCT-AXLES | 5200 | 60265 | 4188
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Cyl Bucket RH High Lift | 2026-12-02 | 2026-12-03 | 18 hrs | FY27 | 36 | 90017977 | B1 | 1000131519 | 02.12.2026 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-BUCYR | 6000 | 74342 | 1701
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Service Minor Air Conditioner | 2026-12-04 | 2026-12-04 | 12 hrs | FY27 | 12 | 90019542 | B1 | 1000290264 | 04.12.2026 | 3500 | CCK-MP-GRDR-GR120 -STRUCT-CABIN-AIRCN | 5200 | 60265 | 18931
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Reseal Tank Hyd | 2026-12-07 | 2026-12-07 | 12 hrs | FY27 | 24 | 90021393 | B1 | 1000224274 | 08.11.2026 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HDTNK | 3100 | 56923 | 56923
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Service Minor Air Conditioner | 2026-12-07 | 2026-12-07 | 12 hrs | FY27 | 12 | 90019542 | B1 | 1000290312 | 09.12.2026 | 3500 | CCK-MP-GRDR-GR122 -STRUCT-CABIN-AIRCN | 5200 | 68036 | 15776
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Operators Seat | 2026-12-09 | 2026-12-09 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108403 | 09.12.2026 | 6000 | CCK-MP-DOZR-DZ171 -STRUCT-CABIN-SEATS | 5000 | 67979 | 11227
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Overhaul Rear Axle Trunnion | 2026-12-14 | 2026-12-16 | 56 hrs | FY27 | 112 | 90002709 | B2 | 1000090603 | 22.11.2026 | 20000 | CCK-MP-LOAD-WL266 -FDRSYS-RRDIF-TRNON | 6000 | 74342 | 18157
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Equaliser Bar | 2026-12-14 | 2026-12-16 | 55 hrs | FY27 | 110 | 90002097 | B1 | 1000108432 | 11.10.2026 | 18000 | CCK-MP-DOZR-DZ173 -STRUCT-CHASS-EQUAL | 5000 | 68788 | 17174
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Minor Service Air Conditioner | 2026-12-14 | 2026-12-14 | 10.5 hrs | FY27 | 10.5 | 90017699 | B1 | 1000196625 | 10.12.2026 | 4500 | CCK-MP-DOZR-DZ173 -STRUCT-CABIN-AIRCN | 5000 | 68788 | 11848
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Aftercooler Engine | 2026-12-14 | 2026-12-14 | 8 hrs | FY27 | 8 | 90010841 | B1 | 1000108428 | 23.12.2026 | 18000 | CCK-MP-DOZR-DZ173 -ENGINE-INTEX-AFTER | 5000 | 68788 | 16178
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Sepura SCC Microphone | 2026-12-17 | 2026-12-17 | 0.5 hrs | FY27 | 0.5 | 90028998 | B1 | 1000289601 | 17.12.2026 | 12 Monthly | CCK-MP-LOAD-WL266 -COMMUN-RADIO | 6000 | 74342 | 74342
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Sepura SCC Microphone | 2026-12-19 | 2026-12-19 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289545 | 19.12.2026 | 12 Monthly | CCK-MP-DOZR-DZ170 -COMMUN-RADIO | 5000 | 54263 | 54263
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Engine Thermostats | 2026-12-21 | 2026-12-21 | 6 hrs | FY27 | 6 | 90021139 | B1 | 1000222772 | 08.12.2026 | 5000 | CCK-MP-LOAD-WL7104-ENGINE-COSYS-THERM | 4000 | 64060 | 3143
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Service Air Conditioner | 2026-12-21 | 2026-12-22 | 24 hrs | FY27 | 24 | 90021130 | B1 | 1000222764 | 08.12.2026 | 5000 | CCK-MP-LOAD-WL7104-STRUCT-CABIN-AIRCN | 4000 | 64060 | 3143
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Repl Operators Seat | 2026-12-21 | 2026-12-21 | 4 hrs | FY27 | 4 | 90002663 | B2 | 1000090863 | 25.12.2026 | 7000 | CCK-MP-GRDR-GR121 -STRUCT-CABIN-SEATS | 5200 | 67029 | 12377
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Sepura SCC Microphone | 2026-12-26 | 2026-12-26 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289546 | 26.12.2026 | 12 Monthly | CCK-MP-DOZR-DZ171 -COMMUN-RADIO | 5000 | 67979 | 67979
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Operators Seat | 2026-12-28 | 2026-12-28 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108487 | 18.01.2027 | 6000 | CCK-MP-DOZR-DZ178 -STRUCT-CABIN-SEATS | 5000 | 54741 | 3721
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Artic Area Hyd Hosing | 2027-01-01 | 2027-01-01 | 6 hrs | FY27 | 6 | 90020831 | B1 | 1000364487 | 01.01.2027 | 8 Monthly | CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-ARTHO
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Operators Seat | 2027-01-05 | 2027-01-05 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108547 | 05.01.2027 | 6000 | CCK-MP-DOZR-DZ183 -STRUCT-CABIN-SEATS | 5000 | 65794 | 4209
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Repl Cyl Blade Lift LH | 2027-01-05 | 2027-01-05 | 8 hrs | FY27 | 16 | 90000287 | B1 | 1000255630 | 05.01.2027 | 9000 | CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-BLCYL | 5000 | 65414 | 7187
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Equaliser Bar | 2027-01-06 | 2027-01-08 | 55 hrs | FY27 | 110 | 90002097 | B1 | 1000108552 | 06.01.2027 | 18000 | CCK-MP-DOZR-DZ183 -STRUCT-CHASS-EQUAL | 5000 | 65794 | 15994
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Repl Hyd Pump Implement | 2027-01-06 | 2027-01-06 | 10 hrs | FY27 | 10 | 90000301 | B2 | 1000091174 | 06.01.2027 | 9000 | CCK-MP-DOZR-DZ174 -HYDSYS-HYDPP-HYIPP | 5000 | 65414 | 7187
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Thermostats | 2027-01-13 | 2027-01-13 | 6 hrs | FY27 | 6 | 90021139 | B1 | 1000222620 | 13.01.2027 | 5000 | CCK-MP-LOAD-WL266 -ENGINE-COSYS-THERM | 6000 | 74342 | 12308
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Service Air Conditioner | 2027-01-13 | 2027-01-14 | 24 hrs | FY27 | 24 | 90021130 | B1 | 1000222610 | 13.01.2027 | 5000 | CCK-MP-LOAD-WL266 -STRUCT-CABIN-AIRCN | 6000 | 74342 | 12308
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 12 Monthly Hydraulic Tune Up | 2027-01-15 | 2027-01-15 | 12 hrs | FY27 | 24 | 90015111 | B1 | 1000126196 | 15.01.2027 | 52 Weekly | CCK-MP-LOAD-WL260 -HYDSYS | 6000 | 75558 | 75558
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Output Drive Shaft Unis | 2027-01-18 | 2027-01-18 | 4 hrs | FY27 | 8 | 90033264 | B1 | 1000333905 | 18.01.2027 | 7000 | CCK-MP-GRDR-GR120 -FDRSYS-DRSHT-SHT01 | 5200 | 60265 | 4679
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Trans Input Drive Shaft Unis | 2027-01-18 | 2027-01-18 | 4 hrs | FY27 | 8 | 90033267 | B1 | 1000333907 | 18.01.2027 | 7000 | CCK-MP-GRDR-GR120 -FDRSYS-DRSHT-SHT02 | 5200 | 60265 | 4679
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Engine Midlife Complete | 2027-01-18 | 2027-01-21 | 71 hrs | FY27 | 103 | 90015859 | B1 | 1000160145 | 18.01.2027 | 9000 | CCK-MP-DOZR-DZ172 -ENGINE | 5000 | 68264 | 6824
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Fan Cooling Motor Hyd | 2027-01-18 | 2027-01-18 | 8 hrs | FY27 | 16 | 90002094 | B2 | 1000108414 | 18.01.2027 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDCFM | 5000 | 68264 | 6824
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Hyd Pump Implement | 2027-01-18 | 2027-01-18 | 10 hrs | FY27 | 10 | 90000301 | B2 | 1000091150 | 18.01.2027 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HYDPP-HYIPP | 5000 | 68264 | 6824
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Major Service Air Conditioner | 2027-01-18 | 2027-01-19 | 24 hrs | FY27 | 24 | 90017469 | B1 | 1000196623 | 18.01.2027 | 9000 | CCK-MP-DOZR-DZ172 -STRUCT-CABIN-AIRCN | 5000 | 68264 | 6824
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Drive Shaft Unis | 2027-01-18 | 2027-01-18 | 3 hrs | FY27 | 6 | 90033292 | B1 | 1000334106 | 18.01.2027 | 9000 | CCK-MP-DOZR-DZ172 -TRNSYS | 5000 | 68264 | 16489
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Centre Bearing Upper Shaft | 2027-01-22 | 2027-01-22 | 12 hrs | FY27 | 24 | 90002702 | B2 | 1000090596 | 22.01.2027 | 10000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-UCTRB | 6000 | 74342 | 18157
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Hyd Pump Pilot & Cooling | 2027-01-24 | 2027-01-24 | 6 hrs | FY27 | 12 | 90002726 | B2 | 1000090622 | 24.01.2027 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP04 | 6000 | 74342 | 7121
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Transmission Charge Pump | 2027-01-24 | 2027-01-24 | 6 hrs | FY27 | 12 | 90002694 | B2 | 1000090588 | 24.01.2027 | 10000 | CCK-MP-LOAD-WL266 -TRNSYS-TRPMP | 6000 | 74342 | 7121
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Cylinder Blade Lift RH | 2027-01-25 | 2027-01-25 | 8 hrs | FY27 | 16 | 90000287 | B1 | 1000255551 | 25.01.2027 | 9000 | CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BLCYR | 5000 | 28779 | 28779
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Operators Seat | 2027-01-29 | 2027-01-29 | 2 hrs | FY27 | 4 | 90002975 | B2 | 1000033602 | 29.01.2027 | 7000 | CCK-MP-DOZR-WD006 -STRUCT-CABIN-SEATS | 6300 | 69386 | 4123
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Minor Service Air Conditioner | 2027-01-31 | 2027-01-31 | 10.5 hrs | FY27 | 10.5 | 90017699 | B1 | 1000196615 | 31.01.2027 | 4500 | CCK-MP-DOZR-DZ171 -STRUCT-CABIN-AIRCN | 5000 | 67979 | 11227
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Sepura SCC Microphone | 2027-02-01 | 2027-02-01 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289548 | 01.02.2027 | 12 Monthly | CCK-MP-DOZR-DZ173 -COMMUN-RADIO | 5000 | 68788 | 68788
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Cyl Steering RH | 2027-02-02 | 2027-02-02 | 12 hrs | FY27 | 22 | 90002961 | B3 | 1000092734 | 02.02.2027 | 22000 | CCK-MP-DOZR-WD204 -STRSYS-STRCY-STCYR | 6300 | 83628 | 18934
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Cyl Bucket RH Ext High Lift | 2027-02-02 | 2027-02-03 | 18 hrs | FY27 | 36 | 90015437 | B2 | 1000131507 | 02.02.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-BUCYR | 6000 | 75558 | 7107
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 500hr Initial Valve Set | 2027-02-03 | 2027-02-03 | 10 hrs | FY27 | 20 | 90015822 | B1 | 1000291751 | 03.02.2027 | 500 | CCK-MP-LOAD-WL004 -ENGINE | 3100 | 64006 | 15676
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Sepura SCC Microphone | 2027-02-04 | 2027-02-04 | 0.5 hrs | FY27 | 0.5 | 90028996 | B1 | 1000289584 | 04.02.2027 | 12 Monthly | CCK-MP-DOZR-WD203 -COMMUN-RADIO | 6300 | 80875 | 80875
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Replace Hyd Pilot System Hoses | 2027-02-07 | 2027-02-07 | 12 hrs | FY27 | 24 | 90013052 | B3 | 1000231934 | 07.02.2027 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HDHLF-HDHPS | 6300 | 69386 | 69386
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Hoses Main Hyd-Fan System | 2027-02-08 | 2027-02-09 | 24 hrs | FY27 | 48 | 90013053 | B3 | 1000231935 | 08.02.2027 | 15000 | CCK-MP-DOZR-WD006 -HYDSYS-HDHLF-HDHMH | 6300 | 69386 | 69386
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Rear Output Drive Shaft Unis | 2027-02-12 | 2027-02-12 | 4 hrs | FY27 | 8 | 90033167 | B1 | 1000333650 | 12.02.2027 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT02 | 4000 | 64060 | 7889
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Ctr Output Drive Shaft Unis | 2027-02-12 | 2027-02-12 | 4 hrs | FY27 | 8 | 90033173 | B1 | 1000333652 | 12.02.2027 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT03 | 4000 | 64060 | 7889
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Sepura SCC Microphone | 2027-02-15 | 2027-02-15 | 0.5 hrs | FY27 | 0.5 | 90028989 | B1 | 1000289371 | 15.02.2027 | 12 Monthly | CCK-MP-GRDR-GR120 -COMMUN-RADIO | 5200 | 60265 | 60265
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Final Drive Position 4 | 2027-02-15 | 2027-02-17 | 44 hrs | FY27 | 83 | 90002710 | B2 | 1000090237 | 15.02.2027 | 16000 | CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR04 | 6000 | 75558 | 12904
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Transmission | 2027-02-15 | 2027-02-16 | 38 hrs | FY27 | 74 | 90002692 | B2 | 1000090217 | 15.02.2027 | 16000 | CCK-MP-LOAD-WL260 -TRNSYS-TRANS | 6000 | 75558 | 12904
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 12 Monthly Hydraulic Tune Up | 2027-02-16 | 2027-02-16 | 12 hrs | FY27 | 24 | 90015111 | B1 | 1000126199 | 16.02.2027 | 52 Weekly | CCK-MP-LOAD-WL266 -HYDSYS | 6000 | 74342 | 31864
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Lube Oil Cooler Front Axle | 2027-02-22 | 2027-02-22 | 3 hrs | FY27 | 6 | 90002770 | B2 | 1000030631 | 22.02.2027 | 20000 | CCK-MP-LOAD-WL017 -FDRSYS-HDOCA-HYOCF | 3100 | 56923 | 18034
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 6M Anritsu Test Wifi Cables | 2027-02-26 | 2027-02-26 | 2 hrs | FY27 | 2 | 90019046 | B2 | 1000257061 | 26.02.2027 | 6 Monthly | CCK-MP-LOAD-WL7162-COMMUN-FLMGT
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Gearbox Circle Drive Rear | 2027-02-27 | 2027-02-27 | 8 hrs | FY27 | 14 | 90011066 | B2 | 1000090810 | 27.02.2027 | 14000 | CCK-MP-GRDR-GR120 -STRUCT-CIRCL-CDBXR | 5200 | 60265 | 11145
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Final Drive RH | 2027-02-27 | 2027-02-27 | 14 hrs | FY27 | 28 | 90000312 | B2 | 1000091267 | 27.02.2027 | 18000 | CCK-MP-DOZR-DZ180 -FDRSYS-FDRRH | 5000 | 63195 | 15197
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Sepura SCC Microphone | 2027-02-28 | 2027-02-28 | 0.5 hrs | FY27 | 0.5 | 90028996 | B1 | 1000289581 | 28.02.2027 | 12 Monthly | CCK-MP-DOZR-WD007 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Thermostats | 2027-03-04 | 2027-03-04 | 6 hrs | FY27 | 6 | 90021139 | B1 | 1000222532 | 04.03.2027 | 5000 | CCK-MP-LOAD-WL261 -ENGINE-COSYS-THERM | 6000 | 77065 | 11736
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Service Air Conditioner | 2027-03-04 | 2027-03-05 | 24 hrs | FY27 | 24 | 90021130 | B1 | 1000222522 | 04.03.2027 | 5000 | CCK-MP-LOAD-WL261 -STRUCT-CABIN-AIRCN | 6000 | 77065 | 11736
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Cyl Blade Lift RH | 2027-03-09 | 2027-03-09 | 8 hrs | FY27 | 14 | 90018821 | B1 | 1000225818 | 09.03.2027 | 9000 | CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-BLCYR | 5000 | 23802 | 6195
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Cyl Blade Lift RH | 2027-03-11 | 2027-03-11 | 8 hrs | FY27 | 16 | 90000287 | B1 | 1000255679 | 11.03.2027 | 9000 | CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-BLCYR | 5000 | 66297 | 6103
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Sepura SCC Microphone | 2027-03-12 | 2027-03-12 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289547 | 12.03.2027 | 12 Monthly | CCK-MP-DOZR-DZ172 -COMMUN-RADIO | 5000 | 68264 | 6824
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Cyl Lift LH | 2027-03-14 | 2027-03-15 | 28 hrs | FY27 | 56 | 90002786 | B2 | 1000131362 | 14.03.2027 | 10000 | CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-HCYLL | 3100 | 56923 | 7866
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Cyl Lift RH | 2027-03-14 | 2027-03-15 | 28 hrs | FY27 | 56 | 90002787 | B2 | 1000131364 | 14.03.2027 | 10000 | CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-HCYLR | 3100 | 56923 | 7866
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Gearbox Pump Drive Front | 2027-03-15 | 2027-03-16 | 38 hrs | FY27 | 74 | 90002705 | B2 | 1000090599 | 15.03.2027 | 16000 | CCK-MP-LOAD-WL266 -TRNSYS-PMPDR-FRPDR | 6000 | 74342 | 12308
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Transmission | 2027-03-15 | 2027-03-16 | 38 hrs | FY27 | 74 | 90002692 | B2 | 1000090587 | 15.03.2027 | 16000 | CCK-MP-LOAD-WL266 -TRNSYS-TRANS | 6000 | 74342 | 12308
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Transmission System Hoses | 2027-03-15 | 2027-03-17 | 48 hrs | FY27 | 96 | 90026923 | B1 | 1000271601 | 15.03.2027 | 16000 | CCK-MP-LOAD-WL266 -TRNSYS-TRHLF-TRNHO | 6000 | 74342 | 12308
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Transmission Transfer Case | 2027-03-15 | 2027-03-16 | 38 hrs | FY27 | 74 | 90017029 | B2 | 1000153217 | 15.03.2027 | 16000 | CCK-MP-LOAD-WL266 -TRNSYS-TRTRF | 6000 | 74342 | 12308
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Equaliser Bar | 2027-03-15 | 2027-03-17 | 55 hrs | FY27 | 110 | 90002097 | B1 | 1000108516 | 15.03.2027 | 18000 | CCK-MP-DOZR-DZ180 -STRUCT-CHASS-EQUAL | 5000 | 63195 | 14959
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Overhaul Chassis Articulation | 2027-03-16 | 2027-03-20 | 96 hrs | FY27 | 288 | 90016399 | B1 | 1000257057 | 16.03.2027 | 18000 | CCK-MP-LOAD-WL7162-STRUCT-CHASS-ARTIC | 6100 | 25829 | 14610
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Operators Seat | 2027-03-16 | 2027-03-16 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000089357 | 16.03.2027 | 6000 | CCK-MP-DOZR-DZ014 -STRUCT-CABIN-SEATS | 5000 | 64687 | 2402
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Operators Seat | 2027-03-17 | 2027-03-17 | 4 hrs | FY27 | 4 | 90002741 | B2 | 1000090257 | 17.03.2027 | 7000 | CCK-MP-LOAD-WL260 -STRUCT-CABIN-SEATS | 6000 | 75558 | 3411
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Drive Shaft Unis | 2027-03-19 | 2027-03-19 | 3 hrs | FY27 | 6 | 90033292 | B1 | 1000334126 | 19.03.2027 | 9000 | CCK-MP-DOZR-DZ183 -TRNSYS | 5000 | 65794 | 34266
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Clean Engine Pre Cleaners | 2027-03-19 | 2027-03-19 | 6 hrs | FY27 | 6 | 90015808 | B1 | 1000286594 | 19.03.2027 | 5500 | CCK-MP-DOZR-WD007 -ENGINE-INTEX-AIRFL
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Service Airconditioner | 2027-03-19 | 2027-03-20 | 24 hrs | FY27 | 24 | 90003915 | B1 | 1000286598 | 19.03.2027 | 5500 | CCK-MP-DOZR-WD007 -STRUCT-CABIN-AIRCN | 6300 | 76489 | 20596
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Air Conditioner Minor Service | 2027-03-25 | 2027-03-25 | 6 hrs | FY27 | 6 | 90018856 | B1 | 1000225826 | 25.03.2027 | 4500 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN-AIRCN | 5000 | 23802 | 10459
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Clean Engine Pre Cleaners | 2027-03-25 | 2027-03-25 | 6 hrs | FY27 | 6 | 90015808 | B1 | 1000286615 | 25.03.2027 | 5500 | CCK-MP-DOZR-WD203 -ENGINE-INTEX-AIRFL | 6300 | 80875 | 44315
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Service Airconditioner | 2027-03-25 | 2027-03-26 | 24 hrs | FY27 | 24 | 90003915 | B1 | 1000286619 | 25.03.2027 | 5500 | CCK-MP-DOZR-WD203 -STRUCT-CABIN-AIRCN | 6300 | 80875 | 13604
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd System Hoses Midlife | 2027-03-27 | 2027-03-28 | 24 hrs | FY27 | 24 | 90026914 | B1 | 1000271583 | 27.03.2027 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-HYDHO | 6000 | 75558 | 9814
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Service Minor Air Conditioner | 2027-03-29 | 2027-03-29 | 12 hrs | FY27 | 12 | 90019542 | B1 | 1000290217 | 29.03.2027 | 3500 | CCK-MP-GRDR-GR012 -STRUCT-CABIN-AIRCN | 5200 | 72353 | 12098
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Adjust 250hr Initial Valve Set | 2027-04-02 | 2027-04-02 | 12 hrs | FY27 | 24 | 90021246 | B1 | 1000222364 | 02.04.2027 | 250 | CCK-MP-LOAD-WL022 -ENGINE | 6000 | 80537 | 15801
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Pump Brake | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 4 | 90002957 | B3 | 1000092677 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -BRKSYS-BRPMP | 6300 | 80875 | 10669
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Rear Differential | 2027-04-04 | 2027-04-07 | 68 hrs | FY27 | 134 | 90002952 | B3 | 1000092669 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -FDRSYS-RRDIF | 6300 | 80875 | 10669
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Overhaul Axle Oscillation Rear | 2027-04-04 | 2027-04-05 | 24 hrs | FY27 | 64 | 90002953 | B3 | 1000092670 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -FDRSYS-RRDIF-TRNON | 6300 | 80875 | 10669
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hyd Motor Fan | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90002969 | B3 | 1000092686 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -HYDSYS-HYDMT-HYM01 | 6300 | 80875 | 10670
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hyd Pump Steer Secondary | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 4 | 90002960 | B3 | 1000092680 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -STRSYS-STPMP-STP03 | 6300 | 80875 | 10670
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Transmission | 2027-04-04 | 2027-04-06 | 57 hrs | FY27 | 167 | 90002944 | B3 | 1000092662 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -TRNSYS-TRANS | 6300 | 80875 | 10670
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Transmission Oil Cooler | 2027-04-04 | 2027-04-04 | 6 hrs | FY27 | 6 | 90002945 | B3 | 1000109669 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -TRNSYS-TROLC | 6300 | 80875 | 10669
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Pump Transmission | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90002946 | B3 | 1000092663 | 04.04.2027 | 15000 | CCK-MP-DOZR-WD203 -TRNSYS-TRPMP | 6300 | 80875 | 10669
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Operators Seat | 2027-04-06 | 2027-04-06 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108463 | 06.04.2027 | 6000 | CCK-MP-DOZR-DZ176 -STRUCT-CABIN-SEATS | 5000 | 69680 | 2541
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Rad Engine Cooling SN 529 UP | 2027-04-08 | 2027-04-09 | 24 hrs | FY27 | 48 | 90000307 | B2 | 1000091332 | 08.04.2027 | 18000 | CCK-MP-DOZR-DZ183 -ENGINE-COSYS-RADTR | 5000 | 65794 | 14763
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Hyd Pump Implement | 2027-04-08 | 2027-04-08 | 10 hrs | FY27 | 10 | 90000301 | B2 | 1000091078 | 08.04.2027 | 9000 | CCK-MP-DOZR-DZ169 -HYDSYS-HYDPP-HYIPP | 5000 | 62015 | 5429
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Repl Sepura SCC Microphone | 2027-04-10 | 2027-04-10 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289549 | 10.04.2027 | 12 Monthly | CCK-MP-DOZR-DZ174 -COMMUN-RADIO | 5000 | 65414 | 65414
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Artic Area Hyd Hosing | 2027-04-12 | 2027-04-12 | 6 hrs | FY27 | 6 | 90020831 | B1 | 1000321324 | 12.04.2027 | 8 Monthly | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Final Drive Position 1 | 2027-04-13 | 2027-04-15 | 44 hrs | FY27 | 83 | 90002710 | B2 | 1000090604 | 13.04.2027 | 16000 | CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR01 | 6000 | 74342 | 11828
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Trans System Hoses Midlife | 2027-04-14 | 2027-04-14 | 4 hrs | FY27 | 4 | 90026915 | B1 | 1000271533 | 14.04.2027 | 8000 | CCK-MP-LOAD-WL021 -TRNSYS-TRHLF-TRNHO | 6000 | 79974 | 9601
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Input Shaft Unis | 2027-04-18 | 2027-04-18 | 4 hrs | FY27 | 8 | 90033167 | B1 | 1000333648 | 18.04.2027 | 10000 | CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT01 | 4000 | 64060 | 6713
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Replace Artic Area Hyd Hosing | 2027-04-18 | 2027-04-18 | 6 hrs | FY27 | 6 | 90020831 | B1 | 1000220503 | 18.04.2027 | 8 Monthly | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-ARTHO
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Minor Service Air Conditioner | 2027-04-20 | 2027-04-20 | 10.5 hrs | FY27 | 10.5 | 90017699 | B1 | 1000196655 | 20.04.2027 | 4500 | CCK-MP-DOZR-DZ183 -STRUCT-CABIN-AIRCN | 5000 | 65794 | 25789
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Replace Artic Area Hyd Hosing | 2027-05-02 | 2027-05-02 | 6 hrs | FY27 | 6 | 90020831 | B1 | 1000220497 | 02.05.2027 | 8 Monthly | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-ARTHO
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Trunnions RrAxle Oscillation | 2027-05-05 | 2027-05-06 | 28 hrs | FY27 | 56 | 90002769 | B2 | 1000030630 | 05.05.2027 | 20000 | CCK-MP-LOAD-WL017 -FDRSYS-RRDIF-TRNON | 3100 | 56923 | 17424
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Steering Cylinder RH | 2027-05-06 | 2027-05-06 | 14 hrs | FY27 | 28 | 90002722 | B2 | 1000138260 | 06.05.2027 | 12000 | CCK-MP-LOAD-WL7104-STRSYS-STRCY-STCYR | 4000 | 64060 | 8512
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Rad Engine Cooling SN 529 UP | 2027-05-07 | 2027-05-08 | 24 hrs | FY27 | 48 | 90000307 | B2 | 1000091284 | 07.05.2027 | 18000 | CCK-MP-DOZR-DZ181 -ENGINE-COSYS-RADTR | 5000 | 66297 | 14318
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Shaft Universals TC - Trans | 2027-05-07 | 2027-05-07 | 3 hrs | FY27 | 3 | 90026669 | B1 | 1000268431 | 07.05.2027 | 11000 | CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT01 | 6300 | 76513 | 8208
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Sepura SCC Microphone | 2027-05-14 | 2027-05-14 | 0.5 hrs | FY27 | 0.5 | 90028989 | B1 | 1000289540 | 02.03.2027 | 12 Monthly | CCK-MP-GRDR-GR7107-COMMUN-RADIO
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Adjust Engine 500hr Valve Set | 2027-05-18 | 2027-05-18 | 12 hrs | FY27 | 24 | 90018851 | B1 | 1000225422 | 18.05.2027 | 500 | CCK-MP-DOZR-DZ8234-ENGINE | 5000 | 26641 | 14816
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Cylinder Blade Tilt RH | 2027-05-19 | 2027-05-19 | 7 hrs | FY27 | 14 | 90002968 | B1 | 1000033649 | 19.05.2027 | 22000 | CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BTCYR | 6300 | 76489 | 17049
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Operators Seat | 2027-05-20 | 2027-05-20 | 4 hrs | FY27 | 4 | 90016397 | B1 | 1000257056 | 20.05.2027 | 7000 | CCK-MP-LOAD-WL7162-STRUCT-CABIN-SEATS | 6100 | 25829 | 2515
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Engine Midlife Complete | 2027-05-23 | 2027-05-27 | 113 hrs | FY27 | 177 | 90016406 | B1 | 1000256933 | 23.05.2027 | 12000 | CCK-MP-LOAD-WL7162-ENGINE | 6100 | 25829 | 7473
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Overhaul Auto Lubrication System | 2027-05-23 | 2027-05-23 | 6 hrs | FY27 | 6 | 90016395 | B1 | 1000257055 | 23.05.2027 | 12000 | CCK-MP-LOAD-WL7162-GRSYST-ALBPP | 6100 | 25829 | 7473
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Service Major Air Conditioner | 2027-05-23 | 2027-05-25 | 48 hrs | FY27 | 48 | 90019466 | B1 | 1000256939 | 23.05.2027 | 12000 | CCK-MP-LOAD-WL7162-STRUCT-CABIN-AIRCN | 6100 | 25829 | 7473
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Sepura SCC Microphone | 2027-05-23 | 2027-05-23 | 0.5 hrs | FY27 | 0.5 | 90028998 | B1 | 1000321326 | 23.05.2027 | 12 Monthly | CCK-MP-LOAD-WL7103-COMMUN-RADIO
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Cylinder Blade Tilt LH | 2027-05-26 | 2027-05-26 | 7 hrs | FY27 | 14 | 90002967 | B1 | 1000033648 | 26.05.2027 | 22000 | CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BTCYL | 6300 | 76489 | 17049
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Sepura SCC Microphone | 2027-05-27 | 2027-05-27 | 0.5 hrs | FY27 | 0.5 | 90028991 | B1 | 1000289544 | 27.05.2027 | 12 Monthly | CCK-MP-DOZR-DZ169 -COMMUN-RADIO | 5000 | 62015 | 62015
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Final Drive Position 1 | 2027-05-30 | 2027-06-01 | 44 hrs | FY27 | 83 | 90002710 | B2 | 1000090382 | 30.05.2027 | 16000 | CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR01 | 6000 | 74441 | 10738
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Actuator Brake HaulX Shield | 2027-05-31 | 2027-06-01 | 26 hrs | FY27 | 50 | 90033498 | B1 | 1000337794 | 31.05.2027 | 14000 | CCK-MP-DOZR-DZ173 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Overhaul Park Brake & Centre Brg | 2027-06-04 | 2027-06-05 | 18 hrs | FY27 | 36 | 90002711 | B2 | 1000138281 | 04.06.2027 | 10000 | CCK-MP-LOAD-WL7104-BRKSYS-BRPRK | 4000 | 64060 | 6713
16M | Onsite PM | Ancillary | Fortescue | GR014 | GR014 Overhaul Ripper Assy | 2027-06-07 | 2027-06-08 | 24 hrs | FY27 | 48 | 90002484 | B1 | 1000027398 | 30.03.2026 | 14000 | CCK-MP-GRDR-GR014 -STRUCT-RIPPR | 3200 | 44181 | 14563
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Operators Seat | 2027-06-09 | 2027-06-09 | 4 hrs | FY27 | 4 | 90002741 | B2 | 1000138269 | 09.06.2027 | 7000 | CCK-MP-LOAD-WL7104-STRUCT-CABIN-SEATS | 4000 | 64060 | 3143
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Pump Hyd Implement 1 | 2027-06-10 | 2027-06-10 | 10 hrs | FY27 | 10 | 90018831 | B1 | 1000225847 | 10.06.2027 | 18000 | CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYIP1 | 5000 | 23802 | 13909
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Pump Hyd Variable Charge | 2027-06-10 | 2027-06-10 | 4 hrs | FY27 | 4 | 90021620 | B1 | 1000226599 | 10.06.2027 | 18000 | CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYDVC | 5000 | 23802 | 13909
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Pump Hyd Implement 2 | 2027-06-10 | 2027-06-10 | 6 hrs | FY27 | 6 | 90021621 | B1 | 1000226709 | 10.06.2027 | 18000 | CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYIP2 | 5000 | 23802 | 13909
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Fan Cooling Motor Hyd | 2027-06-10 | 2027-06-10 | 8 hrs | FY27 | 16 | 90002094 | B2 | 1000108522 | 10.06.2027 | 9000 | CCK-MP-DOZR-DZ181 -HYDSYS-HDCFM | 5000 | 66297 | 4853
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Thermostats | 2027-06-13 | 2027-06-13 | 6 hrs | FY27 | 6 | 90021139 | B1 | 1000222356 | 13.06.2027 | 5000 | CCK-MP-LOAD-WL021 -ENGINE-COSYS-THERM | 6000 | 79974 | 9601
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Service Air Conditioner | 2027-06-13 | 2027-06-14 | 24 hrs | FY27 | 24 | 90021130 | B1 | 1000222346 | 13.06.2027 | 5000 | CCK-MP-LOAD-WL021 -STRUCT-CABIN-AIRCN | 6000 | 79974 | 19277
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 500hr Initial Valve Set | 2027-06-13 | 2027-06-13 | 6 hrs | FY27 | 12 | 90019629 | B1 | 1000201876 | 13.06.2027 | 500 | CCK-MP-GRDR-GR7107-ENGINE | 5500 | 24399 | 9687
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Engine Midlife Complete | 2027-06-16 | 2027-06-19 | 71 hrs | FY27 | 103 | 90015859 | B1 | 1000160181 | 16.06.2027 | 9000 | CCK-MP-DOZR-DZ175 -ENGINE | 5000 | 71802 | 4957
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Hyd Pump Implement | 2027-06-16 | 2027-06-16 | 10 hrs | FY27 | 10 | 90000301 | B2 | 1000091198 | 16.06.2027 | 9000 | CCK-MP-DOZR-DZ175 -HYDSYS-HYDPP-HYIPP | 5000 | 71802 | 4957
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Major Service Air Conditioner | 2027-06-16 | 2027-06-17 | 24 hrs | FY27 | 24 | 90017469 | B1 | 1000196630 | 16.06.2027 | 9000 | CCK-MP-DOZR-DZ175 -STRUCT-CABIN-AIRCN | 5000 | 71802 | 4957
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Drive Shaft Unis | 2027-06-16 | 2027-06-16 | 3 hrs | FY27 | 6 | 90033292 | B1 | 1000334112 | 16.06.2027 | 9000 | CCK-MP-DOZR-DZ175 -TRNSYS | 5000 | 71802 | 4957
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Repl Actuator Brake HaulX Shield | 2027-06-17 | 2027-06-18 | 26 hrs | FY27 | 50 | 90033498 | B1 | 1000337802 | 17.06.2027 | 14000 | CCK-MP-DOZR-DZ174 -MANGMT-CASYS-ACTBK
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Clean Engine Pre Cleaners | 2027-06-19 | 2027-06-19 | 6 hrs | FY27 | 6 | 90015808 | B1 | 1000286608 | 19.06.2027 | 5500 | CCK-MP-DOZR-WD202 -ENGINE-INTEX-AIRFL | 6300 | 79903 | 21666
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Service Airconditioner | 2027-06-19 | 2027-06-20 | 24 hrs | FY27 | 24 | 90003915 | B1 | 1000286612 | 19.06.2027 | 5500 | CCK-MP-DOZR-WD202 -STRUCT-CABIN-AIRCN | 6300 | 79903 | 10962
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Transmission | 2027-06-19 | 2027-06-21 | 57 hrs | FY27 | 167 | 90002944 | B3 | 1000092610 | 28.06.2027 | 15000 | CCK-MP-DOZR-WD202 -TRNSYS-TRANS | 6300 | 79903 | 9020
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Adjust 250hr Initial Valve Set | 2027-06-20 | 2027-06-20 | 6 hrs | FY27 | 12 | 90015780 | B1 | 1000290318 | 20.06.2027 | 250 | CCK-MP-GRDR-GR123 -ENGINE | 5200 | 50884 | 9251
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Operators Seat | 2027-06-20 | 2027-06-20 | 4 hrs | FY27 | 8 | 90000318 | B1 | 1000108511 | 20.06.2027 | 6000 | CCK-MP-DOZR-DZ180 -STRUCT-CABIN-SEATS | 5000 | 63195 | 1342
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Replace Artic Area Hyd Hosing | 2027-06-20 | 2027-06-20 | 6 hrs | FY27 | 6 | 90020831 | B1 | 1000220498 | 20.06.2027 | 8 Monthly | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Thermostats | 2027-06-22 | 2027-06-22 | 6 hrs | FY27 | 6 | 90021139 | B1 | 1000222510 | 22.06.2027 | 5000 | CCK-MP-LOAD-WL260 -ENGINE-COSYS-THERM | 6000 | 75558 | 38
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Service Air Conditioner | 2027-06-22 | 2027-06-23 | 24 hrs | FY27 | 24 | 90021130 | B1 | 1000222500 | 22.06.2027 | 5000 | CCK-MP-LOAD-WL260 -STRUCT-CABIN-AIRCN | 6000 | 75558 | 9814
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Cyl Lift LH Ext High Lift | 2027-06-26 | 2027-06-27 | 28 hrs | FY27 | 54 | 90002728 | B2 | 1000112665 | 26.06.2027 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-HCYLL | 6000 | 77065 | 4775
16M | Onsite PM | Ancillary | Fortescue | GR014 | GR014 Air Conditioner Minor Service | 2027-06-26 | 2027-06-26 | 12 hrs | FY27 | 12 | 90019351 | B1 | 1000269581 | 26.06.2027 | 3500 | CCK-MP-GRDR-GR014 -STRUCT-CABIN-AIRCN | 3200 | 44181 | 8479
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Sepura SCC Microphone | 2027-06-27 | 2027-06-27 | 0.5 hrs | FY27 | 0.5 | 90028989 | B1 | 1000289370 | 27.06.2027 | 12 Monthly | CCK-MP-GRDR-GR012 -COMMUN-RADIO | 5200 | 72353 | 72353
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 12 Monthly Hydraulic Tune Up | 2027-06-27 | 2027-06-27 | 12 hrs | FY27 | 24 | 90015111 | B1 | 1000266797 | 27.06.2027 | 52 Weekly | CCK-MP-LOAD-WL021 -HYDSYS
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Operators Seat | 2027-06-28 | 2027-06-28 | 4 hrs | FY27 | 4 | 90002741 | B2 | 1000090405 | 28.06.2027 | 7000 | CCK-MP-LOAD-WL267 -STRUCT-CABIN-SEATS | 6000 | 74441 | 1115
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Gearbox Pump Drive Front | 2027-06-29 | 2027-06-30 | 38 hrs | FY27 | 74 | 90002705 | B2 | 1000090377 | 29.06.2027 | 16000 | CCK-MP-LOAD-WL267 -TRNSYS-PMPDR-FRPDR | 6000 | 74441 | 10237
| Onsite PM | Ancillary | Fortescue |  | FY28 - ANCILLARY - COMPONENTS DURING PM | 2027-07-01 | 2028-06-30 |  | FY28
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Actuator Brake HaulX Shield | 2027-07-01 | 2027-07-02 | 26 hrs | FY28 | 50 | 90033499 | B1 | 1000337796 | 01.07.2027 | 14000 | CCK-MP-DOZR-DZ8235-MANGMT-CASYS-ACTBK
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Replace Articulation Area Hosing | 2027-07-01 | 2027-07-01 | 6 hrs | FY28 | 6 | 90022236 | B1 | 1000257062 | 01.07.2027 | 8 Monthly | CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Final Drive Position 2 | 2027-07-03 | 2027-07-05 | 44 hrs | FY28 | 83 | 90002710 | B2 | 1000090235 | 03.07.2027 | 16000 | CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR02 | 6000 | 75558 | 528
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Actuator Brake HaulX Shield | 2027-07-05 | 2027-07-06 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337800 | 05.07.2027 | 14000 | CCK-MP-DOZR-DZ170 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Replace Artic Area Hyd Hosing | 2027-07-08 | 2027-07-08 | 6 hrs | FY28 | 6 | 90020831 | B1 | 1000220494 | 08.07.2027 | 8 Monthly | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-ARTHO
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Operators Seat | 2027-07-09 | 2027-07-09 | 2 hrs | FY28 | 2 | 90002797 | B2 | 1000087675 | 09.07.2027 | 6000 | CCK-MP-LOAD-WL017 -STRUCT-CABIN-SEATS | 3100 | 56923 | 9177
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Overhaul Park Brake & Centre Brg | 2027-07-11 | 2027-07-12 | 18 hrs | FY28 | 36 | 90002711 | B2 | 1000090269 | 11.07.2027 | 10000 | CCK-MP-LOAD-WL260 -BRKSYS-BRPRK | 6000 | 75566 | 4503
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Operators Seat | 2027-07-11 | 2027-07-11 | 2 hrs | FY28 | 4 | 90002975 | B2 | 1000228702 | 11.07.2027 | 7000 | CCK-MP-DOZR-WD201 -STRUCT-CABIN-SEATS | 6300 | 81082 | 1968
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Engine Midlife Complete | 2027-07-11 | 2027-07-14 | 71 hrs | FY28 | 103 | 90015859 | B1 | 1000159534 | 11.07.2027 | 9000 | CCK-MP-DOZR-DZ014 -ENGINE | 5000 | 64687 | 3801
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Major Service Air Conditioner | 2027-07-11 | 2027-07-12 | 24 hrs | FY28 | 24 | 90017469 | B1 | 1000160669 | 11.07.2027 | 9000 | CCK-MP-DOZR-DZ014 -STRUCT-CABIN-AIRCN | 5000 | 64687 | 16308
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Cyl Steering LH | 2027-07-15 | 2027-07-15 | 12 hrs | FY28 | 22 | 90002781 | B2 | 1000030645 | 15.07.2027 | 16000 | CCK-MP-LOAD-WL017 -STRSYS-STRCY-STCYL | 3100 | 56923 | 12822
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Sepura SCC Microphone | 2027-07-16 | 2027-07-16 | 0.5 hrs | FY28 | 0.5 | 90028996 | B1 | 1000289582 | 16.07.2027 | 12 Monthly | CCK-MP-DOZR-WD201 -COMMUN-RADIO | 6300 | 81082 | 81082
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Cyl Steering RH | 2027-07-17 | 2027-07-17 | 12 hrs | FY28 | 22 | 90002781 | B2 | 1000030646 | 17.07.2027 | 16000 | CCK-MP-LOAD-WL017 -STRSYS-STRCY-STCYR | 3100 | 56923 | 12798
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Hyd Oil Cooler | 2027-07-17 | 2027-07-17 | 3 hrs | FY28 | 6 | 90002792 | B2 | 1000030653 | 17.07.2027 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HDOCO | 3100 | 56923 | 12798
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Cyl Blade Lift RH | 2027-07-17 | 2027-07-17 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255599 | 17.07.2027 | 9000 | CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BLCYR | 5000 | 54263 | 4295
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Sepura SCC Microphone | 2027-07-18 | 2027-07-18 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289598 | 18.07.2027 | 12 Monthly | CCK-MP-LOAD-WL260 -COMMUN-RADIO | 6000 | 75558 | 75558
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Hyd Pump Implement | 2027-07-20 | 2027-07-20 | 12 hrs | FY28 | 24 | 90002782 | B2 | 1000030647 | 20.07.2027 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP01 | 3100 | 56923 | 12774
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Pump Hyd Impliment Tandem | 2027-07-20 | 2027-07-20 | 12 hrs | FY28 | 24 | 90005123 | B2 | 1000054238 | 20.07.2027 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP06 | 3100 | 56923 | 12774
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Sepura SCC Microphone | 2027-07-23 | 2027-07-23 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289604 | 23.07.2027 | 12 Monthly | CCK-MP-LOAD-WL269 -COMMUN-RADIO | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Replace Artic Area Hyd Hosing | 2027-07-23 | 2027-07-23 | 6 hrs | FY28 | 6 | 90020831 | B1 | 1000220507 | 23.07.2027 | 8 Monthly | CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-ARTHO
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Sepura SCC Microphone | 2027-07-26 | 2027-07-26 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289552 | 26.07.2027 | 12 Monthly | CCK-MP-DOZR-DZ178 -COMMUN-RADIO | 5000 | 54741 | 3721
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Operators Seat | 2027-07-27 | 2027-07-27 | 4 hrs | FY28 | 4 | 90002741 | B2 | 1000138181 | 27.07.2027 | 7000 | CCK-MP-LOAD-WL7103-STRUCT-CABIN-SEATS | 6000 | 72865 | 1168
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Replace Hydraulic Hoses | 2027-07-29 | 2027-07-31 | 48 hrs | FY28 | 96 | 90010152 | B1 | 1000081968 | 29.07.2027 | 16000 | CCK-MP-LOAD-WL017 -HYDSYS-HDHLF-HYDHO | 3100 | 56923 | 12702
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Air Conditioning Service | 2027-07-30 | 2027-07-31 | 24 hrs | FY28 | 24 | 90017478 | B1 | 1000291903 | 30.07.2027 | 4000 | CCK-MP-LOAD-WL017 -STRUCT-CABIN-AIRCN | 3100 | 56923 | 7866
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Fr Pump Drv Shaft Unis | 2027-07-31 | 2027-07-31 | 4 hrs | FY28 | 8 | 90033190 | B1 | 1000333562 | 31.07.2027 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT06 | 6000 | 74583 | 4006
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Sepura SCC Microphone | 2027-08-03 | 2027-08-03 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289570 | 03.08.2027 | 12 Monthly | CCK-MP-DOZR-DZ8235-COMMUN-RADIO
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Sepura SCC Microphone | 2027-08-06 | 2027-08-06 | 0.5 hrs | FY28 | 0.5 | 90028997 | B1 | 1000289594 | 06.08.2027 | 12 Monthly | CCK-MP-LOAD-WL017 -COMMUN-RADIO
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Shaft TConverter to Trans | 2027-08-06 | 2027-08-06 | 2 hrs | FY28 | 4 | 90002947 | B3 | 1000268446 | 06.08.2027 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT01 | 6300 | 79903 | 21666
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Operators Seat | 2027-08-08 | 2027-08-08 | 4 hrs | FY28 | 4 | 90002741 | B2 | 1000028906 | 08.08.2027 | 7000 | CCK-MP-LOAD-WL022 -STRUCT-CABIN-SEATS | 6000 | 80515 | 395
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Actuator Brake HaulX Shield | 2027-08-09 | 2027-08-10 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337804 | 09.08.2027 | 14000 | CCK-MP-DOZR-DZ176 -MANGMT-CASYS-ACTBK
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Engine Midlife complete | 2027-08-11 | 2027-08-13 | 60 hrs | FY28 | 72 | 90015782 | B1 | 1000290309 | 11.08.2027 | 7000 | CCK-MP-GRDR-GR122 -ENGINE | 5200 | 68036 | 1754
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Service Major Air Conditioner | 2027-08-11 | 2027-08-12 | 24 hrs | FY28 | 24 | 90017472 | B1 | 1000290313 | 11.08.2027 | 7000 | CCK-MP-GRDR-GR122 -STRUCT-CABIN-AIRCN | 5200 | 68036 | 15776
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Cyl Steering RH | 2027-08-15 | 2027-08-15 | 14 hrs | FY28 | 28 | 90002722 | B2 | 1000090248 | 15.08.2027 | 12000 | CCK-MP-LOAD-WL260 -STRSYS-STRCY-STCYR | 6000 | 75558 | 5908
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Sepura SCC Microphone | 2027-08-17 | 2027-08-17 | 0.5 hrs | FY28 | 0.5 | 90028989 | B1 | 1000289373 | 17.08.2027 | 12 Monthly | CCK-MP-GRDR-GR122 -COMMUN-RADIO | 5200 | 68036 | 68036
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pump Implement RH | 2027-08-18 | 2027-08-18 | 12 hrs | FY28 | 24 | 90002724 | B2 | 1000028829 | 18.08.2027 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP02 | 6000 | 79974 | 3457
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Thermostats | 2027-08-18 | 2027-08-18 | 6 hrs | FY28 | 6 | 90021139 | B1 | 1000222686 | 18.08.2027 | 5000 | CCK-MP-LOAD-WL269 -ENGINE-COSYS-THERM | 6000 | 74583 | 8436
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Service Air Conditioner | 2027-08-18 | 2027-08-19 | 24 hrs | FY28 | 24 | 90021130 | B1 | 1000222676 | 18.08.2027 | 5000 | CCK-MP-LOAD-WL269 -STRUCT-CABIN-AIRCN | 6000 | 74583 | 16942
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Minor Service Air Conditioner | 2027-08-18 | 2027-08-18 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000196658 | 18.08.2027 | 4500 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN-AIRCN | 5000 | 67674 | 8628
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Final Drive Position 3 | 2027-08-21 | 2027-08-23 | 44 hrs | FY28 | 83 | 90002710 | B2 | 1000090532 | 21.08.2027 | 16000 | CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR03 | 6000 | 74596 | 9638
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Engine Midlife complete | 2027-08-21 | 2027-08-23 | 63 hrs | FY28 | 84 | 90015811 | B1 | 1000286604 | 21.08.2027 | 11000 | CCK-MP-DOZR-WD201 -ENGINE | 6300 | 81082 | 4550
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Overhaul Airconditioner | 2027-08-21 | 2027-08-23 | 48 hrs | FY28 | 48 | 90013087 | B1 | 1000286606 | 21.08.2027 | 11000 | CCK-MP-DOZR-WD201 -STRUCT-CABIN-AIRCN | 6300 | 81082 | 12720
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Final Drive Position 3 | 2027-08-22 | 2027-08-24 | 44 hrs | FY28 | 83 | 90002710 | B2 | 1000090236 | 22.08.2027 | 16000 | CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR03 | 6000 | 75558 | 9814
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Steering LH | 2027-08-22 | 2027-08-22 | 14 hrs | FY28 | 26 | 90002721 | B2 | 1000090543 | 22.08.2027 | 12000 | CCK-MP-LOAD-WL269 -STRSYS-STRCY-STCYL | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Steering RH | 2027-08-22 | 2027-08-22 | 14 hrs | FY28 | 28 | 90002722 | B2 | 1000090544 | 22.08.2027 | 12000 | CCK-MP-LOAD-WL269 -STRSYS-STRCY-STCYR | 6000 | 74583 | 5623
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Adjust 250hr Initial Valve Set | 2027-08-24 | 2027-08-24 | 6 hrs | FY28 | 12 | 90015780 | B1 | 1000290262 | 24.08.2027 | 250 | CCK-MP-GRDR-GR120 -ENGINE | 5200 | 60265 | 8767
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Minor Service Air Conditioner | 2027-08-24 | 2027-08-24 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000196609 | 24.08.2027 | 4500 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN-AIRCN | 5000 | 62015 | 8044
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Engine Midlife Complete | 2027-08-24 | 2027-08-27 | 71 hrs | FY28 | 103 | 90015859 | B1 | 1000160217 | 24.08.2027 | 9000 | CCK-MP-DOZR-DZ178 -ENGINE | 5000 | 54752 | 3721
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Major Service Air Conditioner | 2027-08-24 | 2027-08-25 | 24 hrs | FY28 | 24 | 90017469 | B1 | 1000196641 | 24.08.2027 | 9000 | CCK-MP-DOZR-DZ178 -STRUCT-CABIN-AIRCN | 5000 | 54741 | 3721
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Operators Seat | 2027-08-25 | 2027-08-25 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000108415 | 25.08.2027 | 6000 | CCK-MP-DOZR-DZ172 -STRUCT-CABIN-SEATS | 5000 | 68264 | 6824
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Drive Shaft Unis | 2027-08-25 | 2027-08-25 | 3 hrs | FY28 | 6 | 90033292 | B1 | 1000334116 | 25.08.2027 | 9000 | CCK-MP-DOZR-DZ178 -TRNSYS | 5000 | 54741 | 3721
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Hyd Pump Implement | 2027-08-25 | 2027-08-25 | 10 hrs | FY28 | 10 | 90000301 | B2 | 1000088973 | 25.08.2027 | 9000 | CCK-MP-DOZR-DZ178 -HYDSYS-HYDPP-HYIPP | 5000 | 54741 | 3721
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Cyl Blade Lift LH | 2027-08-25 | 2027-08-25 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255654 | 25.08.2027 | 9000 | CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-BLCYL | 5000 | 54741 | 3721
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Cyl Blade Lift LH | 2027-08-25 | 2027-08-25 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255670 | 25.08.2027 | 9000 | CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BLCYL | 5000 | 63195 | 3729
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Cyl Blade Lift RH | 2027-08-25 | 2027-08-25 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255671 | 25.08.2027 | 9000 | CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BLCYR | 5000 | 63195 | 3729
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 6M Anritsu Test Wifi Cables | 2027-08-25 | 2027-08-25 | 2 hrs | FY28 | 2 | 90019046 | B2 | 1000257061 | 25.08.2027 | 6 Monthly | CCK-MP-LOAD-WL7162-COMMUN-FLMGT
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Sepura SCC Microphone | 2027-08-26 | 2027-08-26 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289557 | 26.08.2027 | 12 Monthly | CCK-MP-DOZR-DZ183 -COMMUN-RADIO | 5000 | 65807 | 65807
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Actuator Brake HaulX Shield | 2027-08-27 | 2027-08-28 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337803 | 27.08.2027 | 14000 | CCK-MP-DOZR-DZ175 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Thermostats | 2027-08-28 | 2027-08-28 | 6 hrs | FY28 | 6 | 90021139 | B1 | 1000222642 | 28.08.2027 | 5000 | CCK-MP-LOAD-WL267 -ENGINE-COSYS-THERM | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Service Air Conditioner | 2027-08-28 | 2027-08-29 | 24 hrs | FY28 | 24 | 90021130 | B1 | 1000222632 | 28.08.2027 | 5000 | CCK-MP-LOAD-WL267 -STRUCT-CABIN-AIRCN | 6000 | 74441 | 8258
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Actuator Brake HaulX Shield | 2027-08-28 | 2027-08-29 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337806 | 28.08.2027 | 14000 | CCK-MP-DOZR-DZ180 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Sepura SCC Microphone | 2027-08-29 | 2027-08-29 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000364484 | 29.08.2027 | 12 Monthly | CCK-MP-LOAD-WL7104-COMMUN-RADIO
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Hyd Pump Implement | 2027-08-30 | 2027-08-30 | 8 hrs | FY28 | 8 | 90002646 | B2 | 1000090916 | 30.08.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-HYIMP | 5200 | 68036 | 8511
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Hyd Pump Steering Main | 2027-08-30 | 2027-08-30 | 8 hrs | FY28 | 8 | 90002647 | B2 | 1000090917 | 30.08.2027 | 14000 | CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-HYSTP | 5200 | 68036 | 8511
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Actuator Brake HaulX Shield | 2027-08-30 | 2027-08-31 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337799 | 30.08.2027 | 14000 | CCK-MP-DOZR-DZ169 -MANGMT-CASYS-ACTBK
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Shaft Trans to Ctr Bearing | 2027-08-31 | 2027-08-31 | 4 hrs | FY28 | 8 | 90002764 | B2 | 1000030463 | 31.08.2027 | 12000 | CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT03 | 3100 | 64003 | 8684
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Sepura SCC Microphone | 2027-08-31 | 2027-08-31 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289554 | 31.08.2027 | 12 Monthly | CCK-MP-DOZR-DZ180 -COMMUN-RADIO | 5000 | 63195 | 63195
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Minor Overhaul Track Frame LH | 2027-09-03 | 2027-09-05 | 50 hrs | FY28 | 98 | 90002098 | B1 | 1000108517 | 03.09.2027 | 18000 | CCK-MP-DOZR-DZ180 -STRUCT-UNDER-TKFRL | 5000 | 63195 | 12632
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Minor Overhaul Track Frame RH | 2027-09-03 | 2027-09-05 | 50 hrs | FY28 | 98 | 90010766 | B1 | 1000108519 | 03.09.2027 | 18000 | CCK-MP-DOZR-DZ180 -STRUCT-UNDER-TKFRR | 5000 | 63195 | 12632
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Sepura SCC Microphone | 2027-09-03 | 2027-09-03 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289569 | 03.09.2027 | 12 Monthly | CCK-MP-DOZR-DZ8234-COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Sepura SCC Microphone | 2027-09-09 | 2027-09-09 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289550 | 09.09.2027 | 12 Monthly | CCK-MP-DOZR-DZ175 -COMMUN-RADIO | 5000 | 71827 | 4957
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Gearbox Circle Drive Rear | 2027-09-12 | 2027-09-12 | 8 hrs | FY28 | 14 | 90011066 | B2 | 1000105639 | 12.09.2027 | 14000 | CCK-MP-GRDR-GR123 -STRUCT-CIRCL-CDBXR | 5200 | 50884 | 7795
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Sepura SCC Microphone | 2027-09-12 | 2027-09-12 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289610 | 12.09.2027 | 12 Monthly | CCK-MP-LOAD-WL7162-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Sepura SCC Microphone | 2027-09-13 | 2027-09-13 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289602 | 13.09.2027 | 12 Monthly | CCK-MP-LOAD-WL267 -COMMUN-RADIO | 6000 | 74441 | 74441
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Sepura SCC Microphone | 2027-09-14 | 2027-09-14 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289599 | 14.09.2027 | 12 Monthly | CCK-MP-LOAD-WL261 -COMMUN-RADIO | 6000 | 77065 | 11736
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Minor Service Air Conditioner | 2027-09-14 | 2027-09-14 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000196646 | 14.09.2027 | 4500 | CCK-MP-DOZR-DZ180 -STRUCT-CABIN-AIRCN | 5000 | 63195 | 7626
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Actuator Brake HaulX Shield | 2027-09-14 | 2027-09-15 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337795 | 14.09.2027 | 14000 | CCK-MP-DOZR-DZ184 -MANGMT-CASYS-ACTBK
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Sepura SCC Microphone | 2027-09-15 | 2027-09-15 | 0.5 hrs | FY28 | 0.5 | 90028996 | B1 | 1000289583 | 15.09.2027 | 12 Monthly | CCK-MP-DOZR-WD202 -COMMUN-RADIO | 6300 | 79903 | 79903
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Adjust 250hr Initial Valve Set | 2027-09-15 | 2027-09-15 | 12 hrs | FY28 | 24 | 90021246 | B1 | 1000222738 | 15.09.2027 | 250 | CCK-MP-LOAD-WL7103-ENGINE | 6000 | 72865 | 2571
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 500hr Initial Valve Set | 2027-09-20 | 2027-09-20 | 6 hrs | FY28 | 12 | 90015809 | B1 | 1000286623 | 20.09.2027 | 500 | CCK-MP-DOZR-WD204 -ENGINE | 6300 | 83628 | 15298
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Repl Sepura SCC Microphone | 2027-09-24 | 2027-09-24 | 0.5 hrs | FY28 | 0.5 | 90028989 | B1 | 1000289372 | 24.09.2027 | 12 Monthly | CCK-MP-GRDR-GR121 -COMMUN-RADIO | 5200 | 67029 | 67029
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Cyl Blade Lift LH | 2027-09-24 | 2027-09-24 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255638 | 24.09.2027 | 9000 | CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-BLCYL | 5000 | 71802 | 3554
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Sepura SCC Microphone | 2027-09-26 | 2027-09-26 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289596 | 26.09.2027 | 12 Monthly | CCK-MP-LOAD-WL022 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Operators Seat | 2027-09-27 | 2027-09-27 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000108451 | 27.09.2027 | 6000 | CCK-MP-DOZR-DZ175 -STRUCT-CABIN-SEATS | 5000 | 71802 | 6554
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Actuator Brake HaulX Shield | 2027-09-30 | 2027-10-01 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337801 | 30.09.2027 | 14000 | CCK-MP-DOZR-DZ172 -MANGMT-CASYS-ACTBK
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Fan Cooling Motor Hyd | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 16 | 90002094 | B2 | 1000108450 | 30.09.2027 | 9000 | CCK-MP-DOZR-DZ175 -HYDSYS-HDCFM | 5000 | 71802 | 1271
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Minor Service Air Conditioner | 2027-09-30 | 2027-09-30 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000196634 | 30.09.2027 | 4500 | CCK-MP-DOZR-DZ176 -STRUCT-CABIN-AIRCN | 5000 | 69680 | 16621
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Cyl Blade Lift LH | 2027-10-04 | 2027-10-04 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255702 | 04.10.2027 | 9000 | CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-BLCYL | 5000 | 67674 | 3474
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Fan Cooling Motor Hyd | 2027-10-05 | 2027-10-05 | 8 hrs | FY28 | 16 | 90002094 | B2 | 1000108378 | 05.10.2027 | 9000 | CCK-MP-DOZR-DZ169 -HYDSYS-HDCFM | 5000 | 62015 | 293
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Operators Seat | 2027-10-05 | 2027-10-05 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000108379 | 05.10.2027 | 6000 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN-SEATS | 5000 | 62015 | 11979
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Sepura SCC Microphone | 2027-10-07 | 2027-10-07 | 0.5 hrs | FY28 | 0.5 | 90028989 | B1 | 1000289374 | 07.10.2027 | 12 Monthly | CCK-MP-GRDR-GR123 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Adjust Engine 500hr Valve Set | 2027-10-08 | 2027-10-08 | 8 hrs | FY28 | 16 | 90015857 | B1 | 1000160167 | 08.10.2027 | 500 | CCK-MP-DOZR-DZ174 -ENGINE | 5000 | 65414 | 12899
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Equaliser Bar | 2027-10-24 | 2027-10-26 | 55 hrs | FY28 | 110 | 90002097 | B1 | 1000108564 | 24.10.2027 | 18000 | CCK-MP-DOZR-DZ184 -STRUCT-CHASS-EQUAL | 5000 | 67674 | 12208
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Final Drive Position 3 | 2027-10-28 | 2027-10-30 | 44 hrs | FY28 | 83 | 90002710 | B2 | 1000090384 | 28.10.2027 | 16000 | CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR03 | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Final Drive Position 4 | 2027-10-28 | 2027-10-30 | 44 hrs | FY28 | 83 | 90002710 | B2 | 1000090385 | 28.10.2027 | 16000 | CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR04 | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Transmission | 2027-10-28 | 2027-10-29 | 38 hrs | FY28 | 74 | 90002692 | B2 | 1000090365 | 28.10.2027 | 16000 | CCK-MP-LOAD-WL267 -TRNSYS-TRANS | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Transmission System Hoses | 2027-10-28 | 2027-10-30 | 48 hrs | FY28 | 96 | 90026923 | B1 | 1000271607 | 28.10.2027 | 16000 | CCK-MP-LOAD-WL267 -TRNSYS-TRHLF-TRNHO | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Brake Cooling | 2027-10-29 | 2027-10-29 | 8 hrs | FY28 | 8 | 90002713 | B2 | 1000028882 | 29.10.2027 | 10000 | CCK-MP-LOAD-WL022 -BRKSYS-BRPMP-BRP02 | 6000 | 80515 | 1155
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Fan Cooling Motor Hyd | 2027-11-04 | 2027-11-04 | 8 hrs | FY28 | 16 | 90002094 | B2 | 1000108558 | 04.11.2027 | 9000 | CCK-MP-DOZR-DZ184 -HYDSYS-HDCFM | 5000 | 67674 | 3050
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Sepura SCC Microphone | 2027-11-07 | 2027-11-07 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000289595 | 07.11.2027 | 12 Monthly | CCK-MP-LOAD-WL021 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Sepura SCC Microphone | 2027-11-08 | 2027-11-08 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289551 | 08.11.2027 | 12 Monthly | CCK-MP-DOZR-DZ176 -COMMUN-RADIO | 5000 | 69693 | 69693
16M | Onsite PM | Ancillary | Fortescue | GR015 | GR015 Repl Sepura SCC Microphone | 2027-11-11 | 2027-11-11 | 0.5 hrs | FY28 | 0.5 | 90028988 | B1 | 1000289365 | 11.11.2027 | 12 Monthly | CCK-MP-GRDR-GR015 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Replace Artic Area Hyd Hosing | 2027-11-17 | 2027-11-17 | 6 hrs | FY28 | 6 | 90020831 | B1 | 1000220496 | 17.11.2027 | 8 Monthly | CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-ARTHO
16M | Onsite PM | Ancillary | Fortescue | GR014 | GR014 Repl Sepura SCC Microphone | 2027-11-17 | 2027-11-17 | 0.5 hrs | FY28 | 0.5 | 90028988 | B1 | 1000289364 | 17.11.2027 | 12 Monthly | CCK-MP-GRDR-GR014 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Lift RH High Lift | 2027-11-21 | 2027-11-22 | 24 hrs | FY28 | 48 | 90002727 | B2 | 1000112688 | 21.11.2027 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-HCYLR | 6000 | 74441 | 1831
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Sepura SCC Microphone | 2027-11-22 | 2027-11-22 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289558 | 22.11.2027 | 12 Monthly | CCK-MP-DOZR-DZ184 -COMMUN-RADIO | 5000 | 67674 | 8628
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hyd & Steering Oil Cooler | 2027-11-26 | 2027-11-26 | 12 hrs | FY28 | 24 | 90010218 | B3 | 1000092692 | 26.11.2027 | 22000 | CCK-MP-DOZR-WD203 -HYDSYS-HDOCO | 6300 | 80875 | 13604
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Adjust 250hr Initial Valve Set | 2027-11-28 | 2027-11-28 | 12 hrs | FY28 | 24 | 90021246 | B1 | 1000222606 | 28.11.2027 | 250 | CCK-MP-LOAD-WL266 -ENGINE | 6000 | 74342 | 12308
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Adjust Engine 500hr Valve Set | 2027-11-28 | 2027-11-28 | 8 hrs | FY28 | 16 | 90015857 | B1 | 1000160251 | 28.11.2027 | 500 | CCK-MP-DOZR-DZ181 -ENGINE | 5000 | 66297 | 12007
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Engine Midlife complete | 2027-11-29 | 2027-12-01 | 60 hrs | FY28 | 72 | 90015782 | B1 | 1000290214 | 29.11.2027 | 7000 | CCK-MP-GRDR-GR012 -ENGINE | 5200 | 72353 | 348
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Service Major Air Conditioner | 2027-11-29 | 2027-11-30 | 24 hrs | FY28 | 24 | 90017472 | B1 | 1000290218 | 29.11.2027 | 7000 | CCK-MP-GRDR-GR012 -STRUCT-CABIN-AIRCN | 5200 | 72353 | 12098
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Rear Axle Assembly | 2027-12-03 | 2027-12-05 | 64 hrs | FY28 | 128 | 90030396 | B1 | 1000303434 | 03.12.2027 | 14000 | CCK-MP-GRDR-GR012 -FDRSYS-DIFFL | 5200 | 72353 | 6847
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Operators Seat | 2027-12-05 | 2027-12-05 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000108391 | 05.12.2027 | 6000 | CCK-MP-DOZR-DZ170 -STRUCT-CABIN-SEATS | 5000 | 54263 | 5339
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Cyl Lift LH Lift | 2027-12-05 | 2027-12-06 | 20 hrs | FY28 | 60 | 90016385 | B1 | 1000257045 | 05.12.2027 | 10000 | CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-HCYLL | 6100 | 25829 | 2179
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Sepura SCC Microphone | 2027-12-07 | 2027-12-07 | 0.5 hrs | FY28 | 0.5 | 90028997 | B1 | 1000289593 | 07.12.2027 | 12 Monthly | CCK-MP-LOAD-WL004 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Adjust Engine 500hr Valve Set | 2027-12-10 | 2027-12-10 | 8 hrs | FY28 | 16 | 90015857 | B1 | 1000160155 | 10.12.2027 | 500 | CCK-MP-DOZR-DZ173 -ENGINE | 5000 | 68788 | 11848
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Minor Service Air Conditioner | 2027-12-12 | 2027-12-12 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000196622 | 12.12.2027 | 4500 | CCK-MP-DOZR-DZ172 -STRUCT-CABIN-AIRCN | 5000 | 68264 | 6824
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Replace Artic Area Hyd Hosing | 2027-12-14 | 2027-12-14 | 6 hrs | FY28 | 6 | 90020831 | B1 | 1000220503 | 14.12.2027 | 8 Monthly | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-ARTHO
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Sepura SCC Microphone | 2027-12-14 | 2027-12-14 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289545 | 14.12.2027 | 12 Monthly | CCK-MP-DOZR-DZ170 -COMMUN-RADIO | 5000 | 54263 | 54263
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Operators Seat | 2027-12-16 | 2027-12-16 | 4 hrs | FY28 | 4 | 90002663 | B2 | 1000028433 | 16.12.2027 | 7000 | CCK-MP-GRDR-GR012 -STRUCT-CABIN-SEATS | 5200 | 72353 | 15438
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Service Brake LHF | 2027-12-19 | 2027-12-20 | 26 hrs | FY28 | 52 | 90002640 | B2 | 1000105593 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -BRKSYS-SRVBK-SVBLF | 5200 | 50884 | 6392
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Aftercooler Engine | 2027-12-19 | 2027-12-19 | 12 hrs | FY28 | 24 | 90002623 | B2 | 1000105666 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -ENGINE-INTEX-AFTER | 5200 | 50884 | 6392
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Drive Shaft Trans to Rr Diff | 2027-12-19 | 2027-12-19 | 3 hrs | FY28 | 6 | 90033262 | B1 | 1000333916 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -FDRSYS-DRSHT-SHT01 | 5200 | 50884 | 6392
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Drive Shaft TCon to Trans | 2027-12-19 | 2027-12-19 | 4 hrs | FY28 | 4 | 90033265 | B1 | 1000333918 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -FDRSYS-DRSHT-SHT02 | 5200 | 50884 | 6392
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Overhaul Auto Lubrication System | 2027-12-19 | 2027-12-19 | 2 hrs | FY28 | 2 | 90002660 | B2 | 1000105630 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -GRSYST-ALBPP
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Power Train System Hoses | 2027-12-19 | 2027-12-20 | 24 hrs | FY28 | 48 | 90009999 | B2 | 1000105664 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HDHLF-PWTRN | 5200 | 50884 | 6392
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Hyd Fan Motor | 2027-12-19 | 2027-12-19 | 6 hrs | FY28 | 6 | 90002651 | B2 | 1000105629 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HDMOT-MOT03 | 5200 | 50884 | 6392
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Hyd Pump Implement | 2027-12-19 | 2027-12-19 | 8 hrs | FY28 | 8 | 90002646 | B2 | 1000105623 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-HYIMP | 5200 | 50884 | 6392
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Hyd Pump Secondary Steering | 2027-12-19 | 2027-12-19 | 6 hrs | FY28 | 6 | 90002645 | B2 | 1000105622 | 19.12.2027 | 14000 | CCK-MP-GRDR-GR123 -STRSYS-STEMG-SESPP | 5200 | 50884 | 6392
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Air Conditioning Service | 2027-12-21 | 2027-12-22 | 24 hrs | FY28 | 24 | 90017478 | B1 | 1000291754 | 21.12.2027 | 4000 | CCK-MP-LOAD-WL004 -STRUCT-CABIN-AIRCN | 3100 | 64003 | 8684
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Lube Oil Cooler Front Axle | 2027-12-21 | 2027-12-21 | 3 hrs | FY28 | 6 | 90002770 | B2 | 1000030469 | 21.12.2027 | 20000 | CCK-MP-LOAD-WL004 -FDRSYS-HDOCA-HYOCF | 3100 | 64003 | 15676
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Shaft TConverter to Trans | 2027-12-21 | 2027-12-21 | 2 hrs | FY28 | 4 | 90002947 | B3 | 1000268454 | 21.12.2027 | 22000 | CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT01 | 6300 | 80875 | 13604
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Replace Shaft Trans to Rear Diff | 2027-12-21 | 2027-12-21 | 4 hrs | FY28 | 8 | 90002948 | B3 | 1000268456 | 21.12.2027 | 22000 | CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT02 | 6300 | 80875 | 13604
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Shaft Trans to Cntr Bearing | 2027-12-21 | 2027-12-21 | 4 hrs | FY28 | 8 | 90002949 | B3 | 1000268458 | 21.12.2027 | 22000 | CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT03 | 6300 | 80875 | 13604
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Torque Converter | 2027-12-22 | 2027-12-23 | 30 hrs | FY28 | 60 | 90000309 | B2 | 1000091262 | 22.12.2027 | 18000 | CCK-MP-DOZR-DZ180 -TRNSYS-TRQUE | 5000 | 63195 | 11095
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Equaliser Bar | 2027-12-24 | 2027-12-26 | 55 hrs | FY28 | 110 | 90002097 | B1 | 1000108468 | 24.12.2027 | 18000 | CCK-MP-DOZR-DZ176 -STRUCT-CHASS-EQUAL | 5000 | 69680 | 10953
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Minor Service Air Conditioner | 2027-12-29 | 2027-12-29 | 12 hrs | FY28 | 12 | 90019636 | B1 | 1000201880 | 29.12.2027 | 3500 | CCK-MP-GRDR-GR7107-STRUCT-CABIN-AIRCN | 5500 | 24399 | 9687
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Cyl Blade Lift RH | 2027-12-30 | 2027-12-30 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255655 | 30.12.2027 | 9000 | CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-BLCYR | 5000 | 54741 | 1969
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Operators Seat | 2028-01-01 | 2028-01-01 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000108559 | 01.01.2028 | 6000 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN-SEATS | 5000 | 67674 | 5213
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-01-09 | 2028-01-09 | 4 hrs | FY28 | 8 | 90033193 | B1 | 1000333536 | 09.01.2028 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT05 | 6000 | 74441 | 10237
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Fr Pump Drv Shaft Unis | 2028-01-09 | 2028-01-09 | 4 hrs | FY28 | 8 | 90033190 | B1 | 1000333538 | 09.01.2028 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT06 | 6000 | 74441 | 10237
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Repl Hyd Pump Brake & Fan | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 8 | 90002648 | B2 | 1000105625 | 12.01.2028 | 14000 | CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-FANPP | 5200 | 50884 | 6039
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Bucket Cyl Tilt RH | 2028-01-13 | 2028-01-13 | 14 hrs | FY28 | 28 | 90002789 | B2 | 1000052495 | 13.01.2028 | 12000 | CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-BUCYR | 3100 | 56923 | 7268
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Service Minor Air Conditioner | 2028-01-15 | 2028-01-15 | 12 hrs | FY28 | 12 | 90019542 | B1 | 1000290305 | 15.01.2028 | 3500 | CCK-MP-GRDR-GR121 -STRUCT-CABIN-AIRCN | 5200 | 67029 | 10195
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Final Drive Position 3 | 2028-01-15 | 2028-01-16 | 22 hrs | FY28 | 58 | 90002954 | B3 | 1000092673 | 15.01.2028 | 22000 | CCK-MP-DOZR-WD203 -FDRSYS-FDRVE-FDR03 | 6300 | 80875 | 12738
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Thermostats | 2028-01-16 | 2028-01-16 | 6 hrs | FY28 | 6 | 90021139 | B1 | 1000222378 | 16.01.2028 | 5000 | CCK-MP-LOAD-WL022 -ENGINE-COSYS-THERM | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Service Air Conditioner | 2028-01-16 | 2028-01-17 | 24 hrs | FY28 | 24 | 90021130 | B1 | 1000222368 | 16.01.2028 | 5000 | CCK-MP-LOAD-WL022 -STRUCT-CABIN-AIRCN | 6000 | 80515 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Adjust 250hr Initial Valve Set | 2028-01-17 | 2028-01-17 | 12 hrs | FY28 | 24 | 90021246 | B1 | 1000222518 | 17.01.2028 | 250 | CCK-MP-LOAD-WL261 -ENGINE | 6000 | 77065 | 11736
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Cyl Steering RH | 2028-01-25 | 2028-01-25 | 12 hrs | FY28 | 22 | 90002961 | B3 | 1000092682 | 25.01.2028 | 22000 | CCK-MP-DOZR-WD203 -STRSYS-STRCY-STCYR | 6300 | 80875 | 12492
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Auto Lube Pump | 2028-01-26 | 2028-01-26 | 6 hrs | FY28 | 6 | 90002737 | B2 | 1000090404 | 26.01.2028 | 10000 | CCK-MP-LOAD-WL267 -GRSYST-ALBPP | 6000 | 74441 | 21055
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Transmission Charge Pump | 2028-01-26 | 2028-01-26 | 6 hrs | FY28 | 12 | 90002694 | B2 | 1000090366 | 26.01.2028 | 10000 | CCK-MP-LOAD-WL267 -TRNSYS-TRPMP | 6000 | 74441 | 21055
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Sepura SCC Microphone | 2028-01-27 | 2028-01-27 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289548 | 27.01.2028 | 12 Monthly | CCK-MP-DOZR-DZ173 -COMMUN-RADIO | 5000 | 68788 | 68788
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Actuator Brake HaulX Shield | 2028-01-27 | 2028-01-28 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000337805 | 27.01.2028 | 14000 | CCK-MP-DOZR-DZ178 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Front Differential | 2028-01-28 | 2028-01-30 | 58 hrs | FY28 | 114 | 90002707 | B2 | 1000090379 | 28.01.2028 | 20000 | CCK-MP-LOAD-WL267 -FDRSYS-FRDIF | 6000 | 74441 | 10738
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Lift LH High Lift | 2028-01-28 | 2028-01-29 | 24 hrs | FY28 | 48 | 90002727 | B2 | 1000112687 | 28.01.2028 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-HCYLL | 6000 | 74441 | 1113
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Pilot & Cooling | 2028-01-28 | 2028-01-28 | 6 hrs | FY28 | 12 | 90002726 | B2 | 1000090400 | 28.01.2028 | 10000 | CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP04 | 6000 | 74441 | 10738
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Cylinder Blade Lift RH | 2028-01-30 | 2028-01-30 | 6 hrs | FY28 | 12 | 90002966 | B1 | 1000228670 | 30.01.2028 | 22000 | CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BLCYR | 6300 | 81082 | 12747
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Sepura SCC Microphone | 2028-01-30 | 2028-01-30 | 0.5 hrs | FY28 | 0.5 | 90028996 | B1 | 1000289584 | 30.01.2028 | 12 Monthly | CCK-MP-DOZR-WD203 -COMMUN-RADIO | 6300 | 80875 | 80875
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Adjust Engine 500hr Valve Set | 2028-01-31 | 2028-01-31 | 8 hrs | FY28 | 16 | 90015857 | B1 | 1000160131 | 31.01.2028 | 500 | CCK-MP-DOZR-DZ171 -ENGINE | 5000 | 67979 | 11227
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Overhaul Auto Lubrication System | 2028-02-01 | 2028-02-03 | 48 hrs | FY28 | 96 | 90002971 | B3 | 1000092586 | 01.02.2028 | 22000 | CCK-MP-DOZR-WD201 -GRSYST | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hyd & Steering Oil Cooler | 2028-02-01 | 2028-02-01 | 12 hrs | FY28 | 24 | 90010218 | B3 | 1000092590 | 01.02.2028 | 22000 | CCK-MP-DOZR-WD201 -HYDSYS-HDOCO | 6300 | 81082 | 12720
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Service Minor Air Conditioner | 2028-02-03 | 2028-02-03 | 12 hrs | FY28 | 12 | 90019542 | B1 | 1000290320 | 03.02.2028 | 3500 | CCK-MP-GRDR-GR123 -STRUCT-CABIN-AIRCN
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Fan Cooling Motor Hyd | 2028-02-03 | 2028-02-03 | 8 hrs | FY28 | 16 | 90002094 | B2 | 1000108510 | 03.02.2028 | 9000 | CCK-MP-DOZR-DZ180 -HYDSYS-HDCFM | 5000 | 63195 | 1456
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Wheel Lean LH | 2028-02-07 | 2028-02-07 | 4 hrs | FY28 | 4 | 90021515 | B1 | 1000225890 | 07.02.2028 | 6000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYL | 5500 | 24399 | 3609
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Wheel Lean RH | 2028-02-07 | 2028-02-07 | 4 hrs | FY28 | 4 | 90021515 | B1 | 1000225891 | 07.02.2028 | 6000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYR | 5500 | 24399 | 3609
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Engine Midlife complete | 2028-02-07 | 2028-02-09 | 63 hrs | FY28 | 84 | 90015811 | B1 | 1000286618 | 07.02.2028 | 11000 | CCK-MP-DOZR-WD203 -ENGINE | 6300 | 80875 | 995
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Replace Shaft Universals Front | 2028-02-07 | 2028-02-07 | 3 hrs | FY28 | 6 | 90026667 | B1 | 1000268461 | 07.02.2028 | 11000 | CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT04 | 6300 | 80875 | 995
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Overhaul Airconditioner | 2028-02-07 | 2028-02-09 | 48 hrs | FY28 | 48 | 90013087 | B1 | 1000286620 | 07.02.2028 | 11000 | CCK-MP-DOZR-WD203 -STRUCT-CABIN-AIRCN | 6300 | 80875 | 13604
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Articulation RH | 2028-02-09 | 2028-02-09 | 4 hrs | FY28 | 4 | 90021512 | B1 | 1000225882 | 09.02.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYR | 5500 | 24399 | 9687
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Cylinder Blade Lift LH | 2028-02-10 | 2028-02-10 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255550 | 10.02.2028 | 9000 | CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BLCYL | 5000 | 64687 | 863
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Hyd Pump Implement | 2028-02-10 | 2028-02-10 | 10 hrs | FY28 | 10 | 90000301 | B2 | 1000020501 | 10.02.2028 | 9000 | CCK-MP-DOZR-DZ014 -HYDSYS-HYDPP-HYIPP | 5000 | 64687 | 862
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Replace Shaft Universals Centre | 2028-02-11 | 2028-02-11 | 3 hrs | FY28 | 6 | 90026668 | B1 | 1000268443 | 11.02.2028 | 11000 | CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT03 | 6300 | 81082 | 18673
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Brake Accumulator Front | 2028-02-13 | 2028-02-13 | 6 hrs | FY28 | 12 | 90002714 | B2 | 1000028884 | 13.02.2028 | 20000 | CCK-MP-LOAD-WL022 -BRKSYS-BRACC-BACCF | 6000 | 80515 | 10370
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Brake Accumulator Rear | 2028-02-13 | 2028-02-13 | 6 hrs | FY28 | 12 | 90002714 | B2 | 1000089005 | 13.02.2028 | 20000 | CCK-MP-LOAD-WL022 -BRKSYS-BRACC-BACCR | 6000 | 80515 | 10370
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Cylinder Blade Lift LH | 2028-02-20 | 2028-02-20 | 6 hrs | FY28 | 12 | 90002965 | B1 | 1000228673 | 20.02.2028 | 22000 | CCK-MP-DOZR-WD202 -HYDSYS-HDCYL-BLCYL | 6300 | 79903 | 11940
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Front Axle Assembly Midlife | 2028-02-21 | 2028-02-22 | 41 hrs | FY28 | 42 | 90025907 | B1 | 1000255881 | 21.02.2028 | 7000 | CCK-MP-GRDR-GR012 -STRUCT-AXLES | 5200 | 72353 | 348
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 6M Anritsu Test Wifi Cables | 2028-02-21 | 2028-02-21 | 2 hrs | FY28 | 2 | 90019046 | B2 | 1000257061 | 21.02.2028 | 6 Monthly | CCK-MP-LOAD-WL7162-COMMUN-FLMGT
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Sepura SCC Microphone | 2028-02-25 | 2028-02-25 | 0.5 hrs | FY28 | 0.5 | 90028989 | B1 | 1000289540 | 25.02.2028 | 12 Monthly | CCK-MP-GRDR-GR7107-COMMUN-RADIO
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Operators Seat | 2028-02-25 | 2028-02-25 | 2 hrs | FY28 | 4 | 90002975 | B2 | 1000228703 | 25.02.2028 | 7000 | CCK-MP-DOZR-WD202 -STRUCT-CABIN-SEATS | 6300 | 79903 | 3832
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Replace Articulation Area Hosing | 2028-02-26 | 2028-02-26 | 6 hrs | FY28 | 6 | 90022236 | B1 | 1000257062 | 26.02.2028 | 8 Monthly | CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-ARTHO
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Shaft TConverter to Trans | 2028-02-27 | 2028-02-27 | 2 hrs | FY28 | 4 | 90002947 | B3 | 1000268438 | 27.02.2028 | 22000 | CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT01 | 6300 | 81082 | 34277
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Replace Shaft Trans to Rear Diff | 2028-02-27 | 2028-02-27 | 4 hrs | FY28 | 8 | 90002948 | B3 | 1000268440 | 27.02.2028 | 22000 | CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT02 | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Shaft Centre Brg to Fr Diff | 2028-02-27 | 2028-02-27 | 4 hrs | FY28 | 8 | 90002950 | B3 | 1000268444 | 27.02.2028 | 22000 | CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT04 | 6300 | 81082 | 18673
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Overhaul Auto Lubrication System | 2028-02-28 | 2028-03-01 | 48 hrs | FY28 | 96 | 90002971 | B3 | 1000033598 | 28.02.2028 | 22000 | CCK-MP-DOZR-WD006 -GRSYST | 6300 | 69386 | 12336
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 500hr Initial Valve Set | 2028-02-29 | 2028-02-29 | 6 hrs | FY28 | 12 | 90015809 | B1 | 1000286595 | 29.02.2028 | 500 | CCK-MP-DOZR-WD007 -ENGINE | 6300 | 76513 | 12682
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Steer Clutch & Brake Assm LH | 2028-03-04 | 2028-03-04 | 14 hrs | FY28 | 28 | 90000313 | B2 | 1000020499 | 04.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -BRKSTR-SCABL | 5000 | 40249 | 40249
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Torque Converter | 2028-03-04 | 2028-03-05 | 30 hrs | FY28 | 60 | 90000309 | B2 | 1000020437 | 04.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -TRNSYS-TRQUE | 5000 | 64687 | 9550
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Air Conditioner Minor Service | 2028-03-05 | 2028-03-05 | 6 hrs | FY28 | 6 | 90018856 | B1 | 1000225398 | 05.03.2028 | 4500 | CCK-MP-DOZR-DZ8234-STRUCT-CABIN-AIRCN | 5000 | 26629 | 12967
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Sepura SCC Microphone | 2028-03-06 | 2028-03-06 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289547 | 06.03.2028 | 12 Monthly | CCK-MP-DOZR-DZ172 -COMMUN-RADIO | 5000 | 68264 | 6824
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hyd Pump Cooling Fan | 2028-03-09 | 2028-03-09 | 4 hrs | FY28 | 8 | 90002964 | B3 | 1000092685 | 09.03.2028 | 15000 | CCK-MP-DOZR-WD203 -HYDSYS-HYDPP-HYP03 | 6300 | 80875 | 4797
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Operators Seat | 2028-03-10 | 2028-03-10 | 2 hrs | FY28 | 4 | 90002975 | B2 | 1000033602 | 10.03.2028 | 7000 | CCK-MP-DOZR-WD006 -STRUCT-CABIN-SEATS | 6300 | 69386 | 4123
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Steer Clutch & Brake Assm RH | 2028-03-11 | 2028-03-11 | 14 hrs | FY28 | 28 | 90000313 | B2 | 1000091269 | 11.03.2028 | 18000 | CCK-MP-DOZR-DZ180 -BRKSTR-SCABR | 5000 | 63195 | 9998
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Rad Engine Cooling SN 529 UP | 2028-03-11 | 2028-03-12 | 24 hrs | FY28 | 48 | 90000307 | B2 | 1000091260 | 11.03.2028 | 18000 | CCK-MP-DOZR-DZ180 -ENGINE-COSYS-RADTR | 5000 | 63195 | 9998
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Pump Trans & TCon Charge | 2028-03-14 | 2028-03-14 | 10 hrs | FY28 | 10 | 90000302 | B2 | 1000091193 | 14.03.2028 | 18000 | CCK-MP-DOZR-DZ175 -TRNSYS-TRPMP | 5000 | 71802 | 10261
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Front Axle Assembly Midlife | 2028-03-21 | 2028-03-22 | 41 hrs | FY28 | 42 | 90025907 | B1 | 1000255888 | 21.03.2028 | 7000 | CCK-MP-GRDR-GR123 -STRUCT-AXLES | 5200 | 50884 | 6392
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Actuator Brake HaulX Shield | 2028-03-24 | 2028-03-25 | 26 hrs | FY28 | 50 | 90033498 | B1 | 1000362566 | 24.03.2028 | 14000 | CCK-MP-DOZR-DZ014 -MANGMT-CASYS-ACTBK
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Adjust Engine 500hr Valve Set | 2028-03-24 | 2028-03-24 | 12 hrs | FY28 | 24 | 90018851 | B1 | 1000225830 | 24.03.2028 | 500 | CCK-MP-DOZR-DZ8235-ENGINE | 5000 | 23802 | 10459
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Minor Service Air Conditioner | 2028-03-25 | 2028-03-25 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000196612 | 25.03.2028 | 4500 | CCK-MP-DOZR-DZ170 -STRUCT-CABIN-AIRCN | 5000 | 54263 | 15137
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Cylinder Blade Tilt LH | 2028-03-28 | 2028-03-28 | 7 hrs | FY28 | 14 | 90002967 | B1 | 1000228679 | 28.03.2028 | 22000 | CCK-MP-DOZR-WD203 -HYDSYS-HDCYL-BTCYL | 6300 | 80875 | 11509
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Cylinder Blade Tilt RH | 2028-03-28 | 2028-03-28 | 7 hrs | FY28 | 14 | 90002968 | B1 | 1000228680 | 28.03.2028 | 22000 | CCK-MP-DOZR-WD203 -HYDSYS-HDCYL-BTCYR | 6300 | 80875 | 80875
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Fan Cooling Motor Hyd | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 16 | 90002094 | B2 | 1000069923 | 28.03.2028 | 9000 | CCK-MP-DOZR-DZ014 -HYDSYS-HDCFM | 5000 | 64687 | 56
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Hyd Oil Cooler | 2028-03-28 | 2028-03-28 | 10 hrs | FY28 | 10 | 90009664 | B2 | 1000075353 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -HYDSYS-HDOCO | 5000 | 64687 | 9227
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Ovhl Hydraulic & Fuel Tank | 2028-03-28 | 2028-03-29 | 24 hrs | FY28 | 48 | 90010842 | B1 | 1000089417 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -HYDSYS-HDTNK | 5000 | 64687 | 9227
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Hyd Pump Cooling Fan | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 16 | 90004952 | B2 | 1000069903 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -HYDSYS-HYDPP-HYFPP | 5000 | 64687 | 9227
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Equaliser Bar | 2028-03-28 | 2028-03-30 | 55 hrs | FY28 | 110 | 90002097 | B1 | 1000089437 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -STRUCT-CHASS-EQUAL | 5000 | 64687 | 9227
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Drive Shaft | 2028-03-28 | 2028-03-28 | 3 hrs | FY28 | 6 | 90033296 | B1 | 1000334085 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -TRNSYS | 5000 | 64687 | 9227
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Transmission | 2028-03-28 | 2028-03-29 | 24 hrs | FY28 | 48 | 90000308 | B2 | 1000020494 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -TRNSYS-TRANS | 5000 | 64687 | 9227
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Pump Trans & TCon Charge | 2028-03-28 | 2028-03-28 | 10 hrs | FY28 | 10 | 90000302 | B2 | 1000020496 | 28.03.2028 | 18000 | CCK-MP-DOZR-DZ014 -TRNSYS-TRPMP | 5000 | 64687 | 9227
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 12 Monthly Hydraulic Tune Up | 2028-03-29 | 2028-03-29 | 12 hrs | FY28 | 24 | 90015111 | B1 | 1000126743 | 29.03.2028 | 52 Weekly | CCK-MP-LOAD-WL022 -HYDSYS
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Overhaul Axle Oscillation Rear | 2028-03-29 | 2028-03-30 | 24 hrs | FY28 | 64 | 90002953 | B3 | 1000092722 | 29.03.2028 | 15000 | CCK-MP-DOZR-WD204 -FDRSYS-RRDIF-TRNON | 6300 | 83628 | 4677
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Operators Seat | 2028-03-31 | 2028-03-31 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000108487 | 31.03.2028 | 6000 | CCK-MP-DOZR-DZ178 -STRUCT-CABIN-SEATS | 5000 | 54741 | 3721
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Output Drive Shaft Unis | 2028-04-04 | 2028-04-04 | 4 hrs | FY28 | 8 | 90033264 | B1 | 1000333901 | 04.04.2028 | 7000 | CCK-MP-GRDR-GR012 -FDRSYS-DRSHT-SHT01 | 5200 | 72353 | 348
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Trans Input Drive Shaft Unis | 2028-04-04 | 2028-04-04 | 4 hrs | FY28 | 8 | 90033267 | B1 | 1000333903 | 04.04.2028 | 7000 | CCK-MP-GRDR-GR012 -FDRSYS-DRSHT-SHT02 | 5200 | 72353 | 348
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Repl Sepura SCC Microphone | 2028-04-04 | 2028-04-04 | 0.5 hrs | FY28 | 0.5 | 90028991 | B1 | 1000289549 | 04.04.2028 | 12 Monthly | CCK-MP-DOZR-DZ174 -COMMUN-RADIO | 5000 | 65414 | 65414
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Replace Hoses Powertrain System | 2028-04-05 | 2028-04-06 | 24 hrs | FY28 | 48 | 90013049 | B3 | 1000116336 | 05.04.2028 | 22000 | CCK-MP-DOZR-WD201 -TRNSYS-TRHLF | 6300 | 81082 | 12720
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Trans System Hoses Midlife | 2028-04-05 | 2028-04-05 | 4 hrs | FY28 | 4 | 90026915 | B1 | 1000271662 | 05.04.2028 | 8000 | CCK-MP-LOAD-WL7103-TRNSYS-TRHLF-TRNHO | 6000 | 72865 | 14006
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Side Shift | 2028-04-10 | 2028-04-10 | 5 hrs | FY28 | 6 | 90021513 | B1 | 1000225889 | 10.04.2028 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-SSCYL | 5500 | 24399 | 4589
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Service Minor Air Conditioner | 2028-04-13 | 2028-04-13 | 12 hrs | FY28 | 12 | 90019542 | B1 | 1000290312 | 13.04.2028 | 3500 | CCK-MP-GRDR-GR122 -STRUCT-CABIN-AIRCN | 5200 | 68036 | 15776
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Cyl Steering LH | 2028-04-16 | 2028-04-16 | 12 hrs | FY28 | 22 | 90002961 | B3 | 1000033587 | 16.04.2028 | 22000 | CCK-MP-DOZR-WD006 -STRSYS-STRCY-STCYL | 6300 | 69386 | 11492
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Cylinder Blade Lift RH | 2028-04-16 | 2028-04-16 | 6 hrs | FY28 | 12 | 90002966 | B1 | 1000033593 | 16.04.2028 | 22000 | CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BLCYR | 6300 | 69386 | 11492
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Final Drive & Brake LHR | 2028-04-21 | 2028-04-23 | 44 hrs | FY28 | 83 | 90002710 | B2 | 1000138161 | 21.04.2028 | 16000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR03 | 6000 | 72865 | 5748
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Engine Midlife complete | 2028-05-03 | 2028-05-05 | 63 hrs | FY28 | 84 | 90015811 | B1 | 1000286611 | 03.05.2028 | 11000 | CCK-MP-DOZR-WD202 -ENGINE | 6300 | 79903 | 21666
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Replace Shaft Universals Rear | 2028-05-03 | 2028-05-03 | 3 hrs | FY28 | 6 | 90026666 | B1 | 1000268449 | 03.05.2028 | 11000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT02 | 6300 | 79903 | 10962
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Replace Shaft Universals Front | 2028-05-03 | 2028-05-03 | 3 hrs | FY28 | 6 | 90026667 | B1 | 1000268453 | 03.05.2028 | 11000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT04 | 6300 | 79903 | 10962
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Overhaul Airconditioner | 2028-05-03 | 2028-05-05 | 48 hrs | FY28 | 48 | 90013087 | B1 | 1000286613 | 03.05.2028 | 11000 | CCK-MP-DOZR-WD202 -STRUCT-CABIN-AIRCN | 6300 | 79903 | 10962
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Adjust 250hr Initial Valve Set | 2028-05-06 | 2028-05-06 | 12 hrs | FY28 | 24 | 90021246 | B1 | 1000222496 | 06.05.2028 | 250 | CCK-MP-LOAD-WL260 -ENGINE | 6000 | 75558 | 9814
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Hyd Pump Steering Main | 2028-05-07 | 2028-05-07 | 6 hrs | FY28 | 12 | 90002958 | B3 | 1000033584 | 07.05.2028 | 15000 | CCK-MP-DOZR-WD006 -STRSYS-STPMP-STP01 | 6300 | 69386 | 4123
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Overhaul Axle Oscillation Rear | 2028-05-07 | 2028-05-08 | 24 hrs | FY28 | 64 | 90002953 | B3 | 1000033576 | 07.05.2028 | 15000 | CCK-MP-DOZR-WD006 -FDRSYS-RRDIF-TRNON | 6300 | 69386 | 4123
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Fan Cooling Motor Hyd | 2028-05-07 | 2028-05-07 | 8 hrs | FY28 | 16 | 90002094 | B2 | 1000108486 | 07.05.2028 | 9000 | CCK-MP-DOZR-DZ178 -HYDSYS-HDCFM | 5000 | 54741 | 433
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Minor Service Air Conditioner | 2028-05-10 | 2028-05-10 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000196631 | 10.05.2028 | 4500 | CCK-MP-DOZR-DZ175 -STRUCT-CABIN-AIRCN | 5000 | 71802 | 4957
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Aftercooler Engine | 2028-05-14 | 2028-05-14 | 12 hrs | FY28 | 12 | 90010216 | B3 | 1000092691 | 14.05.2028 | 22000 | CCK-MP-DOZR-WD203 -ENGINE-INTEX-AFTER | 6300 | 80875 | 10669
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Oil Cooler Front Axle Lube | 2028-05-14 | 2028-05-14 | 6 hrs | FY28 | 6 | 90010219 | B3 | 1000092693 | 14.05.2028 | 22000 | CCK-MP-DOZR-WD203 -FDRSYS-AXLEC-OILCF | 6300 | 80875 | 10670
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Overhaul Auto Lubrication System | 2028-05-14 | 2028-05-16 | 48 hrs | FY28 | 96 | 90002971 | B3 | 1000092688 | 14.05.2028 | 22000 | CCK-MP-DOZR-WD203 -GRSYST | 6300 | 80875 | 10669
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Cyl Blade Lift RH | 2028-05-16 | 2028-05-16 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255647 | 16.05.2028 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BLCYR | 5000 | 69680 | 4914
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Cylinder Blade Tilt LH | 2028-05-17 | 2028-05-17 | 7 hrs | FY28 | 14 | 90002967 | B1 | 1000228671 | 17.05.2028 | 22000 | CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BTCYL | 6300 | 81082 | 21309
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Sepura SCC Microphone | 2028-05-17 | 2028-05-17 | 0.5 hrs | FY28 | 0.5 | 90028998 | B1 | 1000321326 | 17.05.2028 | 12 Monthly | CCK-MP-LOAD-WL7103-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Final Drive Position 4 | 2028-05-20 | 2028-05-22 | 44 hrs | FY28 | 83 | 90002710 | B2 | 1000090607 | 20.05.2028 | 16000 | CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR04 | 6000 | 74342 | 5199
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Cyl Lift RH | 2028-05-26 | 2028-05-27 | 28 hrs | FY28 | 56 | 90002787 | B2 | 1000131361 | 26.05.2028 | 10000 | CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-HCYLR | 3100 | 64003 | 4401
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Cyl Blade Lift LH | 2028-05-26 | 2028-05-26 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255614 | 26.05.2028 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BLCYL | 5000 | 68264 | 9056
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Cyl Blade Lift RH | 2028-05-26 | 2028-05-26 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255615 | 26.05.2028 | 9000 | CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BLCYR | 5000 | 68264 | 9054
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Repl Operators Seat | 2028-05-27 | 2028-05-27 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000089357 | 27.05.2028 | 6000 | CCK-MP-DOZR-DZ014 -STRUCT-CABIN-SEATS | 5000 | 64687 | 2402
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Torque Converter | 2028-06-01 | 2028-06-02 | 24 hrs | FY28 | 48 | 90002693 | B2 | 1000138142 | 01.06.2028 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-TRQUE | 6000 | 72865 | 9061
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Minor Service Air Conditioner | 2028-06-03 | 2028-06-03 | 10.5 hrs | FY28 | 10.5 | 90017699 | B1 | 1000162398 | 03.06.2028 | 4500 | CCK-MP-DOZR-DZ014 -STRUCT-CABIN-AIRCN | 5000 | 64687 | 16308
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Engine Thermostats | 2028-06-16 | 2028-06-16 | 6 hrs | FY28 | 6 | 90021139 | B1 | 1000222750 | 16.06.2028 | 5000 | CCK-MP-LOAD-WL7103-ENGINE-COSYS-THERM | 6000 | 72865 | 2571
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Service Air Conditioner | 2028-06-16 | 2028-06-17 | 24 hrs | FY28 | 24 | 90021130 | B1 | 1000222742 | 16.06.2028 | 5000 | CCK-MP-LOAD-WL7103-STRUCT-CABIN-AIRCN | 6000 | 72865 | 12069
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Operators Seat | 2028-06-17 | 2028-06-17 | 4 hrs | FY28 | 8 | 90000318 | B1 | 1000108463 | 17.06.2028 | 6000 | CCK-MP-DOZR-DZ176 -STRUCT-CABIN-SEATS | 5000 | 69680 | 2541
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Artic Area Hyd Hosing | 2028-06-19 | 2028-06-19 | 6 hrs | FY28 | 6 | 90020831 | B1 | 1000321324 | 19.06.2028 | 8 Monthly | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-ARTHO
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Sepura SCC Microphone | 2028-06-21 | 2028-06-21 | 0.5 hrs | FY28 | 0.5 | 90028989 | B1 | 1000289370 | 21.06.2028 | 12 Monthly | CCK-MP-GRDR-GR012 -COMMUN-RADIO | 5200 | 72353 | 72353
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Cyl Blade Lift LH | 2028-06-21 | 2028-06-21 | 8 hrs | FY28 | 16 | 90000287 | B1 | 1000255646 | 21.06.2028 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BLCYL | 5000 | 69680 | 8485
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Hyd Pump Cooling Fan | 2028-06-21 | 2028-06-21 | 8 hrs | FY28 | 16 | 90004952 | B2 | 1000091225 | 21.06.2028 | 18000 | CCK-MP-DOZR-DZ176 -HYDSYS-HYDPP-HYFPP | 5000 | 69680 | 8485
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Gearbox Circle Drive Rear | 2028-06-23 | 2028-06-23 | 8 hrs | FY28 | 14 | 90011066 | B2 | 1000028443 | 23.06.2028 | 14000 | CCK-MP-GRDR-GR012 -STRUCT-CIRCL-CDBXR | 5200 | 72353 | 652
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 12 Monthly Hydraulic Tune Up | 2028-06-25 | 2028-06-25 | 12 hrs | FY28 | 24 | 90015111 | B1 | 1000266797 | 25.06.2028 | 52 Weekly | CCK-MP-LOAD-WL021 -HYDSYS
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Hyd Pump Cooling Fan | 2028-06-28 | 2028-06-28 | 8 hrs | FY28 | 16 | 90004952 | B2 | 1000091201 | 28.06.2028 | 18000 | CCK-MP-DOZR-DZ175 -HYDSYS-HYDPP-HYFPP | 5000 | 71802 | 8775
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Operators Seat | 2028-06-30 | 2028-06-30 | 4 hrs | FY28 | 4 | 90019606 | B1 | 1000201907 | 30.06.2028 | 10000 | CCK-MP-GRDR-GR7107-STRUCT-CABIN-SEATS | 5500 | 24399 | 9406
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Front Drive Shaft Unis | 2028-06-30 | 2028-06-30 | 4 hrs | FY28 | 8 | 90033188 | B1 | 1000333570 | 30.06.2028 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT04 | 6000 | 72865 | 6385
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-06-30 | 2028-06-30 | 4 hrs | FY28 | 8 | 90033193 | B1 | 1000333572 | 30.06.2028 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT05 | 6000 | 72865 | 16811
| Onsite PM | Ancillary | Fortescue |  | FY29 - ANCILLARY - COMPONENTS DURING PM | 2028-07-01 | 2029-06-30 |  | FY29
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Adjust 250hr Initial Valve Set | 2028-07-02 | 2028-07-02 | 12 hrs | FY29 | 24 | 90021246 | B1 | 1000222672 | 02.07.2028 | 250 | CCK-MP-LOAD-WL269 -ENGINE | 6000 | 74583 | 8436
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Clean Engine Pre Cleaners | 2028-07-05 | 2028-07-05 | 6 hrs | FY29 | 6 | 90015808 | B1 | 1000286622 | 05.07.2028 | 5500 | CCK-MP-DOZR-WD204 -ENGINE-INTEX-AIRFL | 6300 | 83628 | 28312
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Service Airconditioner | 2028-07-05 | 2028-07-06 | 24 hrs | FY29 | 24 | 90003915 | B1 | 1000286626 | 05.07.2028 | 5500 | CCK-MP-DOZR-WD204 -STRUCT-CABIN-AIRCN | 6300 | 83628 | 15298
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Clean Engine Pre Cleaners | 2028-07-05 | 2028-07-05 | 6 hrs | FY29 | 6 | 90015808 | B1 | 1000286601 | 05.07.2028 | 5500 | CCK-MP-DOZR-WD201 -ENGINE-INTEX-AIRFL | 6300 | 81082 | 28558
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Service Airconditioner | 2028-07-05 | 2028-07-06 | 24 hrs | FY29 | 24 | 90003915 | B1 | 1000286605 | 05.07.2028 | 5500 | CCK-MP-DOZR-WD201 -STRUCT-CABIN-AIRCN | 6300 | 81082 | 12720
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Cyl Blade Lift LH | 2028-07-06 | 2028-07-06 | 8 hrs | FY29 | 16 | 90000287 | B1 | 1000255694 | 06.07.2028 | 9000 | CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-BLCYL | 5000 | 65794 | 13113
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Refurbish Cabin | 2028-07-09 | 2028-07-10 | 18 hrs | FY29 | 18 | 90018839 | B1 | 1000225388 | 09.07.2028 | 36000 | CCK-MP-DOZR-DZ8234-STRUCT-CABIN | 5000 | 26629 | 26629
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Track Frame LH | 2028-07-09 | 2028-07-11 | 46 hrs | FY29 | 90 | 90033095 | B1 | 1000331736 | 09.07.2028 | 36000 | CCK-MP-DOZR-DZ8234-STRUCT-UNDER-TKFRL | 5000 | 26629 | 7157
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Track Frame RH | 2028-07-09 | 2028-07-11 | 46 hrs | FY29 | 90 | 90033096 | B1 | 1000331738 | 09.07.2028 | 36000 | CCK-MP-DOZR-DZ8234-STRUCT-UNDER-TKFRR | 5000 | 26629 | 7157
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Sepura SCC Microphone | 2028-07-10 | 2028-07-10 | 0.5 hrs | FY29 | 0.5 | 90028996 | B1 | 1000289582 | 10.07.2028 | 12 Monthly | CCK-MP-DOZR-WD201 -COMMUN-RADIO | 6300 | 81082 | 81082
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Adjust 250hr Initial Valve Set | 2028-07-12 | 2028-07-12 | 12 hrs | FY29 | 24 | 90021246 | B1 | 1000222628 | 12.07.2028 | 250 | CCK-MP-LOAD-WL267 -ENGINE | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Sepura SCC Microphone | 2028-07-12 | 2028-07-12 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000289598 | 12.07.2028 | 12 Monthly | CCK-MP-LOAD-WL260 -COMMUN-RADIO | 6000 | 75558 | 75558
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Final Drive Position 4 | 2028-07-12 | 2028-07-13 | 22 hrs | FY29 | 58 | 90002954 | B3 | 1000092674 | 12.07.2028 | 22000 | CCK-MP-DOZR-WD203 -FDRSYS-FDRVE-FDR04 | 6300 | 80875 | 9561
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Trans System Hoses Midlife | 2028-07-14 | 2028-07-14 | 4 hrs | FY29 | 4 | 90026915 | B1 | 1000271602 | 14.07.2028 | 8000 | CCK-MP-LOAD-WL266 -TRNSYS-TRHLF-TRNHO | 6000 | 74342 | 12308
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Replace Artic Area Hyd Hosing | 2028-07-14 | 2028-07-14 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220496 | 14.07.2028 | 8 Monthly | CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Brake System Hoses | 2028-07-15 | 2028-07-16 | 24 hrs | FY29 | 48 | 90026921 | B1 | 1000271580 | 15.07.2028 | 20000 | CCK-MP-LOAD-WL260 -BRKSYS-BRHLF-BRKHO | 6000 | 75566 | 9814
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Operators Seat | 2028-07-16 | 2028-07-16 | 4 hrs | FY29 | 8 | 90018835 | B1 | 1000225444 | 16.07.2028 | 6000 | CCK-MP-DOZR-DZ8234-STRUCT-CABIN-SEATS | 5000 | 26629 | 8321
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Minor Service Air Conditioner | 2028-07-17 | 2028-07-17 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196640 | 17.07.2028 | 4500 | CCK-MP-DOZR-DZ178 -STRUCT-CABIN-AIRCN | 5000 | 54741 | 3721
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Cylinder Blade Tilt RH | 2028-07-18 | 2028-07-18 | 7 hrs | FY29 | 14 | 90002968 | B1 | 1000228672 | 18.07.2028 | 22000 | CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BTCYR | 6300 | 81082 | 9810
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Cyl Steering RH | 2028-07-18 | 2028-07-18 | 12 hrs | FY29 | 22 | 90002961 | B3 | 1000092580 | 18.07.2028 | 22000 | CCK-MP-DOZR-WD201 -STRSYS-STRCY-STCYR | 6300 | 81082 | 9810
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Sepura SCC Microphone | 2028-07-20 | 2028-07-20 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289552 | 20.07.2028 | 12 Monthly | CCK-MP-DOZR-DZ178 -COMMUN-RADIO | 5000 | 54741 | 3721
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-07-23 | 2028-07-23 | 4 hrs | FY29 | 8 | 90033193 | B1 | 1000333524 | 23.07.2028 | 10000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT05 | 6000 | 74342 | 18157
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Transmission | 2028-07-26 | 2028-07-28 | 57 hrs | FY29 | 167 | 90002944 | B3 | 1000092560 | 26.07.2028 | 15000 | CCK-MP-DOZR-WD201 -TRNSYS-TRANS | 6300 | 81082 | 2675
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Pump Transmission | 2028-07-26 | 2028-07-26 | 4 hrs | FY29 | 8 | 90002946 | B3 | 1000092561 | 26.07.2028 | 15000 | CCK-MP-DOZR-WD201 -TRNSYS-TRPMP | 6300 | 81082 | 2675
D10T | Onsite PM | Ancillary | Fortescue | DZ174 | DZ174 Minor Service Air Conditioner | 2028-07-26 | 2028-07-26 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196628 | 26.07.2028 | 4500 | CCK-MP-DOZR-DZ174 -STRUCT-CABIN-AIRCN | 5000 | 65414 | 20488
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Drive Shaft | 2028-07-27 | 2028-07-27 | 3 hrs | FY29 | 6 | 90033296 | B1 | 1000334103 | 27.07.2028 | 18000 | CCK-MP-DOZR-DZ171 -TRNSYS | 5000 | 67979 | 8290
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Sepura SCC Microphone | 2028-07-28 | 2028-07-28 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289570 | 28.07.2028 | 12 Monthly | CCK-MP-DOZR-DZ8235-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Final Drive Position 2 | 2028-07-30 | 2028-08-01 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000028878 | 30.07.2028 | 16000 | CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-FDR02 | 6000 | 80515 | 19593
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Transmission System Hoses | 2028-07-30 | 2028-08-01 | 48 hrs | FY29 | 96 | 90026923 | B2 | 1000271538 | 30.07.2028 | 16000 | CCK-MP-LOAD-WL022 -TRNSYS-TRHLF-TRNHO | 6000 | 80515 | 35795
993K | Onsite PM | Ancillary | Fortescue | WL017 | WL017 Repl Sepura SCC Microphone | 2028-07-31 | 2028-07-31 | 0.5 hrs | FY29 | 0.5 | 90028997 | B1 | 1000289594 | 31.07.2028 | 12 Monthly | CCK-MP-LOAD-WL017 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Cyl Bucket RH High Lift | 2028-08-01 | 2028-08-02 | 18 hrs | FY29 | 36 | 90017977 | B1 | 1000131519 | 01.08.2028 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-BUCYR | 6000 | 74342 | 1701
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Transmission Transfer Case | 2028-08-02 | 2028-08-03 | 38 hrs | FY29 | 74 | 90017029 | B2 | 1000153362 | 02.08.2028 | 16000 | CCK-MP-LOAD-WL021 -TRNSYS-TRTRF | 6000 | 79974 | 3457
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Clean Engine Pre Cleaners | 2028-08-02 | 2028-08-02 | 6 hrs | FY29 | 6 | 90015808 | B1 | 1000286587 | 02.08.2028 | 5500 | CCK-MP-DOZR-WD006 -ENGINE-INTEX-AIRFL
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Service Airconditioner | 2028-08-02 | 2028-08-03 | 24 hrs | FY29 | 24 | 90003915 | B1 | 1000286591 | 02.08.2028 | 5500 | CCK-MP-DOZR-WD006 -STRUCT-CABIN-AIRCN | 6300 | 69386 | 4123
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Replace Shaft Universals Centre | 2028-08-03 | 2028-08-03 | 3 hrs | FY29 | 6 | 90026668 | B1 | 1000268435 | 03.08.2028 | 11000 | CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT03 | 6300 | 76513 | 20488
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Artic Area Hyd Hosing | 2028-08-04 | 2028-08-04 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000321324 | 04.08.2028 | 8 Monthly | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Cyl Bucket LH Ext High Lift | 2028-08-04 | 2028-08-05 | 20 hrs | FY29 | 38 | 90015438 | B2 | 1000028834 | 04.08.2028 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-BUCYL | 6000 | 79974 | 7368
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Hyd Motor Fan | 2028-08-04 | 2028-08-04 | 4 hrs | FY29 | 8 | 90002790 | B2 | 1000030488 | 04.08.2028 | 8000 | CCK-MP-LOAD-WL004 -HYDSYS-HYDMT-HYM01 | 3100 | 63992 | 8684
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Aftercooler Engine | 2028-08-05 | 2028-08-05 | 12 hrs | FY29 | 24 | 90002623 | B2 | 1000090819 | 05.08.2028 | 14000 | CCK-MP-GRDR-GR120 -ENGINE-INTEX-AFTER | 5200 | 60265 | 18931
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Transmission Charge Pump | 2028-08-07 | 2028-08-07 | 6 hrs | FY29 | 12 | 90002694 | B2 | 1000028861 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-TRPMP | 6000 | 80537 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Centre Bearing Upper Shaft | 2028-08-07 | 2028-08-07 | 12 hrs | FY29 | 24 | 90002702 | B2 | 1000028869 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-UCTRB | 6000 | 80537 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Overhaul Park Brake & Centre Brg | 2028-08-07 | 2028-08-08 | 18 hrs | FY29 | 36 | 90002711 | B2 | 1000087665 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -BRKSYS-BRPRK | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Steering STIC Pilot Valve | 2028-08-07 | 2028-08-07 | 12 hrs | FY29 | 12 | 90026110 | B1 | 1000028890 | 07.08.2028 | 20000 | CCK-MP-LOAD-WL022 -STRSYS-STIPV | 6000 | 80515 | 80515
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Implement LH | 2028-08-07 | 2028-08-07 | 12 hrs | FY29 | 24 | 90002723 | B2 | 1000028893 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP01 | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Implement RH | 2028-08-07 | 2028-08-07 | 12 hrs | FY29 | 24 | 90002724 | B2 | 1000028894 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP02 | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Implement Centre | 2028-08-07 | 2028-08-07 | 12 hrs | FY29 | 24 | 90002725 | B2 | 1000028895 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP03 | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Pilot & Cooling | 2028-08-07 | 2028-08-07 | 6 hrs | FY29 | 12 | 90002726 | B2 | 1000028896 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP04 | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Cyl Lift LH Ext High Lift | 2028-08-07 | 2028-08-08 | 28 hrs | FY29 | 54 | 90002728 | B2 | 1000028897 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-HCYLL | 6000 | 80515 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Cyl Lift RH Ext High Lift | 2028-08-07 | 2028-08-08 | 28 hrs | FY29 | 54 | 90002728 | B2 | 1000028898 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-HCYLR | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Cyl Bucket LH Ext High Lift | 2028-08-07 | 2028-08-08 | 20 hrs | FY29 | 38 | 90015438 | B2 | 1000131514 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-BUCYL | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Cyl Bucket RH Ext High Lift | 2028-08-07 | 2028-08-08 | 18 hrs | FY29 | 36 | 90015437 | B2 | 1000131515 | 07.08.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-BUCYR | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Replace Artic Area Hyd Hosing | 2028-08-10 | 2028-08-10 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220503 | 10.08.2028 | 8 Monthly | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-ARTHO
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Sepura SCC Microphone | 2028-08-10 | 2028-08-10 | 0.5 hrs | FY29 | 0.5 | 90028996 | B1 | 1000289580 | 10.08.2028 | 12 Monthly | CCK-MP-DOZR-WD006 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Transmission Transfer Case | 2028-08-12 | 2028-08-13 | 38 hrs | FY29 | 74 | 90017029 | B2 | 1000153361 | 12.08.2028 | 16000 | CCK-MP-LOAD-WL022 -TRNSYS-TRTRF | 6000 | 80515 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Transmission System Hoses | 2028-08-13 | 2028-08-15 | 48 hrs | FY29 | 96 | 90026923 | B2 | 1000271532 | 13.08.2028 | 16000 | CCK-MP-LOAD-WL021 -TRNSYS-TRHLF-TRNHO | 6000 | 79974 | 9601
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Transmission | 2028-08-17 | 2028-08-18 | 38 hrs | FY29 | 74 | 90002692 | B2 | 1000028795 | 17.08.2028 | 16000 | CCK-MP-LOAD-WL021 -TRNSYS-TRANS | 6000 | 79997 | 3457
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Gearbox Pump Drive Front | 2028-08-17 | 2028-08-18 | 38 hrs | FY29 | 74 | 90002705 | B2 | 1000028807 | 17.08.2028 | 16000 | CCK-MP-LOAD-WL021 -TRNSYS-PMPDR-FRPDR | 6000 | 79974 | 3457
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Final Drive Position 1 | 2028-08-17 | 2028-08-19 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000028812 | 17.08.2028 | 16000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR01 | 6000 | 40013 | 40013
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Final Drive Position 2 | 2028-08-17 | 2028-08-19 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000028813 | 17.08.2028 | 16000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR02 | 6000 | 38502 | 38502
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Final Drive Position 3 | 2028-08-17 | 2028-08-19 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000028814 | 17.08.2028 | 16000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR03 | 6000 | 41373 | 41373
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Final Drive Position 4 | 2028-08-17 | 2028-08-19 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000028815 | 17.08.2028 | 16000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR04 | 6000 | 38502 | 38502
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Adjust Engine 500hr Valve Set | 2028-08-17 | 2028-08-17 | 8 hrs | FY29 | 16 | 90015857 | B1 | 1000160287 | 17.08.2028 | 500 | CCK-MP-DOZR-DZ184 -ENGINE | 5000 | 67674 | 8628
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Sepura SCC Microphone | 2028-08-18 | 2028-08-18 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289555 | 18.08.2028 | 12 Monthly | CCK-MP-DOZR-DZ181 -COMMUN-RADIO | 5000 | 66297 | 66297
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Shaft Centre Brg to Fr Diff | 2028-08-19 | 2028-08-19 | 4 hrs | FY29 | 8 | 90002950 | B3 | 1000268436 | 19.08.2028 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT04 | 6300 | 76513 | 9013
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 6M Anritsu Test Wifi Cables | 2028-08-19 | 2028-08-19 | 2 hrs | FY29 | 2 | 90019046 | B2 | 1000257061 | 19.08.2028 | 6 Monthly | CCK-MP-LOAD-WL7162-COMMUN-FLMGT
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Operators Seat | 2028-08-20 | 2028-08-20 | 2 hrs | FY29 | 4 | 90002975 | B2 | 1000033656 | 20.08.2028 | 7000 | CCK-MP-DOZR-WD007 -STRUCT-CABIN-SEATS | 6300 | 76489 | 892
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Sepura SCC Microphone | 2028-08-20 | 2028-08-20 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289557 | 20.08.2028 | 12 Monthly | CCK-MP-DOZR-DZ183 -COMMUN-RADIO | 5000 | 65807 | 65807
D10T | Onsite PM | Ancillary | Fortescue | DZ178 | DZ178 Repl Hyd Oil Cooler | 2028-08-22 | 2028-08-22 | 10 hrs | FY29 | 10 | 90009664 | B2 | 1000088977 | 22.08.2028 | 18000 | CCK-MP-DOZR-DZ178 -HYDSYS-HDOCO | 5000 | 54741 | 7755
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Adjust Engine 500hr Valve Set | 2028-08-23 | 2028-08-23 | 8 hrs | FY29 | 16 | 90015857 | B1 | 1000160107 | 23.08.2028 | 500 | CCK-MP-DOZR-DZ169 -ENGINE | 5000 | 62015 | 8044
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Sepura SCC Microphone | 2028-08-23 | 2028-08-23 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000364484 | 23.08.2028 | 12 Monthly | CCK-MP-LOAD-WL7104-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Final Drive Position 3 | 2028-08-23 | 2028-08-25 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000090310 | 23.08.2028 | 16000 | CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR03 | 6000 | 77065 | 3904
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Engine Midlife Complete | 2028-08-23 | 2028-08-26 | 71 hrs | FY29 | 103 | 90015859 | B1 | 1000160193 | 23.08.2028 | 9000 | CCK-MP-DOZR-DZ176 -ENGINE | 5000 | 69680 | 784
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Fan Cooling Motor Hyd | 2028-08-23 | 2028-08-23 | 8 hrs | FY29 | 16 | 90002094 | B2 | 1000108462 | 23.08.2028 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HDCFM | 5000 | 69680 | 1080
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Major Service Air Conditioner | 2028-08-23 | 2028-08-24 | 24 hrs | FY29 | 24 | 90017469 | B1 | 1000196635 | 23.08.2028 | 9000 | CCK-MP-DOZR-DZ176 -STRUCT-CABIN-AIRCN | 5000 | 69680 | 16621
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Drive Shaft Unis | 2028-08-23 | 2028-08-23 | 3 hrs | FY29 | 6 | 90033292 | B1 | 1000334114 | 23.08.2028 | 9000 | CCK-MP-DOZR-DZ176 -TRNSYS | 5000 | 69680 | 16621
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Replace Artic Area Hyd Hosing | 2028-08-24 | 2028-08-24 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220497 | 24.08.2028 | 8 Monthly | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Operators Seat | 2028-08-27 | 2028-08-27 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000090405 | 27.08.2028 | 7000 | CCK-MP-LOAD-WL267 -STRUCT-CABIN-SEATS | 6000 | 74441 | 1115
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Sepura SCC Microphone | 2028-08-28 | 2028-08-28 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289569 | 28.08.2028 | 12 Monthly | CCK-MP-DOZR-DZ8234-COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Final Drive LH | 2028-08-29 | 2028-08-29 | 14 hrs | FY29 | 28 | 90000312 | B2 | 1000079430 | 29.08.2028 | 18000 | CCK-MP-DOZR-DZ173 -FDRSYS-FDRLH | 5000 | 68788 | 7762
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Engine Thermostats | 2028-08-31 | 2028-08-31 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222750 | 31.08.2028 | 5000 | CCK-MP-LOAD-WL7103-ENGINE-COSYS-THERM | 6000 | 72865 | 2571
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Service Air Conditioner | 2028-08-31 | 2028-09-01 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222742 | 31.08.2028 | 5000 | CCK-MP-LOAD-WL7103-STRUCT-CABIN-AIRCN | 6000 | 72865 | 12069
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Final Drive Position 1 | 2028-08-31 | 2028-09-02 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000028877 | 31.08.2028 | 16000 | CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-FDR01 | 6000 | 80515 | 3082
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 12 Monthly Hydraulic Tune Up | 2028-09-01 | 2028-09-01 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000126742 | 01.09.2028 | 52 Weekly | CCK-MP-LOAD-WL269 -HYDSYS | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Cyl Steering LH | 2028-09-01 | 2028-09-01 | 14 hrs | FY29 | 26 | 90002721 | B2 | 1000090321 | 01.09.2028 | 12000 | CCK-MP-LOAD-WL261 -STRSYS-STRCY-STCYL | 6000 | 77065 | 11736
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Fan Cooling Motor Hyd | 2028-09-01 | 2028-09-01 | 8 hrs | FY29 | 16 | 90002094 | B2 | 1000108390 | 01.09.2028 | 9000 | CCK-MP-DOZR-DZ170 -HYDSYS-HDCFM | 5000 | 54263 | 1222
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Final Drive Position 4 | 2028-09-03 | 2028-09-05 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000028880 | 03.09.2028 | 16000 | CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-FDR04 | 6000 | 80515 | 1209
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Repl Sepura SCC Microphone | 2028-09-03 | 2028-09-03 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289550 | 03.09.2028 | 12 Monthly | CCK-MP-DOZR-DZ175 -COMMUN-RADIO | 5000 | 71827 | 4957
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Track Frame LH | 2028-09-03 | 2028-09-04 | 20 hrs | FY29 | 40 | 90002099 | B1 | 1000108410 | 03.09.2028 | 36000 | CCK-MP-DOZR-DZ171 -STRUCT-UNDER-TKFRL | 5000 | 67979 | 25809
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Track Frame RH | 2028-09-03 | 2028-09-04 | 20 hrs | FY29 | 40 | 90002102 | B1 | 1000108412 | 03.09.2028 | 36000 | CCK-MP-DOZR-DZ171 -STRUCT-UNDER-TKFRR | 5000 | 67979 | 25809
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 12 Monthly Hydraulic Tune Up | 2028-09-04 | 2028-09-04 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000364486 | 04.09.2028 | 52 Weekly | CCK-MP-LOAD-WL7104-HYDSYS
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Sepura SCC Microphone | 2028-09-06 | 2028-09-06 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000289610 | 06.09.2028 | 12 Monthly | CCK-MP-LOAD-WL7162-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Steering Cylinder LH | 2028-09-07 | 2028-09-07 | 14 hrs | FY29 | 26 | 90002721 | B2 | 1000138259 | 07.09.2028 | 12000 | CCK-MP-LOAD-WL7104-STRSYS-STRCY-STCYL | 4000 | 26203 | 26203
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Sepura SCC Microphone | 2028-09-07 | 2028-09-07 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000289602 | 07.09.2028 | 12 Monthly | CCK-MP-LOAD-WL267 -COMMUN-RADIO | 6000 | 74441 | 74441
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Steering Hyd Pump Secondary | 2028-09-07 | 2028-09-07 | 8 hrs | FY29 | 8 | 90002719 | B2 | 1000090246 | 07.09.2028 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP04 | 6000 | 75558 | 7480
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Sepura SCC Microphone | 2028-09-08 | 2028-09-08 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000289599 | 08.09.2028 | 12 Monthly | CCK-MP-LOAD-WL261 -COMMUN-RADIO | 6000 | 77065 | 11736
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Cyl Lift RH Ext High Lift | 2028-09-09 | 2028-09-10 | 28 hrs | FY29 | 54 | 90002728 | B2 | 1000028833 | 09.09.2028 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-HCYLR | 6000 | 79974 | 6827
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Sepura SCC Microphone | 2028-09-09 | 2028-09-09 | 0.5 hrs | FY29 | 0.5 | 90028996 | B1 | 1000289583 | 09.09.2028 | 12 Monthly | CCK-MP-DOZR-WD202 -COMMUN-RADIO | 6300 | 79903 | 79903
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Brake Cooling | 2028-09-12 | 2028-09-12 | 8 hrs | FY29 | 8 | 90002713 | B2 | 1000090387 | 12.09.2028 | 10000 | CCK-MP-LOAD-WL267 -BRKSYS-BRPMP-BRP02 | 6000 | 74441 | 19742
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Thermostats | 2028-09-12 | 2028-09-12 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222620 | 12.09.2028 | 5000 | CCK-MP-LOAD-WL266 -ENGINE-COSYS-THERM | 6000 | 74342 | 12308
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Service Air Conditioner | 2028-09-12 | 2028-09-13 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222610 | 12.09.2028 | 5000 | CCK-MP-LOAD-WL266 -STRUCT-CABIN-AIRCN | 6000 | 74342 | 12308
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Adjust Engine 500hr Valve Set | 2028-09-13 | 2028-09-13 | 8 hrs | FY29 | 16 | 90015857 | B1 | 1000160239 | 13.09.2028 | 500 | CCK-MP-DOZR-DZ180 -ENGINE | 5000 | 63195 | 7949
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Minor Service Air Conditioner | 2028-09-15 | 2028-09-15 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196649 | 15.09.2028 | 4500 | CCK-MP-DOZR-DZ181 -STRUCT-CABIN-AIRCN | 5000 | 66297 | 12007
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Radiator Engine Cooling | 2028-09-16 | 2028-09-18 | 50 hrs | FY29 | 98 | 90002618 | B3 | 1000090755 | 16.09.2028 | 14000 | CCK-MP-GRDR-GR120 -ENGINE-COSYS-RADTR | 5200 | 60265 | 18931
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Repl Sepura SCC Microphone | 2028-09-18 | 2028-09-18 | 0.5 hrs | FY29 | 0.5 | 90028989 | B1 | 1000289372 | 18.09.2028 | 12 Monthly | CCK-MP-GRDR-GR121 -COMMUN-RADIO | 5200 | 67029 | 67029
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 12 Monthly Hydraulic Tune Up | 2028-09-20 | 2028-09-20 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000126197 | 20.09.2028 | 52 Weekly | CCK-MP-LOAD-WL261 -HYDSYS | 6000 | 77065 | 30681
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Sepura SCC Microphone | 2028-09-20 | 2028-09-20 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000289596 | 20.09.2028 | 12 Monthly | CCK-MP-LOAD-WL022 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Centre Bearing Upper Shaft | 2028-09-22 | 2028-09-22 | 12 hrs | FY29 | 24 | 90002702 | B2 | 1000090596 | 22.09.2028 | 10000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-UCTRB | 6000 | 74342 | 18157
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Engine Radiator | 2028-09-23 | 2028-09-25 | 54 hrs | FY29 | 102 | 90002682 | B2 | 1000138229 | 23.09.2028 | 20000 | CCK-MP-LOAD-WL7104-ENGINE-COSYS-RADTR | 6300 | 64060 | 22080
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Hydraulic Oil Cooler | 2028-09-23 | 2028-09-25 | 48 hrs | FY29 | 96 | 90002733 | B2 | 1000138267 | 23.09.2028 | 20000 | CCK-MP-LOAD-WL7104-HYDSYS-HDOCO | 4000 | 64060 | 10963
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Cyl Steering RH | 2028-09-23 | 2028-09-23 | 12 hrs | FY29 | 22 | 90002781 | B2 | 1000030484 | 23.09.2028 | 16000 | CCK-MP-LOAD-WL004 -STRSYS-STRCY-STCYR | 3100 | 64003 | 21455
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Hyd Pump Pilot & Cooling | 2028-09-24 | 2028-09-24 | 6 hrs | FY29 | 12 | 90002726 | B2 | 1000090622 | 24.09.2028 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP04 | 6000 | 74342 | 7121
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Transmission Charge Pump | 2028-09-24 | 2028-09-24 | 6 hrs | FY29 | 12 | 90002694 | B2 | 1000090588 | 24.09.2028 | 10000 | CCK-MP-LOAD-WL266 -TRNSYS-TRPMP | 6000 | 74342 | 7121
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Sepura SCC Microphone | 2028-09-24 | 2028-09-24 | 0.5 hrs | FY29 | 0.5 | 90028996 | B1 | 1000289585 | 24.09.2028 | 12 Monthly | CCK-MP-DOZR-WD204 -COMMUN-RADIO | 6300 | 83628 | 83628
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Operators Seat | 2028-09-25 | 2028-09-25 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000138181 | 25.09.2028 | 7000 | CCK-MP-LOAD-WL7103-STRUCT-CABIN-SEATS | 6000 | 72865 | 1168
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Minor Overhaul Track Frame LH | 2028-09-26 | 2028-09-28 | 50 hrs | FY29 | 98 | 90002098 | B1 | 1000108469 | 26.09.2028 | 18000 | CCK-MP-DOZR-DZ176 -STRUCT-UNDER-TKFRL | 5000 | 69680 | 7159
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Minor Overhaul Track Frame RH | 2028-09-26 | 2028-09-28 | 50 hrs | FY29 | 98 | 90010766 | B1 | 1000108471 | 26.09.2028 | 18000 | CCK-MP-DOZR-DZ176 -STRUCT-UNDER-TKFRR | 5000 | 69680 | 7159
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Minor Service Air Conditioner | 2028-09-27 | 2028-09-27 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196625 | 27.09.2028 | 4500 | CCK-MP-DOZR-DZ173 -STRUCT-CABIN-AIRCN | 5000 | 68788 | 11848
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Rear Output Drive Shaft Unis | 2028-10-01 | 2028-10-01 | 4 hrs | FY29 | 8 | 90033167 | B1 | 1000333554 | 01.10.2028 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT02 | 6000 | 74583 | 16942
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Ctr Output Drive Shaft Unis | 2028-10-01 | 2028-10-01 | 4 hrs | FY29 | 8 | 90033173 | B1 | 1000333556 | 01.10.2028 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT03 | 6000 | 74583 | 16942
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Front Drive Shaft Unis | 2028-10-01 | 2028-10-01 | 4 hrs | FY29 | 8 | 90033188 | B1 | 1000333558 | 01.10.2028 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT04 | 6000 | 74583 | 16942
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-10-01 | 2028-10-01 | 4 hrs | FY29 | 8 | 90033193 | B1 | 1000333560 | 01.10.2028 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT05 | 6000 | 74583 | 16942
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Pump Drive Gearbox Front | 2028-10-02 | 2028-10-03 | 38 hrs | FY29 | 74 | 90002705 | B2 | 1000138154 | 02.10.2028 | 16000 | CCK-MP-LOAD-WL7103-TRNSYS-PMPDR-FRPDR | 6000 | 72865 | 3040
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Final Drive & Brake RHF | 2028-10-03 | 2028-10-05 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000138160 | 03.10.2028 | 16000 | CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR02 | 6000 | 33158 | 3040
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Transmission Transfer Case | 2028-10-03 | 2028-10-04 | 38 hrs | FY29 | 74 | 90017029 | B2 | 1000153210 | 03.10.2028 | 16000 | CCK-MP-LOAD-WL7103-TRNSYS-TRTRF | 6000 | 72865 | 3040
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Cyl Bucket RH Ext High Lift | 2028-10-03 | 2028-10-04 | 18 hrs | FY29 | 36 | 90015437 | B2 | 1000131507 | 03.10.2028 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-BUCYR | 6000 | 75558 | 7107
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Adjust 250hr Initial Valve Set | 2028-10-04 | 2028-10-04 | 6 hrs | FY29 | 12 | 90015780 | B1 | 1000290303 | 04.10.2028 | 250 | CCK-MP-GRDR-GR121 -ENGINE | 5200 | 67029 | 5487
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Hyd Pump Cooling Fan | 2028-10-06 | 2028-10-06 | 8 hrs | FY29 | 16 | 90004952 | B2 | 1000091105 | 06.10.2028 | 18000 | CCK-MP-DOZR-DZ170 -HYDSYS-HYDPP-HYFPP | 5000 | 54263 | 7185
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Overhaul Park Brake & Centre Brg | 2028-10-07 | 2028-10-08 | 18 hrs | FY29 | 36 | 90002711 | B2 | 1000090417 | 07.10.2028 | 10000 | CCK-MP-LOAD-WL267 -BRKSYS-BRPRK | 6000 | 74441 | 21055
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Operators Seat | 2028-10-07 | 2028-10-07 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000028906 | 07.10.2028 | 7000 | CCK-MP-LOAD-WL022 -STRUCT-CABIN-SEATS | 6000 | 80515 | 395
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Fan Cooling Motor Hyd | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 16 | 90002094 | B2 | 1000108426 | 10.10.2028 | 9000 | CCK-MP-DOZR-DZ173 -HYDSYS-HDCFM | 5000 | 68788 | 994
854K | Onsite PM | Ancillary | Fortescue | WD006 | WD006 Repl Torque Converter | 2028-10-11 | 2028-10-13 | 56 hrs | FY29 | 164 | 90002943 | B3 | 1000033566 | 11.10.2028 | 22000 | CCK-MP-DOZR-WD006 -TRNSYS-TRQUE | 6300 | 69386 | 8416
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Replace Artic Area Hyd Hosing | 2028-10-12 | 2028-10-12 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220498 | 12.10.2028 | 8 Monthly | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Cyl Steering RH | 2028-10-13 | 2028-10-13 | 14 hrs | FY29 | 28 | 90002722 | B2 | 1000028892 | 13.10.2028 | 12000 | CCK-MP-LOAD-WL022 -STRSYS-STRCY-STCYR | 6000 | 80515 | 10370
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Actuator Brake HaulX Shield | 2028-10-13 | 2028-10-14 | 26 hrs | FY29 | 50 | 90033520 | B1 | 1000337658 | 13.10.2028 | 30000 | CCK-MP-DOZR-WD204 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Front Drive Shaft Unis | 2028-10-16 | 2028-10-16 | 4 hrs | FY29 | 8 | 90033188 | B1 | 1000333570 | 16.10.2028 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT04 | 6000 | 72865 | 6385
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-10-16 | 2028-10-16 | 4 hrs | FY29 | 8 | 90033193 | B1 | 1000333572 | 16.10.2028 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT05 | 6000 | 72865 | 16811
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Actuator Brake HaulX Shield | 2028-10-16 | 2028-10-17 | 26 hrs | FY29 | 50 | 90033531 | B1 | 1000337783 | 16.10.2028 | 30000 | CCK-MP-LOAD-WL261 -MANGMT-CASYS-ACTBK
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Radiator Engine Cooling | 2028-10-17 | 2028-10-18 | 24 hrs | FY29 | 72 | 90002931 | B3 | 1000033617 | 17.10.2028 | 22000 | CCK-MP-DOZR-WD007 -ENGINE-COSYS-RADTR | 6300 | 76513 | 51585
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Aftercooler Engine | 2028-10-17 | 2028-10-17 | 12 hrs | FY29 | 12 | 90010216 | B3 | 1000082595 | 17.10.2028 | 22000 | CCK-MP-DOZR-WD007 -ENGINE-INTEX-AFTER | 6300 | 76489 | 8208
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Oil Cooler Front Axle Lube | 2028-10-17 | 2028-10-17 | 6 hrs | FY29 | 6 | 90010219 | B3 | 1000082623 | 17.10.2028 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-AXLEC-OILCF | 6300 | 76489 | 8208
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Cylinder Blade Lift LH | 2028-10-17 | 2028-10-17 | 6 hrs | FY29 | 12 | 90002965 | B1 | 1000033646 | 17.10.2028 | 22000 | CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BLCYL | 6300 | 76489 | 8208
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Hyd & Steering Oil Cooler | 2028-10-17 | 2028-10-17 | 12 hrs | FY29 | 24 | 90010218 | B3 | 1000082599 | 17.10.2028 | 22000 | CCK-MP-DOZR-WD007 -HYDSYS-HDOCO | 6300 | 76489 | 8208
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Refurbish Operators Cabin | 2028-10-17 | 2028-10-17 | 16 hrs | FY29 | 32 | 90002972 | B3 | 1000033653 | 17.10.2028 | 22000 | CCK-MP-DOZR-WD007 -STRUCT-CABIN | 6300 | 76489 | 8208
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Str Pilot Pump & Str Cooling | 2028-10-18 | 2028-10-18 | 4 hrs | FY29 | 4 | 90002959 | B3 | 1000092627 | 18.10.2028 | 15000 | CCK-MP-DOZR-WD202 -STRSYS-STPMP-STP02 | 6300 | 79903 | 15755
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Cyl Steering LH | 2028-10-18 | 2028-10-18 | 12 hrs | FY29 | 22 | 90002961 | B3 | 1000033641 | 18.10.2028 | 22000 | CCK-MP-DOZR-WD007 -STRSYS-STRCY-STCYL | 6300 | 76489 | 8208
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Repl Blade Mounting Bracket LH | 2028-10-19 | 2028-10-20 | 24 hrs | FY29 | 48 | 90002671 | B2 | 1000090868 | 19.10.2028 | 14000 | CCK-MP-GRDR-GR121 -STRUCT-CIRCL-BLMBL | 5200 | 67029 | 47997
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Hyd Pump Cooling Fan | 2028-10-19 | 2028-10-19 | 8 hrs | FY29 | 16 | 90004952 | B2 | 1000091345 | 19.10.2028 | 18000 | CCK-MP-DOZR-DZ183 -HYDSYS-HYDPP-HYFPP | 5000 | 65794 | 7056
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Repl Blade Mounting Bracket RH | 2028-10-20 | 2028-10-21 | 24 hrs | FY29 | 48 | 90002671 | B2 | 1000090869 | 20.10.2028 | 14000 | CCK-MP-GRDR-GR121 -STRUCT-CIRCL-BLMBR | 5200 | 67029 | 47997
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Replace Articulation Area Hosing | 2028-10-23 | 2028-10-23 | 6 hrs | FY29 | 6 | 90022236 | B1 | 1000257062 | 23.10.2028 | 8 Monthly | CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Transmission Pump | 2028-10-24 | 2028-10-24 | 6 hrs | FY29 | 12 | 90002694 | B2 | 1000138144 | 24.10.2028 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-TRPMP | 6000 | 72865 | 6666
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Front Differential | 2028-10-26 | 2028-10-29 | 66 hrs | FY29 | 132 | 90002951 | B3 | 1000033628 | 26.10.2028 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-FRDIF | 6300 | 76513 | 8036
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Final Drive Position 1 | 2028-10-26 | 2028-10-27 | 22 hrs | FY29 | 58 | 90002954 | B3 | 1000033631 | 26.10.2028 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR01 | 6300 | 76489 | 8036
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Cylinder Blade Lift RH | 2028-10-27 | 2028-10-27 | 6 hrs | FY29 | 12 | 90002966 | B1 | 1000033647 | 27.10.2028 | 22000 | CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BLCYR | 6300 | 76489 | 8208
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Replace Artic Area Hyd Hosing | 2028-10-30 | 2028-10-30 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220494 | 30.10.2028 | 8 Monthly | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Thermostats | 2028-11-01 | 2028-11-01 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222532 | 01.11.2028 | 5000 | CCK-MP-LOAD-WL261 -ENGINE-COSYS-THERM | 6000 | 77065 | 11736
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Service Air Conditioner | 2028-11-01 | 2028-11-02 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222522 | 01.11.2028 | 5000 | CCK-MP-LOAD-WL261 -STRUCT-CABIN-AIRCN | 6000 | 77065 | 11736
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Sepura SCC Microphone | 2028-11-01 | 2028-11-01 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000289595 | 01.11.2028 | 12 Monthly | CCK-MP-LOAD-WL021 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Replace Artic Area Hyd Hosing | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220501 | 02.11.2028 | 8 Monthly | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-ARTHO
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Sepura SCC Microphone | 2028-11-02 | 2028-11-02 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289551 | 02.11.2028 | 12 Monthly | CCK-MP-DOZR-DZ176 -COMMUN-RADIO | 5000 | 69693 | 69693
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Actuator Brake HaulX Shield | 2028-11-03 | 2028-11-04 | 26 hrs | FY29 | 50 | 90033520 | B1 | 1000337655 | 03.11.2028 | 30000 | CCK-MP-DOZR-WD007 -MANGMT-CASYS-ACTBK
16M | Onsite PM | Ancillary | Fortescue | GR015 | GR015 Repl Sepura SCC Microphone | 2028-11-05 | 2028-11-05 | 0.5 hrs | FY29 | 0.5 | 90028988 | B1 | 1000289365 | 05.11.2028 | 12 Monthly | CCK-MP-GRDR-GR015 -COMMUN-RADIO
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Cyl Blade Lift LH | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 16 | 90000287 | B1 | 1000255598 | 05.11.2028 | 9000 | CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BLCYL | 5000 | 54263 | 6767
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Operators Seat | 2028-11-10 | 2028-11-10 | 4 hrs | FY29 | 8 | 90000318 | B1 | 1000108523 | 10.11.2028 | 6000 | CCK-MP-DOZR-DZ181 -STRUCT-CABIN-SEATS | 5000 | 66297 | 691
16M | Onsite PM | Ancillary | Fortescue | GR014 | GR014 Repl Sepura SCC Microphone | 2028-11-11 | 2028-11-11 | 0.5 hrs | FY29 | 0.5 | 90028988 | B1 | 1000289364 | 11.11.2028 | 12 Monthly | CCK-MP-GRDR-GR014 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Replace Artic Area Hyd Hosing | 2028-11-14 | 2028-11-14 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220507 | 14.11.2028 | 8 Monthly | CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-ARTHO
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Actuator Brake HaulX Shield | 2028-11-14 | 2028-11-15 | 26 hrs | FY29 | 50 | 90033520 | B1 | 1000337656 | 14.11.2028 | 30000 | CCK-MP-DOZR-WD201 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Engine Midlife complete | 2028-11-15 | 2028-11-20 | 132 hrs | FY29 | 170 | 90021253 | B1 | 1000222376 | 15.11.2028 | 10000 | CCK-MP-LOAD-WL022 -ENGINE | 6000 | 80537 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Overhaul Air Conditioner | 2028-11-15 | 2028-11-17 | 48 hrs | FY29 | 48 | 90021132 | B1 | 1000222367 | 15.11.2028 | 10000 | CCK-MP-LOAD-WL022 -STRUCT-CABIN-AIRCN | 6000 | 80515 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Front Drive Shaft Unis | 2028-11-16 | 2028-11-16 | 4 hrs | FY29 | 8 | 90033188 | B1 | 1000333474 | 16.11.2028 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT04 | 6000 | 80537 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-11-16 | 2028-11-16 | 4 hrs | FY29 | 8 | 90033193 | B1 | 1000333476 | 16.11.2028 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT05 | 6000 | 80537 | 1654
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Fr Pump Drv Shaft Unis | 2028-11-16 | 2028-11-16 | 4 hrs | FY29 | 8 | 90033190 | B1 | 1000333478 | 16.11.2028 | 10000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT06 | 6000 | 80537 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Auto Lube Pump | 2028-11-16 | 2028-11-16 | 6 hrs | FY29 | 6 | 90002737 | B2 | 1000116256 | 16.11.2028 | 10000 | CCK-MP-LOAD-WL022 -GRSYST-ALBPP | 6000 | 80515 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Brake System Hoses Midlife | 2028-11-16 | 2028-11-16 | 4 hrs | FY29 | 4 | 90026908 | B1 | 1000271535 | 16.11.2028 | 10000 | CCK-MP-LOAD-WL022 -BRKSYS-BRHLF-BRKHO | 6000 | 80515 | 7474
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd System Hoses Midlife | 2028-11-16 | 2028-11-17 | 24 hrs | FY29 | 24 | 90026914 | B1 | 1000271537 | 16.11.2028 | 10000 | CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-HYDHO | 6000 | 80515 | 7474
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Sepura SCC Microphone | 2028-11-16 | 2028-11-16 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289558 | 16.11.2028 | 12 Monthly | CCK-MP-DOZR-DZ184 -COMMUN-RADIO | 5000 | 67674 | 8628
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Minor Service Air Conditioner | 2028-11-18 | 2028-11-18 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196615 | 18.11.2028 | 4500 | CCK-MP-DOZR-DZ171 -STRUCT-CABIN-AIRCN | 5000 | 67979 | 11227
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Steering RH | 2028-11-19 | 2028-11-20 | 18 hrs | FY29 | 36 | 90002717 | B2 | 1000028887 | 19.11.2028 | 20000 | CCK-MP-LOAD-WL022 -STRSYS-STPMP-STP02 | 6000 | 80515 | 5719
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Actuator Brake HaulX Shield | 2028-11-19 | 2028-11-20 | 26 hrs | FY29 | 50 | 90033520 | B1 | 1000337657 | 19.11.2028 | 30000 | CCK-MP-DOZR-WD202 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Final Drive Position 3 | 2028-11-21 | 2028-11-23 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000090606 | 21.11.2028 | 16000 | CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR03 | 6000 | 74342 | 1701
16M | Onsite PM | Ancillary | Fortescue | GR015 | GR015 Air Conditioner Minor Service | 2028-11-22 | 2028-11-22 | 12 hrs | FY29 | 12 | 90019351 | B1 | 1000269600 | 22.11.2028 | 3500 | CCK-MP-GRDR-GR015 -STRUCT-CABIN-AIRCN | 3200 | 42638 | 2788
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Replace Brake Hoses | 2028-11-24 | 2028-11-25 | 36 hrs | FY29 | 72 | 90010158 | 2 | 1000081922 | 24.11.2028 | 16000 | CCK-MP-LOAD-WL004 -BRKSYS-BRHLF | 3100 | 64003 | 15676
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Replace Powertrain Hoses | 2028-11-24 | 2028-11-25 | 36 hrs | FY29 | 72 | 90010156 | B1 | 1000081915 | 24.11.2028 | 16000 | CCK-MP-LOAD-WL004 -TRNSYS-TRHLF | 3100 | 64003 | 15676
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hydraulic System Hoses | 2028-11-25 | 2028-11-27 | 48 hrs | FY29 | 96 | 90026922 | B1 | 1000271582 | 25.11.2028 | 20000 | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-HYDHO | 6000 | 75558 | 9814
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hyd Motor & Pump Axle Cooling | 2028-11-25 | 2028-11-25 | 2 hrs | FY29 | 4 | 90002970 | B3 | 1000092687 | 25.11.2028 | 15000 | CCK-MP-DOZR-WD203 -HYDSYS-HYDMT-HYM02 | 6300 | 80875 | 995
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Articulation Overhaul | 2028-11-26 | 2028-12-04 | 194 hrs | FY29 | 360 | 90032991 | B1 | 1000329973 | 26.11.2028 | 16000 | CCK-MP-LOAD-WL266 -STRUCT-CHASS-ARTIC | 6000 | 74342 | 16795
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Actuator Brake HaulX Shield | 2028-11-26 | 2028-11-27 | 26 hrs | FY29 | 50 | 90033531 | B1 | 1000337786 | 26.11.2028 | 30000 | CCK-MP-LOAD-WL7162-MANGMT-CASYS-ACTBK
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Hyd Pump Cooling Fan | 2028-11-27 | 2028-11-27 | 4 hrs | FY29 | 8 | 90002964 | B3 | 1000092737 | 27.11.2028 | 15000 | CCK-MP-DOZR-WD204 -HYDSYS-HYDPP-HYP03 | 6300 | 83628 | 854
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Pump Str Pilot & Str Cooling | 2028-11-27 | 2028-11-27 | 4 hrs | FY29 | 4 | 90002959 | B3 | 1000092731 | 27.11.2028 | 15000 | CCK-MP-DOZR-WD204 -STRSYS-STPMP-STP02 | 6300 | 83628 | 854
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Hyd Pump Steer Secondary | 2028-11-27 | 2028-11-27 | 4 hrs | FY29 | 4 | 90002960 | B3 | 1000092732 | 27.11.2028 | 15000 | CCK-MP-DOZR-WD204 -STRSYS-STPMP-STP03 | 6300 | 83628 | 15298
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Transmission | 2028-11-27 | 2028-11-29 | 57 hrs | FY29 | 167 | 90002944 | B3 | 1000092714 | 27.11.2028 | 15000 | CCK-MP-DOZR-WD204 -TRNSYS-TRANS | 6300 | 83628 | 854
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Pump Transmission | 2028-11-27 | 2028-11-27 | 4 hrs | FY29 | 8 | 90002946 | B3 | 1000092715 | 27.11.2028 | 15000 | CCK-MP-DOZR-WD204 -TRNSYS-TRPMP | 6300 | 83628 | 854
16M | Onsite PM | Ancillary | Fortescue | GR014 | GR014 Repl Brake Assy LHR | 2028-11-29 | 2028-11-30 | 20 hrs | FY29 | 40 | 90002456 | B1 | 1000027366 | 29.11.2028 | 8000 | CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBLR | 3200 | 44181 | 297
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Sepura SCC Microphone | 2028-12-01 | 2028-12-01 | 0.5 hrs | FY29 | 0.5 | 90028997 | B1 | 1000289593 | 01.12.2028 | 12 Monthly | CCK-MP-LOAD-WL004 -COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Articulation Overhaul | 2028-12-04 | 2028-12-12 | 194 hrs | FY29 | 360 | 90032991 | B1 | 1000329970 | 04.12.2028 | 16000 | CCK-MP-LOAD-WL260 -STRUCT-CHASS-ARTIC | 6000 | 75558 | 18081
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Sepura SCC Microphone | 2028-12-06 | 2028-12-06 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000289601 | 06.12.2028 | 12 Monthly | CCK-MP-LOAD-WL266 -COMMUN-RADIO | 6000 | 74342 | 74342
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Torque Converter | 2028-12-08 | 2028-12-10 | 56 hrs | FY29 | 164 | 90002943 | B3 | 1000092713 | 08.12.2028 | 22000 | CCK-MP-DOZR-WD204 -TRNSYS-TRQUE | 6300 | 83628 | 7365
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Sepura SCC Microphone | 2028-12-08 | 2028-12-08 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289545 | 08.12.2028 | 12 Monthly | CCK-MP-DOZR-DZ170 -COMMUN-RADIO | 5000 | 54263 | 54263
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Engine Midlife complete | 2028-12-10 | 2028-12-12 | 60 hrs | FY29 | 72 | 90015782 | B1 | 1000290261 | 10.12.2028 | 7000 | CCK-MP-GRDR-GR120 -ENGINE | 5200 | 60265 | 8767
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Service Major Air Conditioner | 2028-12-10 | 2028-12-11 | 24 hrs | FY29 | 24 | 90017472 | B1 | 1000290265 | 10.12.2028 | 7000 | CCK-MP-GRDR-GR120 -STRUCT-CABIN-AIRCN | 5200 | 60265 | 18931
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Adjust Engine 500hr Valve Set | 2028-12-11 | 2028-12-11 | 8 hrs | FY29 | 16 | 90015857 | B1 | 1000160143 | 11.12.2028 | 500 | CCK-MP-DOZR-DZ172 -ENGINE | 5000 | 68264 | 6824
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Pump Transmission | 2028-12-14 | 2028-12-14 | 4 hrs | FY29 | 8 | 90002760 | B2 | 1000030459 | 14.12.2028 | 8000 | CCK-MP-LOAD-WL004 -TRNSYS-TRPMP | 3100 | 64003 | 527
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Operators Seat | 2028-12-14 | 2028-12-14 | 4 hrs | FY29 | 4 | 90002663 | B2 | 1000090802 | 14.12.2028 | 7000 | CCK-MP-GRDR-GR120 -STRUCT-CABIN-SEATS | 5200 | 60265 | 8768
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Clean Engine Pre Cleaners | 2028-12-15 | 2028-12-15 | 6 hrs | FY29 | 6 | 90015808 | B1 | 1000286594 | 15.12.2028 | 5500 | CCK-MP-DOZR-WD007 -ENGINE-INTEX-AIRFL
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Service Airconditioner | 2028-12-15 | 2028-12-16 | 24 hrs | FY29 | 24 | 90003915 | B1 | 1000286598 | 15.12.2028 | 5500 | CCK-MP-DOZR-WD007 -STRUCT-CABIN-AIRCN | 6300 | 76489 | 20596
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Sepura SCC Microphone | 2028-12-15 | 2028-12-15 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289546 | 15.12.2028 | 12 Monthly | CCK-MP-DOZR-DZ171 -COMMUN-RADIO | 5000 | 67979 | 67979
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Operators Seat | 2028-12-16 | 2028-12-16 | 4 hrs | FY29 | 8 | 90000318 | B1 | 1000108379 | 16.12.2028 | 6000 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN-SEATS | 5000 | 62015 | 11979
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Brake System Hoses | 2028-12-20 | 2028-12-21 | 24 hrs | FY29 | 48 | 90026921 | B1 | 1000271615 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -BRKSYS-BRHLF-BRKHO | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Brake Oil Cooler | 2028-12-20 | 2028-12-21 | 36 hrs | FY29 | 72 | 90002715 | B2 | 1000090538 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -BRKSYS-BROCC | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Brake Cooling | 2028-12-20 | 2028-12-20 | 8 hrs | FY29 | 8 | 90002713 | B2 | 1000090535 | 20.12.2028 | 10000 | CCK-MP-LOAD-WL269 -BRKSYS-BRPMP-BRP02 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Electrical Harness | 2028-12-20 | 2028-12-21 | 36 hrs | FY29 | 36 | 90010123 | B2 | 1000090563 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -ELCTLV-HARNS | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Radiator Engine Cooling | 2028-12-20 | 2028-12-22 | 54 hrs | FY29 | 102 | 90002682 | B2 | 1000090511 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -ENGINE-COSYS-RADTR | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Front Differential | 2028-12-20 | 2028-12-22 | 58 hrs | FY29 | 114 | 90002707 | B2 | 1000090527 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -FDRSYS-FRDIF | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Rear Differential | 2028-12-20 | 2028-12-22 | 58 hrs | FY29 | 114 | 90002708 | B2 | 1000090528 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -FDRSYS-RRDIF | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Overhaul Rear Axle Trunnion | 2028-12-20 | 2028-12-22 | 56 hrs | FY29 | 112 | 90002709 | B2 | 1000090529 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -FDRSYS-RRDIF-TRNON | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hydraulic System Hoses | 2028-12-20 | 2028-12-22 | 48 hrs | FY29 | 96 | 90026922 | B1 | 1000271617 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-HYDHO | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Oil Cooler | 2028-12-20 | 2028-12-22 | 48 hrs | FY29 | 96 | 90002733 | B2 | 1000090549 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -HYDSYS-HDOCO | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Reseal Tank Hyd | 2028-12-20 | 2028-12-20 | 12 hrs | FY29 | 12 | 90010623 | B2 | 1000090564 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -HYDSYS-HDTNK-HYT01 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 O/Haul Hyd Valve Implement Ctrl LH | 2028-12-20 | 2028-12-21 | 24 hrs | FY29 | 24 | 90010965 | B2 | 1000112593 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -HYDSYS-HDVLV-HYV01 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 O/Haul Hyd Valve Implement Ctrl RH | 2028-12-20 | 2028-12-21 | 24 hrs | FY29 | 24 | 90010966 | B2 | 1000112600 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -HYDSYS-HDVLV-HYV02 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Implement LH | 2028-12-20 | 2028-12-20 | 12 hrs | FY29 | 24 | 90002723 | B2 | 1000090545 | 20.12.2028 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP01 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Implement RH | 2028-12-20 | 2028-12-20 | 12 hrs | FY29 | 24 | 90002724 | B2 | 1000090546 | 20.12.2028 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP02 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Implement Centre | 2028-12-20 | 2028-12-20 | 12 hrs | FY29 | 24 | 90002725 | B2 | 1000090547 | 20.12.2028 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP03 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pilot Accumulator | 2028-12-20 | 2028-12-20 | 4 hrs | FY29 | 4 | 90012174 | B2 | 1000112614 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -HYDSYS-PACCM | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Main Airhoses & Valves | 2028-12-20 | 2028-12-21 | 18 hrs | FY29 | 18 | 90011137 | B2 | 1000112607 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -PNEUMC-PNHLF | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Replace Steering System Hoses | 2028-12-20 | 2028-12-22 | 48 hrs | FY29 | 96 | 90009732 | B2 | 1000090561 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STHLF-STRHO | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Steering STIC Pilot Valve | 2028-12-20 | 2028-12-20 | 12 hrs | FY29 | 12 | 90026110 | B1 | 1000257371 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STIPV | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Steering Neutralizer Valves | 2028-12-20 | 2028-12-20 | 6 hrs | FY29 | 6 | 90002720 | B2 | 1000090557 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STNVS | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Steering LH | 2028-12-20 | 2028-12-21 | 18 hrs | FY29 | 36 | 90002716 | B2 | 1000090539 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP01 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Hyd Pump Steering RH | 2028-12-20 | 2028-12-21 | 18 hrs | FY29 | 36 | 90002717 | B2 | 1000090540 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP02 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Steer & Brake Oil Cooler Pump | 2028-12-20 | 2028-12-20 | 8 hrs | FY29 | 8 | 90002718 | B2 | 1000090541 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP03 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Reseal Steering & Brake Tank | 2028-12-20 | 2028-12-21 | 18 hrs | FY29 | 36 | 90010963 | B2 | 1000112586 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -STRSYS-STTNK | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Input Drive Shaft | 2028-12-20 | 2028-12-20 | 6 hrs | FY29 | 12 | 90033166 | B1 | 1000333551 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT01 | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Transmission Oil Cooler | 2028-12-20 | 2028-12-21 | 18 hrs | FY29 | 36 | 90002695 | B2 | 1000090515 | 20.12.2028 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-TROLC | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Transmission Charge Pump | 2028-12-20 | 2028-12-20 | 6 hrs | FY29 | 12 | 90002694 | B2 | 1000090514 | 20.12.2028 | 10000 | CCK-MP-LOAD-WL269 -TRNSYS-TRPMP | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Artic Area Hyd Hosing | 2028-12-21 | 2028-12-21 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000364487 | 21.12.2028 | 8 Monthly | CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-ARTHO
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Drive Shaft Unis | 2028-12-21 | 2028-12-21 | 3 hrs | FY29 | 6 | 90033292 | B1 | 1000334102 | 21.12.2028 | 9000 | CCK-MP-DOZR-DZ170 -TRNSYS | 5000 | 54263 | 15137
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Clean Engine Pre Cleaners | 2028-12-22 | 2028-12-22 | 6 hrs | FY29 | 6 | 90015808 | B1 | 1000286615 | 22.12.2028 | 5500 | CCK-MP-DOZR-WD203 -ENGINE-INTEX-AIRFL | 6300 | 80875 | 44315
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Service Airconditioner | 2028-12-22 | 2028-12-23 | 24 hrs | FY29 | 24 | 90003915 | B1 | 1000286619 | 22.12.2028 | 5500 | CCK-MP-DOZR-WD203 -STRUCT-CABIN-AIRCN | 6300 | 80875 | 13604
16M | Onsite PM | Ancillary | Fortescue | GR015 | GR015 Repl Hyd Motor Fan Hyd Cooler | 2028-12-23 | 2028-12-23 | 8 hrs | FY29 | 8 | 90002464 | B1 | 1000027434 | 23.12.2028 | 14000 | CCK-MP-GRDR-GR015 -HYDSYS-HDMOT-MOFAN | 3200 | 42638 | 19541
16M | Onsite PM | Ancillary | Fortescue | GR015 | GR015 Repl Gearbox Circle Drive | 2028-12-24 | 2028-12-24 | 8 hrs | FY29 | 14 | 90002481 | B1 | 1000027453 | 24.12.2028 | 14000 | CCK-MP-GRDR-GR015 -STRUCT-CIRCL-CDRBX | 3200 | 42638 | 12705
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Hyd Pump Implement | 2028-12-25 | 2028-12-25 | 10 hrs | FY29 | 10 | 90000301 | B2 | 1000091222 | 25.12.2028 | 9000 | CCK-MP-DOZR-DZ176 -HYDSYS-HYDPP-HYIPP | 5000 | 69680 | 5908
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Cyl Blade Lift RH | 2028-12-25 | 2028-12-25 | 8 hrs | FY29 | 14 | 90018821 | B1 | 1000225818 | 25.12.2028 | 9000 | CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-BLCYR | 5000 | 23802 | 6195
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Steer Clutch & Brake Assm LH | 2028-12-27 | 2028-12-27 | 14 hrs | FY29 | 28 | 90000313 | B2 | 1000091220 | 27.12.2028 | 18000 | CCK-MP-DOZR-DZ176 -BRKSTR-SCABL | 5000 | 69693 | 5898
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Cyl Blade Lift RH | 2028-12-27 | 2028-12-27 | 8 hrs | FY29 | 16 | 90000287 | B1 | 1000255679 | 27.12.2028 | 9000 | CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-BLCYR | 5000 | 66297 | 6103
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Adjust 250hr Initial Valve Set | 2029-01-01 | 2029-01-01 | 6 hrs | FY29 | 12 | 90015780 | B1 | 1000290310 | 01.01.2029 | 250 | CCK-MP-GRDR-GR122 -ENGINE | 5200 | 68036 | 1754
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl STIC Steering Valve | 2029-01-04 | 2029-01-04 | 12 hrs | FY29 | 12 | 90026110 | B1 | 1000257375 | 04.01.2029 | 20000 | CCK-MP-LOAD-WL7104-STRSYS-STIPV | 4000 | 64060 | 9837
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Ovhl Hydraulic & Fuel Tank | 2029-01-04 | 2029-01-05 | 24 hrs | FY29 | 48 | 90010842 | B1 | 1000108550 | 04.01.2029 | 18000 | CCK-MP-DOZR-DZ183 -HYDSYS-HDTNK | 5000 | 65794 | 6009
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Drive Shaft | 2029-01-04 | 2029-01-04 | 3 hrs | FY29 | 6 | 90033296 | B1 | 1000334125 | 04.01.2029 | 18000 | CCK-MP-DOZR-DZ183 -TRNSYS | 5000 | 65794 | 34266
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Auto Lube Pump | 2029-01-10 | 2029-01-10 | 6 hrs | FY29 | 6 | 90002737 | B2 | 1000138180 | 10.01.2029 | 10000 | CCK-MP-LOAD-WL7103-GRSYST-ALBPP | 6000 | 72865 | 15227
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Pilot Hyd Cooling Pump | 2029-01-10 | 2029-01-10 | 6 hrs | FY29 | 12 | 90002726 | B2 | 1000138176 | 10.01.2029 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP04 | 6000 | 72865 | 16811
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Front Pump Drv Drive Shaft | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 16 | 90033189 | B1 | 1000333573 | 10.01.2029 | 20000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT06 | 6000 | 72865 | 5406
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Air Conditioner Minor Service | 2029-01-10 | 2029-01-10 | 6 hrs | FY29 | 6 | 90018856 | B1 | 1000225826 | 10.01.2029 | 4500 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN-AIRCN | 5000 | 23802 | 10459
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 12 Monthly Hydraulic Tune Up | 2029-01-12 | 2029-01-12 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000126196 | 12.01.2029 | 52 Weekly | CCK-MP-LOAD-WL260 -HYDSYS | 6000 | 75558 | 75558
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Pump Trans & TCon Charge | 2029-01-12 | 2029-01-12 | 10 hrs | FY29 | 10 | 90000302 | B2 | 1000091289 | 12.01.2029 | 18000 | CCK-MP-DOZR-DZ181 -TRNSYS-TRPMP | 5000 | 66297 | 5876
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hyd Motor & Pump Axle Cooling | 2029-01-20 | 2029-01-20 | 2 hrs | FY29 | 4 | 90002970 | B3 | 1000092585 | 20.01.2029 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDMT-HYM02 | 6300 | 81082 | 14552
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Sepura SCC Microphone | 2029-01-21 | 2029-01-21 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289548 | 21.01.2029 | 12 Monthly | CCK-MP-DOZR-DZ173 -COMMUN-RADIO | 5000 | 68788 | 68788
D10T | Onsite PM | Ancillary | Fortescue | DZ173 | DZ173 Repl Operators Seat | 2029-01-22 | 2029-01-22 | 4 hrs | FY29 | 8 | 90000318 | B1 | 1000108427 | 22.01.2029 | 6000 | CCK-MP-DOZR-DZ173 -STRUCT-CABIN-SEATS | 5000 | 68788 | 11495
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Refurbish Cabin | 2029-01-22 | 2029-01-23 | 18 hrs | FY29 | 18 | 90018839 | B1 | 1000225816 | 22.01.2029 | 36000 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN | 5000 | 23802 | 23802
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Track Frame LH | 2029-01-22 | 2029-01-24 | 46 hrs | FY29 | 90 | 90033095 | B1 | 1000331940 | 22.01.2029 | 36000 | CCK-MP-DOZR-DZ8235-STRUCT-UNDER-TKFRL | 5000 | 23802 | 7343
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Track Frame RH | 2029-01-22 | 2029-01-24 | 46 hrs | FY29 | 90 | 90033096 | B1 | 1000331942 | 22.01.2029 | 36000 | CCK-MP-DOZR-DZ8235-STRUCT-UNDER-TKFRR | 5000 | 23802 | 7343
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Hyd Pump Implement | 2029-01-24 | 2029-01-24 | 10 hrs | FY29 | 10 | 90000301 | B2 | 1000091078 | 24.01.2029 | 9000 | CCK-MP-DOZR-DZ169 -HYDSYS-HYDPP-HYIPP | 5000 | 62015 | 5429
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Radiator Engine Cooling | 2029-01-24 | 2029-01-26 | 54 hrs | FY29 | 102 | 90002682 | B2 | 1000028792 | 24.01.2029 | 20000 | CCK-MP-LOAD-WL021 -ENGINE-COSYS-RADTR | 6000 | 79997 | 61894
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Transmission Oil Cooler | 2029-01-24 | 2029-01-25 | 18 hrs | FY29 | 36 | 90002695 | B2 | 1000028797 | 24.01.2029 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-TROLC | 6000 | 79997 | 24580
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Sepura SCC Microphone | 2029-01-24 | 2029-01-24 | 0.5 hrs | FY29 | 0.5 | 90028996 | B1 | 1000289584 | 24.01.2029 | 12 Monthly | CCK-MP-DOZR-WD203 -COMMUN-RADIO | 6300 | 80875 | 80875
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Operators Seat | 2029-01-27 | 2029-01-27 | 2 hrs | FY29 | 2 | 90002797 | B2 | 1000110129 | 27.01.2029 | 6000 | CCK-MP-LOAD-WL004 -STRUCT-CABIN-SEATS | 3100 | 64003 | 4210
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Engine Midlife Complete | 2029-01-27 | 2029-01-29 | 53 hrs | FY29 | 61 | 90018853 | B1 | 1000225427 | 27.01.2029 | 9000 | CCK-MP-DOZR-DZ8234-ENGINE | 5000 | 26641 | 14816
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Wash Engine Pre Cleaners | 2029-01-27 | 2029-01-27 | 2 hrs | FY29 | 2 | 90018848 | B1 | 1000225428 | 27.01.2029 | 9000 | CCK-MP-DOZR-DZ8234-ENGINE-INTEX-AIRFL
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Air Conditioner Service | 2029-01-27 | 2029-01-28 | 24 hrs | FY29 | 24 | 90018855 | B1 | 1000225420 | 27.01.2029 | 9000 | CCK-MP-DOZR-DZ8234-STRUCT-CABIN-AIRCN | 5000 | 26629 | 12967
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8235 | DZ8235 Repl Operators Seat | 2029-01-31 | 2029-01-31 | 4 hrs | FY29 | 8 | 90018835 | B1 | 1000225852 | 31.01.2029 | 6000 | CCK-MP-DOZR-DZ8235-STRUCT-CABIN-SEATS | 5000 | 23802 | 5679
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Shaft TConverter to Trans | 2029-02-02 | 2029-02-02 | 2 hrs | FY29 | 4 | 90002947 | B3 | 1000268430 | 02.02.2029 | 22000 | CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT01 | 6300 | 76513 | 8208
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Sepura SCC Microphone | 2029-02-04 | 2029-02-04 | 0.5 hrs | FY29 | 0.5 | 90028989 | B1 | 1000289371 | 04.02.2029 | 12 Monthly | CCK-MP-GRDR-GR120 -COMMUN-RADIO | 5200 | 60265 | 60265
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Minor Service Air Conditioner | 2029-02-05 | 2029-02-05 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196655 | 05.02.2029 | 4500 | CCK-MP-DOZR-DZ183 -STRUCT-CABIN-AIRCN | 5000 | 65794 | 25789
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Actuator Brake HaulX Shield | 2029-02-08 | 2029-02-09 | 26 hrs | FY29 | 50 | 90033531 | B1 | 1000337782 | 08.02.2029 | 30000 | CCK-MP-LOAD-WL022 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Thermostats | 2029-02-10 | 2029-02-10 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222356 | 10.02.2029 | 5000 | CCK-MP-LOAD-WL021 -ENGINE-COSYS-THERM | 6000 | 79974 | 9601
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Service Air Conditioner | 2029-02-10 | 2029-02-11 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222346 | 10.02.2029 | 5000 | CCK-MP-LOAD-WL021 -STRUCT-CABIN-AIRCN | 6000 | 79974 | 19277
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 12 Monthly Hydraulic Tune Up | 2029-02-13 | 2029-02-13 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000126199 | 13.02.2029 | 52 Weekly | CCK-MP-LOAD-WL266 -HYDSYS | 6000 | 74342 | 31864
24M | Onsite PM | Ancillary | Fortescue | GR120 | GR120 Repl Hyd Pump Brake & Fan | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 8 | 90002648 | B2 | 1000090796 | 13.02.2029 | 14000 | CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-FANPP | 5200 | 60265 | 559
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Cyl Blade Lift LH | 2029-02-14 | 2029-02-14 | 8 hrs | FY29 | 14 | 90031953 | B1 | 1000225389 | 14.02.2029 | 9000 | CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BLCYL | 5000 | 26629 | 5612
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Shaft TConverter to Trans | 2029-02-15 | 2029-02-15 | 2 hrs | FY29 | 4 | 90002947 | B3 | 1000268462 | 15.02.2029 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT01 | 6300 | 83628 | 7365
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Shaft Centre Brg to Fr Diff | 2029-02-15 | 2029-02-15 | 4 hrs | FY29 | 8 | 90002950 | B3 | 1000268468 | 15.02.2029 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT04 | 6300 | 83628 | 19866
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Hyd Pump Implement | 2029-02-15 | 2029-02-15 | 10 hrs | FY29 | 10 | 90000301 | B2 | 1000091102 | 15.02.2029 | 9000 | CCK-MP-DOZR-DZ170 -HYDSYS-HYDPP-HYIPP | 5000 | 54263 | 5339
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Operators Seat | 2029-02-15 | 2029-02-15 | 4 hrs | FY29 | 8 | 90000318 | B1 | 1000108391 | 15.02.2029 | 6000 | CCK-MP-DOZR-DZ170 -STRUCT-CABIN-SEATS | 5000 | 54263 | 5339
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Steering LH | 2029-02-16 | 2029-02-17 | 18 hrs | FY29 | 36 | 90002716 | B2 | 1000028886 | 16.02.2029 | 20000 | CCK-MP-LOAD-WL022 -STRSYS-STPMP-STP01 | 6000 | 80515 | 24304
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Engine Cat C27 | 2029-02-16 | 2029-02-18 | 60 hrs | FY29 | 114 | 90015849 | B1 | 1000160110 | 16.02.2029 | 18000 | CCK-MP-DOZR-DZ170 -ENGINE | 5000 | 54263 | 5287
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Overhaul Air Conditioner | 2029-02-16 | 2029-02-18 | 48 hrs | FY29 | 48 | 90017468 | B1 | 1000196611 | 16.02.2029 | 18000 | CCK-MP-DOZR-DZ170 -STRUCT-CABIN-AIRCN | 5000 | 54263 | 15137
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Rear Output Drive Shaft | 2029-02-17 | 2029-02-17 | 7 hrs | FY29 | 14 | 90033168 | B1 | 1000333469 | 17.02.2029 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT02 | 6000 | 80537 | 7470
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Repl Sepura SCC Microphone | 2029-02-17 | 2029-02-17 | 0.5 hrs | FY29 | 0.5 | 90028996 | B1 | 1000289581 | 17.02.2029 | 12 Monthly | CCK-MP-DOZR-WD007 -COMMUN-RADIO
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Replace Shaft Trans to Rear Diff | 2029-02-18 | 2029-02-18 | 4 hrs | FY29 | 8 | 90002948 | B3 | 1000268464 | 18.02.2029 | 22000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT02 | 6300 | 83628 | 7365
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Operators Seat | 2029-02-19 | 2029-02-19 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000090553 | 19.02.2029 | 7000 | CCK-MP-LOAD-WL269 -STRUCT-CABIN-SEATS | 6000 | 74583 | 5623
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Thermostats | 2029-02-19 | 2029-02-19 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222510 | 19.02.2029 | 5000 | CCK-MP-LOAD-WL260 -ENGINE-COSYS-THERM | 6000 | 75558 | 38
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Service Air Conditioner | 2029-02-19 | 2029-02-20 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222500 | 19.02.2029 | 5000 | CCK-MP-LOAD-WL260 -STRUCT-CABIN-AIRCN | 6000 | 75558 | 9814
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Sepura SCC Microphone | 2029-02-19 | 2029-02-19 | 0.5 hrs | FY29 | 0.5 | 90028989 | B1 | 1000289540 | 19.02.2029 | 12 Monthly | CCK-MP-GRDR-GR7107-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Transmission Oil Cooler | 2029-02-20 | 2029-02-21 | 18 hrs | FY29 | 36 | 90002695 | B2 | 1000028862 | 20.02.2029 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-TROLC | 6000 | 80537 | 24232
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Gearbox Pump Drive Rear | 2029-02-20 | 2029-02-27 | 182 hrs | FY29 | 326 | 90002706 | B2 | 1000028873 | 20.02.2029 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-PMPDR-RRPDR | 6000 | 80515 | 24232
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Input Drive Shaft | 2029-02-20 | 2029-02-20 | 6 hrs | FY29 | 12 | 90033166 | B1 | 1000333467 | 20.02.2029 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT01 | 6000 | 80537 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Centre Output Drive Shaft | 2029-02-21 | 2029-02-21 | 7 hrs | FY29 | 14 | 90033171 | B1 | 1000333471 | 21.02.2029 | 20000 | CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT03 | 6000 | 80537 | 7470
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Operators Seat | 2029-02-21 | 2029-02-21 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000028841 | 21.02.2029 | 7000 | CCK-MP-LOAD-WL021 -STRUCT-CABIN-SEATS | 6000 | 79974 | 5126
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Torque Converter | 2029-02-21 | 2029-02-22 | 30 hrs | FY29 | 60 | 90000309 | B2 | 1000091094 | 21.02.2029 | 18000 | CCK-MP-DOZR-DZ170 -TRNSYS-TRQUE | 5000 | 54263 | 5287
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Steering Cylinder LH | 2029-02-22 | 2029-02-22 | 14 hrs | FY29 | 26 | 90002721 | B2 | 1000138171 | 22.02.2029 | 12000 | CCK-MP-LOAD-WL7103-STRSYS-STRCY-STCYL | 6000 | 72865 | 8691
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Overhaul Boom | 2029-02-24 | 2029-02-26 | 48 hrs | FY29 | 96 | 90021334 | B1 | 1000223862 | 24.02.2029 | 40000 | CCK-MP-LOAD-WL269 -STRUCT-CHASS-LIARM | 6000 | 74583 | 74583
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Cyl Lift LH Ext High Lift | 2029-02-24 | 2029-02-25 | 28 hrs | FY29 | 54 | 90002728 | B2 | 1000112665 | 24.02.2029 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-HCYLL | 6000 | 77065 | 4775
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Steering LH | 2029-02-25 | 2029-02-25 | 14 hrs | FY29 | 26 | 90002721 | B2 | 1000090395 | 25.02.2029 | 12000 | CCK-MP-LOAD-WL267 -STRSYS-STRCY-STCYL | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Cyl Steering RH | 2029-02-25 | 2029-02-25 | 14 hrs | FY29 | 28 | 90002722 | B2 | 1000090396 | 25.02.2029 | 12000 | CCK-MP-LOAD-WL267 -STRSYS-STRCY-STCYR | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Trans System Hoses Midlife | 2029-02-25 | 2029-02-25 | 4 hrs | FY29 | 4 | 90026915 | B1 | 1000271608 | 25.02.2029 | 8000 | CCK-MP-LOAD-WL267 -TRNSYS-TRHLF-TRNHO | 6000 | 74441 | 8258
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hyd Pump Implement | 2029-03-01 | 2029-03-01 | 6 hrs | FY29 | 12 | 90002962 | B3 | 1000092683 | 01.03.2029 | 15000 | CCK-MP-DOZR-WD203 -HYDSYS-HYDPP-HYP01 | 6300 | 80875 | 995
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hyd Pump Steering Main | 2029-03-01 | 2029-03-01 | 6 hrs | FY29 | 12 | 90002958 | B3 | 1000092678 | 01.03.2029 | 15000 | CCK-MP-DOZR-WD203 -STRSYS-STPMP-STP01 | 6300 | 80875 | 995
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Sepura SCC Microphone | 2029-03-01 | 2029-03-01 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289547 | 01.03.2029 | 12 Monthly | CCK-MP-DOZR-DZ172 -COMMUN-RADIO | 5000 | 68264 | 6824
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Replace Brake System Hoses | 2029-03-03 | 2029-03-04 | 24 hrs | FY29 | 48 | 90013050 | B3 | 1000109632 | 03.03.2029 | 15000 | CCK-MP-DOZR-WD203 -BRKSYS-BRHLF | 6300 | 80875 | 13604
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Replace Hoses Steering System | 2029-03-03 | 2029-03-04 | 24 hrs | FY29 | 48 | 90013051 | B3 | 1000109633 | 03.03.2029 | 15000 | CCK-MP-DOZR-WD203 -STRSYS-STHLF | 6300 | 80875 | 13604
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Replace Hyd Pilot System Hoses | 2029-03-03 | 2029-03-03 | 12 hrs | FY29 | 24 | 90013052 | B3 | 1000231930 | 03.03.2029 | 15000 | CCK-MP-DOZR-WD203 -HYDSYS-HDHLF-HDHPS | 6300 | 80898 | 13604
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Hoses Main Hyd-Fan System | 2029-03-03 | 2029-03-04 | 24 hrs | FY29 | 48 | 90013053 | B3 | 1000231931 | 03.03.2029 | 15000 | CCK-MP-DOZR-WD203 -HYDSYS-HDHLF-HDHMH | 6300 | 80898 | 13604
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Actuator Brake HaulX Shield | 2029-03-03 | 2029-03-04 | 26 hrs | FY29 | 50 | 90033520 | B1 | 1000337791 | 03.03.2029 | 30000 | CCK-MP-DOZR-WD203 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Operators Seat | 2029-03-08 | 2029-03-08 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000138269 | 08.03.2029 | 7000 | CCK-MP-LOAD-WL7104-STRUCT-CABIN-SEATS | 4000 | 64060 | 3143
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Replace Shaft Universals Centre | 2029-03-08 | 2029-03-08 | 3 hrs | FY29 | 6 | 90026668 | B1 | 1000268467 | 08.03.2029 | 11000 | CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT03 | 6300 | 83628 | 2002
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Overhaul Park Brake & Centre Brg | 2029-03-10 | 2029-03-11 | 18 hrs | FY29 | 36 | 90002711 | B2 | 1000090269 | 10.03.2029 | 10000 | CCK-MP-LOAD-WL260 -BRKSYS-BRPRK | 6000 | 75566 | 4503
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Gearbox Pump Drive Rear | 2029-03-10 | 2029-03-17 | 182 hrs | FY29 | 326 | 90002706 | B2 | 1000090230 | 10.03.2029 | 20000 | CCK-MP-LOAD-WL260 -TRNSYS-PMPDR-RRPDR | 6000 | 75558 | 4503
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Replace Artic Area Hyd Hosing | 2029-03-11 | 2029-03-11 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220496 | 11.03.2029 | 8 Monthly | CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 12 Monthly Hydraulic Tune Up | 2029-03-12 | 2029-03-12 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000126740 | 12.03.2029 | 52 Weekly | CCK-MP-LOAD-WL267 -HYDSYS | 6000 | 74441 | 8258
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Wheel Lean LH | 2029-03-12 | 2029-03-12 | 4 hrs | FY29 | 4 | 90021515 | B1 | 1000225890 | 12.03.2029 | 6000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYL | 5500 | 24399 | 3609
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Wheel Lean RH | 2029-03-12 | 2029-03-12 | 4 hrs | FY29 | 4 | 90021515 | B1 | 1000225891 | 12.03.2029 | 6000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYR | 5500 | 24399 | 3609
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Repl Operators Seat | 2029-03-14 | 2029-03-14 | 4 hrs | FY29 | 8 | 90000318 | B1 | 1000108559 | 14.03.2029 | 6000 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN-SEATS | 5000 | 67674 | 5213
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Brake Cooling Pump | 2029-03-16 | 2029-03-16 | 8 hrs | FY29 | 8 | 90002713 | B2 | 1000138164 | 16.03.2029 | 10000 | CCK-MP-LOAD-WL7103-BRKSYS-BRPMP-BRP02 | 6000 | 72865 | 12306
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Operators Seat | 2029-03-17 | 2029-03-17 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000090627 | 17.03.2029 | 7000 | CCK-MP-LOAD-WL266 -STRUCT-CABIN-SEATS | 6000 | 74342 | 5199
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Transmission | 2029-03-17 | 2029-03-18 | 38 hrs | FY29 | 74 | 90002692 | B2 | 1000028860 | 17.03.2029 | 16000 | CCK-MP-LOAD-WL022 -TRNSYS-TRANS | 6000 | 80537 | 15801
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Clean Engine Pre Cleaners | 2029-03-17 | 2029-03-17 | 6 hrs | FY29 | 6 | 90015808 | B1 | 1000286608 | 17.03.2029 | 5500 | CCK-MP-DOZR-WD202 -ENGINE-INTEX-AIRFL | 6300 | 79903 | 21666
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Service Airconditioner | 2029-03-17 | 2029-03-18 | 24 hrs | FY29 | 24 | 90003915 | B1 | 1000286612 | 17.03.2029 | 5500 | CCK-MP-DOZR-WD202 -STRUCT-CABIN-AIRCN | 6300 | 79903 | 10962
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Gearbox Pump Drive Front | 2029-03-18 | 2029-03-19 | 38 hrs | FY29 | 74 | 90002705 | B2 | 1000028872 | 18.03.2029 | 16000 | CCK-MP-LOAD-WL022 -TRNSYS-PMPDR-FRPDR | 6000 | 80515 | 1155
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Articulation Overhaul | 2029-03-18 | 2029-03-26 | 194 hrs | FY29 | 360 | 90032991 | B1 | 1000329969 | 18.03.2029 | 16000 | CCK-MP-LOAD-WL022 -STRUCT-CHASS-ARTIC | 6000 | 80515 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Axle Shaft Position 1 | 2029-03-18 | 2029-03-18 | 6 hrs | FY29 | 12 | 90012242 | B2 | 1000101202 | 18.03.2029 | 32000 | CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP1 | 6000 | 80515 | 15801
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Ctr Output Drive Shaft Unis | 2029-03-21 | 2029-03-21 | 4 hrs | FY29 | 8 | 90033173 | B1 | 1000333520 | 21.03.2029 | 10000 | CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT03 | 6000 | 74342 | 14189
854K | Onsite PM | Ancillary | Fortescue | WD007 | WD007 Overhaul Axle Oscillation Rear | 2029-03-22 | 2029-03-23 | 24 hrs | FY29 | 64 | 90002953 | B3 | 1000033630 | 22.03.2029 | 15000 | CCK-MP-DOZR-WD007 -FDRSYS-RRDIF-TRNON | 6300 | 76489 | 13479
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Adjust Engine 500hr Valve Set | 2029-03-25 | 2029-03-25 | 8 hrs | FY29 | 16 | 90015857 | B1 | 1000160119 | 25.03.2029 | 500 | CCK-MP-DOZR-DZ170 -ENGINE | 5000 | 54263 | 5287
D10T | Onsite PM | Ancillary | Fortescue | DZ176 | DZ176 Repl Transmission | 2029-03-27 | 2029-03-28 | 24 hrs | FY29 | 48 | 90000308 | B2 | 1000091215 | 27.03.2029 | 18000 | CCK-MP-DOZR-DZ176 -TRNSYS-TRANS | 5000 | 69680 | 4667
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 12 Monthly Hydraulic Tune Up | 2029-03-28 | 2029-03-28 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000126743 | 28.03.2029 | 52 Weekly | CCK-MP-LOAD-WL022 -HYDSYS
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Pump AOC Front | 2029-03-28 | 2029-03-28 | 12 hrs | FY29 | 12 | 90016378 | B1 | 1000257038 | 28.03.2029 | 18000 | CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP03 | 6100 | 25829 | 2192
D10T | Onsite PM | Ancillary | Fortescue | DZ181 | DZ181 Repl Fan Cooling Motor Hyd | 2029-03-28 | 2029-03-28 | 8 hrs | FY29 | 16 | 90002094 | B2 | 1000108522 | 28.03.2029 | 9000 | CCK-MP-DOZR-DZ181 -HYDSYS-HDCFM | 5000 | 66297 | 4853
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Front Pump Drv Drive Shaft | 2029-03-30 | 2029-03-30 | 8 hrs | FY29 | 16 | 90033189 | B1 | 1000333561 | 30.03.2029 | 20000 | CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT06 | 6000 | 74583 | 4006
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Artic Area Hyd Hosing | 2029-04-01 | 2029-04-01 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000321324 | 01.04.2029 | 8 Monthly | CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-ARTHO
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Replace High Risk Hoses | 2029-04-05 | 2029-04-05 | 8 hrs | FY29 | 8 | 90021799 | B2 | 1000291756 | 05.04.2029 | 8000 | CCK-MP-LOAD-WL004 -ENGINE | 3100 | 64006 | 15676
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Engine Midlife Complete | 2029-04-05 | 2029-04-08 | 68 hrs | FY29 | 80 | 90015824 | B1 | 1000291753 | 05.04.2029 | 8000 | CCK-MP-LOAD-WL004 -ENGINE | 3100 | 64006 | 15676
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Wash Engine Pre Cleaners | 2029-04-05 | 2029-04-05 | 2 hrs | FY29 | 2 | 90017388 | B1 | 1000291750 | 05.04.2029 | 8000 | CCK-MP-LOAD-WL004 -ENGINE-INTEX-AIRFL
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Bucket Cyl Tilt LH | 2029-04-05 | 2029-04-05 | 14 hrs | FY29 | 28 | 90002788 | B2 | 1000080566 | 05.04.2029 | 12000 | CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-BUCYL | 3100 | 64003 | 15676
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Repl Bucket Cyl Tilt RH | 2029-04-05 | 2029-04-05 | 14 hrs | FY29 | 28 | 90002789 | B2 | 1000080567 | 05.04.2029 | 12000 | CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-BUCYR | 3100 | 64003 | 15676
993K | Onsite PM | Ancillary | Fortescue | WL004 | WL004 Overhaul Air Conditioner | 2029-04-05 | 2029-04-07 | 48 hrs | FY29 | 48 | 90017479 | B1 | 1000291755 | 05.04.2029 | 8000 | CCK-MP-LOAD-WL004 -STRUCT-CABIN-AIRCN | 3100 | 64003 | 8684
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Minor Service Air Conditioner | 2029-04-06 | 2029-04-06 | 12 hrs | FY29 | 12 | 90019636 | B1 | 1000201880 | 06.04.2029 | 3500 | CCK-MP-GRDR-GR7107-STRUCT-CABIN-AIRCN | 5500 | 24399 | 9687
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Replace Artic Area Hyd Hosing | 2029-04-07 | 2029-04-07 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220503 | 07.04.2029 | 8 Monthly | CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Cyl Steering LH | 2029-04-07 | 2029-04-07 | 14 hrs | FY29 | 26 | 90002721 | B2 | 1000028891 | 07.04.2029 | 12000 | CCK-MP-LOAD-WL022 -STRSYS-STRCY-STCYL | 6000 | 80515 | 7470
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Pump Str Pilot & Str Cooling | 2029-04-07 | 2029-04-07 | 4 hrs | FY29 | 4 | 90002959 | B3 | 1000092679 | 07.04.2029 | 15000 | CCK-MP-DOZR-WD203 -STRSYS-STPMP-STP02 | 6300 | 80875 | 995
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Service Brake LHF | 2029-04-11 | 2029-04-12 | 24 hrs | FY29 | 48 | 90019593 | B1 | 1000201893 | 11.04.2029 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBLF | 5500 | 24399 | 13118
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Service Brake LHR | 2029-04-11 | 2029-04-12 | 24 hrs | FY29 | 48 | 90019611 | B1 | 1000201895 | 11.04.2029 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBLR | 5500 | 24399 | 13118
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Service Brake RHF | 2029-04-11 | 2029-04-12 | 24 hrs | FY29 | 48 | 90019593 | B1 | 1000201894 | 11.04.2029 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBRF | 5500 | 24399 | 13118
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Service Brake RHR | 2029-04-11 | 2029-04-12 | 24 hrs | FY29 | 48 | 90019611 | B1 | 1000201896 | 11.04.2029 | 14000 | CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBRR | 5500 | 24399 | 13118
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Steering STIC Pilot Valve | 2029-04-12 | 2029-04-12 | 12 hrs | FY29 | 12 | 90026110 | B1 | 1000257369 | 12.04.2029 | 20000 | CCK-MP-LOAD-WL267 -STRSYS-STIPV | 6000 | 74441 | 24025
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Brake Accumulator Front | 2029-04-12 | 2029-04-12 | 4 hrs | FY29 | 4 | 90002955 | B3 | 1000092675 | 12.04.2029 | 22000 | CCK-MP-DOZR-WD203 -BRKSYS-BACCM-BACCF | 6300 | 80898 | 27939
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Transmission Transfer Case | 2029-04-14 | 2029-04-15 | 38 hrs | FY29 | 74 | 90017029 | B2 | 1000153211 | 14.04.2029 | 16000 | CCK-MP-LOAD-WL7104-TRNSYS-TRTRF | 4000 | 64060 | 4741
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Actuator Brake HaulX Shield | 2029-04-15 | 2029-04-16 | 26 hrs | FY29 | 50 | 90033531 | B1 | 1000337784 | 15.04.2029 | 30000 | CCK-MP-LOAD-WL266 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Thermostats | 2029-04-17 | 2029-04-17 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222686 | 17.04.2029 | 5000 | CCK-MP-LOAD-WL269 -ENGINE-COSYS-THERM | 6000 | 74583 | 8436
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Service Air Conditioner | 2029-04-17 | 2029-04-18 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222676 | 17.04.2029 | 5000 | CCK-MP-LOAD-WL269 -STRUCT-CABIN-AIRCN | 6000 | 74583 | 16942
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Torque Converter | 2029-04-17 | 2029-04-18 | 24 hrs | FY29 | 48 | 90002693 | B2 | 1000028794 | 17.04.2029 | 20000 | CCK-MP-LOAD-WL021 -TRNSYS-TRQUE | 6000 | 79997 | 3457
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Front Differential | 2029-04-17 | 2029-04-19 | 58 hrs | FY29 | 114 | 90002707 | B2 | 1000028809 | 17.04.2029 | 20000 | CCK-MP-LOAD-WL021 -FDRSYS-FRDIF | 6000 | 43294 | 43294
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Hyd Pump Implement RH | 2029-04-17 | 2029-04-17 | 12 hrs | FY29 | 24 | 90002724 | B2 | 1000028829 | 17.04.2029 | 10000 | CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP02 | 6000 | 79974 | 3457
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Steering Neutralizer Valves | 2029-04-17 | 2029-04-17 | 6 hrs | FY29 | 6 | 90002720 | B2 | 1000076051 | 17.04.2029 | 20000 | CCK-MP-LOAD-WL021 -STRSYS-STNVS | 6000 | 79974 | 21107
994H | Onsite PM | Ancillary | Fortescue | WL269 | WL269 Repl Cyl Lift LH Ext High Lift | 2029-04-20 | 2029-04-21 | 28 hrs | FY29 | 54 | 90002728 | B2 | 1000112692 | 20.04.2029 | 10000 | CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-HCYLL | 6000 | 74583 | 1701
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Replace Artic Area Hyd Hosing | 2029-04-21 | 2029-04-21 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220497 | 21.04.2029 | 8 Monthly | CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-ARTHO
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Adjust 250hr Initial Valve Set | 2029-04-21 | 2029-04-21 | 6 hrs | FY29 | 12 | 90015780 | B1 | 1000290215 | 21.04.2029 | 250 | CCK-MP-GRDR-GR012 -ENGINE | 5200 | 72353 | 348
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Final Drive Position 2 | 2029-04-26 | 2029-04-28 | 44 hrs | FY29 | 83 | 90002710 | B2 | 1000090383 | 26.04.2029 | 16000 | CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR02 | 6000 | 74441 | 15269
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Thermostats | 2029-04-27 | 2029-04-27 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222642 | 27.04.2029 | 5000 | CCK-MP-LOAD-WL267 -ENGINE-COSYS-THERM | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Service Air Conditioner | 2029-04-27 | 2029-04-28 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222632 | 27.04.2029 | 5000 | CCK-MP-LOAD-WL267 -STRUCT-CABIN-AIRCN | 6000 | 74441 | 8258
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Actuator Brake HaulX Shield | 2029-05-01 | 2029-05-02 | 26 hrs | FY29 | 50 | 90033531 | B1 | 1000337781 | 01.05.2029 | 30000 | CCK-MP-LOAD-WL021 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Front Differential | 2029-05-02 | 2029-05-04 | 58 hrs | FY29 | 114 | 90002707 | B2 | 1000028874 | 02.05.2029 | 20000 | CCK-MP-LOAD-WL022 -FDRSYS-FRDIF | 6000 | 80515 | 3082
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Cyl Steering LH | 2029-05-02 | 2029-05-02 | 12 hrs | FY29 | 22 | 90002961 | B3 | 1000092629 | 02.05.2029 | 22000 | CCK-MP-DOZR-WD202 -STRSYS-STRCY-STCYL | 6300 | 79903 | 4247
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Cyl Steering RH | 2029-05-02 | 2029-05-02 | 12 hrs | FY29 | 22 | 90002961 | B3 | 1000092630 | 02.05.2029 | 22000 | CCK-MP-DOZR-WD202 -STRSYS-STRCY-STCYR | 6300 | 79903 | 4247
D10T | Onsite PM | Ancillary | Fortescue | DZ171 | DZ171 Repl Operators Seat | 2029-05-03 | 2029-05-03 | 4 hrs | FY29 | 8 | 90000318 | B1 | 1000108403 | 03.05.2029 | 6000 | CCK-MP-DOZR-DZ171 -STRUCT-CABIN-SEATS | 5000 | 67979 | 11227
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Shaft Universals TC - Trans | 2029-05-04 | 2029-05-04 | 3 hrs | FY29 | 3 | 90026669 | B1 | 1000268447 | 04.05.2029 | 11000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT01 | 6300 | 79903 | 21666
D10T | Onsite PM | Ancillary | Fortescue | DZ170 | DZ170 Repl Cyl Blade Lift RH | 2029-05-04 | 2029-05-04 | 8 hrs | FY29 | 16 | 90000287 | B1 | 1000255599 | 04.05.2029 | 9000 | CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BLCYR | 5000 | 54263 | 4295
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Implement Valve LH | 2029-05-05 | 2029-05-06 | 24 hrs | FY29 | 24 | 90010965 | B2 | 1000138284 | 05.05.2029 | 20000 | CCK-MP-LOAD-WL7104-HYDSYS-HDVLV-HYV01 | 4000 | 64060 | 8938
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Overhaul Auto Lubrication System | 2029-05-05 | 2029-05-07 | 48 hrs | FY29 | 96 | 90002971 | B3 | 1000092740 | 05.05.2029 | 22000 | CCK-MP-DOZR-WD204 -GRSYST | 6300 | 83628 | 4244
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Cyl Steering LH | 2029-05-05 | 2029-05-05 | 12 hrs | FY29 | 22 | 90002961 | B3 | 1000092681 | 05.05.2029 | 22000 | CCK-MP-DOZR-WD203 -STRSYS-STRCY-STCYL | 6300 | 80875 | 4483
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Refurbish Cabin | 2029-05-09 | 2029-05-10 | 18 hrs | FY29 | 18 | 90010844 | B1 | 1000108383 | 09.05.2029 | 36000 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN | 5000 | 62015 | 22000
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Replace Brake System Hoses | 2029-05-09 | 2029-05-10 | 24 hrs | FY29 | 48 | 90013050 | B3 | 1000109598 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -BRKSYS-BRHLF | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Pump Brake | 2029-05-09 | 2029-05-09 | 4 hrs | FY29 | 4 | 90002957 | B3 | 1000092575 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -BRKSYS-BRPMP | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Rear Differential | 2029-05-09 | 2029-05-12 | 68 hrs | FY29 | 134 | 90002952 | B3 | 1000092567 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -FDRSYS-RRDIF | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Overhaul Axle Oscillation Rear | 2029-05-09 | 2029-05-10 | 24 hrs | FY29 | 64 | 90002953 | B3 | 1000092568 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -FDRSYS-RRDIF-TRNON | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hyd Motor Fan | 2029-05-09 | 2029-05-09 | 4 hrs | FY29 | 8 | 90002969 | B3 | 1000092584 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDMT-HYM01 | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hyd Pump Implement | 2029-05-09 | 2029-05-09 | 6 hrs | FY29 | 12 | 90002962 | B3 | 1000092581 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDPP-HYP01 | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hyd Pump Cooling Fan | 2029-05-09 | 2029-05-09 | 4 hrs | FY29 | 8 | 90002964 | B3 | 1000092583 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HYDPP-HYP03 | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Replace Hoses Steering System | 2029-05-09 | 2029-05-10 | 24 hrs | FY29 | 48 | 90013051 | B3 | 1000109599 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STHLF | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hyd Pump Steering Main | 2029-05-09 | 2029-05-09 | 6 hrs | FY29 | 12 | 90002958 | B3 | 1000092576 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP01 | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Pump Str Pilot & Str Cooling | 2029-05-09 | 2029-05-09 | 4 hrs | FY29 | 4 | 90002959 | B3 | 1000092577 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP02 | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hyd Pump Steer Secondary | 2029-05-09 | 2029-05-09 | 4 hrs | FY29 | 4 | 90002960 | B3 | 1000092578 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP03 | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Transmission Oil Cooler | 2029-05-09 | 2029-05-09 | 6 hrs | FY29 | 6 | 90002945 | B3 | 1000109666 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -TRNSYS-TROLC | 6300 | 81082 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Replace Hyd Pilot System Hoses | 2029-05-09 | 2029-05-09 | 12 hrs | FY29 | 24 | 90013052 | B3 | 1000231926 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HDHLF-HDHPS | 6300 | 81106 | 12720
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Hoses Main Hyd-Fan System | 2029-05-09 | 2029-05-10 | 24 hrs | FY29 | 48 | 90013053 | B3 | 1000231927 | 09.05.2029 | 15000 | CCK-MP-DOZR-WD201 -HYDSYS-HDHLF-HDHMH | 6300 | 81106 | 12720
D10T | Onsite PM | Ancillary | Fortescue | DZ172 | DZ172 Repl Final Drive RH | 2029-05-09 | 2029-05-09 | 14 hrs | FY29 | 28 | 90000312 | B2 | 1000091147 | 09.05.2029 | 18000 | CCK-MP-DOZR-DZ172 -FDRSYS-FDRRH | 5000 | 68264 | 4271
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Repl Engine | 2029-05-10 | 2029-05-18 | 202 hrs | FY29 | 558 | 90016317 | B1 | 1000256922 | 10.05.2029 | 24000 | CCK-MP-LOAD-WL7162-ENGINE | 6100 | 25829 | 7473
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Overhaul Auto Lubrication System | 2029-05-10 | 2029-05-10 | 6 hrs | FY29 | 6 | 90016395 | B1 | 1000257055 | 10.05.2029 | 12000 | CCK-MP-LOAD-WL7162-GRSYST-ALBPP | 6100 | 25829 | 7473
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Overhaul Air Condtioner System | 2029-05-10 | 2029-05-12 | 48 hrs | FY29 | 48 | 90019467 | B1 | 1000256980 | 10.05.2029 | 24000 | CCK-MP-LOAD-WL7162-STRUCT-CABIN-AIRCN | 6100 | 25829 | 7473
D10T | Onsite PM | Ancillary | Fortescue | DZ175 | DZ175 Adjust Engine 500hr Valve Set | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 16 | 90015857 | B1 | 1000160179 | 10.05.2029 | 500 | CCK-MP-DOZR-DZ175 -ENGINE | 5000 | 71802 | 4957
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Sepura SCC Microphone | 2029-05-12 | 2029-05-12 | 0.5 hrs | FY29 | 0.5 | 90028998 | B1 | 1000321326 | 12.05.2029 | 12 Monthly | CCK-MP-LOAD-WL7103-COMMUN-RADIO
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Hyd Pump Brake | 2029-05-14 | 2029-05-14 | 6 hrs | FY29 | 12 | 90002712 | B2 | 1000090386 | 14.05.2029 | 20000 | CCK-MP-LOAD-WL267 -BRKSYS-BRPMP-BRP01 | 6000 | 74441 | 2987
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Main Airhoses & Valves | 2029-05-14 | 2029-05-15 | 18 hrs | FY29 | 18 | 90011137 | B2 | 1000112601 | 14.05.2029 | 20000 | CCK-MP-LOAD-WL260 -PNEUMC-PNHLF | 6000 | 75558 | 22246
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Repl Sepura SCC Microphone | 2029-05-16 | 2029-05-16 | 0.5 hrs | FY29 | 0.5 | 90028991 | B1 | 1000289544 | 16.05.2029 | 12 Monthly | CCK-MP-DOZR-DZ169 -COMMUN-RADIO | 5000 | 62015 | 62015
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Brake Oil Cooler | 2029-05-16 | 2029-05-17 | 36 hrs | FY29 | 72 | 90002715 | B2 | 1000116285 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -BRKSYS-BROCC | 6000 | 75566 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pump Brake Cooling | 2029-05-16 | 2029-05-16 | 8 hrs | FY29 | 8 | 90002713 | B2 | 1000090239 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -BRKSYS-BRPMP-BRP02 | 6000 | 75566 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Radiator Engine Cooling | 2029-05-16 | 2029-05-18 | 54 hrs | FY29 | 102 | 90002682 | B2 | 1000090215 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -ENGINE-COSYS-RADTR | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Auto Lube Pump | 2029-05-16 | 2029-05-16 | 6 hrs | FY29 | 6 | 90002737 | B2 | 1000090256 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -GRSYST-ALBPP | 6000 | 75553 | 3406
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Cyl Bucket LH Ext High Lift | 2029-05-16 | 2029-05-17 | 20 hrs | FY29 | 38 | 90015438 | B2 | 1000131506 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-BUCYL | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Cyl Lift LH Ext High Lift | 2029-05-16 | 2029-05-17 | 28 hrs | FY29 | 54 | 90002728 | B2 | 1000112695 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-HCYLL | 6000 | 75558 | 814
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Cyl Lift RH Ext High Lift | 2029-05-16 | 2029-05-17 | 28 hrs | FY29 | 54 | 90002728 | B2 | 1000112664 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-HCYLR | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Oil Cooler | 2029-05-16 | 2029-05-18 | 48 hrs | FY29 | 96 | 90002733 | B2 | 1000090253 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -HYDSYS-HDOCO | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pump Implement LH | 2029-05-16 | 2029-05-16 | 12 hrs | FY29 | 24 | 90002723 | B2 | 1000090249 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP01 | 6000 | 75558 | 12904
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pump Implement RH | 2029-05-16 | 2029-05-16 | 12 hrs | FY29 | 24 | 90002724 | B2 | 1000090250 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP02 | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pump Implement Centre | 2029-05-16 | 2029-05-16 | 12 hrs | FY29 | 24 | 90002725 | B2 | 1000090251 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP03 | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pilot Accumulator | 2029-05-16 | 2029-05-16 | 4 hrs | FY29 | 4 | 90012174 | B2 | 1000112608 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -HYDSYS-PACCM | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Steering STIC Pilot Valve | 2029-05-16 | 2029-05-16 | 12 hrs | FY29 | 12 | 90026110 | B1 | 1000257365 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STIPV | 6000 | 75558 | 75558
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pump Steering LH | 2029-05-16 | 2029-05-17 | 18 hrs | FY29 | 36 | 90002716 | B2 | 1000090243 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP01 | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pump Steering RH | 2029-05-16 | 2029-05-17 | 18 hrs | FY29 | 36 | 90002717 | B2 | 1000090244 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP02 | 6000 | 75558 | 3411
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Reseal Steering & Brake Tank | 2029-05-16 | 2029-05-17 | 18 hrs | FY29 | 36 | 90010963 | B2 | 1000112580 | 16.05.2029 | 20000 | CCK-MP-LOAD-WL260 -STRSYS-STTNK | 6000 | 75558 | 22246
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Centre Bearing Upper Shaft | 2029-05-16 | 2029-05-16 | 12 hrs | FY29 | 24 | 90002702 | B2 | 1000090226 | 16.05.2029 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-UCTRB | 6000 | 75558 | 12904
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Cyl Blade Lift RH | 2029-05-16 | 2029-05-16 | 8 hrs | FY29 | 14 | 90031953 | B1 | 1000225390 | 16.05.2029 | 9000 | CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BLCYR | 5000 | 26629 | 4367
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Hyd Pump Pilot & Cooling | 2029-05-17 | 2029-05-17 | 6 hrs | FY29 | 12 | 90002726 | B2 | 1000090252 | 17.05.2029 | 10000 | CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP04 | 6000 | 75542 | 3411
24 | Onsite PM | Ancillary | Fortescue | GR7107 | GR7107 Repl Cyl Articulation RH | 2029-05-18 | 2029-05-18 | 4 hrs | FY29 | 4 | 90021512 | B1 | 1000225882 | 18.05.2029 | 7000 | CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYR | 5500 | 24399 | 9687
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Input Shaft Unis | 2029-05-19 | 2029-05-19 | 4 hrs | FY29 | 8 | 90033167 | B1 | 1000333492 | 19.05.2029 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT01 | 6000 | 77065 | 13476
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Rear Output Drive Shaft Unis | 2029-05-19 | 2029-05-19 | 4 hrs | FY29 | 8 | 90033167 | B1 | 1000333494 | 19.05.2029 | 10000 | CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT02 | 6000 | 77065 | 13476
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Engine Cat C32 | 2029-05-19 | 2029-05-23 | 112 hrs | FY29 | 404 | 90015797 | B1 | 1000286600 | 19.05.2029 | 22000 | CCK-MP-DOZR-WD201 -ENGINE | 6300 | 81082 | 4550
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Overhaul Airconditioner | 2029-05-19 | 2029-05-21 | 48 hrs | FY29 | 48 | 90013087 | B1 | 1000286606 | 19.05.2029 | 11000 | CCK-MP-DOZR-WD201 -STRUCT-CABIN-AIRCN | 6300 | 81082 | 12720
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Gearbox Circle Drive Front | 2029-05-19 | 2029-05-19 | 8 hrs | FY29 | 14 | 90002672 | B2 | 1000090931 | 19.05.2029 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CIRCL-CDBXF | 5200 | 68036 | 15776
24M | Onsite PM | Ancillary | Fortescue | GR122 | GR122 Repl Gearbox Circle Drive Rear | 2029-05-19 | 2029-05-19 | 8 hrs | FY29 | 14 | 90011066 | B2 | 1000090932 | 19.05.2029 | 14000 | CCK-MP-GRDR-GR122 -STRUCT-CIRCL-CDBXR | 5200 | 68036 | 10615
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Engine Midlife complete | 2029-05-20 | 2029-05-22 | 63 hrs | FY29 | 84 | 90015811 | B1 | 1000286625 | 20.05.2029 | 11000 | CCK-MP-DOZR-WD204 -ENGINE | 6300 | 83628 | 15298
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Overhaul Airconditioner | 2029-05-20 | 2029-05-22 | 48 hrs | FY29 | 48 | 90013087 | B1 | 1000286627 | 20.05.2029 | 11000 | CCK-MP-DOZR-WD204 -STRUCT-CABIN-AIRCN | 6300 | 83628 | 15298
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Service Minor Air Conditioner | 2029-05-20 | 2029-05-20 | 12 hrs | FY29 | 12 | 90019542 | B1 | 1000290305 | 20.05.2029 | 3500 | CCK-MP-GRDR-GR121 -STRUCT-CABIN-AIRCN | 5200 | 67029 | 10195
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Hydraulic System Hoses | 2029-05-21 | 2029-05-23 | 48 hrs | FY29 | 96 | 90026922 | B1 | 1000271665 | 21.05.2029 | 20000 | CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-HYDHO | 4000 | 64060 | 8512
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Serv Front Frame Grease Sys | 2029-05-21 | 2029-05-22 | 24 hrs | FY29 | 24 | 90010326 | B1 | 1000138293 | 21.05.2029 | 20000 | CCK-MP-LOAD-WL7104-GRSYST-FFGHO | 4000 | 64060 | 8512
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Brake Cooling | 2029-05-24 | 2029-05-24 | 8 hrs | FY29 | 8 | 90002713 | B2 | 1000090313 | 24.05.2029 | 10000 | CCK-MP-LOAD-WL261 -BRKSYS-BRPMP-BRP02 | 6000 | 77065 | 3344
24M | Onsite PM | Ancillary | Fortescue | GR121 | GR121 Repl Axle Assembly Front | 2029-05-24 | 2029-05-26 | 50 hrs | FY29 | 98 | 90002666 | B1 | 1000180097 | 24.05.2029 | 14000 | CCK-MP-GRDR-GR121 -STRUCT-AXLES | 5200 | 67029 | 50
994K | Onsite PM | Ancillary | Fortescue | WL7162 | WL7162 Adjust 250Hr Initial Valve Set | 2029-05-25 | 2029-05-25 | 12 hrs | FY29 | 24 | 90016404 | B1 | 1000256931 | 25.05.2029 | 250 | CCK-MP-LOAD-WL7162-ENGINE | 6100 | 25829 | 7473
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Articulation Overhaul | 2029-05-28 | 2029-06-05 | 194 hrs | FY29 | 360 | 90032991 | B1 | 1000329968 | 28.05.2029 | 16000 | CCK-MP-LOAD-WL021 -STRUCT-CHASS-ARTIC | 6000 | 79974 | 14537
854K | Onsite PM | Ancillary | Fortescue | WD204 | WD204 Repl Cyl Steering LH | 2029-05-29 | 2029-05-29 | 12 hrs | FY29 | 22 | 90002961 | B3 | 1000092733 | 29.05.2029 | 22000 | CCK-MP-DOZR-WD204 -STRSYS-STRCY-STCYL | 6300 | 83628 | 4368
D10T | Onsite PM | Ancillary | Fortescue | DZ183 | DZ183 Repl Operators Seat | 2029-05-30 | 2029-05-30 | 4 hrs | FY29 | 8 | 90000318 | B1 | 1000108547 | 30.05.2029 | 6000 | CCK-MP-DOZR-DZ183 -STRUCT-CABIN-SEATS | 5000 | 65794 | 4209
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Actuator Brake HaulX Shield | 2029-06-01 | 2029-06-02 | 26 hrs | FY29 | 50 | 90033531 | B1 | 1000337787 | 01.06.2029 | 30000 | CCK-MP-LOAD-WL267 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Implement LH | 2029-06-01 | 2029-06-01 | 12 hrs | FY29 | 24 | 90002723 | B2 | 1000090323 | 01.06.2029 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP01 | 6000 | 77065 | 13476
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Implement RH | 2029-06-01 | 2029-06-01 | 12 hrs | FY29 | 24 | 90002724 | B2 | 1000090324 | 01.06.2029 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP02 | 6000 | 77065 | 13476
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Implement Centre | 2029-06-01 | 2029-06-01 | 12 hrs | FY29 | 24 | 90002725 | B2 | 1000090325 | 01.06.2029 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP03 | 6000 | 77065 | 13476
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Hyd Pump Pilot & Cooling | 2029-06-01 | 2029-06-01 | 6 hrs | FY29 | 12 | 90002726 | B2 | 1000090326 | 01.06.2029 | 10000 | CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP04 | 6000 | 77065 | 13476
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Overhaul Park Brake & Centre Brg | 2029-06-03 | 2029-06-04 | 18 hrs | FY29 | 36 | 90002711 | B2 | 1000138193 | 03.06.2029 | 10000 | CCK-MP-LOAD-WL7103-BRKSYS-BRPRK | 6000 | 72865 | 3040
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Implement Pump LH | 2029-06-03 | 2029-06-03 | 12 hrs | FY29 | 24 | 90002723 | B2 | 1000138173 | 03.06.2029 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP01 | 6000 | 72865 | 3040
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Implement Pump RH | 2029-06-03 | 2029-06-03 | 12 hrs | FY29 | 24 | 90002724 | B2 | 1000138174 | 03.06.2029 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP02 | 6000 | 72865 | 12069
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Implement Pump Centre | 2029-06-03 | 2029-06-03 | 12 hrs | FY29 | 24 | 90002725 | B2 | 1000138175 | 03.06.2029 | 10000 | CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP03 | 6000 | 72865 | 3047
994H | Onsite PM | Ancillary | Fortescue | WL7103 | WL7103 Repl Centre Bearing Upper Shaft | 2029-06-03 | 2029-06-03 | 12 hrs | FY29 | 24 | 90002702 | B2 | 1000138152 | 03.06.2029 | 10000 | CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-UCTRB | 6000 | 72865 | 3040
D10T | Onsite PM | Ancillary | Fortescue | DZ014 | DZ014 Adjust Engine 500hr Valve Set | 2029-06-03 | 2029-06-03 | 8 hrs | FY29 | 16 | 90015857 | B1 | 1000159532 | 03.06.2029 | 500 | CCK-MP-DOZR-DZ014 -ENGINE | 5000 | 64687 | 3801
D10T | Onsite PM | Ancillary | Fortescue | DZ184 | DZ184 Minor Service Air Conditioner | 2029-06-05 | 2029-06-05 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196658 | 05.06.2029 | 4500 | CCK-MP-DOZR-DZ184 -STRUCT-CABIN-AIRCN | 5000 | 67674 | 8628
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Repl Engine Thermostats | 2029-06-08 | 2029-06-08 | 6 hrs | FY29 | 6 | 90021139 | B1 | 1000222772 | 08.06.2029 | 5000 | CCK-MP-LOAD-WL7104-ENGINE-COSYS-THERM | 4000 | 64060 | 3143
994H | Onsite PM | Ancillary | Fortescue | WL7104 | WL7104 Service Air Conditioner | 2029-06-08 | 2029-06-09 | 24 hrs | FY29 | 24 | 90021130 | B1 | 1000222764 | 08.06.2029 | 5000 | CCK-MP-LOAD-WL7104-STRUCT-CABIN-AIRCN | 4000 | 64060 | 3143
994H | Onsite PM | Ancillary | Fortescue | WL267 | WL267 Repl Transmission Transfer Case | 2029-06-08 | 2029-06-09 | 38 hrs | FY29 | 74 | 90017029 | B2 | 1000153218 | 08.06.2029 | 16000 | CCK-MP-LOAD-WL267 -TRNSYS-TRTRF | 6000 | 74441 | 14588
854K | Onsite PM | Ancillary | Fortescue | WD203 | WD203 Repl Cylinder Blade Lift LH | 2029-06-08 | 2029-06-08 | 6 hrs | FY29 | 12 | 90002965 | B1 | 1000228677 | 08.06.2029 | 22000 | CCK-MP-DOZR-WD203 -HYDSYS-HDCYL-BLCYL | 6300 | 80875 | 995
854K | Onsite PM | Ancillary | Fortescue | WD202 | WD202 Repl Shaft Trans to Cntr Bearing | 2029-06-08 | 2029-06-08 | 4 hrs | FY29 | 8 | 90002949 | B3 | 1000268450 | 08.06.2029 | 22000 | CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT03 | 6300 | 79903 | 3832
24M | Onsite PM | Ancillary | Fortescue | GR123 | GR123 Service Minor Air Conditioner | 2029-06-08 | 2029-06-08 | 12 hrs | FY29 | 12 | 90019542 | B1 | 1000290320 | 08.06.2029 | 3500 | CCK-MP-GRDR-GR123 -STRUCT-CABIN-AIRCN
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Replace Artic Area Hyd Hosing | 2029-06-09 | 2029-06-09 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220498 | 09.06.2029 | 8 Monthly | CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL261 | WL261 Repl Operators Seat | 2029-06-10 | 2029-06-10 | 4 hrs | FY29 | 4 | 90002741 | B2 | 1000090331 | 10.06.2029 | 7000 | CCK-MP-LOAD-WL261 -STRUCT-CABIN-SEATS | 6000 | 77065 | 11736
D10T | Onsite PM | Ancillary | Fortescue | DZ169 | DZ169 Minor Service Air Conditioner | 2029-06-11 | 2029-06-11 | 10.5 hrs | FY29 | 10.5 | 90017699 | B1 | 1000196609 | 11.06.2029 | 4500 | CCK-MP-DOZR-DZ169 -STRUCT-CABIN-AIRCN | 5000 | 62015 | 8044
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Cyl Blade Lift LH | 2029-06-12 | 2029-06-12 | 8 hrs | FY29 | 16 | 90000287 | B1 | 1000255670 | 12.06.2029 | 9000 | CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BLCYL | 5000 | 63195 | 3729
D10T | Onsite PM | Ancillary | Fortescue | DZ180 | DZ180 Repl Cyl Blade Lift RH | 2029-06-12 | 2029-06-12 | 8 hrs | FY29 | 16 | 90000287 | B1 | 1000255671 | 12.06.2029 | 9000 | CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BLCYR | 5000 | 63195 | 3729
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Actuator Brake HaulX Shield | 2029-06-14 | 2029-06-15 | 26 hrs | FY29 | 50 | 90033531 | B1 | 1000337788 | 14.06.2029 | 30000 | CCK-MP-LOAD-WL260 -MANGMT-CASYS-ACTBK
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Axle Shaft Position 1 | 2029-06-14 | 2029-06-14 | 6 hrs | FY29 | 12 | 90012242 | B2 | 1000101198 | 14.06.2029 | 32000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP1 | 6000 | 79974 | 14269
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Axle Shaft Position 2 | 2029-06-14 | 2029-06-14 | 6 hrs | FY29 | 12 | 90012242 | B2 | 1000101199 | 14.06.2029 | 32000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP2 | 6000 | 79974 | 14269
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Axle Shaft Position 3 | 2029-06-14 | 2029-06-14 | 6 hrs | FY29 | 12 | 90012242 | B2 | 1000101200 | 14.06.2029 | 32000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP3 | 6000 | 79974 | 14269
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Repl Axle Shaft Position 4 | 2029-06-14 | 2029-06-14 | 6 hrs | FY29 | 12 | 90012242 | B2 | 1000101201 | 14.06.2029 | 32000 | CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP4 | 6000 | 79974 | 14269
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8234 | DZ8234 Repl Drive Shaft Unis | 2029-06-14 | 2029-06-14 | 3 hrs | FY29 | 6 | 90033312 | B1 | 1000334044 | 14.06.2029 | 9000 | CCK-MP-DOZR-DZ8234-TRNSYS-DRSHT | 5000 | 26629 | 12967
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Input Shaft Unis | 2029-06-15 | 2029-06-15 | 4 hrs | FY29 | 8 | 90033167 | B1 | 1000333480 | 15.06.2029 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT01 | 6000 | 75558 | 12904
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Ctr Output Drive Shaft Unis | 2029-06-15 | 2029-06-15 | 4 hrs | FY29 | 8 | 90033173 | B1 | 1000333484 | 15.06.2029 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT03 | 6000 | 75558 | 12904
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Front Drive Shaft Unis | 2029-06-15 | 2029-06-15 | 4 hrs | FY29 | 8 | 90033188 | B1 | 1000333486 | 15.06.2029 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT04 | 6000 | 75558 | 4503
994H | Onsite PM | Ancillary | Fortescue | WL260 | WL260 Repl Rr PDrv Drive Shaft Ctr Brg | 2029-06-15 | 2029-06-15 | 4 hrs | FY29 | 8 | 90033193 | B1 | 1000333488 | 15.06.2029 | 10000 | CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT05 | 6000 | 75558 | 4503
24M | Onsite PM | Ancillary | Fortescue | GR012 | GR012 Repl Sepura SCC Microphone | 2029-06-16 | 2029-06-16 | 0.5 hrs | FY29 | 0.5 | 90028989 | B1 | 1000289370 | 16.06.2029 | 12 Monthly | CCK-MP-GRDR-GR012 -COMMUN-RADIO | 5200 | 72353 | 72353
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 500hr Initial Valve Set | 2029-06-17 | 2029-06-17 | 6 hrs | FY29 | 12 | 90015809 | B1 | 1000286602 | 17.06.2029 | 500 | CCK-MP-DOZR-WD201 -ENGINE | 6300 | 81082 | 4550
854K | Onsite PM | Ancillary | Fortescue | WD201 | WD201 Repl Cylinder Blade Lift LH | 2029-06-17 | 2029-06-17 | 6 hrs | FY29 | 12 | 90002965 | B1 | 1000228669 | 17.06.2029 | 22000 | CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BLCYL | 6300 | 81082 | 4073
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 12 Monthly Hydraulic Tune Up | 2029-06-24 | 2029-06-24 | 12 hrs | FY29 | 24 | 90015111 | B1 | 1000266797 | 24.06.2029 | 52 Weekly | CCK-MP-LOAD-WL021 -HYDSYS
994H | Onsite PM | Ancillary | Fortescue | WL021 | WL021 Replace Artic Area Hyd Hosing | 2029-06-27 | 2029-06-27 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220494 | 27.06.2029 | 8 Monthly | CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-ARTHO
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Hyd Pump Implement LH | 2029-06-29 | 2029-06-29 | 12 hrs | FY29 | 24 | 90002723 | B2 | 1000090619 | 29.06.2029 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP01 | 6000 | 74342 | 2546
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Repl Hyd Pump Implement RH | 2029-06-29 | 2029-06-29 | 12 hrs | FY29 | 24 | 90002724 | B2 | 1000090620 | 29.06.2029 | 10000 | CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP02 | 6000 | 74342 | 2546
994H | Onsite PM | Ancillary | Fortescue | WL022 | WL022 Repl Hyd Pump Brake Cooling | 2029-06-29 | 2029-06-29 | 8 hrs | FY29 | 8 | 90002713 | B2 | 1000028882 | 29.06.2029 | 10000 | CCK-MP-LOAD-WL022 -BRKSYS-BRPMP-BRP02 | 6000 | 80515 | 1155
994H | Onsite PM | Ancillary | Fortescue | WL266 | WL266 Replace Artic Area Hyd Hosing | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 6 | 90020831 | B1 | 1000220501 | 30.06.2029 | 8 Monthly | CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-ARTHO
| Onsite PM | Excavators | Fortescue |  | EXCAVATORS - COMPONENTS DURING PM
| Onsite PM | Excavators | Fortescue |  | FY27 - EXCAVATORS - COMPONENTS DURING PM | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Excavators | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Excavators | Fortescue | MOC | JULY | 2026-07-01 | 2026-07-31 | 30 days | FY27
R9400E | Onsite PM | Excavators | Fortescue | All - R9400E | 9400E Cable Reeler Hydraulic Drive Upgrade | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-07-01 | 2026-07-31 | 30 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | R9400 Bucket Refurbishment | 2026-07-01 | 2026-07-31 | 30 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | Bucket Cylinder Guards | 2026-07-01 | 2026-07-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-07-01 | 2026-07-31 | 30 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-07-01 | 2026-07-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | Bucket Rotable Management - Chichester | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-08-01 | 2026-08-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Bucket Refurbishment | 2026-08-01 | 2026-08-31 | 30 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | Bucket Cylinder Guards | 2026-08-01 | 2026-08-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-08-01 | 2026-08-31 | 30 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
R9400E | Onsite PM | Excavators | Fortescue | All - R9400E | 9400E Cable Reeler Hydraulic Drive Upgrade | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-09-01 | 2026-09-30 | 29 days | FY27
R996B | Onsite PM | Excavators | Fortescue | All - R996B | R996B Bucket Refurbishment | 2026-09-01 | 2026-09-30 | 29 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | Bucket Cylinder Guards | 2026-09-01 | 2026-09-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | Bucket Rotable Management - Chichester | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-10-01 | 2026-10-31 | 30 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | R9400 Bucket Refurbishment | 2026-10-01 | 2026-10-31 | 30 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | Bucket Cylinder Guards | 2026-10-01 | 2026-10-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-10-01 | 2026-10-31 | 30 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
R9400E | Onsite PM | Excavators | Fortescue | All - R9400E | 9400E Cable Reeler Hydraulic Drive Upgrade | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-11-01 | 2026-11-30 | 29 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | RH340 Bucket Refurbishment | 2026-11-01 | 2026-11-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-11-01 | 2026-11-30 | 29 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | Bucket Rotable Management - Chichester | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-12-01 | 2026-12-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Bucket Refurbishment | 2026-12-01 | 2026-12-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
R9400E | Onsite PM | Excavators | Fortescue | All - R9400E | 9400E Cable Reeler Hydraulic Drive Upgrade | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-01-01 | 2027-01-31 | 30 days | FY27
R996B | Onsite PM | Excavators | Fortescue | All - R996B | R996B Bucket Refurbishment | 2027-01-01 | 2027-01-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-01-01 | 2027-01-31 | 30 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | Bucket Rotable Management - Chichester | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-02-01 | 2027-02-28 | 27 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | R9400 Bucket Refurbishment | 2027-02-01 | 2027-02-28 | 27 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy | 2027-02-01 | 2027-02-28 | 27 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-03-01 | 2027-03-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Bucket Refurbishment | 2027-03-01 | 2027-03-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy | 2027-03-01 | 2027-03-31 | 30 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | Bucket Rotable Management - Chichester | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-04-01 | 2027-04-30 | 29 days | FY27
R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | R9400 Bucket Refurbishment | 2027-04-01 | 2027-04-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy | 2027-04-01 | 2027-04-30 | 29 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | MAY | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-05-01 | 2027-05-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Bucket Refurbishment | 2027-05-01 | 2027-05-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy | 2027-05-01 | 2027-05-31 | 30 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | JUNE | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | Bucket Rotable Management - Chichester | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-06-01 | 2027-06-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-06-01 | 2027-06-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Repl Bucket Cylinder - MSR Strategy | 2027-06-01 | 2027-06-30 | 29 days | FY27
RH340 | Onsite PM | Excavators | Fortescue | All - RH340 | 6060 Repl Bucket Cylinder - MSR Strategy On Condition | 2027-06-01 | 2027-06-30 | 29 days | FY27
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Service Air Conditioner Sys 1 | 2026-07-27 | 2026-07-27 | 13 hrs | FY27 | 13 | 90030498 | B1 | 1000351948 | 27.05.2026 | 12 Monthly | CCK-MP-EXCV-EX7146-STRUCT-AIRC1 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Grease Tank Level Valve | 2026-07-29 | 2026-07-29 | 2 hrs | FY27 | 2 | 90029942 | B2 | 1000361369 | 11.09.2026 | 12 Monthly | CCK-MP-EXCV-EX7157-GRSYST
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Air Compressor Unit | 2026-07-31 | 2026-07-31 | 8 hrs | FY27 | 15 | 90030086 | B1 | 1000349869 | 28.07.2028 | 20000 | CCK-MP-EXCV-EX7144-PNEUMC-COMPR | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Cyl Bucket LH Lift | 2026-08-01 | 2026-08-02 | 28 hrs | FY27 | 52 | 90029964 | B1 | 1000350897 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-BUCYL | 6200 | 7526 | 0
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Ovhl 24M Air Conditioner Sys1 Eng | 2026-08-04 | 2026-08-06 | 49 hrs | FY27 | 49 | 90035445 | B1 | 1000359786 | 27.05.2026 | 24 Monthly | CCK-MP-EXCV-EX7120-STRUCT-CABIN-AIRC1
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Ovhl 24M Air Conditioner Sys1 Eng | 2026-08-11 | 2026-08-13 | 49 hrs | FY27 | 49 | 90035445 | B1 | 1000359782 | 16.09.2025 | 24 Monthly | CCK-MP-EXCV-EX7117-STRUCT-CABIN-AIRC1
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Batteries | 2026-08-12 | 2026-08-12 | 5 hrs | FY27 | 9 | 90017122 | B1 | 1000232126 | 29.08.2026 | 12 Monthly | CCK-MP-EXCV-EX7117-ELCTLV-CHARG-BATST | 7200 | 32281 | 12760
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Stick LH | 2026-08-15 | 2026-08-16 | 30 hrs | FY27 | 54 | 90003168 | B1 | 1000206848 | 28.06.2026 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-STCLL | 6900 | 25928 | 12889
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Stick RH | 2026-08-15 | 2026-08-16 | 30 hrs | FY27 | 54 | 90003168 | B1 | 1000206849 | 28.06.2026 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-STCLR | 6900 | 25928 | 12889
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 12M Hydraulic Service & Repairs | 2026-08-17 | 2026-08-18 | 18 hrs | FY27 | 30 | 90019301 | B1 | 1000196309 | 25.07.2025 | 12 Monthly | CCK-MP-EXCV-EX8107-HYDSYS
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Start Batteries | 2026-08-17 | 2026-08-17 | 5 hrs | FY27 | 9 | 90019192 | B1 | 1000195267 | 28.07.2026 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-CHARG
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Electrical Cabinet Mounts - Repl | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 6 | 90020439 | B1 | 1000211661 | 28.07.2026 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-MCCEL
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Grease Tank Level Valve | 2026-08-17 | 2026-08-17 | 2 hrs | FY27 | 2 | 90015003 | B4 | 1000162271 | 20.01.2026 | 12 Monthly | CCK-MP-EXCV-EX8107-GRSYST-GRTNK
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Rotary Connection | 2026-08-17 | 2026-08-18 | 28 hrs | FY27 | 50 | 90015692 | B1 | 1000162228 | 17.03.2026 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-ROTRY | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Gearbox Swing LHF | 2026-08-17 | 2026-08-18 | 30 hrs | FY27 | 60 | 90015674 | B1 | 1000162187 | 12.08.2026 | 15000 | CCK-MP-EXCV-EX8107-SWGSYS-SWBOX-SGBLF | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Gearbox Swing RHF | 2026-08-17 | 2026-08-18 | 30 hrs | FY27 | 60 | 90015674 | B2 | 1000162189 | 29.06.2026 | 15000 | CCK-MP-EXCV-EX8107-SWGSYS-SWBOX-SGBRF | 7200 | 46126 | 15483
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P2 Slew | 2026-08-17 | 2026-08-17 | 2 hrs | FY27 | 2 | 90019421 | B1 | 1000197106 | 10.12.2025 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP2 | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P3 Slew Teeth | 2026-08-17 | 2026-08-17 | 2 hrs | FY27 | 2 | 90019422 | B1 | 1000197107 | 10.12.2025 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP3 | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P1 Slew | 2026-08-17 | 2026-08-17 | 2 hrs | FY27 | 2 | 90015715 | B1 | 1000197105 | 10.12.2025 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP1 | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel LHF | 2026-08-17 | 2026-08-17 | 8 hrs | FY27 | 14 | 90015697 | B1 | 1000162241 | 16.07.2026 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMLF | 7200 | 46126 | 12211
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel LHR | 2026-08-17 | 2026-08-17 | 8 hrs | FY27 | 14 | 90015697 | B1 | 1000162242 | 16.07.2026 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMLR | 7200 | 46126 | 12211
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Swing RHF P1 | 2026-08-17 | 2026-08-17 | 9 hrs | FY27 | 18 | 90015695 | B1 | 1000162235 | 29.08.2026 | 15000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-SWMF1 | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Swing LHF P2 | 2026-08-17 | 2026-08-17 | 9 hrs | FY27 | 18 | 90015695 | B1 | 1000162236 | 29.08.2026 | 15000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-SWMF2 | 7200 | 46126 | 14421
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 12M Service Air Conditioner Sys 1 | 2026-08-24 | 2026-08-24 | 13 hrs | FY27 | 13 | 90030498 | B1 | 1000352511 | 29.06.2026 | 12 Monthly | CCK-MP-EXCV-EX7147-STRUCT-AIRC1 | 6200 | 7547 | 7547
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Bucket LH | 2026-08-24 | 2026-08-25 | 26 hrs | FY27 | 32 | 90027499 | B1 | 1000297498 | 04.06.2026 | 10000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BUCYL | 6900 | 15607 | 10846
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Track Tension Tuning-Adjust | 2026-08-24 | 2026-08-24 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000352515 | 01.08.2026 | 6 Monthly | CCK-MP-EXCV-EX7147-UNDERC | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Air Compressor Unit | 2026-08-24 | 2026-08-24 | 15 hrs | FY27 | 15 | 90030086 | B1 | 1000352530 | 31.07.2028 | 20000 | CCK-MP-EXCV-EX7147-PNEUMC-COMPR | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 12M Service Air Conditioner Sys 2 | 2026-08-24 | 2026-08-24 | 13 hrs | FY27 | 13 | 90030536 | B1 | 1000352513 | 29.06.2026 | 12 Monthly | CCK-MP-EXCV-EX7147-STRUCT-AIRC2 | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Track Tension Tuning-Adjust | 2026-08-31 | 2026-08-31 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000349854 | 28.05.2026 | 6 Monthly | CCK-MP-EXCV-EX7144-UNDERC | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Hydraulic Service & Repairs | 2026-08-31 | 2026-09-01 | 18 hrs | FY27 | 30 | 90029940 | B1 | 1000351915 | 27.05.2026 | 12 Monthly | CCK-MP-EXCV-EX7146-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Minestar Harness | 2026-08-31 | 2026-09-01 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000349867 | 05.08.2026 | 4000 | CCK-MP-EXCV-EX7144-MANGMT-UMMMC | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Hose Bucket Cyl | 2026-08-31 | 2026-09-01 | 18 hrs | FY27 | 54 | 90029911 | B1 | 1000349800 | 13.08.2026 | 8000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HBKCL | 6200 | 8005 | 8005
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 500hr Initial Valve Set | 2026-09-07 | 2026-09-07 | 10 hrs | FY27 | 20 | 90027550 | B1 | 1000296915 | 17.07.2026 | 500 | CCK-MP-EXCV-EX7125-LHENGN | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 500hr Initial Valve Set | 2026-09-07 | 2026-09-07 | 10 hrs | FY27 | 20 | 90027550 | B1 | 1000296920 | 17.07.2026 | 500 | CCK-MP-EXCV-EX7125-RHENGN | 6900 | 18844 | 18844
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 12M Hydraulic Service & Repairs | 2026-09-07 | 2026-09-08 | 18 hrs | FY27 | 30 | 90029940 | B1 | 1000350868 | 01.05.2026 | 12 Monthly | CCK-MP-EXCV-EX7145-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Track Tension Tuning-Adjust | 2026-09-07 | 2026-09-07 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000350905 | 02.07.2026 | 6 Monthly | CCK-MP-EXCV-EX7145-UNDERC | 6200 | 7526 | 7526
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Boom Stick Bucket Cyl Hoses | 2026-09-14 | 2026-09-17 | 88 hrs | FY27 | 136 | 90009468 | B1 | 1000344110 | 10.04.2026 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-HBSBC | 6900 | 25928 | 14431
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Minestar Harness | 2026-09-14 | 2026-09-15 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000350918 | 14.09.2026 | 4000 | CCK-MP-EXCV-EX7145-MANGMT-UMMMC | 6200 | 7526 | 7526
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Track Tension Tuning - Adjust | 2026-09-17 | 2026-09-17 | 3 hrs | FY27 | 9 | 90020545 | B1 | 1000232125 | 17.09.2026 | 6 Monthly | CCK-MP-EXCV-EX7117-UNDERC | 7200 | 32281 | 32281
RH340 | Onsite PM | Excavators | Fortescue | EX105 | EX105 Hyd Clng Fan Circ Hoses | 2026-09-21 | 2026-09-22 | 24 hrs | FY27 | 48 | 90009489 | B2 | 1000074441 | 06.06.2025 | 12000 | CCK-MP-EXCV-EX105 -HYDSYS-HDHLF-HCFC | 7300 | 93139 | 19254
RH340 | Onsite PM | Excavators | Fortescue | EX105 | EX105 MCV Cradle Hoses | 2026-09-21 | 2026-09-23 | 48 hrs | FY27 | 72 | 90009490 | B2 | 1000074443 | 09.12.2025 | 10000 | CCK-MP-EXCV-EX105 -HYDSYS-HDHLF-MCVCR | 7300 | 93139 | 28748
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 PP Initial 500Hr Valve Set | 2026-09-24 | 2026-09-24 | 6 hrs | FY27 | 12 | 90031022 | B1 | 1000307007 | 24.09.2026 | 500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2026-09-24 | 2026-09-24 | 6 hrs | FY27 | 12 | 90035479 | B1 | 1000359911 | 31.10.2026 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Track Tension Tuning-Adjust | 2026-09-25 | 2026-09-25 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000378425 | 25.09.2026 | 6 Monthly | CCK-MP-EXCV-EX7153-UNDERC | 6200 | 2136 | 2136
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Cylinder Bucket RH | 2026-09-28 | 2026-09-29 | 26 hrs | FY27 | 32 | 90027499 | B1 | 1000297499 | 16.08.2026 | 10000 | CCK-MP-EXCV-EX7123-HYDSYS-HDCYL-BUCYR | 6900 | 15607 | 9683
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Clam Cyl | 2026-10-05 | 2026-10-05 | 10 hrs | FY27 | 20 | 90036569 | B2 | 1000366870 | 25.08.2026 | 5000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HCMCL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 12M Hydraulic Service & Repairs | 2026-10-05 | 2026-10-06 | 18 hrs | FY27 | 30 | 90029940 | B2 | 1000361367 | 01.09.2026 | 12 Monthly | CCK-MP-EXCV-EX7157-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Track Tension Tuning-Adjust | 2026-10-05 | 2026-10-05 | 3 hrs | FY27 | 9 | 90029977 | B2 | 1000361406 | 11.09.2026 | 6 Monthly | CCK-MP-EXCV-EX7157-UNDERC | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 12M Service Air Con Side Unit | 2026-10-05 | 2026-10-05 | 13 hrs | FY27 | 13 | 90030498 | B2 | 1000361402 | 01.09.2026 | 12 Monthly | CCK-MP-EXCV-EX7157-STRUCT-AIRC1 | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Stick Cyl | 2026-10-05 | 2026-10-06 | 36 hrs | FY27 | 48 | 90029909 | B1 | 1000351897 | 06.04.2026 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HSTCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Minestar Harness | 2026-10-05 | 2026-10-06 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000351965 | 05.11.2026 | 4000 | CCK-MP-EXCV-EX7146-MANGMT-UMMMC | 6200 | 7286 | 7286
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 4500hr Valve Set | 2026-10-12 | 2026-10-12 | 10 hrs | FY27 | 20 | 90027549 | B1 | 1000288444 | 22.09.2026 | 4500 | CCK-MP-EXCV-EX7121-LHENGN | 6900 | 21434 | 2948
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 4500hr Valve Set | 2026-10-12 | 2026-10-12 | 10 hrs | FY27 | 20 | 90027549 | B1 | 1000288450 | 22.09.2026 | 4500 | CCK-MP-EXCV-EX7121-RHENGN | 6900 | 21434 | 2948
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Annual Air Con Service RH | 2026-10-19 | 2026-10-19 | 13 hrs | FY27 | 13 | 90004141 | B1 | 1000206896 | 29.09.2026 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN-AIRCR | 6900 | 25928 | 25928
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Adjust 4500hr Valve Set | 2026-10-19 | 2026-10-19 | 10 hrs | FY27 | 20 | 90017923 | B1 | 1000206809 | 13.11.2026 | 4500 | CCK-MP-EXCV-EX7110-LHENGN | 6900 | 25928 | 1337
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Ovhl 24M Air Conditioner Sys2 Hyd | 2026-10-19 | 2026-10-20 | 36 hrs | FY27 | 36 | 90035446 | B1 | 1000359784 | 16.09.2025 | 24 Monthly | CCK-MP-EXCV-EX7117-STRUCT-CABIN-AIRC2
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Minestar Harness | 2026-10-26 | 2026-10-27 | 27.5 hrs | FY27 | 43.5 | 90030746 | B1 | 1000307013 | 18.04.2026 | 5000 | CCK-MP-EXCV-EX7136-MANGMT-UMMMC | 7200 | 19274 | 6848
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Track Tension Tuning - Adjust | 2026-10-27 | 2026-10-27 | 3 hrs | FY27 | 9 | 90020546 | B1 | 1000213054 | 27.10.2026 | 6 Monthly | CCK-MP-EXCV-EX8106-UNDERC
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 12M Service Air Con Rear Unit | 2026-11-09 | 2026-11-09 | 13 hrs | FY27 | 13 | 90030536 | B1 | 1000349852 | 26.04.2026 | 12 Monthly | CCK-MP-EXCV-EX7144-STRUCT-AIRC2 | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Bucket Cyl | 2026-11-09 | 2026-11-10 | 18 hrs | FY27 | 54 | 90029911 | B1 | 1000351898 | 18.09.2026 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HBKCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Boom Module Quarter Life | 2026-11-09 | 2026-11-10 | 30 hrs | FY27 | 48 | 90029992 | B1 | 1000349865 | 14.11.2026 | 10000 | CCK-MP-EXCV-EX7144-STRUCT-BOOMS | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 12M Service Air Conditioner Sys 2 | 2026-11-16 | 2026-11-16 | 13 hrs | FY27 | 13 | 90030536 | B1 | 1000350903 | 01.05.2026 | 12 Monthly | CCK-MP-EXCV-EX7145-STRUCT-AIRC2 | 6200 | 7526 | 7526
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Grease Block & Injectors | 2026-11-23 | 2026-11-25 | 48 hrs | FY27 | 84 | 90030749 | B1 | 1000232083 | 13.11.2026 | 20000 | CCK-MP-EXCV-EX7117-GRSYST-GRINJ | 7200 | 32281 | 7621
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Pump Case Drain Hoses | 2026-11-24 | 2026-11-24 | 8 hrs | FY27 | 16 | 90009472 | B2 | 1000344106 | 01.12.2026 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-HPCDL | 6900 | 25928 | 12901
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Minestar Harness | 2026-11-25 | 2026-11-26 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000378437 | 25.11.2026 | 4000 | CCK-MP-EXCV-EX7153-MANGMT-UMMMC | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cylinder Clam LH | 2026-12-14 | 2026-12-14 | 14 hrs | FY27 | 22 | 90035631 | B2 | 1000361398 | 21.10.2026 | 6000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-CLAML | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cylinder Clam RH | 2026-12-14 | 2026-12-14 | 14 hrs | FY27 | 22 | 90035631 | B2 | 1000361399 | 21.10.2026 | 6000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-CLAMR | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Boom Cyl | 2026-12-14 | 2026-12-16 | 54 hrs | FY27 | 72 | 90029908 | B2 | 1000361348 | 25.08.2026 | 8000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HBMCL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Boom Module Quarter Life | 2026-12-14 | 2026-12-15 | 30 hrs | FY27 | 48 | 90029992 | B2 | 1000361416 | 25.03.2027 | 10000 | CCK-MP-EXCV-EX7157-STRUCT-BOOMS | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Service Air Conditioner Sys 2 | 2026-12-14 | 2026-12-14 | 13 hrs | FY27 | 13 | 90030536 | B1 | 1000351950 | 27.05.2026 | 12 Monthly | CCK-MP-EXCV-EX7146-STRUCT-AIRC2 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Boom Cyl | 2026-12-14 | 2026-12-16 | 54 hrs | FY27 | 72 | 90029908 | B1 | 1000351896 | 18.09.2026 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HBMCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Boom Module Quarter Life | 2026-12-14 | 2026-12-15 | 30 hrs | FY27 | 48 | 90029992 | B1 | 1000351963 | 19.11.2026 | 10000 | CCK-MP-EXCV-EX7146-STRUCT-BOOMS | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Pump Swing Combination | 2026-12-17 | 2026-12-18 | 24 hrs | FY27 | 36 | 90030252 | B1 | 1000349872 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HYDPP-SWPP1 | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Bucket LH Lift | 2026-12-17 | 2026-12-18 | 28 hrs | FY27 | 52 | 90029964 | B1 | 1000349846 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-BUCYL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Bucket RH Lift | 2026-12-17 | 2026-12-18 | 28 hrs | FY27 | 52 | 90029967 | B1 | 1000349847 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-BUCYR | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Vlve Bank Module Quarter Life | 2026-12-17 | 2026-12-17 | 6 hrs | FY27 | 12 | 90029987 | B1 | 1000349862 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDVLV-MCVLU | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Valve Pressure Limiting Y4 | 2026-12-17 | 2026-12-17 | 6 hrs | FY27 | 6 | 90030321 | B1 | 1000349880 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDVLV-VVPLV | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Accumulator Servo Hyd | 2026-12-17 | 2026-12-17 | 3 hrs | FY27 | 3 | 90030487 | B1 | 1000349863 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDACC | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Accumulator Ladder Hyd | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 4 | 90030685 | B1 | 1000349891 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDACC | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Track Tensioning Hoses | 2026-12-17 | 2026-12-17 | 12 hrs | FY27 | 24 | 90030538 | B1 | 1000349890 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HHTTL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Hyd Hose Work Pumps to Valves | 2026-12-17 | 2026-12-17 | 10.5 hrs | FY27 | 10.5 | 90030287 | B1 | 1000349877 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HWPVV | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Hyd Hose Swing Pump Swing Motor | 2026-12-17 | 2026-12-17 | 12 hrs | FY27 | 24 | 90030288 | B1 | 1000349878 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HSPSM | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Hyd Hose Rotary Con to Valve Bank | 2026-12-17 | 2026-12-17 | 12 hrs | FY27 | 24 | 90029912 | B1 | 1000349801 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HRCVV | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Hoses Rotary Conn to Travel Motor | 2026-12-17 | 2026-12-18 | 24 hrs | FY27 | 48 | 90029914 | B1 | 1000349802 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HRCTM | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Operators Seat | 2026-12-17 | 2026-12-17 | 8 hrs | FY27 | 16 | 90029915 | B1 | 1000349803 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-STRUCT-CABIN-SEATO | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Auto Lube Pump P1 | 2026-12-17 | 2026-12-17 | 2 hrs | FY27 | 2 | 90030312 | B1 | 1000349807 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-GRSYST-AUTLU-ALBPP | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Auto Lube Pump P3 | 2026-12-17 | 2026-12-17 | 2 hrs | FY27 | 2 | 90035351 | B1 | 1000358635 | 17.12.2026 | 10000 | CCK-MP-EXCV-EX7144-GRSYST-AUTLU-ALBP3 | 6200 | 8005 | 8005
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Power Pack Module 1 Valve set | 2026-12-20 | 2026-12-20 | 8 hrs | FY27 | 16 | 90015717 | B1 | 1000267715 | 20.12.2026 | 1000 | CCK-MP-EXCV-EX8106-FRENGN | 7200 | 46150 | 15799
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Power Pack Module 2 Valve set | 2026-12-20 | 2026-12-20 | 8 hrs | FY27 | 16 | 90015717 | B1 | 1000267718 | 20.12.2026 | 1000 | CCK-MP-EXCV-EX8106-RRENGN | 7200 | 46150 | 15698
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Track Tension Tuning-Adjust | 2026-12-22 | 2026-12-22 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000351952 | 22.12.2026 | 6 Monthly | CCK-MP-EXCV-EX7146-UNDERC | 6200 | 7286 | 7286
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Power Pack Module Qtr Life | 2026-12-22 | 2026-12-22 | 1 hr | FY27 | 1 | 90027378 | B1 | 1000279047 | 22.12.2026 | 5000 | CCK-MP-EXCV-EX7117-ENGINE | 7200 | 32281 | 12760
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Power Pack Module 2 Valve Set | 2026-12-23 | 2026-12-23 | 8 hrs | FY27 | 16 | 90015717 | B1 | 1000267762 | 23.12.2026 | 1000 | CCK-MP-EXCV-EX8107-FRENGN | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Power Pack Module 2 Valve set | 2026-12-23 | 2026-12-23 | 8 hrs | FY27 | 16 | 90015717 | B1 | 1000267770 | 23.12.2026 | 1000 | CCK-MP-EXCV-EX8107-RRENGN | 7200 | 46126 | 14421
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Minestar Harness | 2026-12-26 | 2026-12-27 | 27.5 hrs | FY27 | 43.5 | 90030746 | B1 | 1000281593 | 26.12.2026 | 5000 | CCK-MP-EXCV-EX7117-MANGMT-UMMMC | 7200 | 32281 | 32281
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Engine Midlife Complete RH | 2026-12-28 | 2026-12-30 | 54 hrs | FY27 | 76 | 90018424 | B1 | 1000206824 | 16.01.2027 | 9000 | CCK-MP-EXCV-EX7110-RHENGN | 6900 | 25928 | 6025
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Minestar Harness | 2026-12-28 | 2026-12-29 | 27.5 hrs | FY27 | 43.5 | 90027626 | B2 | 1000281596 | 26.12.2026 | 4000 | CCK-MP-EXCV-EX7110-MANGMT-UMMMC | 6900 | 25928 | 12535
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Adjust 500hr Initial Valve Set | 2026-12-30 | 2026-12-30 | 10 hrs | FY27 | 20 | 90027550 | B1 | 1000297426 | 30.12.2026 | 500 | CCK-MP-EXCV-EX7123-LHENGN | 6900 | 15607 | 15607
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Grease Injectors | 2027-01-02 | 2027-01-04 | 48 hrs | FY27 | 84 | 90029932 | B1 | 1000349814 | 02.01.2027 | 10000 | CCK-MP-EXCV-EX7144-GRSYST-GRINJ | 6200 | 8005 | 8005
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Bucket | 2027-01-04 | 2027-01-06 | 42 hrs | FY27 | 78 | 90017654 | B1 | 1000162300 | 02.11.2026 | 16000 | CCK-MP-EXCV-EX8107-STRUCT-BUCKT | 7200 | 46126 | 35888
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Minestar Harness | 2027-01-14 | 2027-01-15 | 27.5 hrs | FY27 | 43.5 | 90031708 | B1 | 1000369998 | 14.01.2027 | 4000 | CCK-MP-EXCV-EX7125-MANGMT-UMMMC | 6900 | 18844 | 18844
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2027-01-15 | 2027-01-15 | 6 hrs | FY27 | 12 | 90035479 | B1 | 1000359911 | 15.01.2027 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Replace Grease Injectors | 2027-01-18 | 2027-01-20 | 48 hrs | FY27 | 84 | 90019202 | B1 | 1000195347 | 18.01.2027 | 8000 | CCK-MP-EXCV-EX8106-GRSYST-GRINJ | 7200 | 40923 | 7881
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Bucket LH Lift | 2027-01-19 | 2027-01-20 | 30 hrs | FY27 | 54 | 90030725 | B1 | 1000232115 | 19.01.2027 | 10000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-BUCYL | 7200 | 32281 | 2607
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Bucket RH Lift | 2027-01-19 | 2027-01-20 | 30 hrs | FY27 | 54 | 90030726 | B1 | 1000232116 | 19.01.2027 | 10000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-BUCYR | 7200 | 32281 | 6735
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Grease System Audit | 2027-01-23 | 2027-01-24 | 24 hrs | FY27 | 36 | 90029934 | B1 | 1000378387 | 23.01.2027 | 5000 | CCK-MP-EXCV-EX7153-GRSYST-GRINJ | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Pump Swing Combination | 2027-01-26 | 2027-01-27 | 24 hrs | FY27 | 36 | 90030252 | B1 | 1000351970 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HYDPP-SWPP1 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Bucket LH Lift | 2027-01-26 | 2027-01-27 | 28 hrs | FY27 | 52 | 90029964 | B1 | 1000351944 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-BUCYL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Bucket RH Lift | 2027-01-26 | 2027-01-27 | 28 hrs | FY27 | 52 | 90029967 | B1 | 1000351945 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-BUCYR | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Vlve Bank Module Quarter Life | 2027-01-26 | 2027-01-26 | 6 hrs | FY27 | 12 | 90029987 | B1 | 1000351960 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDVLV-MCVLU | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Valve Pressure Limiting Y4 | 2027-01-26 | 2027-01-26 | 6 hrs | FY27 | 6 | 90030321 | B1 | 1000351978 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDVLV-VVPLV | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Accumulator Servo Hyd | 2027-01-26 | 2027-01-26 | 3 hrs | FY27 | 3 | 90030487 | B1 | 1000351961 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDACC | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Accumulator Ladder Hyd | 2027-01-26 | 2027-01-26 | 4 hrs | FY27 | 4 | 90030685 | B1 | 1000351987 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDACC | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Track Tensioning Hoses | 2027-01-26 | 2027-01-26 | 12 hrs | FY27 | 24 | 90030538 | B1 | 1000351986 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HHTTL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Hyd Hose Work Pumps to Valves | 2027-01-26 | 2027-01-26 | 10.5 hrs | FY27 | 10.5 | 90030287 | B1 | 1000351975 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HWPVV | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Hyd Hose Swing Pump Swing Motor | 2027-01-26 | 2027-01-26 | 12 hrs | FY27 | 24 | 90030288 | B1 | 1000351976 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HSPSM | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Hyd Hose Rotary Con to Valve Bank | 2027-01-26 | 2027-01-26 | 12 hrs | FY27 | 24 | 90029912 | B1 | 1000351899 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HRCVV | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Hoses Rotary Conn to Travel Motor | 2027-01-26 | 2027-01-27 | 24 hrs | FY27 | 48 | 90029914 | B1 | 1000351900 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HRCTM | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Operators Seat | 2027-01-26 | 2027-01-26 | 8 hrs | FY27 | 16 | 90029915 | B1 | 1000351901 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-STRUCT-CABIN-SEATO | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Auto Lube Pump P1 | 2027-01-26 | 2027-01-26 | 2 hrs | FY27 | 2 | 90030312 | B1 | 1000351905 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-GRSYST-AUTLU-ALBPP | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Auto Lube Pump P3 | 2027-01-26 | 2027-01-26 | 2 hrs | FY27 | 2 | 90035351 | B1 | 1000358640 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-GRSYST-AUTLU-ALBP3 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Grease Injectors | 2027-01-26 | 2027-01-28 | 48 hrs | FY27 | 84 | 90029932 | B1 | 1000351912 | 26.01.2027 | 10000 | CCK-MP-EXCV-EX7146-GRSYST-GRINJ | 6200 | 7286 | 7286
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Bucket LH | 2027-01-27 | 2027-01-28 | 26 hrs | FY27 | 32 | 90027499 | B1 | 1000296947 | 27.01.2027 | 10000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BUCYL | 6900 | 18844 | 6591
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Bucket RH | 2027-01-27 | 2027-01-28 | 26 hrs | FY27 | 32 | 90027499 | B1 | 1000296948 | 27.01.2027 | 10000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BUCYR | 6900 | 18844 | 6591
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Swing Circuit Hoses | 2027-02-01 | 2027-02-01 | 8 hrs | FY27 | 16 | 90009481 | B1 | 1000206883 | 16.01.2027 | 9000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SWCRT | 6900 | 25928 | 6025
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 4500hr Valve Set | 2027-02-09 | 2027-02-09 | 10 hrs | FY27 | 20 | 90027549 | B1 | 1000296916 | 09.02.2027 | 4500 | CCK-MP-EXCV-EX7125-LHENGN | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 4500hr Valve Set | 2027-02-09 | 2027-02-09 | 10 hrs | FY27 | 20 | 90027549 | B1 | 1000296921 | 09.02.2027 | 4500 | CCK-MP-EXCV-EX7125-RHENGN | 6900 | 18844 | 18844
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Batteries | 2027-02-18 | 2027-02-18 | 5 hrs | FY27 | 9 | 90017122 | B1 | 1000306997 | 18.02.2027 | 12 Monthly | CCK-MP-EXCV-EX7136-ELCTLV-CHARG-BATST | 7200 | 19274 | 19274
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 12M Hydraulic Service & Repairs | 2027-02-24 | 2027-02-25 | 18 hrs | FY27 | 30 | 90019301 | B1 | 1000196308 | 24.02.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-HYDSYS
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Ovhl 24M Air Conditioner Sys2 Hyd | 2027-02-25 | 2027-02-26 | 37 hrs | FY27 | 37 | 90035267 | B1 | 1000359792 | 25.02.2027 | 24 Monthly | CCK-MP-EXCV-EX7136-STRUCT-CABIN-AIRC2
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Boom Cylinders - Replace | 2027-02-27 | 2027-02-27 | 8 hrs | FY27 | 16 | 90015701 | B1 | 1000222962 | 27.02.2027 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HBCYL | 7200 | 46150 | 1397
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Stick Cylinders - Repl | 2027-02-27 | 2027-02-28 | 20 hrs | FY27 | 44 | 90015702 | B1 | 1000222963 | 27.02.2027 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HSCYL | 7200 | 46150 | 1397
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Auto Lube Pump P2 Slew | 2027-02-27 | 2027-02-27 | 2 hrs | FY27 | 2 | 90019421 | B1 | 1000196919 | 27.02.2027 | 10000 | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-ALBP2 | 7200 | 46150 | 1421
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Replace Minestar Harness | 2027-03-04 | 2027-03-05 | 27.5 hrs | FY27 | 43.5 | 90018769 | B2 | 1000281581 | 04.03.2027 | 4000 | CCK-MP-EXCV-EX8106-MANGMT-UMMMC | 7200 | 46150 | 15686
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Stick Cyl | 2027-03-04 | 2027-03-05 | 36 hrs | FY27 | 48 | 90029909 | B1 | 1000350850 | 03.03.2026 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HSTCL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Bucket Cyl | 2027-03-04 | 2027-03-05 | 18 hrs | FY27 | 54 | 90029911 | B1 | 1000350851 | 18.09.2026 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HBKCL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Boom Module Quarter Life | 2027-03-04 | 2027-03-05 | 30 hrs | FY27 | 48 | 90029992 | B1 | 1000350916 | 18.11.2026 | 10000 | CCK-MP-EXCV-EX7145-STRUCT-BOOMS | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Track Tension Tuning-Adjust | 2027-03-04 | 2027-03-04 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000350905 | 29.12.2026 | 6 Monthly | CCK-MP-EXCV-EX7145-UNDERC | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Grease Injectors | 2027-03-04 | 2027-03-06 | 48 hrs | FY27 | 84 | 90029932 | B1 | 1000350865 | 02.01.2027 | 10000 | CCK-MP-EXCV-EX7145-GRSYST-GRINJ | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Pump Swing Combination | 2027-03-04 | 2027-03-05 | 24 hrs | FY27 | 36 | 90030252 | B1 | 1000350923 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HYDPP-SWPP1 | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Vlve Bank Module Quarter Life | 2027-03-04 | 2027-03-04 | 6 hrs | FY27 | 12 | 90029987 | B1 | 1000350913 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDVLV-MCVLU | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Valve Pressure Limiting Y4 | 2027-03-04 | 2027-03-04 | 6 hrs | FY27 | 6 | 90030321 | B1 | 1000350931 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDVLV-VVPLV | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Accumulator Servo Hyd | 2027-03-04 | 2027-03-04 | 3 hrs | FY27 | 3 | 90030487 | B1 | 1000350914 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDACC | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Accumulator Ladder Hyd | 2027-03-04 | 2027-03-04 | 4 hrs | FY27 | 4 | 90030685 | B1 | 1000350940 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDACC | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Track Tensioning Hoses | 2027-03-04 | 2027-03-04 | 12 hrs | FY27 | 24 | 90030538 | B1 | 1000350939 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HHTTL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Hyd Hose Work Pumps to Valves | 2027-03-04 | 2027-03-04 | 10.5 hrs | FY27 | 10.5 | 90030287 | B1 | 1000350928 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HWPVV | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Hyd Hose Swing Pump Swing Motor | 2027-03-04 | 2027-03-04 | 12 hrs | FY27 | 24 | 90030288 | B1 | 1000350929 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HSPSM | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Hyd Hose Rotary Con to Valve Bank | 2027-03-04 | 2027-03-04 | 12 hrs | FY27 | 24 | 90029912 | B1 | 1000350852 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HRCVV | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Hoses Rotary Conn to Travel Motor | 2027-03-04 | 2027-03-05 | 24 hrs | FY27 | 48 | 90029914 | B1 | 1000350853 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HRCTM | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Operators Seat | 2027-03-04 | 2027-03-04 | 8 hrs | FY27 | 16 | 90029915 | B1 | 1000350854 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-STRUCT-CABIN-SEATO | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Auto Lube Pump P1 | 2027-03-04 | 2027-03-04 | 2 hrs | FY27 | 2 | 90030312 | B1 | 1000350858 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-GRSYST-AUTLU-ALBPP | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Auto Lube Pump P3 | 2027-03-04 | 2027-03-04 | 2 hrs | FY27 | 2 | 90035351 | B1 | 1000358636 | 17.01.2027 | 10000 | CCK-MP-EXCV-EX7145-GRSYST-AUTLU-ALBP3 | 6200 | 7526 | 7526
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Swing LHR | 2027-03-05 | 2027-03-06 | 21 hrs | FY27 | 27 | 90003175 | B1 | 1000206855 | 05.03.2027 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-SWMLR | 6900 | 25928 | 11135
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Swing RHF | 2027-03-05 | 2027-03-06 | 21 hrs | FY27 | 27 | 90003175 | B1 | 1000206856 | 05.03.2027 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-SWMRF | 6900 | 25928 | 11135
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Swing RHR | 2027-03-05 | 2027-03-06 | 21 hrs | FY27 | 27 | 90003175 | B1 | 1000206857 | 05.03.2027 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-SWMRR | 6900 | 25928 | 11135
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Air Con System | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 4 | 90019239 | B1 | 1000195764 | 06.03.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-ACONR | 7200 | 46150 | 21475
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Air Condtioner Compr Rear | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 4 | 90019237 | B1 | 1000195762 | 06.03.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-STRUCT-CABIN-ACCN2 | 7200 | 46150 | 21475
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Air Con System | 2027-03-09 | 2027-03-09 | 5 hrs | FY27 | 5 | 90019238 | B1 | 1000195763 | 09.03.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-ACONF | 7200 | 46150 | 21475
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Air Condtioner Compr Front | 2027-03-09 | 2027-03-09 | 5 hrs | FY27 | 5 | 90019236 | B1 | 1000195761 | 09.03.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-STRUCT-CABIN-ACCN1 | 7200 | 46150 | 21475
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Operators Seat | 2027-03-10 | 2027-03-10 | 2 hrs | FY27 | 2 | 90003180 | B1 | 1000206867 | 10.03.2027 | 10000 | CCK-MP-EXCV-EX7110-STRUCT-CABIN-SEATS | 6900 | 25928 | 6025
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Track Tension Tuning-Adjust | 2027-03-11 | 2027-03-11 | 3 hrs | FY27 | 9 | 90029977 | B2 | 1000361406 | 11.03.2027 | 6 Monthly | CCK-MP-EXCV-EX7157-UNDERC | 6000 | 4778 | 4778
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Grease Tank Level Valve | 2027-03-14 | 2027-03-14 | 2 hrs | FY27 | 2 | 90015003 | B2 | 1000232088 | 14.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7117-GRSYST-AUTLU-GRTNK | 7200 | 32281 | 32281
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Stick Cyl | 2027-03-15 | 2027-03-16 | 36 hrs | FY27 | 48 | 90029909 | B2 | 1000361349 | 15.03.2027 | 8000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HSTCL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Bucket Cyl | 2027-03-15 | 2027-03-16 | 18 hrs | FY27 | 54 | 90029911 | B2 | 1000361350 | 15.03.2027 | 8000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HBKCL | 6000 | 4778 | 4778
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Main Control Valve Block LH | 2027-03-16 | 2027-03-17 | 34 hrs | FY27 | 50 | 90003172 | B1 | 1000206887 | 16.03.2027 | 30000 | CCK-MP-EXCV-EX7110-HYDSYS-HDVLV-MCVVL | 6900 | 25928 | 25928
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Main Control Valve Block RH | 2027-03-16 | 2027-03-17 | 34 hrs | FY27 | 50 | 90003172 | B1 | 1000206888 | 16.03.2027 | 30000 | CCK-MP-EXCV-EX7110-HYDSYS-HDVLV-MCVVR | 6900 | 25928 | 25928
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 12M Hydraulic Service & Repairs | 2027-03-16 | 2027-03-17 | 18 hrs | FY27 | 30 | 90014448 | B2 | 1000232086 | 16.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7117-HYDSYS | 7200 | 32281 | 32281
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Track Tension Tuning - Adjust | 2027-03-16 | 2027-03-16 | 3 hrs | FY27 | 9 | 90020545 | B1 | 1000232125 | 16.03.2027 | 6 Monthly | CCK-MP-EXCV-EX7117-UNDERC | 7200 | 32281 | 32281
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Wiper Blades | 2027-03-19 | 2027-03-19 | 1 hr | FY27 | 1 | 90027557 | B1 | 1000288564 | 19.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl 24V Batteries | 2027-03-24 | 2027-03-24 | 5 hrs | FY27 | 9 | 90029978 | B1 | 1000378426 | 24.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7153-ELCTLV-CHARG-BATST | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Track Tension Tuning-Adjust | 2027-03-24 | 2027-03-24 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000378425 | 24.03.2027 | 6 Monthly | CCK-MP-EXCV-EX7153-UNDERC | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 12M Hydraulic Service & Repairs | 2027-03-24 | 2027-03-25 | 18 hrs | FY27 | 30 | 90029940 | B1 | 1000378388 | 24.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7153-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 12M Service Air Con Side Unit | 2027-03-24 | 2027-03-24 | 13 hrs | FY27 | 13 | 90030498 | B1 | 1000378421 | 24.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7153-STRUCT-AIRC1 | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 12M Service Air Con Rear Unit | 2027-03-24 | 2027-03-24 | 13 hrs | FY27 | 13 | 90030536 | B1 | 1000378423 | 24.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7153-STRUCT-AIRC2 | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Grease Tank Level Valve | 2027-03-24 | 2027-03-24 | 2 hrs | FY27 | 2 | 90029942 | B1 | 1000378390 | 24.03.2027 | 12 Monthly | CCK-MP-EXCV-EX7153-GRSYST
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Batteries | 2027-03-30 | 2027-03-30 | 4 hrs | FY27 | 4 | 90027525 | B1 | 1000288559 | 30.03.2027 | 10000 | CCK-MP-EXCV-EX7121-ELCTLV-CHARG-BATTY | 6900 | 21434 | 5556
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Annual Air Con Service LH | 2027-04-01 | 2027-04-01 | 13 hrs | FY27 | 13 | 90004141 | B1 | 1000287617 | 01.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN-AIRCL
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2027-04-01 | 2027-04-01 | 6 hrs | FY27 | 12 | 90035479 | B1 | 1000359911 | 01.04.2027 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Final Drive RH Side | 2027-04-02 | 2027-04-07 | 126 hrs | FY27 | 218 | 90015667 | B1 | 1000162036 | 02.04.2027 | 18000 | CCK-MP-EXCV-EX8106-UNDERC-TKFRR-FDRRH | 7200 | 46150 | 13113
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Minestar Harness | 2027-04-04 | 2027-04-05 | 27.5 hrs | FY27 | 43.5 | 90031708 | B1 | 1000369996 | 04.04.2027 | 4000 | CCK-MP-EXCV-EX7121-MANGMT-UMMMC | 6900 | 21434 | 21434
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl 24V Batteries | 2027-04-09 | 2027-04-09 | 5 hrs | FY27 | 9 | 90029978 | B1 | 1000349855 | 09.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7144-ELCTLV-CHARG-BATST | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 12M Hydraulic Service & Repairs | 2027-04-10 | 2027-04-11 | 18 hrs | FY27 | 30 | 90029940 | B1 | 1000349817 | 10.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7144-HYDSYS
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Operators Seat | 2027-04-14 | 2027-04-14 | 2 hrs | FY27 | 2 | 90027613 | B1 | 1000297515 | 14.04.2027 | 10000 | CCK-MP-EXCV-EX7123-STRUCT-CABIN-SEATS | 6900 | 15607 | 5134
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Auto Lube Pump P3 | 2027-04-16 | 2027-04-16 | 2 hrs | FY27 | 2 | 90035368 | B1 | 1000358744 | 16.04.2027 | 10000 | CCK-MP-EXCV-EX7136-GRSYST-AUTLU-ALBP3 | 7200 | 19274 | 4847
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Minestar Harness | 2027-04-17 | 2027-04-18 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000352528 | 17.04.2027 | 4000 | CCK-MP-EXCV-EX7147-MANGMT-UMMMC | 6200 | 7547 | 7547
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Wiper Blades | 2027-04-19 | 2027-04-19 | 2 hrs | FY27 | 2 | 90004684 | B1 | 1000206897 | 19.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN | 6900 | 25928 | 25928
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Minestar Harness | 2027-04-20 | 2027-04-21 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000349867 | 20.04.2027 | 4000 | CCK-MP-EXCV-EX7144-MANGMT-UMMMC | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Grease Tank Level Valve | 2027-04-21 | 2027-04-21 | 2 hrs | FY27 | 2 | 90029942 | B1 | 1000349819 | 21.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7144-GRSYST
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Track Tension Tuning - Adjust | 2027-04-25 | 2027-04-25 | 3 hrs | FY27 | 9 | 90020546 | B1 | 1000213054 | 25.04.2027 | 6 Monthly | CCK-MP-EXCV-EX8106-UNDERC
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl 24V Batteries | 2027-04-26 | 2027-04-26 | 5 hrs | FY27 | 9 | 90029978 | B1 | 1000350906 | 26.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7145-ELCTLV-CHARG-BATST | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 12M Hydraulic Service & Repairs | 2027-04-26 | 2027-04-27 | 18 hrs | FY27 | 30 | 90029940 | B1 | 1000350868 | 26.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7145-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 24M Ovhl AirCondtioner Sys 1 | 2027-04-26 | 2027-04-27 | 36 hrs | FY27 | 36 | 90030500 | B1 | 1000350902 | 26.04.2027 | 24 Monthly | CCK-MP-EXCV-EX7145-STRUCT-AIRC1 | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 24M Ovhl AirCondtioner Sys 2 | 2027-04-26 | 2027-04-27 | 36 hrs | FY27 | 36 | 90030537 | B1 | 1000350904 | 26.04.2027 | 24 Monthly | CCK-MP-EXCV-EX7145-STRUCT-AIRC2 | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Grease Tank Level Valve | 2027-04-26 | 2027-04-26 | 2 hrs | FY27 | 2 | 90029942 | B1 | 1000350870 | 26.04.2027 | 12 Monthly | CCK-MP-EXCV-EX7145-GRSYST
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Maintenance Batteries | 2027-05-02 | 2027-05-02 | 3 hrs | FY27 | 5 | 90019334 | 1 | 1000195273 | 07.05.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-CHARG
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Hose Stick Cyl | 2027-05-06 | 2027-05-07 | 36 hrs | FY27 | 48 | 90030737 | B1 | 1000232062 | 06.05.2027 | 8000 | CCK-MP-EXCV-EX7117-HYDSYS-HDHLF-HSTCL | 7200 | 32281 | 7621
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Start Batteries | 2027-05-07 | 2027-05-07 | 5 hrs | FY27 | 9 | 90019192 | B1 | 1000195266 | 07.05.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-CHARG
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Hose Bucket Cyl | 2027-05-07 | 2027-05-08 | 18 hrs | FY27 | 54 | 90030738 | B1 | 1000325211 | 07.05.2027 | 8000 | CCK-MP-EXCV-EX7117-HYDSYS-HDHLF-HBKCL | 7200 | 32281 | 2639
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Hose Boom Cyl | 2027-05-07 | 2027-05-09 | 54 hrs | FY27 | 72 | 90030735 | B1 | 1000232061 | 07.05.2027 | 8000 | CCK-MP-EXCV-EX7117-HYDSYS-HDHLF-HBMCL | 7200 | 32281 | 2639
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Grease Tank Level Valve | 2027-05-08 | 2027-05-08 | 2 hrs | FY27 | 2 | 90015003 | B4 | 1000162121 | 08.05.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-GRTNK
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Electrical Cabinet Mounts - Rep | 2027-05-08 | 2027-05-08 | 6 hrs | FY27 | 6 | 90020439 | B1 | 1000211660 | 08.05.2027 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-MCCEL
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Travel RHR | 2027-05-08 | 2027-05-08 | 6 hrs | FY27 | 12 | 90022657 | B1 | 1000206865 | 08.05.2027 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-TRMRR | 6900 | 25928 | 6943
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Auto Lube SStructure | 2027-05-09 | 2027-05-09 | 12 hrs | FY27 | 12 | 90018988 | B1 | 1000206903 | 09.05.2027 | 6000 | CCK-MP-EXCV-EX7110-GRSYST-ALBPP | 6900 | 25928 | 12901
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Hydraulic Oil Replacement | 2027-05-09 | 2027-05-09 | 12 hrs | FY27 | 12 | 90016793 | B1 | 1000206891 | 09.05.2027 | 6000 | CCK-MP-EXCV-EX7110-HYDSYS | 6900 | 25928 | 25928
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Hydraulic System Tune Up | 2027-05-10 | 2027-05-10 | 12 hrs | FY27 | 24 | 90017865 | B1 | 1000206902 | 10.05.2027 | 6000 | CCK-MP-EXCV-EX7110-HYDSYS | 6900 | 25928 | 25928
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Auto Lube Pump P1 | 2027-05-10 | 2027-05-10 | 2 hrs | FY27 | 2 | 90035369 | B1 | 1000306951 | 10.05.2027 | 10000 | CCK-MP-EXCV-EX7136-GRSYST-AUTLU-ALBPP | 7200 | 19274 | 4382
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Bucket LH Lift | 2027-05-10 | 2027-05-11 | 30 hrs | FY27 | 54 | 90030725 | B1 | 1000306990 | 10.05.2027 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-BUCYL | 7200 | 19274 | 4382
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P2 Slew | 2027-05-10 | 2027-05-10 | 2 hrs | FY27 | 2 | 90019421 | B1 | 1000197106 | 10.05.2027 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP2 | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P3 Slew Teeth | 2027-05-10 | 2027-05-10 | 2 hrs | FY27 | 2 | 90019422 | B1 | 1000197107 | 10.05.2027 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP3 | 7200 | 46126 | 14421
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Auto Lube Pump P1 Slew | 2027-05-10 | 2027-05-10 | 2 hrs | FY27 | 2 | 90015715 | B1 | 1000197105 | 10.05.2027 | 10000 | CCK-MP-EXCV-EX8107-GRSYST-AUTLU-ALBP1 | 7200 | 46126 | 14421
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Batteries | 2027-05-11 | 2027-05-11 | 5 hrs | FY27 | 9 | 90017122 | B1 | 1000250314 | 11.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7120-ELCTLV-CHARG-BATST | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Grease Tank Level Valve | 2027-05-11 | 2027-05-11 | 2 hrs | FY27 | 2 | 90015003 | B2 | 1000250276 | 11.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7120-GRSYST-AUTLU-GRTNK | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 12M Hydraulic Service & Repairs | 2027-05-11 | 2027-05-12 | 18 hrs | FY27 | 30 | 90014448 | B2 | 1000250274 | 11.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7120-HYDSYS | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Track Tension Tuning-Adjust | 2027-05-12 | 2027-05-12 | 3 hrs | FY27 | 9 | 90020545 | B1 | 1000306996 | 12.05.2027 | 6 Monthly | CCK-MP-EXCV-EX7136-UNDERC | 7200 | 19274 | 19274
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Bucket Cylinder - Repl | 2027-05-14 | 2027-05-15 | 18 hrs | FY27 | 54 | 90015703 | B1 | 1000162252 | 14.05.2027 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HBKCL | 7200 | 46126 | 571
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Minestar Harness | 2027-05-15 | 2027-05-16 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000350918 | 15.05.2027 | 4000 | CCK-MP-EXCV-EX7145-MANGMT-UMMMC | 6200 | 7526 | 7526
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Power Pack Module Qtr Life | 2027-05-15 | 2027-05-15 | 7 hrs | FY27 | 13 | 90031021 | B1 | 1000307006 | 15.05.2027 | 5000 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Grease System Audit | 2027-05-15 | 2027-05-16 | 24 hrs | FY27 | 36 | 90030748 | B1 | 1000306960 | 15.05.2027 | 5000 | CCK-MP-EXCV-EX7136-GRSYST-GRINJ | 7200 | 19274 | 6872
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Auto Lube Pump P3 | 2027-05-17 | 2027-05-17 | 2 hrs | FY27 | 2 | 90035368 | B1 | 1000358743 | 17.05.2027 | 10000 | CCK-MP-EXCV-EX7120-GRSYST-AUTLU-ALBP3 | 7200 | 28725 | 4421
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Auto Lube Pump P1 | 2027-05-17 | 2027-05-17 | 2 hrs | FY27 | 2 | 90035369 | B1 | 1000250261 | 17.05.2027 | 10000 | CCK-MP-EXCV-EX7120-GRSYST-AUTLU-ALBPP | 7200 | 28725 | 4421
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Batteries | 2027-05-20 | 2027-05-20 | 4 hrs | FY27 | 4 | 90027525 | B1 | 1000297540 | 20.05.2027 | 10000 | CCK-MP-EXCV-EX7123-ELCTLV-CHARG-BATTY | 6900 | 15607 | 4439
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Adjust 4500hr Valve Set | 2027-05-22 | 2027-05-22 | 10 hrs | FY27 | 20 | 90027549 | B1 | 1000297432 | 22.05.2027 | 4500 | CCK-MP-EXCV-EX7123-RHENGN | 6900 | 15607 | 7903
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl 24V Batteries | 2027-05-22 | 2027-05-22 | 5 hrs | FY27 | 9 | 90029978 | B1 | 1000351953 | 22.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7146-ELCTLV-CHARG-BATST | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Hydraulic Service & Repairs | 2027-05-22 | 2027-05-23 | 18 hrs | FY27 | 30 | 90029940 | B1 | 1000351915 | 22.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7146-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 24M Ovhl AirCondtioner Sys 1 | 2027-05-22 | 2027-05-23 | 36 hrs | FY27 | 36 | 90030500 | B1 | 1000351949 | 22.05.2027 | 24 Monthly | CCK-MP-EXCV-EX7146-STRUCT-AIRC1 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 24M Ovhl AirCondtioner Sys 2 | 2027-05-22 | 2027-05-23 | 36 hrs | FY27 | 36 | 90030537 | B1 | 1000351951 | 22.05.2027 | 24 Monthly | CCK-MP-EXCV-EX7146-STRUCT-AIRC2 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Grease Tank Level Valve | 2027-05-22 | 2027-05-22 | 2 hrs | FY27 | 2 | 90029942 | B1 | 1000351917 | 22.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7146-GRSYST
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Auto Lube Pump P1 | 2027-05-22 | 2027-05-22 | 2 hrs | FY27 | 2 | 90030312 | B1 | 1000352468 | 22.05.2027 | 10000 | CCK-MP-EXCV-EX7147-GRSYST-AUTLU-ALBPP | 6200 | 7547 | 7547
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Svc 12M Air Conditioner Sys1 Eng | 2027-05-22 | 2027-05-22 | 12 hrs | FY27 | 12 | 90035236 | B1 | 1000359785 | 22.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7120-STRUCT-CABIN-AIRC1
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Track Tension Tuning-Adjust | 2027-05-23 | 2027-05-23 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000349854 | 23.05.2027 | 6 Monthly | CCK-MP-EXCV-EX7144-UNDERC | 6200 | 8005 | 8005
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Case Drain Hoses | 2027-05-25 | 2027-05-25 | 8 hrs | FY27 | 16 | 90027566 | B1 | 1000288541 | 25.05.2027 | 15000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-HPCDL | 6900 | 21434 | 9486
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 12M Service Air Con Side Unit | 2027-05-26 | 2027-05-26 | 13 hrs | FY27 | 13 | 90030498 | B1 | 1000349850 | 26.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7144-STRUCT-AIRC1 | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 12M Service Air Con Rear Unit | 2027-05-26 | 2027-05-26 | 13 hrs | FY27 | 13 | 90030536 | B1 | 1000349852 | 26.05.2027 | 12 Monthly | CCK-MP-EXCV-EX7144-STRUCT-AIRC2 | 6200 | 8005 | 8005
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Stick LH | 2027-05-30 | 2027-05-31 | 30 hrs | FY27 | 54 | 90027498 | B1 | 1000288515 | 30.05.2027 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-STCLL | 6900 | 21434 | 6378
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Stick RH | 2027-05-30 | 2027-05-31 | 30 hrs | FY27 | 54 | 90027498 | B1 | 1000288516 | 30.05.2027 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-STCLR | 6900 | 21434 | 6378
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Track Tension Tuning-Adjust | 2027-05-31 | 2027-05-31 | 3 hrs | FY27 | 9 | 90020545 | B1 | 1000250313 | 31.05.2027 | 6 Monthly | CCK-MP-EXCV-EX7120-UNDERC | 7200 | 28725 | 28725
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Swing Pmp Swg Mtr - Repl | 2027-06-01 | 2027-06-03 | 48 hrs | FY27 | 144 | 90015705 | B1 | 1000162254 | 01.06.2027 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HSPSM | 7200 | 46126 | 548
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2027-06-16 | 2027-06-16 | 6 hrs | FY27 | 12 | 90035479 | B1 | 1000359911 | 16.06.2027 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Track Tension Tuning-Adjust | 2027-06-20 | 2027-06-20 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000351952 | 20.06.2027 | 6 Monthly | CCK-MP-EXCV-EX7146-UNDERC | 6200 | 7286 | 7286
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Swing Circuit Hoses | 2027-06-21 | 2027-06-21 | 8 hrs | FY27 | 16 | 90027576 | B1 | 1000288550 | 21.06.2027 | 9000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-SWCRT | 6900 | 21434 | 13568
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Engine Midlife Complete LH | 2027-06-21 | 2027-06-23 | 56 hrs | FY27 | 66 | 90027554 | B1 | 1000288445 | 21.06.2027 | 9000 | CCK-MP-EXCV-EX7121-LHENGN | 6900 | 21434 | 2948
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Engine Midlife Complete RH | 2027-06-21 | 2027-06-23 | 56 hrs | FY27 | 66 | 90027554 | B1 | 1000288451 | 21.06.2027 | 9000 | CCK-MP-EXCV-EX7121-RHENGN | 6900 | 21434 | 2948
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Replace Minestar Harness | 2027-06-22 | 2027-06-23 | 27.5 hrs | FY27 | 43.5 | 90018769 | B2 | 1000281586 | 22.06.2027 | 4000 | CCK-MP-EXCV-EX8107-MANGMT-UMMMC | 7200 | 46126 | 46126
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Fan Drive Hyd Cooling Hoses | 2027-06-24 | 2027-06-25 | 18 hrs | FY27 | 36 | 90009470 | B2 | 1000344108 | 24.06.2027 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-FDHCH | 6900 | 25928 | 6025
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Servo Hoses Bulkhead to MCV | 2027-06-24 | 2027-06-24 | 8 hrs | FY27 | 16 | 90009479 | B1 | 1000343096 | 24.06.2027 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-SHMCV | 6900 | 25928 | 6025
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Track Tensioning Hoses | 2027-06-24 | 2027-06-24 | 3 hrs | FY27 | 3 | 90022741 | B1 | 1000206886 | 24.06.2027 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDHLF-TRTNH | 6900 | 25928 | 6025
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl 24V Batteries | 2027-06-24 | 2027-06-24 | 5 hrs | FY27 | 9 | 90029978 | B1 | 1000352516 | 24.06.2027 | 12 Monthly | CCK-MP-EXCV-EX7147-ELCTLV-CHARG-BATST | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 12M Hydraulic Service & Repairs | 2027-06-24 | 2027-06-25 | 18 hrs | FY27 | 30 | 90029940 | B1 | 1000352478 | 24.06.2027 | 12 Monthly | CCK-MP-EXCV-EX7147-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 24M Ovhl AirCondtioner Sys 1 | 2027-06-24 | 2027-06-25 | 36 hrs | FY27 | 36 | 90030500 | B1 | 1000352512 | 24.06.2027 | 24 Monthly | CCK-MP-EXCV-EX7147-STRUCT-AIRC1 | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 24M Ovhl AirCondtioner Sys 2 | 2027-06-24 | 2027-06-25 | 36 hrs | FY27 | 36 | 90030537 | B1 | 1000352514 | 24.06.2027 | 24 Monthly | CCK-MP-EXCV-EX7147-STRUCT-AIRC2 | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Grease Tank Level Valve | 2027-06-24 | 2027-06-24 | 2 hrs | FY27 | 2 | 90029942 | B1 | 1000352480 | 24.06.2027 | 12 Monthly | CCK-MP-EXCV-EX7147-GRSYST
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Bucket LH | 2027-06-25 | 2027-06-26 | 26 hrs | FY27 | 32 | 90003169 | B1 | 1000206850 | 25.06.2027 | 10000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-BUCYL | 6900 | 25928 | 4012
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Cylinder Bucket RH | 2027-06-25 | 2027-06-26 | 26 hrs | FY27 | 32 | 90003169 | B1 | 1000206851 | 25.06.2027 | 10000 | CCK-MP-EXCV-EX7110-HYDSYS-HDCYL-BUCYR | 6900 | 25928 | 4012
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Track Tension Tuning-Adjust | 2027-06-27 | 2027-06-27 | 3 hrs | FY27 | 9 | 90029977 | B1 | 1000350905 | 27.06.2027 | 6 Monthly | CCK-MP-EXCV-EX7145-UNDERC | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Minestar Harness | 2027-06-28 | 2027-06-29 | 27.5 hrs | FY27 | 43.5 | 90029998 | B1 | 1000351965 | 28.06.2027 | 4000 | CCK-MP-EXCV-EX7146-MANGMT-UMMMC | 6200 | 7286 | 7286
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Bucket | 2027-08-02 | 2027-08-04 | 42 hrs | FY27 | 78 | 90017654 | B1 | 1000162150 | 11.08.2026 | 16000 | CCK-MP-EXCV-EX8106-STRUCT-BUCKT | 7200 | 46150 | 15698
| Onsite PM | Excavators | Fortescue |  | FY28 - EXCAVATORS - COMPONENTS DURING PM | 2027-07-01 |  |  | FY28
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Air Con System | 2027-07-01 | 2027-07-01 | 5 hrs | FY28 | 5 | 90019238 | B1 | 1000195767 | 01.07.2027 | 12 Monthly | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-ACONF | 7200 | 46126 | 7049
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Air Con System | 2027-07-01 | 2027-07-01 | 4 hrs | FY28 | 4 | 90019239 | B1 | 1000195768 | 01.07.2027 | 12 Monthly | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-ACONR | 7200 | 46126 | 7049
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Air Condtioner Compr Front | 2027-07-01 | 2027-07-01 | 5 hrs | FY28 | 5 | 90019236 | B1 | 1000195765 | 01.07.2027 | 12 Monthly | CCK-MP-EXCV-EX8107-STRUCT-CABIN-ACCN1 | 7200 | 46126 | 6810
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Air Condtioner Compr Rear | 2027-07-01 | 2027-07-01 | 4 hrs | FY28 | 4 | 90019237 | B1 | 1000195766 | 01.07.2027 | 12 Monthly | CCK-MP-EXCV-EX8107-STRUCT-CABIN-ACCN2 | 7200 | 46126 | 6810
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Minestar Harness | 2027-07-03 | 2027-07-04 | 27.5 hrs | FY28 | 43.5 | 90031708 | B1 | 1000369997 | 03.07.2027 | 4000 | CCK-MP-EXCV-EX7123-MANGMT-UMMMC | 6900 | 15607 | 15607
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Engine Midlife Complete LH | 2027-07-09 | 2027-07-11 | 54 hrs | FY28 | 76 | 90018424 | B1 | 1000206810 | 09.07.2027 | 9000 | CCK-MP-EXCV-EX7110-LHENGN | 6900 | 25928 | 1337
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Annual Air Con Service RH | 2027-07-15 | 2027-07-15 | 13 hrs | FY28 | 13 | 90027615 | B1 | 1000288563 | 15.07.2027 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN-AIRCR | 6900 | 21434 | 21434
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Pump Swing Combination | 2027-07-15 | 2027-07-16 | 24 hrs | FY28 | 36 | 90030252 | B2 | 1000361422 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HYDPP-SWPP1 | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Bucket LH Lift | 2027-07-15 | 2027-07-16 | 28 hrs | FY28 | 52 | 90029964 | B2 | 1000361396 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-BUCYL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Bucket RH Lift | 2027-07-15 | 2027-07-16 | 28 hrs | FY28 | 52 | 90029967 | B2 | 1000361397 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-BUCYR | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Vlve Bank Module Quarter Life | 2027-07-15 | 2027-07-15 | 6 hrs | FY28 | 12 | 90029987 | B2 | 1000361413 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDVLV-MCVLU | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Valve pressure Limiting Y4 | 2027-07-15 | 2027-07-15 | 6 hrs | FY28 | 6 | 90030321 | B2 | 1000361430 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDVLV-VVPLV | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Accumulator Ladder Hyd | 2027-07-15 | 2027-07-15 | 4 hrs | FY28 | 4 | 90030685 | B2 | 1000361439 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDACC-HACCB | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Accumulator Servo Hyd | 2027-07-15 | 2027-07-15 | 3 hrs | FY28 | 3 | 90030487 | B2 | 1000361414 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDACC-HACCS | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Track Tensioning Hoses | 2027-07-15 | 2027-07-15 | 12 hrs | FY28 | 24 | 90030538 | B2 | 1000361438 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HHTTL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Hyd Hose Work Pumps to Valves | 2027-07-15 | 2027-07-15 | 10.5 hrs | FY28 | 10.5 | 90030287 | B2 | 1000361427 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HWPVV | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Hyd Hose Swing Pump Swing Motor | 2027-07-15 | 2027-07-15 | 12 hrs | FY28 | 24 | 90030288 | B2 | 1000361428 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HSPSM | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Hyd Hose Rotary Con to Valve Bank | 2027-07-15 | 2027-07-15 | 12 hrs | FY28 | 24 | 90029912 | B2 | 1000361351 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HRCVV | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Hoses Rotary Conn to Travel Motor | 2027-07-15 | 2027-07-16 | 24 hrs | FY28 | 48 | 90029914 | B2 | 1000361352 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HRCTM | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Operators Seat | 2027-07-15 | 2027-07-15 | 9 hrs | FY28 | 17 | 90029915 | B2 | 1000361353 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-STRUCT-CABIN-SEATO | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Auto Lube Pump P1 | 2027-07-15 | 2027-07-15 | 2 hrs | FY28 | 2 | 90030312 | B2 | 1000361357 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-GRSYST-AUTLU-ALBPP | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Auto Lube Pump P3 | 2027-07-15 | 2027-07-15 | 2 hrs | FY28 | 2 | 90035351 | B2 | 1000361214 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-GRSYST-AUTLU-ALBP3 | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Grease Injectors | 2027-07-15 | 2027-07-17 | 48 hrs | FY28 | 84 | 90029932 | B2 | 1000361364 | 15.07.2027 | 10000 | CCK-MP-EXCV-EX7157-GRSYST-GRINJ | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Clam Cyl | 2027-07-15 | 2027-07-15 | 10 hrs | FY28 | 20 | 90036569 | B2 | 1000366870 | 15.07.2027 | 5000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HCMCL | 6000 | 4778 | 4778
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 12M Hydraulic Service & Repairs | 2027-07-15 | 2027-07-16 | 18 hrs | FY28 | 30 | 90019301 | B1 | 1000196309 | 15.07.2027 | 12 Monthly | CCK-MP-EXCV-EX8107-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Boom Cyl | 2027-07-20 | 2027-07-22 | 54 hrs | FY28 | 72 | 90029908 | B1 | 1000350849 | 20.07.2027 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HBMCL | 6200 | 7526 | 7526
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Start Batteries | 2027-07-23 | 2027-07-23 | 5 hrs | FY28 | 9 | 90019192 | B1 | 1000195267 | 23.07.2027 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-CHARG
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Track Tension Tuning - Adjust | 2027-07-23 | 2027-07-23 | 3 hrs | FY28 | 9 | 90020546 | B1 | 1000213055 | 23.07.2027 | 6 Monthly | CCK-MP-EXCV-EX8107-UNDERC
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Electrical Cabinet Mounts - Repl | 2027-07-23 | 2027-07-23 | 6 hrs | FY28 | 6 | 90020439 | B1 | 1000211661 | 23.07.2027 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-MCCEL
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Travel RHF | 2027-07-26 | 2027-07-26 | 6 hrs | FY28 | 12 | 90022657 | B1 | 1000206864 | 26.07.2027 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-TRMRF | 6900 | 25928 | 5424
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Hose Boom Cyl | 2027-07-27 | 2027-07-29 | 54 hrs | FY28 | 72 | 90029908 | B1 | 1000349798 | 27.07.2027 | 8000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HBMCL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Hose Stick Cyl | 2027-07-27 | 2027-07-28 | 36 hrs | FY28 | 48 | 90029909 | B1 | 1000349799 | 27.07.2027 | 8000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HSTCL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Track Tension Tuning-Adjust | 2027-07-27 | 2027-07-27 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000352515 | 27.07.2027 | 6 Monthly | CCK-MP-EXCV-EX7147-UNDERC | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Stick Cyl | 2027-07-30 | 2027-07-31 | 36 hrs | FY28 | 48 | 90029909 | B1 | 1000352460 | 30.07.2027 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HSTCL | 6200 | 7547 | 7547
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Minestar Harness | 2027-08-07 | 2027-08-08 | 27.5 hrs | FY28 | 43.5 | 90030746 | B1 | 1000281594 | 07.08.2027 | 5000 | CCK-MP-EXCV-EX7120-MANGMT-UMMMC | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Power Pack Module Qtr Life | 2027-08-11 | 2027-08-11 | 1 hr | FY28 | 1 | 90027378 | B1 | 1000279052 | 11.08.2027 | 5000 | CCK-MP-EXCV-EX7120-ENGINE | 7200 | 28725 | 8287
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Minestar Harness | 2027-08-13 | 2027-08-14 | 27.5 hrs | FY28 | 43.5 | 90031708 | B1 | 1000369998 | 13.08.2027 | 4000 | CCK-MP-EXCV-EX7125-MANGMT-UMMMC | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Bucket LH | 2027-08-13 | 2027-08-14 | 26 hrs | FY28 | 32 | 90027499 | B1 | 1000288517 | 13.08.2027 | 10000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-BUCYL | 6900 | 21434 | 2948
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Cylinder Bucket RH | 2027-08-13 | 2027-08-14 | 26 hrs | FY28 | 32 | 90027499 | B1 | 1000288518 | 13.08.2027 | 10000 | CCK-MP-EXCV-EX7121-HYDSYS-HDCYL-BUCYR | 6900 | 21434 | 11598
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Operators Seat | 2027-08-13 | 2027-08-13 | 2 hrs | FY28 | 2 | 90027613 | B1 | 1000288534 | 13.08.2027 | 10000 | CCK-MP-EXCV-EX7121-STRUCT-CABIN-SEATS | 6900 | 21434 | 21434
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Annual Air Con Service LH | 2027-08-20 | 2027-08-20 | 13 hrs | FY28 | 13 | 90027615 | B1 | 1000288593 | 20.08.2027 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN-AIRCL
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Bucket LH Lift | 2027-08-25 | 2027-08-26 | 22 hrs | FY28 | 46 | 90015688 | B1 | 1000162222 | 25.08.2027 | 10000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-BUCYL | 7200 | 46126 | 548
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Wiper Blades | 2027-08-30 | 2027-08-30 | 1 hr | FY28 | 1 | 90027557 | B1 | 1000296994 | 30.08.2027 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2027-08-31 | 2027-08-31 | 6 hrs | FY28 | 12 | 90035479 | B1 | 1000359911 | 31.08.2027 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 12M Hydraulic Service & Repairs | 2027-09-01 | 2027-09-02 | 18 hrs | FY28 | 30 | 90029940 | B2 | 1000361367 | 01.09.2027 | 12 Monthly | CCK-MP-EXCV-EX7157-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 24M Ovhl Air Con Side Unit | 2027-09-01 | 2027-09-02 | 36 hrs | FY28 | 36 | 90030500 | B2 | 1000361403 | 01.09.2027 | 24 Monthly | CCK-MP-EXCV-EX7157-STRUCT-AIRC1 | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 12M Service Air Con Rear Unit | 2027-09-01 | 2027-09-02 | 36 hrs | FY28 | 36 | 90030537 | B2 | 1000361405 | 01.09.2027 | 24 Monthly | CCK-MP-EXCV-EX7157-STRUCT-AIRC2 | 6000 | 4778 | 4778
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Minestar Harness | 2027-09-10 | 2027-09-11 | 27.5 hrs | FY28 | 43.5 | 90030746 | B1 | 1000307013 | 10.09.2027 | 5000 | CCK-MP-EXCV-EX7136-MANGMT-UMMMC | 7200 | 19274 | 6848
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Minestar Harness | 2027-09-11 | 2027-09-12 | 27.5 hrs | FY28 | 43.5 | 90027626 | B2 | 1000281596 | 11.09.2027 | 4000 | CCK-MP-EXCV-EX7110-MANGMT-UMMMC | 6900 | 25928 | 12535
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Adjust 4500hr Valve Set | 2027-09-11 | 2027-09-11 | 10 hrs | FY28 | 20 | 90017923 | B1 | 1000206823 | 11.09.2027 | 4500 | CCK-MP-EXCV-EX7110-RHENGN | 6900 | 25928 | 6025
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl 24V Batteries | 2027-09-11 | 2027-09-11 | 5 hrs | FY28 | 9 | 90029978 | B2 | 1000361407 | 11.09.2027 | 12 Monthly | CCK-MP-EXCV-EX7157-ELCTLV-CHARG-BATST | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Track Tension Tuning-Adjust | 2027-09-11 | 2027-09-11 | 3 hrs | FY28 | 9 | 90029977 | B2 | 1000361406 | 11.09.2027 | 6 Monthly | CCK-MP-EXCV-EX7157-UNDERC | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Grease Tank Level Valve | 2027-09-11 | 2027-09-11 | 2 hrs | FY28 | 2 | 90029942 | B2 | 1000361369 | 11.09.2027 | 12 Monthly | CCK-MP-EXCV-EX7157-GRSYST
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Annual Air Con Service RH | 2027-09-24 | 2027-09-24 | 13 hrs | FY28 | 13 | 90004141 | B1 | 1000206896 | 24.09.2027 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN-AIRCR | 6900 | 25928 | 25928
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Svc 12M Air Conditioner Sys2 Hyd | 2027-10-07 | 2027-10-07 | 12 hrs | FY28 | 12 | 90035237 | B1 | 1000359787 | 07.10.2027 | 12 Monthly | CCK-MP-EXCV-EX7120-STRUCT-CABIN-AIRC2
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Grease System Audit | 2027-10-24 | 2027-10-25 | 24 hrs | FY28 | 36 | 90029934 | B1 | 1000349816 | 24.10.2027 | 5000 | CCK-MP-EXCV-EX7144-GRSYST-GRINJ | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Grease System Audit | 2027-10-24 | 2027-10-25 | 24 hrs | FY28 | 36 | 90029934 | B1 | 1000350867 | 24.10.2027 | 5000 | CCK-MP-EXCV-EX7145-GRSYST-GRINJ | 6200 | 7526 | 7526
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Valve pressure Limiting Y4 | 2027-10-28 | 2027-10-28 | 4 hrs | FY28 | 4 | 90019283 | B1 | 1000196179 | 28.10.2027 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDVLV-VVPLV | 7200 | 46126 | 7049
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Fan Engine Cool LH | 2027-10-30 | 2027-10-30 | 6 hrs | FY28 | 12 | 90027494 | B1 | 1000288507 | 30.10.2027 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-HECPL | 6900 | 21434 | 9474
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Minestar Harness | 2027-11-01 | 2027-11-02 | 27.5 hrs | FY28 | 43.5 | 90031708 | B1 | 1000369996 | 01.11.2027 | 4000 | CCK-MP-EXCV-EX7121-MANGMT-UMMMC | 6900 | 21434 | 21434
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Operators Seat | 2027-11-11 | 2027-11-11 | 9 hrs | FY28 | 17 | 90030739 | B1 | 1000250257 | 11.11.2027 | 10000 | CCK-MP-EXCV-EX7120-STRUCT-CABIN-SEATO | 7200 | 28725 | 2083
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Grease Injectors | 2027-11-12 | 2027-11-14 | 48 hrs | FY28 | 84 | 90030744 | B1 | 1000250270 | 12.11.2027 | 10000 | CCK-MP-EXCV-EX7120-GRSYST-GRINJ | 7200 | 28725 | 8287
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Bucket | 2027-11-12 | 2027-11-14 | 42 hrs | FY28 | 78 | 90030745 | B1 | 1000250309 | 12.11.2027 | 20000 | CCK-MP-EXCV-EX7120-STRUCT-BUCKT | 7200 | 28725 | 28725
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cylinder Clam LH | 2027-11-13 | 2027-11-13 | 14 hrs | FY28 | 22 | 90035631 | B2 | 1000361398 | 13.11.2027 | 6000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-CLAML | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cylinder Clam RH | 2027-11-13 | 2027-11-13 | 14 hrs | FY28 | 22 | 90035631 | B2 | 1000361399 | 13.11.2027 | 6000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-CLAMR | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Grease System Audit | 2027-11-16 | 2027-11-17 | 24 hrs | FY28 | 36 | 90029934 | B1 | 1000351914 | 16.11.2027 | 5000 | CCK-MP-EXCV-EX7146-GRSYST-GRINJ | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Track Tension Tuning-Adjust | 2027-11-19 | 2027-11-19 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000349854 | 19.11.2027 | 6 Monthly | CCK-MP-EXCV-EX7144-UNDERC | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Grease System Audit | 2027-11-24 | 2027-11-25 | 24 hrs | FY28 | 36 | 90029934 | B1 | 1000352477 | 24.11.2027 | 5000 | CCK-MP-EXCV-EX7147-GRSYST-GRINJ | 6200 | 7547 | 7547
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Batteries | 2027-11-24 | 2027-11-24 | 8 hrs | FY28 | 8 | 90016788 | B1 | 1000206892 | 24.11.2027 | 10000 | CCK-MP-EXCV-EX7110-ELCTLV-CHARG-BATTY | 6900 | 25928 | 11135
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Pump Fan Engine Cool RH | 2027-11-25 | 2027-11-25 | 6 hrs | FY28 | 12 | 90027494 | B1 | 1000288508 | 25.11.2027 | 18000 | CCK-MP-EXCV-EX7121-HYDSYS-HYDPP-HECPR | 6900 | 21434 | 9474
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Track Tension Tuning-Adjust | 2027-11-27 | 2027-11-27 | 3 hrs | FY28 | 9 | 90020545 | B1 | 1000250313 | 27.11.2027 | 6 Monthly | CCK-MP-EXCV-EX7120-UNDERC | 7200 | 28725 | 28725
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Auto Lube Pump | 2027-11-27 | 2027-11-27 | 6 hrs | FY28 | 6 | 90027592 | B1 | 1000288569 | 27.11.2027 | 6000 | CCK-MP-EXCV-EX7121-GRSYST-ALBPP | 6900 | 21434 | 9780
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Hydraulic System Tune Up | 2027-11-27 | 2027-11-27 | 12 hrs | FY28 | 24 | 90017865 | B1 | 1000288568 | 27.11.2027 | 6000 | CCK-MP-EXCV-EX7121-HYDSYS | 6900 | 21434 | 21434
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Hydraulic Oil Replacement | 2027-11-27 | 2027-11-27 | 12 hrs | FY28 | 12 | 90016793 | B1 | 1000288558 | 27.11.2027 | 6000 | CCK-MP-EXCV-EX7121-HYDSYS | 6900 | 21434 | 21434
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Main Pump to Rotor Hoses | 2027-11-27 | 2027-11-28 | 24 hrs | FY28 | 48 | 90027567 | B1 | 1000288542 | 27.11.2027 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-MPRCH | 6900 | 21434 | 13548
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Boom LH | 2027-12-06 | 2027-12-07 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000349842 | 06.12.2027 | 16000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-BMCYL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Boom RH | 2027-12-06 | 2027-12-07 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000349843 | 06.12.2027 | 16000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-BMCYR | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Stick LH | 2027-12-06 | 2027-12-07 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000349844 | 06.12.2027 | 16000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-STCLL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Cyl Stick RH | 2027-12-06 | 2027-12-07 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000349845 | 06.12.2027 | 16000 | CCK-MP-EXCV-EX7144-HYDSYS-HDCYL-STCLR | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Hose Bucket Cyl | 2027-12-06 | 2027-12-07 | 18 hrs | FY28 | 54 | 90029911 | B1 | 1000349800 | 06.12.2027 | 8000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HBKCL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Boom LH | 2027-12-09 | 2027-12-10 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000352503 | 09.12.2027 | 16000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-BMCYL | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Boom RH | 2027-12-09 | 2027-12-10 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000352504 | 09.12.2027 | 16000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-BMCYR | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Stick LH | 2027-12-09 | 2027-12-10 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000352505 | 09.12.2027 | 16000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-STCLL | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Cyl Stick RH | 2027-12-09 | 2027-12-10 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000352506 | 09.12.2027 | 16000 | CCK-MP-EXCV-EX7147-HYDSYS-HDCYL-STCLR | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Boom Cyl | 2027-12-09 | 2027-12-11 | 54 hrs | FY28 | 72 | 90029908 | B1 | 1000352459 | 09.12.2027 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HBMCL | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Bucket Cyl | 2027-12-09 | 2027-12-10 | 18 hrs | FY28 | 54 | 90029911 | B1 | 1000352461 | 09.12.2027 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HBKCL | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Minestar Harness | 2027-12-09 | 2027-12-10 | 27.5 hrs | FY28 | 43.5 | 90029998 | B1 | 1000352528 | 09.12.2027 | 4000 | CCK-MP-EXCV-EX7147-MANGMT-UMMMC | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Minestar Harness | 2027-12-11 | 2027-12-12 | 27.5 hrs | FY28 | 43.5 | 90029998 | B1 | 1000349867 | 11.12.2027 | 4000 | CCK-MP-EXCV-EX7144-MANGMT-UMMMC | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Track Tension Tuning-Adjust | 2027-12-17 | 2027-12-17 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000351952 | 17.12.2027 | 6 Monthly | CCK-MP-EXCV-EX7146-UNDERC | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Track Tension Tuning-Adjust | 2027-12-24 | 2027-12-24 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000350905 | 24.12.2027 | 6 Monthly | CCK-MP-EXCV-EX7145-UNDERC | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Cyl Boom LH | 2028-01-06 | 2028-01-07 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000350893 | 06.01.2028 | 16000 | CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-BMCYL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Cyl Boom RH | 2028-01-06 | 2028-01-07 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000350894 | 06.01.2028 | 16000 | CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-BMCYR | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Cyl Stick LH | 2028-01-06 | 2028-01-07 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000350895 | 06.01.2028 | 16000 | CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-STCLL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Cyl Stick RH | 2028-01-06 | 2028-01-07 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000350896 | 06.01.2028 | 16000 | CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-STCLR | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Stick Cyl | 2028-01-06 | 2028-01-07 | 36 hrs | FY28 | 48 | 90029909 | B1 | 1000350850 | 06.01.2028 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HSTCL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Bucket Cyl | 2028-01-06 | 2028-01-07 | 18 hrs | FY28 | 54 | 90029911 | B1 | 1000350851 | 06.01.2028 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HBKCL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Minestar Harness | 2028-01-06 | 2028-01-07 | 27.5 hrs | FY28 | 43.5 | 90029998 | B1 | 1000350918 | 06.01.2028 | 4000 | CCK-MP-EXCV-EX7145-MANGMT-UMMMC | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Boom LH | 2028-01-14 | 2028-01-15 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000351940 | 14.01.2028 | 16000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-BMCYL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Boom RH | 2028-01-14 | 2028-01-15 | 40 hrs | FY28 | 76 | 90029951 | B1 | 1000351941 | 14.01.2028 | 16000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-BMCYR | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Stick LH | 2028-01-14 | 2028-01-15 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000351942 | 14.01.2028 | 16000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-STCLL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Cyl Stick RH | 2028-01-14 | 2028-01-15 | 28 hrs | FY28 | 52 | 90029971 | B1 | 1000351943 | 14.01.2028 | 16000 | CCK-MP-EXCV-EX7146-HYDSYS-HDCYL-STCLR | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Boom Cyl | 2028-01-14 | 2028-01-16 | 54 hrs | FY28 | 72 | 90029908 | B1 | 1000351896 | 14.01.2028 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HBMCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Stick Cyl | 2028-01-14 | 2028-01-15 | 36 hrs | FY28 | 48 | 90029909 | B1 | 1000351897 | 14.01.2028 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HSTCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Bucket Cyl | 2028-01-14 | 2028-01-15 | 18 hrs | FY28 | 54 | 90029911 | B1 | 1000351898 | 14.01.2028 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HBKCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Track Tension Tuning-Adjust | 2028-01-23 | 2028-01-23 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000352515 | 23.01.2028 | 6 Monthly | CCK-MP-EXCV-EX7147-UNDERC | 6200 | 7547 | 7547
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Track Tensioning Hoses | 2028-02-09 | 2028-02-09 | 3 hrs | FY28 | 3 | 90027579 | B1 | 1000288553 | 09.02.2028 | 12000 | CCK-MP-EXCV-EX7121-HYDSYS-HDHLF-TRTNH | 6900 | 21434 | 13548
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Adjust 500hr Initial Valve Set | 2028-02-11 | 2028-02-11 | 10 hrs | FY28 | 20 | 90027550 | B1 | 1000297431 | 11.02.2028 | 500 | CCK-MP-EXCV-EX7123-RHENGN | 6900 | 15607 | 7903
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 4500hr Valve Set | 2028-02-14 | 2028-02-14 | 10 hrs | FY28 | 20 | 90027549 | B1 | 1000288444 | 14.02.2028 | 4500 | CCK-MP-EXCV-EX7121-LHENGN | 6900 | 21434 | 2948
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 4500hr Valve Set | 2028-02-14 | 2028-02-14 | 10 hrs | FY28 | 20 | 90027549 | B1 | 1000288450 | 14.02.2028 | 4500 | CCK-MP-EXCV-EX7121-RHENGN | 6900 | 21434 | 2948
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Minestar Harness | 2028-02-19 | 2028-02-20 | 27.5 hrs | FY28 | 43.5 | 90029998 | B1 | 1000351965 | 19.02.2028 | 4000 | CCK-MP-EXCV-EX7146-MANGMT-UMMMC | 6200 | 7286 | 7286
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Adjust 4500hr Valve Set | 2028-03-03 | 2028-03-03 | 10 hrs | FY28 | 20 | 90017923 | B1 | 1000206809 | 03.03.2028 | 4500 | CCK-MP-EXCV-EX7110-LHENGN | 6900 | 25928 | 1337
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Minestar Harness | 2028-03-10 | 2028-03-11 | 27.5 hrs | FY28 | 43.5 | 90029998 | B1 | 1000378437 | 10.03.2028 | 4000 | CCK-MP-EXCV-EX7153-MANGMT-UMMMC | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Track Tension Tuning-Adjust | 2028-03-11 | 2028-03-11 | 3 hrs | FY28 | 9 | 90029977 | B2 | 1000361406 | 11.03.2028 | 6 Monthly | CCK-MP-EXCV-EX7157-UNDERC | 6000 | 4778 | 4778
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Wiper Blades | 2028-03-13 | 2028-03-13 | 1 hr | FY28 | 1 | 90027557 | B1 | 1000288564 | 13.03.2028 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl 24V Batteries | 2028-03-18 | 2028-03-18 | 5 hrs | FY28 | 9 | 90029978 | B1 | 1000378426 | 18.03.2028 | 12 Monthly | CCK-MP-EXCV-EX7153-ELCTLV-CHARG-BATST | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Track Tension Tuning-Adjust | 2028-03-18 | 2028-03-18 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000378425 | 18.03.2028 | 6 Monthly | CCK-MP-EXCV-EX7153-UNDERC | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 12M Hydraulic Service & Repairs | 2028-03-18 | 2028-03-19 | 18 hrs | FY28 | 30 | 90029940 | B1 | 1000378388 | 18.03.2028 | 12 Monthly | CCK-MP-EXCV-EX7153-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 24M Ovhl Air Con Side Unit | 2028-03-18 | 2028-03-19 | 36 hrs | FY28 | 36 | 90030500 | B1 | 1000378422 | 18.03.2028 | 24 Monthly | CCK-MP-EXCV-EX7153-STRUCT-AIRC1 | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 24M Ovhl Air Con Rear Unit | 2028-03-18 | 2028-03-19 | 36 hrs | FY28 | 36 | 90030537 | B1 | 1000378424 | 18.03.2028 | 24 Monthly | CCK-MP-EXCV-EX7153-STRUCT-AIRC2 | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Grease Tank Level Valve | 2028-03-18 | 2028-03-18 | 2 hrs | FY28 | 2 | 90029942 | B1 | 1000378390 | 18.03.2028 | 12 Monthly | CCK-MP-EXCV-EX7153-GRSYST
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl 24V Batteries | 2028-04-03 | 2028-04-03 | 5 hrs | FY28 | 9 | 90029978 | B1 | 1000349855 | 03.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7144-ELCTLV-CHARG-BATST | 6200 | 8005 | 8005
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Grease Injectors | 2028-04-03 | 2028-04-05 | 48 hrs | FY28 | 84 | 90030744 | B1 | 1000232082 | 03.04.2028 | 10000 | CCK-MP-EXCV-EX7117-GRSYST-GRINJ | 7200 | 32281 | 7621
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 12M Hydraulic Service & Repairs | 2028-04-04 | 2028-04-05 | 18 hrs | FY28 | 30 | 90029940 | B1 | 1000349817 | 04.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7144-HYDSYS
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Replace Minestar Harness | 2028-04-12 | 2028-04-13 | 27.5 hrs | FY28 | 43.5 | 90018769 | B2 | 1000281581 | 12.04.2028 | 4000 | CCK-MP-EXCV-EX8106-MANGMT-UMMMC | 7200 | 46150 | 15686
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Grease Tank Level Valve | 2028-04-15 | 2028-04-15 | 2 hrs | FY28 | 2 | 90029942 | B1 | 1000349819 | 15.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7144-GRSYST
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2028-04-15 | 2028-04-15 | 6 hrs | FY28 | 12 | 90035479 | B1 | 1000359911 | 15.04.2028 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Track Tension Tuning - Adjust | 2028-04-19 | 2028-04-19 | 3 hrs | FY28 | 9 | 90020546 | B1 | 1000213054 | 19.04.2028 | 6 Monthly | CCK-MP-EXCV-EX8106-UNDERC
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl 24V Batteries | 2028-04-20 | 2028-04-20 | 5 hrs | FY28 | 9 | 90029978 | B1 | 1000350906 | 20.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7145-ELCTLV-CHARG-BATST | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 12M Hydraulic Service & Repairs | 2028-04-20 | 2028-04-21 | 18 hrs | FY28 | 30 | 90029940 | B1 | 1000350868 | 20.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7145-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 12M Service Air Conditioner Sys 1 | 2028-04-20 | 2028-04-20 | 13 hrs | FY28 | 13 | 90030498 | B1 | 1000350901 | 20.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7145-STRUCT-AIRC1 | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 12M Service Air Conditioner Sys 2 | 2028-04-20 | 2028-04-20 | 13 hrs | FY28 | 13 | 90030536 | B1 | 1000350903 | 20.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7145-STRUCT-AIRC2 | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Grease Tank Level Valve | 2028-04-20 | 2028-04-20 | 2 hrs | FY28 | 2 | 90029942 | B1 | 1000350870 | 20.04.2028 | 12 Monthly | CCK-MP-EXCV-EX7145-GRSYST
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Start Batteries | 2028-05-01 | 2028-05-01 | 5 hrs | FY28 | 9 | 90019192 | B1 | 1000195266 | 01.05.2028 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-CHARG
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Maintenance Batteries | 2028-05-01 | 2028-05-01 | 3 hrs | FY28 | 5 | 90019334 | 1 | 1000195273 | 01.05.2028 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-CHARG
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Grease Tank Level Valve | 2028-05-02 | 2028-05-02 | 2 hrs | FY28 | 2 | 90015003 | B4 | 1000162121 | 02.05.2028 | 12 Monthly | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-GRTNK
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Electrical Cabinet Mounts - Rep | 2028-05-02 | 2028-05-02 | 6 hrs | FY28 | 6 | 90020439 | B1 | 1000211660 | 02.05.2028 | 12 Monthly | CCK-MP-EXCV-EX8106-ELCTLV-MCCEL
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Swing LHR | 2028-05-03 | 2028-05-04 | 21 hrs | FY28 | 27 | 90027503 | B1 | 1000288522 | 03.05.2028 | 15000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-SWMLR | 6900 | 21434 | 21434
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Final Drive LH | 2028-05-03 | 2028-05-08 | 126 hrs | FY28 | 218 | 90015667 | B1 | 1000162034 | 03.05.2028 | 18000 | CCK-MP-EXCV-EX8106-UNDERC-TKFRL-FDRLH | 7200 | 46150 | 5321
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Swing RHF | 2028-05-04 | 2028-05-05 | 21 hrs | FY28 | 27 | 90027503 | B1 | 1000288523 | 04.05.2028 | 15000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-SWMRF | 6900 | 21434 | 21434
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Hyd Motor Swing RHR | 2028-05-04 | 2028-05-05 | 21 hrs | FY28 | 27 | 90027503 | B1 | 1000288524 | 04.05.2028 | 15000 | CCK-MP-EXCV-EX7121-HYDSYS-HDMOT-SWMRR | 6900 | 21434 | 21434
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Track Tension Tuning-Adjust | 2028-05-06 | 2028-05-06 | 3 hrs | FY28 | 9 | 90020545 | B1 | 1000306996 | 06.05.2028 | 6 Monthly | CCK-MP-EXCV-EX7136-UNDERC | 7200 | 19274 | 19274
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Power Pack Module Qtr Life | 2028-05-12 | 2028-05-12 | 1 hr | FY28 | 1 | 90027378 | B1 | 1000279047 | 12.05.2028 | 5000 | CCK-MP-EXCV-EX7117-ENGINE | 7200 | 32281 | 12760
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Grease System Audit | 2028-05-14 | 2028-05-15 | 24 hrs | FY28 | 36 | 90029934 | B2 | 1000361366 | 14.05.2028 | 5000 | CCK-MP-EXCV-EX7157-GRSYST-GRINJ | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Clam Cyl | 2028-05-14 | 2028-05-14 | 10 hrs | FY28 | 20 | 90036569 | B2 | 1000366870 | 14.05.2028 | 5000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HCMCL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl 24V Batteries | 2028-05-16 | 2028-05-16 | 5 hrs | FY28 | 9 | 90029978 | B1 | 1000351953 | 16.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7146-ELCTLV-CHARG-BATST | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Hydraulic Service & Repairs | 2028-05-16 | 2028-05-17 | 18 hrs | FY28 | 30 | 90029940 | B1 | 1000351915 | 16.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7146-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Service Air Conditioner Sys 1 | 2028-05-16 | 2028-05-16 | 13 hrs | FY28 | 13 | 90030498 | B1 | 1000351948 | 16.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7146-STRUCT-AIRC1 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Service Air Conditioner Sys 2 | 2028-05-16 | 2028-05-16 | 13 hrs | FY28 | 13 | 90030536 | B1 | 1000351950 | 16.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7146-STRUCT-AIRC2 | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Grease Tank Level Valve | 2028-05-16 | 2028-05-16 | 2 hrs | FY28 | 2 | 90029942 | B1 | 1000351917 | 16.05.2028 | 12 Monthly | CCK-MP-EXCV-EX7146-GRSYST
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Minestar Harness | 2028-05-16 | 2028-05-17 | 27.5 hrs | FY28 | 43.5 | 90030746 | B1 | 1000281593 | 16.05.2028 | 5000 | CCK-MP-EXCV-EX7117-MANGMT-UMMMC | 7200 | 32281 | 32281
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Track Tension Tuning-Adjust | 2028-05-17 | 2028-05-17 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000349854 | 17.05.2028 | 6 Monthly | CCK-MP-EXCV-EX7144-UNDERC | 6200 | 8005 | 8005
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Bucket | 2028-05-21 | 2028-05-23 | 42 hrs | FY28 | 78 | 90030745 | B1 | 1000232121 | 21.05.2028 | 20000 | CCK-MP-EXCV-EX7117-STRUCT-BUCKT | 7200 | 32281 | 7046
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Minestar Harness | 2028-05-21 | 2028-05-22 | 27.5 hrs | FY28 | 43.5 | 90030746 | B1 | 1000307013 | 21.05.2028 | 5000 | CCK-MP-EXCV-EX7136-MANGMT-UMMMC | 7200 | 19274 | 6848
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 4500hr Valve Set | 2028-05-30 | 2028-05-30 | 10 hrs | FY28 | 20 | 90027549 | B1 | 1000296916 | 30.05.2028 | 4500 | CCK-MP-EXCV-EX7125-LHENGN | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 4500hr Valve Set | 2028-05-30 | 2028-05-30 | 10 hrs | FY28 | 20 | 90027549 | B1 | 1000296921 | 30.05.2028 | 4500 | CCK-MP-EXCV-EX7125-RHENGN | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Minestar Harness | 2028-05-31 | 2028-06-01 | 27.5 hrs | FY28 | 43.5 | 90031708 | B1 | 1000369996 | 31.05.2028 | 4000 | CCK-MP-EXCV-EX7121-MANGMT-UMMMC | 6900 | 21434 | 21434
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Adjust 500hr Initial Valve Set | 2028-06-02 | 2028-06-02 | 10 hrs | FY28 | 20 | 90017925 | B1 | 1000206822 | 02.06.2028 | 500 | CCK-MP-EXCV-EX7110-RHENGN | 6900 | 25928 | 6025
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Bucket LH Lift | 2028-06-09 | 2028-06-10 | 30 hrs | FY28 | 54 | 90030725 | B1 | 1000232115 | 09.06.2028 | 10000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-BUCYL | 7200 | 32281 | 2607
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Bucket RH Lift | 2028-06-09 | 2028-06-10 | 30 hrs | FY28 | 54 | 90030726 | B1 | 1000232116 | 09.06.2028 | 10000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-BUCYR | 7200 | 32281 | 6735
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Bucket RH Lift | 2028-06-13 | 2028-06-14 | 24 hrs | FY28 | 48 | 90015689 | B1 | 1000162074 | 13.06.2028 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-BUCYR | 7200 | 46150 | 279
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Track Tension Tuning-Adjust | 2028-06-14 | 2028-06-14 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000351952 | 14.06.2028 | 6 Monthly | CCK-MP-EXCV-EX7146-UNDERC | 6200 | 7286 | 7286
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Boom RH | 2028-06-14 | 2028-06-16 | 42 hrs | FY28 | 78 | 90030723 | B1 | 1000232112 | 14.06.2028 | 16000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-BMCYR | 7200 | 32281 | 2607
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Stick RH | 2028-06-14 | 2028-06-15 | 30 hrs | FY28 | 54 | 90030724 | B1 | 1000232114 | 14.06.2028 | 16000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-STCLR | 7200 | 32281 | 2607
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Hose Stick Cyl | 2028-06-15 | 2028-06-16 | 36 hrs | FY28 | 48 | 90030737 | B1 | 1000232062 | 15.06.2028 | 8000 | CCK-MP-EXCV-EX7117-HYDSYS-HDHLF-HSTCL | 7200 | 32281 | 7621
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Cyl Boom LH | 2028-06-16 | 2028-06-18 | 42 hrs | FY28 | 78 | 90030723 | B1 | 1000232111 | 16.06.2028 | 16000 | CCK-MP-EXCV-EX7117-HYDSYS-HDCYL-BMCYL | 7200 | 32281 | 2607
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Hose Bucket Cyl | 2028-06-16 | 2028-06-17 | 18 hrs | FY28 | 54 | 90030738 | B1 | 1000325211 | 16.06.2028 | 8000 | CCK-MP-EXCV-EX7117-HYDSYS-HDHLF-HBKCL | 7200 | 32281 | 2639
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Hyd Hose Boom Cyl | 2028-06-16 | 2028-06-18 | 54 hrs | FY28 | 72 | 90030735 | B1 | 1000232061 | 16.06.2028 | 8000 | CCK-MP-EXCV-EX7117-HYDSYS-HDHLF-HBMCL | 7200 | 32281 | 2639
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl 24V Batteries | 2028-06-18 | 2028-06-18 | 5 hrs | FY28 | 9 | 90029978 | B1 | 1000352516 | 18.06.2028 | 12 Monthly | CCK-MP-EXCV-EX7147-ELCTLV-CHARG-BATST | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 12M Hydraulic Service & Repairs | 2028-06-18 | 2028-06-19 | 18 hrs | FY28 | 30 | 90029940 | B1 | 1000352478 | 18.06.2028 | 12 Monthly | CCK-MP-EXCV-EX7147-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 12M Service Air Conditioner Sys 1 | 2028-06-18 | 2028-06-18 | 13 hrs | FY28 | 13 | 90030498 | B1 | 1000352511 | 18.06.2028 | 12 Monthly | CCK-MP-EXCV-EX7147-STRUCT-AIRC1 | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 12M Service Air Conditioner Sys 2 | 2028-06-18 | 2028-06-18 | 13 hrs | FY28 | 13 | 90030536 | B1 | 1000352513 | 18.06.2028 | 12 Monthly | CCK-MP-EXCV-EX7147-STRUCT-AIRC2 | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Grease Tank Level Valve | 2028-06-18 | 2028-06-18 | 2 hrs | FY28 | 2 | 90029942 | B1 | 1000352480 | 18.06.2028 | 12 Monthly | CCK-MP-EXCV-EX7147-GRSYST
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Boom Module Quarter Life | 2028-06-19 | 2028-06-20 | 30 hrs | FY28 | 48 | 90029992 | B1 | 1000352526 | 17.06.2028 | 10000 | CCK-MP-EXCV-EX7147-STRUCT-BOOMS | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Track Tension Tuning-Adjust | 2028-06-21 | 2028-06-21 | 3 hrs | FY28 | 9 | 90029977 | B1 | 1000350905 | 21.06.2028 | 6 Monthly | CCK-MP-EXCV-EX7145-UNDERC | 6200 | 7526 | 7526
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Boom LH | 2028-06-25 | 2028-06-27 | 42 hrs | FY28 | 78 | 90030723 | B1 | 1000306986 | 25.06.2028 | 16000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-BMCYL | 7200 | 19274 | 2254
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Boom RH | 2028-06-25 | 2028-06-27 | 42 hrs | FY28 | 78 | 90030723 | B1 | 1000306987 | 25.06.2028 | 16000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-BMCYR | 7200 | 19274 | 2254
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Boom Stick Bucket Cyl Hoses | 2028-06-28 | 2028-07-01 | 88 hrs | FY28 | 136 | 90027560 | B1 | 1000296967 | 28.06.2028 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-HBSBC | 6900 | 18844 | 10809
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Boom & MCV Hoses | 2028-06-28 | 2028-07-01 | 88 hrs | FY28 | 136 | 90032593 | B1 | 1000325063 | 28.06.2028 | 12000 | CCK-MP-EXCV-EX7125-HYDSYS-HDHLF-HBSBC | 6900 | 18844 | 10809
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 1500Hr Engine Valve Set | 2028-06-30 | 2028-06-30 | 6 hrs | FY28 | 12 | 90035479 | B1 | 1000359911 | 30.06.2028 | 1500 | CCK-MP-EXCV-EX7136-ENGINE | 7200 | 19274 | 1969
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hydraulic Tank Module Midlife | 2028-06-30 | 2028-07-01 | 24 hrs | FY28 | 48 | 90026633 | B1 | 1000267598 | 30.06.2028 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDTNK | 7200 | 46150 | 21475
| Onsite PM | Excavators | Fortescue |  | FY29 - EXCAVATORS - COMPONENTS DURING PM | 2028-07-01 | 2029-06-30 |  | FY29
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Annual Air Con Service LH | 2028-07-03 | 2028-07-03 | 13 hrs | FY29 | 13 | 90027615 | B1 | 1000297574 | 03.07.2028 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN-AIRCL
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Hydraulic Tank Module Midlife | 2028-07-03 | 2028-07-04 | 24 hrs | FY29 | 48 | 90026633 | B1 | 1000268043 | 03.07.2028 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDTNK | 7200 | 46126 | 21919
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Bucket LH | 2028-07-09 | 2028-07-10 | 26 hrs | FY29 | 32 | 90027499 | B1 | 1000296947 | 09.07.2028 | 10000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BUCYL | 6900 | 18844 | 6591
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Cylinder Bucket RH | 2028-07-09 | 2028-07-10 | 26 hrs | FY29 | 32 | 90027499 | B1 | 1000296948 | 09.07.2028 | 10000 | CCK-MP-EXCV-EX7125-HYDSYS-HDCYL-BUCYR | 6900 | 18844 | 6591
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 12M Hydraulic Service & Repairs | 2028-07-09 | 2028-07-10 | 18 hrs | FY29 | 30 | 90019301 | B1 | 1000196309 | 09.07.2028 | 12 Monthly | CCK-MP-EXCV-EX8107-HYDSYS
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel RHF | 2028-07-09 | 2028-07-09 | 8 hrs | FY29 | 14 | 90015697 | B1 | 1000162243 | 09.07.2028 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMRF | 7200 | 46126 | 10005
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Travel RHR | 2028-07-09 | 2028-07-09 | 8 hrs | FY29 | 14 | 90015697 | B1 | 1000162244 | 09.07.2028 | 12000 | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-TRMRR | 7200 | 46126 | 10005
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Service Trap & Ladder Harns | 2028-07-09 | 2028-07-09 | 12 hrs | FY29 | 12 | 90019319 | B1 | 1000245271 | 09.07.2028 | 24000 | CCK-MP-EXCV-EX8107-ELCTLV-HARNS-HARLA | 7200 | 46126 | 9981
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Hyd Hose Swing Pmp Swg Mtr - Repl | 2028-07-10 | 2028-07-12 | 48 hrs | FY29 | 144 | 90015705 | B1 | 1000162254 | 10.07.2028 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HSPSM | 7200 | 46126 | 548
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Cyl Bucket LH Lift | 2028-07-10 | 2028-07-11 | 22 hrs | FY29 | 46 | 90015688 | B1 | 1000162073 | 10.07.2028 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDCYL-BUCYL | 7200 | 46150 | 5656
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Bucket Cylinders - Repl | 2028-07-10 | 2028-07-11 | 18 hrs | FY29 | 54 | 90015703 | B1 | 1000222964 | 10.07.2028 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HBKCL | 7200 | 46150 | 21475
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Auto Lube Pump P3 Slew Teeth | 2028-07-10 | 2028-07-10 | 2 hrs | FY29 | 2 | 90019422 | B1 | 1000197104 | 10.07.2028 | 10000 | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-ALBP3 | 7200 | 46150 | 5656
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Annual Air Con Service LH | 2028-07-14 | 2028-07-14 | 13 hrs | FY29 | 13 | 90027615 | B1 | 1000297023 | 14.07.2028 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN-AIRCL
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Boom LH | 2028-07-14 | 2028-07-15 | 40 hrs | FY29 | 76 | 90029951 | B2 | 1000361392 | 14.07.2028 | 16000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-BMCYL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Boom RH | 2028-07-14 | 2028-07-15 | 40 hrs | FY29 | 76 | 90029951 | B2 | 1000361393 | 14.07.2028 | 16000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-BMCYR | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Stick LH | 2028-07-14 | 2028-07-15 | 28 hrs | FY29 | 52 | 90029971 | B2 | 1000361394 | 14.07.2028 | 16000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-STCLL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cyl Stick RH | 2028-07-14 | 2028-07-15 | 28 hrs | FY29 | 52 | 90029971 | B2 | 1000361395 | 14.07.2028 | 16000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-STCLR | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Boom Cyl | 2028-07-14 | 2028-07-16 | 54 hrs | FY29 | 72 | 90029908 | B2 | 1000361348 | 14.07.2028 | 8000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HBMCL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Stick Cyl | 2028-07-14 | 2028-07-15 | 36 hrs | FY29 | 48 | 90029909 | B2 | 1000361349 | 14.07.2028 | 8000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HSTCL | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Hyd Hose Bucket Cyl | 2028-07-14 | 2028-07-15 | 18 hrs | FY29 | 54 | 90029911 | B2 | 1000361350 | 14.07.2028 | 8000 | CCK-MP-EXCV-EX7157-HYDSYS-HDHLF-HBKCL | 6000 | 4778 | 4778
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Annual Air Con Service RH | 2028-07-15 | 2028-07-15 | 13 hrs | FY29 | 13 | 90027615 | B1 | 1000296993 | 15.07.2028 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN-AIRCR | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Auto Lube Pump | 2028-07-17 | 2028-07-17 | 6 hrs | FY29 | 6 | 90027592 | B1 | 1000297550 | 17.07.2028 | 6000 | CCK-MP-EXCV-EX7123-GRSYST-ALBPP | 6900 | 15681 | 503
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Hydraulic System Tune Up | 2028-07-17 | 2028-07-17 | 12 hrs | FY29 | 24 | 90017865 | B1 | 1000297549 | 17.07.2028 | 6000 | CCK-MP-EXCV-EX7123-HYDSYS | 6900 | 15607 | 15607
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Hydraulic Oil Replacement | 2028-07-17 | 2028-07-17 | 12 hrs | FY29 | 12 | 90016793 | B1 | 1000297539 | 17.07.2028 | 6000 | CCK-MP-EXCV-EX7123-HYDSYS | 6900 | 15607 | 15607
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Swing Circuit Hoses | 2028-07-17 | 2028-07-17 | 8 hrs | FY29 | 16 | 90027576 | B1 | 1000297531 | 17.07.2028 | 9000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-SWCRT | 6900 | 15607 | 4439
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Start Batteries | 2028-07-17 | 2028-07-17 | 5 hrs | FY29 | 9 | 90019192 | B1 | 1000195267 | 17.07.2028 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-CHARG
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Track Tension Tuning - Adjust | 2028-07-17 | 2028-07-17 | 3 hrs | FY29 | 9 | 90020546 | B1 | 1000213055 | 17.07.2028 | 6 Monthly | CCK-MP-EXCV-EX8107-UNDERC
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Electrical Cabinet Mounts - Repl | 2028-07-17 | 2028-07-17 | 6 hrs | FY29 | 6 | 90020439 | B1 | 1000211661 | 17.07.2028 | 12 Monthly | CCK-MP-EXCV-EX8107-ELCTLV-MCCEL
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Boom Cylinders - Replace | 2028-07-17 | 2028-07-17 | 8 hrs | FY29 | 16 | 90015701 | B1 | 1000222962 | 17.07.2028 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HBCYL | 7200 | 46150 | 1397
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Stick Cylinders - Repl | 2028-07-17 | 2028-07-18 | 20 hrs | FY29 | 44 | 90015702 | B1 | 1000222963 | 17.07.2028 | 10000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HSCYL | 7200 | 46150 | 1397
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Auto Lube Pump P2 Slew | 2028-07-17 | 2028-07-17 | 2 hrs | FY29 | 2 | 90019421 | B1 | 1000196919 | 17.07.2028 | 10000 | CCK-MP-EXCV-EX8106-GRSYST-AUTLU-ALBP2 | 7200 | 46150 | 1421
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Grease System Audit | 2028-07-22 | 2028-07-23 | 24 hrs | FY29 | 36 | 90030748 | B1 | 1000250272 | 22.07.2028 | 5000 | CCK-MP-EXCV-EX7120-GRSYST-GRINJ | 7200 | 28725 | 8287
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing RHF P1 | 2028-07-23 | 2028-07-23 | 10 hrs | FY29 | 18 | 90015695 | B1 | 1000162086 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMF1 | 7200 | 46150 | 15698
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing LHF P2 | 2028-07-23 | 2028-07-23 | 10 hrs | FY29 | 18 | 90015695 | B1 | 1000162087 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMF2 | 7200 | 46150 | 15698
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing RHR P1 | 2028-07-23 | 2028-07-23 | 10 hrs | FY29 | 18 | 90015695 | B1 | 1000162084 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMR1 | 7200 | 46150 | 15698
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Hyd Motor Swing LHR P2 | 2028-07-23 | 2028-07-23 | 10 hrs | FY29 | 18 | 90015695 | B1 | 1000162085 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-HYDSYS-HDMOT-SWMR2 | 7200 | 46150 | 15698
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing LHF | 2028-07-23 | 2028-07-24 | 36 hrs | FY29 | 60 | 90015674 | B1 | 1000162038 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBLF | 7200 | 46150 | 15698
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing LHR | 2028-07-23 | 2028-07-24 | 36 hrs | FY29 | 60 | 90015674 | B4 | 1000162039 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBLR | 7200 | 46150 | 15698
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing RHF | 2028-07-23 | 2028-07-24 | 36 hrs | FY29 | 60 | 90015674 | B2 | 1000162040 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBRF | 7200 | 46150 | 15698
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Repl Gearbox Swing RHR | 2028-07-23 | 2028-07-24 | 36 hrs | FY29 | 60 | 90015674 | B3 | 1000162041 | 23.07.2028 | 15000 | CCK-MP-EXCV-EX8106-SWGSYS-SWBOX-SGBRR | 7200 | 46150 | 15698
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Stick LH | 2028-07-28 | 2028-07-29 | 30 hrs | FY29 | 54 | 90030724 | B1 | 1000250301 | 28.07.2028 | 16000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-STCLL | 7200 | 28725 | 536
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Replace Minestar Harness | 2028-08-01 | 2028-08-02 | 27.5 hrs | FY29 | 43.5 | 90018769 | B2 | 1000281586 | 01.08.2028 | 4000 | CCK-MP-EXCV-EX8107-MANGMT-UMMMC | 7200 | 46126 | 46126
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Valve-Travel Mtrs - Repl | 2028-08-03 | 2028-08-04 | 36 hrs | FY29 | 72 | 90015707 | B1 | 1000162107 | 03.08.2028 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HVVTM | 7200 | 46150 | 1397
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Bucket | 2028-08-07 | 2028-08-09 | 42 hrs | FY29 | 78 | 90030745 | B1 | 1000306993 | 07.08.2028 | 20000 | CCK-MP-EXCV-EX7136-STRUCT-BUCKT | 7200 | 19274 | 5368
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Repl Batteries | 2028-08-18 | 2028-08-18 | 5 hrs | FY29 | 9 | 90017122 | B1 | 1000232126 | 18.08.2028 | 12 Monthly | CCK-MP-EXCV-EX7117-ELCTLV-CHARG-BATST | 7200 | 32281 | 12760
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Wiper Blades | 2028-08-24 | 2028-08-24 | 1 hr | FY29 | 1 | 90027557 | B1 | 1000296994 | 24.08.2028 | 12 Monthly | CCK-MP-EXCV-EX7125-STRUCT-CABIN
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Bucket RH Lift | 2028-08-28 | 2028-08-29 | 30 hrs | FY29 | 54 | 90030726 | B1 | 1000250304 | 28.08.2028 | 10000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BUCYR | 7200 | 28725 | 5217
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Pump Case Drain Hoses | 2028-08-30 | 2028-08-30 | 8 hrs | FY29 | 16 | 90027566 | B1 | 1000297522 | 30.08.2028 | 15000 | CCK-MP-EXCV-EX7123-HYDSYS-HDHLF-HPCDL | 6900 | 15607 | 15607
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Swing LHR | 2028-08-30 | 2028-08-31 | 21 hrs | FY29 | 27 | 90027503 | B1 | 1000297503 | 30.08.2028 | 15000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-SWMLR | 6900 | 15607 | 181
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Swing RHF | 2028-08-30 | 2028-08-31 | 21 hrs | FY29 | 27 | 90027503 | B1 | 1000297504 | 30.08.2028 | 15000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-SWMRF | 6900 | 15607 | 181
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Swing RHR | 2028-08-30 | 2028-08-31 | 21 hrs | FY29 | 27 | 90027503 | B1 | 1000297505 | 30.08.2028 | 15000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-SWMRR | 6900 | 15607 | 181
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Minestar Harness | 2028-08-30 | 2028-08-31 | 27.5 hrs | FY29 | 43.5 | 90031708 | B1 | 1000369997 | 30.08.2028 | 4000 | CCK-MP-EXCV-EX7123-MANGMT-UMMMC | 6900 | 15607 | 15607
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Svc 12M Air Conditioner Sys1 Eng | 2028-08-31 | 2028-08-31 | 12 hrs | FY29 | 12 | 90035236 | B1 | 1000359781 | 31.08.2028 | 12 Monthly | CCK-MP-EXCV-EX7117-STRUCT-CABIN-AIRC1
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 12M Hydraulic Service & Repairs | 2028-09-01 | 2028-09-02 | 18 hrs | FY29 | 30 | 90029940 | B2 | 1000361367 | 01.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7157-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 12M Service Air Con Side Unit | 2028-09-01 | 2028-09-01 | 13 hrs | FY29 | 13 | 90030498 | B2 | 1000361402 | 01.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7157-STRUCT-AIRC1 | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 12M Service Air Con Rear Unit | 2028-09-01 | 2028-09-01 | 13 hrs | FY29 | 13 | 90030536 | B2 | 1000361404 | 01.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7157-STRUCT-AIRC2 | 6000 | 4778 | 4778
R996B | Onsite PM | Excavators | Fortescue | EX8106 | EX8106 Hyd Hose Mono-Block C/Over - Repl | 2028-09-01 | 2028-09-01 | 6 hrs | FY29 | 12 | 90015706 | B1 | 1000162106 | 01.09.2028 | 12000 | CCK-MP-EXCV-EX8106-HYDSYS-HDHLF-HMBCO | 7200 | 46150 | 8894
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Grease System Audit | 2028-09-03 | 2028-09-04 | 24 hrs | FY29 | 36 | 90029934 | B1 | 1000378387 | 03.09.2028 | 5000 | CCK-MP-EXCV-EX7153-GRSYST-GRINJ | 6200 | 2136 | 2136
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Auto Lube Pump P3 | 2028-09-04 | 2028-09-04 | 2 hrs | FY29 | 2 | 90035368 | B1 | 1000358744 | 04.09.2028 | 10000 | CCK-MP-EXCV-EX7136-GRSYST-AUTLU-ALBP3 | 7200 | 19274 | 4847
R9400 | Onsite PM | Excavators | Fortescue | EX7117 | EX7117 Track Tension Tuning - Adjust | 2028-09-06 | 2028-09-06 | 3 hrs | FY29 | 9 | 90020545 | B1 | 1000232125 | 06.09.2028 | 6 Monthly | CCK-MP-EXCV-EX7117-UNDERC | 7200 | 32281 | 32281
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Annual Air Con Service RH | 2028-09-08 | 2028-09-08 | 13 hrs | FY29 | 13 | 90027615 | B1 | 1000297544 | 08.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN-AIRCR | 6900 | 15607 | 15607
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Svc 12M Air Conditioner Sys1 Eng | 2028-09-09 | 2028-09-09 | 12 hrs | FY29 | 12 | 90035241 | B1 | 1000359789 | 09.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7136-STRUCT-CABIN-AIRC1
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Adjust 4500hr Valve Set | 2028-09-09 | 2028-09-09 | 10 hrs | FY29 | 20 | 90027549 | B1 | 1000297432 | 09.09.2028 | 4500 | CCK-MP-EXCV-EX7123-RHENGN | 6900 | 15607 | 7903
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl 24V Batteries | 2028-09-11 | 2028-09-11 | 5 hrs | FY29 | 9 | 90029978 | B2 | 1000361407 | 11.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7157-ELCTLV-CHARG-BATST | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Track Tension Tuning-Adjust | 2028-09-11 | 2028-09-11 | 3 hrs | FY29 | 9 | 90029977 | B2 | 1000361406 | 11.09.2028 | 6 Monthly | CCK-MP-EXCV-EX7157-UNDERC | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Grease Tank Level Valve | 2028-09-11 | 2028-09-11 | 2 hrs | FY29 | 2 | 90029942 | B2 | 1000361369 | 11.09.2028 | 12 Monthly | CCK-MP-EXCV-EX7157-GRSYST
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Batteries | 2028-09-14 | 2028-09-14 | 4 hrs | FY29 | 4 | 90027525 | B1 | 1000296989 | 14.09.2028 | 10000 | CCK-MP-EXCV-EX7125-ELCTLV-CHARG-BATTY | 6900 | 18815 | 5438
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Track Tension Tuning-Adjust | 2028-09-14 | 2028-09-14 | 3 hrs | FY29 | 9 | 90029977 | B1 | 1000378425 | 14.09.2028 | 6 Monthly | CCK-MP-EXCV-EX7153-UNDERC | 6200 | 2136 | 2136
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Roller Load RH Pos8 | 2028-09-19 | 2028-09-19 | 8 hrs | FY29 | 24 | 90030741 | B1 | 1000306980 | 19.09.2028 | 20000 | CCK-MP-EXCV-EX7136-UNDERC-TKFRR-LORH8 | 7200 | 19274 | 19274
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Operators Seat | 2028-09-24 | 2028-09-24 | 2 hrs | FY29 | 2 | 90027613 | B1 | 1000297515 | 24.09.2028 | 10000 | CCK-MP-EXCV-EX7123-STRUCT-CABIN-SEATS | 6900 | 15607 | 5134
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Auto Lube Pump P1 | 2028-09-28 | 2028-09-28 | 2 hrs | FY29 | 2 | 90035369 | B1 | 1000306951 | 28.09.2028 | 10000 | CCK-MP-EXCV-EX7136-GRSYST-AUTLU-ALBPP | 7200 | 19274 | 4382
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Cyl Bucket LH Lift | 2028-09-28 | 2028-09-29 | 30 hrs | FY29 | 54 | 90030725 | B1 | 1000306990 | 28.09.2028 | 10000 | CCK-MP-EXCV-EX7136-HYDSYS-HDCYL-BUCYL | 7200 | 19274 | 4382
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Ovhl 24M Air Conditioner Sys2 Hyd | 2028-10-01 | 2028-10-02 | 36 hrs | FY29 | 36 | 90035446 | B1 | 1000359788 | 01.10.2028 | 24 Monthly | CCK-MP-EXCV-EX7120-STRUCT-CABIN-AIRC2
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Grease System Audit | 2028-10-03 | 2028-10-04 | 24 hrs | FY29 | 36 | 90030748 | B1 | 1000306960 | 03.10.2028 | 5000 | CCK-MP-EXCV-EX7136-GRSYST-GRINJ | 7200 | 19274 | 6872
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Auto Lube Pump P3 | 2028-10-04 | 2028-10-04 | 2 hrs | FY29 | 2 | 90035368 | B1 | 1000358743 | 04.10.2028 | 10000 | CCK-MP-EXCV-EX7120-GRSYST-AUTLU-ALBP3 | 7200 | 28725 | 4421
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Auto Lube Pump P1 | 2028-10-04 | 2028-10-04 | 2 hrs | FY29 | 2 | 90035369 | B1 | 1000250261 | 04.10.2028 | 10000 | CCK-MP-EXCV-EX7120-GRSYST-AUTLU-ALBPP | 7200 | 28725 | 4421
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Minestar Harness | 2028-10-09 | 2028-10-10 | 27.5 hrs | FY29 | 43.5 | 90031708 | B1 | 1000369998 | 09.10.2028 | 4000 | CCK-MP-EXCV-EX7125-MANGMT-UMMMC | 6900 | 18844 | 18844
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Minestar Harness | 2028-10-11 | 2028-10-12 | 27.5 hrs | FY29 | 43.5 | 90029998 | B1 | 1000351965 | 11.10.2028 | 4000 | CCK-MP-EXCV-EX7146-MANGMT-UMMMC | 6200 | 7286 | 7286
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Travel RHR | 2028-10-22 | 2028-10-22 | 8 hrs | FY29 | 14 | 90027506 | B1 | 1000297513 | 22.10.2028 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-TRMRR | 6900 | 15607 | 8493
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Batteries | 2028-10-30 | 2028-10-30 | 4 hrs | FY29 | 4 | 90027525 | B1 | 1000297540 | 30.10.2028 | 10000 | CCK-MP-EXCV-EX7123-ELCTLV-CHARG-BATTY | 6900 | 15607 | 4439
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Grease Tank Level Valve | 2028-11-01 | 2028-11-01 | 2 hrs | FY29 | 2 | 90015003 | B2 | 1000306963 | 01.11.2028 | 12 Monthly | CCK-MP-EXCV-EX7136-GRSYST-AUTLU-GRTNK | 7200 | 19274 | 19274
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Boom LH | 2028-11-01 | 2028-11-02 | 40 hrs | FY29 | 76 | 90029951 | B1 | 1000378413 | 01.11.2028 | 16000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-BMCYL | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Boom RH | 2028-11-01 | 2028-11-02 | 40 hrs | FY29 | 76 | 90029951 | B1 | 1000378414 | 01.11.2028 | 16000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-BMCYR | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Stick LH | 2028-11-01 | 2028-11-02 | 28 hrs | FY29 | 52 | 90029971 | B1 | 1000378415 | 01.11.2028 | 16000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-STCLL | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Cyl Stick RH | 2028-11-01 | 2028-11-02 | 28 hrs | FY29 | 52 | 90029971 | B1 | 1000378416 | 01.11.2028 | 16000 | CCK-MP-EXCV-EX7153-HYDSYS-HDCYL-STCLR | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Hose Boom Cyl | 2028-11-01 | 2028-11-03 | 54 hrs | FY29 | 72 | 90029908 | B1 | 1000378369 | 01.11.2028 | 8000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HBMCL | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Hose Stick Cyl | 2028-11-01 | 2028-11-02 | 36 hrs | FY29 | 48 | 90029909 | B1 | 1000378370 | 01.11.2028 | 8000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HSTCL | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Hyd Hose Bucket Cyl | 2028-11-01 | 2028-11-02 | 18 hrs | FY29 | 54 | 90029911 | B1 | 1000378371 | 01.11.2028 | 8000 | CCK-MP-EXCV-EX7153-HYDSYS-HDHLF-HBKCL | 6200 | 2136 | 2136
R9400E | Onsite PM | Excavators | Fortescue | EX7153 | EX7153 Repl Minestar Harness | 2028-11-01 | 2028-11-02 | 27.5 hrs | FY29 | 43.5 | 90029998 | B1 | 1000378437 | 01.11.2028 | 4000 | CCK-MP-EXCV-EX7153-MANGMT-UMMMC | 6200 | 2136 | 2136
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Track Tension Tuning-Adjust | 2028-11-02 | 2028-11-02 | 3 hrs | FY29 | 9 | 90020545 | B1 | 1000306996 | 02.11.2028 | 6 Monthly | CCK-MP-EXCV-EX7136-UNDERC | 7200 | 19274 | 19274
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 500hr Initial Valve Set | 2028-11-05 | 2028-11-05 | 10 hrs | FY29 | 20 | 90027550 | B1 | 1000288443 | 05.11.2028 | 500 | CCK-MP-EXCV-EX7121-LHENGN | 6900 | 21434 | 2948
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 500hr Initial Valve Set | 2028-11-05 | 2028-11-05 | 10 hrs | FY29 | 20 | 90027550 | B1 | 1000288449 | 05.11.2028 | 500 | CCK-MP-EXCV-EX7121-RHENGN | 6900 | 21434 | 2948
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Stick Cyl | 2028-11-12 | 2028-11-13 | 36 hrs | FY29 | 48 | 90029909 | B1 | 1000352460 | 12.11.2028 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HSTCL | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cylinder Clam LH | 2028-11-12 | 2028-11-12 | 14 hrs | FY29 | 22 | 90035631 | B2 | 1000361398 | 12.11.2028 | 6000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-CLAML | 6000 | 4778 | 4778
R9400E | Onsite PM | Excavators | Fortescue | EX7157 | EX7157 Repl Cylinder Clam RH | 2028-11-12 | 2028-11-12 | 14 hrs | FY29 | 22 | 90035631 | B2 | 1000361399 | 12.11.2028 | 6000 | CCK-MP-EXCV-EX7157-HYDSYS-HDCYL-CLAMR | 6000 | 4778 | 4778
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Adjust 4500hr Valve Set | 2028-11-17 | 2028-11-17 | 10 hrs | FY29 | 20 | 90027549 | B1 | 1000297427 | 17.11.2028 | 4500 | CCK-MP-EXCV-EX7123-LHENGN | 6900 | 15607 | 15607
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Stick Cyl | 2028-11-19 | 2028-11-20 | 36 hrs | FY29 | 48 | 90030737 | B1 | 1000306945 | 19.11.2028 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HSTCL | 7200 | 19274 | 7384
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Track Tension Tuning-Adjust | 2028-11-21 | 2028-11-21 | 3 hrs | FY29 | 9 | 90020545 | B1 | 1000250313 | 21.11.2028 | 6 Monthly | CCK-MP-EXCV-EX7120-UNDERC | 7200 | 28725 | 28725
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Travel LHR | 2028-11-21 | 2028-11-21 | 8 hrs | FY29 | 14 | 90027506 | B1 | 1000297511 | 21.11.2028 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-TRMLR | 6900 | 15607 | 8020
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Adjust 500hr Initial Valve Set | 2028-11-22 | 2028-11-22 | 10 hrs | FY29 | 20 | 90017925 | B1 | 1000206808 | 22.11.2028 | 500 | CCK-MP-EXCV-EX7110-LHENGN | 6900 | 25928 | 1337
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Travel LHF | 2028-11-28 | 2028-11-28 | 8 hrs | FY29 | 14 | 90027506 | B1 | 1000297510 | 28.11.2028 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-TRMLF | 6900 | 15607 | 7903
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Hyd Motor Travel RHF | 2028-11-28 | 2028-11-28 | 8 hrs | FY29 | 14 | 90027506 | B1 | 1000297512 | 28.11.2028 | 12000 | CCK-MP-EXCV-EX7123-HYDSYS-HDMOT-TRMRF | 6900 | 15607 | 600
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Hyd Motor Fan Engine Cool LH | 2028-12-02 | 2028-12-02 | 6 hrs | FY29 | 18 | 90027505 | B1 | 1000296957 | 02.12.2028 | 18000 | CCK-MP-EXCV-EX7125-HYDSYS-HDMOT-FMECL | 6900 | 18844 | 1833
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Boom LH | 2028-12-03 | 2028-12-05 | 42 hrs | FY29 | 78 | 90030723 | B1 | 1000250299 | 03.12.2028 | 16000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BMCYL | 7200 | 28725 | 15249
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Boom Cyl | 2028-12-13 | 2028-12-15 | 54 hrs | FY29 | 72 | 90030735 | B1 | 1000306944 | 13.12.2028 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HBMCL | 7200 | 19274 | 6872
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Hyd Hose Bucket Cyl | 2028-12-14 | 2028-12-15 | 18 hrs | FY29 | 54 | 90030738 | B1 | 1000306946 | 14.12.2028 | 8000 | CCK-MP-EXCV-EX7136-HYDSYS-HDHLF-HBKCL | 7200 | 19274 | 6848
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 12M Hydraulic Service & Repairs | 2028-12-20 | 2028-12-21 | 18 hrs | FY29 | 30 | 90014448 | B2 | 1000306961 | 20.12.2028 | 12 Monthly | CCK-MP-EXCV-EX7136-HYDSYS | 7200 | 19274 | 19274
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Minestar Harness | 2028-12-26 | 2028-12-27 | 27.5 hrs | FY29 | 43.5 | 90030746 | B1 | 1000281594 | 26.12.2028 | 5000 | CCK-MP-EXCV-EX7120-MANGMT-UMMMC | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Power Pack Module Qtr Life | 2028-12-30 | 2028-12-30 | 1 hr | FY29 | 1 | 90027378 | B1 | 1000279052 | 30.12.2028 | 5000 | CCK-MP-EXCV-EX7120-ENGINE | 7200 | 28725 | 8287
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Adjust 4500hr Valve Set | 2028-12-31 | 2028-12-31 | 10 hrs | FY29 | 20 | 90017923 | B1 | 1000206823 | 31.12.2028 | 4500 | CCK-MP-EXCV-EX7110-RHENGN | 6900 | 25928 | 6025
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Auto Lube Pump P1 | 2028-12-31 | 2028-12-31 | 2 hrs | FY29 | 2 | 90030312 | B1 | 1000352468 | 31.12.2028 | 10000 | CCK-MP-EXCV-EX7147-GRSYST-AUTLU-ALBPP | 6200 | 7547 | 7547
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Cyl Boom RH | 2029-01-06 | 2029-01-08 | 42 hrs | FY29 | 78 | 90030723 | B1 | 1000250300 | 06.01.2029 | 16000 | CCK-MP-EXCV-EX7120-HYDSYS-HDCYL-BMCYR | 7200 | 28725 | 14582
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Minestar Harness | 2029-01-29 | 2029-01-30 | 27.5 hrs | FY29 | 43.5 | 90030746 | B1 | 1000307013 | 29.01.2029 | 5000 | CCK-MP-EXCV-EX7136-MANGMT-UMMMC | 7200 | 19274 | 6848
R9400 | Onsite PM | Excavators | Fortescue | EX7136 | EX7136 Repl Batteries | 2029-02-07 | 2029-02-07 | 5 hrs | FY29 | 9 | 90017122 | B1 | 1000306997 | 07.02.2029 | 12 Monthly | CCK-MP-EXCV-EX7136-ELCTLV-CHARG-BATST | 7200 | 19274 | 19274
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Wiper Blades | 2029-02-13 | 2029-02-13 | 1 hr | FY29 | 1 | 90027557 | B1 | 1000297545 | 13.02.2029 | 12 Monthly | CCK-MP-EXCV-EX7123-STRUCT-CABIN
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 500hr Initial Valve Set | 2029-02-19 | 2029-02-19 | 10 hrs | FY29 | 20 | 90027550 | B1 | 1000296915 | 19.02.2029 | 500 | CCK-MP-EXCV-EX7125-LHENGN | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Adjust 500hr Initial Valve Set | 2029-02-19 | 2029-02-19 | 10 hrs | FY29 | 20 | 90027550 | B1 | 1000296920 | 19.02.2029 | 500 | CCK-MP-EXCV-EX7125-RHENGN | 6900 | 18844 | 18844
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Repl Wiper Blades | 2029-03-08 | 2029-03-08 | 1 hr | FY29 | 1 | 90027557 | B1 | 1000288564 | 08.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7121-STRUCT-CABIN
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Hyd Hose Bucket Cyl | 2029-03-21 | 2029-03-22 | 18 hrs | FY29 | 54 | 90029911 | B1 | 1000349800 | 21.03.2029 | 8000 | CCK-MP-EXCV-EX7144-HYDSYS-HDHLF-HBKCL | 6200 | 8005 | 8005
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Boom Cyl | 2029-03-24 | 2029-03-26 | 54 hrs | FY29 | 72 | 90029908 | B1 | 1000352459 | 24.03.2029 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HBMCL | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Hyd Hose Bucket Cyl | 2029-03-24 | 2029-03-25 | 18 hrs | FY29 | 54 | 90029911 | B1 | 1000352461 | 24.03.2029 | 8000 | CCK-MP-EXCV-EX7147-HYDSYS-HDHLF-HBKCL | 6200 | 7547 | 7547
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl 24V Batteries | 2029-03-29 | 2029-03-29 | 5 hrs | FY29 | 9 | 90029978 | B1 | 1000349855 | 29.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7144-ELCTLV-CHARG-BATST | 6200 | 8005 | 8005
6040 | Onsite PM | Excavators | Fortescue | EX7123 | EX7123 Repl Minestar Harness | 2029-03-29 | 2029-03-30 | 27.5 hrs | FY29 | 43.5 | 90031708 | B1 | 1000369997 | 29.03.2029 | 4000 | CCK-MP-EXCV-EX7123-MANGMT-UMMMC | 6900 | 15607 | 15607
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 12M Hydraulic Service & Repairs | 2029-03-30 | 2029-03-31 | 18 hrs | FY29 | 30 | 90029940 | B1 | 1000349817 | 30.03.2029 | 12 Monthly | CCK-MP-EXCV-EX7144-HYDSYS
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Grease Block & Injectors | 2029-04-01 | 2029-04-03 | 48 hrs | FY29 | 84 | 90030749 | B1 | 1000250271 | 01.04.2029 | 20000 | CCK-MP-EXCV-EX7120-GRSYST-GRINJ | 7200 | 28725 | 8287
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Operators Seat | 2029-04-01 | 2029-04-01 | 9 hrs | FY29 | 17 | 90030739 | B1 | 1000250257 | 01.04.2029 | 10000 | CCK-MP-EXCV-EX7120-STRUCT-CABIN-SEATO | 7200 | 28725 | 2083
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Wiper Blades | 2029-04-08 | 2029-04-08 | 2 hrs | FY29 | 2 | 90004684 | B1 | 1000206897 | 08.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7110-STRUCT-CABIN | 6900 | 25928 | 25928
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Repl Grease Tank Level Valve | 2029-04-10 | 2029-04-10 | 2 hrs | FY29 | 2 | 90029942 | B1 | 1000349819 | 10.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7144-GRSYST
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl 24V Batteries | 2029-04-15 | 2029-04-15 | 5 hrs | FY29 | 9 | 90029978 | B1 | 1000350906 | 15.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7145-ELCTLV-CHARG-BATST | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 12M Hydraulic Service & Repairs | 2029-04-15 | 2029-04-16 | 18 hrs | FY29 | 30 | 90029940 | B1 | 1000350868 | 15.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7145-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 24M Ovhl AirCondtioner Sys 1 | 2029-04-15 | 2029-04-16 | 36 hrs | FY29 | 36 | 90030500 | B1 | 1000350902 | 15.04.2029 | 24 Monthly | CCK-MP-EXCV-EX7145-STRUCT-AIRC1 | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 24M Ovhl AirCondtioner Sys 2 | 2029-04-15 | 2029-04-16 | 36 hrs | FY29 | 36 | 90030537 | B1 | 1000350904 | 15.04.2029 | 24 Monthly | CCK-MP-EXCV-EX7145-STRUCT-AIRC2 | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Grease Tank Level Valve | 2029-04-15 | 2029-04-15 | 2 hrs | FY29 | 2 | 90029942 | B1 | 1000350870 | 15.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7145-GRSYST
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Stick Cyl | 2029-04-21 | 2029-04-22 | 36 hrs | FY29 | 48 | 90029909 | B1 | 1000350850 | 21.04.2029 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HSTCL | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Repl Hyd Hose Bucket Cyl | 2029-04-21 | 2029-04-22 | 18 hrs | FY29 | 54 | 90029911 | B1 | 1000350851 | 21.04.2029 | 8000 | CCK-MP-EXCV-EX7145-HYDSYS-HDHLF-HBKCL | 6200 | 7526 | 7526
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Travel RHF | 2029-04-21 | 2029-04-21 | 6 hrs | FY29 | 12 | 90022657 | B1 | 1000206864 | 21.04.2029 | 12000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-TRMRF | 6900 | 25928 | 5424
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Gearbox Swing P1 | 2029-04-23 | 2029-04-25 | 55 hrs | FY29 | 109 | 90030720 | B1 | 1000250210 | 23.04.2029 | 20000 | CCK-MP-EXCV-EX7120-SWGSYS-SWBOX-SGBPF | 7200 | 28725 | 20457
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Boom Cyl | 2029-04-29 | 2029-05-01 | 54 hrs | FY29 | 72 | 90029908 | B1 | 1000351896 | 29.04.2029 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HBMCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Stick Cyl | 2029-04-29 | 2029-04-30 | 36 hrs | FY29 | 48 | 90029909 | B1 | 1000351897 | 29.04.2029 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HSTCL | 6200 | 7286 | 7286
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Hyd Hose Bucket Cyl | 2029-04-29 | 2029-04-30 | 18 hrs | FY29 | 54 | 90029911 | B1 | 1000351898 | 29.04.2029 | 8000 | CCK-MP-EXCV-EX7146-HYDSYS-HDHLF-HBKCL | 6200 | 7286 | 7286
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Batteries | 2029-04-30 | 2029-04-30 | 5 hrs | FY29 | 9 | 90017122 | B1 | 1000250314 | 30.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7120-ELCTLV-CHARG-BATST | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Grease Tank Level Valve | 2029-04-30 | 2029-04-30 | 2 hrs | FY29 | 2 | 90015003 | B2 | 1000250276 | 30.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7120-GRSYST-AUTLU-GRTNK | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 12M Hydraulic Service & Repairs | 2029-04-30 | 2029-05-01 | 18 hrs | FY29 | 30 | 90014448 | B2 | 1000250274 | 30.04.2029 | 12 Monthly | CCK-MP-EXCV-EX7120-HYDSYS | 7200 | 28725 | 28725
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Hose Boom Cyl | 2029-05-05 | 2029-05-07 | 54 hrs | FY29 | 72 | 90030735 | B1 | 1000250249 | 05.05.2029 | 8000 | CCK-MP-EXCV-EX7120-HYDSYS-HDHLF-HBMCL | 7200 | 28725 | 12234
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Batteries | 2029-05-06 | 2029-05-06 | 8 hrs | FY29 | 8 | 90016788 | B1 | 1000206892 | 06.05.2029 | 10000 | CCK-MP-EXCV-EX7110-ELCTLV-CHARG-BATTY | 6900 | 25928 | 11135
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Swing LHR | 2029-05-06 | 2029-05-07 | 21 hrs | FY29 | 27 | 90003175 | B1 | 1000206855 | 06.05.2029 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-SWMLR | 6900 | 25928 | 11135
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Swing RHF | 2029-05-06 | 2029-05-07 | 21 hrs | FY29 | 27 | 90003175 | B1 | 1000206856 | 06.05.2029 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-SWMRF | 6900 | 25928 | 11135
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Repl Hyd Motor Swing RHR | 2029-05-06 | 2029-05-07 | 21 hrs | FY29 | 27 | 90003175 | B1 | 1000206857 | 06.05.2029 | 15000 | CCK-MP-EXCV-EX7110-HYDSYS-HDMOT-SWMRR | 6900 | 25928 | 11135
6040 | Onsite PM | Excavators | Fortescue | EX7125 | EX7125 Repl Minestar Harness | 2029-05-09 | 2029-05-10 | 27.5 hrs | FY29 | 43.5 | 90031708 | B1 | 1000369998 | 09.05.2029 | 4000 | CCK-MP-EXCV-EX7125-MANGMT-UMMMC | 6900 | 18844 | 18844
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Svc 12M Air Conditioner Sys1 Eng | 2029-05-11 | 2029-05-11 | 12 hrs | FY29 | 12 | 90035236 | B1 | 1000359785 | 11.05.2029 | 12 Monthly | CCK-MP-EXCV-EX7120-STRUCT-CABIN-AIRC1
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 12M Hydraulic Service & Repairs | 2029-05-11 | 2029-05-12 | 18 hrs | FY29 | 30 | 90029940 | B1 | 1000351915 | 11.05.2029 | 12 Monthly | CCK-MP-EXCV-EX7146-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Repl Grease Tank Level Valve | 2029-05-11 | 2029-05-11 | 2 hrs | FY29 | 2 | 90029942 | B1 | 1000351917 | 11.05.2029 | 12 Monthly | CCK-MP-EXCV-EX7146-GRSYST
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Track Tension Tuning-Adjust | 2029-05-20 | 2029-05-20 | 3 hrs | FY29 | 9 | 90020545 | B1 | 1000250313 | 20.05.2029 | 6 Monthly | CCK-MP-EXCV-EX7120-UNDERC | 7200 | 28725 | 28725
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Stick LH | 2029-05-25 | 2029-05-26 | 24 hrs | FY29 | 48 | 90015687 | B1 | 1000162220 | 25.05.2029 | 16000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-STCLL | 7200 | 46126 | 11696
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Track Idler LH | 2029-06-01 | 2029-06-01 | 14 hrs | FY29 | 38 | 90015669 | B1 | 1000162275 | 01.06.2029 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRL-IDLLH | 500 | 2526 | 1073
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Track Assembly LH | 2029-06-01 | 2029-06-01 | 12 hrs | FY29 | 36 | 90015666 | B1 | 1000162273 | 01.06.2029 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRL-TRKLH | 500 | 2526 | 1073
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Track Idler RH | 2029-06-01 | 2029-06-01 | 14 hrs | FY29 | 38 | 90015669 | B1 | 1000162288 | 01.06.2029 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRR-IDLRH | 500 | 2526 | 1073
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Track Assembly RH | 2029-06-01 | 2029-06-01 | 12 hrs | FY29 | 36 | 90015666 | B1 | 1000162286 | 01.06.2029 | 1400 | CCK-MP-EXCV-EX8107-UNDERC-TKFRR-TRKRH | 500 | 2526 | 1073
R9400E | Onsite PM | Excavators | Fortescue | EX7145 | EX7145 Grease System Audit | 2029-06-03 | 2029-06-04 | 24 hrs | FY29 | 36 | 90029934 | B1 | 1000350867 | 03.06.2029 | 5000 | CCK-MP-EXCV-EX7145-GRSYST-GRINJ | 6200 | 7526 | 7526
R9400E | Onsite PM | Excavators | Fortescue | EX7144 | EX7144 Grease System Audit | 2029-06-03 | 2029-06-04 | 24 hrs | FY29 | 36 | 90029934 | B1 | 1000349816 | 03.06.2029 | 5000 | CCK-MP-EXCV-EX7144-GRSYST-GRINJ | 6200 | 8005 | 8005
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Cyl Stick RH | 2029-06-04 | 2029-06-05 | 24 hrs | FY29 | 48 | 90015687 | B1 | 1000162221 | 04.06.2029 | 16000 | CCK-MP-EXCV-EX8107-HYDSYS-HDCYL-STCLR | 7200 | 46126 | 11696
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 4500hr Valve Set | 2029-06-05 | 2029-06-05 | 10 hrs | FY29 | 20 | 90027549 | B1 | 1000288444 | 05.06.2029 | 4500 | CCK-MP-EXCV-EX7121-LHENGN | 6900 | 21434 | 2948
6040 | Onsite PM | Excavators | Fortescue | EX7121 | EX7121 Adjust 4500hr Valve Set | 2029-06-05 | 2029-06-05 | 10 hrs | FY29 | 20 | 90027549 | B1 | 1000288450 | 05.06.2029 | 4500 | CCK-MP-EXCV-EX7121-RHENGN | 6900 | 21434 | 2948
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Boom Arch Hoses | 2029-06-11 | 2029-06-14 | 72 hrs | FY29 | 96 | 90026637 | B1 | 1000268046 | 11.06.2029 | 8000 | CCK-MP-EXCV-EX8107-HYDSYS-HDHLF-HBMAR | 7200 | 46126 | 571
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 12M Hydraulic Service & Repairs | 2029-06-13 | 2029-06-14 | 18 hrs | FY29 | 30 | 90029940 | B1 | 1000352478 | 13.06.2029 | 12 Monthly | CCK-MP-EXCV-EX7147-HYDSYS
R9400E | Onsite PM | Excavators | Fortescue | EX7147 | EX7147 Repl Grease Tank Level Valve | 2029-06-13 | 2029-06-13 | 2 hrs | FY29 | 2 | 90029942 | B1 | 1000352480 | 13.06.2029 | 12 Monthly | CCK-MP-EXCV-EX7147-GRSYST
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Air Con System | 2029-06-20 | 2029-06-20 | 5 hrs | FY29 | 5 | 90019238 | B1 | 1000195767 | 20.06.2029 | 12 Monthly | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-ACONF | 7200 | 46126 | 7049
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Hyd Motor Air Con System | 2029-06-20 | 2029-06-20 | 4 hrs | FY29 | 4 | 90019239 | B1 | 1000195768 | 20.06.2029 | 12 Monthly | CCK-MP-EXCV-EX8107-HYDSYS-HDMOT-ACONR | 7200 | 46126 | 7049
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Air Condtioner Compr Front | 2029-06-20 | 2029-06-20 | 5 hrs | FY29 | 5 | 90019236 | B1 | 1000195765 | 20.06.2029 | 12 Monthly | CCK-MP-EXCV-EX8107-STRUCT-CABIN-ACCN1 | 7200 | 46126 | 6810
R996B | Onsite PM | Excavators | Fortescue | EX8107 | EX8107 Repl Air Condtioner Compr Rear | 2029-06-20 | 2029-06-20 | 4 hrs | FY29 | 4 | 90019237 | B1 | 1000195766 | 20.06.2029 | 12 Monthly | CCK-MP-EXCV-EX8107-STRUCT-CABIN-ACCN2 | 7200 | 46126 | 6810
6040 | Onsite PM | Excavators | Fortescue | EX7110 | EX7110 Adjust 4500hr Valve Set | 2029-06-22 | 2029-06-22 | 10 hrs | FY29 | 20 | 90017923 | B1 | 1000206809 | 22.06.2029 | 4500 | CCK-MP-EXCV-EX7110-LHENGN | 6900 | 25928 | 1337
R9400 | Onsite PM | Excavators | Fortescue | EX7120 | EX7120 Repl Hyd Motor Swing Front | 2029-06-24 | 2029-06-24 | 16 hrs | FY29 | 24 | 90030727 | B1 | 1000250229 | 24.06.2029 | 20000 | CCK-MP-EXCV-EX7120-HYDSYS-HDMOT-SWMOF | 7200 | 28725 | 19245
R9400E | Onsite PM | Excavators | Fortescue | EX7146 | EX7146 Grease System Audit | 2029-06-27 | 2029-06-28 | 24 hrs | FY29 | 36 | 90029934 | B1 | 1000351914 | 27.06.2029 | 5000 | CCK-MP-EXCV-EX7146-GRSYST-GRINJ | 6200 | 7286 | 7286
| Onsite PM | Drills | Fortescue |  | DRILLS - COMPONENTS DURING PM
| Onsite PM | Drills | Fortescue |  | FY27 - DRILLS - COMPONENTS DURING PM | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Drills | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Drills | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
PV271 | Onsite PM | Drills | Fortescue | All - Drills | Water Tank Replacements | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Drills | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Air Compressor Conversion | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
PV271 | Onsite PM | Drills | Fortescue | All - Drills | Water Tank Replacements | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Drills | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
PV271 | Onsite PM | Drills | Fortescue | All - Drills | Water Tank Replacements | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
PV271 | Onsite PM | Drills | Fortescue | All - Drills | Flanders AI Hydraulic Lockout Integration Upgrade | 2027-02-01 | 2027-02-28 | 27 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Air Compressor Conversion | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Drills | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
PV271 | Onsite PM | Drills | Fortescue | All - Drills | Water Tank Replacements | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Drills | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Drills | Fortescue | MOC | MAY | 2027-05-01 | 2027-05-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Air Compressor Conversion | 2027-05-01 | 2027-05-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | JUNE | 2027-06-01 | 2027-06-30 | 29 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl ADS LiDAR | 2026-07-26 | 2026-07-26 | 4 hrs | FY27 | 4 | 90029065 | B1 | 1000291549 | 17.05.2026 | 5000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPR-LIDAR | 6800 | 21646 | 6175
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Water & Fuel Tank Mounts | 2026-07-27 | 2026-07-27 | 10 hrs | FY27 | 20 | 90017453 | B1 | 1000160345 | 05.11.2026 | 6000 | CCK-MP-DRLL-DR2111-ENGINE-FUSYS-FULTK | 6800 | 49393 | 11797
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 24M Air Cond Rencool Overhaul | 2026-07-28 | 2026-07-28 | 12 hrs | FY27 | 24 | 90018580 | B1 | 1000180960 | 02.10.2026 | 24 Monthly | CCK-MP-DRLL-DR055 -STRUCT-CABIN-AIRCN | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Control Harnesses Chassis | 2026-07-28 | 2026-07-29 | 39 hrs | FY27 | 39 | 90029952 | B1 | 1000303818 | 16.12.2025 | 20000 | CCK-MP-DRLL-DR055 -ELCTLV-HARNS-HARCO | 6800 | 64593 | 64593
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 PV271 Hydraulic Tune | 2026-07-29 | 2026-07-30 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000345149 | 12.07.2026 | 3000 | CCK-MP-DRLL-DR055 -HYDSYS | 6800 | 64569 | 64569
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Engine Valve Set | 2026-07-31 | 2026-07-31 | 8 hrs | FY27 | 16 | 90021723 | B1 | 1000305070 | 31.07.2026 | 3000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 24M Air Conditioner Overhaul | 2026-08-10 | 2026-08-15 | 132 hrs | FY27 | 180 | 90018566 | B1 | 1000180542 | 02.10.2026 | 24 Monthly | CCK-MP-DRLL-DR055 -STRUCT-CABIN-AIRCN | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 12M Air Conditioner Service | 2026-08-10 | 2026-08-11 | 18 hrs | FY27 | 36 | 90018564 | B1 | 1000180529 | 17.07.2026 | 12 Monthly | CCK-MP-DRLL-DR2111-STRUCT-CABIN-AIRCN
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 12M Air Cond Rencool Service | 2026-08-10 | 2026-08-10 | 8 hrs | FY27 | 16 | 90018579 | B1 | 1000180989 | 17.07.2026 | 12 Monthly | CCK-MP-DRLL-DR2111-STRUCT-CABIN-AIRCN
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 EncoderHarness Cab to Aframe Repl | 2026-08-15 | 2026-08-15 | 6 hrs | FY27 | 6 | 90036144 | B1 | 1000365254 | 15.08.2026 | 5000 | CCK-MP-DRLL-DR2111-ADSYST-HARNC | 6800 | 49417 | 4564
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Drive Shaft Pump Drive | 2026-08-16 | 2026-08-16 | 6 hrs | FY27 | 12 | 90028862 | B1 | 1000287874 | 05.07.2026 | 5000 | CCK-MP-DRLL-DR2113-HYDSYS-PMPDG-DRSHT | 6800 | 33987 | 2582
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Adjust 3750Hr Valve Set | 2026-08-16 | 2026-08-16 | 12 hrs | FY27 | 24 | 90020402 | B1 | 1000214045 | 13.07.2026 | 3750 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Compressor Coupling | 2026-08-16 | 2026-08-16 | 12 hrs | FY27 | 24 | 90030404 | B1 | 1000303533 | 21.06.2026 | 7500 | CCK-MP-DRLL-DR2113-AIRSYS-COMPR-COUPL | 6800 | 34008 | 11590
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Secondary Water Tank Anodes | 2026-08-16 | 2026-08-16 | 8 hrs | FY27 | 8 | 90037834 | B1 | 1000377466 | 05.03.2026 | 10000 | CCK-MP-DRLL-DR2113-DSTSUP-WTNKS | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS Vibration Sensors | 2026-08-17 | 2026-08-17 | 1 hr | FY27 | 1 | 90029062 | B1 | 1000316820 | 29.12.2025 | 10000 | CCK-MP-DRLL-DR2136-ADSYST-ADSIS-DSVSN | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS LiDAR | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 4 | 90029065 | B1 | 1000316824 | 26.02.2025 | 5000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS LiDAR | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 4 | 90029065 | B1 | 1000316824 | 29.12.2025 | 5000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Washdown Pump | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90030681 | B1 | 1000316836 | 30.08.2026 | 7500 | CCK-MP-DRLL-DR2136-DSTSUP-WSHPP | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Primary Water Tank Anodes | 2026-08-17 | 2026-08-17 | 8 hrs | FY27 | 8 | 90037834 | B1 | 1000377553 | 09.02.2026 | 10000 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKP | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Secondary Water Tank | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 12 | 90037832 | B1 | 1000377485 | 09.02.2026 | 40000 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack RHF NDE CS | 2026-08-17 | 2026-08-17 | 12 hrs | FY27 | 24 | 90030670 | B1 | 1000316717 | 29.01.2026 | 6000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRF | 6700 | 13361 | 8546
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Vehicle Loading Crane | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 12 | 90032931 | B1 | 1000331368 | 25.09.2030 | 40000 | CCK-MP-DRLL-DR2136-STRUCT-CRANE | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Mast Module Qtr Life | 2026-08-17 | 2026-08-21 | 93 hrs | FY27 | 201 | 90030335 | B1 | 1000316827 | 29.07.2025 | 10000 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos5 | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000316789 | 11.07.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF05 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Compressor Coupling | 2026-08-17 | 2026-08-17 | 12 hrs | FY27 | 24 | 90030404 | B1 | 1000316754 | 19.04.2026 | 7500 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR-COUPL | 6700 | 13361 | 8815
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast Cables | 2026-08-17 | 2026-08-18 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000316826 | 29.04.2026 | 2500 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 EncoderHarness Cab to Aframe Repl | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 6 | 90036144 | B1 | 1000365252 | 23.06.2026 | 5000 | CCK-MP-DRLL-DR2104-ADSYST-HARNC | 6800 | 77589 | 14943
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Timing Chain Maintenance | 2026-08-17 | 2026-08-17 | 7 hrs | FY27 | 14 | 90022023 | B1 | 1000361317 | 31.07.2026 | 3000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHP | 5400 | 14414 | 7858
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Boom Module Assembly | 2026-08-17 | 2026-08-18 | 24 hrs | FY27 | 48 | 90022011 | B1 | 1000295074 | 03.11.2026 | 18000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BMASY | 5400 | 16590 | 16590
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Overhaul 24M Air Conditioner | 2026-08-17 | 2026-08-17 | 12 hrs | FY27 | 24 | 90028299 | B1 | 1000316808 | 28.05.2026 | 24 Monthly | CCK-MP-DRLL-DR2136-STRUCT-CABIN-AIRCN | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Primary Water Tank | 2026-08-18 | 2026-08-18 | 6 hrs | FY27 | 12 | 90037833 | B1 | 1000377541 | 12.02.2026 | 40000 | CCK-MP-DRLL-DR2129-DSTSUP-WTNKP | 6800 | 18062 | 18062
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 PV271 Hydraulic Tune | 2026-08-18 | 2026-08-19 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000153014 | 06.04.2026 | 3000 | CCK-MP-DRLL-DR2104-HYDSYS | 6800 | 77566 | 10891
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Vehicle Loading Crane | 2026-08-18 | 2026-08-18 | 6 hrs | FY27 | 12 | 90032931 | B1 | 1000331059 | 15.08.2029 | 40000 | CCK-MP-DRLL-DR2129-STRUCT-CRANE | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Adjust 3750Hr Valve Set | 2026-08-18 | 2026-08-18 | 12 hrs | FY27 | 24 | 90020402 | B1 | 1000278372 | 18.08.2026 | 3750 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 Repl Cables & Hoses | 2026-08-18 | 2026-08-20 | 52 hrs | FY27 | 104 | 90029852 | B1 | 1000303746 | 01.08.2026 | 5000 | CCK-MP-DRLL-DR2104-STRUCT-TOWER | 6800 | 77566 | 34508
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Primary Water Tank | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 8 | 90037834 | B1 | 1000377514 | 17.11.2025 | 10000 | CCK-MP-DRLL-DR2112-DSTSUP-WTNKP | 6800 | 34249 | 10037
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Secondary Water Tank | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 12 | 90037832 | B1 | 1000377251 | 17.11.2025 | 40000 | CCK-MP-DRLL-DR2112-DSTSUP-WTNKS | 6800 | 34249 | 10037
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl LiDAR Sensor | 2026-08-24 | 2026-08-25 | 24 hrs | FY27 | 24 | 90023242 | B1 | 1000240813 | 07.05.2026 | 12 Monthly | CCK-MP-DRLL-DR2110-ADSYST-ADSPR-LIDAR | 6800 | 54907 | 14230
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Drive Shaft Pump Drive | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 12 | 90028862 | B1 | 1000287873 | 20.06.2026 | 5000 | CCK-MP-DRLL-DR2112-HYDSYS-PMPDG-DRSHT | 6800 | 34249 | 2406
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Power Pack Quarter Life | 2026-08-24 | 2026-08-26 | 44 hrs | FY27 | 68 | 90029574 | B1 | 1000295329 | 03.07.2026 | 5000 | CCK-MP-DRLL-DR2110-ENGINE | 6800 | 54907 | 5228
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Pump Water Injection | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90016011 | B1 | 1000144924 | 07.08.2026 | 5000 | CCK-MP-DRLL-DR2111-DSTSUP-WTRPP | 6800 | 49393 | 4564
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Fish Eye Camera | 2026-08-24 | 2026-08-24 | 16 hrs | FY27 | 16 | 90029067 | B1 | 1000290889 | 28.07.2026 | 10000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR-HTCAM | 6800 | 34252 | 34252
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Mast Cables | 2026-08-24 | 2026-08-25 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000302720 | 08.08.2026 | 2500 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
PV271 | Onsite PM | Drills | Fortescue | DR2110 | STAT DR2110 Repl Receiver PRV | 2026-08-25 | 2026-08-25 | 1.5 hrs | FY27 | 1.5 | 90016949 | B2 | 1000144780 | 05.06.2026 | 48 Monthly | CCK-MP-DRLL-DR2110-AIRSYS-ARTNK | 6800 | 54955 | 54955
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Yoke Oscillation | 2026-08-25 | 2026-08-25 | 12 hrs | FY27 | 24 | 90016004 | B1 | 1000144836 | 10.06.2026 | 20000 | CCK-MP-DRLL-DR2110-STRUCT-UNDER-YKOSC | 6800 | 54883 | 20610
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Cables & Hoses | 2026-08-25 | 2026-08-27 | 50 hrs | FY27 | 100 | 90029843 | B1 | 1000303753 | 27.06.2026 | 5000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER | 6800 | 54883 | 5228
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Raise NCS | 2026-08-25 | 2026-08-25 | 4 hrs | FY27 | 8 | 90011666 | B1 | 1000233276 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYL | 6800 | 49393 | 8364
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Raise CS | 2026-08-25 | 2026-08-25 | 4 hrs | FY27 | 8 | 90011667 | B1 | 1000233275 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYR | 6800 | 49393 | 8364
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Hyd Motor Screw Jack NCS | 2026-08-25 | 2026-08-25 | 1 hr | FY27 | 1 | 90022221 | B1 | 1000232742 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTL | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Hyd Motor Screw Jack CS | 2026-08-25 | 2026-08-25 | 1 hr | FY27 | 1 | 90022221 | B1 | 1000232741 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTR | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Tower Cylinders | 2026-08-25 | 2026-08-26 | 34 hrs | FY27 | 58 | 90029866 | B1 | 1000303763 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Grbx Powerhead Midlife | 2026-08-25 | 2026-08-25 | 6 hrs | FY27 | 6 | 90029861 | B1 | 1000303762 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-PWRHD | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Rod Support | 2026-08-25 | 2026-08-25 | 8 hrs | FY27 | 20 | 90022208 | B1 | 1000232732 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-RDSPT | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Rod Thread lube Pump | 2026-08-31 | 2026-08-31 | 2 hrs | FY27 | 2 | 90011732 | B1 | 1000102875 | 28.08.2026 | 10000 | CCK-MP-DRLL-DR055 -GRSYST-RTLPP | 6800 | 64569 | 6663
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Engine Valve Set | 2026-09-02 | 2026-09-02 | 8 hrs | FY27 | 16 | 90021723 | B1 | 1000295750 | 02.09.2026 | 3000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Timing Chain Maintenance | 2026-09-02 | 2026-09-02 | 7 hrs | FY27 | 14 | 90022023 | B1 | 1000361310 | 02.09.2026 | 3000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHP | 5400 | 14232 | 14232
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 PV271 Hydraulic Tune | 2026-09-07 | 2026-09-08 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000153015 | 22.03.2026 | 3000 | CCK-MP-DRLL-DR2110-HYDSYS | 6800 | 54883 | 22468
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 Power Pack Quarter Life | 2026-09-07 | 2026-09-09 | 44 hrs | FY27 | 68 | 90029578 | B1 | 1000295325 | 06.07.2026 | 5000 | CCK-MP-DRLL-DR2104-ENGINE | 6800 | 77589 | 3577
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 Repl Auto Lube Pump | 2026-09-07 | 2026-09-07 | 2 hrs | FY27 | 2 | 90011731 | B1 | 1000098349 | 25.07.2026 | 12000 | CCK-MP-DRLL-DR2104-GRSYST-ALBPP | 6800 | 77566 | 11637
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 Repl Cyl Jack Leg NDE NCS | 2026-09-07 | 2026-09-07 | 11 hrs | FY27 | 15 | 90011671 | B1 | 1000098300 | 22.08.2026 | 15000 | CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-JCYLF | 6800 | 77566 | 14087
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 Repl Cyl Jack Leg DE NCS | 2026-09-07 | 2026-09-07 | 11 hrs | FY27 | 15 | 90011673 | B1 | 1000098302 | 22.08.2026 | 15000 | CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-JCYLR | 6800 | 77566 | 14087
PV271 | Onsite PM | Drills | Fortescue | DR2104 | DR2104 PV271 Hydraulic Tune | 2026-09-07 | 2026-09-08 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000153014 | 01.09.2026 | 3000 | CCK-MP-DRLL-DR2104-HYDSYS | 6800 | 77566 | 10891
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Water & Fuel Tank Mounts | 2026-09-07 | 2026-09-07 | 10 hrs | FY27 | 20 | 90017453 | B1 | 1000160344 | 15.08.2026 | 6000 | CCK-MP-DRLL-DR2110-ENGINE-FUSYS-FULTK | 6800 | 54883 | 5228
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 PV271 Hydraulic Tune | 2026-09-07 | 2026-09-08 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000153015 | 17.08.2026 | 3000 | CCK-MP-DRLL-DR2110-HYDSYS | 6800 | 54883 | 22468
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 EncoderHarness Cab to Aframe Repl | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 6 | 90036144 | B1 | 1000365253 | 17.08.2026 | 5000 | CCK-MP-DRLL-DR2110-ADSYST-HARNC | 6800 | 54907 | 14230
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Mast Cables | 2026-09-16 | 2026-09-17 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000302727 | 16.09.2026 | 2500 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Pump Water Inj | 2026-09-17 | 2026-09-17 | 2 hrs | FY27 | 4 | 90031899 | B1 | 1000315426 | 17.09.2026 | 7500 | CCK-MP-DRLL-DR2128-DSTSUP-WTRPP | 6800 | 21646 | 6363
PV271 | Onsite PM | Drills | Fortescue | DR2111 | STAT DR2111 Repl Receiver PRV | 2026-09-18 | 2026-09-18 | 1.5 hrs | FY27 | 1.5 | 90016949 | B2 | 1000144865 | 18.09.2026 | 48 Monthly | CCK-MP-DRLL-DR2111-AIRSYS-ARTNK | 6800 | 49465 | 49465
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl LiDAR Sensor | 2026-09-19 | 2026-09-20 | 24 hrs | FY27 | 24 | 90023242 | B1 | 1000240814 | 19.09.2026 | 12 Monthly | CCK-MP-DRLL-DR2111-ADSYST-ADSPR-LIDAR | 6800 | 49417 | 6939
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2026-09-20 | 2026-09-20 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000295716 | 20.09.2026 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Mast Beam Module | 2026-09-21 | 2026-09-23 | 48 hrs | FY27 | 96 | 90020447 | B1 | 1000361302 | 01.11.2026 | 18000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-DMAST | 5400 | 16590 | 16590
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier NCS NDE | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020189 | B1 | 1000213655 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLF | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier NCS Middle | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020189 | B1 | 1000213656 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLM | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier NCS DE | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020189 | B1 | 1000213657 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLR | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos1 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213629 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF01 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos2 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213630 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF02 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos3 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213631 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF03 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos4 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213632 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF04 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos5 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213633 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF05 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos6 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213634 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF06 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos7 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213635 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF07 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos9 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213637 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF09 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos10 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213638 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF10 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos11 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213639 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF11 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos12 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213640 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF12 | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load NCS Pos13 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213641 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF13 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier CS NDE | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020189 | B1 | 1000213658 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRF | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier CS Middle | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020189 | B1 | 1000213661 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRM | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Carrier CS DE | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020189 | B1 | 1000213662 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRR | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos1 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213642 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF01 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos2 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213643 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF02 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos3 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213644 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF03 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos4 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213645 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF04 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos5 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213646 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF05 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos6 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213647 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF06 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos7 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213648 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF07 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos8 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213649 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF08 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos9 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213650 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF09 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos10 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213651 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF10 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos11 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213652 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF11 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos12 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213653 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF12 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Roller Load CS Pos13 | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90020188 | B1 | 1000213654 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF13 | 6800 | 34249 | 22131
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Final Drive & Sprocket RH | 2026-09-21 | 2026-09-21 | 14 hrs | FY27 | 26 | 90020182 | B1 | 1000213622 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-TRAVEL-FDRRH | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Track Assembly NCS | 2026-09-21 | 2026-09-21 | 12 hrs | FY27 | 24 | 90020187 | B1 | 1000213627 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-TRAVEL-TRKLH | 6800 | 34249 | 22114
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Track Assembly CS | 2026-09-21 | 2026-09-21 | 12 hrs | FY27 | 24 | 90020187 | B1 | 1000213628 | 10.03.2026 | 20000 | CCK-MP-DRLL-DR2112-TRAVEL-TRKRH | 6800 | 34249 | 22118
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Cab Harnesses | 2026-09-21 | 2026-09-21 | 14 hrs | FY27 | 14 | 90028947 | B1 | 1000289023 | 01.06.2026 | 15000 | CCK-MP-DRLL-DR2112-ELCTLV-HARNS | 6800 | 34252 | 34228
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 PV271 Hydraulic Tune | 2026-09-23 | 2026-09-24 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000153016 | 23.09.2026 | 3000 | CCK-MP-DRLL-DR2111-HYDSYS | 6800 | 49393 | 8364
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Power Pack Quarter Life | 2026-09-26 | 2026-09-28 | 44 hrs | FY27 | 68 | 90029574 | B1 | 1000295333 | 19.09.2026 | 5000 | CCK-MP-DRLL-DR2111-ENGINE | 6800 | 49411 | 11797
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Primary Water Tank | 2026-09-28 | 2026-09-28 | 6 hrs | FY27 | 12 | 90037833 | B1 | 1000377519 | 19.06.2025 | 40000 | CCK-MP-DRLL-DR2128-DSTSUP-WTNKP | 6800 | 21646 | 21646
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Secondary Water Tank | 2026-09-28 | 2026-09-28 | 6 hrs | FY27 | 12 | 90037832 | B1 | 1000377469 | 19.06.2025 | 40000 | CCK-MP-DRLL-DR2128-DSTSUP-WTNKS | 6800 | 21646 | 21646
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Sheaves & Cables | 2026-09-28 | 2026-10-01 | 70 hrs | FY27 | 140 | 90029857 | B1 | 1000303761 | 16.08.2026 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Valve Dual Counter Balance | 2026-10-04 | 2026-10-04 | 2 hrs | FY27 | 2 | 90015975 | B1 | 1000144888 | 04.10.2026 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDCB | 6800 | 49393 | 16543
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl ADS PTZ Camera & LIDAR | 2026-10-04 | 2026-10-04 | 10 hrs | FY27 | 10 | 90029206 | B1 | 1000294211 | 04.10.2026 | 10000 | CCK-MP-DRLL-DR2111-ADSYST-ADSPR-HTCAM | 6800 | 49417 | 19408
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 EncoderHarness Cab to Aframe Repl | 2026-10-05 | 2026-10-05 | 6 hrs | FY27 | 6 | 90036144 | B1 | 1000365255 | 24.10.2026 | 5000 | CCK-MP-DRLL-DR055 -ADSYST-HARNC | 6800 | 64593 | 35395
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack LHF NDE NCS | 2026-10-12 | 2026-10-12 | 12 hrs | FY27 | 24 | 90020196 | B1 | 1000316715 | 16.08.2026 | 6000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLF | 6700 | 13361 | 5509
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Drive Gearbox | 2026-10-12 | 2026-10-13 | 30 hrs | FY27 | 78 | 90020181 | B1 | 1000316759 | 22.08.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-PMPDG | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS LiDAR | 2026-10-12 | 2026-10-12 | 4 hrs | FY27 | 4 | 90029065 | B1 | 1000316824 | 25.10.2026 | 5000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack LHF NDE NCS | 2026-10-12 | 2026-10-12 | 12 hrs | FY27 | 24 | 90020196 | B1 | 1000214056 | 12.10.2026 | 6000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLF | 6800 | 33987 | 1040
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Auto Lube Pump | 2026-10-12 | 2026-10-12 | 2 hrs | FY27 | 2 | 90016009 | B1 | 1000144838 | 19.09.2026 | 12000 | CCK-MP-DRLL-DR2110-GRSYST-ALBPP | 6800 | 54883 | 2172
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 12M Air Cond Rencool Service | 2026-10-12 | 2026-10-12 | 16 hrs | FY27 | 16 | 90018579 | B1 | 1000180987 | 30.09.2026 | 12 Monthly | CCK-MP-DRLL-DR2110-STRUCT-CABIN-AIRCN
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 12M Air Conditioner Service | 2026-10-12 | 2026-10-13 | 36 hrs | FY27 | 36 | 90018564 | B1 | 1000180528 | 30.09.2026 | 12 Monthly | CCK-MP-DRLL-DR2110-STRUCT-CABIN-AIRCN
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl ADS GPS Components | 2026-10-12 | 2026-10-12 | 3.5 hrs | FY27 | 3.5 | 90029191 | B1 | 1000294209 | 22.01.2025 | 40000 | CCK-MP-DRLL-DR2111-ADSYST-ADSPO | 6800 | 49417 | 45632
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Cabin ADS Components | 2026-10-12 | 2026-10-13 | 31.5 hrs | FY27 | 31.5 | 90029189 | B1 | 1000294208 | 22.01.2025 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSHW-HMIJK | 6800 | 49417 | 45632
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl ADS IO Modules | 2026-10-12 | 2026-10-12 | 4 hrs | FY27 | 4 | 90029208 | B1 | 1000294206 | 22.01.2025 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSHW-ARDIO | 6800 | 49417 | 45632
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Deck ADS Elec Hardware | 2026-10-12 | 2026-10-12 | 9.5 hrs | FY27 | 9.5 | 90029190 | B1 | 1000294205 | 22.01.2025 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSHW-ADSMF | 6800 | 49417 | 45632
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl ADS 3D sensor | 2026-10-12 | 2026-10-12 | 1 hr | FY27 | 1 | 90029207 | B1 | 1000294210 | 22.01.2025 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-ADSPR | 6800 | 49417 | 45632
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cab Harnesses | 2026-10-25 | 2026-10-25 | 14 hrs | FY27 | 14 | 90028947 | B1 | 1000316811 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Chassis Harnesses | 2026-10-25 | 2026-10-29 | 104 hrs | FY27 | 208 | 90028944 | B1 | 1000316810 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Battery Cables | 2026-10-25 | 2026-10-26 | 24 hrs | FY27 | 24 | 90028942 | B1 | 1000316809 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Compressor Harnesses | 2026-10-25 | 2026-10-25 | 12 hrs | FY27 | 12 | 90028948 | B1 | 1000316812 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack LHR DE NCS | 2026-10-25 | 2026-10-25 | 12 hrs | FY27 | 24 | 90020204 | B1 | 1000316716 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack RHR DE CS | 2026-10-25 | 2026-10-25 | 12 hrs | FY27 | 24 | 90030672 | B1 | 1000316718 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cyl Mast Locking NCS | 2026-10-25 | 2026-10-25 | 12 hrs | FY27 | 24 | 90020197 | B1 | 1000316740 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYL | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cyl Mast Locking CS | 2026-10-25 | 2026-10-25 | 12 hrs | FY27 | 24 | 90030657 | B1 | 1000316719 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cyl Mast Raise CS | 2026-10-25 | 2026-10-25 | 16 hrs | FY27 | 32 | 90020198 | B1 | 1000316741 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MRCYR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Pump Fan Oil Cooler LH | 2026-10-25 | 2026-10-25 | 2 hrs | FY27 | 2 | 90020239 | B1 | 1000316761 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP1 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Pump Fan Engine Cool RH | 2026-10-25 | 2026-10-25 | 2 hrs | FY27 | 2 | 90020240 | B1 | 1000316762 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP2 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Main Hyd NCS | 2026-10-25 | 2026-10-25 | 6 hrs | FY27 | 6 | 90020235 | B1 | 1000316763 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP1 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Main Hyd CS | 2026-10-25 | 2026-10-25 | 6 hrs | FY27 | 6 | 90020234 | B1 | 1000316764 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP2 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Charge | 2026-10-25 | 2026-10-25 | 2 hrs | FY27 | 2 | 90020232 | B1 | 1000316758 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP3 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Pump Auxiliary | 2026-10-25 | 2026-10-25 | 4 hrs | FY27 | 4 | 90020236 | B1 | 1000316757 | 25.10.2026 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-PPAUX | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast Cables | 2026-10-25 | 2026-10-26 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000316826 | 25.10.2026 | 2500 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Main Air Compressor LP | 2026-10-26 | 2026-10-27 | 25 hrs | FY27 | 50 | 90020192 | B1 | 1000213906 | 24.01.2027 | 15000 | CCK-MP-DRLL-DR2112-AIRSYS-COMPR | 6800 | 34252 | 10999
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2026-10-27 | 2026-10-27 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000304876 | 27.10.2026 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Timing Chain Maintenance | 2026-11-02 | 2026-11-02 | 7 hrs | FY27 | 14 | 90022023 | B1 | 1000361303 | 20.04.2026 | 3000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHP | 5400 | 16590 | 567
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Service Airconditioning System | 2026-11-07 | 2026-11-07 | 12 hrs | FY27 | 12 | 90023281 | B1 | 1000295747 | 07.11.2026 | 12 Monthly | CCK-MP-DRLL-DR3137-STRUCT-CABIN-ACCOM | 5400 | 14232 | 8625
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Mast & A-Frame Harnesses | 2026-11-09 | 2026-11-12 | 70.5 hrs | FY27 | 70.5 | 90030429 | B1 | 1000303721 | 08.02.2026 | 20000 | CCK-MP-DRLL-DR055 -ELCTLV-HARNS-HARCO | 6800 | 64593 | 64593
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Power Pack Midlife | 2026-11-09 | 2026-11-14 | 125 hrs | FY27 | 197 | 90029572 | B1 | 1000295336 | 13.11.2026 | 10000 | CCK-MP-DRLL-DR055 -ENGINE | 6800 | 64593 | 10155
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Boom Module Assembly | 2026-11-09 | 2026-11-10 | 24 hrs | FY27 | 48 | 90022011 | B1 | 1000295034 | 22.11.2026 | 18000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BMASY | 5400 | 16251 | 16251
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Mast Beam Module | 2026-11-09 | 2026-11-11 | 48 hrs | FY27 | 96 | 90020447 | B1 | 1000361227 | 29.11.2026 | 18000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-DMAST | 5400 | 16251 | 16251
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS IO Modules | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 4 | 90029208 | B1 | 1000294215 | 20.11.2025 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-ARDIO | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS Ace Cabinet Components | 2026-11-09 | 2026-11-11 | 44.5 hrs | FY27 | 44.5 | 90029187 | B1 | 1000294216 | 20.11.2025 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-CLXEN | 6800 | 64593 | 35395
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump | 2026-11-27 | 2026-11-27 | 2 hrs | FY27 | 2 | 90020875 | B1 | 1000295715 | 27.11.2026 | 8000 | CCK-MP-DRLL-DR3137-GRSYST-ALBPP | 5400 | 14232 | 14232
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Battery Cables | 2026-12-07 | 2026-12-08 | 24 hrs | FY27 | 24 | 90028942 | B1 | 1000316809 | 11.08.2025 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Adjust 3750Hr Valve Set | 2026-12-11 | 2026-12-11 | 12 hrs | FY27 | 24 | 90020402 | B1 | 1000316745 | 11.12.2026 | 3750 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Engine Midlife Complete | 2026-12-11 | 2026-12-12 | 36 hrs | FY27 | 54 | 90029233 | B1 | 1000316746 | 11.12.2026 | 7500 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Pump Main Hyd CS | 2026-12-12 | 2026-12-12 | 6 hrs | FY27 | 6 | 90020234 | B1 | 1000214071 | 13.12.2026 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-MNPP2 | 6800 | 33987 | 12311
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Hyd Pump Auxiliary | 2026-12-13 | 2026-12-13 | 4 hrs | FY27 | 4 | 90020236 | B1 | 1000214072 | 13.12.2026 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-PPAUX | 6800 | 33987 | 12311
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 PV271 Hydraulic Tune | 2026-12-16 | 2026-12-17 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000345149 | 16.12.2026 | 3000 | CCK-MP-DRLL-DR055 -HYDSYS | 6800 | 64569 | 64569
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack RHF NDE CS | 2026-12-19 | 2026-12-19 | 12 hrs | FY27 | 24 | 90030670 | B1 | 1000214058 | 19.12.2026 | 6000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYRF | 6800 | 33987 | 306
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 XLF Repl Main Feed Chain | 2026-12-21 | 2026-12-21 | 8 hrs | FY27 | 16 | 90021711 | B1 | 1000295025 | 21.12.2026 | 2500 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHH | 5400 | 16251 | 1197
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Washdown Pump | 2027-01-01 | 2027-01-01 | 4 hrs | FY27 | 8 | 90030681 | B1 | 1000305733 | 01.01.2027 | 7500 | CCK-MP-DRLL-DR2128-DSTSUP-WSHPP | 6800 | 21646 | 3234
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Mast Cables | 2027-01-11 | 2027-01-12 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000302800 | 11.01.2027 | 2500 | CCK-MP-DRLL-DR2128-STRUCT-DMAST | 6800 | 21646 | 1486
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Washdown Pump | 2027-01-18 | 2027-01-18 | 4 hrs | FY27 | 8 | 90030681 | B1 | 1000305724 | 18.01.2027 | 7500 | CCK-MP-DRLL-DR2113-DSTSUP-WSHPP | 6800 | 33987 | 9462
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Mast Cables | 2027-01-24 | 2027-01-25 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000302727 | 24.01.2027 | 2500 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Adjust 3750Hr Valve Set | 2027-01-25 | 2027-01-25 | 12 hrs | FY27 | 24 | 90020402 | B1 | 1000214045 | 25.01.2027 | 3750 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Engine Midlife Complete | 2027-01-25 | 2027-01-26 | 36 hrs | FY27 | 54 | 90029233 | B1 | 1000293339 | 25.01.2027 | 7500 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Compressor Coupling | 2027-01-25 | 2027-01-25 | 12 hrs | FY27 | 24 | 90030404 | B1 | 1000303538 | 25.01.2027 | 7500 | CCK-MP-DRLL-DR2128-AIRSYS-COMPR-COUPL | 6800 | 21646 | 3367
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Overhaul 24M Air Conditioner | 2027-02-01 | 2027-02-01 | 12 hrs | FY27 | 24 | 90028299 | B1 | 1000283240 | 01.02.2027 | 24 Monthly | CCK-MP-DRLL-DR2128-STRUCT-CABIN-AIRCN | 6800 | 21646 | 21646
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Overhaul 24M Air Conditioner | 2027-02-01 | 2027-02-01 | 12 hrs | FY27 | 24 | 90028299 | B1 | 1000283242 | 01.02.2027 | 24 Monthly | CCK-MP-DRLL-DR2129-STRUCT-CABIN-AIRCN | 6800 | 18062 | 18062
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2027-02-03 | 2027-02-03 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000295060 | 03.02.2027 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl ADS LiDAR | 2027-02-06 | 2027-02-06 | 4 hrs | FY27 | 4 | 90029065 | B1 | 1000290902 | 06.02.2027 | 5000 | CCK-MP-DRLL-DR2113-ADSYST-ADSPR-LIDAR | 6800 | 34008 | 10800
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Pump Main Hyd CS | 2027-02-07 | 2027-02-07 | 6 hrs | FY27 | 6 | 90020234 | B1 | 1000278211 | 07.02.2027 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-MNPP2 | 6800 | 21646 | 79
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack RHF NDE CS | 2027-02-09 | 2027-02-09 | 12 hrs | FY27 | 24 | 90030670 | B1 | 1000316717 | 09.02.2027 | 6000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRF | 6700 | 13361 | 8546
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump | 2027-02-09 | 2027-02-09 | 2 hrs | FY27 | 2 | 90020875 | B1 | 1000304875 | 16.08.2026 | 8000 | CCK-MP-DRLL-DR3138-GRSYST-ALBPP | 5400 | 14414 | 14414
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Jack Leg DE NCS | 2027-02-11 | 2027-02-11 | 11 hrs | FY27 | 15 | 90011673 | B1 | 1000102827 | 11.02.2027 | 15000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYLR | 6800 | 64569 | 11474
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Drive Shaft Pump Drive | 2027-02-13 | 2027-02-13 | 6 hrs | FY27 | 12 | 90028862 | B1 | 1000287879 | 13.02.2027 | 5000 | CCK-MP-DRLL-DR2128-HYDSYS-PMPDG-DRSHT | 6800 | 21646 | 1486
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 PV271 Hydraulic Tune | 2027-02-18 | 2027-02-19 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000153016 | 18.02.2027 | 3000 | CCK-MP-DRLL-DR2111-HYDSYS | 6800 | 49393 | 8364
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Mast Cables | 2027-02-24 | 2027-02-25 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000302804 | 24.02.2027 | 2500 | CCK-MP-DRLL-DR2129-STRUCT-DMAST | 6800 | 18062 | 4985
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2027-02-26 | 2027-02-26 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000304876 | 26.02.2027 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack LHF NDE NCS | 2027-02-28 | 2027-02-28 | 12 hrs | FY27 | 24 | 90020196 | B1 | 1000278357 | 28.02.2027 | 6000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYLF | 6800 | 18062 | 1556
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Adjust 3750Hr Valve Set | 2027-03-01 | 2027-03-01 | 12 hrs | FY27 | 24 | 90020402 | B1 | 1000278372 | 01.03.2027 | 3750 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Engine Midlife Complete | 2027-03-01 | 2027-03-02 | 36 hrs | FY27 | 54 | 90029233 | B1 | 1000293345 | 01.03.2027 | 7500 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Compressor Coupling | 2027-03-09 | 2027-03-09 | 12 hrs | FY27 | 24 | 90030404 | B1 | 1000303533 | 09.03.2027 | 7500 | CCK-MP-DRLL-DR2113-AIRSYS-COMPR-COUPL | 6800 | 34008 | 11590
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Washdown Pump | 2027-03-11 | 2027-03-11 | 4 hrs | FY27 | 8 | 90030681 | B1 | 1000305734 | 11.03.2027 | 7500 | CCK-MP-DRLL-DR2129-DSTSUP-WSHPP | 6800 | 18062 | 3449
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Adjust 3750Hr Valve Set | 2027-03-17 | 2027-03-17 | 12 hrs | FY27 | 24 | 90020402 | B1 | 1000278184 | 17.03.2027 | 3750 | CCK-MP-DRLL-DR2128-ENGINE | 6800 | 21646 | 3367
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2027-03-18 | 2027-03-18 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000295020 | 18.03.2027 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast Cables | 2027-03-21 | 2027-03-22 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000316826 | 21.03.2027 | 2500 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Pump Drive Gearbox | 2027-03-23 | 2027-03-24 | 30 hrs | FY27 | 78 | 90020181 | B1 | 1000213976 | 23.03.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-PMPDG | 6800 | 33987 | 2582
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Overhaul 24M Air Conditioner | 2027-03-27 | 2027-03-27 | 12 hrs | FY27 | 24 | 90028299 | B1 | 1000283158 | 27.03.2027 | 24 Monthly | CCK-MP-DRLL-DR2113-STRUCT-CABIN-AIRCN | 6800 | 33987 | 20657
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Compressor Coupling | 2027-03-31 | 2027-03-31 | 12 hrs | FY27 | 24 | 90030404 | B1 | 1000303539 | 31.03.2027 | 7500 | CCK-MP-DRLL-DR2129-AIRSYS-COMPR-COUPL | 6800 | 18062 | 13204
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack LHR DE NCS | 2027-04-02 | 2027-04-02 | 12 hrs | FY27 | 24 | 90020204 | B1 | 1000214057 | 02.04.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLR | 6800 | 33987 | 22917
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Battery Cables | 2027-04-03 | 2027-04-04 | 24 hrs | FY27 | 24 | 90028942 | B1 | 1000289036 | 03.04.2027 | 15000 | CCK-MP-DRLL-DR2129-ELCTLV-HARNS | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | STAT DR2128 Repl Receiver PRV | 2027-04-04 | 2027-04-04 | 1 hr | FY27 | 1 | 90026270 | B1 | 1000278212 | 04.04.2027 | 48 Monthly | CCK-MP-DRLL-DR2128-AIRSYS-ARTNK | 6800 | 21693 | 21693
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Engine Valve Set | 2027-04-15 | 2027-04-15 | 8 hrs | FY27 | 16 | 90021723 | B1 | 1000295094 | 15.04.2027 | 3000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Pump Water Inj | 2027-04-24 | 2027-04-24 | 2 hrs | FY27 | 4 | 90031899 | B1 | 1000315425 | 24.04.2027 | 7500 | CCK-MP-DRLL-DR2113-DSTSUP-WTRPP | 6800 | 33987 | 306
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Initial 250Hr Valve Set | 2027-04-28 | 2027-04-28 | 12 hrs | FY27 | 24 | 90016058 | B1 | 1000295327 | 28.03.2027 | 250 | CCK-MP-DRLL-DR2110-ENGINE | 6800 | 54907 | 5228
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack RHF NDE CS | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 24 | 90030670 | B1 | 1000278170 | 05.05.2027 | 6000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYRF | 6800 | 21646 | 1486
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack RHR DE CS | 2027-05-08 | 2027-05-08 | 12 hrs | FY27 | 24 | 90030672 | B1 | 1000214059 | 08.05.2027 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYRR | 6800 | 33987 | 9499
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Cylinder Jack LHF NDE NCS | 2027-05-10 | 2027-05-10 | 12 hrs | FY27 | 24 | 90020196 | B1 | 1000278169 | 10.05.2027 | 6000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYLF | 6800 | 21646 | 2309
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Timing Chain Maintenance | 2027-05-14 | 2027-05-14 | 7 hrs | FY27 | 14 | 90022023 | B1 | 1000361303 | 14.05.2027 | 3000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHP | 5400 | 16590 | 567
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Repl Main Feed Chain | 2027-05-16 | 2027-05-16 | 8 hrs | FY27 | 16 | 90021711 | B1 | 1000295065 | 16.05.2027 | 2500 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHH | 5400 | 16590 | 3175
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Mast Cables | 2027-05-21 | 2027-05-22 | 32 hrs | FY27 | 64 | 90030334 | B1 | 1000302800 | 21.05.2027 | 2500 | CCK-MP-DRLL-DR2128-STRUCT-DMAST | 6800 | 21646 | 1486
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Engine Valve Set | 2027-05-22 | 2027-05-22 | 8 hrs | FY27 | 16 | 90021723 | B1 | 1000295054 | 22.05.2027 | 3000 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Service 12M Air Conditioner | 2027-05-23 | 2027-05-23 | 6 hrs | FY27 | 12 | 90028298 | B1 | 1000316807 | 23.05.2027 | 12 Monthly | CCK-MP-DRLL-DR2136-STRUCT-CABIN-AIRCN | 6700 | 13361 | 13361
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Jack Leg DE CS | 2027-05-25 | 2027-05-25 | 11 hrs | FY27 | 15 | 90011674 | B1 | 1000102828 | 25.05.2027 | 15000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYRR | 6800 | 64569 | 9560
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 PV271 Hydraulic Tune | 2027-05-27 | 2027-05-28 | 21 hrs | FY27 | 31.5 | 90017118 | B1 | 1000345149 | 27.05.2027 | 3000 | CCK-MP-DRLL-DR055 -HYDSYS | 6800 | 64569 | 64569
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 XLF Repl Main Feed Chain | 2027-05-27 | 2027-05-27 | 8 hrs | FY27 | 16 | 90021711 | B1 | 1000305041 | 27.05.2027 | 2500 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | 5400 | 14356 | 943
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 XLF Repl Main Feed Chain | 2027-06-02 | 2027-06-02 | 8 hrs | FY27 | 16 | 90021711 | B1 | 1000295025 | 02.06.2027 | 2500 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHH | 5400 | 16251 | 1197
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Primary Water Tank | 2027-06-04 | 2027-06-04 | 6 hrs | FY27 | 12 | 90037833 | B1 | 1000377517 | 04.06.2027 | 40000 | CCK-MP-DRLL-DR2113-DSTSUP-WTNKP | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Secondary Water Tank | 2027-06-04 | 2027-06-04 | 6 hrs | FY27 | 12 | 90037832 | B1 | 1000377467 | 04.06.2027 | 40000 | CCK-MP-DRLL-DR2113-DSTSUP-WTNKS | 6800 | 33987 | 33987
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2027-06-08 | 2027-06-08 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000295716 | 08.06.2027 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl ADS LiDAR | 2027-06-11 | 2027-06-11 | 4 hrs | FY27 | 4 | 90029065 | B1 | 1000291549 | 11.06.2027 | 5000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPR-LIDAR | 6800 | 21646 | 6175
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Drive Shaft Pump Drive | 2027-06-12 | 2027-06-12 | 6 hrs | FY27 | 12 | 90028862 | B1 | 1000316760 | 12.06.2027 | 5000 | CCK-MP-DRLL-DR2136-HYDSYS-PMPDG-DRSHT | 6700 | 13361 | 13361
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Timing Chain Maintenance | 2027-06-12 | 2027-06-12 | 7 hrs | FY27 | 14 | 90022023 | B1 | 1000361228 | 12.06.2027 | 3000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHP | 5400 | 16251 | 1197
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2027-06-13 | 2027-06-13 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000295060 | 13.06.2027 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 XLF Repl Main Feed Chain | 2027-06-27 | 2027-06-27 | 8 hrs | FY27 | 16 | 90021711 | B1 | 1000295721 | 27.06.2027 | 2500 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHH | 5400 | 14232 | 1011
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2027-06-28 | 2027-06-28 | 1 hr | FY27 | 1 | 90020876 | B1 | 1000304876 | 28.06.2027 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl ADS LiDAR | 2027-06-28 | 2027-06-28 | 4 hrs | FY27 | 4 | 90029065 | B1 | 1000290890 | 28.06.2027 | 5000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR-LIDAR | 6800 | 34252 | 34252
| Onsite PM | Drills | Fortescue |  | FY28 - DRILLS - COMPONENTS DURING PM | 2027-07-01 | 2028-06-30 |  | FY28
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack RHF NDE CS | 2027-07-02 | 2027-07-02 | 12 hrs | FY28 | 24 | 90030670 | B1 | 1000213910 | 02.07.2027 | 6000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYRF | 6800 | 34249 | 2739
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Drive Shaft Pump Drive | 2027-07-07 | 2027-07-07 | 6 hrs | FY28 | 12 | 90028862 | B1 | 1000287881 | 07.07.2027 | 5000 | CCK-MP-DRLL-DR2129-HYDSYS-PMPDG-DRSHT | 6800 | 18062 | 3449
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Cyl Mast Raise CS | 2027-07-13 | 2027-07-13 | 16 hrs | FY28 | 32 | 90020198 | B1 | 1000213524 | 13.07.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MRCYR | 6800 | 34249 | 7731
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Fish Eye Camera | 2027-07-15 | 2027-07-15 | 16 hrs | FY28 | 16 | 90029067 | B1 | 1000290901 | 15.07.2027 | 10000 | CCK-MP-DRLL-DR2113-ADSYST-ADSPR-HTCAM | 6800 | 34008 | 34008
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl ADS LiDAR | 2027-07-15 | 2027-07-15 | 4 hrs | FY28 | 4 | 90029065 | B1 | 1000293041 | 15.07.2027 | 5000 | CCK-MP-DRLL-DR2129-ADSYST-ADSPR-LIDAR | 6800 | 18062 | 13815
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Compressor Coupling | 2027-07-15 | 2027-07-15 | 12 hrs | FY28 | 24 | 90030404 | B1 | 1000303539 | 15.07.2027 | 7500 | CCK-MP-DRLL-DR2129-AIRSYS-COMPR-COUPL | 6800 | 18062 | 13204
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Power Pack Quarter Life | 2027-07-18 | 2027-07-20 | 44 hrs | FY28 | 68 | 90029574 | B1 | 1000295337 | 18.07.2027 | 5000 | CCK-MP-DRLL-DR055 -ENGINE | 6800 | 64593 | 10155
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Raise NCS | 2027-07-19 | 2027-07-19 | 4 hrs | FY28 | 8 | 90011666 | B1 | 1000233111 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYL | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Raise CS | 2027-07-19 | 2027-07-19 | 4 hrs | FY28 | 8 | 90011667 | B1 | 1000233110 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYR | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Dual Counter Balance | 2027-07-19 | 2027-07-19 | 2 hrs | FY28 | 2 | 90011690 | B1 | 1000102835 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDCB | 6800 | 64569 | 13103
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Hyd Motor Screw Jack NCS | 2027-07-19 | 2027-07-19 | 1 hr | FY28 | 1 | 90022221 | B1 | 1000232449 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MSJTL | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Hyd Motor Screw Jack CS | 2027-07-19 | 2027-07-19 | 1 hr | FY28 | 1 | 90022221 | B1 | 1000232448 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MSJTR | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Sheaves & Cables | 2027-07-19 | 2027-07-22 | 70 hrs | FY28 | 140 | 90029857 | B1 | 1000303656 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Tower Cylinders Repl | 2027-07-19 | 2027-07-20 | 34 hrs | FY28 | 58 | 90029866 | B1 | 1000303658 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Grbx Powerhead Midlife | 2027-07-19 | 2027-07-19 | 6 hrs | FY28 | 6 | 90029861 | B1 | 1000303657 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-PWRHD | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Rod Support | 2027-07-19 | 2027-07-19 | 8 hrs | FY28 | 20 | 90022208 | B1 | 1000232419 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-RDSPT | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Pump Water Injection | 2027-07-19 | 2027-07-19 | 2 hrs | FY28 | 2 | 90011733 | B1 | 1000102876 | 19.07.2027 | 5000 | CCK-MP-DRLL-DR055 -DSTSUP-WTRPP | 6800 | 64569 | 14276
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 EncoderHarness Cab to Aframe Repl | 2027-07-19 | 2027-07-19 | 6 hrs | FY28 | 6 | 90036144 | B1 | 1000365255 | 19.07.2027 | 5000 | CCK-MP-DRLL-DR055 -ADSYST-HARNC | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS PTZ Camera & LIDAR | 2027-07-19 | 2027-07-19 | 10 hrs | FY28 | 10 | 90029206 | B1 | 1000294220 | 19.07.2027 | 10000 | CCK-MP-DRLL-DR055 -ADSYST-ADSPR-HTCAM | 6800 | 64593 | 35395
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Adjust 3750Hr Valve Set | 2027-07-20 | 2027-07-20 | 12 hrs | FY28 | 24 | 90020402 | B1 | 1000316745 | 20.07.2027 | 3750 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2027-07-26 | 2027-07-26 | 1 hr | FY28 | 1 | 90020876 | B1 | 1000295020 | 26.07.2027 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Seat Operators | 2027-07-29 | 2027-07-29 | 4 hrs | FY28 | 8 | 90020200 | B2 | 1000213917 | 29.07.2027 | 20000 | CCK-MP-DRLL-DR2112-STRUCT-CABIN-SEATS | 6800 | 34249 | 12444
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Engine Valve Set | 2027-07-31 | 2027-07-31 | 8 hrs | FY28 | 16 | 90021723 | B1 | 1000305070 | 31.07.2027 | 3000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Timing Chain Maintenance | 2027-07-31 | 2027-07-31 | 7 hrs | FY28 | 14 | 90022023 | B1 | 1000361317 | 31.07.2027 | 3000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHP | 5400 | 14414 | 7858
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Primary Water Tank Anodes | 2027-08-01 | 2027-08-01 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377518 | 01.08.2027 | 10000 | CCK-MP-DRLL-DR2128-DSTSUP-WTNKP | 6800 | 21646 | 21646
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Secondary Water Tank Anodes | 2027-08-01 | 2027-08-01 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377468 | 01.08.2027 | 10000 | CCK-MP-DRLL-DR2128-DSTSUP-WTNKS | 6800 | 21646 | 21646
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Primary Water Tank Anodes | 2027-08-01 | 2027-08-01 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377540 | 01.08.2027 | 10000 | CCK-MP-DRLL-DR2129-DSTSUP-WTNKP | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Secondary Water Tank Anodes | 2027-08-01 | 2027-08-01 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377471 | 01.08.2027 | 10000 | CCK-MP-DRLL-DR2129-DSTSUP-WTNKS | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Primary Water Tank Anodes | 2027-08-01 | 2027-08-01 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377514 | 01.08.2027 | 10000 | CCK-MP-DRLL-DR2112-DSTSUP-WTNKP | 6800 | 34249 | 10037
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Secondary Water Tank Anodes | 2027-08-01 | 2027-08-01 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377250 | 01.08.2027 | 10000 | CCK-MP-DRLL-DR2112-DSTSUP-WTNKS | 6800 | 34249 | 10037
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack LHF NDE NCS | 2027-08-04 | 2027-08-04 | 12 hrs | FY28 | 24 | 90020196 | B1 | 1000316715 | 04.08.2027 | 6000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLF | 6700 | 13361 | 5509
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Battery Cables | 2027-08-04 | 2027-08-05 | 24 hrs | FY28 | 24 | 90028942 | B1 | 1000289021 | 04.08.2027 | 15000 | CCK-MP-DRLL-DR2112-ELCTLV-HARNS | 6800 | 34252 | 34228
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Adjust 3750Hr Valve Set | 2027-08-08 | 2027-08-08 | 12 hrs | FY28 | 24 | 90020402 | B1 | 1000214045 | 08.08.2027 | 3750 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Operators Seat | 2027-08-11 | 2027-08-11 | 6 hrs | FY28 | 6 | 90011710 | B2 | 1000102848 | 11.08.2027 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-CABIN-SEATS | 6800 | 64569 | 13103
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Main Air Compressor LP | 2027-08-14 | 2027-08-15 | 25 hrs | FY28 | 50 | 90020192 | B1 | 1000316753 | 14.08.2027 | 15000 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast ADS Hardware | 2027-08-15 | 2027-08-17 | 49 hrs | FY28 | 49 | 90029071 | B1 | 1000316814 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Deck ADS Elec Hardware | 2027-08-15 | 2027-08-15 | 10 hrs | FY28 | 10 | 90029060 | B1 | 1000316815 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW-ADSMF | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cabin ADS Components | 2027-08-15 | 2027-08-17 | 58.5 hrs | FY28 | 58.5 | 90029058 | B1 | 1000316818 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW-HMIJK | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS Field Instruments | 2027-08-15 | 2027-08-15 | 7.5 hrs | FY28 | 7.5 | 90029064 | B1 | 1000316819 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-ADSYST-ADSIS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS Vibration Sensors | 2027-08-15 | 2027-08-15 | 1 hr | FY28 | 1 | 90029062 | B1 | 1000316820 | 15.08.2027 | 10000 | CCK-MP-DRLL-DR2136-ADSYST-ADSIS-DSVSN | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS 3D Sensor Harness | 2027-08-15 | 2027-08-15 | 2 hrs | FY28 | 2 | 90029068 | B1 | 1000316822 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS LiDAR | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 4 | 90029065 | B1 | 1000316824 | 15.08.2027 | 5000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS Harnesses | 2027-08-15 | 2027-08-17 | 43.5 hrs | FY28 | 43.5 | 90029073 | B1 | 1000316825 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-ADSYST-HARNC | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Primary Water Tank Anodes | 2027-08-15 | 2027-08-15 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377553 | 15.08.2027 | 10000 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKP | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Secondary Water Tank Anodes | 2027-08-15 | 2027-08-15 | 8 hrs | FY28 | 8 | 90037834 | B1 | 1000377484 | 15.08.2027 | 10000 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Motor Propel NCS | 2027-08-15 | 2027-08-15 | 6 hrs | FY28 | 12 | 90020190 | B1 | 1000316756 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MPRPL | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Motor Propel CS | 2027-08-15 | 2027-08-15 | 6 hrs | FY28 | 12 | 90020190 | B1 | 1000316755 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MPRPR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Seat Operators | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020200 | B2 | 1000316799 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-SEATS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Mast Module Midlife | 2027-08-15 | 2027-08-20 | 125 hrs | FY28 | 253 | 90030336 | B1 | 1000316828 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Carrier NCS NDE | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020189 | B1 | 1000316770 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLF | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Carrier NCS Middle | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020189 | B1 | 1000316771 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLM | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Carrier NCS DE | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020189 | B1 | 1000316772 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Idler & Recoil Gp NCS | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90030377 | B1 | 1000316834 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-IDLLH | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos1 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316774 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF01 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos2 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316784 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF02 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos3 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316786 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF03 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos4 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316788 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF04 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos5 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316790 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF05 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos6 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316792 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF06 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos7 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316794 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF07 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos8 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316796 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF08 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos9 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316798 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF09 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos10 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316776 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF10 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos11 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316778 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF11 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos12 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316780 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF12 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos13 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316782 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF13 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load NCS Pos14 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316839 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF14 | 6700 | 13361 | 8814
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Carrier CS NDE | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020189 | B1 | 1000316769 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRF | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Carrier CS Middle | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020189 | B1 | 1000316768 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRM | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Carrier CS DE | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020189 | B1 | 1000316767 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Idler & Recoil Gp CS | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90030377 | B1 | 1000316835 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-IDLRH | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos1 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316773 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF01 | 6700 | 13361 | 4130
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos2 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316783 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF02 | 6700 | 13361 | 4130
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos3 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316785 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF03 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos4 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316787 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF04 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos6 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316791 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF06 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos7 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316793 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF07 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos8 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316795 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF08 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos9 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316797 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF09 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos10 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316775 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF10 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos11 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316777 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF11 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos12 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316779 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF12 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos13 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316781 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF13 | 6700 | 13361 | 4130
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Roller Load CS Pos14 | 2027-08-15 | 2027-08-15 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000316838 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF14 | 6700 | 13361 | 4130
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Final Drive & Sprocket RH | 2027-08-15 | 2027-08-15 | 14 hrs | FY28 | 26 | 90020182 | B1 | 1000316749 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-TRAVEL-FDRRH | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Track Assembly NCS | 2027-08-15 | 2027-08-15 | 12 hrs | FY28 | 24 | 90020187 | B1 | 1000316801 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-TRAVEL-TRKLH | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Track Assembly CS | 2027-08-15 | 2027-08-15 | 12 hrs | FY28 | 24 | 90020187 | B1 | 1000316800 | 15.08.2027 | 20000 | CCK-MP-DRLL-DR2136-TRAVEL-TRKRH | 6700 | 13361 | 13361
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Initial 250Hr Valve Set | 2027-08-15 | 2027-08-15 | 12 hrs | FY28 | 24 | 90016058 | B1 | 1000295331 | 05.06.2027 | 250 | CCK-MP-DRLL-DR2111-ENGINE | 6800 | 49411 | 11797
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Pump Main Hyd NCS | 2027-08-15 | 2027-08-15 | 6 hrs | FY28 | 6 | 90020235 | B1 | 1000213925 | 15.08.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-MNPP1 | 6800 | 34249 | 13155
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Sprocket RH | 2027-08-15 | 2027-08-15 | 12 hrs | FY28 | 24 | 90020186 | B1 | 1000302908 | 15.08.2027 | 10000 | CCK-MP-DRLL-DR2112-TRAVEL-SPRKR | 6800 | 34249 | 4197
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack LHF NDE NCS | 2027-08-21 | 2027-08-21 | 12 hrs | FY28 | 24 | 90020196 | B1 | 1000214056 | 21.08.2027 | 6000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLF | 6800 | 33987 | 1040
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Final Drive & Sprocket LH | 2027-08-25 | 2027-08-25 | 14 hrs | FY28 | 26 | 90020182 | B1 | 1000213621 | 25.08.2027 | 20000 | CCK-MP-DRLL-DR2112-TRAVEL-FDRLH | 6800 | 34249 | 11924
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Cyl Mast Locking CS | 2027-08-26 | 2027-08-26 | 12 hrs | FY28 | 24 | 90030657 | B1 | 1000213914 | 26.08.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MLCYR | 6800 | 34249 | 7732
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Cyl Mast Raise NCS | 2027-08-26 | 2027-08-26 | 16 hrs | FY28 | 32 | 90030659 | B1 | 1000213915 | 26.08.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MRCYL | 6800 | 34249 | 22682
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Hyd Pump Fan Oil Cooler LH | 2027-08-26 | 2027-08-26 | 2 hrs | FY28 | 2 | 90020239 | B1 | 1000213928 | 26.08.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-FANP1 | 6800 | 34249 | 6803
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Hyd Pump Fan Engine Cool RH | 2027-08-26 | 2027-08-26 | 2 hrs | FY28 | 2 | 90020240 | B1 | 1000213929 | 26.08.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-FANP2 | 6800 | 34249 | 6803
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Pump Main Hyd CS | 2027-08-26 | 2027-08-26 | 6 hrs | FY28 | 6 | 90020234 | B1 | 1000213926 | 26.08.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-MNPP2 | 6800 | 34249 | 6803
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Pump Charge | 2027-08-31 | 2027-08-31 | 2 hrs | FY28 | 2 | 90020232 | B1 | 1000213924 | 31.08.2027 | 15000 | CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-MNPP3 | 6800 | 34249 | 6803
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Pump Water Inj | 2027-09-03 | 2027-09-03 | 2 hrs | FY28 | 4 | 90031899 | B1 | 1000315427 | 03.09.2027 | 7500 | CCK-MP-DRLL-DR2129-DSTSUP-WTRPP | 6800 | 18062 | 7100
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Mast Cables | 2027-09-03 | 2027-09-04 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000302720 | 03.09.2027 | 2500 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Jack Leg NDE CS | 2027-09-13 | 2027-09-13 | 11 hrs | FY28 | 15 | 90011672 | B1 | 1000102826 | 13.09.2027 | 15000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYRF | 6800 | 64569 | 7492
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Adjust 3750Hr Valve Set | 2027-09-13 | 2027-09-13 | 12 hrs | FY28 | 24 | 90020402 | B1 | 1000278372 | 13.09.2027 | 3750 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Valve Dual Counter Balance | 2027-09-20 | 2027-09-20 | 2 hrs | FY28 | 2 | 90015975 | B1 | 1000144803 | 20.09.2027 | 10000 | CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDCB | 6800 | 54883 | 11134
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Rod Thread lube Pump | 2027-09-20 | 2027-09-20 | 2 hrs | FY28 | 2 | 90011732 | B1 | 1000207193 | 20.09.2027 | 10000 | CCK-MP-DRLL-DR2110-GRSYST-RTLPP | 6800 | 54883 | 11134
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Fish Eye Camera | 2027-09-22 | 2027-09-22 | 16 hrs | FY28 | 16 | 90029067 | B1 | 1000316823 | 22.09.2027 | 10000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-HTCAM | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cyl Mast Raise NCS | 2027-09-25 | 2027-09-25 | 16 hrs | FY28 | 32 | 90030659 | B1 | 1000316742 | 25.09.2027 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MRCYL | 6700 | 13361 | 7669
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 24M Air Cond Rencool Overhaul | 2027-09-25 | 2027-09-25 | 12 hrs | FY28 | 24 | 90018580 | B1 | 1000180988 | 25.09.2027 | 24 Monthly | CCK-MP-DRLL-DR2110-STRUCT-CABIN-AIRCN
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 24M Air Conditioner Overhaul | 2027-09-25 | 2027-09-30 | 132 hrs | FY28 | 180 | 90018566 | B1 | 1000180540 | 25.09.2027 | 24 Monthly | CCK-MP-DRLL-DR2110-STRUCT-CABIN-AIRCN
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Pump Water Injection | 2027-09-26 | 2027-09-26 | 2 hrs | FY28 | 2 | 90016011 | B1 | 1000144840 | 26.09.2027 | 5000 | CCK-MP-DRLL-DR2110-DSTSUP-WTRPP | 6800 | 54883 | 11134
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 12M Air Cond Rencool Service | 2027-09-27 | 2027-09-27 | 8 hrs | FY28 | 16 | 90018579 | B1 | 1000180738 | 27.09.2027 | 12 Monthly | CCK-MP-DRLL-DR055 -STRUCT-CABIN-AIRCN | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 12M Air Conditioner Service | 2027-09-27 | 2027-09-28 | 18 hrs | FY28 | 36 | 90018564 | B1 | 1000180530 | 27.09.2027 | 12 Monthly | CCK-MP-DRLL-DR055 -STRUCT-CABIN-AIRCN | 6800 | 64569 | 13121
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Engine Valve Set | 2027-09-28 | 2027-09-28 | 8 hrs | FY28 | 16 | 90021723 | B1 | 1000295750 | 28.09.2027 | 3000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Timing Chain Maintenance | 2027-09-28 | 2027-09-28 | 7 hrs | FY28 | 14 | 90022023 | B1 | 1000361310 | 28.09.2027 | 3000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHP | 5400 | 14232 | 14232
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Deck ADS Elec Hardware | 2027-10-04 | 2027-10-04 | 10 hrs | FY28 | 10 | 90029060 | B1 | 1000290893 | 04.10.2027 | 20000 | CCK-MP-DRLL-DR2113-ADSYST-ADSHW-ADSMF | 6800 | 34008 | 34008
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Hyd Motor Propel NCS | 2027-10-06 | 2027-10-06 | 6 hrs | FY28 | 12 | 90020190 | B1 | 1000214049 | 06.10.2027 | 20000 | CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-MPRPL | 6800 | 33987 | 11590
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Hyd Motor Propel CS | 2027-10-06 | 2027-10-06 | 6 hrs | FY28 | 12 | 90020190 | B1 | 1000214050 | 06.10.2027 | 20000 | CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-MPRPR | 6800 | 33987 | 11590
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl ADS Vibration Sensors | 2027-10-06 | 2027-10-06 | 1 hr | FY28 | 1 | 90029062 | B1 | 1000290898 | 06.10.2027 | 10000 | CCK-MP-DRLL-DR2113-ADSYST-ADSIS-DSVSN | 6800 | 34008 | 34008
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Mast Cables | 2027-10-12 | 2027-10-13 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000302727 | 12.10.2027 | 2500 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2027-10-16 | 2027-10-16 | 1 hr | FY28 | 1 | 90020876 | B1 | 1000295716 | 16.10.2027 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Adjust 500Hr Initial Valve Set | 2027-10-24 | 2027-10-24 | 12 hrs | FY28 | 24 | 90020604 | B1 | 1000278177 | 24.10.2027 | 500 | CCK-MP-DRLL-DR2128-ENGINE | 6800 | 21646 | 3367
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2027-10-27 | 2027-10-27 | 1 hr | FY28 | 1 | 90020876 | B1 | 1000304876 | 27.10.2027 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack RHF NDE CS | 2027-10-30 | 2027-10-30 | 12 hrs | FY28 | 24 | 90030670 | B1 | 1000278358 | 30.10.2027 | 6000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYRF | 6800 | 18057 | 1556
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Jack Leg DE CS | 2027-11-02 | 2027-11-02 | 4 hrs | FY28 | 8 | 90015959 | B1 | 1000144796 | 02.11.2027 | 15000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYRR | 6800 | 54883 | 5228
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Cables & Hoses | 2027-11-02 | 2027-11-04 | 50 hrs | FY28 | 100 | 90029843 | B1 | 1000303753 | 02.11.2027 | 5000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER | 6800 | 54883 | 5228
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 PV271 Hydraulic Tune | 2027-11-04 | 2027-11-05 | 21 hrs | FY28 | 31.5 | 90017118 | B1 | 1000153015 | 04.11.2027 | 3000 | CCK-MP-DRLL-DR2110-HYDSYS | 6800 | 54883 | 22468
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 XLF Repl Main Feed Chain | 2027-11-05 | 2027-11-05 | 8 hrs | FY28 | 16 | 90021711 | B1 | 1000295721 | 05.11.2027 | 2500 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHH | 5400 | 14232 | 1011
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Water Inj | 2027-11-06 | 2027-11-06 | 2 hrs | FY28 | 4 | 90031899 | B1 | 1000316840 | 06.11.2027 | 7500 | CCK-MP-DRLL-DR2136-DSTSUP-WTRPP | 6700 | 13361 | 1577
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Mast Cables | 2027-11-11 | 2027-11-12 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000302804 | 11.11.2027 | 2500 | CCK-MP-DRLL-DR2129-STRUCT-DMAST | 6800 | 18062 | 4985
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Power Pack Quarter Life | 2027-11-17 | 2027-11-19 | 44 hrs | FY28 | 68 | 90029574 | B1 | 1000295329 | 17.11.2027 | 5000 | CCK-MP-DRLL-DR2110-ENGINE | 6800 | 54907 | 5228
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2027-12-08 | 2027-12-08 | 1 hr | FY28 | 1 | 90020876 | B1 | 1000295020 | 11.04.2028 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 PV271 Hydraulic Tune | 2027-12-11 | 2027-12-12 | 21 hrs | FY28 | 31.5 | 90017118 | B1 | 1000153016 | 11.12.2027 | 3000 | CCK-MP-DRLL-DR2111-HYDSYS | 6800 | 49393 | 8364
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | STAT DR2136 Repl Receiver PRV | 2027-12-12 | 2027-12-12 | 1 hr | FY28 | 1 | 90026270 | B1 | 1000316803 | 12.12.2027 | 48 Monthly | CCK-MP-DRLL-DR2136-AIRSYS-ARTNK | 6700 | 13362 | 13362
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Engine Initial 250hrs Valve Set | 2027-12-16 | 2027-12-16 | 8 hrs | FY28 | 16 | 90021722 | B1 | 1000295093 | 06.11.2027 | 250 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Engine Initial 250hrs Valve Set | 2027-12-20 | 2027-12-20 | 8 hrs | FY28 | 16 | 90021722 | B1 | 1000295053 | 20.12.2027 | 250 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 EncoderHarness Cab to Aframe Repl | 2027-12-23 | 2027-12-23 | 6 hrs | FY28 | 6 | 90036144 | B1 | 1000365253 | 23.12.2027 | 5000 | CCK-MP-DRLL-DR2110-ADSYST-HARNC | 6800 | 54907 | 14230
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Washdown Pump | 2027-12-25 | 2027-12-25 | 4 hrs | FY28 | 8 | 90030681 | B1 | 1000316836 | 25.12.2027 | 7500 | CCK-MP-DRLL-DR2136-DSTSUP-WSHPP | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Battery Cables | 2028-01-09 | 2028-01-10 | 24 hrs | FY28 | 24 | 90028942 | B1 | 1000316809 | 09.01.2028 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast Cables | 2028-01-09 | 2028-01-10 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000316826 | 09.01.2028 | 2500 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack RHF NDE CS | 2028-01-28 | 2028-01-28 | 12 hrs | FY28 | 24 | 90030670 | B1 | 1000316717 | 28.01.2028 | 6000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRF | 6700 | 13361 | 8546
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Engine Initial 250hrs Valve Set | 2028-02-14 | 2028-02-14 | 8 hrs | FY28 | 16 | 90021722 | B1 | 1000305069 | 14.02.2028 | 250 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Engine Assy Caterpillar C32B | 2028-02-25 | 2028-02-27 | 50 hrs | FY28 | 150 | 90034138 | B1 | 1000316743 | 25.02.2028 | 15000 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2028-02-26 | 2028-02-26 | 1 hr | FY28 | 1 | 90020876 | B1 | 1000304876 | 26.02.2028 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2028-02-29 | 2028-02-29 | 1 hr | FY28 | 1 | 90020876 | B1 | 1000295060 | 29.02.2028 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Adjust 500Hr Initial Valve Set | 2028-03-17 | 2028-03-17 | 12 hrs | FY28 | 24 | 90020604 | B1 | 1000214038 | 17.03.2028 | 500 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Mast Cables | 2028-03-21 | 2028-03-22 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000302804 | 21.03.2028 | 2500 | CCK-MP-DRLL-DR2129-STRUCT-DMAST | 6800 | 18062 | 4985
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Adjust 500Hr Initial Valve Set | 2028-03-26 | 2028-03-26 | 12 hrs | FY28 | 24 | 90020604 | B1 | 1000316744 | 26.03.2028 | 500 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 XLF Repl Main Feed Chain | 2028-03-26 | 2028-03-26 | 8 hrs | FY28 | 16 | 90021711 | B1 | 1000305041 | 26.03.2028 | 2500 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | 5400 | 14356 | 943
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Water & Fuel Tank Mounts | 2028-03-29 | 2028-03-29 | 10 hrs | FY28 | 20 | 90017453 | B1 | 1000160344 | 29.03.2028 | 6000 | CCK-MP-DRLL-DR2110-ENGINE-FUSYS-FULTK | 6800 | 54883 | 5228
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 PV271 Hydraulic Tune | 2028-03-31 | 2028-04-01 | 21 hrs | FY28 | 31.5 | 90017118 | B1 | 1000153015 | 31.03.2028 | 3000 | CCK-MP-DRLL-DR2110-HYDSYS | 6800 | 54883 | 22468
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Drive Shaft Pump Drive | 2028-04-02 | 2028-04-02 | 6 hrs | FY28 | 12 | 90028862 | B1 | 1000316760 | 02.04.2028 | 5000 | CCK-MP-DRLL-DR2136-HYDSYS-PMPDG-DRSHT | 6700 | 13361 | 13361
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Repl Main Feed Chain | 2028-04-06 | 2028-04-06 | 8 hrs | FY28 | 16 | 90021711 | B1 | 1000295065 | 06.04.2028 | 2500 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHH | 5400 | 16590 | 3175
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Adjust 3750Hr Valve Set | 2028-04-11 | 2028-04-11 | 12 hrs | FY28 | 24 | 90020402 | B1 | 1000278184 | 11.04.2028 | 3750 | CCK-MP-DRLL-DR2128-ENGINE | 6800 | 21646 | 3367
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 XLF Repl Main Feed Chain | 2028-04-16 | 2028-04-16 | 8 hrs | FY28 | 16 | 90021711 | B1 | 1000295721 | 16.04.2028 | 2500 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHH | 5400 | 14232 | 1011
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Adjust 500Hr Initial Valve Set | 2028-04-21 | 2028-04-21 | 12 hrs | FY28 | 24 | 90020604 | B1 | 1000278365 | 21.04.2028 | 500 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 XLF Repl Main Feed Chain | 2028-04-23 | 2028-04-23 | 8 hrs | FY28 | 16 | 90021711 | B1 | 1000295025 | 23.04.2028 | 2500 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHH | 5400 | 16251 | 1197
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Initial 250Hr Valve Set | 2028-04-25 | 2028-04-25 | 12 hrs | FY28 | 24 | 90016058 | B1 | 1000295335 | 25.04.2028 | 250 | CCK-MP-DRLL-DR055 -ENGINE | 6800 | 64593 | 10155
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl LiDAR Sensor | 2028-04-26 | 2028-04-27 | 24 hrs | FY28 | 24 | 90023242 | B1 | 1000240813 | 26.04.2028 | 12 Monthly | CCK-MP-DRLL-DR2110-ADSYST-ADSPR-LIDAR | 6800 | 54907 | 14230
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Battery Cables | 2028-04-28 | 2028-04-29 | 24 hrs | FY28 | 24 | 90028942 | B1 | 1000289036 | 28.04.2028 | 15000 | CCK-MP-DRLL-DR2129-ELCTLV-HARNS | 6800 | 18062 | 18062
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Auto Lube Pump | 2028-05-02 | 2028-05-02 | 2 hrs | FY28 | 2 | 90016009 | B1 | 1000144838 | 02.05.2028 | 12000 | CCK-MP-DRLL-DR2110-GRSYST-ALBPP | 6800 | 54883 | 2172
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | STAT DR2136 48M Pressure Vessel Insp Int | 2028-05-07 | 2028-05-07 | 5 hrs | FY28 | 5 | 90014200 | B1 | 1000316804 | 07.05.2028 | 48 Monthly | CCK-MP-DRLL-DR2136-AIRSYS-ARTNK | 6700 | 13362 | 13362
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Engine Valve Set | 2028-05-10 | 2028-05-10 | 8 hrs | FY28 | 16 | 90021723 | B1 | 1000295094 | 10.05.2028 | 3000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Overhaul 24M Air Conditioner | 2028-05-17 | 2028-05-17 | 12 hrs | FY28 | 24 | 90028299 | B1 | 1000316808 | 17.05.2028 | 24 Monthly | CCK-MP-DRLL-DR2136-STRUCT-CABIN-AIRCN | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl ADS Vibration Sensors | 2028-05-20 | 2028-05-20 | 1 hr | FY28 | 1 | 90029062 | B1 | 1000293017 | 20.05.2028 | 10000 | CCK-MP-DRLL-DR2129-ADSYST-ADSIS-DSVSN | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Adjust 500Hr Initial Valve Set | 2028-05-20 | 2028-05-20 | 12 hrs | FY28 | 24 | 90020604 | B1 | 1000213706 | 20.05.2028 | 500 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Mast Cables | 2028-05-21 | 2028-05-22 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000302720 | 21.05.2028 | 2500 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Engine Initial 250hrs Valve Set | 2028-05-27 | 2028-05-27 | 8 hrs | FY28 | 16 | 90021722 | B1 | 1000295749 | 27.04.2028 | 250 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Pump Water Injection | 2028-05-30 | 2028-05-30 | 2 hrs | FY28 | 2 | 90016011 | B1 | 1000144840 | 30.05.2028 | 5000 | CCK-MP-DRLL-DR2110-DSTSUP-WTRPP | 6800 | 54883 | 11134
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS LiDAR | 2028-06-05 | 2028-06-05 | 4 hrs | FY28 | 4 | 90029065 | B1 | 1000316824 | 05.06.2028 | 5000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast Cables | 2028-06-05 | 2028-06-06 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000316826 | 05.06.2028 | 2500 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Pump Water Injection | 2028-06-05 | 2028-06-05 | 4 hrs | FY28 | 4 | 90021716 | B1 | 1000295729 | 05.06.2028 | 6000 | CCK-MP-DRLL-DR3137-DSTSUP-WTRPP | 5400 | 14232 | 7384
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Cyl Feed Holder Swing | 2028-06-08 | 2028-06-08 | 4 hrs | FY28 | 4 | 90022007 | B1 | 1000295075 | 08.06.2028 | 9000 | CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-FDHCS | 5400 | 16590 | 7567
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Timing Chain Maintenance | 2028-06-08 | 2028-06-08 | 7 hrs | FY28 | 14 | 90022023 | B1 | 1000361303 | 08.06.2028 | 3000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHP | 5400 | 16590 | 567
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Hose Drum Assembly | 2028-06-08 | 2028-06-08 | 8 hrs | FY28 | 16 | 90022021 | B1 | 1000361307 | 08.06.2028 | 9000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDHDA | 5400 | 16590 | 8396
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Cyl Mast Raise CS | 2028-06-12 | 2028-06-12 | 16 hrs | FY28 | 32 | 90020198 | B1 | 1000278174 | 12.06.2028 | 15000 | CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MRCYR | 6800 | 21646 | 4602
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos3 | 2028-06-13 | 2028-06-13 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000278245 | 13.06.2028 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF03 | 6800 | 21646 | 1486
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Roller Load CS Pos4 | 2028-06-13 | 2028-06-13 | 4 hrs | FY28 | 8 | 90020188 | B1 | 1000278247 | 13.06.2028 | 20000 | CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF04 | 6800 | 21646 | 1486
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Mast Cables | 2028-06-15 | 2028-06-16 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000302800 | 15.06.2028 | 2500 | CCK-MP-DRLL-DR2128-STRUCT-DMAST | 6800 | 21646 | 1486
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Engine Valve Set | 2028-06-16 | 2028-06-16 | 8 hrs | FY28 | 16 | 90021723 | B1 | 1000295054 | 16.06.2028 | 3000 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2028-06-27 | 2028-06-27 | 1 hr | FY28 | 1 | 90020876 | B1 | 1000304876 | 27.06.2028 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Mast Cables | 2028-06-29 | 2028-06-30 | 32 hrs | FY28 | 64 | 90030334 | B1 | 1000302727 | 29.06.2028 | 2500 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Compressor Coupling | 2028-06-29 | 2028-06-29 | 12 hrs | FY28 | 24 | 90030404 | B1 | 1000303532 | 29.06.2028 | 7500 | CCK-MP-DRLL-DR2112-AIRSYS-COMPR-COUPL | 6800 | 34252 | 3236
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Compressor Coupling | 2028-06-30 | 2028-06-30 | 12 hrs | FY28 | 24 | 90030404 | B1 | 1000303538 | 30.06.2028 | 7500 | CCK-MP-DRLL-DR2128-AIRSYS-COMPR-COUPL | 6800 | 21646 | 3367
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Drive Shaft Pump Drive | 2028-06-30 | 2028-06-30 | 6 hrs | FY28 | 12 | 90028862 | B1 | 1000287879 | 30.06.2028 | 5000 | CCK-MP-DRLL-DR2128-HYDSYS-PMPDG-DRSHT | 6800 | 21646 | 1486
| Onsite PM | Drills | Fortescue |  | FY29 - DRILLS - COMPONENTS DURING PM | 2028-07-01 | 2029-06-30 |  | FY29
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2028-07-03 | 2028-07-03 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295716 | 03.07.2028 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 12M Air Cond Rencool Service | 2028-07-06 | 2028-07-06 | 8 hrs | FY29 | 16 | 90018579 | B1 | 1000180989 | 06.07.2028 | 12 Monthly | CCK-MP-DRLL-DR2111-STRUCT-CABIN-AIRCN
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 12M Air Conditioner Service | 2028-07-06 | 2028-07-07 | 18 hrs | FY29 | 36 | 90018564 | B1 | 1000180529 | 06.07.2028 | 12 Monthly | CCK-MP-DRLL-DR2111-STRUCT-CABIN-AIRCN
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2028-07-08 | 2028-07-08 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295060 | 08.07.2028 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Cyl Feed Holder Swing | 2028-07-08 | 2028-07-08 | 4 hrs | FY29 | 4 | 90022007 | B1 | 1000295035 | 08.07.2028 | 9000 | CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-FDHCS | 5400 | 16251 | 8583
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Timing Chain Maintenance | 2028-07-08 | 2028-07-08 | 7 hrs | FY29 | 14 | 90022023 | B1 | 1000361228 | 08.07.2028 | 3000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHP | 5400 | 16251 | 1197
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Hose Drum Assembly | 2028-07-08 | 2028-07-08 | 8 hrs | FY29 | 16 | 90022021 | B1 | 1000361232 | 08.07.2028 | 9000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDHDA | 5400 | 16251 | 8563
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl ADS LiDAR | 2028-07-12 | 2028-07-12 | 4 hrs | FY29 | 4 | 90029065 | B1 | 1000290902 | 12.07.2028 | 5000 | CCK-MP-DRLL-DR2113-ADSYST-ADSPR-LIDAR | 6800 | 34008 | 10800
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Jack Leg NDE NCS | 2028-07-17 | 2028-07-17 | 11 hrs | FY29 | 15 | 90011671 | B1 | 1000102825 | 17.07.2028 | 15000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYLF | 6800 | 64569 | 710
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack LHF NDE NCS | 2028-07-22 | 2028-07-22 | 12 hrs | FY29 | 24 | 90020196 | B1 | 1000316715 | 22.07.2028 | 6000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLF | 6700 | 13361 | 5509
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Cab Harnesses | 2028-07-23 | 2028-07-23 | 14 hrs | FY29 | 14 | 90028947 | B1 | 1000289023 | 23.07.2028 | 15000 | CCK-MP-DRLL-DR2112-ELCTLV-HARNS | 6800 | 34252 | 34228
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Mast Cables | 2028-07-29 | 2028-07-30 | 32 hrs | FY29 | 64 | 90030334 | B1 | 1000302804 | 29.07.2028 | 2500 | CCK-MP-DRLL-DR2129-STRUCT-DMAST | 6800 | 18062 | 4985
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Engine Valve Set | 2028-07-30 | 2028-07-30 | 8 hrs | FY29 | 16 | 90021723 | B1 | 1000305070 | 30.07.2028 | 3000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Cyl Feed Holder Swing | 2028-07-30 | 2028-07-30 | 4 hrs | FY29 | 4 | 90022007 | B1 | 1000305051 | 30.07.2028 | 9000 | CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-FDHCS | 5400 | 14414 | 2853
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Timing Chain Maintenance | 2028-07-30 | 2028-07-30 | 7 hrs | FY29 | 14 | 90022023 | B1 | 1000361317 | 30.07.2028 | 3000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHP | 5400 | 14414 | 7858
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Hose Drum Assembly | 2028-07-30 | 2028-07-30 | 8 hrs | FY29 | 16 | 90022021 | B1 | 1000361481 | 30.07.2028 | 9000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDHDA | 5400 | 14414 | 3216
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Drive Shaft Pump Drive | 2028-08-10 | 2028-08-10 | 6 hrs | FY29 | 12 | 90028862 | B1 | 1000287873 | 10.08.2028 | 5000 | CCK-MP-DRLL-DR2112-HYDSYS-PMPDG-DRSHT | 6800 | 34249 | 2406
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Compressor Coupling | 2028-08-11 | 2028-08-11 | 12 hrs | FY29 | 24 | 90030404 | B1 | 1000303533 | 11.08.2028 | 7500 | CCK-MP-DRLL-DR2113-AIRSYS-COMPR-COUPL | 6800 | 34008 | 11590
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Service Airconditioning System | 2028-08-17 | 2028-08-17 | 12 hrs | FY29 | 12 | 90023281 | B1 | 1000295091 | 17.08.2028 | 12 Monthly | CCK-MP-DRLL-DR3134-STRUCT-CABIN-ACCOM | 5400 | 16590 | 16590
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2028-08-20 | 2028-08-20 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295020 | 20.08.2028 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl ADS Harnesses | 2028-08-24 | 2028-08-29 | 131.5 hrs | FY29 | 131.5 | 90029210 | B1 | 1000294213 | 24.08.2028 | 20000 | CCK-MP-DRLL-DR2111-ADSYST-HARNC | 6800 | 49417 | 4564
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Drive Shaft Pump Drive | 2028-08-25 | 2028-08-25 | 6 hrs | FY29 | 12 | 90028862 | B1 | 1000287874 | 25.08.2028 | 5000 | CCK-MP-DRLL-DR2113-HYDSYS-PMPDG-DRSHT | 6800 | 33987 | 2582
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 XLF Repl Main Feed Chain | 2028-08-25 | 2028-08-25 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000305041 | 25.08.2028 | 2500 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | 5400 | 14356 | 943
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Cables & Hoses | 2028-08-25 | 2028-08-27 | 50 hrs | FY29 | 100 | 90029843 | B1 | 1000303760 | 25.08.2028 | 5000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Battery Cables | 2028-08-29 | 2028-08-30 | 24 hrs | FY29 | 24 | 90028942 | B1 | 1000289021 | 29.08.2028 | 15000 | CCK-MP-DRLL-DR2112-ELCTLV-HARNS | 6800 | 34252 | 34228
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Adjust 3750Hr Valve Set | 2028-09-02 | 2028-09-02 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000214045 | 02.09.2028 | 3750 | CCK-MP-DRLL-DR2113-ENGINE | 6800 | 33987 | 13861
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Cylinder Jack RHF NDE CS | 2028-09-04 | 2028-09-04 | 12 hrs | FY29 | 24 | 90030670 | B1 | 1000214058 | 04.09.2028 | 6000 | CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYRF | 6800 | 33987 | 306
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack RHF NDE CS | 2028-09-07 | 2028-09-07 | 12 hrs | FY29 | 24 | 90030670 | B1 | 1000278358 | 07.09.2028 | 6000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYRF | 6800 | 18057 | 1556
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl LiDAR Sensor | 2028-09-08 | 2028-09-09 | 24 hrs | FY29 | 24 | 90023242 | B1 | 1000240814 | 08.09.2028 | 12 Monthly | CCK-MP-DRLL-DR2111-ADSYST-ADSPR-LIDAR | 6800 | 49417 | 6939
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Service Airconditioning System | 2028-09-15 | 2028-09-15 | 12 hrs | FY29 | 12 | 90023281 | B1 | 1000295051 | 15.09.2028 | 12 Monthly | CCK-MP-DRLL-DR3133-STRUCT-CABIN-ACCOM | 5400 | 16251 | 16251
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Repl Main Feed Chain | 2028-09-16 | 2028-09-16 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000295065 | 16.09.2028 | 2500 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHH | 5400 | 16590 | 3175
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 PV271 Hydraulic Tune | 2028-09-21 | 2028-09-22 | 21 hrs | FY29 | 31.5 | 90017118 | B1 | 1000345149 | 21.09.2028 | 3000 | CCK-MP-DRLL-DR055 -HYDSYS | 6800 | 64569 | 64569
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 24M Air Cond Rencool Overhaul | 2028-09-21 | 2028-09-21 | 12 hrs | FY29 | 24 | 90018580 | B1 | 1000180960 | 21.09.2028 | 24 Monthly | CCK-MP-DRLL-DR055 -STRUCT-CABIN-AIRCN | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 24M Air Conditioner Overhaul | 2028-09-21 | 2028-09-26 | 132 hrs | FY29 | 180 | 90018566 | B1 | 1000180542 | 21.09.2028 | 24 Monthly | CCK-MP-DRLL-DR055 -STRUCT-CABIN-AIRCN | 6800 | 64569 | 13121
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 XLF Repl Main Feed Chain | 2028-09-26 | 2028-09-26 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000295721 | 26.09.2028 | 2500 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHH | 5400 | 14232 | 1011
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Pump Water Inj | 2028-09-28 | 2028-09-28 | 2 hrs | FY29 | 4 | 90031899 | B1 | 1000315427 | 28.09.2028 | 7500 | CCK-MP-DRLL-DR2129-DSTSUP-WTRPP | 6800 | 18062 | 7100
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Mast Module Qtr Life | 2028-09-28 | 2028-10-02 | 93 hrs | FY29 | 201 | 90030335 | B1 | 1000302721 | 28.09.2028 | 10000 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Power Pack Midlife | 2028-09-28 | 2028-10-03 | 125 hrs | FY29 | 197 | 90029572 | B1 | 1000295332 | 28.09.2028 | 10000 | CCK-MP-DRLL-DR2111-ENGINE | 6800 | 49411 | 11797
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Hyd Motor Fan Hyd Cooler | 2028-09-28 | 2028-09-28 | 6 hrs | FY29 | 6 | 90011697 | B1 | 1000144867 | 28.09.2028 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MFMCA | 6800 | 49393 | 1608
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Adjust 3750Hr Valve Set | 2028-10-03 | 2028-10-03 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000316745 | 03.10.2028 | 3750 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Cylinder Jack LHF NDE NCS | 2028-10-03 | 2028-10-03 | 12 hrs | FY29 | 24 | 90020196 | B1 | 1000213907 | 03.10.2028 | 6000 | CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYLF | 6800 | 34249 | 2981
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 XLF Repl Main Feed Chain | 2028-10-03 | 2028-10-03 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000295025 | 03.10.2028 | 2500 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHH | 5400 | 16251 | 1197
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Adjust 3750Hr Valve Set | 2028-10-08 | 2028-10-08 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000278372 | 08.10.2028 | 3750 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Engine Midlife Complete | 2028-10-23 | 2028-10-24 | 36 hrs | FY29 | 54 | 90029233 | B1 | 1000293344 | 23.10.2028 | 7500 | CCK-MP-DRLL-DR2128-ENGINE | 6800 | 21646 | 3367
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Adjust 3750Hr Valve Set | 2028-10-23 | 2028-10-23 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000278184 | 23.10.2028 | 3750 | CCK-MP-DRLL-DR2128-ENGINE | 6800 | 21646 | 3367
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Mast Cables | 2028-10-23 | 2028-10-24 | 32 hrs | FY29 | 64 | 90030334 | B1 | 1000302800 | 23.10.2028 | 2500 | CCK-MP-DRLL-DR2128-STRUCT-DMAST | 6800 | 21646 | 1486
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Engine Valve Set | 2028-10-23 | 2028-10-23 | 8 hrs | FY29 | 16 | 90021723 | B1 | 1000295750 | 23.10.2028 | 3000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Cyl Feed Holder Swing | 2028-10-23 | 2028-10-23 | 4 hrs | FY29 | 4 | 90022007 | B1 | 1000295731 | 23.10.2028 | 9000 | CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-FDHCS | 5400 | 14232 | 4692
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Timing Chain Maintenance | 2028-10-23 | 2028-10-23 | 7 hrs | FY29 | 14 | 90022023 | B1 | 1000361310 | 23.10.2028 | 3000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHP | 5400 | 14232 | 14232
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Hose Drum Assembly | 2028-10-23 | 2028-10-23 | 8 hrs | FY29 | 16 | 90022021 | B1 | 1000361314 | 23.10.2028 | 9000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDHDA | 5400 | 14232 | 14232
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2028-10-26 | 2028-10-26 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000304876 | 26.10.2028 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Service Airconditioning System | 2028-10-27 | 2028-10-27 | 12 hrs | FY29 | 12 | 90023281 | B1 | 1000295747 | 27.10.2028 | 12 Monthly | CCK-MP-DRLL-DR3137-STRUCT-CABIN-ACCOM | 5400 | 14232 | 8625
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Compressor Coupling | 2028-10-29 | 2028-10-29 | 12 hrs | FY29 | 24 | 90030404 | B1 | 1000316754 | 29.10.2028 | 7500 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR-COUPL | 6700 | 13361 | 8815
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast Cables | 2028-10-30 | 2028-10-31 | 32 hrs | FY29 | 64 | 90030334 | B1 | 1000316826 | 30.10.2028 | 2500 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Adjust 3750Hr Valve Set | 2028-11-05 | 2028-11-05 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000213713 | 05.11.2028 | 3750 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Mast Module Qtr Life | 2028-11-06 | 2028-11-10 | 93 hrs | FY29 | 201 | 90030335 | B1 | 1000302726 | 06.11.2028 | 10000 | CCK-MP-DRLL-DR2113-STRUCT-DMAST | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Pump Water Inj | 2028-11-07 | 2028-11-07 | 2 hrs | FY29 | 4 | 90031899 | B1 | 1000315426 | 07.11.2028 | 7500 | CCK-MP-DRLL-DR2128-DSTSUP-WTRPP | 6800 | 21646 | 6363
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Battery Cables | 2028-11-07 | 2028-11-08 | 24 hrs | FY29 | 24 | 90028942 | B1 | 1000289031 | 07.11.2028 | 15000 | CCK-MP-DRLL-DR2128-ELCTLV-HARNS | 6800 | 21646 | 6363
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Primary Water Tank Anodes | 2028-11-07 | 2028-11-07 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377516 | 07.11.2028 | 10000 | CCK-MP-DRLL-DR2113-DSTSUP-WTNKP | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Secondary Water Tank Anodes | 2028-11-07 | 2028-11-07 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377466 | 07.11.2028 | 10000 | CCK-MP-DRLL-DR2113-DSTSUP-WTNKS | 6800 | 33987 | 33987
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Battery Cables | 2028-11-08 | 2028-11-09 | 24 hrs | FY29 | 24 | 90028942 | B1 | 1000289026 | 08.11.2028 | 15000 | CCK-MP-DRLL-DR2113-ELCTLV-HARNS | 6800 | 34008 | 16998
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2028-11-10 | 2028-11-10 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295716 | 10.11.2028 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS GPS Components | 2028-11-10 | 2028-11-10 | 3.5 hrs | FY29 | 3.5 | 90029191 | B1 | 1000294218 | 10.11.2028 | 40000 | CCK-MP-DRLL-DR055 -ADSYST-ADSPO | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS Ace Cabinet Components | 2028-11-10 | 2028-11-12 | 44.5 hrs | FY29 | 44.5 | 90029187 | B1 | 1000294216 | 10.11.2028 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-CLXEN | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS IO Modules | 2028-11-10 | 2028-11-10 | 4 hrs | FY29 | 4 | 90029208 | B1 | 1000294215 | 10.11.2028 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-ARDIO | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Control Harnesses Chassis | 2028-11-10 | 2028-11-11 | 39 hrs | FY29 | 39 | 90029952 | B1 | 1000303818 | 10.11.2028 | 20000 | CCK-MP-DRLL-DR055 -ELCTLV-HARNS-HARCO | 6800 | 64593 | 64593
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl ADS LiDAR | 2028-11-13 | 2028-11-13 | 4 hrs | FY29 | 4 | 90029065 | B1 | 1000291549 | 13.11.2028 | 5000 | CCK-MP-DRLL-DR2128-ADSYST-ADSPR-LIDAR | 6800 | 21646 | 6175
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Cylinder Jack LHF NDE NCS | 2028-11-14 | 2028-11-14 | 12 hrs | FY29 | 24 | 90020196 | B1 | 1000278357 | 14.11.2028 | 6000 | CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYLF | 6800 | 18062 | 1556
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Power Pack Module Midlife | 2028-11-14 | 2028-11-17 | 85 hrs | FY29 | 129 | 90026035 | B1 | 1000295095 | 14.11.2028 | 6000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2028-11-16 | 2028-11-16 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295060 | 16.11.2028 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Pump Air Lubrication | 2028-11-20 | 2028-11-20 | 2 hrs | FY29 | 2 | 90021656 | B1 | 1000295071 | 20.11.2028 | 6000 | CCK-MP-DRLL-DR3134-AIRSYS-COMPR-PALUB | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Pump Water Injection | 2028-11-20 | 2028-11-20 | 4 hrs | FY29 | 4 | 90021716 | B1 | 1000295073 | 20.11.2028 | 6000 | CCK-MP-DRLL-DR3134-DSTSUP-WTRPP | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Pump Rod Thread Lube | 2028-11-20 | 2028-11-20 | 2 hrs | FY29 | 2 | 90021715 | B1 | 1000295083 | 20.11.2028 | 6000 | CCK-MP-DRLL-DR3134-GRSYST-RTLPP | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Operators Seat | 2028-11-20 | 2028-11-20 | 4 hrs | FY29 | 4 | 90021702 | B1 | 1000295069 | 20.11.2028 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-CABIN-SEATS | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Engine Valve Set | 2028-11-21 | 2028-11-21 | 8 hrs | FY29 | 16 | 90021723 | B1 | 1000295094 | 21.11.2028 | 3000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Drive Shaft Pump Drive | 2028-12-09 | 2028-12-09 | 6 hrs | FY29 | 12 | 90028862 | B1 | 1000287881 | 09.12.2028 | 5000 | CCK-MP-DRLL-DR2129-HYDSYS-PMPDG-DRSHT | 6800 | 18062 | 3449
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl ADS LiDAR | 2028-12-17 | 2028-12-17 | 4 hrs | FY29 | 4 | 90029065 | B1 | 1000293041 | 17.12.2028 | 5000 | CCK-MP-DRLL-DR2129-ADSYST-ADSPR-LIDAR | 6800 | 18062 | 13815
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Compressor Coupling | 2028-12-17 | 2028-12-17 | 12 hrs | FY29 | 24 | 90030404 | B1 | 1000303539 | 17.12.2028 | 7500 | CCK-MP-DRLL-DR2129-AIRSYS-COMPR-COUPL | 6800 | 18062 | 13204
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Fish Eye Camera | 2028-12-17 | 2028-12-17 | 16 hrs | FY29 | 16 | 90029067 | B1 | 1000290901 | 17.12.2028 | 10000 | CCK-MP-DRLL-DR2113-ADSYST-ADSPR-HTCAM | 6800 | 34008 | 34008
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Hyd Feed Motor | 2028-12-21 | 2028-12-21 | 6 hrs | FY29 | 6 | 90022025 | B1 | 1000361305 | 21.12.2028 | 6000 | CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MFEED | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Timing Chain Maintenance | 2028-12-21 | 2028-12-21 | 7 hrs | FY29 | 14 | 90022023 | B1 | 1000361303 | 21.12.2028 | 3000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHP | 5400 | 16590 | 567
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Feed Chain Sprockets | 2028-12-21 | 2028-12-21 | 12 hrs | FY29 | 24 | 90022030 | B1 | 1000361304 | 21.12.2028 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHS | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Hose Drum Sprocket | 2028-12-21 | 2028-12-21 | 6 hrs | FY29 | 6 | 90022032 | B1 | 1000361308 | 21.12.2028 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDHDS | 5400 | 16590 | 5065
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Gearbox Powerhead | 2028-12-21 | 2028-12-21 | 16 hrs | FY29 | 32 | 90021707 | B1 | 1000361306 | 21.12.2028 | 6000 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-PWRHD | 5400 | 16590 | 5716
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Pump Air Lubrication | 2028-12-28 | 2028-12-28 | 2 hrs | FY29 | 2 | 90021656 | B1 | 1000295031 | 28.12.2028 | 6000 | CCK-MP-DRLL-DR3133-AIRSYS-COMPR-PALUB | 5400 | 16251 | 10110
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Pump Water Injection | 2028-12-28 | 2028-12-28 | 4 hrs | FY29 | 4 | 90021716 | B1 | 1000295033 | 28.12.2028 | 6000 | CCK-MP-DRLL-DR3133-DSTSUP-WTRPP | 5400 | 16251 | 1685
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2028-12-28 | 2028-12-28 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295020 | 28.12.2028 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Pump Rod Thread Lube | 2028-12-28 | 2028-12-28 | 2 hrs | FY29 | 2 | 90021715 | B1 | 1000295043 | 28.12.2028 | 6000 | CCK-MP-DRLL-DR3133-GRSYST-RTLPP | 5400 | 16251 | 10110
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Operators Seat | 2028-12-28 | 2028-12-28 | 4 hrs | FY29 | 4 | 90021702 | B1 | 1000295029 | 28.12.2028 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-CABIN-SEATS | 5400 | 16251 | 10110
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Engine Valve Set | 2028-12-29 | 2028-12-29 | 8 hrs | FY29 | 16 | 90021723 | B1 | 1000295054 | 29.12.2028 | 3000 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Power Pack Module Midlife | 2028-12-29 | 2029-01-01 | 85 hrs | FY29 | 129 | 90026035 | B1 | 1000295055 | 29.12.2028 | 6000 | CCK-MP-DRLL-DR3133-ENGINE | 5400 | 16251 | 4587
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Electrical Harness | 2028-12-30 | 2028-12-30 | 15 hrs | FY29 | 30 | 90021727 | B1 | 1000295049 | 30.12.2028 | 18000 | CCK-MP-DRLL-DR3133-ELCTLV-HARNS | 5400 | 16251 | 4587
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Rod Thread lube Pump | 2028-12-31 | 2028-12-31 | 2 hrs | FY29 | 2 | 90016010 | B1 | 1000207194 | 31.12.2028 | 10000 | CCK-MP-DRLL-DR2111-GRSYST-RTLPP | 6800 | 49393 | 4564
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Pump Water Injection | 2028-12-31 | 2028-12-31 | 2 hrs | FY29 | 2 | 90016011 | B1 | 1000144924 | 31.12.2028 | 5000 | CCK-MP-DRLL-DR2111-DSTSUP-WTRPP | 6800 | 49393 | 4564
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Vehicle Loading Crane | 2028-12-31 | 2028-12-31 | 6 hrs | FY29 | 12 | 90032932 | B1 | 1000331360 | 31.12.2028 | 40000 | CCK-MP-DRLL-DR055 -STRUCT-CRANE | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Track Frame Module-NCS | 2028-12-31 | 2029-01-01 | 36 hrs | FY29 | 72 | 90022185 | B1 | 1000205855 | 31.12.2028 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TKFRL | 6800 | 64569 | 1827
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Track Frame Module CS | 2028-12-31 | 2029-01-01 | 36 hrs | FY29 | 72 | 90022183 | B1 | 1000206293 | 31.12.2028 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TKFRR | 6800 | 64569 | 1827
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Primary Water Tank Anodes | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377540 | 04.01.2029 | 10000 | CCK-MP-DRLL-DR2129-DSTSUP-WTNKP | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Secondary Water Tank Anodes | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377471 | 04.01.2029 | 10000 | CCK-MP-DRLL-DR2129-DSTSUP-WTNKS | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Primary Water Tank Anodes | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377518 | 04.01.2029 | 10000 | CCK-MP-DRLL-DR2128-DSTSUP-WTNKP | 6800 | 21646 | 21646
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Repl Secondary Water Tank Anodes | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377468 | 04.01.2029 | 10000 | CCK-MP-DRLL-DR2128-DSTSUP-WTNKS | 6800 | 21646 | 21646
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Primary Water Tank Anodes | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377514 | 04.01.2029 | 10000 | CCK-MP-DRLL-DR2112-DSTSUP-WTNKP | 6800 | 34249 | 10037
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Secondary Water Tank Anodes | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377250 | 04.01.2029 | 10000 | CCK-MP-DRLL-DR2112-DSTSUP-WTNKS | 6800 | 34249 | 10037
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Power Pack Quarter Life | 2029-01-05 | 2029-01-07 | 44 hrs | FY29 | 68 | 90029574 | B1 | 1000295337 | 05.01.2029 | 5000 | CCK-MP-DRLL-DR055 -ENGINE | 6800 | 64593 | 10155
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Raise NCS | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 8 | 90011666 | B1 | 1000233111 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYL | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Raise CS | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 8 | 90011667 | B1 | 1000233110 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYR | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Angle Locking NCS | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 4 | 90011670 | B1 | 1000242374 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TACYL | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Tower Angle Locking CS | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 4 | 90011670 | B1 | 1000242375 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TACYR | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Stacking 8 Spool | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 8 | 90011688 | B1 | 1000233106 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVS8S | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Stacking 11 spool | 2029-01-06 | 2029-01-06 | 6 hrs | FY29 | 10 | 90011689 | B1 | 1000233107 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VV11S | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Dual Counter Balance | 2029-01-06 | 2029-01-06 | 2 hrs | FY29 | 2 | 90011690 | B1 | 1000102835 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDCB | 6800 | 64569 | 13103
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Diverter NCS | 2029-01-06 | 2029-01-06 | 9 hrs | FY29 | 9 | 90011692 | B1 | 1000102837 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDVL | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Diverter CS | 2029-01-06 | 2029-01-06 | 9 hrs | FY29 | 9 | 90011693 | B1 | 1000102838 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDVR | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Drill & Propel Control | 2029-01-06 | 2029-01-06 | 6 hrs | FY29 | 6 | 90011694 | B1 | 1000102839 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDPC | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Valve Tension Cable | 2029-01-06 | 2029-01-06 | 2 hrs | FY29 | 2 | 90022224 | B1 | 1000232414 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVTNC | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Hyd Motor Screw Jack NCS | 2029-01-06 | 2029-01-06 | 1 hr | FY29 | 1 | 90022221 | B1 | 1000232449 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MSJTL | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Hyd Motor Screw Jack CS | 2029-01-06 | 2029-01-06 | 1 hr | FY29 | 1 | 90022221 | B1 | 1000232448 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MSJTR | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Sheaves & Cables | 2029-01-06 | 2029-01-09 | 70 hrs | FY29 | 140 | 90029857 | B1 | 1000303656 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Tower Cylinders Repl | 2029-01-06 | 2029-01-07 | 34 hrs | FY29 | 58 | 90029866 | B1 | 1000303658 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Gearbox Power Head | 2029-01-06 | 2029-01-07 | 26 hrs | FY29 | 52 | 90011716 | B1 | 1000232408 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-PWRHD | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Screw Jack Cable Tension NCS | 2029-01-06 | 2029-01-06 | 6 hrs | FY29 | 12 | 90022222 | B1 | 1000232412 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-SCBTL | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Screw Jack Cable Tension CS | 2029-01-06 | 2029-01-06 | 6 hrs | FY29 | 12 | 90022222 | B1 | 1000232413 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-SCBTR | 6800 | 64569 | 3533
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Rod Support | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 20 | 90022208 | B1 | 1000232419 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-RDSPT | 6800 | 64569 | 13121
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Overhaul Rod Changer Carousel Assy | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 8 | 90029755 | B1 | 1000303720 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-CARAS | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Brkout Wrench & Fork Assy | 2029-01-06 | 2029-01-07 | 20 hrs | FY29 | 38 | 90029873 | B1 | 1000303659 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-TOWER-BOWRH | 6800 | 64569 | 3965
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Yoke Oscillation | 2029-01-06 | 2029-01-06 | 12 hrs | FY29 | 24 | 90011726 | B1 | 1000102869 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -STRUCT-UNDER-YKOSC | 6800 | 64569 | 23653
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Pump Water Injection | 2029-01-06 | 2029-01-06 | 2 hrs | FY29 | 2 | 90011733 | B1 | 1000102876 | 06.01.2029 | 5000 | CCK-MP-DRLL-DR055 -DSTSUP-WTRPP | 6800 | 64569 | 14276
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cabin ADS Components | 2029-01-06 | 2029-01-07 | 31.5 hrs | FY29 | 31.5 | 90029189 | B1 | 1000294217 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-HMIJK | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS Harnesses | 2029-01-06 | 2029-01-11 | 131.5 hrs | FY29 | 131.5 | 90029210 | B1 | 1000294222 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-HARNC | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Deck ADS Elec Hardware | 2029-01-06 | 2029-01-06 | 9.5 hrs | FY29 | 9.5 | 90029190 | B1 | 1000294214 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSHW-ADSMF | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS 3D sensor | 2029-01-06 | 2029-01-06 | 1 hr | FY29 | 1 | 90029207 | B1 | 1000294219 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -ADSYST-ADSPR | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl ADS PTZ Camera & LIDAR | 2029-01-06 | 2029-01-06 | 10 hrs | FY29 | 10 | 90029206 | B1 | 1000294220 | 06.01.2029 | 10000 | CCK-MP-DRLL-DR055 -ADSYST-ADSPR-HTCAM | 6800 | 64593 | 35395
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Mast & A-Frame Harnesses | 2029-01-06 | 2029-01-09 | 70.5 hrs | FY29 | 70.5 | 90030429 | B1 | 1000303721 | 06.01.2029 | 20000 | CCK-MP-DRLL-DR055 -ELCTLV-HARNS-HARCO | 6800 | 64593 | 64593
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Pump Rod Thread Lube | 2029-01-09 | 2029-01-09 | 2 hrs | FY29 | 2 | 90021715 | B1 | 1000305059 | 09.01.2029 | 6000 | CCK-MP-DRLL-DR3138-GRSYST-RTLPP | 5400 | 14414 | 2620
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack RHF NDE CS | 2029-01-15 | 2029-01-15 | 12 hrs | FY29 | 24 | 90030670 | B1 | 1000316717 | 15.01.2029 | 6000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRF | 6700 | 13361 | 8546
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Pump Water Inj | 2029-01-16 | 2029-01-16 | 2 hrs | FY29 | 4 | 90031899 | B1 | 1000315425 | 16.01.2029 | 7500 | CCK-MP-DRLL-DR2113-DSTSUP-WTRPP | 6800 | 33987 | 306
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Hyd Motor Feed | 2029-01-19 | 2029-01-19 | 6 hrs | FY29 | 6 | 90022025 | B1 | 1000361230 | 19.01.2029 | 6000 | CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MFEED | 5400 | 16251 | 10609
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Timing Chain Maintenance | 2029-01-19 | 2029-01-19 | 7 hrs | FY29 | 14 | 90022023 | B1 | 1000361228 | 19.01.2029 | 3000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHP | 5400 | 16251 | 1197
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Feed Chain Sprockets | 2029-01-19 | 2029-01-19 | 12 hrs | FY29 | 24 | 90022030 | B1 | 1000361229 | 19.01.2029 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHS | 5400 | 16251 | 2448
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Hose Drum Sprocket | 2029-01-19 | 2029-01-19 | 6 hrs | FY29 | 6 | 90022032 | B1 | 1000361233 | 19.01.2029 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDHDS | 5400 | 16251 | 16251
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Gearbox Power Head | 2029-01-19 | 2029-01-19 | 16 hrs | FY29 | 32 | 90021707 | B1 | 1000361231 | 19.01.2029 | 6000 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-PWRHD | 5400 | 16251 | 7735
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Water Inj | 2029-01-21 | 2029-01-21 | 2 hrs | FY29 | 4 | 90031899 | B1 | 1000316840 | 21.01.2029 | 7500 | CCK-MP-DRLL-DR2136-DSTSUP-WTRPP | 6700 | 13361 | 1577
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Drive Gearbox | 2029-01-21 | 2029-01-22 | 30 hrs | FY29 | 78 | 90020181 | B1 | 1000316759 | 21.01.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-PMPDG | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Overhaul 24M Air Conditioner | 2029-01-21 | 2029-01-21 | 12 hrs | FY29 | 24 | 90028299 | B1 | 1000283242 | 21.01.2029 | 24 Monthly | CCK-MP-DRLL-DR2129-STRUCT-CABIN-AIRCN | 6800 | 18062 | 18062
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Pump Rod Thread Lube | 2029-01-22 | 2029-01-22 | 2 hrs | FY29 | 2 | 90021715 | B1 | 1000295739 | 22.01.2029 | 6000 | CCK-MP-DRLL-DR3137-GRSYST-RTLPP | 5400 | 14232 | 2559
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 XLF Repl Main Feed Chain | 2029-01-24 | 2029-01-24 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000305041 | 24.01.2029 | 2500 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | 5400 | 14356 | 943
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Engine Valve Set | 2029-01-29 | 2029-01-29 | 8 hrs | FY29 | 16 | 90021723 | B1 | 1000305070 | 29.01.2029 | 3000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Power Pack Module Midlife | 2029-01-29 | 2029-02-01 | 85 hrs | FY29 | 129 | 90026035 | B1 | 1000305071 | 29.01.2029 | 6000 | CCK-MP-DRLL-DR3138-ENGINE | 5400 | 14414 | 3216
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Hyd Motor Feed | 2029-01-29 | 2029-01-29 | 6 hrs | FY29 | 6 | 90022025 | B1 | 1000361319 | 29.01.2029 | 6000 | CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MFEED | 5400 | 14414 | 3216
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Timing Chain Maintenance | 2029-01-29 | 2029-01-29 | 7 hrs | FY29 | 14 | 90022023 | B1 | 1000361317 | 29.01.2029 | 3000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHP | 5400 | 14414 | 7858
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Feed Chain Sprockets | 2029-01-29 | 2029-01-29 | 12 hrs | FY29 | 24 | 90022030 | B1 | 1000361318 | 29.01.2029 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHS | 5400 | 14414 | 7858
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Hose Drum Sprocket | 2029-01-29 | 2029-01-29 | 6 hrs | FY29 | 6 | 90022032 | B1 | 1000361482 | 29.01.2029 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDHDS | 5400 | 14414 | 7858
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Gearbox Power Head | 2029-01-29 | 2029-01-29 | 16 hrs | FY29 | 32 | 90021707 | B1 | 1000361480 | 29.01.2029 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-PWRHD | 5400 | 14414 | 3216
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Auto Lube Pump | 2029-01-29 | 2029-01-29 | 2 hrs | FY29 | 2 | 90016009 | B1 | 1000144923 | 29.01.2029 | 12000 | CCK-MP-DRLL-DR2111-GRSYST-ALBPP | 6800 | 49393 | 5207
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Pump Main Hyd NCS | 2029-02-02 | 2029-02-02 | 6 hrs | FY29 | 6 | 90020235 | B1 | 1000214070 | 02.02.2029 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-MNPP1 | 6800 | 33987 | 12311
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Pump Main Hyd CS | 2029-02-02 | 2029-02-02 | 6 hrs | FY29 | 6 | 90020234 | B1 | 1000214071 | 02.02.2029 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-MNPP2 | 6800 | 33987 | 12311
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Hyd Pump Auxiliary | 2029-02-02 | 2029-02-02 | 4 hrs | FY29 | 4 | 90020236 | B1 | 1000214072 | 02.02.2029 | 15000 | CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-PPAUX | 6800 | 33987 | 12311
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Washdown Pump | 2029-02-18 | 2029-02-18 | 4 hrs | FY29 | 8 | 90030681 | B1 | 1000305734 | 18.02.2029 | 7500 | CCK-MP-DRLL-DR2129-DSTSUP-WSHPP | 6800 | 18062 | 3449
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2029-02-25 | 2029-02-25 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000304876 | 25.02.2029 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 XLF Repl Main Feed Chain | 2029-02-25 | 2029-02-25 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000295065 | 25.02.2029 | 2500 | CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHH | 5400 | 16590 | 3175
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | STAT DR2113 Repl Receiver PRV | 2029-03-04 | 2029-03-04 | 1 hr | FY29 | 1 | 90026270 | B1 | 1000259187 | 04.03.2029 | 48 Monthly | CCK-MP-DRLL-DR2113-AIRSYS-ARTNK | 6800 | 34054 | 3746
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Pump Air Lubrication | 2029-03-04 | 2029-03-04 | 2 hrs | FY29 | 2 | 90021656 | B1 | 1000305047 | 04.03.2029 | 6000 | CCK-MP-DRLL-DR3138-AIRSYS-COMPR-PALUB | 5400 | 14414 | 3216
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Pump Water Injection | 2029-03-04 | 2029-03-04 | 4 hrs | FY29 | 4 | 90021716 | B1 | 1000305049 | 04.03.2029 | 6000 | CCK-MP-DRLL-DR3138-DSTSUP-WTRPP | 5400 | 14414 | 3216
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Operators Seat | 2029-03-04 | 2029-03-04 | 4 hrs | FY29 | 4 | 90021702 | B1 | 1000305045 | 04.03.2029 | 6000 | CCK-MP-DRLL-DR3138-STRUCT-CABIN-SEATS | 5400 | 14414 | 7858
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 XLF Repl Main Feed Chain | 2029-03-08 | 2029-03-08 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000295721 | 08.03.2029 | 2500 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHH | 5400 | 14232 | 1011
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Washdown Pump | 2029-03-10 | 2029-03-10 | 4 hrs | FY29 | 8 | 90030681 | B1 | 1000316836 | 10.03.2029 | 7500 | CCK-MP-DRLL-DR2136-DSTSUP-WSHPP | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl Washdown Pump | 2029-03-10 | 2029-03-10 | 4 hrs | FY29 | 8 | 90030681 | B1 | 1000305724 | 10.03.2029 | 7500 | CCK-MP-DRLL-DR2113-DSTSUP-WSHPP | 6800 | 33987 | 9462
MD6310 | Onsite PM | Drills | Fortescue | DR2113 | DR2113 Repl ADS Vibration Sensors | 2029-03-10 | 2029-03-10 | 1 hr | FY29 | 1 | 90029062 | B1 | 1000290898 | 10.03.2029 | 10000 | CCK-MP-DRLL-DR2113-ADSYST-ADSIS-DSVSN | 6800 | 34008 | 34008
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Cables & Hoses | 2029-03-10 | 2029-03-12 | 50 hrs | FY29 | 100 | 90029843 | B1 | 1000303753 | 10.03.2029 | 5000 | CCK-MP-DRLL-DR2110-STRUCT-TOWER | 6800 | 54883 | 5228
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 XLF Repl Main Feed Chain | 2029-03-15 | 2029-03-15 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000295025 | 15.03.2029 | 2500 | CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHH | 5400 | 16251 | 1197
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Auto lube Pump Safety Valve | 2029-03-21 | 2029-03-21 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295716 | 21.03.2029 | 2000 | CCK-MP-DRLL-DR3137-GRSYST-ALPSV | 5400 | 14232 | 8625
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Power Pack Quarter Life | 2029-03-24 | 2029-03-26 | 44 hrs | FY29 | 68 | 90029574 | B1 | 1000295329 | 24.03.2029 | 5000 | CCK-MP-DRLL-DR2110-ENGINE | 6800 | 54907 | 5228
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS Vibration Sensors | 2029-03-26 | 2029-03-26 | 1 hr | FY29 | 1 | 90029062 | B1 | 1000316820 | 26.03.2029 | 10000 | CCK-MP-DRLL-DR2136-ADSYST-ADSIS-DSVSN | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS GPS Components | 2029-03-26 | 2029-03-26 | 3 hrs | FY29 | 3 | 90029061 | B1 | 1000316821 | 26.03.2029 | 30000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPO | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl ADS LiDAR | 2029-03-26 | 2029-03-26 | 4 hrs | FY29 | 4 | 90029065 | B1 | 1000316824 | 26.03.2029 | 5000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hydraulic Cooler Module | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90020220 | B1 | 1000316765 | 26.03.2029 | 30000 | CCK-MP-DRLL-DR2136-COOLER | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Primary Water Tank Anodes | 2029-03-26 | 2029-03-26 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377553 | 26.03.2029 | 10000 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKP | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Secondary Water Tank Anodes | 2029-03-26 | 2029-03-26 | 8 hrs | FY29 | 8 | 90037834 | B1 | 1000377484 | 26.03.2029 | 10000 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cab Harnesses | 2029-03-26 | 2029-03-26 | 14 hrs | FY29 | 14 | 90028947 | B1 | 1000316811 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Chassis Harnesses | 2029-03-26 | 2029-03-30 | 104 hrs | FY29 | 208 | 90028944 | B1 | 1000316810 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Battery Cables | 2029-03-26 | 2029-03-27 | 24 hrs | FY29 | 24 | 90028942 | B1 | 1000316809 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Compressor Harnesses | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 12 | 90028948 | B1 | 1000316812 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Mast Harnesses | 2029-03-26 | 2029-03-28 | 56 hrs | FY29 | 112 | 90028949 | B1 | 1000316813 | 26.03.2029 | 30000 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Radiator Cooler Module | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90021617 | B1 | 1000316766 | 26.03.2029 | 30000 | CCK-MP-DRLL-DR2136-ENGINE-COSYS-RADTR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack LHR DE NCS | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90020204 | B1 | 1000316716 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cylinder Jack RHR DE CS | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90030672 | B1 | 1000316718 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cyl Mast Locking NCS | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90020197 | B1 | 1000316740 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYL | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cyl Mast Locking CS | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90030657 | B1 | 1000316719 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Cyl Mast Raise CS | 2029-03-26 | 2029-03-26 | 16 hrs | FY29 | 32 | 90020198 | B1 | 1000316741 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MRCYR | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Pump Fan Oil Cooler LH | 2029-03-26 | 2029-03-26 | 2 hrs | FY29 | 2 | 90020239 | B1 | 1000316761 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP1 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Pump Fan Engine Cool RH | 2029-03-26 | 2029-03-26 | 2 hrs | FY29 | 2 | 90020240 | B1 | 1000316762 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP2 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Main Hyd NCS | 2029-03-26 | 2029-03-26 | 6 hrs | FY29 | 6 | 90020235 | B1 | 1000316763 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP1 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Main Hyd CS | 2029-03-26 | 2029-03-26 | 6 hrs | FY29 | 6 | 90020234 | B1 | 1000316764 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP2 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Pump Charge | 2029-03-26 | 2029-03-26 | 2 hrs | FY29 | 2 | 90020232 | B1 | 1000316758 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP3 | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Hyd Pump Auxiliary | 2029-03-26 | 2029-03-26 | 4 hrs | FY29 | 4 | 90020236 | B1 | 1000316757 | 26.03.2029 | 15000 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-PPAUX | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Mast Module Qtr Life | 2029-03-26 | 2029-03-30 | 93 hrs | FY29 | 201 | 90030335 | B1 | 1000316827 | 26.03.2029 | 10000 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Sprocket LH | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90020186 | B1 | 1000316748 | 26.03.2029 | 10000 | CCK-MP-DRLL-DR2136-TRAVEL-SPRKL | 6700 | 13361 | 4373
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Sprocket RH | 2029-03-26 | 2029-03-26 | 12 hrs | FY29 | 24 | 90020186 | B1 | 1000316750 | 26.03.2029 | 10000 | CCK-MP-DRLL-DR2136-TRAVEL-SPRKR | 6700 | 13361 | 4130
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump | 2029-03-26 | 2029-03-26 | 2 hrs | FY29 | 2 | 90020875 | B1 | 1000295059 | 26.03.2029 | 8000 | CCK-MP-DRLL-DR3134-GRSYST-ALBPP | 5400 | 16590 | 970
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Auto lube Pump Safety Valve | 2029-03-26 | 2029-03-26 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295060 | 26.03.2029 | 2000 | CCK-MP-DRLL-DR3134-GRSYST-ALPSV | 5400 | 16590 | 5065
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 Repl Cyl Jack Leg NDE CS | 2029-04-07 | 2029-04-07 | 4 hrs | FY29 | 8 | 90015957 | B1 | 1000144794 | 07.04.2029 | 15000 | CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYRF | 6800 | 54883 | 9679
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Pump Air Lubrication | 2029-04-11 | 2029-04-11 | 2 hrs | FY29 | 2 | 90021656 | B1 | 1000295727 | 11.04.2029 | 6000 | CCK-MP-DRLL-DR3137-AIRSYS-COMPR-PALUB | 5400 | 14232 | 8625
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Operators Seat | 2029-04-11 | 2029-04-11 | 4 hrs | FY29 | 4 | 90021702 | B1 | 1000295725 | 11.04.2029 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-CABIN-SEATS | 5400 | 14232 | 4056
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Mast Cables | 2029-04-16 | 2029-04-17 | 32 hrs | FY29 | 64 | 90030334 | B1 | 1000302804 | 16.04.2029 | 2500 | CCK-MP-DRLL-DR2129-STRUCT-DMAST | 6800 | 18062 | 4985
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump | 2029-04-16 | 2029-04-16 | 2 hrs | FY29 | 2 | 90020875 | B1 | 1000304875 | 16.04.2029 | 8000 | CCK-MP-DRLL-DR3138-GRSYST-ALBPP | 5400 | 14414 | 14414
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Adjust 3750Hr Valve Set | 2029-04-21 | 2029-04-21 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000278372 | 21.04.2029 | 3750 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Engine Midlife Complete | 2029-04-21 | 2029-04-22 | 36 hrs | FY29 | 54 | 90029233 | B1 | 1000293345 | 21.04.2029 | 7500 | CCK-MP-DRLL-DR2129-ENGINE | 6800 | 18158 | 3449
PV271 | Onsite PM | Drills | Fortescue | DR055 | DR055 Repl Cyl Jack Leg DE NCS | 2029-04-26 | 2029-04-26 | 11 hrs | FY29 | 15 | 90011673 | B1 | 1000102827 | 26.04.2029 | 15000 | CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYLR | 6800 | 64569 | 11474
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Drive Shaft Pump Drive | 2029-04-27 | 2029-04-27 | 6 hrs | FY29 | 12 | 90028862 | B1 | 1000287873 | 27.04.2029 | 5000 | CCK-MP-DRLL-DR2112-HYDSYS-PMPDG-DRSHT | 6800 | 34249 | 2406
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 EncoderHarness Cab to Aframe Repl | 2029-04-27 | 2029-04-27 | 6 hrs | FY29 | 6 | 90036144 | B1 | 1000365254 | 27.04.2029 | 5000 | CCK-MP-DRLL-DR2111-ADSYST-HARNC | 6800 | 49417 | 4564
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Raise NCS | 2029-04-29 | 2029-04-29 | 4 hrs | FY29 | 8 | 90011666 | B1 | 1000233276 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYL | 6800 | 49393 | 8364
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Tower Raise CS | 2029-04-29 | 2029-04-29 | 4 hrs | FY29 | 8 | 90011667 | B1 | 1000233275 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYR | 6800 | 49393 | 8364
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Hyd Motor Screw Jack NCS | 2029-04-29 | 2029-04-29 | 1 hr | FY29 | 1 | 90022221 | B1 | 1000232742 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTL | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Hyd Motor Screw Jack CS | 2029-04-29 | 2029-04-29 | 1 hr | FY29 | 1 | 90022221 | B1 | 1000232741 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTR | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Sheaves & Cables | 2029-04-29 | 2029-05-02 | 70 hrs | FY29 | 140 | 90029857 | B1 | 1000303761 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Tower Cylinders | 2029-04-29 | 2029-04-30 | 34 hrs | FY29 | 58 | 90029866 | B1 | 1000303763 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Grbx Powerhead Midlife | 2029-04-29 | 2029-04-29 | 6 hrs | FY29 | 6 | 90029861 | B1 | 1000303762 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-PWRHD | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Rod Support | 2029-04-29 | 2029-04-29 | 8 hrs | FY29 | 20 | 90022208 | B1 | 1000232732 | 29.04.2029 | 10000 | CCK-MP-DRLL-DR2111-STRUCT-TOWER-RDSPT | 6800 | 49393 | 8353
PV271 | Onsite PM | Drills | Fortescue | DR2110 | DR2110 EncoderHarness Cab to Aframe Repl | 2029-04-29 | 2029-04-29 | 6 hrs | FY29 | 6 | 90036144 | B1 | 1000365253 | 29.04.2029 | 5000 | CCK-MP-DRLL-DR2110-ADSYST-HARNC | 6800 | 54907 | 14230
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Repl Fish Eye Camera | 2029-05-03 | 2029-05-03 | 16 hrs | FY29 | 16 | 90029067 | B1 | 1000316823 | 03.05.2029 | 10000 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-HTCAM | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2128 | DR2128 Adjust 3750Hr Valve Set | 2029-05-07 | 2029-05-07 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000278184 | 07.05.2029 | 3750 | CCK-MP-DRLL-DR2128-ENGINE | 6800 | 21646 | 3367
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Engine Valve Set | 2029-05-07 | 2029-05-07 | 8 hrs | FY29 | 16 | 90021723 | B1 | 1000295750 | 07.05.2029 | 3000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Power Pack Module Midlife | 2029-05-07 | 2029-05-10 | 85 hrs | FY29 | 129 | 90026035 | B1 | 1000295751 | 07.05.2029 | 6000 | CCK-MP-DRLL-DR3137-ENGINE | 5400 | 14232 | 2835
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Hyd Motor Feed | 2029-05-07 | 2029-05-07 | 6 hrs | FY29 | 6 | 90022025 | B1 | 1000361312 | 07.05.2029 | 6000 | CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MFEED | 5400 | 14232 | 4926
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Timing Chain Maintenance | 2029-05-07 | 2029-05-07 | 7 hrs | FY29 | 14 | 90022023 | B1 | 1000361310 | 07.05.2029 | 3000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHP | 5400 | 14232 | 14232
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Feed Chain Sprockets | 2029-05-07 | 2029-05-07 | 12 hrs | FY29 | 24 | 90022030 | B1 | 1000361311 | 07.05.2029 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHS | 5400 | 14232 | 8625
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Hose Drum Sprocket | 2029-05-07 | 2029-05-07 | 6 hrs | FY29 | 6 | 90022032 | B1 | 1000361315 | 07.05.2029 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDHDS | 5400 | 14232 | 8625
D65 | Onsite PM | Drills | Fortescue | DR3137 | DR3137 Repl Gearbox Power Head | 2029-05-07 | 2029-05-07 | 16 hrs | FY29 | 32 | 90021707 | B1 | 1000361313 | 07.05.2029 | 6000 | CCK-MP-DRLL-DR3137-STRUCT-BOOMS-PWRHD | 5400 | 14232 | 7186
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump | 2029-05-08 | 2029-05-08 | 2 hrs | FY29 | 2 | 90020875 | B1 | 1000294979 | 08.05.2029 | 8000 | CCK-MP-DRLL-DR3133-GRSYST-ALBPP | 5400 | 16251 | 8583
D65 | Onsite PM | Drills | Fortescue | DR3133 | DR3133 Repl Auto lube Pump Safety Valve | 2029-05-08 | 2029-05-08 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000295020 | 08.05.2029 | 2000 | CCK-MP-DRLL-DR3133-GRSYST-ALPSV | 5400 | 16251 | 4587
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Adjust 3750Hr Valve Set | 2029-05-12 | 2029-05-12 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000316745 | 12.05.2029 | 3750 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Engine Midlife Complete | 2029-05-12 | 2029-05-13 | 36 hrs | FY29 | 54 | 90029233 | B1 | 1000316746 | 12.05.2029 | 7500 | CCK-MP-DRLL-DR2136-ENGINE | 6700 | 13361 | 8815
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | DR2136 Service 12M Air Conditioner | 2029-05-12 | 2029-05-12 | 6 hrs | FY29 | 12 | 90028298 | B1 | 1000316807 | 12.05.2029 | 12 Monthly | CCK-MP-DRLL-DR2136-STRUCT-CABIN-AIRCN | 6700 | 13361 | 13361
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Adjust 3750Hr Valve Set | 2029-05-20 | 2029-05-20 | 12 hrs | FY29 | 24 | 90020402 | B1 | 1000213713 | 20.05.2029 | 3750 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Engine Midlife Complete | 2029-05-20 | 2029-05-21 | 36 hrs | FY29 | 54 | 90029233 | B1 | 1000293338 | 20.05.2029 | 7500 | CCK-MP-DRLL-DR2112-ENGINE | 6800 | 34249 | 1582
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Battery Cables | 2029-05-24 | 2029-05-25 | 24 hrs | FY29 | 24 | 90028942 | B1 | 1000289036 | 24.05.2029 | 15000 | CCK-MP-DRLL-DR2129-ELCTLV-HARNS | 6800 | 18062 | 18062
MD6310 | Onsite PM | Drills | Fortescue | DR2129 | DR2129 Repl Final Drive & Sprocket RH | 2029-05-31 | 2029-05-31 | 14 hrs | FY29 | 26 | 90020182 | B1 | 1000278377 | 31.05.2029 | 20000 | CCK-MP-DRLL-DR2129-TRAVEL-FDRRH | 6800 | 18062 | 18062
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Power Pack Quarter Life | 2029-06-02 | 2029-06-04 | 44 hrs | FY29 | 68 | 90029574 | B1 | 1000295333 | 02.06.2029 | 5000 | CCK-MP-DRLL-DR2111-ENGINE | 6800 | 49411 | 11797
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Fish Eye Camera | 2029-06-05 | 2029-06-05 | 16 hrs | FY29 | 16 | 90029067 | B1 | 1000290889 | 05.06.2029 | 10000 | CCK-MP-DRLL-DR2112-ADSYST-ADSPR-HTCAM | 6800 | 34252 | 34252
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Engine Valve Set | 2029-06-05 | 2029-06-05 | 8 hrs | FY29 | 16 | 90021723 | B1 | 1000295094 | 05.06.2029 | 3000 | CCK-MP-DRLL-DR3134-ENGINE | 5400 | 16590 | 5149
MD6310 | Onsite PM | Drills | Fortescue | DR2112 | DR2112 Repl Mast Cables | 2029-06-16 | 2029-06-17 | 32 hrs | FY29 | 64 | 90030334 | B1 | 1000302720 | 16.06.2029 | 2500 | CCK-MP-DRLL-DR2112-STRUCT-DMAST | 6800 | 34249 | 7732
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Valve Dual Counter Balance | 2029-06-16 | 2029-06-16 | 2 hrs | FY29 | 2 | 90015975 | B1 | 1000144888 | 16.06.2029 | 10000 | CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDCB | 6800 | 49393 | 16543
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl ADS PTZ Camera & LIDAR | 2029-06-16 | 2029-06-16 | 10 hrs | FY29 | 10 | 90029206 | B1 | 1000294211 | 16.06.2029 | 10000 | CCK-MP-DRLL-DR2111-ADSYST-ADSPR-HTCAM | 6800 | 49417 | 19408
PV271 | Onsite PM | Drills | Fortescue | DR2111 | DR2111 Repl Cyl Jack Leg DE CS | 2029-06-18 | 2029-06-18 | 4 hrs | FY29 | 8 | 90015959 | B1 | 1000144881 | 18.06.2029 | 15000 | CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYRR | 6800 | 49393 | 8373
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 XLF Repl Main Feed Chain | 2029-06-25 | 2029-06-25 | 8 hrs | FY29 | 16 | 90021711 | B1 | 1000305041 | 25.06.2029 | 2500 | CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | 5400 | 14356 | 943
D65 | Onsite PM | Drills | Fortescue | DR3138 | DR3138 Repl Auto lube Pump Safety Valve | 2029-06-27 | 2029-06-27 | 1 hr | FY29 | 1 | 90020876 | B1 | 1000304876 | 27.06.2029 | 2000 | CCK-MP-DRLL-DR3138-GRSYST-ALPSV | 5400 | 14414 | 2291
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Cylinder Oscillation LH | 2029-06-29 | 2029-06-29 | 4 hrs | FY29 | 8 | 90021662 | B1 | 1000295063 | 29.06.2029 | 12000 | CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-TFCOL | 5400 | 16590 | 7605
D65 | Onsite PM | Drills | Fortescue | DR3134 | DR3134 Repl Cylinder Oscillation RH | 2029-06-29 | 2029-06-29 | 4 hrs | FY29 | 8 | 90021663 | B1 | 1000295064 | 29.06.2029 | 12000 | CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-TFCOR | 5400 | 16590 | 7605
| Onsite PM | Haul | Fortescue |  | HAUL - COMPONENTS DURING PM
| Onsite PM | Haul | Fortescue |  | FY27 - HAUL - COMPONENTS DURING PM | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Haul | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-06-30 |  | FY27
| Onsite PM | Haul | Fortescue | MOC | JULY | 2026-07-01 | 2026-07-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793 Cab Replacements | 2026-07-01 | 2026-07-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E HV Cabinet Replacement | 2026-07-01 | 2026-07-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2026-07-01 | 2026-07-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2026-07-01 | 2026-07-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Boarding Ladders | 2026-07-01 | 2026-07-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2026-07-01 | 2026-07-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Hangup Plates | 2026-07-01 | 2026-07-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Intake Chutes | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Reline Kits | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Relines Labour | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2026-07-01 | 2026-07-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2026-07-01 | 2026-07-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2026-07-01 | 2026-07-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Grid Box Replacement | 2026-08-01 | 2026-08-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2026-08-01 | 2026-08-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Cyl Hoist - MSR Strategy On Condition | 2026-08-01 | 2026-08-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2026-08-01 | 2026-08-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2026-08-01 | 2026-08-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2026-08-01 | 2026-08-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | IMU Replacement - BER Planning | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacement - BER Planning | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | PCS Replacement - BER Planning | 2026-09-01 | 2026-09-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793 Cab Replacements | 2026-09-01 | 2026-09-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2026-09-01 | 2026-09-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Hangup Plates | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2026-09-01 | 2026-09-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2026-09-01 | 2026-09-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Haul | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E HV Cabinet Replacement | 2026-10-01 | 2026-10-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2026-10-01 | 2026-10-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2026-10-01 | 2026-10-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Boarding Ladders | 2026-10-01 | 2026-10-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2026-10-01 | 2026-10-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Intake Chutes | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Reline Kits | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Relines Labour | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2026-10-01 | 2026-10-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2026-10-01 | 2026-10-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2026-10-01 | 2026-10-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793 Cab Replacements | 2026-11-01 | 2026-11-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Grid Box Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2026-11-01 | 2026-11-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2026-11-01 | 2026-11-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Hangup Plates | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2026-11-01 | 2026-11-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2026-11-01 | 2026-11-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2026-11-01 | 2026-11-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2026-11-01 | 2026-11-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Haul | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | IMU Replacement - BER Planning | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacement - BER Planning | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | PCS Replacement - BER Planning | 2026-12-01 | 2026-12-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2026-12-01 | 2026-12-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2026-12-01 | 2026-12-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
Panther 450T | Onsite PM | Haul | Fortescue | All - Haul | 450T Float RARS Bearings | 2027-01-01 | 2027-01-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793 Cab Replacements | 2027-01-01 | 2027-01-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E HV Cabinet Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2027-01-01 | 2027-01-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2027-01-01 | 2027-01-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Boarding Ladders | 2027-01-01 | 2027-01-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2027-01-01 | 2027-01-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Hangup Plates | 2027-01-01 | 2027-01-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Intake Chutes | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Reline Kits | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Relines Labour | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2027-01-01 | 2027-01-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2027-01-01 | 2027-01-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Grid Box Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2027-02-01 | 2027-02-28 | 27 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2027-02-01 | 2027-02-28 | 27 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Haul | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | IMU Replacement - BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacement - BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | PCS Replacement - BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2027-03-01 | 2027-03-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2027-03-01 | 2027-03-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2027-03-01 | 2027-03-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E HV Cabinet Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Boarding Ladders | 2027-04-01 | 2027-04-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2027-04-01 | 2027-04-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Intake Chutes | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Reline Kits | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Tray Relines Labour | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2027-04-01 | 2027-04-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2027-04-01 | 2027-04-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Haul | Fortescue | MOC | MAY | 2027-05-01 | 2027-05-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793 Cab Replacements | 2027-05-01 | 2027-05-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Grid Box Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Valve Hoist - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2027-05-01 | 2027-05-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2027-05-01 | 2027-05-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2027-05-01 | 2027-05-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | JUNE | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | IMU Replacement - BER Planning | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacement - BER Planning | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | PCS Replacement - BER Planning | 2027-06-01 | 2027-06-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Repl Nose Cone - MSR Strategy On Condition | 2027-06-01 | 2027-06-30 | 29 days | FY27
930E | Onsite PM | Haul | Fortescue | All - 930E | 930E Gridbox Handrails | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | FSI Lite Systems | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | GPS 90-degree connectors | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Wifi and GPS cable rollout | 2027-06-01 | 2027-06-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | Zephyr 3 Upgrades | 2027-06-01 | 2027-06-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Operator Seat - MSR Strategy On Condition | 2027-06-01 | 2027-06-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Repl Pump Towing - MSR Strategy On Condition | 2027-06-01 | 2027-07-01 | 30 days | FY27
793F | Onsite PM | Haul | Fortescue | All - 793F | 793F Reseal Tank Hyd & Steering - MSR Strategy On Condition | 2027-06-01 | 2027-06-30 | 29 days | FY27
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Wheel Group Front RH | 2026-07-02 | 2026-07-03 | 28 hrs | FY27 | 54 | 90017287 | B1 | 1000157217 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRUCT-AXLES-HUBRH | 7400 | 83804 | 642
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Replace Operator Cabin Dash Bulbs | 2026-07-03 | 2026-07-03 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158221 | 28.06.2026 | 3000 | CCK-MP-HAUL-DT756 -STRUCT-CABIN | 6800 | 78754 | 78754
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Air Con Service & Overhaul | 2026-07-03 | 2026-07-04 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110625 | 13.04.2026 | 12 Monthly | CCK-MP-HAUL-DT756 -STRUCT-CABIN-AIRCN | 6800 | 78754 | 19465
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Repl Bulk Grease Tank Breather | 2026-07-03 | 2026-07-03 | 1 hr | FY27 | 1 | 90022533 | B1 | 1000236909 | 03.07.2026 | 6 Monthly | CCK-MP-SUPP-SV220 -GRSYST-GRTNK | 5100 | 58259 | 58259
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Wheel End RH | 2026-07-26 | 2026-07-27 | 32.5 hrs | FY27 | 58.5 | 90007352 | B1 | 1000026407 | 05.01.2027 | 24000 | CCK-MP-HAUL-DT150 -FDRSYS-FDRVE-FDRRH | 7400 | 86656 | 20534
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Operator Cabin Dash Bulbs | 2026-07-27 | 2026-07-27 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158218 | 10.07.2026 | 3000 | CCK-MP-HAUL-DT753 -STRUCT-CABIN | 6800 | 85999 | 22050
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Tyre Sense Battery | 2026-07-28 | 2026-07-28 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153118 | 12.04.2026 | 24 Monthly | CCK-MP-HAUL-DT086 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Suspension LHF | 2026-07-28 | 2026-07-30 | 60 hrs | FY27 | 112 | 90011365 | B1 | 1000094407 | 10.07.2027 | 18000 | CCK-MP-HAUL-DT753 -STRUCT-SUSPN-SCYLF | 6800 | 85999 | 93
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Service Air Conditioner 12M | 2026-07-28 | 2026-07-29 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174166 | 29.08.2026 | 12 Monthly | CCK-MP-HAUL-DT127 -STRUCT-CABIN-AIRCN | 7400 | 83059 | 27545
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Operators Seat | 2026-07-28 | 2026-07-28 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000025071 | 31.07.2026 | 15000 | CCK-MP-HAUL-DT127 -STRUCT-CABIN-SEATS | 7400 | 83059 | 0
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Motor Lube Axle Hoses | 2026-07-28 | 2026-07-28 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272012 | 04.07.2026 | 12000 | CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYM01 | 7400 | 83108 | 0
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl AOC Fan Motor Rear | 2026-07-28 | 2026-07-28 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000026145 | 04.07.2026 | 12000 | CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYM02 | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Tyre Sense Battery | 2026-07-28 | 2026-07-28 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153158 | 14.03.2026 | 24 Monthly | CCK-MP-HAUL-DT146 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Spider Trans Driveshaft | 2026-07-28 | 2026-07-28 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154970 | 04.07.2026 | 6000 | CCK-MP-HAUL-DT146 -FDRSYS-DRSHT-UNVSL | 7400 | 83062 | 26
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Cyl Steering RH | 2026-07-30 | 2026-07-30 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000128118 | 27.02.2027 | 15000 | CCK-MP-HAUL-DT223 -STRSYS-STRCY-STCYR | 7400 | 54920 | 10976
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Operators Seat | 2026-07-30 | 2026-07-30 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000026765 | 02.09.2026 | 15000 | CCK-MP-HAUL-DT155 -STRUCT-CABIN-SEATS | 7400 | 81407 | 42
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Replace Hoses Hoist System | 2026-07-31 | 2026-08-01 | 20 hrs | FY27 | 40 | 90010105 | B1 | 1000083434 | 08.03.2026 | 24000 | CCK-MP-HAUL-DT150 -HYDSYS-HDHLF-HSTHO | 7400 | 86608 | 0
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Replace Brake Cooling Hoses | 2026-07-31 | 2026-07-31 | 8.5 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223879 | 25.12.2025 | 25000 | CCK-MP-HAUL-DT759 -BRKSYS-BRHLF | 6800 | 79716 | 28650
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Sepura SCC Microphone | 2026-07-31 | 2026-07-31 | 0.5 hrs | FY27 | 0.5 | 90029001 | B1 | 1000289628 | 14.08.2026 | 12 Monthly | CCK-MP-SUPP-WC3111-COMMUN-RADIO | 5600 | 51257 | 51257
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Steering Link & Arm Rebush | 2026-07-31 | 2026-07-31 | 14 hrs | FY27 | 22 | 90004007 | B2 | 1000079206 | 17.08.2026 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STLTR | 5600 | 51257 | 14617
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Steering Cylinder LH | 2026-07-31 | 2026-07-31 | 10 hrs | FY27 | 18 | 90004005 | B2 | 1000079204 | 17.08.2026 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STRCY-STCYL | 5600 | 51257 | 14617
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Steering RH | 2026-08-01 | 2026-08-01 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000026421 | 11.04.2026 | 15000 | CCK-MP-HAUL-DT150 -STRSYS-STRCY-STCYR | 7400 | 86608 | 0
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Brake Accumulator | 2026-08-01 | 2026-08-01 | 4 hrs | FY27 | 4 | 90004001 | B2 | 1000079198 | 17.08.2026 | 15000 | CCK-MP-SUPP-WC3111-BRKSYS-BACCM | 5500 | 14617 | 14617
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Steering Pump | 2026-08-01 | 2026-08-01 | 4 hrs | FY27 | 4 | 90004003 | B2 | 1000079202 | 17.08.2026 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STPMP | 5600 | 51257 | 14617
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Air Drier and Tank | 2026-08-01 | 2026-08-01 | 12 hrs | FY27 | 24 | 90004010 | B2 | 1000079211 | 05.09.2026 | 9000 | CCK-MP-SUPP-WC3111-PNEUMC-AIRDR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl PTO Uni's & Driveshaft | 2026-08-02 | 2026-08-02 | 2 hrs | FY27 | 2 | 90031094 | B1 | 1000307814 | 17.08.2026 | 10000 | CCK-MP-SUPP-WC3111-ENGINE-PMPDR-DRSHT | 5600 | 51257 | 9904
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Steering Oil Cooler | 2026-08-02 | 2026-08-02 | 3 hrs | FY27 | 3 | 90004006 | B2 | 1000079207 | 17.08.2026 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STOLC | 5600 | 51257 | 14617
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Service Air Conditioner 12M | 2026-08-03 | 2026-08-04 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174172 | 13.09.2026 | 12 Monthly | CCK-MP-HAUL-DT140 -STRUCT-CABIN-AIRCN | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Tyre Sense Battery | 2026-08-03 | 2026-08-03 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153174 | 12.04.2026 | 24 Monthly | CCK-MP-HAUL-DT5202-MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Motor Lube Axle Hoses | 2026-08-03 | 2026-08-03 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272046 | 23.05.2026 | 12000 | CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYM01 | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl AOC Fan Motor Rear | 2026-08-03 | 2026-08-03 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000111925 | 23.05.2026 | 12000 | CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYM02 | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Front Wheel Bearings RH | 2026-08-03 | 2026-08-04 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157276 | 25.07.2026 | 16000 | CCK-MP-HAUL-DT5202-STRUCT-AXLES-FWBRH | 7400 | 84333 | 15833
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Pump Brake Right | 2026-08-04 | 2026-08-04 | 6 hrs | FY27 | 12 | 90026966 | B1 | 1000272838 | 09.03.2027 | 18000 | CCK-MP-SUPP-LL0007-BRKSYS-BRPMP-BRP02 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Motor Hyd Pump Right | 2026-08-04 | 2026-08-04 | 4 hrs | FY27 | 8 | 90026976 | B1 | 1000272846 | 11.05.2025 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HDMOT-MOT02 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Pump Hydraulic Main Left | 2026-08-04 | 2026-08-04 | 4 hrs | FY27 | 8 | 90026977 | B1 | 1000272847 | 11.05.2025 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HYDPP-HYP01 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Pump Hydraulic Main Right | 2026-08-04 | 2026-08-04 | 4 hrs | FY27 | 8 | 90026977 | B1 | 1000272848 | 11.05.2025 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HYDPP-HYP02 | 3400 | 15216 | 15216
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Motor Lube Axle Rear & Hoses | 2026-08-04 | 2026-08-04 | 8 hrs | FY27 | 8 | 90026943 | B1 | 1000286276 | 09.04.2026 | 24000 | CCK-MP-SUPP-PM0001-FDRSYS-AXLEC-HYM01 | 3400 | 48287 | 48287
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Inspect Rear Axle Housing | 2026-08-04 | 2026-08-04 | 1 hr | FY27 | 1 | 90019256 | B1 | 1000196434 | 28.07.2026 | 2000 | CCK-MP-SUPP-WC224 -STRUCT-RAXHO | 5000 | 71088 | 71088
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Operator Seat | 2026-08-04 | 2026-08-04 | 3 hrs | FY27 | 6 | 90011567 | B1 | 1000098152 | 04.08.2026 | 6000 | CCK-MP-SUPP-SV220 -STRUCT-CABIN-SEATS | 5100 | 58259 | 5249
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Cyl Steering LH | 2026-08-06 | 2026-08-06 | 10 hrs | FY27 | 16 | 90011350 | B1 | 1000095027 | 11.07.2026 | 15000 | CCK-MP-HAUL-DT765 -STRSYS-STRCY-STCYL | 6800 | 78429 | 10743
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Air Conditioner 12M-Service | 2026-08-06 | 2026-08-07 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000272732 | 02.06.2026 | 12 Monthly | CCK-MP-SUPP-PM0001-STRUCT-CABIN-AIRCN | 3400 | 48287 | 48287
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 789C AHS Replace Proactive Coax | 2026-08-08 | 2026-08-08 | 12 hrs | FY27 | 12 | 90022477 | B2 | 1000235591 | 13.07.2026 | 24 Monthly | CCK-MP-SUPP-WC224 -COMMUN-FLMGT
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Steering Linkages | 2026-08-10 | 2026-08-10 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317671 | 01.08.2026 | 15000 | CCK-MP-HAUL-DT5316-STRSYS-STLTR | 7400 | 45108 | 30055
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Auto Lube Pump | 2026-08-10 | 2026-08-10 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285808 | 17.08.2026 | 8000 | CCK-MP-HAUL-DT5316-GRSYST-ALBPP | 7400 | 45108 | 45108
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Service Air Conditioner 12M | 2026-08-10 | 2026-08-11 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000172996 | 12.09.2026 | 12 Monthly | CCK-MP-HAUL-DT5316-STRUCT-CABIN-AIRCN | 7400 | 45108 | 45108
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Drive Shaft Transmission | 2026-08-10 | 2026-08-10 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154997 | 10.07.2026 | 18000 | CCK-MP-HAUL-DT221 -FDRSYS-DRSHT | 7400 | 57237 | 17825
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Steering Bell Crank & Links | 2026-08-10 | 2026-08-11 | 20 hrs | FY27 | 36 | 90028566 | B1 | 1000317656 | 27.07.2026 | 30000 | CCK-MP-HAUL-DT221 -STRSYS-STLTR-STLAC | 7400 | 57237 | 30334
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Tyre Sense Battery | 2026-08-10 | 2026-08-10 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153167 | 17.08.2026 | 24 Monthly | CCK-MP-HAUL-DT158 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Motor Lube Axle Hoses | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272030 | 25.09.2026 | 12000 | CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYM01 | 7400 | 85964 | 11104
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Operator Cabin Dash Bulbs | 2026-08-10 | 2026-08-10 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158234 | 27.08.2026 | 3000 | CCK-MP-HAUL-DT769 -STRUCT-CABIN | 6800 | 80508 | 80508
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Auto Lube Pump | 2026-08-10 | 2026-08-10 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095249 | 08.09.2026 | 8000 | CCK-MP-HAUL-DT769 -GRSYST-ALBPP | 6800 | 80508 | 7418
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Transmisson Calibration | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298732 | 10.07.2026 | 4500 | CCK-MP-HAUL-DT151 -TRNSYS-TRANS | 7400 | 84253 | 9530
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Transmission Oil Cooler | 2026-08-10 | 2026-08-10 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000083069 | 11.06.2026 | 18000 | CCK-MP-HAUL-DT100 -TRNSYS-TROLC | 7400 | 87135 | 19314
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Radiator Fan Hoses | 2026-08-10 | 2026-08-10 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307497 | 03.07.2026 | 12000 | CCK-MP-HAUL-DT100 -ENGINE-COSYS-RADTR | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Transmisson Calibration | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298676 | 10.07.2026 | 4500 | CCK-MP-HAUL-DT100 -TRNSYS-TRANS | 7400 | 87135 | 5195
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Drive Shaft Transmission | 2026-08-10 | 2026-08-10 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154949 | 10.08.2026 | 18000 | CCK-MP-HAUL-DT100 -FDRSYS-DRSHT | 7400 | 87135 | 17914
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Motor Lube Axle Hoses | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000271990 | 03.07.2026 | 12000 | CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYM01 | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl AOC Fan Motor Rear | 2026-08-10 | 2026-08-10 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000024920 | 03.07.2026 | 12000 | CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYM02 | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Tyre Sense Battery | 2026-08-10 | 2026-08-10 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153147 | 19.08.2026 | 24 Monthly | CCK-MP-HAUL-DT100 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Suspension LHR | 2026-08-10 | 2026-08-11 | 22 hrs | FY27 | 39 | 90002409 | B1 | 1000024953 | 09.10.2027 | 28000 | CCK-MP-HAUL-DT100 -STRUCT-SUSPN-SCYLR | 7400 | 87135 | 19314
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Brake Dual Relay Valves | 2026-08-10 | 2026-08-10 | 8.5 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223769 | 30.04.2026 | 25000 | CCK-MP-HAUL-DT769 -BRKSYS-BRVRL | 6800 | 80508 | 26878
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Brake Cabinet Hoses | 2026-08-10 | 2026-08-11 | 32.5 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126516 | 09.05.2026 | 25000 | CCK-MP-HAUL-DT769 -BRKSYS-BRHLF | 6800 | 80508 | 26878
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Cyl Steering LH | 2026-08-10 | 2026-08-10 | 10 hrs | FY27 | 16 | 90011350 | B1 | 1000095239 | 11.09.2025 | 15000 | CCK-MP-HAUL-DT769 -STRSYS-STRCY-STCYL | 6800 | 80508 | 21383
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Cyl Steering RH | 2026-08-10 | 2026-08-10 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000095240 | 27.05.2026 | 15000 | CCK-MP-HAUL-DT769 -STRSYS-STRCY-STCYR | 6800 | 80508 | 16026
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Wheel Motor Oil RH | 2026-08-10 | 2026-08-10 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338235 | 30.04.2026 | 25000 | CCK-MP-HAUL-DT769 -FDRSYS-WLMTR-WHMRH | 6800 | 80508 | 534
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Brake Cooling Hoses | 2026-08-10 | 2026-08-10 | 8.5 hrs | FY27 | 14.5 | 90011344 | B1 | 1000223889 | 30.04.2026 | 25000 | CCK-MP-HAUL-DT769 -BRKSYS-BRHLF | 6800 | 80508 | 26878
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Pump Module Hosing | 2026-08-10 | 2026-08-10 | 15 hrs | FY27 | 27 | 90021389 | B1 | 1000223913 | 30.04.2026 | 25000 | CCK-MP-HAUL-DT769 -HYDSYS-HDHLF | 6800 | 80508 | 26878
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Engine Midlife Complete | 2026-08-10 | 2026-08-11 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000161151 | 03.07.2026 | 12000 | CCK-MP-HAUL-DT100 -ENGINE | 7400 | 87135 | 33202
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Grid Box Blower Motor LH | 2026-08-10 | 2026-08-10 | 10 hrs | FY27 | 10 | 90011331 | B1 | 1000094641 | 15.07.2026 | 25000 | CCK-MP-HAUL-DT758 -ELCTHV-HVGBM-GBMLH | 6800 | 85895 | 25601
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Grid Box Blower Motor RH | 2026-08-10 | 2026-08-10 | 10 hrs | FY27 | 10 | 90011332 | B1 | 1000094642 | 15.07.2026 | 25000 | CCK-MP-HAUL-DT758 -ELCTHV-HVGBM-GBMRH | 6800 | 85895 | 25545
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Steering LH | 2026-08-10 | 2026-08-10 | 10 hrs | FY27 | 16 | 90011350 | B1 | 1000094656 | 31.07.2026 | 15000 | CCK-MP-HAUL-DT758 -STRSYS-STRCY-STCYL | 6800 | 85895 | 15304
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Engine Midlife Complete | 2026-08-10 | 2026-08-12 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285176 | 17.03.2026 | 12500 | CCK-MP-HAUL-DT758 -ENGINE | 6800 | 85895 | 15304
777G SV | Onsite PM | Haul | Fortescue | SV220 | 24 Monthly HP Grease Lines Replace | 2026-08-10 | 2026-08-10 | 3 hrs | FY27 | 3 | 90016826 | B1 | 1000152002 | 12.04.2026 | 24 Monthly | CCK-MP-SUPP-SV220 -MODULE | 5100 | 58259 | 16547
777G WC | Onsite PM | Haul | Fortescue | WC2501 | WC2501 Repl Auto Lube Pump | 2026-08-10 | 2026-08-10 | 2 hrs | FY27 | 2 | 90011565 | B1 | 1000136175 | 18.03.2026 | 9000 | CCK-MP-SUPP-WC2501-GRSYST-ALBPP | 2000 | 56945 | 9849
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Operator Cabin Dash Bulbs | 2026-08-10 | 2026-08-10 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158237 | 21.08.2026 | 3000 | CCK-MP-HAUL-DT772 -STRUCT-CABIN | 6800 | 85256 | 10385
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Transmission | 2026-08-17 | 2026-08-18 | 26 hrs | FY27 | 50 | 90018504 | B1 | 1000201226 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-TRNSYS-TRANS | 5100 | 23504 | 7410
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Wheel Group Front RH | 2026-08-17 | 2026-08-18 | 28 hrs | FY27 | 54 | 90017287 | B1 | 1000157207 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRUCT-AXLES-HUBRH | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Transmission | 2026-08-17 | 2026-08-18 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000271877 | 22.03.2027 | 18000 | CCK-MP-HAUL-DT082 -TRNSYS-TRANS | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Spider Trans Driveshaft | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154934 | 06.08.2026 | 6000 | CCK-MP-HAUL-DT090 -FDRSYS-DRSHT-UNVSL | 7400 | 81670 | 5994
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Pump Module Hosing | 2026-08-17 | 2026-08-17 | 15 hrs | FY27 | 27 | 90021389 | B1 | 1000223895 | 25.07.2026 | 25000 | CCK-MP-HAUL-DT751 -HYDSYS-HDHLF | 6800 | 86211 | 86211
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Brake Dual Relay Valves | 2026-08-17 | 2026-08-17 | 8.5 hrs | FY27 | 8.5 | 90021353 | B1 | 1000223471 | 26.07.2026 | 25000 | CCK-MP-HAUL-DT751 -BRKSYS-BRVRL | 6800 | 86211 | 25788
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Transmisson Calibration | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298741 | 26.08.2026 | 4500 | CCK-MP-HAUL-DT222 -TRNSYS-TRANS | 7400 | 55735 | 4006
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Wheel Motor Oil LH | 2026-08-17 | 2026-08-17 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338224 | 13.02.2027 | 25000 | CCK-MP-HAUL-DT764 -FDRSYS-WLMTR-WHMLH | 6800 | 75315 | 21117
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Transmisson Calibration | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298817 | 25.09.2026 | 4500 | CCK-MP-HAUL-DT5317-TRNSYS-TRANS | 7400 | 45576 | 9163
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Spiders Pump Drive Shaft | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026265 | 04.08.2026 | 18000 | CCK-MP-HAUL-DT148 -ENGINE-PMPDR-DRSHT | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Differential | 2026-08-17 | 2026-08-18 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000026273 | 04.08.2026 | 18000 | CCK-MP-HAUL-DT148 -FDRSYS-DIFFL | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Replace Trans TCon System Hoses | 2026-08-17 | 2026-08-18 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000091465 | 06.08.2026 | 18000 | CCK-MP-HAUL-DT148 -TRNSYS-TRANS-TRNHO | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Replace Hoses Differential System | 2026-08-17 | 2026-08-17 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000091466 | 06.08.2026 | 18000 | CCK-MP-HAUL-DT148 -FDRSYS-DIFFL-DIFHO | 7400 | 85451 | 18023
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Valve Flow Amplifier | 2026-08-17 | 2026-08-17 | 13 hrs | FY27 | 13.5 | 90011348 | B1 | 1000094283 | 26.05.2026 | 25000 | CCK-MP-HAUL-DT751 -STRSYS-STVLV | 6800 | 86211 | 26664
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Hub & Spindle LH | 2026-08-17 | 2026-08-18 | 32 hrs | FY27 | 60 | 90011363 | B1 | 1000094299 | 29.03.2026 | 18000 | CCK-MP-HAUL-DT751 -STRUCT-AXLES-HUBLH | 6800 | 86211 | 20723
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Suspension LHF | 2026-08-17 | 2026-08-19 | 60 hrs | FY27 | 112 | 90011365 | B1 | 1000094301 | 29.03.2026 | 18000 | CCK-MP-HAUL-DT751 -STRUCT-SUSPN-SCYLF | 6800 | 86211 | 20723
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Tyre Sense Battery | 2026-08-17 | 2026-08-17 | 1 hr | FY27 | 1 | 90017025 | B1 | 1000153176 | 05.05.2026 | 24 Monthly | CCK-MP-HAUL-DT751 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Replace Hoses Hoist System | 2026-08-17 | 2026-08-18 | 20 hrs | FY27 | 40 | 90010105 | B1 | 1000091450 | 18.06.2026 | 24000 | CCK-MP-HAUL-DT148 -HYDSYS-HDHLF-HSTHO | 7400 | 85451 | 24979
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Brake Cooling System Hoses | 2026-08-17 | 2026-08-18 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000091457 | 24.02.2026 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BRHLF-CBRHO | 7400 | 85451 | 27203
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Front Wheel Bearings LH | 2026-08-17 | 2026-08-18 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157160 | 30.04.2026 | 16000 | CCK-MP-HAUL-DT148 -STRUCT-AXLES-FWBLH | 7400 | 85451 | 18023
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Repl Sepura SCC Microphone | 2026-08-17 | 2026-08-17 | 0.5 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289617 | 26.08.2026 | 12 Monthly | CCK-MP-SUPP-SV4104-COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Engine Midlife Complete | 2026-08-24 | 2026-08-25 | 36 hrs | FY27 | 62 | 90015886 | B1 | 1000156020 | 19.06.2026 | 12000 | CCK-MP-HAUL-DT147 -ENGINE | 7400 | 84659 | 31850
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Radiator Fan Hoses | 2026-08-24 | 2026-08-24 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307525 | 18.06.2026 | 12000 | CCK-MP-HAUL-DT147 -ENGINE-COSYS-RADTR | 7400 | 84708 | 31850
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Spiders Pump Drive Shaft | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026199 | 21.12.2026 | 18000 | CCK-MP-HAUL-DT147 -ENGINE-PMPDR-DRSHT | 7400 | 84708 | 16832
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Transmisson Calibration | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298728 | 14.10.2026 | 4500 | CCK-MP-HAUL-DT147 -TRNSYS-TRANS | 7400 | 84659 | 716
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Auto Lube Pump | 2026-08-24 | 2026-08-24 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285788 | 19.02.2027 | 8000 | CCK-MP-HAUL-DT147 -GRSYST-ALBPP | 7400 | 84664 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Service Air Conditioner 12M | 2026-08-24 | 2026-08-25 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174176 | 17.01.2027 | 12 Monthly | CCK-MP-HAUL-DT147 -STRUCT-CABIN-AIRCN | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Tyre Sense Battery | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153159 | 06.01.2027 | 24 Monthly | CCK-MP-HAUL-DT147 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Replace Operator Cabin Dash Bulbs | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158219 | 24.08.2026 | 3000 | CCK-MP-HAUL-DT754 -STRUCT-CABIN | 6800 | 83256 | 83256
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 789C AHS Replace Proactive Coax | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 12 | 90022477 | B2 | 1000235593 | 12.08.2026 | 24 Monthly | CCK-MP-SUPP-WC225 -COMMUN-FLMGT
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Engine Midlife complete | 2026-08-24 | 2026-08-27 | 86 hrs | FY27 | 102 | 90017302 | B1 | 1000290433 | 21.08.2026 | 11000 | CCK-MP-SUPP-WC225 -ENGINE | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Pump Drive Driveshaft Unis | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90000911 | B2 | 1000033353 | 21.08.2026 | 11000 | CCK-MP-SUPP-WC225 -ENGINE-PMPDR-DRSHT | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Spiders Trans Drive Shaft | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90000910 | B2 | 1000033359 | 21.08.2026 | 11000 | CCK-MP-SUPP-WC225 -FDRSYS-DRSHT | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Slack Adjuster Rear | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90002911 | B2 | 1000040610 | 21.08.2026 | 11000 | CCK-MP-SUPP-WC225 -BRKSYS-SLACK-SLACR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Airconditioner Overhaul | 2026-08-24 | 2026-08-26 | 48 hrs | FY27 | 48 | 90017507 | B1 | 1000290435 | 21.08.2026 | 11000 | CCK-MP-SUPP-WC225 -STRUCT-CABIN-AIRCN | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Seat Assy | 2026-08-24 | 2026-08-24 | 3 hrs | FY27 | 6 | 90003494 | B2 | 1000039956 | 21.08.2026 | 11000 | CCK-MP-SUPP-WC225 -STRUCT-CABIN-SEATS | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Torque Converter System Hoses | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 8 | 90010494 | B2 | 1000238427 | 21.08.2026 | 11000 | CCK-MP-SUPP-WC225 -TRNSYS-TRQUE-TRQHO | 5000 | 22459 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Service Suspension Cylinder LHF | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 16 | 90009025 | B2 | 1000067707 | 25.08.2026 | 11000 | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Service Suspension Cylinder RHF | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 16 | 90009025 | B2 | 1000067709 | 25.08.2026 | 11000 | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Inspect Rear Axle Housing | 2026-08-24 | 2026-08-24 | 1 hr | FY27 | 1 | 90019256 | B1 | 1000196435 | 08.09.2026 | 2000 | CCK-MP-SUPP-WC225 -STRUCT-RAXHO | 5000 | 75244 | 75244
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Repl Sepura SCC Microphone | 2026-08-24 | 2026-08-24 | 0.5 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289618 | 30.07.2026 | 12 Monthly | CCK-MP-SUPP-WC008 -COMMUN-RADIO
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Replace Operator Cabin Dash Bulbs | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158226 | 30.09.2026 | 3000 | CCK-MP-HAUL-DT761 -STRUCT-CABIN | 6800 | 78336 | 19424
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Wheel Motor Oil RH | 2026-08-24 | 2026-08-24 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338233 | 27.05.2026 | 25000 | CCK-MP-HAUL-DT768 -FDRSYS-WLMTR-WHMRH | 6800 | 79837 | 26332
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Steering HMU | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 8 | 90002384 | B1 | 1000026749 | 17.09.2026 | 24000 | CCK-MP-HAUL-DT155 -STRSYS-STHMU | 7400 | 81407 | 23145
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Radiator Fan Hoses | 2026-08-24 | 2026-08-24 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307517 | 27.07.2026 | 12000 | CCK-MP-HAUL-DT143 -ENGINE-COSYS-RADTR | 7400 | 88225 | 30720
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Motor Lube Axle Hoses | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272010 | 27.07.2026 | 12000 | CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYM01 | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl AOC Fan Motor Rear | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000025947 | 27.07.2026 | 12000 | CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYM02 | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Spider Trans Driveshaft | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154966 | 24.07.2026 | 6000 | CCK-MP-HAUL-DT142 -FDRSYS-DRSHT-UNVSL | 7400 | 87027 | 11970
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Adjust Engine Valve Set | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 24 | 90015645 | B1 | 1000269779 | 02.09.2026 | 4500 | CCK-MP-SUPP-SV221 -ENGINE | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Service Airconditioner | 2026-08-24 | 2026-08-25 | 24 hrs | FY27 | 24 | 90018538 | B2 | 1000269902 | 02.09.2026 | 4500 | CCK-MP-SUPP-SV221 -STRUCT-CABIN-AIRCN | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Tyre Sense Battery | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153152 | 29.08.2026 | 24 Monthly | CCK-MP-HAUL-DT136 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Service Air Conditioner 12M | 2026-08-31 | 2026-09-01 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000172995 | 23.12.2025 | 12 Monthly | CCK-MP-HAUL-DT5313-STRUCT-CABIN-AIRCN | 7400 | 44693 | 44693
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Drive Line Axle LH | 2026-08-31 | 2026-08-31 | 2 hrs | FY27 | 4 | 90014919 | B1 | 1000124273 | 26.09.2026 | 24000 | CCK-MP-HAUL-DT057 -FDRSYS-DRLAX-AXLLH | 7400 | 91273 | 22845
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Drive Line Axle RH | 2026-08-31 | 2026-08-31 | 2 hrs | FY27 | 4 | 90014943 | B1 | 1000124274 | 26.09.2026 | 24000 | CCK-MP-HAUL-DT057 -FDRSYS-DRLAX-AXLRH | 7400 | 91273 | 22845
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Engine Midlife Complete | 2026-08-31 | 2026-09-01 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000155882 | 29.09.2026 | 12000 | CCK-MP-HAUL-DT057 -ENGINE | 7400 | 91273 | 91273
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Radiator Fan Hoses | 2026-08-31 | 2026-08-31 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307471 | 29.09.2026 | 12000 | CCK-MP-HAUL-DT057 -ENGINE-COSYS-RADTR | 7400 | 91273 | 58459
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl AOC Fan Motor Rear | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000023785 | 29.09.2026 | 12000 | CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYM02 | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Pump Brake Cooling | 2026-08-31 | 2026-08-31 | 9 hrs | FY27 | 17 | 90002379 | B1 | 1000023789 | 22.09.2026 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-HYFPP | 7400 | 91273 | 22845
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Spider Trans Driveshaft | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154924 | 29.09.2026 | 6000 | CCK-MP-HAUL-DT057 -FDRSYS-DRSHT-UNVSL | 7400 | 91273 | 3875
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Steering LH | 2026-08-31 | 2026-08-31 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000023796 | 21.10.2026 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STRCY-STCYL | 7400 | 91273 | 13167
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Steering RH | 2026-08-31 | 2026-08-31 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000023797 | 21.10.2026 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STRCY-STCYR | 7400 | 91273 | 13167
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Steering Brake Pump Compensator | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 7 | 90019922 | B1 | 1000204771 | 29.09.2026 | 6000 | CCK-MP-HAUL-DT767 -STRSYS-STPMP | 6800 | 74312 | 4545
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl 50A Aux Cabinet Relays | 2026-08-31 | 2026-08-31 | 0.5 hrs | FY27 | 0.5 | 90029280 | B1 | 1000292270 | 22.08.2026 | 25000 | CCK-MP-HAUL-DT767 -ELCTLV-AUCAB | 6800 | 74312 | 19669
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 25000hr Ground Fault Test | 2026-08-31 | 2026-08-31 | 1 hr | FY27 | 1 | 90021455 | B2 | 1000226128 | 26.08.2026 | 25000 | CCK-MP-HAUL-DT767 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Steering Brake Pump Compensator | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 7 | 90019922 | B1 | 1000204775 | 29.08.2026 | 6000 | CCK-MP-HAUL-DT771 -STRSYS-STPMP | 6800 | 84423 | 18016
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Cyl Steering RH | 2026-08-31 | 2026-08-31 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000095134 | 29.05.2026 | 15000 | CCK-MP-HAUL-DT767 -STRSYS-STRCY-STCYR | 6800 | 74312 | 15082
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Hyd Pump Steering Main & Fan | 2026-08-31 | 2026-08-31 | 17 hrs | FY27 | 17 | 90002383 | B1 | 1000026352 | 23.09.2026 | 24000 | CCK-MP-HAUL-DT149 -STRSYS-STPMP | 7400 | 86975 | 23026
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Service Air Conditioner 12M | 2026-08-31 | 2026-09-01 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174168 | 05.07.2026 | 12 Monthly | CCK-MP-HAUL-DT135 -STRUCT-CABIN-AIRCN | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Front Wheel Bearings LH | 2026-08-31 | 2026-09-01 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157142 | 17.09.2026 | 16000 | CCK-MP-HAUL-DT135 -STRUCT-AXLES-FWBLH | 7400 | 82965 | 15252
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Steering LH | 2026-08-31 | 2026-08-31 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000026354 | 18.04.2026 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STRCY-STCYL | 7400 | 86975 | 17339
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Steering RH | 2026-08-31 | 2026-08-31 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000026355 | 18.04.2026 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STRCY-STCYR | 7400 | 86975 | 17339
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Transmisson Calibration | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298679 | 01.10.2026 | 4500 | CCK-MP-HAUL-DT130 -TRNSYS-TRANS | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Spider Trans Driveshaft | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154954 | 14.10.2026 | 6000 | CCK-MP-HAUL-DT130 -FDRSYS-DRSHT-UNVSL | 7400 | 85185 | 10692
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Replace Brake Cabinet Hoses | 2026-08-31 | 2026-09-01 | 32.5 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126213 | 11.03.2026 | 25000 | CCK-MP-HAUL-DT756 -BRKSYS-BRHLF | 6800 | 78754 | 27589
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Service Air Conditioner 12M | 2026-09-07 | 2026-09-08 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174187 | 23.08.2026 | 12 Monthly | CCK-MP-HAUL-DT160 -STRUCT-CABIN-AIRCN | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Auto Lube Pump | 2026-09-07 | 2026-09-07 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285798 | 12.09.2026 | 8000 | CCK-MP-HAUL-DT160 -GRSYST-ALBPP | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Steering Bell Crank & Links | 2026-09-07 | 2026-09-08 | 20 hrs | FY27 | 36 | 90028566 | B1 | 1000317582 | 10.07.2026 | 30000 | CCK-MP-HAUL-DT055 -STRSYS-STLTR-STLAC | 7400 | 84122 | 84122
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Transmisson Calibration | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298663 | 15.09.2026 | 4500 | CCK-MP-HAUL-DT055 -TRNSYS-TRANS | 7400 | 84122 | 15848
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Air Con Service & Overhaul | 2026-09-07 | 2026-09-08 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110612 | 14.08.2026 | 12 Monthly | CCK-MP-HAUL-DT752 -STRUCT-CABIN-AIRCN | 6800 | 80681 | 31412
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Hyd Pump Steering & Brake | 2026-09-07 | 2026-09-08 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204431 | 17.08.2026 | 12000 | CCK-MP-HAUL-DT752 -STRSYS-STPMP | 6800 | 80681 | 13250
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Replace Operator Cabin Dash Bulbs | 2026-09-07 | 2026-09-07 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158217 | 12.09.2026 | 3000 | CCK-MP-HAUL-DT752 -STRUCT-CABIN | 6800 | 80681 | 80681
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Steering System Hoses | 2026-09-07 | 2026-09-09 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083368 | 21.05.2026 | 15000 | CCK-MP-HAUL-DT5255-STRSYS-STHLF-STRHO | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Steering Hyd Oil Cooler | 2026-09-07 | 2026-09-07 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107001 | 21.05.2026 | 15000 | CCK-MP-HAUL-DT5255-STRSYS-STOCO | 7400 | 87580 | 16634
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Air Con Service & Overhaul | 2026-09-07 | 2026-09-08 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110643 | 10.08.2026 | 12 Monthly | CCK-MP-HAUL-DT774 -STRUCT-CABIN-AIRCN | 6800 | 81047 | 35545
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Replace Operator Cabin Dash Bulbs | 2026-09-07 | 2026-09-07 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158239 | 13.08.2026 | 3000 | CCK-MP-HAUL-DT774 -STRUCT-CABIN | 6800 | 81047 | 28490
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Steering Brake Pump Compensator | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 7 | 90019922 | B1 | 1000204778 | 12.10.2026 | 6000 | CCK-MP-HAUL-DT774 -STRSYS-STPMP | 6800 | 81047 | 4812
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Replace Brake Cabinet Hoses | 2026-09-07 | 2026-09-08 | 32.5 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126521 | 22.02.2026 | 25000 | CCK-MP-HAUL-DT774 -BRKSYS-BRHLF | 6800 | 81047 | 28490
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Cyl Hoist RH | 2026-09-07 | 2026-09-07 | 17 hrs | FY27 | 33 | 90011358 | B1 | 1000095512 | 19.02.2026 | 25000 | CCK-MP-HAUL-DT774 -HYDSYS-HOCYL-HCYLR | 6800 | 81047 | 28490
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Cyl Suspension RHR | 2026-09-07 | 2026-09-08 | 32 hrs | FY27 | 50 | 90011368 | B1 | 1000095523 | 19.02.2026 | 25000 | CCK-MP-HAUL-DT774 -STRUCT-SUSPN-SCYRR | 6800 | 81047 | 28490
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Steering LH | 2026-09-07 | 2026-09-07 | 10 hrs | FY27 | 16 | 90011350 | B1 | 1000094338 | 07.11.2027 | 15000 | CCK-MP-HAUL-DT752 -STRSYS-STRCY-STCYL | 6800 | 80681 | 6552
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Steering RH | 2026-09-07 | 2026-09-07 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000094339 | 07.03.2027 | 15000 | CCK-MP-HAUL-DT752 -STRSYS-STRCY-STCYR | 6800 | 80681 | 11115
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Steering RH | 2026-09-07 | 2026-09-07 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000095399 | 12.12.2027 | 15000 | CCK-MP-HAUL-DT772 -STRSYS-STRCY-STCYR | 6800 | 85256 | 7496
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Pump Module Hosing | 2026-09-07 | 2026-09-07 | 15 hrs | FY27 | 27 | 90021389 | B1 | 1000223916 | 22.02.2026 | 25000 | CCK-MP-HAUL-DT772 -HYDSYS-HDHLF | 6800 | 85256 | 29127
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Brake Oil Cooler Front | 2026-09-07 | 2026-09-07 | 13 hrs | FY27 | 13 | 90010109 | B1 | 1000083002 | 18.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BROCO-BROCF | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Brake Oil Cooler Rear | 2026-09-07 | 2026-09-07 | 13 hrs | FY27 | 13 | 90010108 | B1 | 1000083001 | 18.11.2026 | 24000 | CCK-MP-HAUL-DT095 -BRKSYS-BROCO-BROCR | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Transmisson Calibration | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298673 | 31.08.2026 | 4500 | CCK-MP-HAUL-DT095 -TRNSYS-TRANS | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Steering LH | 2026-09-14 | 2026-09-14 | 10 hrs | FY27 | 20 | 90002385 | B1 | 1000023733 | 23.02.2026 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STRCY-STCYL | 7400 | 84421 | 17941
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Steering RH | 2026-09-14 | 2026-09-14 | 10 hrs | FY27 | 20 | 90002385 | B2 | 1000023734 | 23.02.2026 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STRCY-STCYR | 7400 | 84421 | 17941
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Steering Linkages | 2026-09-14 | 2026-09-14 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317583 | 14.10.2026 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STLTR | 7400 | 84421 | 20273
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Replace Steering System Hoses | 2026-09-14 | 2026-09-16 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000082494 | 14.10.2026 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STHLF-STRHO | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 250hr Initial Valve Set | 2026-09-14 | 2026-09-14 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000155904 | 14.07.2026 | 250 | CCK-MP-HAUL-DT088 -ENGINE | 7400 | 89037 | 50219
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Tyre Sense Battery | 2026-09-14 | 2026-09-14 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000167374 | 21.09.2026 | 24 Monthly | CCK-MP-HAUL-DT5318-MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Transmisson Calibration | 2026-09-14 | 2026-09-14 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298733 | 24.08.2026 | 4500 | CCK-MP-HAUL-DT153 -TRNSYS-TRANS | 7400 | 84230 | 2506
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Hoist RH | 2026-09-14 | 2026-09-14 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128598 | 14.08.2026 | 28000 | CCK-MP-HAUL-DT153 -HYDSYS-HOCYL-HCYLR | 7400 | 84230 | 27608
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Auto Lube Pump | 2026-09-14 | 2026-09-14 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285793 | 29.08.2026 | 8000 | CCK-MP-HAUL-DT153 -GRSYST-ALBPP | 7400 | 84230 | 7415
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Air Con Service & Overhaul | 2026-09-14 | 2026-09-15 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110626 | 05.03.2026 | 12 Monthly | CCK-MP-HAUL-DT757 -STRUCT-CABIN-AIRCN | 6800 | 80700 | 25834
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Service Air Conditioner 12M | 2026-09-14 | 2026-09-15 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174165 | 22.08.2026 | 12 Monthly | CCK-MP-HAUL-DT126 -STRUCT-CABIN-AIRCN | 7400 | 88657 | 54006
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Replace Steering Hoses & Lines | 2026-09-14 | 2026-09-14 | 8 hrs | FY27 | 8 | 90011560 | B1 | 1000098082 | 04.02.2026 | 18000 | CCK-MP-SUPP-WC220 -STRSYS-STHLF | 4300 | 58137 | 18617
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Replace Operator Seat | 2026-09-14 | 2026-09-14 | 3 hrs | FY27 | 6 | 90011567 | B1 | 1000098089 | 15.07.2026 | 6000 | CCK-MP-SUPP-WC220 -STRUCT-CABIN-SEATS | 4300 | 58137 | 5120
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Steering Link & Arm Rebush | 2026-09-14 | 2026-09-15 | 30 hrs | FY27 | 60 | 90003473 | B2 | 1000039680 | 20.09.2026 | 15000 | CCK-MP-SUPP-WC224 -STRSYS-STLTR | 5000 | 71088 | 14480
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Sepura SCC Microphone | 2026-09-14 | 2026-09-14 | 0.5 hrs | FY27 | 0.5 | 90029002 | B1 | 1000289635 | 22.09.2026 | 12 Monthly | CCK-MP-SUPP-WC224 -COMMUN-RADIO
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Slack Adjuster Front | 2026-09-14 | 2026-09-14 | 2 hrs | FY27 | 2 | 90002910 | B2 | 1000040561 | 29.09.2026 | 11000 | CCK-MP-SUPP-WC224 -BRKSYS-SLACK-SLACF | 5000 | 71088 | 10363
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Slack Adjuster Rear | 2026-09-14 | 2026-09-14 | 2 hrs | FY27 | 2 | 90002911 | B2 | 1000040562 | 29.09.2026 | 11000 | CCK-MP-SUPP-WC224 -BRKSYS-SLACK-SLACR | 5000 | 71088 | 10363
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Repl Sepura SCC Microphone | 2026-09-14 | 2026-09-14 | 0.5 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289620 | 21.09.2026 | 12 Monthly | CCK-MP-SUPP-WC220 -COMMUN-RADIO
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Air Drier and Tank | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 24 | 90004010 | B2 | 1000079276 | 03.10.2026 | 9000 | CCK-MP-SUPP-WC3112-PNEUMC-AIRDR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Steering Link & Arm Rebush | 2026-09-14 | 2026-09-14 | 14 hrs | FY27 | 22 | 90004007 | B2 | 1000079271 | 10.10.2026 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STLTR | 5600 | 52240 | 14062
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Engine Midlife Complete | 2026-09-21 | 2026-09-23 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285177 | 17.08.2026 | 12500 | CCK-MP-HAUL-DT759 -ENGINE | 6800 | 79716 | 12763
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 250hr Initial Valve Set | 2026-09-21 | 2026-09-21 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000155898 | 31.07.2026 | 250 | CCK-MP-HAUL-DT086 -ENGINE | 7400 | 86822 | 24006
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Transmisson Calibration | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298668 | 12.06.2026 | 4500 | CCK-MP-HAUL-DT086 -TRNSYS-TRANS | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Tyre Sense Battery | 2026-09-21 | 2026-09-21 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000272719 | 21.09.2026 | 24 Monthly | CCK-MP-SUPP-PM0001-MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Cyl Suspension RHF | 2026-09-21 | 2026-09-23 | 60 hrs | FY27 | 112 | 90011366 | B1 | 1000094779 | 16.07.2026 | 18000 | CCK-MP-HAUL-DT760 -STRUCT-SUSPN-SCYRF | 6800 | 80390 | 18688
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Cyl Suspension LHF | 2026-09-21 | 2026-09-23 | 60 hrs | FY27 | 112 | 90011365 | B1 | 1000094778 | 13.08.2027 | 18000 | CCK-MP-HAUL-DT760 -STRUCT-SUSPN-SCYLF | 6800 | 80390 | 11271
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Steering Bleed Down Manifold | 2026-09-21 | 2026-09-21 | 6.5 hrs | FY27 | 8 | 90011347 | B1 | 1000094759 | 14.08.2026 | 25000 | CCK-MP-HAUL-DT760 -STRSYS-STBDM | 6800 | 80390 | 25051
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Replace Operator Cabin Dash Bulbs | 2026-09-21 | 2026-09-21 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158225 | 13.09.2026 | 3000 | CCK-MP-HAUL-DT760 -STRUCT-CABIN | 6800 | 80390 | 80390
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Steering RH | 2026-09-21 | 2026-09-21 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000094392 | 16.06.2026 | 15000 | CCK-MP-HAUL-DT753 -STRSYS-STRCY-STCYR | 6800 | 85999 | 15852
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Transmisson Calibration | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298742 | 18.09.2026 | 4500 | CCK-MP-HAUL-DT223 -TRNSYS-TRANS | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Steering Bell Crank & Links | 2026-09-21 | 2026-09-22 | 20 hrs | FY27 | 36 | 90028566 | B1 | 1000317660 | 25.09.2026 | 30000 | CCK-MP-HAUL-DT223 -STRSYS-STLTR-STLAC | 7400 | 54920 | 29074
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Replace Steering System Hoses | 2026-09-21 | 2026-09-23 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083444 | 12.08.2026 | 15000 | CCK-MP-HAUL-DT150 -STRSYS-STHLF-STRHO | 7400 | 86608 | 29495
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Tyre Sense Battery | 2026-09-21 | 2026-09-21 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153149 | 14.04.2026 | 24 Monthly | CCK-MP-HAUL-DT127 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Service Air Conditioner 12M | 2026-09-21 | 2026-09-22 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174185 | 26.08.2026 | 12 Monthly | CCK-MP-HAUL-DT159 -STRUCT-CABIN-AIRCN | 7400 | 90235 | 41100
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Cyl Suspension RHF | 2026-09-21 | 2026-09-23 | 43 hrs | FY27 | 84 | 90002408 | B2 | 1000067639 | 18.09.2026 | 28000 | CCK-MP-HAUL-DT159 -STRUCT-SUSPN-SCYRF | 7400 | 90235 | 26732
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Auto Lube Pump | 2026-09-21 | 2026-09-21 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285797 | 15.10.2026 | 8000 | CCK-MP-HAUL-DT159 -GRSYST-ALBPP | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Radiator Fan Hoses | 2026-09-21 | 2026-09-21 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307523 | 04.07.2026 | 12000 | CCK-MP-HAUL-DT146 -ENGINE-COSYS-RADTR | 7400 | 83108 | 66584
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Brake Cooling System Hoses | 2026-09-21 | 2026-09-22 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000091435 | 03.07.2026 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BRHLF-CBRHO | 7400 | 83062 | 51566
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Front Wheel Bearings LH | 2026-09-21 | 2026-09-22 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157156 | 25.07.2026 | 16000 | CCK-MP-HAUL-DT146 -STRUCT-AXLES-FWBLH | 7400 | 83062 | 16275
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Transmisson Calibration | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298727 | 20.09.2026 | 4500 | CCK-MP-HAUL-DT146 -TRNSYS-TRANS | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Transmisson Calibration | 2026-09-28 | 2026-09-28 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298815 | 06.09.2026 | 4500 | CCK-MP-HAUL-DT5315-TRNSYS-TRANS | 7400 | 45392 | 8391
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl 50A Aux Cabinet Relays | 2026-09-28 | 2026-09-28 | 0.5 hrs | FY27 | 0.5 | 90029280 | B1 | 1000292266 | 24.09.2026 | 25000 | CCK-MP-HAUL-DT763 -ELCTLV-AUCAB | 6800 | 74143 | 30934
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Replace Operator Cabin Dash Bulbs | 2026-09-28 | 2026-09-28 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158228 | 29.09.2026 | 3000 | CCK-MP-HAUL-DT763 -STRUCT-CABIN | 6800 | 74143 | 74143
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Replace Operator Cabin Dash Bulbs | 2026-09-28 | 2026-09-28 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158230 | 17.09.2026 | 3000 | CCK-MP-HAUL-DT765 -STRUCT-CABIN | 6800 | 78429 | 78429
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Operators Seat | 2026-09-28 | 2026-09-28 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000027161 | 25.09.2026 | 15000 | CCK-MP-HAUL-DT161 -STRUCT-CABIN-SEATS | 7400 | 80609 | 13960
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Transmission Oil Cooler | 2026-09-28 | 2026-09-28 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000083278 | 13.08.2026 | 18000 | CCK-MP-HAUL-DT140 -TRNSYS-TROLC | 7400 | 86767 | 17833
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Auto Lube Pump | 2026-09-28 | 2026-09-28 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285784 | 03.10.2026 | 8000 | CCK-MP-HAUL-DT140 -GRSYST-ALBPP | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Transmisson Calibration | 2026-09-28 | 2026-09-28 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298724 | 21.11.2026 | 4500 | CCK-MP-HAUL-DT140 -TRNSYS-TRANS | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Steering RH | 2026-09-28 | 2026-09-28 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000024869 | 20.08.2026 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STRCY-STCYR | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Radiator Fan Hoses | 2026-09-28 | 2026-09-28 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307551 | 23.05.2026 | 12000 | CCK-MP-HAUL-DT5202-ENGINE-COSYS-RADTR | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Replace Steering System Hoses | 2026-09-28 | 2026-09-30 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000111975 | 08.10.2026 | 15000 | CCK-MP-HAUL-DT5202-STRSYS-STHLF-STRHO | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Steering Linkages | 2026-09-28 | 2026-09-28 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317661 | 31.01.2026 | 15000 | CCK-MP-HAUL-DT5202-STRSYS-STLTR | 7400 | 84333 | 33598
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Sepura SCC Microphone | 2026-09-28 | 2026-09-28 | 0.5 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289612 | 01.10.2026 | 12 Monthly | CCK-MP-SUPP-SV221 -COMMUN-RADIO | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Bulk Grease Tank Breather | 2026-09-28 | 2026-09-28 | 1 hr | FY27 | 1 | 90022533 | B1 | 1000236910 | 01.10.2026 | 6 Monthly | CCK-MP-SUPP-SV221 -GRSYST-GRTNK | 5100 | 64374 | 4253
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Replace Operator Cabin Dash Bulbs | 2026-09-29 | 2026-09-29 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158224 | 29.09.2026 | 3000 | CCK-MP-HAUL-DT759 -STRUCT-CABIN | 6800 | 79716 | 79716
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Operator Cabin Dash Bulbs | 2026-10-01 | 2026-10-01 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158223 | 01.10.2026 | 3000 | CCK-MP-HAUL-DT758 -STRUCT-CABIN | 6800 | 85895 | 23936
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Tyre Sense Battery | 2026-10-05 | 2026-10-05 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000167214 | 12.10.2026 | 24 Monthly | CCK-MP-HAUL-DT5316-MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl AOC Fan Motor Rear | 2026-10-05 | 2026-10-05 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000026937 | 25.09.2026 | 12000 | CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYM02 | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Spider Trans Driveshaft | 2026-10-05 | 2026-10-05 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154988 | 25.09.2026 | 6000 | CCK-MP-HAUL-DT158 -FDRSYS-DRSHT-UNVSL | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Engine Midlife Complete | 2026-10-05 | 2026-10-06 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000156062 | 07.09.2026 | 12000 | CCK-MP-HAUL-DT158 -ENGINE | 7400 | 85964 | 11614
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Replace Hoses Hoist System | 2026-10-05 | 2026-10-06 | 20 hrs | FY27 | 40 | 90010105 | B1 | 1000091538 | 30.09.2026 | 24000 | CCK-MP-HAUL-DT158 -HYDSYS-HDHLF-HSTHO | 7400 | 85964 | 23196
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Replace Brake System Hoses | 2026-10-05 | 2026-10-07 | 46 hrs | FY27 | 90 | 90010129 | B4 | 1000091544 | 28.09.2026 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BRHLF-BRHOS | 7400 | 85964 | 23229
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Brake Cooling System Hoses | 2026-10-05 | 2026-10-06 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000091545 | 28.09.2026 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BRHLF-CBRHO | 7400 | 85964 | 23229
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Hyd Pump Steering & Brake | 2026-10-05 | 2026-10-06 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204749 | 26.09.2026 | 12000 | CCK-MP-HAUL-DT769 -STRSYS-STPMP | 6800 | 80508 | 15397
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Service Air Conditioner 12M | 2026-10-05 | 2026-10-06 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174180 | 05.08.2026 | 12 Monthly | CCK-MP-HAUL-DT151 -STRUCT-CABIN-AIRCN | 7400 | 84253 | 21869
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Wheel Group Front RH | 2026-10-05 | 2026-10-06 | 28 hrs | FY27 | 54 | 90017287 | B1 | 1000157223 | 20.09.2026 | 24000 | CCK-MP-HAUL-DT100 -STRUCT-AXLES-HUBRH | 7400 | 87135 | 23110
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Steering RH | 2026-10-05 | 2026-10-05 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000024554 | 29.06.2026 | 15000 | CCK-MP-HAUL-DT094 -STRSYS-STRCY-STCYR | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 250hr Initial Valve Set | 2026-10-05 | 2026-10-05 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000155916 | 01.09.2026 | 250 | CCK-MP-HAUL-DT091 -ENGINE | 7400 | 83859 | 23814
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Tyre Sense Battery | 2026-10-06 | 2026-10-06 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000167134 | 06.10.2026 | 24 Monthly | CCK-MP-HAUL-DT5315-MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Auto Lube Pump | 2026-10-10 | 2026-10-10 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285803 | 10.10.2026 | 8000 | CCK-MP-HAUL-DT5202-GRSYST-ALBPP | 7400 | 84333 | 6577
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Service Air Conditioner 12M | 2026-10-12 | 2026-10-13 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174117 | 27.10.2026 | 12 Monthly | CCK-MP-HAUL-DT090 -STRUCT-CABIN-AIRCN | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Auto Lube Pump | 2026-10-12 | 2026-10-12 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285630 | 08.11.2026 | 8000 | CCK-MP-HAUL-DT090 -GRSYST-ALBPP | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Transmission | 2026-10-12 | 2026-10-13 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000272473 | 12.10.2026 | 18000 | CCK-MP-HAUL-DT5255-TRNSYS-TRANS | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Trans TCon System Hoses | 2026-10-12 | 2026-10-13 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000090139 | 12.10.2026 | 18000 | CCK-MP-HAUL-DT5255-TRNSYS-TRANS-TRNHO | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Hoses Differential System | 2026-10-12 | 2026-10-12 | 5 hrs | FY27 | 5 | 90010101 | B1 | 1000090140 | 12.10.2026 | 18000 | CCK-MP-HAUL-DT5255-FDRSYS-DIFFL-DIFHO | 7400 | 87580 | 16634
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Water Cannon Maintenance | 2026-10-12 | 2026-10-12 | 3 hrs | FY27 | 3 | 90001682 | B1 | 1000018408 | 30.09.2026 | 6 Monthly | CCK-MP-SUPP-WC008 -STRUCT-WTANK-SPRAY | 3500 | 51417 | 5947
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Wheel Motor Oil RH | 2026-10-12 | 2026-10-12 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338237 | 27.08.2026 | 25000 | CCK-MP-HAUL-DT770 -FDRSYS-WLMTR-WHMRH | 6800 | 79305 | 24535
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Hub and Spindle LH | 2026-10-12 | 2026-10-12 | 12 hrs | FY27 | 22 | 90000273 | B2 | 1000018406 | 22.06.2026 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-AXLES-HUBLH | 3500 | 51417 | 18129
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Hub and Spindle RH | 2026-10-12 | 2026-10-12 | 12 hrs | FY27 | 22 | 90000273 | B2 | 1000018407 | 22.06.2026 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-AXLES-HUBRH | 3500 | 51417 | 18129
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Steering LH | 2026-10-12 | 2026-10-12 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000023985 | 28.10.2026 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STRCY-STCYL | 7400 | 84375 | 13167
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Sepura SCC Microphone | 2026-10-16 | 2026-10-16 | 0.5 hrs | FY27 | 0.5 | 90029002 | B1 | 1000289636 | 16.10.2026 | 12 Monthly | CCK-MP-SUPP-WC225 -COMMUN-RADIO
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Engine Midlife complete | 2026-10-16 | 2026-10-18 | 58 hrs | FY27 | 70 | 90015646 | B1 | 1000201193 | 16.10.2026 | 9000 | CCK-MP-SUPP-SV4104-ENGINE | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Adjust Engine Valve Set | 2026-10-16 | 2026-10-16 | 12 hrs | FY27 | 24 | 90015645 | B1 | 1000201197 | 16.10.2026 | 4500 | CCK-MP-SUPP-SV4104-ENGINE | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Repl Pump Brake Charge & Cooling | 2026-10-16 | 2026-10-16 | 6 hrs | FY27 | 6 | 90037883 | B1 | 1000379699 | 16.10.2026 | 9000 | CCK-MP-SUPP-SV4104-BRKSYS-BRPMP | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Auto Lube Pump | 2026-10-16 | 2026-10-16 | 2 hrs | FY27 | 2 | 90018537 | B1 | 1000201177 | 16.10.2026 | 9000 | CCK-MP-SUPP-SV4104-GRSYST-ALBPP | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Overhaul Airconditioner | 2026-10-16 | 2026-10-17 | 24 hrs | FY27 | 24 | 90011566 | B2 | 1000229147 | 16.10.2026 | 9000 | CCK-MP-SUPP-SV4104-STRUCT-CABIN-AIRCN | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Brake Slack Adjuster Front | 2026-10-16 | 2026-10-16 | 6 hrs | FY27 | 6 | 90036701 | B1 | 1000368010 | 16.10.2026 | 18000 | CCK-MP-SUPP-SV4104-BRKSYS-SLACK-SLACF | 5100 | 23504 | 23504
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Brake Slack Adjuster Rear Left | 2026-10-16 | 2026-10-16 | 6 hrs | FY27 | 6 | 90036703 | B1 | 1000368011 | 16.10.2026 | 18000 | CCK-MP-SUPP-SV4104-BRKSYS-SLACK-SLARL | 5100 | 23504 | 23504
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Brake Slack Adjuster Rear Right | 2026-10-16 | 2026-10-16 | 6 hrs | FY27 | 6 | 90036703 | B1 | 1000368012 | 16.10.2026 | 18000 | CCK-MP-SUPP-SV4104-BRKSYS-SLACK-SLARR | 5100 | 23504 | 23504
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension LHF | 2026-10-17 | 2026-10-17 | 2 hrs | FY27 | 2 | 90038229 | B1 | 1000382496 | 17.10.2026 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension RHF | 2026-10-17 | 2026-10-17 | 2 hrs | FY27 | 2 | 90038229 | B1 | 1000382497 | 17.10.2026 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Water Tank Cannon & Spray Sys Insp | 2026-10-18 | 2026-10-18 | 3 hrs | FY27 | 3 | 90036927 | B1 | 1000368894 | 18.10.2026 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-WTANK | 5000 | 75244 | 75244
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Transmission Oil Cooler | 2026-10-19 | 2026-10-19 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000083392 | 01.10.2026 | 18000 | CCK-MP-HAUL-DT147 -TRNSYS-TROLC | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Differential | 2026-10-19 | 2026-10-20 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000026207 | 01.10.2026 | 18000 | CCK-MP-HAUL-DT147 -FDRSYS-DIFFL | 7400 | 84708 | 16832
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Wheel End LH | 2026-10-19 | 2026-10-20 | 32.5 hrs | FY27 | 58.5 | 90002374 | B1 | 1000026208 | 31.01.2027 | 24000 | CCK-MP-HAUL-DT147 -FDRSYS-FDRVE-FDRLH | 7400 | 84708 | 20354
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Motor Lube Axle Hoses | 2026-10-19 | 2026-10-19 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272014 | 18.06.2026 | 12000 | CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYM01 | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl AOC Fan Motor Rear | 2026-10-19 | 2026-10-19 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000026211 | 18.06.2026 | 12000 | CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYM02 | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Axle Lube Hyd Pump | 2026-10-19 | 2026-10-19 | 4 hrs | FY27 | 4 | 90010102 | B1 | 1000083394 | 27.11.2026 | 24000 | CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYPUM | 7400 | 84708 | 21673
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Replace Trans TCon System Hoses | 2026-10-19 | 2026-10-20 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000090145 | 01.10.2026 | 18000 | CCK-MP-HAUL-DT147 -TRNSYS-TRANS-TRNHO | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Replace Hoses Differential System | 2026-10-19 | 2026-10-19 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000090146 | 01.10.2026 | 18000 | CCK-MP-HAUL-DT147 -FDRSYS-DIFFL-DIFHO | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Transmisson Calibration | 2026-10-19 | 2026-10-19 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298725 | 18.10.2026 | 4500 | CCK-MP-HAUL-DT142 -TRNSYS-TRANS | 7400 | 87027 | 9824
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Brake Oil Cooler Front | 2026-10-19 | 2026-10-19 | 13 hrs | FY27 | 13 | 90010109 | B1 | 1000083325 | 26.10.2026 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BROCO-BROCF | 7400 | 87027 | 22338
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Brake Oil Cooler Rear | 2026-10-19 | 2026-10-19 | 13 hrs | FY27 | 13 | 90010108 | B1 | 1000083324 | 26.10.2026 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BROCO-BROCR | 7400 | 87027 | 22338
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Steering Brake Pump Compensator | 2026-10-19 | 2026-10-19 | 6 hrs | FY27 | 7 | 90019922 | B1 | 1000204758 | 28.09.2026 | 6000 | CCK-MP-HAUL-DT754 -STRSYS-STPMP | 6800 | 83256 | 5013
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Air Con Service & Overhaul | 2026-10-19 | 2026-10-20 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110623 | 20.10.2026 | 12 Monthly | CCK-MP-HAUL-DT754 -STRUCT-CABIN-AIRCN | 6800 | 83256 | 12630
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Grid Box Blower Motor LH | 2026-10-19 | 2026-10-19 | 10 hrs | FY27 | 10 | 90011331 | B1 | 1000094429 | 02.11.2026 | 25000 | CCK-MP-HAUL-DT754 -ELCTHV-HVGBM-GBMLH | 6800 | 83256 | 23370
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Wheel Motor RH | 2026-10-19 | 2026-10-21 | 45.5 hrs | FY27 | 83.5 | 90011336 | B1 | 1000094434 | 02.11.2026 | 25000 | CCK-MP-HAUL-DT754 -FDRSYS-WLMTR-WHMRH | 6800 | 83256 | 23370
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Replace Brake Cabinet Hoses | 2026-10-19 | 2026-10-20 | 32.5 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126211 | 02.11.2026 | 25000 | CCK-MP-HAUL-DT754 -BRKSYS-BRHLF | 6800 | 83256 | 30214
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Hoist LH | 2026-10-19 | 2026-10-19 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128593 | 25.09.2026 | 28000 | CCK-MP-HAUL-DT150 -HYDSYS-HOCYL-HCYLL | 7400 | 86656 | 26544
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Hoist RH | 2026-10-19 | 2026-10-19 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128594 | 25.09.2026 | 28000 | CCK-MP-HAUL-DT150 -HYDSYS-HOCYL-HCYLR | 7400 | 86656 | 26544
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Transmisson Calibration | 2026-10-19 | 2026-10-19 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298726 | 09.10.2026 | 4500 | CCK-MP-HAUL-DT143 -TRNSYS-TRANS | 7400 | 88225 | 11934
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Adjust Engine Valve Set | 2026-10-19 | 2026-10-19 | 12 hrs | FY27 | 24 | 90015645 | B1 | 1000269773 | 25.09.2026 | 4500 | CCK-MP-SUPP-SV220 -ENGINE | 5100 | 58303 | 11037
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Service Airconditioner | 2026-10-19 | 2026-10-20 | 24 hrs | FY27 | 24 | 90018538 | B2 | 1000269776 | 25.09.2026 | 4500 | CCK-MP-SUPP-SV220 -STRUCT-CABIN-AIRCN | 5100 | 58259 | 16547
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Radiator Fan Hoses | 2026-10-19 | 2026-10-19 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307507 | 07.09.2026 | 12000 | CCK-MP-HAUL-DT136 -ENGINE-COSYS-RADTR | 7400 | 87780 | 24460
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Motor Lube Axle Hoses | 2026-10-19 | 2026-10-19 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272000 | 07.09.2026 | 12000 | CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYM01 | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl AOC Fan Motor Rear | 2026-10-19 | 2026-10-19 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000025491 | 07.09.2026 | 12000 | CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYM02 | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Engine Midlife Complete | 2026-10-19 | 2026-10-20 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000155978 | 11.09.2026 | 12000 | CCK-MP-HAUL-DT136 -ENGINE | 7400 | 87780 | 87780
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Replace Steering System Hoses | 2026-10-25 | 2026-10-27 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000082893 | 25.10.2026 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STHLF-STRHO | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Steering Hyd Oil Cooler | 2026-10-25 | 2026-10-25 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000106979 | 25.10.2026 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STOCO | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Wheel End RH | 2026-10-26 | 2026-10-27 | 32.5 hrs | FY27 | 58.5 | 90007352 | B1 | 1000023783 | 20.09.2026 | 24000 | CCK-MP-HAUL-DT057 -FDRSYS-FDRVE-FDRRH | 7400 | 91273 | 22845
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Radiator Fan Hoses | 2026-10-26 | 2026-10-26 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307511 | 25.05.2026 | 12000 | CCK-MP-HAUL-DT138 -ENGINE-COSYS-RADTR | 7400 | 82982 | 35790
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Steering Bell Crank & Links | 2026-10-26 | 2026-10-27 | 20 hrs | FY27 | 36 | 90028566 | B1 | 1000317622 | 12.03.2026 | 30000 | CCK-MP-HAUL-DT138 -STRSYS-STLTR-STLAC | 7400 | 82982 | 29498
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Replace Hoses Hoist System | 2026-10-26 | 2026-10-27 | 20 hrs | FY27 | 40 | 90010105 | B1 | 1000083244 | 09.09.2026 | 24000 | CCK-MP-HAUL-DT138 -HYDSYS-HDHLF-HSTHO | 7400 | 82982 | 23314
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Replace Brake System Hoses | 2026-10-26 | 2026-10-28 | 46 hrs | FY27 | 90 | 90010129 | B4 | 1000083250 | 03.09.2026 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BRHLF-BRHOS | 7400 | 82982 | 23396
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Brake Cooling System Hoses | 2026-10-26 | 2026-10-27 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000083251 | 03.09.2026 | 24000 | CCK-MP-HAUL-DT138 -BRKSYS-BRHLF-CBRHO | 7400 | 82982 | 23396
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Drive Line Axle LH | 2026-10-26 | 2026-10-26 | 2 hrs | FY27 | 4 | 90014919 | B1 | 1000124601 | 01.09.2026 | 24000 | CCK-MP-HAUL-DT138 -FDRSYS-DRLAX-AXLLH | 7400 | 82982 | 23396
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Drive Line Axle RH | 2026-10-26 | 2026-10-26 | 2 hrs | FY27 | 4 | 90014943 | B1 | 1000124602 | 01.09.2026 | 24000 | CCK-MP-HAUL-DT138 -FDRSYS-DRLAX-AXLRH | 7400 | 82982 | 23396
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Transmisson Calibration | 2026-10-26 | 2026-10-26 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298723 | 16.10.2026 | 4500 | CCK-MP-HAUL-DT138 -TRNSYS-TRANS | 7400 | 82982 | 6438
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Steering HMU | 2026-10-26 | 2026-10-26 | 8 hrs | FY27 | 8 | 90002384 | B1 | 1000025630 | 03.09.2026 | 24000 | CCK-MP-HAUL-DT138 -STRSYS-STHMU | 7400 | 82982 | 23396
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Steering LH | 2026-10-26 | 2026-10-26 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000025631 | 22.10.2026 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STRCY-STCYL | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Steering RH | 2026-10-26 | 2026-10-26 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000025632 | 22.10.2026 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STRCY-STCYR | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Ovhl Accumulator Steering Rear | 2026-10-26 | 2026-10-26 | 8 hrs | FY27 | 12 | 90002386 | B1 | 1000025635 | 03.09.2026 | 24000 | CCK-MP-HAUL-DT138 -STRSYS-STACC-SACCR | 7400 | 82982 | 23396
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Service Air Conditioner 12M | 2026-10-26 | 2026-10-27 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174171 | 14.10.2026 | 12 Monthly | CCK-MP-HAUL-DT138 -STRUCT-CABIN-AIRCN | 7400 | 82982 | 35790
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Replace Steering System Hoses | 2026-10-26 | 2026-10-28 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083254 | 22.10.2026 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STHLF-STRHO | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Steering Hyd Oil Cooler | 2026-10-26 | 2026-10-26 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000106996 | 22.10.2026 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STOCO | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Auto Lube Pump | 2026-10-26 | 2026-10-26 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285783 | 14.11.2026 | 8000 | CCK-MP-HAUL-DT138 -GRSYST-ALBPP | 7400 | 82982 | 5976
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Air Con Service & Overhaul | 2026-10-26 | 2026-10-27 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110640 | 30.09.2026 | 12 Monthly | CCK-MP-HAUL-DT771 -STRUCT-CABIN-AIRCN | 6800 | 84423 | 84423
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Auto Lube Pump | 2026-10-26 | 2026-10-26 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095355 | 18.10.2026 | 8000 | CCK-MP-HAUL-DT771 -GRSYST-ALBPP | 6800 | 84423 | 6819
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Spider Trans Driveshaft | 2026-10-26 | 2026-10-26 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154976 | 13.11.2026 | 6000 | CCK-MP-HAUL-DT149 -FDRSYS-DRSHT-UNVSL | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Torque Converter | 2026-10-26 | 2026-10-27 | 27 hrs | FY27 | 53 | 90002369 | B1 | 1000025419 | 28.09.2026 | 24000 | CCK-MP-HAUL-DT135 -TRNSYS-TRQUE | 7400 | 82965 | 23080
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Transmisson Calibration | 2026-10-26 | 2026-10-26 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298720 | 01.10.2026 | 4500 | CCK-MP-HAUL-DT135 -TRNSYS-TRANS | 7400 | 82965 | 7974
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Replace Trans TCon System Hoses | 2026-10-26 | 2026-10-27 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000091421 | 12.10.2026 | 18000 | CCK-MP-HAUL-DT135 -TRNSYS-TRANS-TRNHO | 7400 | 82965 | 36862
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Steering LH | 2026-10-26 | 2026-10-26 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000025246 | 24.09.2026 | 15000 | CCK-MP-HAUL-DT130 -STRSYS-STRCY-STCYL | 7400 | 85185 | 14144
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Spiders Pump Drive Shaft | 2026-10-26 | 2026-10-26 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000025223 | 04.11.2026 | 18000 | CCK-MP-HAUL-DT130 -ENGINE-PMPDR-DRSHT | 7400 | 85185 | 16330
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Operators Seat | 2026-10-26 | 2026-10-26 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000025260 | 20.11.2026 | 15000 | CCK-MP-HAUL-DT130 -STRUCT-CABIN-SEATS | 7400 | 85185 | 12955
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Water Tank Cannon & Spray Sys Insp | 2026-10-26 | 2026-10-26 | 3 hrs | FY27 | 3 | 90036927 | B1 | 1000368892 | 02.10.2026 | 6 Monthly | CCK-MP-SUPP-WC224 -STRUCT-WTANK | 5000 | 70936 | 6229
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Spider Trans Driveshaft | 2026-10-29 | 2026-10-29 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154986 | 29.10.2026 | 6000 | CCK-MP-HAUL-DT157 -FDRSYS-DRSHT-UNVSL | 7400 | 83026 | 4183
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Operator Cabin Dash Bulbs | 2026-10-30 | 2026-10-30 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158220 | 30.10.2026 | 3000 | CCK-MP-HAUL-DT755 -STRUCT-CABIN | 6800 | 84587 | 84587
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Steering LH | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000027080 | 12.10.2026 | 15000 | CCK-MP-HAUL-DT160 -STRSYS-STRCY-STCYL | 7400 | 85085 | 13594
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Steering RH | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000027081 | 12.10.2026 | 15000 | CCK-MP-HAUL-DT160 -STRSYS-STRCY-STCYR | 7400 | 85037 | 13594
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Transmisson Calibration | 2026-11-02 | 2026-11-02 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298738 | 31.10.2026 | 4500 | CCK-MP-HAUL-DT160 -TRNSYS-TRANS | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Rear Axle Linkages | 2026-11-02 | 2026-11-04 | 57 hrs | FY27 | 113 | 90002396 | B1 | 1000023685 | 26.08.2025 | 24000 | CCK-MP-HAUL-DT055 -STRUCT-CHASS-AXLIK | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Cyl Steering RH | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000023671 | 12.10.2026 | 15000 | CCK-MP-HAUL-DT055 -STRSYS-STRCY-STCYR | 7400 | 84122 | 13600
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Auto Lube Pump | 2026-11-02 | 2026-11-02 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094348 | 29.10.2026 | 8000 | CCK-MP-HAUL-DT752 -GRSYST-ALBPP | 6800 | 80681 | 6552
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Hoist LH | 2026-11-02 | 2026-11-02 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128613 | 21.09.2026 | 28000 | CCK-MP-HAUL-DT5255-HYDSYS-HOCYL-HCYLL | 7400 | 87580 | 27012
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Hoist RH | 2026-11-02 | 2026-11-02 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128614 | 23.09.2026 | 28000 | CCK-MP-HAUL-DT5255-HYDSYS-HOCYL-HCYLR | 7400 | 87580 | 27012
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Hub & Spindle LH | 2026-11-09 | 2026-11-10 | 32 hrs | FY27 | 60 | 90011363 | B1 | 1000095094 | 28.10.2026 | 18000 | CCK-MP-HAUL-DT766 -STRUCT-AXLES-HUBLH | 6800 | 78074 | 17489
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Cyl Suspension LHF | 2026-11-09 | 2026-11-11 | 60 hrs | FY27 | 112 | 90011365 | B1 | 1000095096 | 28.10.2026 | 18000 | CCK-MP-HAUL-DT766 -STRUCT-SUSPN-SCYLF | 6800 | 78074 | 17489
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Hoist LH | 2026-11-09 | 2026-11-09 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128597 | 14.08.2026 | 28000 | CCK-MP-HAUL-DT153 -HYDSYS-HOCYL-HCYLL | 7400 | 84230 | 27608
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Steering Linkages | 2026-11-09 | 2026-11-09 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317641 | 17.10.2026 | 15000 | CCK-MP-HAUL-DT153 -STRSYS-STLTR | 7400 | 84230 | 21906
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Service Air Conditioner 12M | 2026-11-09 | 2026-11-10 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174181 | 14.10.2026 | 12 Monthly | CCK-MP-HAUL-DT153 -STRUCT-CABIN-AIRCN | 7400 | 84230 | 34787
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Operators Seat | 2026-11-09 | 2026-11-09 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000026633 | 17.10.2026 | 15000 | CCK-MP-HAUL-DT153 -STRUCT-CABIN-SEATS | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Suspension RHF | 2026-11-09 | 2026-11-11 | 43 hrs | FY27 | 84 | 90002408 | B2 | 1000067615 | 02.11.2026 | 28000 | CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYRF | 7400 | 84230 | 26146
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Replace Steering System Hoses | 2026-11-09 | 2026-11-11 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083501 | 17.10.2026 | 15000 | CCK-MP-HAUL-DT153 -STRSYS-STHLF-STRHO | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Steering Hyd Oil Cooler | 2026-11-09 | 2026-11-09 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107008 | 17.10.2026 | 15000 | CCK-MP-HAUL-DT153 -STRSYS-STOCO | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Pump Drive | 2026-11-09 | 2026-11-10 | 20 hrs | FY27 | 39 | 90002365 | B1 | 1000024970 | 21.05.2026 | 24000 | CCK-MP-HAUL-DT126 -ENGINE-PMPDR | 7400 | 88657 | 25790
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Hoist LH | 2026-11-09 | 2026-11-09 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128565 | 21.05.2026 | 28000 | CCK-MP-HAUL-DT126 -HYDSYS-HOCYL-HCYLL | 7400 | 88657 | 25780
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Hoist RH | 2026-11-09 | 2026-11-09 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128566 | 17.01.2026 | 28000 | CCK-MP-HAUL-DT126 -HYDSYS-HOCYL-HCYLR | 7400 | 88657 | 28279
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Replace Brake System Hoses | 2026-11-09 | 2026-11-11 | 46 hrs | FY27 | 90 | 90010129 | B3 | 1000083098 | 21.05.2026 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BRHLF-BRHOS | 7400 | 88657 | 25790
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Brake Cooling System Hoses | 2026-11-09 | 2026-11-10 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000083099 | 20.05.2026 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BRHLF-CBRHO | 7400 | 88657 | 25809
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Replace Steering System Hoses | 2026-11-09 | 2026-11-11 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083102 | 02.03.2026 | 15000 | CCK-MP-HAUL-DT126 -STRSYS-STHLF-STRHO | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Steering Hyd Oil Cooler | 2026-11-09 | 2026-11-09 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107024 | 02.03.2026 | 15000 | CCK-MP-HAUL-DT126 -STRSYS-STOCO | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Transmisson Calibration | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298677 | 11.12.2026 | 4500 | CCK-MP-HAUL-DT126 -TRNSYS-TRANS | 7400 | 88657 | 2432
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Engine Midlife Complete | 2026-11-09 | 2026-11-13 | 94 hrs | FY27 | 122 | 90028722 | B1 | 1000289478 | 09.11.2026 | 10000 | CCK-MP-SUPP-WC3111-ENGINE | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Rear Axle Oil Pump | 2026-11-09 | 2026-11-09 | 2 hrs | FY27 | 2 | 90003996 | B2 | 1000079192 | 09.11.2026 | 10000 | CCK-MP-SUPP-WC3111-FDRSYS-AXLEC-HYPUM | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Rear Axle Cooling Fan Motor | 2026-11-09 | 2026-11-09 | 2 hrs | FY27 | 2 | 90003997 | B2 | 1000079193 | 09.11.2026 | 10000 | CCK-MP-SUPP-WC3111-FDRSYS-AXLEC-MTFAN | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Overhaul Airconditioner | 2026-11-09 | 2026-11-10 | 24 hrs | FY27 | 24 | 90028727 | B1 | 1000289480 | 09.11.2026 | 10000 | CCK-MP-SUPP-WC3111-STRUCT-CABIN-AIRCN | 5600 | 51257 | 8333
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Suspension LHR | 2026-11-11 | 2026-11-12 | 22 hrs | FY27 | 39 | 90002409 | B1 | 1000026047 | 11.11.2026 | 28000 | CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYLR | 7400 | 87580 | 25990
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Suspension LHF | 2026-11-14 | 2026-11-16 | 43 hrs | FY27 | 84 | 90002408 | B1 | 1000067577 | 14.11.2026 | 28000 | CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYLF | 7400 | 87580 | 25846
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Suspension RHF | 2026-11-14 | 2026-11-16 | 43 hrs | FY27 | 84 | 90002408 | B2 | 1000067579 | 14.11.2026 | 28000 | CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYRF | 7400 | 87580 | 25846
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Replace Operator Cabin Dash Bulbs | 2026-11-14 | 2026-11-14 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158227 | 14.11.2026 | 3000 | CCK-MP-HAUL-DT762 -STRUCT-CABIN | 6800 | 76486 | 20565
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Cyl Steering LH | 2026-11-16 | 2026-11-16 | 10 hrs | FY27 | 16 | 90011350 | B1 | 1000094762 | 30.10.2026 | 15000 | CCK-MP-HAUL-DT760 -STRSYS-STRCY-STCYL | 6800 | 80390 | 13611
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Air Con Service & Overhaul | 2026-11-16 | 2026-11-17 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110629 | 03.11.2026 | 12 Monthly | CCK-MP-HAUL-DT760 -STRUCT-CABIN-AIRCN | 6800 | 80390 | 23992
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Wheel Motor Oil RH | 2026-11-16 | 2026-11-16 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338205 | 02.11.2026 | 25000 | CCK-MP-HAUL-DT754 -FDRSYS-WLMTR-WHMRH | 6800 | 83256 | 23370
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Hub and Spindle RH | 2026-11-16 | 2026-11-16 | 12 hrs | FY27 | 22 | 90011571 | B1 | 1000098147 | 16.11.2026 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-AXLES-HUBRH | 4000 | 56923 | 16518
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Transmisson Calibration | 2026-11-16 | 2026-11-16 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298678 | 18.11.2026 | 4500 | CCK-MP-HAUL-DT127 -TRNSYS-TRANS | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 250hr Initial Valve Set | 2026-11-18 | 2026-11-18 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000155868 | 18.11.2026 | 250 | CCK-MP-HAUL-DT055 -ENGINE | 7400 | 84122 | 54657
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Final Drive LH | 2026-11-18 | 2026-11-19 | 26 hrs | FY27 | 50 | 90011542 | B1 | 1000098120 | 18.11.2026 | 18000 | CCK-MP-SUPP-WC221 -FDRSYS-FDRVE-FDRLH | 4000 | 56923 | 16506
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Final Drive RH | 2026-11-18 | 2026-11-19 | 26 hrs | FY27 | 50 | 90011543 | B1 | 1000098121 | 18.11.2026 | 18000 | CCK-MP-SUPP-WC221 -FDRSYS-FDRVE-FDRRH | 4000 | 56923 | 16506
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Hydraulic Oil Cooler | 2026-11-18 | 2026-11-18 | 12 hrs | FY27 | 12 | 90011563 | B1 | 1000098139 | 18.11.2026 | 18000 | CCK-MP-SUPP-WC221 -HYDSYS-HDOCO | 4000 | 56923 | 16496
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Hub and Spindle LH | 2026-11-18 | 2026-11-18 | 12 hrs | FY27 | 22 | 90011570 | B1 | 1000098146 | 18.11.2026 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-AXLES-HUBLH | 4000 | 56923 | 16506
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Service Air Conditioner 12M | 2026-11-20 | 2026-11-21 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174182 | 20.11.2026 | 12 Monthly | CCK-MP-HAUL-DT155 -STRUCT-CABIN-AIRCN | 7400 | 81407 | 5297
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Water Cannon Maintenance | 2026-11-21 | 2026-11-21 | 3 hrs | FY27 | 3 | 90001682 | B1 | 1000107576 | 21.11.2026 | 6 Monthly | CCK-MP-SUPP-WC009 -STRUCT-WTANK-SPRAY
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Repl Sepura SCC Microphone | 2026-11-21 | 2026-11-21 | 0.5 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289619 | 21.11.2026 | 12 Monthly | CCK-MP-SUPP-WC009 -COMMUN-RADIO
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Park Brake Control Valve | 2026-11-22 | 2026-11-22 | 10 hrs | FY27 | 10 | 90000914 | B2 | 1000033363 | 22.11.2026 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRVLV | 5000 | 75244 | 20486
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Steering Valve | 2026-11-22 | 2026-11-22 | 6 hrs | FY27 | 12 | 90000918 | B2 | 1000033368 | 22.11.2026 | 22000 | CCK-MP-SUPP-WC225 -STRSYS-STVLV | 5000 | 75244 | 10710
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Hoist RH | 2026-11-23 | 2026-11-23 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128542 | 28.09.2026 | 28000 | CCK-MP-HAUL-DT058 -HYDSYS-HOCYL-HCYLR | 7400 | 87864 | 26627
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Adjust Engine Valve Set | 2026-11-23 | 2026-11-23 | 12 hrs | FY27 | 24 | 90015766 | B1 | 1000269919 | 26.08.2026 | 4500 | CCK-MP-SUPP-WC221 -ENGINE | 4300 | 56923 | 12761
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Service Airconditioner | 2026-11-23 | 2026-11-24 | 24 hrs | FY27 | 24 | 90018538 | B2 | 1000269921 | 26.08.2026 | 4500 | CCK-MP-SUPP-WC221 -STRUCT-CABIN-AIRCN | 4000 | 56923 | 4347
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 250hr Initial Valve Set | 2026-11-23 | 2026-11-23 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000167061 | 23.11.2026 | 250 | CCK-MP-HAUL-DT5314-ENGINE | 7400 | 45898 | 22018
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Steering LH | 2026-11-23 | 2026-11-23 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000027146 | 24.09.2026 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STRCY-STCYL | 7400 | 80609 | 13960
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Transmisson Calibration | 2026-11-23 | 2026-11-23 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298739 | 03.12.2026 | 4500 | CCK-MP-HAUL-DT161 -TRNSYS-TRANS | 7400 | 80609 | 12241
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Brake Slack Adjuster Front | 2026-11-23 | 2026-11-23 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000027142 | 05.12.2026 | 20000 | CCK-MP-HAUL-DT161 -BRKSYS-SLACK-SLACF | 7400 | 80609 | 17509
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Engine Midlife Complete | 2026-11-23 | 2026-11-24 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000155948 | 01.11.2026 | 12000 | CCK-MP-HAUL-DT099 -ENGINE | 7400 | 87442 | 32853
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Radiator Fan Hoses | 2026-11-23 | 2026-11-23 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307495 | 01.11.2026 | 12000 | CCK-MP-HAUL-DT099 -ENGINE-COSYS-RADTR | 7400 | 87442 | 32853
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Motor Lube Axle Hoses | 2026-11-23 | 2026-11-23 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000271988 | 01.11.2026 | 12000 | CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYM01 | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl AOC Fan Motor Rear | 2026-11-23 | 2026-11-23 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000024857 | 01.11.2026 | 12000 | CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYM02 | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Auto Lube Pump | 2026-11-23 | 2026-11-23 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285635 | 22.11.2026 | 8000 | CCK-MP-HAUL-DT099 -GRSYST-ALBPP | 7400 | 87442 | 14730
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Transmisson Calibration | 2026-11-24 | 2026-11-24 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298666 | 24.11.2026 | 4500 | CCK-MP-HAUL-DT058 -TRNSYS-TRANS | 7400 | 87864 | 1976
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Cylinder Suspension LHR | 2026-11-24 | 2026-11-24 | 6 hrs | FY27 | 10 | 90011574 | B1 | 1000098150 | 24.11.2026 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-SUSPN-SCYLR | 4000 | 56923 | 16424
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Cyl Steering LH | 2026-11-27 | 2026-11-27 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000026750 | 27.11.2026 | 15000 | CCK-MP-HAUL-DT155 -STRSYS-STRCY-STCYL | 7400 | 81407 | 12608
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Auto Lube Pump | 2026-11-27 | 2026-11-27 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094613 | 27.11.2026 | 8000 | CCK-MP-HAUL-DT757 -GRSYST-ALBPP | 6800 | 80700 | 14095
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Operators Seat | 2026-11-29 | 2026-11-29 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000026303 | 29.11.2026 | 15000 | CCK-MP-HAUL-DT148 -STRUCT-CABIN-SEATS | 7400 | 85451 | 13242
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Engine Cat C175-16 | 2026-11-30 | 2026-12-03 | 84 hrs | FY27 | 137 | 90015881 | B1 | 1000155865 | 05.11.2026 | 24000 | CCK-MP-HAUL-DT055 -ENGINE | 7400 | 84122 | 54657
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Auto Lube Pump | 2026-11-30 | 2026-11-30 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285627 | 30.11.2026 | 8000 | CCK-MP-HAUL-DT082 -GRSYST-ALBPP | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Differential | 2026-11-30 | 2026-12-01 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000127964 | 10.10.2026 | 18000 | CCK-MP-HAUL-DT221 -FDRSYS-DIFFL | 7400 | 57237 | 16760
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Replace Hoses Differential System | 2026-11-30 | 2026-11-30 | 5 hrs | FY27 | 5 | 90010101 | B4 | 1000127999 | 17.04.2026 | 18000 | CCK-MP-HAUL-DT221 -FDRSYS-DIFFL-DIFHO | 7400 | 57237 | 20442
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Replace Trans TCon System Hoses | 2026-11-30 | 2026-12-01 | 20 hrs | FY27 | 20 | 90010099 | B2 | 1000127997 | 17.04.2026 | 18000 | CCK-MP-HAUL-DT221 -TRNSYS-TRANS-TRNHO | 7400 | 57237 | 20442
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Engine Midlife Complete | 2026-11-30 | 2026-12-01 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000156086 | 28.10.2026 | 12000 | CCK-MP-HAUL-DT221 -ENGINE | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Radiator Fan Hoses | 2026-11-30 | 2026-11-30 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307553 | 26.10.2026 | 12000 | CCK-MP-HAUL-DT221 -ENGINE-COSYS-RADTR | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Motor Lube Axle Hoses | 2026-11-30 | 2026-11-30 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272038 | 26.10.2026 | 12000 | CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYM01 | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl AOC Fan Motor Rear | 2026-11-30 | 2026-11-30 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000127968 | 26.10.2026 | 12000 | CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYM02 | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Cyl Steering LH | 2026-11-30 | 2026-11-30 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000127979 | 05.11.2026 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STRCY-STCYL | 7400 | 57237 | 13199
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Cyl Steering RH | 2026-11-30 | 2026-11-30 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000127980 | 05.11.2026 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STRCY-STCYR | 7400 | 57237 | 13199
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Wheel Group Front LH | 2026-11-30 | 2026-12-01 | 28 hrs | FY27 | 54 | 90017286 | B1 | 1000157175 | 07.10.2026 | 24000 | CCK-MP-HAUL-DT158 -STRUCT-AXLES-HUBLH | 7400 | 85964 | 22843
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Radiator Fan Hoses | 2026-11-30 | 2026-11-30 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307543 | 02.12.2026 | 12000 | CCK-MP-HAUL-DT158 -ENGINE-COSYS-RADTR | 7400 | 85964 | 33728
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Transmisson Calibration | 2026-11-30 | 2026-11-30 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298736 | 08.12.2026 | 4500 | CCK-MP-HAUL-DT158 -TRNSYS-TRANS | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Steering RH | 2026-11-30 | 2026-11-30 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000024932 | 21.11.2026 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STRCY-STCYR | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Steering Linkages | 2026-11-30 | 2026-11-30 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317607 | 21.11.2026 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STLTR | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Replace Steering System Hoses | 2026-11-30 | 2026-12-02 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083083 | 21.11.2026 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STHLF-STRHO | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Steering Hyd Oil Cooler | 2026-11-30 | 2026-11-30 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000106988 | 21.11.2026 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STOCO | 7400 | 87135 | 12861
777G SV | Onsite PM | Haul | Fortescue | SV221 | 24 Monthly HP Grease Lines Replace | 2026-11-30 | 2026-11-30 | 3 hrs | FY27 | 3 | 90016826 | B1 | 1000152003 | 18.11.2026 | 24 Monthly | CCK-MP-SUPP-SV221 -MODULE | 5100 | 64374 | 64374
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Hub & Spindle LH | 2026-11-30 | 2026-12-01 | 32 hrs | FY27 | 60 | 90011363 | B1 | 1000095412 | 06.11.2026 | 18000 | CCK-MP-HAUL-DT772 -STRUCT-AXLES-HUBLH | 6800 | 85256 | 18043
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Replace Steering System Hoses | 2026-11-30 | 2026-12-02 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000091438 | 30.11.2026 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STHLF-STRHO | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Pump Drive | 2026-12-01 | 2026-12-02 | 20 hrs | FY27 | 39 | 90002365 | B1 | 1000023961 | 01.12.2026 | 24000 | CCK-MP-HAUL-DT082 -ENGINE-PMPDR | 7400 | 84374 | 21416
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Operator Seat | 2026-12-01 | 2026-12-01 | 3 hrs | FY27 | 6 | 90011567 | B1 | 1000098143 | 01.12.2026 | 6000 | CCK-MP-SUPP-WC221 -STRUCT-CABIN-SEATS | 4000 | 56923 | 4771
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Pump Drive | 2026-12-03 | 2026-12-04 | 20 hrs | FY27 | 39 | 90002365 | B1 | 1000023646 | 03.12.2026 | 24000 | CCK-MP-HAUL-DT055 -ENGINE-PMPDR | 7400 | 84122 | 21547
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Hub & Spindle RH | 2026-12-03 | 2026-12-04 | 32 hrs | FY27 | 60 | 90011364 | B1 | 1000094406 | 03.12.2026 | 18000 | CCK-MP-HAUL-DT753 -STRUCT-AXLES-HUBRH | 6800 | 85999 | 15852
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Operators Seat | 2026-12-03 | 2026-12-03 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000024567 | 03.12.2026 | 15000 | CCK-MP-HAUL-DT094 -STRUCT-CABIN-SEATS | 7400 | 88788 | 12373
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Steering LH | 2026-12-03 | 2026-12-03 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000026156 | 03.12.2026 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STRCY-STCYL | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Steering RH | 2026-12-03 | 2026-12-03 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000026157 | 03.12.2026 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STRCY-STCYR | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Steering Linkages | 2026-12-03 | 2026-12-03 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317629 | 03.12.2026 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STLTR | 7400 | 83062 | 31809
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Operator Cabin Dash Bulbs | 2026-12-04 | 2026-12-04 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158216 | 04.12.2026 | 3000 | CCK-MP-HAUL-DT751 -STRUCT-CABIN | 6800 | 86211 | 11291
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Transmisson Calibration | 2026-12-04 | 2026-12-04 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298729 | 04.12.2026 | 4500 | CCK-MP-HAUL-DT148 -TRNSYS-TRANS | 7400 | 85451 | 10451
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Replace Operator Cabin Dash Bulbs | 2026-12-04 | 2026-12-04 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158221 | 04.12.2026 | 3000 | CCK-MP-HAUL-DT756 -STRUCT-CABIN | 6800 | 78754 | 78754
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Spider Trans Driveshaft | 2026-12-06 | 2026-12-06 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000272710 | 06.12.2026 | 6000 | CCK-MP-SUPP-PM0001-FDRSYS-DRSHT-UNVSL | 3400 | 48287 | 3257
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Wheel Motor Oil LH | 2026-12-07 | 2026-12-07 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338220 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -FDRSYS-WLMTR-WHMLH | 6800 | 76486 | 22280
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Wheel Motor Oil RH | 2026-12-07 | 2026-12-07 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338221 | 16.12.2026 | 25000 | CCK-MP-HAUL-DT762 -FDRSYS-WLMTR-WHMRH | 6800 | 76486 | 22280
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Transmission Oil Cooler | 2026-12-07 | 2026-12-07 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000082955 | 16.12.2026 | 18000 | CCK-MP-HAUL-DT090 -TRNSYS-TROLC | 7400 | 81670 | 15228
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 250hr Initial Valve Set | 2026-12-07 | 2026-12-07 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000155982 | 05.10.2026 | 250 | CCK-MP-HAUL-DT137 -ENGINE | 7400 | 84196 | 49397
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Hoist RH | 2026-12-07 | 2026-12-07 | 17 hrs | FY27 | 33 | 90011358 | B1 | 1000094293 | 09.10.2026 | 25000 | CCK-MP-HAUL-DT751 -HYDSYS-HOCYL-HCYLR | 6800 | 86211 | 24686
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Engine Midlife Complete | 2026-12-07 | 2026-12-09 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285169 | 16.11.2026 | 12500 | CCK-MP-HAUL-DT751 -ENGINE | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Auto Lube Pump | 2026-12-07 | 2026-12-07 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094295 | 01.12.2026 | 8000 | CCK-MP-HAUL-DT751 -GRSYST-ALBPP | 6800 | 86211 | 22422
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Steering Bell Crank & Links | 2026-12-07 | 2026-12-08 | 20 hrs | FY27 | 36 | 90028566 | B1 | 1000317658 | 21.09.2026 | 30000 | CCK-MP-HAUL-DT222 -STRSYS-STLTR-STLAC | 7400 | 55735 | 28978
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Drive Shaft Transmission | 2026-12-07 | 2026-12-07 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154999 | 14.11.2026 | 18000 | CCK-MP-HAUL-DT222 -FDRSYS-DRSHT | 7400 | 55735 | 15829
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Hyd Pump Steering & Brake | 2026-12-07 | 2026-12-08 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204744 | 23.10.2026 | 12000 | CCK-MP-HAUL-DT764 -STRSYS-STPMP | 6800 | 75315 | 9695
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Replace Operator Cabin Dash Bulbs | 2026-12-07 | 2026-12-07 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158229 | 22.11.2026 | 3000 | CCK-MP-HAUL-DT764 -STRUCT-CABIN | 6800 | 75315 | 21117
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Pump Brake Cooling | 2026-12-07 | 2026-12-07 | 9 hrs | FY27 | 17 | 90002379 | B1 | 1000026611 | 18.11.2026 | 24000 | CCK-MP-HAUL-DT153 -BRKSYS-HYFPP | 7400 | 84230 | 21755
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Wheel Group Front LH | 2026-12-07 | 2026-12-08 | 28 hrs | FY27 | 54 | 90017286 | B1 | 1000157169 | 15.11.2026 | 24000 | CCK-MP-HAUL-DT153 -STRUCT-AXLES-HUBLH | 7400 | 84230 | 21882
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Service Air Conditioner 12M | 2026-12-09 | 2026-12-10 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174183 | 09.12.2026 | 12 Monthly | CCK-MP-HAUL-DT157 -STRUCT-CABIN-AIRCN | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Transmisson Calibration | 2026-12-10 | 2026-12-10 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298672 | 10.12.2026 | 4500 | CCK-MP-HAUL-DT094 -TRNSYS-TRANS | 7400 | 88788 | 5404
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Transmisson Calibration | 2026-12-11 | 2026-12-11 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298665 | 11.12.2026 | 4500 | CCK-MP-HAUL-DT057 -TRNSYS-TRANS | 7400 | 91273 | 10672
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Replace Operator Cabin Dash Bulbs | 2026-12-11 | 2026-12-11 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158235 | 11.12.2026 | 3000 | CCK-MP-HAUL-DT770 -STRUCT-CABIN | 6800 | 79305 | 79305
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Front Wheel Bearings RH | 2026-12-13 | 2026-12-14 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157202 | 13.12.2026 | 16000 | CCK-MP-HAUL-DT082 -STRUCT-AXLES-FWBRH | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Brake Oil Cooler Front | 2026-12-14 | 2026-12-14 | 13 hrs | FY27 | 13 | 90010109 | B1 | 1000083401 | 27.11.2026 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BROCO-BROCF | 7400 | 84708 | 21673
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Brake Oil Cooler Rear | 2026-12-14 | 2026-12-14 | 13 hrs | FY27 | 13 | 90010108 | B1 | 1000083400 | 27.11.2026 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BROCO-BROCR | 7400 | 84708 | 21673
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Steering RH | 2026-12-14 | 2026-12-14 | 10 hrs | FY27 | 20 | 90002385 | B2 | 1000026223 | 15.11.2026 | 15000 | CCK-MP-HAUL-DT147 -STRSYS-STRCY-STCYR | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Front Wheel Bearings LH | 2026-12-14 | 2026-12-15 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157108 | 14.12.2026 | 16000 | CCK-MP-HAUL-DT056 -STRUCT-AXLES-FWBLH | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Front Wheel Bearings RH | 2026-12-14 | 2026-12-15 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157196 | 14.12.2026 | 16000 | CCK-MP-HAUL-DT056 -STRUCT-AXLES-FWBRH | 7400 | 84421 | 13282
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Cyl Hoist RH | 2026-12-14 | 2026-12-14 | 17 hrs | FY27 | 33 | 90011358 | B1 | 1000094452 | 19.12.2026 | 25000 | CCK-MP-HAUL-DT754 -HYDSYS-HOCYL-HCYLR | 6800 | 83256 | 22493
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Auto Lube Pump | 2026-12-14 | 2026-12-14 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285791 | 28.11.2026 | 8000 | CCK-MP-HAUL-DT150 -GRSYST-ALBPP | 7400 | 86656 | 5319
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Transmission | 2026-12-14 | 2026-12-15 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000272345 | 10.12.2026 | 18000 | CCK-MP-HAUL-DT150 -TRNSYS-TRANS | 7400 | 86608 | 14649
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Drive Shaft Transmission | 2026-12-14 | 2026-12-14 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154979 | 10.12.2026 | 18000 | CCK-MP-HAUL-DT150 -FDRSYS-DRSHT | 7400 | 86656 | 14622
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Spiders Pump Drive Shaft | 2026-12-14 | 2026-12-14 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026397 | 01.01.2027 | 18000 | CCK-MP-HAUL-DT150 -ENGINE-PMPDR-DRSHT | 7400 | 86656 | 14622
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Replace Steering HMU | 2026-12-14 | 2026-12-14 | 12 hrs | FY27 | 12 | 90000265 | B2 | 1000037399 | 08.06.2026 | 18000 | CCK-MP-SUPP-WC009 -STRSYS-STHMU | 1500 | 34052 | 17579
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Replace Pump Hoist | 2026-12-14 | 2026-12-14 | 4 hrs | FY27 | 4 | 90000260 | B2 | 1000037404 | 27.03.2026 | 9000 | CCK-MP-SUPP-WC009 -HYDSYS-HOPMP | 1500 | 34052 | 8933
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Water Cannon Maintenance | 2026-12-14 | 2026-12-14 | 3 hrs | FY27 | 3 | 90001682 | B1 | 1000107576 | 25.05.2026 | 6 Monthly | CCK-MP-SUPP-WC009 -STRUCT-WTANK-SPRAY
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Engine Midlife Complete | 2026-12-14 | 2026-12-18 | 94 hrs | FY27 | 122 | 90028722 | B1 | 1000289484 | 07.12.2026 | 10000 | CCK-MP-SUPP-WC3112-ENGINE | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl PTO Uni's & Driveshaft | 2026-12-14 | 2026-12-14 | 2 hrs | FY27 | 2 | 90031094 | B1 | 1000307816 | 07.12.2026 | 10000 | CCK-MP-SUPP-WC3112-ENGINE-PMPDR-DRSHT | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Rear Axle Oil Pump | 2026-12-14 | 2026-12-14 | 2 hrs | FY27 | 2 | 90003996 | B2 | 1000079257 | 07.12.2026 | 10000 | CCK-MP-SUPP-WC3112-FDRSYS-AXLEC-HYPUM | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Rear Axle Cooling Fan Motor | 2026-12-14 | 2026-12-14 | 2 hrs | FY27 | 2 | 90003997 | B2 | 1000079258 | 07.12.2026 | 10000 | CCK-MP-SUPP-WC3112-FDRSYS-AXLEC-MTFAN | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Overhaul Airconditioner | 2026-12-14 | 2026-12-15 | 24 hrs | FY27 | 24 | 90028727 | B1 | 1000289486 | 07.12.2026 | 10000 | CCK-MP-SUPP-WC3112-STRUCT-CABIN-AIRCN | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Seat Operators | 2026-12-14 | 2026-12-14 | 3 hrs | FY27 | 6 | 90004012 | B1 | 1000161837 | 07.12.2026 | 10000 | CCK-MP-SUPP-WC3112-STRUCT-CABIN-SEATS | 5600 | 52240 | 8166
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Transmission | 2026-12-14 | 2026-12-15 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000272357 | 02.12.2026 | 18000 | CCK-MP-HAUL-DT159 -TRNSYS-TRANS | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Replace Trans TCon System Hoses | 2026-12-14 | 2026-12-15 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000090166 | 02.12.2026 | 18000 | CCK-MP-HAUL-DT159 -TRNSYS-TRANS-TRNHO | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Replace Hoses Differential System | 2026-12-14 | 2026-12-14 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000090167 | 02.12.2026 | 18000 | CCK-MP-HAUL-DT159 -FDRSYS-DIFFL-DIFHO | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Spider Trans Driveshaft | 2026-12-14 | 2026-12-14 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154990 | 03.02.2027 | 6000 | CCK-MP-HAUL-DT159 -FDRSYS-DRSHT-UNVSL | 7400 | 90235 | 7642
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Transmisson Calibration | 2026-12-14 | 2026-12-14 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298721 | 03.11.2026 | 4500 | CCK-MP-HAUL-DT136 -TRNSYS-TRANS | 7400 | 87780 | 9256
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Brake Slack Adjuster Front | 2026-12-14 | 2026-12-14 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000025498 | 05.11.2026 | 20000 | CCK-MP-HAUL-DT136 -BRKSYS-SLACK-SLACF | 7400 | 87780 | 18275
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Cyl Hoist LH | 2026-12-15 | 2026-12-15 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128595 | 18.07.2026 | 28000 | CCK-MP-HAUL-DT151 -HYDSYS-HOCYL-HCYLL | 7400 | 84301 | 28327
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Spider Trans Driveshaft | 2026-12-15 | 2026-12-15 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154984 | 15.12.2026 | 6000 | CCK-MP-HAUL-DT155 -FDRSYS-DRSHT-UNVSL | 7400 | 81407 | 10226
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Auto Lube Pump | 2026-12-17 | 2026-12-17 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094772 | 17.12.2026 | 8000 | CCK-MP-HAUL-DT760 -GRSYST-ALBPP | 6800 | 80390 | 11271
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Auto Lube Pump | 2026-12-17 | 2026-12-17 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285794 | 17.12.2026 | 8000 | CCK-MP-HAUL-DT155 -GRSYST-ALBPP | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Motor Lube Axle Rear & Hoses | 2026-12-18 | 2026-12-18 | 8 hrs | FY27 | 8 | 90026943 | B1 | 1000271947 | 18.12.2026 | 24000 | CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYM01 | 7400 | 91273 | 15565
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Operator Seat | 2026-12-18 | 2026-12-18 | 3 hrs | FY27 | 6 | 90011567 | B1 | 1000098153 | 18.12.2026 | 6000 | CCK-MP-SUPP-SV221 -STRUCT-CABIN-SEATS | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Replace Brake System Hoses | 2026-12-19 | 2026-12-21 | 46 hrs | FY27 | 90 | 90010129 | B4 | 1000091434 | 19.12.2026 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BRHLF-BRHOS | 7400 | 83062 | 51566
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Differential | 2026-12-20 | 2026-12-21 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000026867 | 20.12.2026 | 18000 | CCK-MP-HAUL-DT157 -FDRSYS-DIFFL | 7400 | 83041 | 15134
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Steering Linkages | 2026-12-21 | 2026-12-21 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317589 | 21.12.2026 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STLTR | 7400 | 84375 | 13167
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Brake Slack Adjuster Rear Left | 2026-12-21 | 2026-12-21 | 6 hrs | FY27 | 6 | 90036703 | B1 | 1000368017 | 02.11.2026 | 18000 | CCK-MP-SUPP-WC221 -BRKSYS-SLACK-SLARL | 4300 | 56923 | 16516
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Brake Slack Adjuster Rear Right | 2026-12-21 | 2026-12-21 | 6 hrs | FY27 | 6 | 90036703 | B1 | 1000368018 | 02.11.2026 | 18000 | CCK-MP-SUPP-WC221 -BRKSYS-SLACK-SLARR | 4300 | 56923 | 16516
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Repl Sepura SCC Microphone | 2026-12-21 | 2026-12-21 | 0.5 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289621 | 12.11.2026 | 12 Monthly | CCK-MP-SUPP-WC221 -COMMUN-RADIO
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Replace Operator Cabin Dash Bulbs | 2026-12-21 | 2026-12-21 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158232 | 31.12.2026 | 3000 | CCK-MP-HAUL-DT767 -STRUCT-CABIN | 6800 | 74312 | 19669
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Axle Lube Hyd Pump | 2026-12-21 | 2026-12-21 | 4 hrs | FY27 | 4 | 90010102 | B1 | 1000083413 | 22.11.2026 | 24000 | CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYPUM | 7400 | 87258 | 31553
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Front Wheel Bearings LH | 2026-12-21 | 2026-12-22 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157162 | 06.12.2026 | 16000 | CCK-MP-HAUL-DT149 -STRUCT-AXLES-FWBLH | 7400 | 86975 | 13875
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Radiator Fan Hoses | 2026-12-21 | 2026-12-21 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307529 | 07.12.2026 | 12000 | CCK-MP-HAUL-DT149 -ENGINE-COSYS-RADTR | 7400 | 87258 | 31553
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Motor Lube Axle Hoses | 2026-12-21 | 2026-12-21 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272018 | 07.12.2026 | 12000 | CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYM01 | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl AOC Fan Motor Rear | 2026-12-21 | 2026-12-21 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000026343 | 07.12.2026 | 12000 | CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYM02 | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Engine Midlife Complete | 2026-12-21 | 2026-12-22 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000156032 | 21.12.2026 | 12000 | CCK-MP-HAUL-DT149 -ENGINE | 7400 | 86975 | 31553
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Steering LH | 2026-12-21 | 2026-12-21 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000025438 | 21.12.2026 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STRCY-STCYL | 7400 | 82965 | 12254
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Steering RH | 2026-12-21 | 2026-12-21 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000025439 | 21.12.2026 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STRCY-STCYR | 7400 | 82965 | 12254
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Differential | 2026-12-21 | 2026-12-22 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000025231 | 30.12.2026 | 18000 | CCK-MP-HAUL-DT130 -FDRSYS-DIFFL | 7400 | 85185 | 15131
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Inspect Rear Axle Housing | 2026-12-21 | 2026-12-21 | 1 hr | FY27 | 1 | 90019256 | B1 | 1000196434 | 21.12.2026 | 2000 | CCK-MP-SUPP-WC224 -STRUCT-RAXHO | 5000 | 71088 | 71088
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Replace Steering System Hoses | 2026-12-22 | 2026-12-24 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000091416 | 22.12.2026 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STHLF-STRHO | 7400 | 82965 | 12254
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Steering LH | 2026-12-22 | 2026-12-22 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000025958 | 22.12.2026 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STRCY-STCYL | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Steering RH | 2026-12-22 | 2026-12-22 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000025959 | 22.12.2026 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STRCY-STCYR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Steering Linkages | 2026-12-22 | 2026-12-22 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317627 | 22.12.2026 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STLTR | 7400 | 88225 | 35974
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Replace Steering System Hoses | 2026-12-22 | 2026-12-24 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083349 | 22.12.2026 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STHLF-STRHO | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Steering Hyd Oil Cooler | 2026-12-22 | 2026-12-22 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107000 | 22.12.2026 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STOCO | 7400 | 88225 | 11934
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Suspension RHF | 2026-12-23 | 2026-12-25 | 60 hrs | FY27 | 112 | 90011366 | B1 | 1000094355 | 23.12.2026 | 18000 | CCK-MP-HAUL-DT752 -STRUCT-SUSPN-SCYRF | 6800 | 80681 | 326
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Cyl Steering LH | 2026-12-23 | 2026-12-23 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000128048 | 23.12.2026 | 15000 | CCK-MP-HAUL-DT222 -STRSYS-STRCY-STCYL | 7400 | 55735 | 12092
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Replace Hoses Differential System | 2026-12-23 | 2026-12-23 | 5 hrs | FY27 | 5 | 90010101 | B1 | 1000090110 | 30.12.2026 | 18000 | CCK-MP-HAUL-DT130 -FDRSYS-DIFFL-DIFHO | 7400 | 85185 | 33489
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Tyre Sense Battery | 2026-12-23 | 2026-12-23 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153157 | 23.12.2026 | 24 Monthly | CCK-MP-HAUL-DT143 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Wheel Group Front RH | 2026-12-24 | 2026-12-25 | 28 hrs | FY27 | 54 | 90017287 | B1 | 1000157241 | 24.12.2026 | 24000 | CCK-MP-HAUL-DT142 -STRUCT-AXLES-HUBRH | 7400 | 87027 | 21161
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Steering Hyd Oil Cooler | 2026-12-25 | 2026-12-25 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107025 | 25.12.2026 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STOCO | 7400 | 82941 | 12254
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Replace Operator Cabin Dash Bulbs | 2026-12-25 | 2026-12-25 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158222 | 25.12.2026 | 3000 | CCK-MP-HAUL-DT757 -STRUCT-CABIN | 6800 | 80700 | 80700
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 OHaul WaterTank Cannon & SpraySys | 2026-12-26 | 2026-12-27 | 24 hrs | FY27 | 48 | 90036930 | B1 | 1000368897 | 26.12.2026 | 24 Monthly | CCK-MP-SUPP-WC3111-STRUCT-WTANK | 5600 | 28968 | 28968
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Wheel Motor Oil LH | 2026-12-28 | 2026-12-28 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338242 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -FDRSYS-WLMTR-WHMLH | 6800 | 75884 | 22415
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Wheel Motor Oil RH | 2026-12-28 | 2026-12-28 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338243 | 15.12.2026 | 25000 | CCK-MP-HAUL-DT773 -FDRSYS-WLMTR-WHMRH | 6800 | 75884 | 22415
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Transmisson Calibration | 2026-12-28 | 2026-12-28 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298670 | 28.12.2026 | 4500 | CCK-MP-HAUL-DT090 -TRNSYS-TRANS | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Auto Lube Pump | 2026-12-28 | 2026-12-28 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285811 | 28.12.2026 | 8000 | CCK-MP-SUPP-PM0001-GRSYST-ALBPP | 3400 | 48287 | 48287
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Replace Trans TCon System Hoses | 2026-12-28 | 2026-12-29 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000091553 | 27.12.2026 | 18000 | CCK-MP-HAUL-DT158 -TRNSYS-TRANS-TRNHO | 7400 | 85964 | 33728
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Auto Lube Pump | 2026-12-28 | 2026-12-28 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094719 | 28.12.2026 | 8000 | CCK-MP-HAUL-DT759 -GRSYST-ALBPP | 6800 | 79716 | 16971
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Auto Lube Pump | 2026-12-28 | 2026-12-28 | 2 hrs | FY27 | 2 | 90011565 | B1 | 1000093013 | 28.12.2026 | 9000 | CCK-MP-SUPP-SV221 -GRSYST-ALBPP | 5100 | 64374 | 14753
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Hub & Spindle LH | 2026-12-30 | 2026-12-31 | 32 hrs | FY27 | 60 | 90011363 | B1 | 1000094670 | 30.12.2026 | 18000 | CCK-MP-HAUL-DT758 -STRUCT-AXLES-HUBLH | 6800 | 85895 | 15304
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Hub & Spindle RH | 2026-12-30 | 2026-12-31 | 32 hrs | FY27 | 60 | 90011364 | B1 | 1000094671 | 30.12.2026 | 18000 | CCK-MP-HAUL-DT758 -STRUCT-AXLES-HUBRH | 6800 | 85895 | 15304
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Operator Cabin Dash Bulbs | 2027-01-01 | 2027-01-01 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158218 | 01.01.2027 | 3000 | CCK-MP-HAUL-DT753 -STRUCT-CABIN | 6800 | 85999 | 22050
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Transmisson Calibration | 2027-01-02 | 2027-01-02 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298722 | 02.01.2027 | 4500 | CCK-MP-HAUL-DT137 -TRNSYS-TRANS | 7400 | 84196 | 1006
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Hyd Pump Steering & Brake | 2027-01-03 | 2027-01-04 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204435 | 03.01.2027 | 12000 | CCK-MP-HAUL-DT755 -STRSYS-STPMP | 6800 | 84587 | 9678
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Operators Seat | 2027-01-03 | 2027-01-03 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000024945 | 03.01.2027 | 15000 | CCK-MP-HAUL-DT100 -STRUCT-CABIN-SEATS | 7400 | 87135 | 19823
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Cyl Steering RH | 2027-01-03 | 2027-01-03 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000094551 | 03.01.2027 | 15000 | CCK-MP-HAUL-DT756 -STRSYS-STRCY-STCYR | 6800 | 78754 | 11883
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Auto Lube Pump | 2027-01-04 | 2027-01-04 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285624 | 04.01.2027 | 8000 | CCK-MP-HAUL-DT056 -GRSYST-ALBPP | 7400 | 84421 | 4851
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Auto Lube Pump | 2027-01-04 | 2027-01-04 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094454 | 14.01.2027 | 8000 | CCK-MP-HAUL-DT754 -GRSYST-ALBPP | 6800 | 83256 | 4996
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Wheel End LH | 2027-01-04 | 2027-01-05 | 32.5 hrs | FY27 | 58.5 | 90002374 | B1 | 1000025488 | 16.01.2027 | 24000 | CCK-MP-HAUL-DT136 -FDRSYS-FDRVE-FDRLH | 7400 | 87780 | 20807
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Pump Brake Cooling | 2027-01-04 | 2027-01-04 | 9 hrs | FY27 | 17 | 90002379 | B1 | 1000025495 | 17.01.2027 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-HYFPP | 7400 | 87780 | 20793
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Steering LH | 2027-01-05 | 2027-01-05 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000023859 | 05.01.2027 | 15000 | CCK-MP-HAUL-DT058 -STRSYS-STRCY-STCYL | 7400 | 87864 | 11626
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Steering RH | 2027-01-05 | 2027-01-05 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000023860 | 05.01.2027 | 15000 | CCK-MP-HAUL-DT058 -STRSYS-STRCY-STCYR | 7400 | 87864 | 11626
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Spiders Pump Drive Shaft | 2027-01-05 | 2027-01-05 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000025935 | 05.01.2027 | 18000 | CCK-MP-HAUL-DT143 -ENGINE-PMPDR-DRSHT | 7400 | 88225 | 14631
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Front Wheel Bearings RH | 2027-01-05 | 2027-01-06 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157244 | 05.01.2027 | 16000 | CCK-MP-HAUL-DT146 -STRUCT-AXLES-FWBRH | 7400 | 83062 | 12458
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Adjust Engine Valve Set | 2027-01-05 | 2027-01-05 | 6 hrs | FY27 | 6 | 90017451 | B1 | 1000290661 | 05.01.2027 | 3000 | CCK-MP-SUPP-WC009 -ENGINE | 1500 | 34052 | 10936
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Cyl Steering RH | 2027-01-07 | 2027-01-07 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000024301 | 07.01.2027 | 15000 | CCK-MP-HAUL-DT090 -STRSYS-STRCY-STCYR | 7400 | 81670 | 11697
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Air Con Service & Overhaul | 2027-01-07 | 2027-01-08 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110611 | 07.01.2027 | 12 Monthly | CCK-MP-HAUL-DT751 -STRUCT-CABIN-AIRCN | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Hyd Pump Steering & Brake | 2027-01-07 | 2027-01-08 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204438 | 07.01.2027 | 12000 | CCK-MP-HAUL-DT758 -STRSYS-STPMP | 6800 | 85895 | 10280
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Transmisson Calibration | 2027-01-08 | 2027-01-08 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298740 | 08.01.2027 | 4500 | CCK-MP-HAUL-DT221 -TRNSYS-TRANS | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Transmission | 2027-01-09 | 2027-01-10 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000272313 | 09.01.2027 | 18000 | CCK-MP-HAUL-DT099 -TRNSYS-TRANS | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Service Air Conditioner 12M | 2027-01-10 | 2027-01-11 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174189 | 10.01.2027 | 12 Monthly | CCK-MP-HAUL-DT222 -STRUCT-CABIN-AIRCN | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Motor Fan Cool Axle Rear | 2027-01-11 | 2027-01-11 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000272703 | 11.01.2027 | 12000 | CCK-MP-SUPP-PM0001-FDRSYS-AXLEC-HYM02 | 3400 | 48287 | 9867
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Pump Gearbox Scavenge | 2027-01-11 | 2027-01-11 | 6 hrs | FY27 | 12 | 90026962 | B1 | 1000272717 | 11.01.2027 | 12000 | CCK-MP-SUPP-PM0001-HYDSYS-GSPMP | 3400 | 48287 | 9867
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Steering Brake Pump Compensator | 2027-01-11 | 2027-01-11 | 6 hrs | FY27 | 7 | 90019922 | B1 | 1000204755 | 11.01.2027 | 6000 | CCK-MP-HAUL-DT751 -STRSYS-STPMP | 6800 | 86211 | 3654
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Front Wheel Bearings RH | 2027-01-11 | 2027-01-12 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157252 | 19.01.2027 | 16000 | CCK-MP-HAUL-DT150 -STRUCT-AXLES-FWBRH | 7400 | 86608 | 12300
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Steering Hyd Oil Cooler | 2027-01-12 | 2027-01-12 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107014 | 12.01.2027 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STOCO | 7400 | 80609 | 11737
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Auto Lube Pump | 2027-01-12 | 2027-01-12 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285637 | 12.01.2027 | 8000 | CCK-MP-HAUL-DT126 -GRSYST-ALBPP | 7400 | 88657 | 14100
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Differential | 2027-01-13 | 2027-01-14 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000024853 | 13.01.2027 | 18000 | CCK-MP-HAUL-DT099 -FDRSYS-DIFFL | 7400 | 87442 | 14781
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Steering RH | 2027-01-13 | 2027-01-13 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000025247 | 13.01.2027 | 15000 | CCK-MP-HAUL-DT130 -STRSYS-STRCY-STCYR | 7400 | 85185 | 11817
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Trans TCon System Hoses | 2027-01-15 | 2027-01-16 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000090094 | 15.01.2027 | 18000 | CCK-MP-HAUL-DT099 -TRNSYS-TRANS-TRNHO | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Front Wheel Bearings RH | 2027-01-15 | 2027-01-16 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157230 | 15.01.2027 | 16000 | CCK-MP-HAUL-DT135 -STRUCT-AXLES-FWBRH | 7400 | 82965 | 12819
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Hoses Differential System | 2027-01-16 | 2027-01-16 | 5 hrs | FY27 | 5 | 90010101 | B1 | 1000090095 | 16.01.2027 | 18000 | CCK-MP-HAUL-DT099 -FDRSYS-DIFFL-DIFHO | 7400 | 87442 | 14729
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Wheel Motor Oil LH | 2027-01-18 | 2027-01-18 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338218 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -FDRSYS-WLMTR-WHMLH | 6800 | 78336 | 23274
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Wheel Motor Oil RH | 2027-01-18 | 2027-01-18 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338219 | 12.11.2026 | 25000 | CCK-MP-HAUL-DT761 -FDRSYS-WLMTR-WHMRH | 6800 | 78336 | 23274
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Pressure Reducing Valve | 2027-01-18 | 2027-01-18 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204784 | 18.01.2027 | 12000 | CCK-MP-HAUL-DT752 -BRKSYS-BRVLV-VVPRV | 6800 | 80681 | 23618
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Suspension LHF | 2027-01-18 | 2027-01-20 | 43 hrs | FY27 | 84 | 90002408 | B1 | 1000067645 | 16.12.2026 | 28000 | CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYLF | 7400 | 80609 | 24548
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Drive Shaft Transmission | 2027-01-18 | 2027-01-18 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154947 | 09.01.2027 | 18000 | CCK-MP-HAUL-DT099 -FDRSYS-DRSHT | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Auto Lube Pump | 2027-01-18 | 2027-01-18 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285636 | 18.01.2027 | 8000 | CCK-MP-HAUL-DT100 -GRSYST-ALBPP | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl AOC Fan Motor Rear | 2027-01-20 | 2027-01-20 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000128106 | 20.01.2027 | 12000 | CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYM02 | 7400 | 54920 | 19069
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Replace Operator Cabin Dash Bulbs | 2027-01-21 | 2027-01-21 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158239 | 21.01.2027 | 3000 | CCK-MP-HAUL-DT774 -STRUCT-CABIN | 6800 | 81047 | 28490
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Tyre Sense Battery | 2027-01-23 | 2027-01-23 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153116 | 23.01.2027 | 24 Monthly | CCK-MP-HAUL-DT058 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Hoist LH | 2027-01-23 | 2027-01-23 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128609 | 23.01.2027 | 28000 | CCK-MP-HAUL-DT161 -HYDSYS-HOCYL-HCYLL | 7400 | 80609 | 24548
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Hoist RH | 2027-01-23 | 2027-01-23 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128610 | 23.01.2027 | 28000 | CCK-MP-HAUL-DT161 -HYDSYS-HOCYL-HCYLR | 7400 | 80609 | 24548
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Suspension RHR | 2027-01-23 | 2027-01-24 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000027170 | 23.01.2027 | 28000 | CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYRR | 7400 | 80609 | 24548
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Suspension Cylinder RHR | 2027-01-23 | 2027-01-23 | 16 hrs | FY27 | 28 | 90004014 | B2 | 1000079215 | 23.01.2027 | 20000 | CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYRR | 5600 | 51257 | 11166
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Torque Converter | 2027-01-24 | 2027-01-25 | 27 hrs | FY27 | 53 | 90002369 | B1 | 1000025939 | 24.01.2027 | 24000 | CCK-MP-HAUL-DT143 -TRNSYS-TRQUE | 7400 | 88225 | 20247
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Transmission Oil Cooler | 2027-01-25 | 2027-01-25 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000083335 | 25.01.2027 | 18000 | CCK-MP-HAUL-DT143 -TRNSYS-TROLC | 7400 | 88225 | 13924
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Service Air Conditioner 12M | 2027-01-26 | 2027-01-27 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174173 | 26.01.2027 | 12 Monthly | CCK-MP-HAUL-DT142 -STRUCT-CABIN-AIRCN | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Auto Lube Pump | 2027-01-28 | 2027-01-28 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285789 | 28.01.2027 | 8000 | CCK-MP-HAUL-DT148 -GRSYST-ALBPP | 7400 | 85452 | 20768
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Hoist LH | 2027-01-28 | 2027-01-28 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128553 | 28.01.2027 | 28000 | CCK-MP-HAUL-DT094 -HYDSYS-HOCYL-HCYLL | 7400 | 88788 | 24241
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Hoist RH | 2027-01-28 | 2027-01-28 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128554 | 28.01.2027 | 28000 | CCK-MP-HAUL-DT094 -HYDSYS-HOCYL-HCYLR | 7400 | 88788 | 24241
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Sepura SCC Microphone | 2027-01-28 | 2027-01-28 | 0.5 hrs | FY27 | 0.5 | 90029001 | B1 | 1000289629 | 28.01.2027 | 12 Monthly | CCK-MP-SUPP-WC3112-COMMUN-RADIO | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 OHaul WaterTank Cannon & SpraySys | 2027-01-28 | 2027-01-29 | 24 hrs | FY27 | 48 | 90036930 | B1 | 1000368899 | 28.01.2027 | 24 Monthly | CCK-MP-SUPP-WC3112-STRUCT-WTANK | 5600 | 30406 | 30406
777G WC | Onsite PM | Haul | Fortescue | WC2501 | WC2501 Repl Sepura SCC Microphone | 2027-01-28 | 2027-01-28 | 0.5 hrs | FY27 | 0.5 | 90029000 | B1 | 1000289622 | 28.01.2027 | 12 Monthly | CCK-MP-SUPP-WC2501-COMMUN-RADIO
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Grid Box Blower Motor LH | 2027-01-29 | 2027-01-29 | 10 hrs | FY27 | 10 | 90011331 | B1 | 1000094270 | 29.01.2027 | 25000 | CCK-MP-HAUL-DT751 -ELCTHV-HVGBM-GBMLH | 6800 | 86211 | 22422
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Cyl Steering LH | 2027-01-29 | 2027-01-29 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000026882 | 29.01.2027 | 15000 | CCK-MP-HAUL-DT157 -STRSYS-STRCY-STCYL | 7400 | 83041 | 11339
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Cyl Steering RH | 2027-01-29 | 2027-01-29 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000026883 | 29.01.2027 | 15000 | CCK-MP-HAUL-DT157 -STRSYS-STRCY-STCYR | 7400 | 83041 | 11339
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Valve Retard & Brake Treadle | 2027-01-29 | 2027-01-29 | 5.5 hrs | FY27 | 5.5 | 90011345 | B1 | 1000094651 | 29.01.2027 | 25000 | CCK-MP-HAUL-DT758 -BRKSYS-BRVTR | 6800 | 85895 | 21747
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Brake Cabinet Hoses | 2027-01-29 | 2027-01-30 | 32.5 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126505 | 29.01.2027 | 25000 | CCK-MP-HAUL-DT758 -BRKSYS-BRHLF | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Hoist LH | 2027-01-29 | 2027-01-29 | 17 hrs | FY27 | 33 | 90011357 | B1 | 1000094663 | 29.01.2027 | 25000 | CCK-MP-HAUL-DT758 -HYDSYS-HOCYL-HCYLL | 6800 | 85895 | 21747
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Hoist RH | 2027-01-29 | 2027-01-29 | 17 hrs | FY27 | 33 | 90011358 | B1 | 1000094664 | 29.01.2027 | 25000 | CCK-MP-HAUL-DT758 -HYDSYS-HOCYL-HCYLR | 6800 | 85895 | 21747
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Operator Cabin Dash Bulbs | 2027-01-29 | 2027-01-29 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158237 | 29.01.2027 | 3000 | CCK-MP-HAUL-DT772 -STRUCT-CABIN | 6800 | 85256 | 10385
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Spider Trans Driveshaft | 2027-01-31 | 2027-01-31 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154952 | 31.01.2027 | 6000 | CCK-MP-HAUL-DT127 -FDRSYS-DRSHT-UNVSL | 7400 | 83059 | 9436
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Inspect Rear Axle Housing | 2027-02-01 | 2027-02-01 | 1 hr | FY27 | 1 | 90019256 | B1 | 1000196435 | 01.02.2027 | 2000 | CCK-MP-SUPP-WC225 -STRUCT-RAXHO | 5000 | 75244 | 75244
777G WC | Onsite PM | Haul | Fortescue | WC2501 | WC2501 Repl Operator Seat | 2027-02-01 | 2027-02-01 | 3 hrs | FY27 | 6 | 90011567 | B1 | 1000136177 | 01.02.2027 | 6000 | CCK-MP-SUPP-WC2501-STRUCT-CABIN-SEATS | 2000 | 56945 | 3687
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Replace Operator Cabin Dash Bulbs | 2027-02-02 | 2027-02-02 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158219 | 02.02.2027 | 3000 | CCK-MP-HAUL-DT754 -STRUCT-CABIN | 6800 | 83256 | 83256
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Seat Assy | 2027-02-02 | 2027-02-02 | 3 hrs | FY27 | 6 | 90003494 | B2 | 1000039954 | 02.02.2027 | 11000 | CCK-MP-SUPP-WC224 -STRUCT-CABIN-SEATS | 5000 | 71088 | 8630
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Steering LH | 2027-02-02 | 2027-02-02 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000025502 | 02.02.2027 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STRCY-STCYL | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Steering RH | 2027-02-02 | 2027-02-02 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000025503 | 02.02.2027 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STRCY-STCYR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Steering Linkages | 2027-02-02 | 2027-02-02 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317617 | 02.02.2027 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STLTR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Replace Steering System Hoses | 2027-02-02 | 2027-02-04 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083216 | 02.02.2027 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STHLF-STRHO | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Steering Hyd Oil Cooler | 2027-02-02 | 2027-02-02 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000106994 | 02.02.2027 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STOCO | 7400 | 87780 | 11471
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Replace Operator Cabin Dash Bulbs | 2027-02-03 | 2027-02-03 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158236 | 03.02.2027 | 3000 | CCK-MP-HAUL-DT771 -STRUCT-CABIN | 6800 | 84423 | 84423
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl AOC Fan Motor Rear | 2027-02-03 | 2027-02-03 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000025751 | 03.02.2027 | 12000 | CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYM02 | 7400 | 86767 | 8224
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Hoist LH | 2027-02-03 | 2027-02-03 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128585 | 03.02.2027 | 28000 | CCK-MP-HAUL-DT146 -HYDSYS-HOCYL-HCYLL | 7400 | 83108 | 24149
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Hoist RH | 2027-02-03 | 2027-02-03 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128586 | 03.02.2027 | 28000 | CCK-MP-HAUL-DT146 -HYDSYS-HOCYL-HCYLR | 7400 | 83108 | 24149
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Operator Cabin Dash Bulbs | 2027-02-04 | 2027-02-04 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158234 | 04.02.2027 | 3000 | CCK-MP-HAUL-DT769 -STRUCT-CABIN | 6800 | 80508 | 80508
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Pressure Reducing Valve | 2027-02-04 | 2027-02-04 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204841 | 04.02.2027 | 12000 | CCK-MP-HAUL-DT769 -BRKSYS-BRVLV-VVPRV | 6800 | 80508 | 12222
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Transmisson Calibration | 2027-02-04 | 2027-02-04 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298734 | 04.02.2027 | 4500 | CCK-MP-HAUL-DT155 -TRNSYS-TRANS | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 250hr Initial Valve Set | 2027-02-05 | 2027-02-05 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000155862 | 19.01.2027 | 250 | CCK-MP-HAUL-DT054 -ENGINE | 7400 | 88111 | 21034
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 250hr Initial Valve Set | 2027-02-05 | 2027-02-05 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000167141 | 05.02.2027 | 250 | CCK-MP-HAUL-DT5315-ENGINE | 7400 | 45392 | 20546
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Replace Operator Cabin Dash Bulbs | 2027-02-05 | 2027-02-05 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158231 | 05.02.2027 | 3000 | CCK-MP-HAUL-DT766 -STRUCT-CABIN | 6800 | 78074 | 10283
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Auto Lube Pump | 2027-02-05 | 2027-02-05 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285795 | 05.02.2027 | 8000 | CCK-MP-HAUL-DT157 -GRSYST-ALBPP | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Spider Trans Driveshaft | 2027-02-06 | 2027-02-06 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154920 | 06.02.2027 | 6000 | CCK-MP-HAUL-DT055 -FDRSYS-DRSHT-UNVSL | 7400 | 84122 | 9073
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Service Air Conditioner 12M | 2027-02-06 | 2027-02-07 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174190 | 06.02.2027 | 12 Monthly | CCK-MP-HAUL-DT223 -STRUCT-CABIN-AIRCN | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Motor Lube Axle Hoses | 2027-02-07 | 2027-02-07 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272006 | 07.02.2027 | 12000 | CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYM01 | 7400 | 86767 | 8224
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Transmission Oil Cooler | 2027-02-07 | 2027-02-07 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000083107 | 07.02.2027 | 18000 | CCK-MP-HAUL-DT127 -TRNSYS-TROLC | 7400 | 83059 | 14187
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Transmisson Calibration | 2027-02-07 | 2027-02-07 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298671 | 07.02.2027 | 4500 | CCK-MP-HAUL-DT091 -TRNSYS-TRANS | 7400 | 83859 | 5241
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Auto Lube Pump | 2027-02-08 | 2027-02-08 | 4 hrs | FY27 | 4 | 90003064 | B2 | 1000239786 | 08.02.2027 | 6000 | CCK-MP-SUPP-WC008 -GRSYST-ALBPP | 3500 | 51417 | 3913
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Suspension LHF | 2027-02-08 | 2027-02-10 | 43 hrs | FY27 | 84 | 90002408 | B1 | 1000067601 | 07.02.2027 | 28000 | CCK-MP-HAUL-DT150 -STRUCT-SUSPN-SCYLF | 7400 | 86608 | 23907
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Suspension RHF | 2027-02-08 | 2027-02-10 | 43 hrs | FY27 | 84 | 90002408 | B2 | 1000067603 | 07.02.2027 | 28000 | CCK-MP-HAUL-DT150 -STRUCT-SUSPN-SCYRF | 7400 | 86608 | 23907
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Auto Lube Pump | 2027-02-08 | 2027-02-08 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285787 | 08.02.2027 | 8000 | CCK-MP-HAUL-DT146 -GRSYST-ALBPP | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Hyd Pump Steering Main & Fan | 2027-02-09 | 2027-02-09 | 17 hrs | FY27 | 17 | 90002383 | B1 | 1000026022 | 09.02.2027 | 24000 | CCK-MP-HAUL-DT5255-STRSYS-STPMP | 7400 | 87580 | 20163
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Spiders Pump Drive Shaft | 2027-02-09 | 2027-02-09 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026859 | 09.02.2027 | 18000 | CCK-MP-HAUL-DT157 -ENGINE-PMPDR-DRSHT | 7400 | 83041 | 15134
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Replace Trans TCon System Hoses | 2027-02-09 | 2027-02-10 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000091531 | 09.02.2027 | 18000 | CCK-MP-HAUL-DT157 -TRNSYS-TRANS-TRNHO | 7400 | 83026 | 14033
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Replace Hoses Differential System | 2027-02-09 | 2027-02-09 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000091532 | 09.02.2027 | 18000 | CCK-MP-HAUL-DT157 -FDRSYS-DIFFL-DIFHO | 7400 | 83026 | 14033
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Front Wheel Bearings LH | 2027-02-09 | 2027-02-10 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157154 | 09.02.2027 | 16000 | CCK-MP-HAUL-DT143 -STRUCT-AXLES-FWBLH | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Front Wheel Bearings RH | 2027-02-09 | 2027-02-10 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157242 | 09.02.2027 | 16000 | CCK-MP-HAUL-DT143 -STRUCT-AXLES-FWBRH | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Rear Axle Linkages | 2027-02-09 | 2027-02-11 | 57 hrs | FY27 | 113 | 90002396 | B1 | 1000026172 | 09.02.2027 | 24000 | CCK-MP-HAUL-DT146 -STRUCT-CHASS-AXLIK | 7400 | 83062 | 20016
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Cyl Suspension RHF | 2027-02-10 | 2027-02-12 | 60 hrs | FY27 | 112 | 90011366 | B1 | 1000095097 | 10.02.2027 | 18000 | CCK-MP-HAUL-DT766 -STRUCT-SUSPN-SCYRF | 6800 | 78074 | 15537
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Transmisson Calibration | 2027-02-10 | 2027-02-10 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298676 | 10.02.2027 | 4500 | CCK-MP-HAUL-DT100 -TRNSYS-TRANS | 7400 | 87135 | 5195
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Spider Trans Driveshaft | 2027-02-10 | 2027-02-10 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000155002 | 10.02.2027 | 6000 | CCK-MP-HAUL-DT5202-FDRSYS-DRSHT-UNVSL | 7400 | 84333 | 7715
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 250hr Initial Valve Set | 2027-02-11 | 2027-02-11 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000167301 | 11.02.2027 | 250 | CCK-MP-HAUL-DT5317-ENGINE | 7400 | 45576 | 20480
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Air Con Service & Overhaul | 2027-02-12 | 2027-02-13 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110624 | 12.02.2027 | 12 Monthly | CCK-MP-HAUL-DT755 -STRUCT-CABIN-AIRCN | 6800 | 84587 | 57456
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Hub & Spindle RH | 2027-02-12 | 2027-02-13 | 32 hrs | FY27 | 60 | 90011364 | B1 | 1000094512 | 12.02.2027 | 18000 | CCK-MP-HAUL-DT755 -STRUCT-AXLES-HUBRH | 6800 | 84587 | 11052
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Tag Link | 2027-02-12 | 2027-02-12 | 6 hrs | FY27 | 6 | 90011569 | B1 | 1000098145 | 12.02.2027 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-CHASS-TAGLK | 4000 | 56923 | 15581
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Cylinder Suspension RHR | 2027-02-12 | 2027-02-12 | 6 hrs | FY27 | 10 | 90011575 | B1 | 1000098151 | 12.02.2027 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-SUSPN-SCYRR | 4000 | 56923 | 15581
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Cyl Steering LH | 2027-02-12 | 2027-02-12 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000025057 | 12.02.2027 | 15000 | CCK-MP-HAUL-DT127 -STRSYS-STRCY-STCYL | 7400 | 83059 | 11091
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Cyl Steering RH | 2027-02-12 | 2027-02-12 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000025058 | 12.02.2027 | 15000 | CCK-MP-HAUL-DT127 -STRSYS-STRCY-STCYR | 7400 | 83059 | 11091
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Auto Lube Pump | 2027-02-13 | 2027-02-13 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285625 | 13.02.2027 | 8000 | CCK-MP-HAUL-DT057 -GRSYST-ALBPP | 7400 | 91273 | 3875
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Transmisson Calibration | 2027-02-13 | 2027-02-13 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298732 | 13.02.2027 | 4500 | CCK-MP-HAUL-DT151 -TRNSYS-TRANS | 7400 | 84253 | 9530
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Auto Lube Pump | 2027-02-14 | 2027-02-14 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094507 | 14.02.2027 | 8000 | CCK-MP-HAUL-DT755 -GRSYST-ALBPP | 6800 | 84587 | 13093
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Spider Trans Driveshaft | 2027-02-15 | 2027-02-15 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000155000 | 15.02.2027 | 6000 | CCK-MP-HAUL-DT223 -FDRSYS-DRSHT-UNVSL | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Auto Lube Pump | 2027-02-15 | 2027-02-15 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285801 | 15.02.2027 | 8000 | CCK-MP-HAUL-DT222 -GRSYST-ALBPP | 7400 | 55735 | 4006
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Steering Brake Pump Compensator | 2027-02-17 | 2027-02-17 | 6 hrs | FY27 | 7 | 90019922 | B1 | 1000204761 | 17.02.2027 | 6000 | CCK-MP-HAUL-DT757 -STRSYS-STPMP | 6800 | 80700 | 14601
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Final Drive LH | 2027-02-18 | 2027-02-19 | 22 hrs | FY27 | 40 | 90000912 | B2 | 1000033361 | 18.02.2027 | 22000 | CCK-MP-SUPP-WC225 -FDRSYS-FDRVE-FDRLH | 5000 | 75244 | 19295
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Axle shaft LH | 2027-02-18 | 2027-02-18 | 4 hrs | FY27 | 8 | 90014551 | B2 | 1000238498 | 18.02.2027 | 22000 | CCK-MP-SUPP-WC225 -FDRSYS-DRLAX-AXLLH | 5000 | 75197 | 19295
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Air Con Service & Overhaul | 2027-02-18 | 2027-02-19 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110627 | 18.02.2027 | 12 Monthly | CCK-MP-HAUL-DT758 -STRUCT-CABIN-AIRCN | 6800 | 85895 | 34467
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Steering Linkages | 2027-02-19 | 2027-02-19 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317625 | 19.02.2027 | 15000 | CCK-MP-HAUL-DT142 -STRSYS-STLTR | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Brake Slack Adjuster Front | 2027-02-19 | 2027-02-19 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000023855 | 19.02.2027 | 20000 | CCK-MP-HAUL-DT058 -BRKSYS-SLACK-SLACF | 7400 | 87864 | 15544
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Brake Slack Adjuster Rear | 2027-02-19 | 2027-02-19 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000023856 | 19.02.2027 | 20000 | CCK-MP-HAUL-DT058 -BRKSYS-SLACK-SLACR | 7400 | 87864 | 15544
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Repl Pump Brake Charge & Cooling | 2027-02-19 | 2027-02-19 | 6 hrs | FY27 | 6 | 90037882 | B1 | 1000379765 | 19.02.2027 | 9000 | CCK-MP-SUPP-WC221 -BRKSYS-BRPMP | 4300 | 56923 | 6479
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Brake Slack Adjuster Front | 2027-02-19 | 2027-02-19 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000111932 | 19.02.2027 | 20000 | CCK-MP-HAUL-DT5202-BRKSYS-SLACK-SLACF | 7400 | 84333 | 15880
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Brake Slack Adjuster Rear | 2027-02-19 | 2027-02-19 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000111933 | 19.02.2027 | 20000 | CCK-MP-HAUL-DT5202-BRKSYS-SLACK-SLACR | 7400 | 84333 | 15880
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Service Air Conditioner 12M | 2027-02-19 | 2027-02-20 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174191 | 19.02.2027 | 12 Monthly | CCK-MP-HAUL-DT5202-STRUCT-CABIN-AIRCN | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Steering Hyd Oil Cooler | 2027-02-20 | 2027-02-20 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000106999 | 20.02.2027 | 15000 | CCK-MP-HAUL-DT142 -STRSYS-STOCO | 7400 | 87027 | 27424
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Replace Operator Cabin Dash Bulbs | 2027-02-20 | 2027-02-20 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158217 | 20.02.2027 | 3000 | CCK-MP-HAUL-DT752 -STRUCT-CABIN | 6800 | 80681 | 80681
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Steering RH | 2027-02-20 | 2027-02-20 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000026949 | 20.02.2027 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STRCY-STCYR | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Steering Linkages | 2027-02-20 | 2027-02-20 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317647 | 20.02.2027 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STLTR | 7400 | 85964 | 23196
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Operators Seat | 2027-02-20 | 2027-02-20 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000026963 | 20.02.2027 | 15000 | CCK-MP-HAUL-DT158 -STRUCT-CABIN-SEATS | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Replace Steering System Hoses | 2027-02-20 | 2027-02-22 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000091548 | 20.02.2027 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STHLF-STRHO | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Steering Hyd Oil Cooler | 2027-02-20 | 2027-02-20 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107013 | 20.02.2027 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STOCO | 7400 | 85964 | 11104
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Pressure Reducing Valve | 2027-02-20 | 2027-02-20 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204840 | 20.02.2027 | 12000 | CCK-MP-HAUL-DT768 -BRKSYS-BRVLV-VVPRV | 6800 | 79837 | 13890
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Auto Lube Pump | 2027-02-20 | 2027-02-20 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285633 | 20.02.2027 | 8000 | CCK-MP-HAUL-DT095 -GRSYST-ALBPP | 7400 | 88921 | 3967
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Hyd Pump Steering & Brake | 2027-02-20 | 2027-02-21 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204752 | 20.02.2027 | 12000 | CCK-MP-HAUL-DT772 -STRSYS-STPMP | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Hyd Pump Steering & Brake | 2027-02-21 | 2027-02-22 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204740 | 21.02.2027 | 12000 | CCK-MP-HAUL-DT760 -STRSYS-STPMP | 6800 | 80390 | 8061
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Replace Operator Cabin Dash Bulbs | 2027-02-21 | 2027-02-21 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158225 | 21.02.2027 | 3000 | CCK-MP-HAUL-DT760 -STRUCT-CABIN | 6800 | 80390 | 80390
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Replace Hoses Differential System | 2027-02-21 | 2027-02-21 | 5 hrs | FY27 | 5 | 90010101 | B1 | 1000091422 | 21.02.2027 | 18000 | CCK-MP-HAUL-DT135 -FDRSYS-DIFFL-DIFHO | 7400 | 82965 | 36862
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Tyre Sense Battery | 2027-02-22 | 2027-02-22 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153115 | 22.02.2027 | 24 Monthly | CCK-MP-HAUL-DT057 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Service Air Conditioner 12M | 2027-02-22 | 2027-02-23 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174184 | 22.02.2027 | 12 Monthly | CCK-MP-HAUL-DT158 -STRUCT-CABIN-AIRCN | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Drive Shaft Transmission | 2027-02-22 | 2027-02-22 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154995 | 19.02.2027 | 18000 | CCK-MP-HAUL-DT161 -FDRSYS-DRSHT | 7400 | 80609 | 13960
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Ovhl Axle A Frame | 2027-02-22 | 2027-02-23 | 36 hrs | FY27 | 60 | 90002922 | B2 | 1000074508 | 13.11.2025 | 15000 | CCK-MP-SUPP-WC225 -STRUCT-CHASS-AFRME | 5000 | 75244 | 18684
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Steering Linkages | 2027-02-23 | 2027-02-23 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317585 | 23.02.2027 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STLTR | 7400 | 91273 | 22845
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Replace Steering System Hoses | 2027-02-23 | 2027-02-25 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000082513 | 23.02.2027 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STHLF-STRHO | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Steering Hyd Oil Cooler | 2027-02-23 | 2027-02-23 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107016 | 23.02.2027 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STOCO | 7400 | 91273 | 10672
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Engine Midlife Complete | 2027-02-23 | 2027-02-25 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285173 | 23.02.2027 | 12500 | CCK-MP-HAUL-DT755 -ENGINE | 6800 | 84587 | 9678
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Engine Midlife Complete | 2027-02-23 | 2027-02-24 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000155972 | 23.02.2027 | 12000 | CCK-MP-HAUL-DT135 -ENGINE | 7400 | 82965 | 31710
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Radiator Fan Hoses | 2027-02-23 | 2027-02-23 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307505 | 23.02.2027 | 12000 | CCK-MP-HAUL-DT135 -ENGINE-COSYS-RADTR | 7400 | 82965 | 31127
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Motor Lube Axle Hoses | 2027-02-23 | 2027-02-23 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000271998 | 23.02.2027 | 12000 | CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYM01 | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl AOC Fan Motor Rear | 2027-02-23 | 2027-02-23 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000025427 | 23.02.2027 | 12000 | CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYM02 | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Spider Trans Driveshaft | 2027-02-23 | 2027-02-23 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154956 | 23.02.2027 | 6000 | CCK-MP-HAUL-DT135 -FDRSYS-DRSHT-UNVSL | 7400 | 82965 | 1709
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Spiders Pump Drive Shaft | 2027-02-24 | 2027-02-24 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026331 | 24.02.2027 | 18000 | CCK-MP-HAUL-DT149 -ENGINE-PMPDR-DRSHT | 7400 | 87258 | 13875
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Service Air Conditioner 12M | 2027-02-24 | 2027-02-25 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174164 | 24.02.2027 | 12 Monthly | CCK-MP-HAUL-DT100 -STRUCT-CABIN-AIRCN | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Motor Brake Oil Cooling | 2027-02-25 | 2027-02-25 | 3 hrs | FY27 | 3 | 90002381 | B1 | 1000024295 | 25.02.2027 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BROCO-HYMO1 | 7400 | 81670 | 19847
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Cyl Steering LH | 2027-02-25 | 2027-02-25 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000128117 | 25.02.2027 | 15000 | CCK-MP-HAUL-DT223 -STRSYS-STRCY-STCYL | 7400 | 54920 | 10976
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Replace Operator Cabin Dash Bulbs | 2027-02-25 | 2027-02-25 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158230 | 25.02.2027 | 3000 | CCK-MP-HAUL-DT765 -STRUCT-CABIN | 6800 | 78429 | 78429
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Air Con Service & Overhaul | 2027-02-25 | 2027-02-26 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110635 | 25.02.2027 | 12 Monthly | CCK-MP-HAUL-DT766 -STRUCT-CABIN-AIRCN | 6800 | 78074 | 78074
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Auto Lube Pump | 2027-02-25 | 2027-02-25 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095302 | 25.02.2027 | 8000 | CCK-MP-HAUL-DT770 -GRSYST-ALBPP | 6800 | 79304 | 9634
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Engine Midlife Complete | 2027-02-26 | 2027-02-27 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000155966 | 26.02.2027 | 12000 | CCK-MP-HAUL-DT130 -ENGINE | 7400 | 85185 | 49739
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Radiator Fan Hoses | 2027-02-26 | 2027-02-26 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307503 | 26.02.2027 | 12000 | CCK-MP-HAUL-DT130 -ENGINE-COSYS-RADTR | 7400 | 85185 | 60620
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Motor Lube Axle Hoses | 2027-02-26 | 2027-02-26 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000271996 | 26.02.2027 | 12000 | CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYM01 | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl AOC Fan Motor Rear | 2027-02-26 | 2027-02-26 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000025235 | 26.02.2027 | 12000 | CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYM02 | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Wheel Group Front RH | 2027-02-26 | 2027-02-27 | 28 hrs | FY27 | 54 | 90017287 | B1 | 1000157229 | 26.02.2027 | 24000 | CCK-MP-HAUL-DT130 -STRUCT-AXLES-HUBRH | 7400 | 85185 | 19963
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Transmisson Calibration | 2027-02-26 | 2027-02-26 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298744 | 26.02.2027 | 4500 | CCK-MP-HAUL-DT5202-TRNSYS-TRANS | 7400 | 84333 | 975
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Engine Midlife Complete | 2027-02-27 | 2027-03-01 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285170 | 27.02.2027 | 12500 | CCK-MP-HAUL-DT752 -ENGINE | 6800 | 80681 | 6574
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Spiders Pump Drive Shaft | 2027-02-27 | 2027-02-27 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000025479 | 27.02.2027 | 18000 | CCK-MP-HAUL-DT136 -ENGINE-PMPDR-DRSHT | 7400 | 87780 | 13954
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Wheel End LH | 2027-02-28 | 2027-03-01 | 32.5 hrs | FY27 | 58.5 | 90002374 | B1 | 1000024854 | 28.02.2027 | 24000 | CCK-MP-HAUL-DT099 -FDRSYS-FDRVE-FDRLH | 7400 | 87442 | 19843
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Air Con Service & Overhaul | 2027-02-28 | 2027-03-01 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110626 | 28.02.2027 | 12 Monthly | CCK-MP-HAUL-DT757 -STRUCT-CABIN-AIRCN | 6800 | 80700 | 25834
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Cyl Suspension LHF | 2027-02-28 | 2027-03-02 | 43 hrs | FY27 | 84 | 90002408 | B1 | 1000067473 | 28.02.2027 | 28000 | CCK-MP-HAUL-DT091 -STRUCT-SUSPN-SCYLF | 7400 | 83859 | 23814
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Wheel Motor Oil LH | 2027-03-01 | 2027-03-01 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338226 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -FDRSYS-WLMTR-WHMLH | 6800 | 78429 | 23008
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Wheel Motor Oil RH | 2027-03-01 | 2027-03-01 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338227 | 01.12.2026 | 25000 | CCK-MP-HAUL-DT765 -FDRSYS-WLMTR-WHMRH | 6800 | 78429 | 23008
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Replace Operator Cabin Dash Bulbs | 2027-03-02 | 2027-03-02 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158233 | 02.03.2027 | 3000 | CCK-MP-HAUL-DT768 -STRUCT-CABIN | 6800 | 79837 | 18344
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Operators Seat | 2027-03-03 | 2027-03-03 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000024315 | 03.03.2027 | 15000 | CCK-MP-HAUL-DT090 -STRUCT-CABIN-SEATS | 7400 | 81670 | 10666
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Engine Midlife Complete | 2027-03-03 | 2027-03-05 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285530 | 03.03.2027 | 12500 | CCK-MP-HAUL-DT772 -ENGINE | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Air Con Service & Overhaul | 2027-03-03 | 2027-03-04 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110641 | 03.03.2027 | 12 Monthly | CCK-MP-HAUL-DT772 -STRUCT-CABIN-AIRCN | 6800 | 85256 | 35729
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Operators Seat | 2027-03-04 | 2027-03-04 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000026039 | 04.03.2027 | 15000 | CCK-MP-HAUL-DT5255-STRUCT-CABIN-SEATS | 7400 | 87580 | 10729
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Auto Lube Pump | 2027-03-04 | 2027-03-04 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095408 | 04.03.2027 | 8000 | CCK-MP-HAUL-DT772 -GRSYST-ALBPP | 6800 | 85256 | 10385
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Replace Cylinder Steering LH | 2027-03-04 | 2027-03-04 | 8 hrs | FY27 | 14 | 90000275 | B2 | 1000037401 | 04.03.2027 | 9000 | CCK-MP-SUPP-WC009 -STRSYS-STRCY-STCYL | 1500 | 34052 | 7697
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Transmisson Calibration | 2027-03-05 | 2027-03-05 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298730 | 05.03.2027 | 4500 | CCK-MP-HAUL-DT149 -TRNSYS-TRANS | 7400 | 86975 | 9207
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Hub & Spindle RH | 2027-03-06 | 2027-03-07 | 32 hrs | FY27 | 60 | 90011364 | B1 | 1000095201 | 06.03.2027 | 18000 | CCK-MP-HAUL-DT768 -STRUCT-AXLES-HUBRH | 6800 | 79837 | 13890
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Steering LH | 2027-03-06 | 2027-03-06 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000025762 | 06.03.2027 | 15000 | CCK-MP-HAUL-DT140 -STRSYS-STRCY-STCYL | 7400 | 86767 | 10686
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Steering RH | 2027-03-06 | 2027-03-06 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000025763 | 06.03.2027 | 15000 | CCK-MP-HAUL-DT140 -STRSYS-STRCY-STCYR | 7400 | 86767 | 10686
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Cyl Steering RH | 2027-03-06 | 2027-03-06 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000024365 | 06.03.2027 | 15000 | CCK-MP-HAUL-DT091 -STRSYS-STRCY-STCYR | 7400 | 83859 | 10692
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Brake Accumulator | 2027-03-08 | 2027-03-08 | 4 hrs | FY27 | 4 | 90004001 | B2 | 1000079263 | 08.03.2027 | 15000 | CCK-MP-SUPP-WC3112-BRKSYS-BACCM | 5500 | 29590 | 29590
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Steering HMU | 2027-03-08 | 2027-03-08 | 8 hrs | FY27 | 8 | 90004004 | B2 | 1000079268 | 08.03.2027 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STHMU | 5600 | 52240 | 11771
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Steering Oil Cooler | 2027-03-08 | 2027-03-08 | 3 hrs | FY27 | 3 | 90004006 | B2 | 1000079272 | 08.03.2027 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STOLC | 5600 | 52240 | 11669
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Steering Pump | 2027-03-08 | 2027-03-08 | 4 hrs | FY27 | 4 | 90004003 | B2 | 1000079267 | 08.03.2027 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STPMP | 5600 | 52240 | 11771
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Hoist LH | 2027-03-09 | 2027-03-09 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128517 | 09.03.2027 | 28000 | CCK-MP-HAUL-DT056 -HYDSYS-HOCYL-HCYLL | 7400 | 84421 | 23496
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Hoist RH | 2027-03-09 | 2027-03-09 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128518 | 09.03.2027 | 28000 | CCK-MP-HAUL-DT056 -HYDSYS-HOCYL-HCYLR | 7400 | 84421 | 23496
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Hyd Pump Steering & Brake | 2027-03-09 | 2027-03-10 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204439 | 09.03.2027 | 12000 | CCK-MP-HAUL-DT759 -STRSYS-STPMP | 6800 | 79716 | 8626
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Replace Operator Cabin Dash Bulbs | 2027-03-09 | 2027-03-09 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158224 | 09.03.2027 | 3000 | CCK-MP-HAUL-DT759 -STRUCT-CABIN | 6800 | 79716 | 79716
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Overhaul Valve Control Brake | 2027-03-10 | 2027-03-11 | 20 hrs | FY27 | 20 | 90002380 | B2 | 1000023790 | 10.03.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BRVLV | 7400 | 91273 | 19382
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Pump Hoist & Brake | 2027-03-10 | 2027-03-10 | 9 hrs | FY27 | 15 | 90002388 | B1 | 1000023802 | 10.03.2027 | 24000 | CCK-MP-HAUL-DT057 -HYDSYS-HOPMP | 7400 | 91273 | 19382
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Auto Lube Pump | 2027-03-10 | 2027-03-10 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285802 | 10.03.2027 | 8000 | CCK-MP-HAUL-DT223 -GRSYST-ALBPP | 7400 | 54920 | 3706
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Engine Midlife Complete | 2027-03-10 | 2027-03-11 | 36 hrs | FY27 | 50 | 90029080 | B1 | 1000290653 | 10.03.2027 | 9000 | CCK-MP-SUPP-WC008 -ENGINE | 3500 | 51417 | 5947
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Overhaul Airconditioner | 2027-03-10 | 2027-03-11 | 24 hrs | FY27 | 24 | 90029085 | B1 | 1000290655 | 10.03.2027 | 9000 | CCK-MP-SUPP-WC008 -STRUCT-CABIN-AIRCN | 3500 | 51417 | 5947
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Replace Operator Cabin Dash Bulbs | 2027-03-10 | 2027-03-10 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158226 | 10.03.2027 | 3000 | CCK-MP-HAUL-DT761 -STRUCT-CABIN | 6800 | 78336 | 19424
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Auto Lube Pump | 2027-03-10 | 2027-03-10 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095090 | 10.03.2027 | 8000 | CCK-MP-HAUL-DT766 -GRSYST-ALBPP | 6800 | 78074 | 3021
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Transmisson Calibration | 2027-03-10 | 2027-03-10 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298814 | 10.03.2027 | 4500 | CCK-MP-HAUL-DT5314-TRNSYS-TRANS | 7400 | 45898 | 950
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Operator Cabin Dash Bulbs | 2027-03-11 | 2027-03-11 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158223 | 11.03.2027 | 3000 | CCK-MP-HAUL-DT758 -STRUCT-CABIN | 6800 | 85895 | 23936
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Service Air Conditioner 12M | 2027-03-13 | 2027-03-14 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174114 | 13.03.2027 | 12 Monthly | CCK-MP-HAUL-DT082 -STRUCT-CABIN-AIRCN | 7400 | 84375 | 35900
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Spider Trans Driveshaft | 2027-03-14 | 2027-03-14 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154932 | 14.03.2027 | 6000 | CCK-MP-HAUL-DT088 -FDRSYS-DRSHT-UNVSL | 7400 | 89037 | 7099
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Spider Trans Driveshaft | 2027-03-14 | 2027-03-14 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000167216 | 14.03.2027 | 6000 | CCK-MP-HAUL-DT5316-FDRSYS-DRSHT-UNVSL | 7400 | 45108 | 1608
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Spiders Pump Drive Shaft | 2027-03-14 | 2027-03-14 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026595 | 14.03.2027 | 18000 | CCK-MP-HAUL-DT153 -ENGINE-PMPDR-DRSHT | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Service Air Conditioner 12M | 2027-03-14 | 2027-03-15 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174169 | 14.03.2027 | 12 Monthly | CCK-MP-HAUL-DT136 -STRUCT-CABIN-AIRCN | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Operators Seat | 2027-03-15 | 2027-03-15 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000023747 | 15.03.2027 | 15000 | CCK-MP-HAUL-DT056 -STRUCT-CABIN-SEATS | 7400 | 84421 | 10436
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Air Con Service & Overhaul | 2027-03-15 | 2027-03-16 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110638 | 15.03.2027 | 12 Monthly | CCK-MP-HAUL-DT769 -STRUCT-CABIN-AIRCN | 6800 | 80508 | 36906
Panther 150T | Onsite PM | Haul | Fortescue | LL0010 | LL0010 12M NDT Inspection | 2027-03-16 | 2027-03-16 | 9 hrs | FY27 | 11 | 90038241 | B1 | 1000383086 | 16.03.2027 | 12 Monthly | CCK-MP-SUPP-LL0010 | 2000 | 587 | 587
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Hub & Spindle LH | 2027-03-16 | 2027-03-17 | 32 hrs | FY27 | 60 | 90011363 | B1 | 1000095200 | 16.03.2027 | 18000 | CCK-MP-HAUL-DT768 -STRUCT-AXLES-HUBLH | 6800 | 79837 | 13890
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Cyl Suspension LHF | 2027-03-16 | 2027-03-18 | 60 hrs | FY27 | 112 | 90011365 | B1 | 1000095202 | 16.03.2027 | 18000 | CCK-MP-HAUL-DT768 -STRUCT-SUSPN-SCYLF | 6800 | 79837 | 13890
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Cyl Suspension RHF | 2027-03-16 | 2027-03-18 | 60 hrs | FY27 | 112 | 90011366 | B1 | 1000095203 | 16.03.2027 | 18000 | CCK-MP-HAUL-DT768 -STRUCT-SUSPN-SCYRF | 6800 | 79837 | 13890
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Brake Slack Adjuster Front | 2027-03-16 | 2027-03-16 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000024990 | 16.03.2027 | 20000 | CCK-MP-HAUL-DT126 -BRKSYS-SLACK-SLACF | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Brake Slack Adjuster Rear | 2027-03-16 | 2027-03-16 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000024991 | 16.03.2027 | 20000 | CCK-MP-HAUL-DT126 -BRKSYS-SLACK-SLACR | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Service Air Conditioner 12M | 2027-03-17 | 2027-03-18 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174112 | 17.03.2027 | 12 Monthly | CCK-MP-HAUL-DT057 -STRUCT-CABIN-AIRCN | 7400 | 91273 | 10672
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Steering Linkages | 2027-03-17 | 2027-03-17 | 12 hrs | FY27 | 24 | 90011557 | B1 | 1000093006 | 17.03.2027 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STLTR | 5100 | 64374 | 15010
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Transmission Oil Cooler | 2027-03-18 | 2027-03-18 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000083525 | 18.03.2027 | 18000 | CCK-MP-HAUL-DT159 -TRNSYS-TROLC | 7400 | 90235 | 13326
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Auto Lube Pump | 2027-03-19 | 2027-03-19 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285796 | 19.03.2027 | 8000 | CCK-MP-HAUL-DT158 -GRSYST-ALBPP | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Operators Seat | 2027-03-19 | 2027-03-19 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000024378 | 19.03.2027 | 15000 | CCK-MP-HAUL-DT091 -STRUCT-CABIN-SEATS | 7400 | 83859 | 23814
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Transmission Pump | 2027-03-19 | 2027-03-19 | 6 hrs | FY27 | 6 | 90003991 | B2 | 1000079183 | 19.03.2027 | 10000 | CCK-MP-SUPP-WC3111-TRNSYS-TRPMP-TMCPP | 5600 | 51257 | 8333
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Differential | 2027-03-19 | 2027-03-20 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000111921 | 19.03.2027 | 18000 | CCK-MP-HAUL-DT5202-FDRSYS-DIFFL | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Replace Hoses Differential System | 2027-03-19 | 2027-03-19 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000111978 | 19.03.2027 | 18000 | CCK-MP-HAUL-DT5202-FDRSYS-DIFFL-DIFHO | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Transmission Oil Cooler | 2027-03-20 | 2027-03-20 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000082499 | 20.03.2027 | 18000 | CCK-MP-HAUL-DT057 -TRNSYS-TROLC | 7400 | 91273 | 13167
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Radiator Fan Hoses | 2027-03-20 | 2027-03-20 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307549 | 20.03.2027 | 12000 | CCK-MP-HAUL-DT161 -ENGINE-COSYS-RADTR | 7400 | 80609 | 68404
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Suspension LHR | 2027-03-21 | 2027-03-22 | 22 hrs | FY27 | 39 | 90002409 | B1 | 1000025654 | 21.03.2027 | 28000 | CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYLR | 7400 | 82982 | 23314
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Spiders Pump Drive Shaft | 2027-03-22 | 2027-03-22 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000023962 | 22.03.2027 | 18000 | CCK-MP-HAUL-DT082 -ENGINE-PMPDR-DRSHT | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Transmission Oil Cooler | 2027-03-22 | 2027-03-22 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000082879 | 22.03.2027 | 18000 | CCK-MP-HAUL-DT082 -TRNSYS-TROLC | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Replace Trans TCon System Hoses | 2027-03-22 | 2027-03-23 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000090067 | 22.03.2027 | 18000 | CCK-MP-HAUL-DT082 -TRNSYS-TRANS-TRNHO | 7400 | 84374 | 13167
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Auto Lube Pump | 2027-03-22 | 2027-03-22 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094560 | 22.03.2027 | 8000 | CCK-MP-HAUL-DT756 -GRSYST-ALBPP | 6800 | 78754 | 3428
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Auto Lube Pump | 2027-03-23 | 2027-03-23 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285804 | 23.03.2027 | 8000 | CCK-MP-HAUL-DT5255-GRSYST-ALBPP | 7400 | 87580 | 3331
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Replace Steering System Hoses | 2027-03-23 | 2027-03-25 | 54 hrs | FY27 | 106 | 90010133 | B2 | 1000128014 | 23.03.2027 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STHLF-STRHO | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Steering Hyd Oil Cooler | 2027-03-23 | 2027-03-23 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000128018 | 23.03.2027 | 15000 | CCK-MP-HAUL-DT221 -STRSYS-STOCO | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Operators Seat | 2027-03-23 | 2027-03-23 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000127987 | 23.03.2027 | 15000 | CCK-MP-HAUL-DT221 -STRUCT-CABIN-SEATS | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Front Wheel Bearings LH | 2027-03-23 | 2027-03-24 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157144 | 23.03.2027 | 16000 | CCK-MP-HAUL-DT136 -STRUCT-AXLES-FWBLH | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Front Wheel Bearings RH | 2027-03-23 | 2027-03-24 | 23 hrs | FY27 | 44 | 90017285 | B1 | 1000157232 | 23.03.2027 | 16000 | CCK-MP-HAUL-DT136 -STRUCT-AXLES-FWBRH | 7400 | 87780 | 11471
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Hyd Pump Steering & Brake | 2027-03-24 | 2027-03-25 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204433 | 24.03.2027 | 12000 | CCK-MP-HAUL-DT753 -STRSYS-STPMP | 6800 | 85999 | 7576
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Engine Midlife Complete | 2027-03-24 | 2027-03-25 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000155996 | 24.03.2027 | 12000 | CCK-MP-HAUL-DT140 -ENGINE | 7400 | 86695 | 31795
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Transmission Oil Cooler | 2027-03-25 | 2027-03-25 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000128138 | 25.03.2027 | 18000 | CCK-MP-HAUL-DT223 -TRNSYS-TROLC | 7400 | 54920 | 13339
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Auto Lube Pump | 2027-03-25 | 2027-03-25 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095196 | 25.03.2027 | 8000 | CCK-MP-HAUL-DT768 -GRSYST-ALBPP | 6800 | 79837 | 12182
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Pump Brake Cooling | 2027-03-26 | 2027-03-26 | 9 hrs | FY27 | 17 | 90002379 | B1 | 1000024924 | 26.03.2027 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-HYFPP | 7400 | 87135 | 19314
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Brake Cooling System Hoses | 2027-03-26 | 2027-03-27 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000083080 | 26.03.2027 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BRHLF-CBRHO | 7400 | 87135 | 19314
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Suspension RHR | 2027-03-27 | 2027-03-28 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000024008 | 27.03.2027 | 28000 | CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYRR | 7400 | 84375 | 22524
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Transmisson Calibration | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298735 | 27.03.2027 | 4500 | CCK-MP-HAUL-DT157 -TRNSYS-TRANS | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Wheel End RH | 2027-03-27 | 2027-03-28 | 32.5 hrs | FY27 | 58.5 | 90007352 | B1 | 1000024918 | 27.03.2027 | 24000 | CCK-MP-HAUL-DT100 -FDRSYS-FDRVE-FDRRH | 7400 | 87135 | 19314
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Grease Line/Burst Sleeve | 2027-03-27 | 2027-03-27 | 2 hrs | FY27 | 2 | 90017071 | B1 | 1000201220 | 27.03.2027 | 104 Weekly | CCK-MP-SUPP-SV4104-MODULE
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Service Air Conditioner 12M | 2027-03-28 | 2027-03-29 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174110 | 28.03.2027 | 12 Monthly | CCK-MP-HAUL-DT055 -STRUCT-CABIN-AIRCN | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 250hr Initial Valve Set | 2027-03-28 | 2027-03-28 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000167221 | 28.03.2027 | 250 | CCK-MP-HAUL-DT5316-ENGINE | 7400 | 45108 | 19566
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Cylinder Suspension LHF | 2027-03-28 | 2027-03-28 | 14 hrs | FY27 | 26 | 90011572 | B1 | 1000098148 | 28.03.2027 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-SUSPN-SCYLF | 4000 | 56923 | 15072
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Cylinder Suspension RHF | 2027-03-28 | 2027-03-29 | 23 hrs | FY27 | 44 | 90011573 | B1 | 1000098149 | 28.03.2027 | 18000 | CCK-MP-SUPP-WC221 -STRUCT-SUSPN-SCYRF | 4000 | 56923 | 15072
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Accumulator Hyd Steer Front | 2027-03-28 | 2027-03-28 | 7.5 hrs | FY27 | 11.5 | 90011352 | B1 | 1000095294 | 28.03.2027 | 25000 | CCK-MP-HAUL-DT770 -STRSYS-STACC-SACCF | 6800 | 79305 | 20439
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Hoist RH | 2027-03-28 | 2027-03-28 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128562 | 28.03.2027 | 28000 | CCK-MP-HAUL-DT099 -HYDSYS-HOCYL-HCYLR | 7400 | 87442 | 23283
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Water Cannon Maintenance | 2027-03-29 | 2027-03-29 | 3 hrs | FY27 | 3 | 90001682 | B1 | 1000018408 | 29.03.2027 | 6 Monthly | CCK-MP-SUPP-WC008 -STRUCT-WTANK-SPRAY | 3500 | 51417 | 5947
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Drive Shaft Transmission | 2027-03-29 | 2027-03-29 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154983 | 14.03.2027 | 18000 | CCK-MP-HAUL-DT153 -FDRSYS-DRSHT | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Steering LH | 2027-03-29 | 2027-03-29 | 12 hrs | FY27 | 20 | 90002385 | B1 | 1000024868 | 29.03.2027 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STRCY-STCYL | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Steering Linkages | 2027-03-29 | 2027-03-29 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317605 | 29.03.2027 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STLTR | 7400 | 87442 | 32853
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Steering System Hoses | 2027-03-29 | 2027-03-31 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083064 | 29.03.2027 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STHLF-STRHO | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Steering Hyd Oil Cooler | 2027-03-29 | 2027-03-29 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107023 | 29.03.2027 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STOCO | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Spiders Pump Drive Shaft | 2027-03-29 | 2027-03-29 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000025415 | 29.03.2027 | 18000 | CCK-MP-HAUL-DT135 -ENGINE-PMPDR-DRSHT | 7400 | 82965 | 13334
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Spider Trans Driveshaft | 2027-03-29 | 2027-03-29 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154950 | 29.03.2027 | 6000 | CCK-MP-HAUL-DT126 -FDRSYS-DRSHT-UNVSL | 7400 | 88657 | 132
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Bulk Grease Tank Breather | 2027-03-30 | 2027-03-30 | 1 hr | FY27 | 1 | 90022533 | B1 | 1000236910 | 30.03.2027 | 6 Monthly | CCK-MP-SUPP-SV221 -GRSYST-GRTNK | 5100 | 64374 | 4253
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Steering LH | 2027-03-31 | 2027-03-31 | 10 hrs | FY27 | 16 | 90011350 | B1 | 1000094285 | 31.03.2027 | 15000 | CCK-MP-HAUL-DT751 -STRSYS-STRCY-STCYL | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Steering RH | 2027-03-31 | 2027-03-31 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000094286 | 31.03.2027 | 15000 | CCK-MP-HAUL-DT751 -STRSYS-STRCY-STCYR | 6800 | 86211 | 11291
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 OHaul WaterTank Cannon & Spray Sys | 2027-03-31 | 2027-04-01 | 24 hrs | FY27 | 48 | 90036926 | B1 | 1000368893 | 31.03.2027 | 24 Monthly | CCK-MP-SUPP-WC224 -STRUCT-WTANK | 5000 | 70936 | 6229
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 250hr Initial Valve Set | 2027-04-01 | 2027-04-01 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000166981 | 01.04.2027 | 250 | CCK-MP-HAUL-DT5313-ENGINE | 7400 | 44693 | 19408
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Hoist LH | 2027-04-01 | 2027-04-01 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128603 | 01.04.2027 | 28000 | CCK-MP-HAUL-DT158 -HYDSYS-HOCYL-HCYLL | 7400 | 85964 | 23196
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Hoist RH | 2027-04-01 | 2027-04-01 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128604 | 01.04.2027 | 28000 | CCK-MP-HAUL-DT158 -HYDSYS-HOCYL-HCYLR | 7400 | 85964 | 23285
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Water Tank Module Midlife | 2027-04-01 | 2027-04-01 | 1 hr | FY27 | 1 | 90028970 | B1 | 1000288987 | 01.04.2027 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-WTANK | 3500 | 51417 | 51417
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Air Con Service & Overhaul | 2027-04-02 | 2027-04-03 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110613 | 02.04.2027 | 12 Monthly | CCK-MP-HAUL-DT753 -STRUCT-CABIN-AIRCN | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Air Con Service & Overhaul | 2027-04-02 | 2027-04-03 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110628 | 02.04.2027 | 12 Monthly | CCK-MP-HAUL-DT759 -STRUCT-CABIN-AIRCN | 6800 | 79716 | 28650
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl AOC Fan Motor Rear | 2027-04-03 | 2027-04-03 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000023659 | 03.04.2027 | 12000 | CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYM02 | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Service Air Conditioner 12M | 2027-04-04 | 2027-04-05 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174188 | 04.04.2027 | 12 Monthly | CCK-MP-HAUL-DT221 -STRUCT-CABIN-AIRCN | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Suspension RHF | 2027-04-04 | 2027-04-06 | 43 hrs | FY27 | 84 | 90002408 | B2 | 1000067511 | 04.04.2027 | 28000 | CCK-MP-HAUL-DT100 -STRUCT-SUSPN-SCYRF | 7400 | 87135 | 23110
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Spider Trans Driveshaft | 2027-04-04 | 2027-04-04 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154968 | 04.04.2027 | 6000 | CCK-MP-HAUL-DT143 -FDRSYS-DRSHT-UNVSL | 7400 | 88225 | 7566
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Spiders Pump Drive Shaft | 2027-04-05 | 2027-04-05 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026001 | 05.04.2027 | 18000 | CCK-MP-HAUL-DT5255-ENGINE-PMPDR-DRSHT | 7400 | 87580 | 13068
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Transmisson Calibration | 2027-04-05 | 2027-04-05 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298741 | 05.04.2027 | 4500 | CCK-MP-HAUL-DT222 -TRNSYS-TRANS | 7400 | 55735 | 4006
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Pressure Reducing Valve | 2027-04-05 | 2027-04-05 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204789 | 05.04.2027 | 12000 | CCK-MP-HAUL-DT757 -BRKSYS-BRVLV-VVPRV | 6800 | 80700 | 7627
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Wheel Group Front LH | 2027-04-05 | 2027-04-06 | 28 hrs | FY27 | 54 | 90017286 | B1 | 1000157159 | 05.04.2027 | 24000 | CCK-MP-HAUL-DT147 -STRUCT-AXLES-HUBLH | 7400 | 84659 | 19041
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Wheel Group Front RH | 2027-04-05 | 2027-04-06 | 28 hrs | FY27 | 54 | 90017287 | B1 | 1000157247 | 05.04.2027 | 24000 | CCK-MP-HAUL-DT147 -STRUCT-AXLES-HUBRH | 7400 | 84659 | 700
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Suspension RHF | 2027-04-05 | 2027-04-07 | 43 hrs | FY27 | 84 | 90002408 | B2 | 1000067591 | 05.04.2027 | 28000 | CCK-MP-HAUL-DT147 -STRUCT-SUSPN-SCYRF | 7400 | 84659 | 19041
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Auto Lube Pump | 2027-04-06 | 2027-04-06 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285786 | 06.04.2027 | 8000 | CCK-MP-HAUL-DT143 -GRSYST-ALBPP | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Transmisson Calibration | 2027-04-07 | 2027-04-07 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298733 | 07.04.2027 | 4500 | CCK-MP-HAUL-DT153 -TRNSYS-TRANS | 7400 | 84230 | 2506
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Service Air Conditioner 12M | 2027-04-07 | 2027-04-08 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174175 | 07.04.2027 | 12 Monthly | CCK-MP-HAUL-DT146 -STRUCT-CABIN-AIRCN | 7400 | 83062 | 31809
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Auto Lube Pump | 2027-04-07 | 2027-04-07 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285781 | 07.04.2027 | 8000 | CCK-MP-HAUL-DT136 -GRSYST-ALBPP | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Transmisson Calibration | 2027-04-08 | 2027-04-08 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298674 | 08.04.2027 | 4500 | CCK-MP-HAUL-DT097 -TRNSYS-TRANS | 7400 | 83804 | 17427
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Air Con Service & Overhaul | 2027-04-08 | 2027-04-09 | 36 hrs | FY27 | 36 | 90013265 | B1 | 1000110625 | 08.04.2027 | 12 Monthly | CCK-MP-HAUL-DT756 -STRUCT-CABIN-AIRCN | 6800 | 78754 | 19465
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Auto Lube Pump | 2027-04-09 | 2027-04-09 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285785 | 09.04.2027 | 8000 | CCK-MP-HAUL-DT142 -GRSYST-ALBPP | 7400 | 87027 | 11970
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Radiator Fan Hoses | 2027-04-09 | 2027-04-09 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307467 | 09.04.2027 | 12000 | CCK-MP-HAUL-DT055 -ENGINE-COSYS-RADTR | 7400 | 84122 | 30645
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Replace Operator Cabin Dash Bulbs | 2027-04-09 | 2027-04-09 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158228 | 09.04.2027 | 3000 | CCK-MP-HAUL-DT763 -STRUCT-CABIN | 6800 | 74143 | 74143
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Operator Cabin Dash Bulbs | 2027-04-09 | 2027-04-09 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158220 | 09.04.2027 | 3000 | CCK-MP-HAUL-DT755 -STRUCT-CABIN | 6800 | 84587 | 84587
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Brake Slack Adjuster Rear | 2027-04-09 | 2027-04-09 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000026417 | 09.04.2027 | 20000 | CCK-MP-HAUL-DT150 -BRKSYS-SLACK-SLACR | 7400 | 86656 | 14622
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Service Air Conditioner 12M | 2027-04-09 | 2027-04-10 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174174 | 09.04.2027 | 12 Monthly | CCK-MP-HAUL-DT143 -STRUCT-CABIN-AIRCN | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Transmisson Calibration | 2027-04-10 | 2027-04-10 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298673 | 10.04.2027 | 4500 | CCK-MP-HAUL-DT095 -TRNSYS-TRANS | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Brake Slack Adjuster Front | 2027-04-10 | 2027-04-10 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000026416 | 10.04.2027 | 20000 | CCK-MP-HAUL-DT150 -BRKSYS-SLACK-SLACF | 7400 | 86656 | 14622
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Wheel End LH | 2027-04-11 | 2027-04-12 | 32.5 hrs | FY27 | 58.5 | 90002374 | B1 | 1000023782 | 11.04.2027 | 24000 | CCK-MP-HAUL-DT057 -FDRSYS-FDRVE-FDRLH | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Brake Oil Cooler Front | 2027-04-11 | 2027-04-11 | 13 hrs | FY27 | 13 | 90010109 | B1 | 1000082508 | 11.04.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BROCO-BROCF | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Hyd Pump Steering Main & Fan | 2027-04-11 | 2027-04-11 | 17 hrs | FY27 | 17 | 90002383 | B1 | 1000023794 | 11.04.2027 | 24000 | CCK-MP-HAUL-DT057 -STRSYS-STPMP | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Replace Hoses Hoist System | 2027-04-11 | 2027-04-12 | 20 hrs | FY27 | 40 | 90010105 | B1 | 1000082503 | 11.04.2027 | 24000 | CCK-MP-HAUL-DT057 -HYDSYS-HDHLF-HSTHO | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Replace Brake System Hoses | 2027-04-11 | 2027-04-13 | 46 hrs | FY27 | 90 | 90010129 | B3 | 1000082509 | 11.04.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BRHLF-BRHOS | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Brake Cooling System Hoses | 2027-04-11 | 2027-04-12 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000082510 | 11.04.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BRHLF-CBRHO | 7400 | 91273 | 18727
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Pressure Reducing Valve | 2027-04-11 | 2027-04-11 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204783 | 11.04.2027 | 12000 | CCK-MP-HAUL-DT751 -BRKSYS-BRVLV-VVPRV | 6800 | 86211 | 8088
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Spiders Pump Drive Shaft | 2027-04-11 | 2027-04-11 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000024341 | 11.04.2027 | 18000 | CCK-MP-HAUL-DT091 -ENGINE-PMPDR-DRSHT | 7400 | 83859 | 12875
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Service Air Conditioner 12M | 2027-04-12 | 2027-04-13 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174113 | 12.04.2027 | 12 Monthly | CCK-MP-HAUL-DT058 -STRUCT-CABIN-AIRCN | 7400 | 87864 | 1976
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Wheel Motor Oil RH | 2027-04-12 | 2027-04-12 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338223 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -FDRSYS-WLMTR-WHMRH | 6800 | 74143 | 21626
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Wheel Motor Oil LH | 2027-04-12 | 2027-04-12 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338222 | 06.02.2027 | 25000 | CCK-MP-HAUL-DT763 -FDRSYS-WLMTR-WHMLH | 6800 | 74143 | 21626
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Engine Midlife Complete | 2027-04-12 | 2027-04-14 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285178 | 12.04.2027 | 12500 | CCK-MP-HAUL-DT760 -ENGINE | 6800 | 80390 | 8061
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Pressure Reducing Valve | 2027-04-12 | 2027-04-12 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204785 | 12.04.2027 | 12000 | CCK-MP-HAUL-DT753 -BRKSYS-BRVLV-VVPRV | 6800 | 85999 | 20943
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Wheel Motor Oil LH | 2027-04-12 | 2027-04-12 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338244 | 12.04.2027 | 25000 | CCK-MP-HAUL-DT774 -FDRSYS-WLMTR-WHMLH | 6800 | 81047 | 20532
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Wheel Motor LH | 2027-04-12 | 2027-04-14 | 45.5 hrs | FY27 | 83.5 | 90011335 | B1 | 1000095493 | 12.04.2027 | 25000 | CCK-MP-HAUL-DT774 -FDRSYS-WLMTR-WHMLH | 6800 | 81047 | 20532
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Wheel Motor Oil RH | 2027-04-12 | 2027-04-12 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338245 | 12.04.2027 | 25000 | CCK-MP-HAUL-DT774 -FDRSYS-WLMTR-WHMRH | 6800 | 81047 | 20532
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Wheel Motor RH | 2027-04-12 | 2027-04-14 | 45.5 hrs | FY27 | 83.5 | 90011336 | B1 | 1000095494 | 12.04.2027 | 25000 | CCK-MP-HAUL-DT774 -FDRSYS-WLMTR-WHMRH | 6800 | 81047 | 20532
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Cyl Hoist LH | 2027-04-12 | 2027-04-12 | 17 hrs | FY27 | 33 | 90011357 | B1 | 1000095511 | 12.04.2027 | 25000 | CCK-MP-HAUL-DT774 -HYDSYS-HOCYL-HCYLL | 6800 | 81047 | 20532
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Brake Accumulator LHF | 2027-04-12 | 2027-04-12 | 2 hrs | FY27 | 2 | 90026963 | B1 | 1000272831 | 12.04.2027 | 18000 | CCK-MP-SUPP-LL0007-BRKSYS-BACCM-ACC01 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Brake Accumulator LH Mid | 2027-04-12 | 2027-04-12 | 2 hrs | FY27 | 2 | 90026963 | B1 | 1000272832 | 12.04.2027 | 18000 | CCK-MP-SUPP-LL0007-BRKSYS-BACCM-ACC02 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Brake Accumulator LHR | 2027-04-12 | 2027-04-12 | 2 hrs | FY27 | 2 | 90026965 | B2 | 1000272833 | 12.04.2027 | 18000 | CCK-MP-SUPP-LL0007-BRKSYS-BACCM-ACC03 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Brake Accumulator RHF | 2027-04-12 | 2027-04-12 | 2 hrs | FY27 | 2 | 90026965 | B2 | 1000272834 | 12.04.2027 | 18000 | CCK-MP-SUPP-LL0007-BRKSYS-BACCM-ACC04 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Brake Accumulator RH Mid | 2027-04-12 | 2027-04-12 | 2 hrs | FY27 | 2 | 90026963 | B1 | 1000272835 | 12.04.2027 | 18000 | CCK-MP-SUPP-LL0007-BRKSYS-BACCM-ACC05 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Brake Accumulator RHR | 2027-04-12 | 2027-04-12 | 2 hrs | FY27 | 2 | 90026963 | B1 | 1000272836 | 12.04.2027 | 18000 | CCK-MP-SUPP-LL0007-BRKSYS-BACCM-ACC06 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Wheel Hub Right Rear | 2027-04-12 | 2027-04-12 | 8 hrs | FY27 | 16 | 90026984 | B1 | 1000272858 | 12.04.2027 | 18000 | CCK-MP-SUPP-LL0007-STRUCT-AXLRR-HUBRR | 3400 | 15216 | 5278
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Spider Trans Driveshaft | 2027-04-12 | 2027-04-12 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154958 | 12.04.2027 | 6000 | CCK-MP-HAUL-DT136 -FDRSYS-DRSHT-UNVSL | 7400 | 87780 | 6584
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Auto Lube Pump | 2027-04-13 | 2027-04-13 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094878 | 13.04.2027 | 8000 | CCK-MP-HAUL-DT762 -GRSYST-ALBPP | 6800 | 76486 | 10392
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Operators Seat | 2027-04-13 | 2027-04-13 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000027029 | 13.04.2027 | 15000 | CCK-MP-HAUL-DT159 -STRUCT-CABIN-SEATS | 7400 | 90235 | 18567
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Cyl Suspension RHR | 2027-04-13 | 2027-04-14 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000027038 | 13.04.2027 | 28000 | CCK-MP-HAUL-DT159 -STRUCT-SUSPN-SCYRR | 7400 | 90235 | 22947
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Transmisson Calibration | 2027-04-14 | 2027-04-14 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298664 | 14.04.2027 | 4500 | CCK-MP-HAUL-DT056 -TRNSYS-TRANS | 7400 | 84421 | 8230
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension LHF | 2027-04-15 | 2027-04-15 | 2 hrs | FY27 | 2 | 90038229 | B1 | 1000382496 | 15.04.2027 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension RHF | 2027-04-15 | 2027-04-15 | 2 hrs | FY27 | 2 | 90038229 | B1 | 1000382497 | 15.04.2027 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC224 OHaul WaterTank Cannon & Spray Sys | 2027-04-16 | 2027-04-17 | 24 hrs | FY27 | 48 | 90036926 | B1 | 1000368895 | 16.04.2027 | 24 Monthly | CCK-MP-SUPP-WC225 -STRUCT-WTANK | 5000 | 75244 | 75244
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Radiator Fan Hoses | 2027-04-18 | 2027-04-18 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307513 | 18.04.2027 | 12000 | CCK-MP-HAUL-DT140 -ENGINE-COSYS-RADTR | 7400 | 86767 | 75352
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Spider Trans Driveshaft | 2027-04-18 | 2027-04-18 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154964 | 18.04.2027 | 6000 | CCK-MP-HAUL-DT140 -FDRSYS-DRSHT-UNVSL | 7400 | 86767 | 888
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Service Air Conditioner 12M | 2027-04-18 | 2027-04-19 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174163 | 18.04.2027 | 12 Monthly | CCK-MP-HAUL-DT099 -STRUCT-CABIN-AIRCN | 7400 | 87442 | 10255
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Steering RH | 2027-04-18 | 2027-04-18 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000094657 | 18.04.2027 | 15000 | CCK-MP-HAUL-DT758 -STRSYS-STRCY-STCYR | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Engine Midlife Complete | 2027-04-20 | 2027-04-22 | 49 hrs | FY27 | 76 | 90028571 | B1 | 1000285171 | 20.04.2027 | 12500 | CCK-MP-HAUL-DT753 -ENGINE | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Pressure Reducing Valve | 2027-04-20 | 2027-04-20 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204790 | 20.04.2027 | 12000 | CCK-MP-HAUL-DT758 -BRKSYS-BRVLV-VVPRV | 6800 | 85895 | 17961
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Auto Lube Pump | 2027-04-22 | 2027-04-22 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285623 | 22.04.2027 | 8000 | CCK-MP-HAUL-DT055 -GRSYST-ALBPP | 7400 | 84122 | 15901
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Transmission Oil Cooler | 2027-04-22 | 2027-04-22 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000091468 | 22.04.2027 | 18000 | CCK-MP-HAUL-DT155 -TRNSYS-TROLC | 7400 | 81407 | 12608
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Auto Lube Pump | 2027-04-24 | 2027-04-24 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285782 | 24.04.2027 | 8000 | CCK-MP-HAUL-DT137 -GRSYST-ALBPP | 7400 | 84196 | 9757
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Replace Operator Cabin Dash Bulbs | 2027-04-24 | 2027-04-24 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158227 | 24.04.2027 | 3000 | CCK-MP-HAUL-DT762 -STRUCT-CABIN | 6800 | 76486 | 20565
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Radiator Fan Hoses | 2027-04-24 | 2027-04-24 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307531 | 24.04.2027 | 12000 | CCK-MP-HAUL-DT150 -ENGINE-COSYS-RADTR | 7400 | 86656 | 33066
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Transmission | 2027-04-25 | 2027-04-26 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000271869 | 25.04.2027 | 18000 | CCK-MP-HAUL-DT055 -TRNSYS-TRANS | 7400 | 84122 | 15848
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Motor Lube Axle Hoses | 2027-04-25 | 2027-04-25 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000271944 | 25.04.2027 | 12000 | CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYM01 | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Spider Trans Driveshaft | 2027-04-25 | 2027-04-25 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154996 | 25.04.2027 | 6000 | CCK-MP-HAUL-DT221 -FDRSYS-DRSHT-UNVSL | 7400 | 57237 | 5640
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Hyd Pump Steering Main | 2027-04-25 | 2027-04-25 | 6 hrs | FY27 | 6 | 90000896 | B2 | 1000033294 | 25.04.2027 | 15000 | CCK-MP-SUPP-WC224 -STRSYS-STPMP | 5000 | 71088 | 11436
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Spider Trans Driveshaft | 2027-04-26 | 2027-04-26 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154922 | 26.04.2027 | 6000 | CCK-MP-HAUL-DT056 -FDRSYS-DRSHT-UNVSL | 7400 | 84421 | 11711
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Engine Cat C175-16 | 2027-04-26 | 2027-04-29 | 84 hrs | FY27 | 137 | 90015881 | B1 | 1000155907 | 26.04.2027 | 24000 | CCK-MP-HAUL-DT090 -ENGINE | 7400 | 81670 | 81670
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Pressure Reducing Valve | 2027-04-27 | 2027-04-27 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204793 | 27.04.2027 | 12000 | CCK-MP-HAUL-DT761 -BRKSYS-BRVLV-VVPRV | 6800 | 78336 | 20667
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Pressure Reducing Valve | 2027-04-27 | 2027-04-27 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204845 | 27.04.2027 | 12000 | CCK-MP-HAUL-DT773 -BRKSYS-BRVLV-VVPRV | 6800 | 75884 | 10579
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Spiders Pump Drive Shaft | 2027-04-27 | 2027-04-27 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000026133 | 27.04.2027 | 18000 | CCK-MP-HAUL-DT146 -ENGINE-PMPDR-DRSHT | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Drive Shaft Transmission | 2027-04-27 | 2027-04-27 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154971 | 27.04.2027 | 18000 | CCK-MP-HAUL-DT146 -FDRSYS-DRSHT | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Differential | 2027-04-27 | 2027-04-28 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000026141 | 27.04.2027 | 18000 | CCK-MP-HAUL-DT146 -FDRSYS-DIFFL | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Transmisson Calibration | 2027-04-28 | 2027-04-28 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298742 | 28.04.2027 | 4500 | CCK-MP-HAUL-DT223 -TRNSYS-TRANS | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Spider Trans Driveshaft | 2027-04-28 | 2027-04-28 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154962 | 28.04.2027 | 6000 | CCK-MP-HAUL-DT138 -FDRSYS-DRSHT-UNVSL | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Transmisson Calibration | 2027-04-28 | 2027-04-28 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298818 | 28.04.2027 | 4500 | CCK-MP-HAUL-DT5318-TRNSYS-TRANS | 7400 | 45240 | 9085
T264 | Onsite PM | Haul | Fortescue | DT5489 | DT5489 Service Air Conditioner 12M | 2027-04-29 | 2027-04-29 | 12 hrs | FY27 | 12 | 90029300 | B1 | 1000372286 | 29.04.2027 | 12 Monthly | CCK-MP-HAUL-DT5489-STRUCT-CABIN-AIRCN | 3000 | 1 | 1
T264 | Onsite PM | Haul | Fortescue | DT5490 | DT5490 Service Air Conditioner 12M | 2027-04-29 | 2027-04-29 | 12 hrs | FY27 | 12 | 90029300 | B1 | 1000372331 | 29.04.2027 | 12 Monthly | CCK-MP-HAUL-DT5490-STRUCT-CABIN-AIRCN | 3000 | 1 | 1
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 HP Grease Gun, Hose & Burst Sleeve | 2027-04-29 | 2027-04-29 | 4 hrs | FY27 | 4 | 90022836 | B1 | 1000238751 | 29.04.2027 | 12 Monthly | CCK-MP-SUPP-SV221 -GRSYST-ALHLF | 5100 | 64374 | 64374
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Brake Cabinet Hoses | 2027-04-30 | 2027-05-01 | 32.5 hrs | FY27 | 62.5 | 90015041 | B1 | 1000126208 | 30.04.2027 | 25000 | CCK-MP-HAUL-DT751 -BRKSYS-BRHLF | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Pump Hoist | 2027-04-30 | 2027-04-30 | 11.5 hrs | FY27 | 12 | 90011355 | B1 | 1000094290 | 30.04.2027 | 25000 | CCK-MP-HAUL-DT751 -HYDSYS-HOPMP | 6800 | 86211 | 2446
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Steering Bell Crank & Links | 2027-04-30 | 2027-05-01 | 20 hrs | FY27 | 36 | 90028566 | B1 | 1000317654 | 30.04.2027 | 30000 | CCK-MP-HAUL-DT161 -STRSYS-STLTR-STLAC | 7400 | 80609 | 24548
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Suspension RHR | 2027-04-30 | 2027-05-01 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000024765 | 30.04.2027 | 28000 | CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYRR | 7400 | 83804 | 22486
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Transmission | 2027-04-30 | 2027-05-01 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000272337 | 30.04.2027 | 18000 | CCK-MP-HAUL-DT146 -TRNSYS-TRANS | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Transmission Oil Cooler | 2027-04-30 | 2027-04-30 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000091424 | 30.04.2027 | 18000 | CCK-MP-HAUL-DT146 -TRNSYS-TROLC | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Replace Trans TCon System Hoses | 2027-04-30 | 2027-05-01 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000091443 | 30.04.2027 | 18000 | CCK-MP-HAUL-DT146 -TRNSYS-TRANS-TRNHO | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Replace Hoses Differential System | 2027-04-30 | 2027-04-30 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000091444 | 30.04.2027 | 18000 | CCK-MP-HAUL-DT146 -FDRSYS-DIFFL-DIFHO | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Spiders Pump Drive Shaft | 2027-05-01 | 2027-05-01 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000226750 | 01.05.2027 | 18000 | CCK-MP-HAUL-DT055 -ENGINE-PMPDR-DRSHT | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Hoist LH | 2027-05-01 | 2027-05-01 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128583 | 01.05.2027 | 28000 | CCK-MP-HAUL-DT143 -HYDSYS-HOCYL-HCYLL | 7400 | 88225 | 22268
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Hoist RH | 2027-05-01 | 2027-05-01 | 17 hrs | FY27 | 33 | 90015131 | B1 | 1000128584 | 01.05.2027 | 28000 | CCK-MP-HAUL-DT143 -HYDSYS-HOCYL-HCYLR | 7400 | 88225 | 22268
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Operators Seat | 2027-05-02 | 2027-05-02 | 3 hrs | FY27 | 6 | 90002395 | B1 | 1000128056 | 02.05.2027 | 15000 | CCK-MP-HAUL-DT222 -STRUCT-CABIN-SEATS | 7400 | 55735 | 9457
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Suspension RHF | 2027-05-02 | 2027-05-04 | 43 hrs | FY27 | 84 | 90002408 | B2 | 1000067555 | 02.05.2027 | 28000 | CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYRF | 7400 | 82982 | 22553
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Auto Lube Pump | 2027-05-02 | 2027-05-02 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285634 | 02.05.2027 | 8000 | CCK-MP-HAUL-DT097 -GRSYST-ALBPP | 7400 | 83804 | 2994
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl AOC Fan Motor Rear | 2027-05-02 | 2027-05-02 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000027003 | 02.05.2027 | 12000 | CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYM02 | 7400 | 90235 | 18811
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Pressure Reducing Valve | 2027-05-04 | 2027-05-04 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204798 | 04.05.2027 | 12000 | CCK-MP-HAUL-DT766 -BRKSYS-BRVLV-VVPRV | 6800 | 78074 | 11013
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Brake Slack Adjuster Front | 2027-05-07 | 2027-05-07 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000024044 | 07.05.2027 | 20000 | CCK-MP-HAUL-DT086 -BRKSYS-SLACK-SLACF | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Brake Slack Adjuster Rear | 2027-05-07 | 2027-05-07 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000024045 | 07.05.2027 | 20000 | CCK-MP-HAUL-DT086 -BRKSYS-SLACK-SLACR | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 250hr Initial Valve Set | 2027-05-08 | 2027-05-08 | 8 hrs | FY27 | 16 | 90015884 | B1 | 1000155910 | 08.05.2027 | 250 | CCK-MP-HAUL-DT090 -ENGINE | 7400 | 81670 | 81670
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Pressure Reducing Valve | 2027-05-08 | 2027-05-08 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204846 | 08.05.2027 | 12000 | CCK-MP-HAUL-DT774 -BRKSYS-BRVLV-VVPRV | 6800 | 81047 | 6986
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Suspension RHR | 2027-05-09 | 2027-05-10 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000023882 | 09.05.2027 | 28000 | CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYRR | 7400 | 87864 | 22115
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Auto Lube Pump | 2027-05-09 | 2027-05-09 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000095514 | 09.05.2027 | 8000 | CCK-MP-HAUL-DT774 -GRSYST-ALBPP | 6800 | 81047 | 3051
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Hoist LH | 2027-05-09 | 2027-05-09 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128557 | 09.05.2027 | 28000 | CCK-MP-HAUL-DT097 -HYDSYS-HOCYL-HCYLL | 7400 | 83804 | 22316
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Auto Lube Pump | 2027-05-10 | 2027-05-10 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285638 | 10.05.2027 | 8000 | CCK-MP-HAUL-DT127 -GRSYST-ALBPP | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Transmisson Calibration | 2027-05-11 | 2027-05-11 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298720 | 11.05.2027 | 4500 | CCK-MP-HAUL-DT135 -TRNSYS-TRANS | 7400 | 82965 | 7974
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Transmisson Calibration | 2027-05-11 | 2027-05-11 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298679 | 11.05.2027 | 4500 | CCK-MP-HAUL-DT130 -TRNSYS-TRANS | 7400 | 85185 | 7959
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Wheel Motor Oil LH | 2027-05-12 | 2027-05-12 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338238 | 12.05.2027 | 25000 | CCK-MP-HAUL-DT771 -FDRSYS-WLMTR-WHMLH | 6800 | 84423 | 19973
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Wheel Motor Oil RH | 2027-05-12 | 2027-05-12 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338239 | 12.05.2027 | 25000 | CCK-MP-HAUL-DT771 -FDRSYS-WLMTR-WHMRH | 6800 | 84423 | 19973
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Operator Cabin Dash Bulbs | 2027-05-14 | 2027-05-14 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158216 | 14.05.2027 | 3000 | CCK-MP-HAUL-DT751 -STRUCT-CABIN | 6800 | 86211 | 11291
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Service Air Conditioner 12M | 2027-05-14 | 2027-05-15 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174186 | 14.05.2027 | 12 Monthly | CCK-MP-HAUL-DT161 -STRUCT-CABIN-AIRCN | 7400 | 80609 | 1574
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Replace Operator Cabin Dash Bulbs | 2027-05-14 | 2027-05-14 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158221 | 14.05.2027 | 3000 | CCK-MP-HAUL-DT756 -STRUCT-CABIN | 6800 | 78754 | 78754
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Auto Lube Pump | 2027-05-16 | 2027-05-16 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285626 | 16.05.2027 | 8000 | CCK-MP-HAUL-DT058 -GRSYST-ALBPP | 7400 | 87864 | 1976
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Inspect Rear Axle Housing | 2027-05-16 | 2027-05-16 | 1 hr | FY27 | 1 | 90019256 | B1 | 1000196434 | 16.05.2027 | 2000 | CCK-MP-SUPP-WC224 -STRUCT-RAXHO | 5000 | 71088 | 71088
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Auto Lube Pump | 2027-05-17 | 2027-05-17 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285805 | 17.05.2027 | 8000 | CCK-MP-HAUL-DT5313-GRSYST-ALBPP | 7400 | 44693 | 7599
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Auto Lube Pump | 2027-05-17 | 2027-05-17 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285800 | 17.05.2027 | 8000 | CCK-MP-HAUL-DT221 -GRSYST-ALBPP | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Service Air Conditioner 12M | 2027-05-17 | 2027-05-18 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174178 | 17.05.2027 | 12 Monthly | CCK-MP-HAUL-DT149 -STRUCT-CABIN-AIRCN | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Tyre Sense Battery | 2027-05-17 | 2027-05-17 | 2 hrs | FY27 | 2 | 90017022 | B1 | 1000153161 | 17.05.2027 | 24 Monthly | CCK-MP-HAUL-DT149 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Brake Cooling System Hoses | 2027-05-17 | 2027-05-18 | 30 hrs | FY27 | 60 | 90010130 | B1 | 1000111972 | 17.05.2027 | 24000 | CCK-MP-HAUL-DT5202-BRKSYS-BRHLF-CBRHO | 7400 | 89142 | 13327
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Steering Linkages | 2027-05-18 | 2027-05-18 | 15 hrs | FY27 | 28 | 90028568 | B1 | 1000317635 | 18.05.2027 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STLTR | 7400 | 86975 | 31553
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Replace Steering System Hoses | 2027-05-18 | 2027-05-20 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000083425 | 18.05.2027 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STHLF-STRHO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Steering Hyd Oil Cooler | 2027-05-18 | 2027-05-18 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107027 | 18.05.2027 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STOCO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Front Wheel Bearings LH | 2027-05-18 | 2027-05-19 | 23 hrs | FY27 | 44 | 90017284 | B1 | 1000157132 | 18.05.2027 | 16000 | CCK-MP-HAUL-DT099 -STRUCT-AXLES-FWBLH | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Engine Midlife Complete | 2027-05-19 | 2027-05-20 | 40 hrs | FY27 | 62 | 90015886 | B1 | 1000167383 | 19.05.2027 | 12000 | CCK-MP-HAUL-DT5318-ENGINE | 7400 | 45240 | 6204
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Transmission | 2027-05-19 | 2027-05-20 | 22 hrs | FY27 | 39 | 90026996 | B2 | 1000272335 | 19.05.2027 | 18000 | CCK-MP-HAUL-DT143 -TRNSYS-TRANS | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Differential | 2027-05-19 | 2027-05-20 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000025943 | 19.05.2027 | 18000 | CCK-MP-HAUL-DT143 -FDRSYS-DIFFL | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Replace Trans TCon System Hoses | 2027-05-19 | 2027-05-20 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000090136 | 19.05.2027 | 18000 | CCK-MP-HAUL-DT143 -TRNSYS-TRANS-TRNHO | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Replace Hoses Differential System | 2027-05-19 | 2027-05-19 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000090137 | 19.05.2027 | 18000 | CCK-MP-HAUL-DT143 -FDRSYS-DIFFL-DIFHO | 7400 | 88225 | 11934
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Initial Engine Valve Set | 2027-05-19 | 2027-05-19 | 12 hrs | FY27 | 24 | 90015765 | B1 | 1000269912 | 19.05.2027 | 250 | CCK-MP-SUPP-WC220 -ENGINE | 4300 | 58137 | 14252
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Water Cannon Maintenance | 2027-05-20 | 2027-05-20 | 3 hrs | FY27 | 3 | 90001682 | B1 | 1000107576 | 20.05.2027 | 6 Monthly | CCK-MP-SUPP-WC009 -STRUCT-WTANK-SPRAY
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Hub & Spindle RH | 2027-05-21 | 2027-05-22 | 32 hrs | FY27 | 60 | 90011364 | B1 | 1000094459 | 21.05.2027 | 18000 | CCK-MP-HAUL-DT754 -STRUCT-AXLES-HUBRH | 6800 | 83256 | 12630
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Transmisson Calibration | 2027-05-21 | 2027-05-21 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298795 | 21.05.2027 | 4500 | CCK-MP-HAUL-DT5255-TRNSYS-TRANS | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Cyl Suspension LHF | 2027-05-21 | 2027-05-23 | 43 hrs | FY27 | 84 | 90002408 | B1 | 1000128063 | 21.05.2027 | 28000 | CCK-MP-HAUL-DT222 -STRUCT-SUSPN-SCYLF | 7400 | 55735 | 22120
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Replace Operator Cabin Dash Bulbs | 2027-05-21 | 2027-05-21 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158235 | 21.05.2027 | 3000 | CCK-MP-HAUL-DT770 -STRUCT-CABIN | 6800 | 79305 | 79305
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Suspension RHR | 2027-05-21 | 2027-05-22 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000024576 | 21.05.2027 | 28000 | CCK-MP-HAUL-DT094 -STRUCT-SUSPN-SCYRR | 7400 | 88788 | 21945
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Airconditioner Service | 2027-05-21 | 2027-05-22 | 24 hrs | FY27 | 24 | 90017449 | B1 | 1000290430 | 21.05.2027 | 5500 | CCK-MP-SUPP-WC224 -STRUCT-CABIN-AIRCN | 5000 | 71088 | 6229
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Transmisson Calibration | 2027-05-21 | 2027-05-21 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298728 | 21.05.2027 | 4500 | CCK-MP-HAUL-DT147 -TRNSYS-TRANS | 7400 | 84659 | 716
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Service Air Conditioner 12M | 2027-05-22 | 2027-05-23 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174118 | 22.05.2027 | 12 Monthly | CCK-MP-HAUL-DT091 -STRUCT-CABIN-AIRCN | 7400 | 83859 | 23814
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Torque Converter | 2027-05-23 | 2027-05-24 | 27 hrs | FY27 | 53 | 90002369 | B1 | 1000023714 | 23.05.2027 | 24000 | CCK-MP-HAUL-DT056 -TRNSYS-TRQUE | 7400 | 84421 | 18034
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Wheel End LH | 2027-05-23 | 2027-05-24 | 32.5 hrs | FY27 | 58.5 | 90002374 | B1 | 1000023719 | 23.05.2027 | 24000 | CCK-MP-HAUL-DT056 -FDRSYS-FDRVE-FDRLH | 7400 | 84421 | 18034
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Wheel End RH | 2027-05-23 | 2027-05-24 | 32.5 hrs | FY27 | 58.5 | 90007352 | B1 | 1000023720 | 23.05.2027 | 24000 | CCK-MP-HAUL-DT056 -FDRSYS-FDRVE-FDRRH | 7400 | 84421 | 18034
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Auto Lube Pump | 2027-05-23 | 2027-05-23 | 2 hrs | FY27 | 2 | 90002914 | B2 | 1000040611 | 23.05.2027 | 6000 | CCK-MP-SUPP-WC225 -GRSYST-ALBPP | 5000 | 75244 | 1997
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Motor Lube Axle Hoses | 2027-05-23 | 2027-05-23 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000271982 | 23.05.2027 | 12000 | CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-HYM01 | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Spider Trans Driveshaft | 2027-05-24 | 2027-05-24 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154928 | 24.05.2027 | 6000 | CCK-MP-HAUL-DT082 -FDRSYS-DRSHT-UNVSL | 7400 | 84374 | 4829
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Transmisson Calibration | 2027-05-24 | 2027-05-24 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298816 | 24.05.2027 | 4500 | CCK-MP-HAUL-DT5316-TRNSYS-TRANS | 7400 | 45108 | 15135
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Service Air Conditioner 12M | 2027-05-24 | 2027-05-25 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000174192 | 24.05.2027 | 12 Monthly | CCK-MP-HAUL-DT5255-STRUCT-CABIN-AIRCN | 7400 | 87580 | 87580
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Wheel Motor Oil LH | 2027-05-24 | 2027-05-24 | 1 hr | FY27 | 1 | 90033606 | B1 | 1000338230 | 28.04.2027 | 25000 | CCK-MP-HAUL-DT767 -FDRSYS-WLMTR-WHMLH | 6800 | 74312 | 19669
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Radiator Fan Hoses | 2027-05-25 | 2027-05-25 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307483 | 25.05.2027 | 12000 | CCK-MP-HAUL-DT090 -ENGINE-COSYS-RADTR | 7400 | 81670 | 29126
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Motor Lube Axle Hoses | 2027-05-25 | 2027-05-25 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000271958 | 25.05.2027 | 12000 | CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYM01 | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl AOC Fan Motor Rear | 2027-05-25 | 2027-05-25 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000024289 | 25.05.2027 | 12000 | CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYM02 | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Spider Trans Driveshaft | 2027-05-25 | 2027-05-25 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154934 | 25.05.2027 | 6000 | CCK-MP-HAUL-DT090 -FDRSYS-DRSHT-UNVSL | 7400 | 81670 | 5994
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Replace Operator Cabin Dash Bulbs | 2027-05-25 | 2027-05-25 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158238 | 25.05.2027 | 3000 | CCK-MP-HAUL-DT773 -STRUCT-CABIN | 6800 | 75884 | 75884
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Spider Trans Driveshaft | 2027-05-26 | 2027-05-26 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154926 | 26.05.2027 | 6000 | CCK-MP-HAUL-DT058 -FDRSYS-DRSHT-UNVSL | 7400 | 87864 | 5769
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Transmisson Calibration | 2027-05-26 | 2027-05-26 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298723 | 26.05.2027 | 4500 | CCK-MP-HAUL-DT138 -TRNSYS-TRANS | 7400 | 82982 | 6438
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Transmisson Calibration | 2027-05-28 | 2027-05-28 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298725 | 28.05.2027 | 4500 | CCK-MP-HAUL-DT142 -TRNSYS-TRANS | 7400 | 87027 | 9824
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Drive Shaft Transmission | 2027-05-28 | 2027-05-28 | 8 hrs | FY27 | 16 | 90017195 | B1 | 1000154967 | 28.05.2027 | 18000 | CCK-MP-HAUL-DT142 -FDRSYS-DRSHT | 7400 | 87027 | 11970
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Pressure Reducing Valve | 2027-05-28 | 2027-05-28 | 4.5 hrs | FY27 | 4.5 | 90019929 | B1 | 1000204842 | 28.05.2027 | 12000 | CCK-MP-HAUL-DT770 -BRKSYS-BRVLV-VVPRV | 6800 | 79305 | 6269
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Differential | 2027-05-30 | 2027-05-31 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000025877 | 30.05.2027 | 18000 | CCK-MP-HAUL-DT142 -FDRSYS-DIFFL | 7400 | 87027 | 11970
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Steering Brake Pump Compensator | 2027-05-30 | 2027-05-30 | 6 hrs | FY27 | 7 | 90019922 | B1 | 1000204774 | 30.05.2027 | 6000 | CCK-MP-HAUL-DT770 -STRSYS-STPMP | 6800 | 79305 | 24817
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Cyl Suspension LHF | 2027-05-30 | 2027-06-01 | 60 hrs | FY27 | 112 | 90011365 | B1 | 1000094619 | 30.05.2027 | 18000 | CCK-MP-HAUL-DT757 -STRUCT-SUSPN-SCYLF | 6800 | 80690 | 12602
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Spider Trans Driveshaft | 2027-06-01 | 2027-06-01 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154948 | 01.06.2027 | 6000 | CCK-MP-HAUL-DT100 -FDRSYS-DRSHT-UNVSL | 7400 | 87135 | 5703
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Spider Trans Driveshaft | 2027-06-01 | 2027-06-01 | 6 hrs | FY27 | 12 | 90017211 | B1 | 1000154972 | 01.06.2027 | 6000 | CCK-MP-HAUL-DT147 -FDRSYS-DRSHT-UNVSL | 7400 | 84659 | 716
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Air Conditioner 12M-Service | 2027-06-02 | 2027-06-03 | 18 hrs | FY27 | 18 | 90018230 | B1 | 1000272732 | 02.06.2027 | 12 Monthly | CCK-MP-SUPP-PM0001-STRUCT-CABIN-AIRCN | 3400 | 48287 | 48287
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Cyl Steering RH | 2027-06-03 | 2027-06-03 | 9 hrs | FY27 | 15 | 90011351 | B1 | 1000094763 | 03.06.2027 | 15000 | CCK-MP-HAUL-DT760 -STRSYS-STRCY-STCYR | 6800 | 80390 | 9568
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Cyl Suspension LHF | 2027-06-03 | 2027-06-05 | 43 hrs | FY27 | 84 | 90002408 | B1 | 1000067489 | 03.06.2027 | 28000 | CCK-MP-HAUL-DT095 -STRUCT-SUSPN-SCYLF | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Cyl Suspension LHR | 2027-06-03 | 2027-06-04 | 22 hrs | FY27 | 39 | 90002409 | B1 | 1000024638 | 03.06.2027 | 28000 | CCK-MP-HAUL-DT095 -STRUCT-SUSPN-SCYLR | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Cyl Suspension RHR | 2027-06-03 | 2027-06-04 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000024639 | 03.06.2027 | 28000 | CCK-MP-HAUL-DT095 -STRUCT-SUSPN-SCYRR | 7400 | 88921 | 21880
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Transmission Pump | 2027-06-03 | 2027-06-03 | 4 hrs | FY27 | 4 | 90000897 | B2 | 1000033284 | 03.06.2027 | 11000 | CCK-MP-SUPP-WC224 -TRNSYS-TRPMP-TMCPP | 5000 | 71088 | 6964
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Auto Lube Pump | 2027-06-04 | 2027-06-04 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094401 | 04.06.2027 | 8000 | CCK-MP-HAUL-DT753 -GRSYST-ALBPP | 6800 | 85999 | 2700
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Differential | 2027-06-04 | 2027-06-05 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000026009 | 04.06.2027 | 18000 | CCK-MP-HAUL-DT5255-FDRSYS-DIFFL | 7400 | 87580 | 11919
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Torque Converter | 2027-06-04 | 2027-06-05 | 27 hrs | FY27 | 53 | 90002369 | B1 | 1000024912 | 04.06.2027 | 24000 | CCK-MP-HAUL-DT100 -TRNSYS-TRQUE | 7400 | 87135 | 17914
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Replace Operator Cabin Dash Bulbs | 2027-06-04 | 2027-06-04 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158222 | 04.06.2027 | 3000 | CCK-MP-HAUL-DT757 -STRUCT-CABIN | 6800 | 80700 | 80700
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Spiders Pump Drive Shaft | 2027-06-06 | 2027-06-06 | 4 hrs | FY27 | 4 | 90002366 | B1 | 1000024719 | 06.06.2027 | 18000 | CCK-MP-HAUL-DT097 -ENGINE-PMPDR-DRSHT | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Transmission Oil Cooler | 2027-06-06 | 2027-06-06 | 12 hrs | FY27 | 12 | 90010097 | B1 | 1000083012 | 06.06.2027 | 18000 | CCK-MP-HAUL-DT097 -TRNSYS-TROLC | 7400 | 83804 | 11742
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Aftercooler | 2027-06-06 | 2027-06-06 | 6 hrs | FY27 | 6 | 90004021 | B2 | 1000079242 | 06.06.2027 | 20000 | CCK-MP-SUPP-WC3112-ENGINE-INTEX-AFTER | 5600 | 52240 | 10839
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Steering Bell Crank & Links | 2027-06-07 | 2027-06-08 | 20 hrs | FY27 | 36 | 90028566 | B1 | 1000317598 | 07.06.2027 | 30000 | CCK-MP-HAUL-DT091 -STRSYS-STLTR-STLAC | 7400 | 83859 | 23814
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Transmisson Calibration | 2027-06-10 | 2027-06-10 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298738 | 10.06.2027 | 4500 | CCK-MP-HAUL-DT160 -TRNSYS-TRANS | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Pump Brake Cooling | 2027-06-10 | 2027-06-10 | 9 hrs | FY27 | 17 | 90002379 | B1 | 1000023978 | 10.06.2027 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-HYFPP | 7400 | 84374 | 17432
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Replace Operator Cabin Dash Bulbs | 2027-06-10 | 2027-06-10 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158232 | 10.06.2027 | 3000 | CCK-MP-HAUL-DT767 -STRUCT-CABIN | 6800 | 74312 | 19669
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Auto Lube Pump | 2027-06-10 | 2027-06-10 | 2.5 hrs | FY27 | 2.5 | 90011370 | B1 | 1000094666 | 10.06.2027 | 8000 | CCK-MP-HAUL-DT758 -GRSYST-ALBPP | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Operator Cabin Dash Bulbs | 2027-06-11 | 2027-06-11 | 2 hrs | FY27 | 2 | 90017265 | B1 | 1000158218 | 11.06.2027 | 3000 | CCK-MP-HAUL-DT753 -STRUCT-CABIN | 6800 | 85999 | 22050
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Operator Seat | 2027-06-11 | 2027-06-11 | 3 hrs | FY27 | 6 | 90018539 | B1 | 1000201213 | 11.06.2027 | 6000 | CCK-MP-SUPP-SV4104-STRUCT-CABIN-SEATS | 5100 | 23504 | 1084
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Motor Lube Axle Hoses | 2027-06-13 | 2027-06-13 | 4 hrs | FY27 | 4 | 90026944 | B1 | 1000272020 | 13.06.2027 | 12000 | CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYM01 | 7400 | 86656 | 5355
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl AOC Fan Motor Rear | 2027-06-13 | 2027-06-13 | 6 hrs | FY27 | 6 | 90002376 | B1 | 1000026409 | 13.06.2027 | 12000 | CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYM02 | 7400 | 86656 | 5355
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Transmisson Calibration | 2027-06-13 | 2027-06-13 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298721 | 13.06.2027 | 4500 | CCK-MP-HAUL-DT136 -TRNSYS-TRANS | 7400 | 87780 | 9256
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Steering Hyd Oil Cooler | 2027-06-14 | 2027-06-14 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107010 | 14.06.2027 | 15000 | CCK-MP-HAUL-DT155 -STRSYS-STOCO | 7400 | 81407 | 8629
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Brake Oil Cooler Front | 2027-06-16 | 2027-06-16 | 13 hrs | FY27 | 13 | 90010109 | B1 | 1000091587 | 16.06.2027 | 24000 | CCK-MP-HAUL-DT161 -BRKSYS-BROCO-BROCF | 7400 | 80609 | 17509
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Brake Oil Cooler Rear | 2027-06-16 | 2027-06-16 | 13 hrs | FY27 | 13 | 90010108 | B1 | 1000091586 | 16.06.2027 | 24000 | CCK-MP-HAUL-DT161 -BRKSYS-BROCO-BROCR | 7400 | 80609 | 17509
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Steering RH | 2027-06-17 | 2027-06-17 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000027147 | 17.06.2027 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STRCY-STCYR | 7400 | 80609 | 8581
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Auto Lube Pump | 2027-06-17 | 2027-06-17 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285799 | 17.06.2027 | 8000 | CCK-MP-HAUL-DT161 -GRSYST-ALBPP | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Replace Steering System Hoses | 2027-06-17 | 2027-06-19 | 54 hrs | FY27 | 106 | 90010133 | B1 | 1000091592 | 17.06.2027 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STHLF-STRHO | 7400 | 80609 | 8581
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Hyd Pump Steering & Brake | 2027-06-19 | 2027-06-20 | 28 hrs | FY27 | 38 | 90019919 | B1 | 1000204746 | 19.06.2027 | 12000 | CCK-MP-HAUL-DT766 -STRSYS-STPMP | 6800 | 78074 | 7137
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Radiator Fan Hoses | 2027-06-19 | 2027-06-19 | 11 hrs | FY27 | 11 | 90031073 | B1 | 1000307541 | 19.06.2027 | 12000 | CCK-MP-HAUL-DT157 -ENGINE-COSYS-RADTR | 7400 | 83041 | 29465
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Replace Hoses Differential System | 2027-06-19 | 2027-06-19 | 5 hrs | FY27 | 5 | 90010101 | B2 | 1000091488 | 19.06.2027 | 18000 | CCK-MP-HAUL-DT155 -FDRSYS-DIFFL-DIFHO | 7400 | 81407 | 30632
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Seal Left Front | 2027-06-19 | 2027-06-19 | 5 hrs | FY27 | 5 | 90039057 | B1 | 1000390739 | 19.06.2027 | 5000 | CCK-MP-SUPP-LL0007-STRUCT-AXLLF | 3400 | 15216 | 1628
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Seal Left Rear | 2027-06-19 | 2027-06-19 | 5 hrs | FY27 | 5 | 90039057 | B1 | 1000390881 | 19.06.2027 | 5000 | CCK-MP-SUPP-LL0007-STRUCT-AXLLR | 3400 | 15216 | 1628
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Seal Right Front | 2027-06-19 | 2027-06-19 | 5 hrs | FY27 | 5 | 90039057 | B1 | 1000390885 | 19.06.2027 | 5000 | CCK-MP-SUPP-LL0007-STRUCT-AXLRF | 3400 | 15216 | 1628
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Seal Right Rear | 2027-06-19 | 2027-06-19 | 5 hrs | FY27 | 5 | 90039057 | B1 | 1000390883 | 19.06.2027 | 5000 | CCK-MP-SUPP-LL0007-STRUCT-AXLRR | 3400 | 15216 | 1628
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Brake Slack Adjuster Front | 2027-06-21 | 2027-06-21 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000026614 | 21.06.2027 | 20000 | CCK-MP-HAUL-DT153 -BRKSYS-SLACK-SLACF | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Brake Slack Adjuster Rear | 2027-06-21 | 2027-06-21 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000026615 | 21.06.2027 | 20000 | CCK-MP-HAUL-DT153 -BRKSYS-SLACK-SLACR | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Auto Lube Pump | 2027-06-23 | 2027-06-23 | 3 hrs | FY27 | 3 | 90002391 | B1 | 1000285790 | 23.06.2027 | 8000 | CCK-MP-HAUL-DT149 -GRSYST-ALBPP | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Hoist LH | 2027-06-23 | 2027-06-23 | 17 hrs | FY27 | 33 | 90015130 | B1 | 1000128571 | 23.06.2027 | 28000 | CCK-MP-HAUL-DT135 -HYDSYS-HOCYL-HCYLL | 7400 | 82965 | 23752
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 WaterTank Cannon & Spray Sys Insp | 2027-06-24 | 2027-06-24 | 3 hrs | FY27 | 3 | 90036929 | B1 | 1000368896 | 24.06.2027 | 6 Monthly | CCK-MP-SUPP-WC3111-STRUCT-WTANK | 5600 | 28968 | 28968
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Axle Lube Hyd Pump | 2027-06-26 | 2027-06-26 | 4 hrs | FY27 | 4 | 90010102 | B1 | 1000083318 | 26.06.2027 | 24000 | CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYPUM | 7400 | 87027 | 17423
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Pump Brake Cooling | 2027-06-26 | 2027-06-26 | 9 hrs | FY27 | 17 | 90002379 | B1 | 1000025885 | 26.06.2027 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-HYFPP | 7400 | 87027 | 17423
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Brake Slack Adjuster Front | 2027-06-26 | 2027-06-26 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000025627 | 26.06.2027 | 20000 | CCK-MP-HAUL-DT138 -BRKSYS-SLACK-SLACF | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Brake Slack Adjuster Rear | 2027-06-26 | 2027-06-26 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000025628 | 26.06.2027 | 20000 | CCK-MP-HAUL-DT138 -BRKSYS-SLACK-SLACR | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Differential | 2027-06-26 | 2027-06-27 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000026735 | 26.06.2027 | 18000 | CCK-MP-HAUL-DT155 -FDRSYS-DIFFL | 7400 | 81407 | 11450
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Inspect Rear Axle Housing | 2027-06-27 | 2027-06-27 | 1 hr | FY27 | 1 | 90019256 | B1 | 1000196435 | 27.06.2027 | 2000 | CCK-MP-SUPP-WC225 -STRUCT-RAXHO | 5000 | 75244 | 75244
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Steering Hyd Oil Cooler | 2027-06-28 | 2027-06-28 | 9 hrs | FY27 | 9 | 90012866 | B2 | 1000107021 | 28.06.2027 | 15000 | CCK-MP-HAUL-DT095 -STRSYS-STOCO | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Transmisson Calibration | 2027-06-28 | 2027-06-28 | 4 hrs | FY27 | 8 | 90029836 | B1 | 1000298678 | 28.06.2027 | 4500 | CCK-MP-HAUL-DT127 -TRNSYS-TRANS | 7400 | 83059 | 2333
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Repl Bulk Grease Tank Breather | 2027-06-28 | 2027-06-28 | 1 hr | FY27 | 1 | 90022533 | B1 | 1000236909 | 28.06.2027 | 6 Monthly | CCK-MP-SUPP-SV220 -GRSYST-GRTNK | 5100 | 58259 | 58259
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Suspension RHR | 2027-06-29 | 2027-06-30 | 22 hrs | FY27 | 39 | 90002409 | B2 | 1000026048 | 29.06.2027 | 28000 | CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYRR | 7400 | 87580 | 21361
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Pump Hoist | 2027-06-29 | 2027-06-29 | 11.5 hrs | FY27 | 12 | 90011355 | B1 | 1000095244 | 29.06.2027 | 25000 | CCK-MP-HAUL-DT769 -HYDSYS-HOPMP | 6800 | 80508 | 18606
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Differential | 2027-06-29 | 2027-06-30 | 38 hrs | FY27 | 66 | 90014504 | B1 | 1000025487 | 29.06.2027 | 18000 | CCK-MP-HAUL-DT136 -FDRSYS-DIFFL | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Brake Slack Adjuster Front | 2027-06-30 | 2027-06-30 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000023729 | 30.06.2027 | 20000 | CCK-MP-HAUL-DT056 -BRKSYS-SLACK-SLACF | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Brake Slack Adjuster Rear | 2027-06-30 | 2027-06-30 | 4 hrs | FY27 | 4 | 90002382 | B1 | 1000023730 | 30.06.2027 | 20000 | CCK-MP-HAUL-DT056 -BRKSYS-SLACK-SLACR | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Cyl Steering RH | 2027-06-30 | 2027-06-30 | 12 hrs | FY27 | 20 | 90002385 | B2 | 1000024049 | 30.06.2027 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STRCY-STCYR | 7400 | 86822 | 8185
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Overhaul Accumulator Brake LHF | 2027-06-30 | 2027-06-30 | 8 hrs | FY27 | 11 | 90002378 | B1 | 1000025752 | 30.06.2027 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BACCM-FRLFT | 7400 | 86767 | 17344
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Overhaul Accumulator Brake RHF | 2027-06-30 | 2027-06-30 | 8 hrs | FY27 | 11 | 90002378 | B1 | 1000025753 | 30.06.2027 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BACCM-FRRGT | 7400 | 86767 | 17344
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Overhaul Accumulator Brake Rear | 2027-06-30 | 2027-06-30 | 8 hrs | FY27 | 11 | 90002378 | B1 | 1000025754 | 30.06.2027 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BACCM-BACCR | 7400 | 86767 | 17344
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Replace Trans TCon System Hoses | 2027-06-30 | 2027-07-01 | 20 hrs | FY27 | 20 | 90010099 | B1 | 1000090115 | 30.06.2027 | 18000 | CCK-MP-HAUL-DT136 -TRNSYS-TRANS-TRNHO | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Replace Hoses Differential System | 2027-06-30 | 2027-06-30 | 5 hrs | FY27 | 5 | 90010101 | B1 | 1000090116 | 30.06.2027 | 18000 | CCK-MP-HAUL-DT136 -FDRSYS-DIFFL-DIFHO | 7400 | 87780 | 11471
| Onsite PM | Haul | Fortescue |  | FY28 - HAUL - COMPONENTS DURING PM | 2027-07-01 | 2028-06-30 |  | FY28
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Replace Operator Cabin Dash Bulbs | 2027-07-01 | 2027-07-01 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158239 | 01.07.2027 | 3000 | CCK-MP-HAUL-DT774 -STRUCT-CABIN | 6800 | 81047 | 28490
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Transmisson Calibration | 2027-07-01 | 2027-07-01 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298724 | 01.07.2027 | 4500 | CCK-MP-HAUL-DT140 -TRNSYS-TRANS | 7400 | 86767 | 6817
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Cyl Steering RH | 2027-07-02 | 2027-07-02 | 10 hrs | FY28 | 15 | 90011351 | B1 | 1000094922 | 02.07.2027 | 15000 | CCK-MP-HAUL-DT763 -STRSYS-STRCY-STCYR | 6800 | 74143 | 9025
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Engine Midlife Complete | 2027-07-02 | 2027-07-03 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000156050 | 02.07.2027 | 12000 | CCK-MP-HAUL-DT155 -ENGINE | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Radiator Fan Hoses | 2027-07-02 | 2027-07-02 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307537 | 02.07.2027 | 12000 | CCK-MP-HAUL-DT155 -ENGINE-COSYS-RADTR | 7400 | 81407 | 30632
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Motor Lube Axle Hoses | 2027-07-02 | 2027-07-02 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000272026 | 02.07.2027 | 12000 | CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYM01 | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl AOC Fan Motor Rear | 2027-07-02 | 2027-07-02 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000026739 | 02.07.2027 | 12000 | CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYM02 | 7400 | 81407 | 5297
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Cyl Steering RH | 2027-07-03 | 2027-07-03 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000094445 | 03.07.2027 | 15000 | CCK-MP-HAUL-DT754 -STRSYS-STRCY-STCYR | 6800 | 83256 | 8841
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Transmission Calibration | 2027-07-04 | 2027-07-04 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298905 | 04.07.2027 | 4500 | CCK-MP-SUPP-PM0001-TRNSYS-TRANS | 3400 | 48287 | 4072
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Steering Bell Crank & Links | 2027-07-04 | 2027-07-05 | 20 hrs | FY28 | 36 | 90028566 | B1 | 1000317664 | 04.07.2027 | 30000 | CCK-MP-HAUL-DT5255-STRSYS-STLTR-STLAC | 7400 | 87580 | 22547
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Transmisson Calibration | 2027-07-04 | 2027-07-04 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298666 | 04.07.2027 | 4500 | CCK-MP-HAUL-DT058 -TRNSYS-TRANS | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Service Air Conditioner 12M | 2027-07-05 | 2027-07-06 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174168 | 05.07.2027 | 12 Monthly | CCK-MP-HAUL-DT135 -STRUCT-CABIN-AIRCN | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl AOC Fan Motor Rear | 2027-07-05 | 2027-07-05 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024353 | 05.07.2027 | 12000 | CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYM02 | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Front Wheel Bearings RH | 2027-07-07 | 2027-07-08 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157250 | 07.07.2027 | 16000 | CCK-MP-HAUL-DT149 -STRUCT-AXLES-FWBRH | 7400 | 86975 | 9207
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Hoist & Rear Brake Pump | 2027-07-08 | 2027-07-08 | 7 hrs | FY28 | 7 | 90004008 | B2 | 1000079210 | 08.07.2027 | 20000 | CCK-MP-SUPP-WC3111-HYDSYS-HOPMP | 5600 | 51257 | 14617
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Pressure Reducing Valve | 2027-07-08 | 2027-07-08 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204844 | 08.07.2027 | 12000 | CCK-MP-HAUL-DT772 -BRKSYS-BRVLV-VVPRV | 6800 | 85256 | 10385
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl PTO Uni's | 2027-07-09 | 2027-07-09 | 4 hrs | FY28 | 4 | 90031093 | B1 | 1000307813 | 09.07.2027 | 5000 | CCK-MP-SUPP-WC3111-ENGINE-PMPDR-DRSHT | 5600 | 51257 | 9904
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl TC-Park Brake-Scavenge Pump | 2027-07-09 | 2027-07-09 | 6 hrs | FY28 | 6 | 90003990 | B2 | 1000079196 | 09.07.2027 | 20000 | CCK-MP-SUPP-WC3111-TRNSYS-TRPMP-TCCPP | 5600 | 51257 | 14617
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Operator Cabin Dash Bulbs | 2027-07-09 | 2027-07-09 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158237 | 09.07.2027 | 3000 | CCK-MP-HAUL-DT772 -STRUCT-CABIN | 6800 | 85256 | 10385
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Wheel Group Front RH | 2027-07-09 | 2027-07-10 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157221 | 09.07.2027 | 24000 | CCK-MP-HAUL-DT099 -STRUCT-AXLES-HUBRH | 7400 | 87442 | 17201
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Wheel Group Front LH | 2027-07-11 | 2027-07-12 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157127 | 11.07.2027 | 24000 | CCK-MP-HAUL-DT095 -STRUCT-AXLES-HUBLH | 7400 | 88921 | 17105
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Replace Operator Cabin Dash Bulbs | 2027-07-13 | 2027-07-13 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158219 | 13.07.2027 | 3000 | CCK-MP-HAUL-DT754 -STRUCT-CABIN | 6800 | 83256 | 83256
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Transmisson Calibration | 2027-07-13 | 2027-07-13 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298739 | 13.07.2027 | 4500 | CCK-MP-HAUL-DT161 -TRNSYS-TRANS | 7400 | 80609 | 12241
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Torque Converter | 2027-07-13 | 2027-07-14 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000026137 | 13.07.2027 | 24000 | CCK-MP-HAUL-DT146 -TRNSYS-TRQUE | 7400 | 83062 | 16890
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Transmisson Calibration | 2027-07-13 | 2027-07-13 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298737 | 13.07.2027 | 4500 | CCK-MP-HAUL-DT159 -TRNSYS-TRANS | 7400 | 90235 | 15586
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Steering Brake Pump Compensator | 2027-07-14 | 2027-07-14 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204756 | 14.07.2027 | 6000 | CCK-MP-HAUL-DT752 -STRSYS-STPMP | 6800 | 80681 | 13250
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Spider Trans Driveshaft | 2027-07-14 | 2027-07-14 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000155235 | 14.07.2027 | 6000 | CCK-MP-HAUL-DT5255-FDRSYS-DRSHT-UNVSL | 7400 | 87580 | 10729
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Transmisson Calibration | 2027-07-14 | 2027-07-14 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298729 | 14.07.2027 | 4500 | CCK-MP-HAUL-DT148 -TRNSYS-TRANS | 7400 | 85451 | 10451
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Operator Cabin Dash Bulbs | 2027-07-15 | 2027-07-15 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158234 | 15.07.2027 | 3000 | CCK-MP-HAUL-DT769 -STRUCT-CABIN | 6800 | 80508 | 80508
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Transmisson Calibration | 2027-07-16 | 2027-07-16 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298662 | 16.07.2027 | 4500 | CCK-MP-HAUL-DT054 -TRNSYS-TRANS | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Service Air Conditioner 12M | 2027-07-16 | 2027-07-17 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174195 | 16.07.2027 | 12 Monthly | CCK-MP-HAUL-DT5318-STRUCT-CABIN-AIRCN | 7400 | 45240 | 9085
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Engine Midlife Complete | 2027-07-16 | 2027-07-17 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155960 | 16.07.2027 | 12000 | CCK-MP-HAUL-DT127 -ENGINE | 7400 | 83059 | 27545
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Replace Operator Cabin Dash Bulbs | 2027-07-17 | 2027-07-17 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158231 | 17.07.2027 | 3000 | CCK-MP-HAUL-DT766 -STRUCT-CABIN | 6800 | 78074 | 10283
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Pump Hoist | 2027-07-17 | 2027-07-17 | 11.5 hrs | FY28 | 12 | 90011355 | B1 | 1000094343 | 17.07.2027 | 25000 | CCK-MP-HAUL-DT752 -HYDSYS-HOPMP | 6800 | 80681 | 18693
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Brake Slack Adjuster Front | 2027-07-17 | 2027-07-17 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026218 | 17.07.2027 | 20000 | CCK-MP-HAUL-DT147 -BRKSYS-SLACK-SLACF | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Brake Slack Adjuster Rear | 2027-07-17 | 2027-07-17 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026219 | 17.07.2027 | 20000 | CCK-MP-HAUL-DT147 -BRKSYS-SLACK-SLACR | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Steering Bell Crank & Links | 2027-07-17 | 2027-07-18 | 20 hrs | FY28 | 36 | 90028566 | B1 | 1000317646 | 17.07.2027 | 30000 | CCK-MP-HAUL-DT157 -STRSYS-STLTR-STLAC | 7400 | 82954 | 22902
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Spiders Pump Drive Shaft | 2027-07-18 | 2027-07-18 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000026925 | 18.07.2027 | 18000 | CCK-MP-HAUL-DT158 -ENGINE-PMPDR-DRSHT | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Transmission | 2027-07-18 | 2027-07-19 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272355 | 18.07.2027 | 18000 | CCK-MP-HAUL-DT158 -TRNSYS-TRANS | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Transmission Oil Cooler | 2027-07-18 | 2027-07-18 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000091534 | 18.07.2027 | 18000 | CCK-MP-HAUL-DT158 -TRNSYS-TROLC | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Drive Shaft Transmission | 2027-07-18 | 2027-07-18 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154989 | 18.07.2027 | 18000 | CCK-MP-HAUL-DT158 -FDRSYS-DRSHT | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Differential | 2027-07-18 | 2027-07-19 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000026933 | 18.07.2027 | 18000 | CCK-MP-HAUL-DT158 -FDRSYS-DIFFL | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Replace Hoses Differential System | 2027-07-18 | 2027-07-18 | 5 hrs | FY28 | 5 | 90010101 | B2 | 1000091554 | 18.07.2027 | 18000 | CCK-MP-HAUL-DT158 -FDRSYS-DIFFL-DIFHO | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Motor Lube Axle Hoses | 2027-07-18 | 2027-07-18 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000272042 | 18.07.2027 | 12000 | CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYM01 | 7400 | 54920 | 29074
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Brake Slack Adjuster Front | 2027-07-19 | 2027-07-19 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026152 | 19.07.2027 | 20000 | CCK-MP-HAUL-DT146 -BRKSYS-SLACK-SLACF | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Brake Slack Adjuster Rear | 2027-07-19 | 2027-07-19 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026153 | 19.07.2027 | 20000 | CCK-MP-HAUL-DT146 -BRKSYS-SLACK-SLACR | 7400 | 83108 | 12458
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Steering Brake Pump Compensator | 2027-07-20 | 2027-07-20 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204760 | 20.07.2027 | 6000 | CCK-MP-HAUL-DT756 -STRSYS-STPMP | 6800 | 78754 | 308
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Transmisson Calibration | 2027-07-20 | 2027-07-20 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298672 | 20.07.2027 | 4500 | CCK-MP-HAUL-DT094 -TRNSYS-TRANS | 7400 | 88788 | 5404
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Transmisson Calibration | 2027-07-20 | 2027-07-20 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298731 | 20.07.2027 | 4500 | CCK-MP-HAUL-DT150 -TRNSYS-TRANS | 7400 | 86608 | 14649
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Tyre Sense Battery | 2027-07-21 | 2027-07-21 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153178 | 21.07.2027 | 24 Monthly | CCK-MP-HAUL-DT753 -MANGMT-TYRSN
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Pump Brake Charge & Cooling | 2027-07-21 | 2027-07-21 | 6 hrs | FY28 | 6 | 90037883 | B1 | 1000379672 | 21.07.2027 | 9000 | CCK-MP-SUPP-SV221 -BRKSYS-BRPMP | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Engine Midlife complete | 2027-07-21 | 2027-07-23 | 58 hrs | FY28 | 70 | 90015646 | B1 | 1000269903 | 21.07.2027 | 9000 | CCK-MP-SUPP-SV221 -ENGINE | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Adjust Engine Valve Set | 2027-07-21 | 2027-07-21 | 12 hrs | FY28 | 24 | 90015645 | B1 | 1000269779 | 21.07.2027 | 4500 | CCK-MP-SUPP-SV221 -ENGINE | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Overhaul Airconditioner | 2027-07-21 | 2027-07-22 | 24 hrs | FY28 | 24 | 90011566 | B2 | 1000269901 | 21.07.2027 | 9000 | CCK-MP-SUPP-SV221 -STRUCT-CABIN-AIRCN | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Pump Hoist & Brake | 2027-07-21 | 2027-07-21 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000026229 | 21.07.2027 | 24000 | CCK-MP-HAUL-DT147 -HYDSYS-HOPMP | 7400 | 84708 | 16832
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Spiders Pump Drive Shaft | 2027-07-21 | 2027-07-21 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000023773 | 21.07.2027 | 18000 | CCK-MP-HAUL-DT057 -ENGINE-PMPDR-DRSHT | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Transmission | 2027-07-21 | 2027-07-22 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000271873 | 21.07.2027 | 18000 | CCK-MP-HAUL-DT057 -TRNSYS-TRANS | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Differential | 2027-07-21 | 2027-07-22 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000023781 | 21.07.2027 | 18000 | CCK-MP-HAUL-DT057 -FDRSYS-DIFFL | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Replace Hoses Differential System | 2027-07-21 | 2027-07-21 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000081857 | 21.07.2027 | 18000 | CCK-MP-HAUL-DT057 -FDRSYS-DIFFL-DIFHO | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Replace Trans TCon System Hoses | 2027-07-21 | 2027-07-22 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000081851 | 21.07.2027 | 18000 | CCK-MP-HAUL-DT057 -TRNSYS-TRANS-TRNHO | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Transmisson Calibration | 2027-07-21 | 2027-07-21 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298677 | 21.07.2027 | 4500 | CCK-MP-HAUL-DT126 -TRNSYS-TRANS | 7400 | 88657 | 2432
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Steering Linkages | 2027-07-21 | 2027-07-21 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317615 | 21.07.2027 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STLTR | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Operators Seat | 2027-07-21 | 2027-07-21 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000025452 | 21.07.2027 | 15000 | CCK-MP-HAUL-DT135 -STRUCT-CABIN-SEATS | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Drive Shaft Transmission | 2027-07-22 | 2027-07-22 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154925 | 22.07.2027 | 18000 | CCK-MP-HAUL-DT057 -FDRSYS-DRSHT | 7400 | 91273 | 10672
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Air Con Service & Overhaul | 2027-07-23 | 2027-07-24 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110630 | 23.07.2027 | 12 Monthly | CCK-MP-HAUL-DT761 -STRUCT-CABIN-AIRCN | 6800 | 78336 | 23274
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Steering Linkages | 2027-07-24 | 2027-07-24 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317613 | 24.07.2027 | 15000 | CCK-MP-HAUL-DT130 -STRSYS-STLTR | 7400 | 85185 | 33489
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Replace Steering System Hoses | 2027-07-24 | 2027-07-26 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000083178 | 24.07.2027 | 15000 | CCK-MP-HAUL-DT130 -STRSYS-STHLF-STRHO | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Steering Hyd Oil Cooler | 2027-07-24 | 2027-07-24 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000106991 | 24.07.2027 | 15000 | CCK-MP-HAUL-DT130 -STRSYS-STOCO | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Brake Slack Adjuster Front | 2027-07-25 | 2027-07-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024927 | 25.07.2027 | 20000 | CCK-MP-HAUL-DT100 -BRKSYS-SLACK-SLACF | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Brake Slack Adjuster Rear | 2027-07-25 | 2027-07-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024928 | 25.07.2027 | 20000 | CCK-MP-HAUL-DT100 -BRKSYS-SLACK-SLACR | 7400 | 87135 | 12861
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Repl Sepura SCC Microphone | 2027-07-25 | 2027-07-25 | 0.5 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289618 | 25.07.2027 | 12 Monthly | CCK-MP-SUPP-WC008 -COMMUN-RADIO
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Hub & Spindle LH | 2027-07-26 | 2027-07-27 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000095465 | 26.07.2027 | 18000 | CCK-MP-HAUL-DT773 -STRUCT-AXLES-HUBLH | 6800 | 75884 | 11261
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 WaterTank Cannon & Spray Sys Insp | 2027-07-27 | 2027-07-27 | 3 hrs | FY28 | 3 | 90036929 | B1 | 1000368898 | 27.07.2027 | 6 Monthly | CCK-MP-SUPP-WC3112-STRUCT-WTANK | 5600 | 30406 | 30406
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Axle Lube Hyd Pump | 2027-07-28 | 2027-07-28 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000083204 | 28.07.2027 | 24000 | CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYPUM | 7400 | 87780 | 16897
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Spiders Trans Drive Shaft | 2027-07-28 | 2027-07-28 | 4 hrs | FY28 | 4 | 90000910 | B2 | 1000033287 | 28.07.2027 | 11000 | CCK-MP-SUPP-WC224 -FDRSYS-DRSHT | 5000 | 71088 | 6229
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Service Suspension Cylinder LHF | 2027-07-28 | 2027-07-28 | 8 hrs | FY28 | 16 | 90009025 | B2 | 1000067699 | 28.07.2027 | 11000 | CCK-MP-SUPP-WC224 -STRUCT-SUSPN-SCYLF | 5000 | 71056 | 6229
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Service Suspension Cylinder RHF | 2027-07-28 | 2027-07-28 | 8 hrs | FY28 | 16 | 90009025 | B2 | 1000067701 | 28.07.2027 | 11000 | CCK-MP-SUPP-WC224 -STRUCT-SUSPN-SCYRF | 5000 | 71056 | 6229
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Torque Converter System Hoses | 2027-07-28 | 2027-07-28 | 8 hrs | FY28 | 8 | 90010494 | B2 | 1000238426 | 28.07.2027 | 11000 | CCK-MP-SUPP-WC224 -TRNSYS-TRQUE-TRQHO | 5000 | 19972 | 6229
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Transmission System Hoses | 2027-07-28 | 2027-07-28 | 4 hrs | FY28 | 4 | 90010493 | B2 | 1000238428 | 28.07.2027 | 11000 | CCK-MP-SUPP-WC224 -TRNSYS-TRANS-TRNHO | 5000 | 19972 | 6229
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Replace Trans TCon System Hoses | 2027-07-29 | 2027-07-30 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090079 | 29.07.2027 | 18000 | CCK-MP-HAUL-DT090 -TRNSYS-TRANS-TRNHO | 7400 | 81670 | 29126
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Cyl Steering LH | 2027-07-31 | 2027-07-31 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000095186 | 31.07.2027 | 15000 | CCK-MP-HAUL-DT768 -STRSYS-STRCY-STCYL | 6800 | 79837 | 8153
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Replace Operator Cabin Dash Bulbs | 2027-07-31 | 2027-07-31 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158217 | 31.07.2027 | 3000 | CCK-MP-HAUL-DT752 -STRUCT-CABIN | 6800 | 80681 | 80681
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Replace Operator Cabin Dash Bulbs | 2027-08-01 | 2027-08-01 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158225 | 01.08.2027 | 3000 | CCK-MP-HAUL-DT760 -STRUCT-CABIN | 6800 | 80390 | 80390
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Service Air Conditioner 12M | 2027-08-01 | 2027-08-02 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174167 | 01.08.2027 | 12 Monthly | CCK-MP-HAUL-DT130 -STRUCT-CABIN-AIRCN | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Tyre Sense Battery | 2027-08-02 | 2027-08-02 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153165 | 02.08.2027 | 24 Monthly | CCK-MP-HAUL-DT155 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Wheel Group Front RH | 2027-08-02 | 2027-08-03 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157211 | 02.08.2027 | 24000 | CCK-MP-HAUL-DT091 -STRUCT-AXLES-HUBRH | 7400 | 83859 | 16663
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Engine Cat C175-16 LMR | 2027-08-03 | 2027-08-06 | 84 hrs | FY28 | 137 | 90018364 | B1 | 1000156105 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-ENGINE | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Radiator Engine Cooling | 2027-08-03 | 2027-08-04 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307518 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-ENGINE-COSYS-RADTR | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Pump Drive | 2027-08-03 | 2027-08-04 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000026000 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-ENGINE-PMPDR | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Torque Converter | 2027-08-03 | 2027-08-04 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000026005 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-TRNSYS-TRQUE | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Motor Lube Axle Rear & Hoses | 2027-08-03 | 2027-08-03 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000272147 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYM01 | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Axle Lube Hyd Pump | 2027-08-03 | 2027-08-03 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000083356 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYPUM | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Overhaul Accumulator Brake LHF | 2027-08-03 | 2027-08-03 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026014 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BACCM-FRLFT | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Overhaul Accumulator Brake RHF | 2027-08-03 | 2027-08-03 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026015 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BACCM-FRRGT | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Overhaul Accumulator Brake Rear | 2027-08-03 | 2027-08-03 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026016 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BACCM-BACCR | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Pump Brake Cooling | 2027-08-03 | 2027-08-03 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000026017 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-HYFPP | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Motor Brake Oil Cooling | 2027-08-03 | 2027-08-03 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000026019 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BROCO-HYMO1 | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Steering HMU | 2027-08-03 | 2027-08-03 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000026023 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-STRSYS-STHMU | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Rear Axle Linkages | 2027-08-03 | 2027-08-05 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000026040 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-STRUCT-CHASS-AXLIK | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Hoses Hoist System | 2027-08-03 | 2027-08-04 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083358 | 03.08.2027 | 24000 | CCK-MP-HAUL-DT5255-HYDSYS-HDHLF-HSTHO | 7400 | 87580 | 16634
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Tyre Sense Battery | 2027-08-04 | 2027-08-04 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153181 | 04.08.2027 | 24 Monthly | CCK-MP-HAUL-DT756 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Transmisson Calibration | 2027-08-04 | 2027-08-04 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298669 | 04.08.2027 | 4500 | CCK-MP-HAUL-DT088 -TRNSYS-TRANS | 7400 | 89037 | 14711
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Replace Operator Cabin Dash Bulbs | 2027-08-05 | 2027-08-05 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158230 | 05.08.2027 | 3000 | CCK-MP-HAUL-DT765 -STRUCT-CABIN | 6800 | 78429 | 78429
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Air Con Service & Overhaul | 2027-08-05 | 2027-08-06 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110643 | 05.08.2027 | 12 Monthly | CCK-MP-HAUL-DT774 -STRUCT-CABIN-AIRCN | 6800 | 81047 | 35545
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Service Air Conditioner 12M | 2027-08-05 | 2027-08-06 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174180 | 05.08.2027 | 12 Monthly | CCK-MP-HAUL-DT151 -STRUCT-CABIN-AIRCN | 7400 | 84253 | 21869
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Drive Shaft Transmission | 2027-08-06 | 2027-08-06 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154955 | 06.08.2027 | 18000 | CCK-MP-HAUL-DT130 -FDRSYS-DRSHT | 7400 | 85185 | 10692
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Pump Brake Cooling | 2027-08-06 | 2027-08-06 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000026149 | 06.08.2027 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-HYFPP | 7400 | 83108 | 16416
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Brake Oil Cooler Front | 2027-08-06 | 2027-08-06 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000091433 | 06.08.2027 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BROCO-BROCF | 7400 | 83108 | 16275
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Brake Oil Cooler Rear | 2027-08-06 | 2027-08-06 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000091432 | 06.08.2027 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BROCO-BROCR | 7400 | 83108 | 16275
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Transmisson Calibration | 2027-08-07 | 2027-08-07 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298670 | 07.08.2027 | 4500 | CCK-MP-HAUL-DT090 -TRNSYS-TRANS | 7400 | 81670 | 5994
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Overhaul Water Tank Module | 2027-08-08 | 2027-08-08 | 1 hr | FY28 | 1 | 90028969 | B1 | 1000288990 | 08.08.2027 | 36000 | CCK-MP-SUPP-WC009 -STRUCT-WTANK | 1500 | 34052 | 34052
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Air Con Service & Overhaul | 2027-08-09 | 2027-08-10 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110612 | 09.08.2027 | 12 Monthly | CCK-MP-HAUL-DT752 -STRUCT-CABIN-AIRCN | 6800 | 80681 | 31412
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Sepura SCC Microphone | 2027-08-09 | 2027-08-09 | 0.5 hrs | FY28 | 0.5 | 90029001 | B1 | 1000289628 | 09.08.2027 | 12 Monthly | CCK-MP-SUPP-WC3111-COMMUN-RADIO | 5600 | 51257 | 51257
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Hyd Pump Steering & Brake | 2027-08-10 | 2027-08-11 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204748 | 10.08.2027 | 12000 | CCK-MP-HAUL-DT768 -STRSYS-STPMP | 6800 | 79837 | 4916
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Replace Operator Cabin Dash Bulbs | 2027-08-10 | 2027-08-10 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158233 | 10.08.2027 | 3000 | CCK-MP-HAUL-DT768 -STRUCT-CABIN | 6800 | 79837 | 18344
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Cyl Steering RH | 2027-08-10 | 2027-08-10 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000094710 | 10.08.2027 | 15000 | CCK-MP-HAUL-DT759 -STRSYS-STRCY-STCYR | 6800 | 79716 | 16193
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Hub & Spindle LH | 2027-08-11 | 2027-08-12 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000094776 | 11.08.2027 | 18000 | CCK-MP-HAUL-DT760 -STRUCT-AXLES-HUBLH | 6800 | 80390 | 11271
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Tyre Sense Battery | 2027-08-12 | 2027-08-12 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153197 | 12.08.2027 | 24 Monthly | CCK-MP-HAUL-DT772 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Transmisson Calibration | 2027-08-12 | 2027-08-12 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298722 | 12.08.2027 | 4500 | CCK-MP-HAUL-DT137 -TRNSYS-TRANS | 7400 | 84196 | 1006
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Spiders Pump Drive Shaft | 2027-08-14 | 2027-08-14 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000024593 | 14.08.2027 | 18000 | CCK-MP-HAUL-DT095 -ENGINE-PMPDR-DRSHT | 7400 | 88921 | 10426
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Differential | 2027-08-14 | 2027-08-15 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000024601 | 14.08.2027 | 18000 | CCK-MP-HAUL-DT095 -FDRSYS-DIFFL | 7400 | 88921 | 10426
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Steering Brake Pump Compensator | 2027-08-15 | 2027-08-15 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204773 | 15.08.2027 | 6000 | CCK-MP-HAUL-DT769 -STRSYS-STPMP | 6800 | 80508 | 15397
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Pump Hoist & Brake | 2027-08-15 | 2027-08-15 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000026757 | 15.08.2027 | 24000 | CCK-MP-HAUL-DT155 -HYDSYS-HOPMP | 7400 | 81407 | 30632
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Torque Converter | 2027-08-15 | 2027-08-16 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000023966 | 15.08.2027 | 24000 | CCK-MP-HAUL-DT082 -TRNSYS-TRQUE | 7400 | 84375 | 16213
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Accumulator Hyd Steering Rear | 2027-08-16 | 2027-08-16 | 7.5 hrs | FY28 | 11.5 | 90011353 | B1 | 1000094818 | 16.08.2027 | 25000 | CCK-MP-HAUL-DT761 -STRSYS-STACC-SACCR | 6800 | 78336 | 18110
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Hyd Pump Steering & Brake | 2027-08-16 | 2027-08-17 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204434 | 16.08.2027 | 12000 | CCK-MP-HAUL-DT754 -STRSYS-STPMP | 6800 | 83256 | 5013
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 250hr Initial Valve Set | 2027-08-16 | 2027-08-16 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156108 | 16.08.2027 | 250 | CCK-MP-HAUL-DT5255-ENGINE | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Radiator Fan Hoses | 2027-08-16 | 2027-08-16 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307533 | 16.08.2027 | 12000 | CCK-MP-HAUL-DT151 -ENGINE-COSYS-RADTR | 7400 | 84301 | 54538
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Operators Seat | 2027-08-16 | 2027-08-16 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000023684 | 16.08.2027 | 15000 | CCK-MP-HAUL-DT055 -STRUCT-CABIN-SEATS | 7400 | 84122 | 7365
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Replace Operator Cabin Dash Bulbs | 2027-08-17 | 2027-08-17 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158228 | 17.08.2027 | 3000 | CCK-MP-HAUL-DT763 -STRUCT-CABIN | 6800 | 74143 | 74143
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Hyd Pump Steering & Brake | 2027-08-17 | 2027-08-18 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204747 | 17.08.2027 | 12000 | CCK-MP-HAUL-DT767 -STRSYS-STPMP | 6800 | 74312 | 4545
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Hub & Spindle LH | 2027-08-17 | 2027-08-18 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000094352 | 17.08.2027 | 18000 | CCK-MP-HAUL-DT752 -STRUCT-AXLES-HUBLH | 6800 | 80681 | 11115
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Hub & Spindle RH | 2027-08-17 | 2027-08-18 | 32 hrs | FY28 | 60 | 90011364 | B1 | 1000094353 | 17.08.2027 | 18000 | CCK-MP-HAUL-DT752 -STRUCT-AXLES-HUBRH | 6800 | 80681 | 11115
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Suspension LHF | 2027-08-17 | 2027-08-19 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000094354 | 17.08.2027 | 18000 | CCK-MP-HAUL-DT752 -STRUCT-SUSPN-SCYLF | 6800 | 80681 | 11115
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Cyl Suspension RHF | 2027-08-17 | 2027-08-19 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000094514 | 17.08.2027 | 18000 | CCK-MP-HAUL-DT755 -STRUCT-SUSPN-SCYRF | 6800 | 84587 | 11052
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Replace Operator Cabin Dash Bulbs | 2027-08-17 | 2027-08-17 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158224 | 17.08.2027 | 3000 | CCK-MP-HAUL-DT759 -STRUCT-CABIN | 6800 | 79716 | 79716
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Steering Brake Pump Compensator | 2027-08-18 | 2027-08-18 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204765 | 18.08.2027 | 6000 | CCK-MP-HAUL-DT761 -STRSYS-STPMP | 6800 | 78336 | 10559
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Replace Operator Cabin Dash Bulbs | 2027-08-18 | 2027-08-18 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158226 | 18.08.2027 | 3000 | CCK-MP-HAUL-DT761 -STRUCT-CABIN | 6800 | 78336 | 19424
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Spiders Pump Drive Shaft | 2027-08-18 | 2027-08-18 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000025544 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT137 -ENGINE-PMPDR-DRSHT | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Transmission Oil Cooler | 2027-08-18 | 2027-08-18 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000083221 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT137 -TRNSYS-TROLC | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Drive Shaft Transmission | 2027-08-18 | 2027-08-18 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154961 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT137 -FDRSYS-DRSHT | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Differential | 2027-08-18 | 2027-08-19 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000025552 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT137 -FDRSYS-DIFFL | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Replace Trans TCon System Hoses | 2027-08-18 | 2027-08-19 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090118 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT137 -TRNSYS-TRANS-TRNHO | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Replace Hoses Differential System | 2027-08-18 | 2027-08-18 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000090119 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT137 -FDRSYS-DIFFL-DIFHO | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Transmission | 2027-08-18 | 2027-08-19 | 22 hrs | FY28 | 39 | 90026996 | B1 | 1000272363 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT221 -TRNSYS-TRANS | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Transmission Oil Cooler | 2027-08-18 | 2027-08-18 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000128000 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT221 -TRNSYS-TROLC | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Replace Trans TCon System Hoses | 2027-08-18 | 2027-08-19 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000091487 | 18.08.2027 | 18000 | CCK-MP-HAUL-DT155 -TRNSYS-TRANS-TRNHO | 7400 | 81407 | 30632
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Front Wheel Bearings RH | 2027-08-18 | 2027-08-19 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157204 | 18.08.2027 | 16000 | CCK-MP-HAUL-DT086 -STRUCT-AXLES-FWBRH | 7400 | 86822 | 8185
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Hub & Spindle LH | 2027-08-19 | 2027-08-20 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000094935 | 19.08.2027 | 18000 | CCK-MP-HAUL-DT763 -STRUCT-AXLES-HUBLH | 6800 | 74143 | 11011
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Hub & Spindle RH | 2027-08-19 | 2027-08-20 | 32 hrs | FY28 | 60 | 90011364 | B1 | 1000094936 | 19.08.2027 | 18000 | CCK-MP-HAUL-DT763 -STRUCT-AXLES-HUBRH | 6800 | 74143 | 11011
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Accumulator Hyd Steer Front | 2027-08-19 | 2027-08-19 | 7.5 hrs | FY28 | 11.5 | 90011352 | B1 | 1000095453 | 19.08.2027 | 25000 | CCK-MP-HAUL-DT773 -STRSYS-STACC-SACCF | 6800 | 75884 | 17843
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Operator Cabin Dash Bulbs | 2027-08-19 | 2027-08-19 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158223 | 19.08.2027 | 3000 | CCK-MP-HAUL-DT758 -STRUCT-CABIN | 6800 | 85895 | 23936
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Transmisson Calibration | 2027-08-19 | 2027-08-19 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298675 | 19.08.2027 | 4500 | CCK-MP-HAUL-DT099 -TRNSYS-TRANS | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Service Air Conditioner 12M | 2027-08-19 | 2027-08-20 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174111 | 19.08.2027 | 12 Monthly | CCK-MP-HAUL-DT056 -STRUCT-CABIN-AIRCN | 7400 | 84421 | 18034
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Motor Lube Axle Rear & Hoses | 2027-08-20 | 2027-08-20 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271983 | 20.08.2027 | 24000 | CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYM01 | 7400 | 88921 | 40108
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Repl Sepura SCC Microphone | 2027-08-21 | 2027-08-21 | 0.5 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289617 | 21.08.2027 | 12 Monthly | CCK-MP-SUPP-SV4104-COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Motor Lube Axle Hoses | 2027-08-21 | 2027-08-21 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000272028 | 21.08.2027 | 12000 | CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYM01 | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl AOC Fan Motor Rear | 2027-08-21 | 2027-08-21 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000026871 | 21.08.2027 | 12000 | CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYM02 | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Spider Trans Driveshaft | 2027-08-21 | 2027-08-21 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154986 | 21.08.2027 | 6000 | CCK-MP-HAUL-DT157 -FDRSYS-DRSHT-UNVSL | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Wheel End LH | 2027-08-21 | 2027-08-22 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000026142 | 21.08.2027 | 24000 | CCK-MP-HAUL-DT146 -FDRSYS-FDRVE-FDRLH | 7400 | 83108 | 16116
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Auto Lube Pump | 2027-08-22 | 2027-08-22 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095461 | 22.08.2027 | 8000 | CCK-MP-HAUL-DT773 -GRSYST-ALBPP | 6800 | 75884 | 15103
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Front Wheel Bearings LH | 2027-08-22 | 2027-08-23 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157190 | 22.08.2027 | 16000 | CCK-MP-HAUL-DT5255-STRUCT-AXLES-FWBLH | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Front Wheel Bearings RH | 2027-08-22 | 2027-08-23 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157278 | 22.08.2027 | 16000 | CCK-MP-HAUL-DT5255-STRUCT-AXLES-FWBRH | 7400 | 87580 | 13477
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Service Air Conditioner 12M | 2027-08-22 | 2027-08-23 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174165 | 22.08.2027 | 12 Monthly | CCK-MP-HAUL-DT126 -STRUCT-CABIN-AIRCN | 7400 | 88657 | 54006
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Transmission Oil Cooler | 2027-08-22 | 2027-08-22 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000082860 | 22.08.2027 | 18000 | CCK-MP-HAUL-DT055 -TRNSYS-TROLC | 7400 | 84122 | 10235
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Wheel End LH | 2027-08-23 | 2027-08-24 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000026934 | 23.08.2027 | 24000 | CCK-MP-HAUL-DT158 -FDRSYS-FDRVE-FDRLH | 7400 | 85964 | 16304
777G WC | Onsite PM | Haul | Fortescue | WC2501 | WC2501 Initial Engine Valve Set | 2027-08-23 | 2027-08-23 | 12 hrs | FY28 | 24 | 90015765 | B1 | 1000136144 | 23.08.2027 | 250 | CCK-MP-SUPP-WC2501-ENGINE | 2000 | 56945 | 15935
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Steering Linkages | 2027-08-23 | 2027-08-23 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317651 | 23.08.2027 | 15000 | CCK-MP-HAUL-DT160 -STRSYS-STLTR | 7400 | 85085 | 32389
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Service Air Conditioner 12M | 2027-08-23 | 2027-08-24 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174187 | 23.08.2027 | 12 Monthly | CCK-MP-HAUL-DT160 -STRUCT-CABIN-AIRCN | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Replace Steering System Hoses | 2027-08-23 | 2027-08-25 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000091570 | 23.08.2027 | 15000 | CCK-MP-HAUL-DT160 -STRSYS-STHLF-STRHO | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Steering Hyd Oil Cooler | 2027-08-23 | 2027-08-23 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107029 | 23.08.2027 | 15000 | CCK-MP-HAUL-DT160 -STRSYS-STOCO | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Tyre Sense Battery | 2027-08-23 | 2027-08-23 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153169 | 23.08.2027 | 24 Monthly | CCK-MP-HAUL-DT160 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Steering Hyd Oil Cooler | 2027-08-23 | 2027-08-23 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000106989 | 23.08.2027 | 15000 | CCK-MP-HAUL-DT127 -STRSYS-STOCO | 7400 | 83059 | 7188
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Transmission Oil Cooler | 2027-08-24 | 2027-08-24 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000083050 | 24.08.2027 | 18000 | CCK-MP-HAUL-DT099 -TRNSYS-TROLC | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Steering LH | 2027-08-24 | 2027-08-24 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000024994 | 24.08.2027 | 15000 | CCK-MP-HAUL-DT126 -STRSYS-STRCY-STCYL | 7400 | 88657 | 7138
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Steering RH | 2027-08-24 | 2027-08-24 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000024995 | 24.08.2027 | 15000 | CCK-MP-HAUL-DT126 -STRSYS-STRCY-STCYR | 7400 | 88657 | 7138
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Pump Drive | 2027-08-24 | 2027-08-25 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000025222 | 24.08.2027 | 24000 | CCK-MP-HAUL-DT130 -ENGINE-PMPDR | 7400 | 85185 | 16330
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Service Air Conditioner 12M | 2027-08-24 | 2027-08-25 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174116 | 24.08.2027 | 12 Monthly | CCK-MP-HAUL-DT088 -STRUCT-CABIN-AIRCN | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Wheel Group Front LH | 2027-08-24 | 2027-08-25 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157157 | 24.08.2027 | 24000 | CCK-MP-HAUL-DT146 -STRUCT-AXLES-HUBLH | 7400 | 83061 | 16107
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Brake Slack Adjuster Front | 2027-08-25 | 2027-08-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025954 | 25.08.2027 | 20000 | CCK-MP-HAUL-DT143 -BRKSYS-SLACK-SLACF | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Brake Slack Adjuster Rear | 2027-08-25 | 2027-08-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025955 | 25.08.2027 | 20000 | CCK-MP-HAUL-DT143 -BRKSYS-SLACK-SLACR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Suspension RHR | 2027-08-25 | 2027-08-26 | 22 hrs | FY28 | 39 | 90002409 | B2 | 1000026972 | 25.08.2027 | 28000 | CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYRR | 7400 | 85964 | 20324
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Auto Lube Pump | 2027-08-26 | 2027-08-26 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095143 | 26.08.2027 | 8000 | CCK-MP-HAUL-DT767 -GRSYST-ALBPP | 6800 | 74312 | 7873
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Air Con Service & Overhaul | 2027-08-26 | 2027-08-27 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110639 | 26.08.2027 | 12 Monthly | CCK-MP-HAUL-DT770 -STRUCT-CABIN-AIRCN | 6800 | 79305 | 24535
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Tyre Sense Battery | 2027-08-27 | 2027-08-27 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153177 | 27.08.2027 | 24 Monthly | CCK-MP-HAUL-DT752 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Service Air Conditioner 12M | 2027-08-27 | 2027-08-28 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174115 | 27.08.2027 | 12 Monthly | CCK-MP-HAUL-DT086 -STRUCT-CABIN-AIRCN | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Service Air Conditioner 12M | 2027-08-27 | 2027-08-28 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174179 | 27.08.2027 | 12 Monthly | CCK-MP-HAUL-DT150 -STRUCT-CABIN-AIRCN | 7400 | 86656 | 49988
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Service Air Conditioner 12M | 2027-08-29 | 2027-08-30 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174166 | 29.08.2027 | 12 Monthly | CCK-MP-HAUL-DT127 -STRUCT-CABIN-AIRCN | 7400 | 83059 | 27545
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Hyd Pump Steering & Brake | 2027-08-30 | 2027-08-31 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204754 | 30.08.2027 | 12000 | CCK-MP-HAUL-DT774 -STRSYS-STPMP | 6800 | 81047 | 4812
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Initial Engine Valve Set | 2027-08-30 | 2027-08-30 | 12 hrs | FY28 | 24 | 90015644 | B1 | 1000269774 | 30.08.2027 | 250 | CCK-MP-SUPP-SV220 -ENGINE | 5100 | 58303 | 11037
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Engine Midlife Complete | 2027-08-31 | 2027-09-01 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000156092 | 31.08.2027 | 12000 | CCK-MP-HAUL-DT222 -ENGINE | 7400 | 55735 | 3987
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Radiator Fan Hoses | 2027-08-31 | 2027-08-31 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307555 | 31.08.2027 | 12000 | CCK-MP-HAUL-DT222 -ENGINE-COSYS-RADTR | 7400 | 55735 | 3987
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Motor Lube Axle Hoses | 2027-08-31 | 2027-08-31 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000272040 | 31.08.2027 | 12000 | CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYM01 | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl AOC Fan Motor Rear | 2027-08-31 | 2027-08-31 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000128037 | 31.08.2027 | 12000 | CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYM02 | 7400 | 55735 | 4006
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Cyl Suspension RHF | 2027-09-01 | 2027-09-03 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000095468 | 01.09.2027 | 18000 | CCK-MP-HAUL-DT773 -STRUCT-SUSPN-SCYRF | 6800 | 75884 | 10573
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Tyre Sense Battery | 2027-09-02 | 2027-09-02 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153162 | 02.09.2027 | 24 Monthly | CCK-MP-HAUL-DT150 -MANGMT-TYRSN
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Adjust Engine Valve Set | 2027-09-03 | 2027-09-03 | 12 hrs | FY28 | 24 | 90015645 | B1 | 1000201197 | 03.09.2027 | 4500 | CCK-MP-SUPP-SV4104-ENGINE | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Service Airconditioner | 2027-09-03 | 2027-09-04 | 24 hrs | FY28 | 24 | 90018538 | B2 | 1000229148 | 03.09.2027 | 4500 | CCK-MP-SUPP-SV4104-STRUCT-CABIN-AIRCN | 5100 | 23504 | 7410
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Spider Trans Driveshaft | 2027-09-05 | 2027-09-05 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154976 | 05.09.2027 | 6000 | CCK-MP-HAUL-DT149 -FDRSYS-DRSHT-UNVSL | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Spider Trans Driveshaft | 2027-09-05 | 2027-09-05 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154940 | 05.09.2027 | 6000 | CCK-MP-HAUL-DT095 -FDRSYS-DRSHT-UNVSL | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Cyl Steering LH | 2027-09-06 | 2027-09-06 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000167013 | 06.09.2027 | 15000 | CCK-MP-HAUL-DT5314-STRSYS-STRCY-STCYL | 7400 | 45898 | 6943
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Spider Trans Driveshaft | 2027-09-06 | 2027-09-06 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154998 | 06.09.2027 | 6000 | CCK-MP-HAUL-DT222 -FDRSYS-DRSHT-UNVSL | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Wheel End LH | 2027-09-06 | 2027-09-07 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000027066 | 06.09.2027 | 24000 | CCK-MP-HAUL-DT160 -FDRSYS-FDRVE-FDRLH | 7400 | 85085 | 15924
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Overhaul Valve Control Brake | 2027-09-06 | 2027-09-07 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000023853 | 06.09.2027 | 24000 | CCK-MP-HAUL-DT058 -BRKSYS-BRVLV | 7400 | 87864 | 15676
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Hyd Pump Steering Main & Fan | 2027-09-06 | 2027-09-06 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000023857 | 06.09.2027 | 24000 | CCK-MP-HAUL-DT058 -STRSYS-STPMP | 7400 | 87864 | 15676
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Torque Converter | 2027-09-07 | 2027-09-08 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000026467 | 07.09.2027 | 24000 | CCK-MP-HAUL-DT151 -TRNSYS-TRQUE | 7400 | 84253 | 15853
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Auto Lube Pump | 2027-09-08 | 2027-09-08 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285780 | 08.09.2027 | 8000 | CCK-MP-HAUL-DT135 -GRSYST-ALBPP | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Radiator Engine Cooling | 2027-09-08 | 2027-09-09 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307486 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -ENGINE-COSYS-RADTR | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Pump Drive | 2027-09-08 | 2027-09-09 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000024529 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -ENGINE-PMPDR | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Torque Converter | 2027-09-08 | 2027-09-09 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000024534 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -TRNSYS-TRQUE | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Wheel End LH | 2027-09-08 | 2027-09-09 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000024539 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -FDRSYS-FDRVE-FDRLH | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Wheel End RH | 2027-09-08 | 2027-09-09 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000024540 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -FDRSYS-FDRVE-FDRRH | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Axle Lube Hyd Pump | 2027-09-08 | 2027-09-08 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000082976 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-HYPUM | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Overhaul Accumulator Brake LHF | 2027-09-08 | 2027-09-08 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024543 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-BACCM-FRLFT | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Overhaul Accumulator Brake RHF | 2027-09-08 | 2027-09-08 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024544 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-BACCM-FRRGT | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Overhaul Accumulator Brake Rear | 2027-09-08 | 2027-09-08 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024545 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-BACCM-BACCR | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Pump Brake Cooling | 2027-09-08 | 2027-09-08 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000024546 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-HYFPP | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Overhaul Valve Control Brake | 2027-09-08 | 2027-09-09 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000024547 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-BRVLV | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Motor Brake Oil Cooling | 2027-09-08 | 2027-09-08 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000024548 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-BROCO-HYMO1 | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Hyd Pump Steering Main & Fan | 2027-09-08 | 2027-09-08 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000024551 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -STRSYS-STPMP | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Ovhl Accumulator Steering Front | 2027-09-08 | 2027-09-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024555 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -STRSYS-STACC-SACCF | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Ovhl Accumulator Steering Middle | 2027-09-08 | 2027-09-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024556 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -STRSYS-STACC-SACCM | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Ovhl Accumulator Steering Rear | 2027-09-08 | 2027-09-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024557 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -STRSYS-STACC-SACCR | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Pump Hoist & Brake | 2027-09-08 | 2027-09-08 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000024559 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -HYDSYS-HOPMP | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Rear Axle Linkages | 2027-09-08 | 2027-09-10 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000024568 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -STRUCT-CHASS-AXLIK | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Wheel Group Front RH | 2027-09-08 | 2027-09-09 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157213 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -STRUCT-AXLES-HUBRH | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Drive Line Axle LH | 2027-09-08 | 2027-09-08 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124573 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -FDRSYS-DRLAX-AXLLH | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Drive Line Axle RH | 2027-09-08 | 2027-09-08 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124574 | 08.09.2027 | 24000 | CCK-MP-HAUL-DT094 -FDRSYS-DRLAX-AXLRH | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Spider Trans Driveshaft | 2027-09-08 | 2027-09-08 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154938 | 08.09.2027 | 6000 | CCK-MP-HAUL-DT094 -FDRSYS-DRSHT-UNVSL | 7400 | 88788 | 3009
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Transmisson Calibration | 2027-09-08 | 2027-09-08 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298668 | 08.09.2027 | 4500 | CCK-MP-HAUL-DT086 -TRNSYS-TRANS | 7400 | 86822 | 14283
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Wheel Motor Oil LH | 2027-09-09 | 2027-09-09 | 1 hr | FY28 | 1 | 90033606 | B1 | 1000338202 | 09.09.2027 | 25000 | CCK-MP-HAUL-DT753 -FDRSYS-WLMTR-WHMLH | 6800 | 85999 | 17631
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Wheel Motor LH | 2027-09-09 | 2027-09-11 | 45.5 hrs | FY28 | 83.5 | 90011335 | B1 | 1000094380 | 09.09.2027 | 25000 | CCK-MP-HAUL-DT753 -FDRSYS-WLMTR-WHMLH | 6800 | 85999 | 17631
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Axle Lube Hyd Pump | 2027-09-09 | 2027-09-09 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000082501 | 09.09.2027 | 24000 | CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYPUM | 7400 | 91273 | 15567
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Brake Oil Cooler Rear | 2027-09-09 | 2027-09-09 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000082507 | 09.09.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BROCO-BROCR | 7400 | 91273 | 15565
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl AOC Fan Motor Rear | 2027-09-09 | 2027-09-09 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000026013 | 09.09.2027 | 12000 | CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYM02 | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Service Air Conditioner 12M | 2027-09-09 | 2027-09-10 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174119 | 09.09.2027 | 12 Monthly | CCK-MP-HAUL-DT094 -STRUCT-CABIN-AIRCN | 7400 | 88788 | 50851
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Replace Steering System Hoses | 2027-09-09 | 2027-09-11 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000083007 | 09.09.2027 | 15000 | CCK-MP-HAUL-DT095 -STRSYS-STHLF-STRHO | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Pump Drive | 2027-09-09 | 2027-09-10 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000023835 | 09.09.2027 | 24000 | CCK-MP-HAUL-DT058 -ENGINE-PMPDR | 7400 | 87864 | 15616
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Wheel End RH | 2027-09-09 | 2027-09-10 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000023846 | 09.09.2027 | 24000 | CCK-MP-HAUL-DT058 -FDRSYS-FDRVE-FDRRH | 7400 | 87864 | 15616
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Overhaul Accumulator Brake LHF | 2027-09-09 | 2027-09-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023849 | 09.09.2027 | 24000 | CCK-MP-HAUL-DT058 -BRKSYS-BACCM-FRLFT | 7400 | 87864 | 15616
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Overhaul Accumulator Brake RHF | 2027-09-09 | 2027-09-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023850 | 09.09.2027 | 24000 | CCK-MP-HAUL-DT058 -BRKSYS-BACCM-FRRGT | 7400 | 87864 | 15616
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Rear Axle Linkages | 2027-09-09 | 2027-09-11 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000023874 | 09.09.2027 | 24000 | CCK-MP-HAUL-DT058 -STRUCT-CHASS-AXLIK | 7400 | 87864 | 15616
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Steering Brake Pump Compensator | 2027-09-10 | 2027-09-10 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204768 | 10.09.2027 | 6000 | CCK-MP-HAUL-DT764 -STRSYS-STPMP | 6800 | 75315 | 9695
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Spider Trans Driveshaft | 2027-09-10 | 2027-09-10 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154942 | 10.09.2027 | 6000 | CCK-MP-HAUL-DT097 -FDRSYS-DRSHT-UNVSL | 7400 | 83804 | 3219
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Auto Lube Pump | 2027-09-11 | 2027-09-11 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285639 | 11.09.2027 | 8000 | CCK-MP-HAUL-DT130 -GRSYST-ALBPP | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Front Wheel Bearings LH | 2027-09-11 | 2027-09-12 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157140 | 11.09.2027 | 16000 | CCK-MP-HAUL-DT130 -STRUCT-AXLES-FWBLH | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Wheel End RH | 2027-09-11 | 2027-09-12 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000026143 | 11.09.2027 | 24000 | CCK-MP-HAUL-DT146 -FDRSYS-FDRVE-FDRRH | 7400 | 83108 | 15678
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Cyl Steering LH | 2027-09-12 | 2027-09-12 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000094921 | 12.09.2027 | 15000 | CCK-MP-HAUL-DT763 -STRSYS-STRCY-STCYL | 6800 | 74143 | 7576
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Steering Brake Pump Compensator | 2027-09-12 | 2027-09-12 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204777 | 12.09.2027 | 6000 | CCK-MP-HAUL-DT773 -STRSYS-STPMP | 6800 | 75884 | 10573
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Service Air Conditioner 12M | 2027-09-12 | 2027-09-13 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000172996 | 12.09.2027 | 12 Monthly | CCK-MP-HAUL-DT5316-STRUCT-CABIN-AIRCN | 7400 | 45108 | 45108
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Axle Lube Hyd Pump | 2027-09-12 | 2027-09-12 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000082520 | 12.09.2027 | 24000 | CCK-MP-HAUL-DT058 -FDRSYS-AXLEC-HYPUM | 7400 | 87864 | 15544
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Ovhl Accumulator Steering Front | 2027-09-12 | 2027-09-12 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023861 | 12.09.2027 | 24000 | CCK-MP-HAUL-DT058 -STRSYS-STACC-SACCF | 7400 | 87864 | 15544
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Ovhl Accumulator Steering Middle | 2027-09-12 | 2027-09-12 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023862 | 12.09.2027 | 24000 | CCK-MP-HAUL-DT058 -STRSYS-STACC-SACCM | 7400 | 87864 | 15544
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Ovhl Accumulator Steering Rear | 2027-09-12 | 2027-09-12 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023863 | 12.09.2027 | 24000 | CCK-MP-HAUL-DT058 -STRSYS-STACC-SACCR | 7400 | 87864 | 15544
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Suspension RHF | 2027-09-13 | 2027-09-15 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067575 | 13.09.2027 | 28000 | CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYRF | 7400 | 88225 | 15547
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Brake Slack Adjuster Front | 2027-09-13 | 2027-09-13 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024738 | 13.09.2027 | 20000 | CCK-MP-HAUL-DT097 -BRKSYS-SLACK-SLACF | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Brake Slack Adjuster Rear | 2027-09-13 | 2027-09-13 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024739 | 13.09.2027 | 20000 | CCK-MP-HAUL-DT097 -BRKSYS-SLACK-SLACR | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Steering Linkages | 2027-09-13 | 2027-09-13 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317623 | 13.09.2027 | 15000 | CCK-MP-HAUL-DT140 -STRSYS-STLTR | 7400 | 86767 | 27334
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Service Air Conditioner 12M | 2027-09-13 | 2027-09-14 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174172 | 13.09.2027 | 12 Monthly | CCK-MP-HAUL-DT140 -STRUCT-CABIN-AIRCN | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Operators Seat | 2027-09-13 | 2027-09-13 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000025776 | 13.09.2027 | 15000 | CCK-MP-HAUL-DT140 -STRUCT-CABIN-SEATS | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Replace Steering System Hoses | 2027-09-13 | 2027-09-15 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000083292 | 13.09.2027 | 15000 | CCK-MP-HAUL-DT140 -STRSYS-STHLF-STRHO | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Steering Hyd Oil Cooler | 2027-09-13 | 2027-09-13 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000106998 | 13.09.2027 | 15000 | CCK-MP-HAUL-DT140 -STRSYS-STOCO | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Tyre Sense Battery | 2027-09-13 | 2027-09-13 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153155 | 13.09.2027 | 24 Monthly | CCK-MP-HAUL-DT140 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Cyl Steering LH | 2027-09-14 | 2027-09-14 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000095133 | 14.09.2027 | 15000 | CCK-MP-HAUL-DT767 -STRSYS-STRCY-STCYL | 6800 | 74312 | 7082
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Overhaul Accumulator Brake LHF | 2027-09-14 | 2027-09-14 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023786 | 14.09.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BACCM-FRLFT | 7400 | 91273 | 42405
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Overhaul Accumulator Brake RHF | 2027-09-14 | 2027-09-14 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023787 | 14.09.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BACCM-FRRGT | 7400 | 91273 | 42405
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Overhaul Accumulator Brake Rear | 2027-09-14 | 2027-09-14 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023788 | 14.09.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BACCM-BACCR | 7400 | 91273 | 42405
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Motor Brake Oil Cooling | 2027-09-14 | 2027-09-14 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000023791 | 14.09.2027 | 24000 | CCK-MP-HAUL-DT057 -BRKSYS-BROCO-HYMO1 | 7400 | 91273 | 15567
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Steering HMU | 2027-09-14 | 2027-09-14 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000023795 | 14.09.2027 | 24000 | CCK-MP-HAUL-DT057 -STRSYS-STHMU | 7400 | 91273 | 15565
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Transmisson Calibration | 2027-09-14 | 2027-09-14 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298734 | 14.09.2027 | 4500 | CCK-MP-HAUL-DT155 -TRNSYS-TRANS | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Replace Trans TCon System Hoses | 2027-09-16 | 2027-09-17 | 20 hrs | FY28 | 20 | 90010099 | B2 | 1000128135 | 16.09.2027 | 18000 | CCK-MP-HAUL-DT223 -TRNSYS-TRANS-TRNHO | 7400 | 54920 | 29074
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Repl Sepura SCC Microphone | 2027-09-16 | 2027-09-16 | 0.5 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289620 | 16.09.2027 | 12 Monthly | CCK-MP-SUPP-WC220 -COMMUN-RADIO
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Cyl Suspension RHF | 2027-09-17 | 2027-09-19 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000094567 | 17.09.2027 | 18000 | CCK-MP-HAUL-DT756 -STRUCT-SUSPN-SCYRF | 6800 | 78754 | 10095
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Operator Cabin Dash Bulbs | 2027-09-17 | 2027-09-17 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158220 | 17.09.2027 | 3000 | CCK-MP-HAUL-DT755 -STRUCT-CABIN | 6800 | 84587 | 84587
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Sepura SCC Microphone | 2027-09-17 | 2027-09-17 | 0.5 hrs | FY28 | 0.5 | 90029002 | B1 | 1000289635 | 17.09.2027 | 12 Monthly | CCK-MP-SUPP-WC224 -COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Transmisson Calibration | 2027-09-17 | 2027-09-17 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298671 | 17.09.2027 | 4500 | CCK-MP-HAUL-DT091 -TRNSYS-TRANS | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Spiders Pump Drive Shaft | 2027-09-18 | 2027-09-18 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000166994 | 18.09.2027 | 18000 | CCK-MP-HAUL-DT5314-ENGINE-PMPDR-DRSHT | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Transmission Oil Cooler | 2027-09-18 | 2027-09-18 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000167028 | 18.09.2027 | 18000 | CCK-MP-HAUL-DT5314-TRNSYS-TROLC | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Differential | 2027-09-18 | 2027-09-19 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000166999 | 18.09.2027 | 18000 | CCK-MP-HAUL-DT5314-FDRSYS-DIFFL | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Replace Hoses Differential System | 2027-09-18 | 2027-09-18 | 5 hrs | FY28 | 5 | 90010101 | B3 | 1000167038 | 18.09.2027 | 18000 | CCK-MP-HAUL-DT5314-FDRSYS-DIFFL-DIFHO | 7400 | 45898 | 22018
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Auto Lube Pump | 2027-09-18 | 2027-09-18 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285808 | 18.09.2027 | 8000 | CCK-MP-HAUL-DT5316-GRSYST-ALBPP | 7400 | 45108 | 45108
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Grid Box Blower Motor RH | 2027-09-19 | 2027-09-19 | 10 hrs | FY28 | 10 | 90011332 | B1 | 1000094589 | 19.09.2027 | 25000 | CCK-MP-HAUL-DT757 -ELCTHV-HVGBM-GBMRH | 6800 | 80700 | 17501
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Transmisson Calibration | 2027-09-20 | 2027-09-20 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298676 | 20.09.2027 | 4500 | CCK-MP-HAUL-DT100 -TRNSYS-TRANS | 7400 | 87135 | 5195
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Engine Midlife Complete | 2027-09-20 | 2027-09-21 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155930 | 20.09.2027 | 12000 | CCK-MP-HAUL-DT095 -ENGINE | 7400 | 88921 | 28299
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Cyl Hoist LH | 2027-09-22 | 2027-09-22 | 17 hrs | FY28 | 33 | 90011357 | B1 | 1000095193 | 22.09.2027 | 25000 | CCK-MP-HAUL-DT768 -HYDSYS-HOCYL-HCYLL | 6800 | 79837 | 16968
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Torque Converter | 2027-09-23 | 2027-09-24 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000025548 | 23.09.2027 | 24000 | CCK-MP-HAUL-DT137 -TRNSYS-TRQUE | 7400 | 84196 | 15059
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Engine Midlife Complete | 2027-09-23 | 2027-09-24 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000156098 | 23.09.2027 | 12000 | CCK-MP-HAUL-DT223 -ENGINE | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Radiator Fan Hoses | 2027-09-23 | 2027-09-23 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307557 | 23.09.2027 | 12000 | CCK-MP-HAUL-DT223 -ENGINE-COSYS-RADTR | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Spiders Pump Drive Shaft | 2027-09-23 | 2027-09-23 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000026463 | 23.09.2027 | 18000 | CCK-MP-HAUL-DT151 -ENGINE-PMPDR-DRSHT | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Transmission | 2027-09-23 | 2027-09-24 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272347 | 23.09.2027 | 18000 | CCK-MP-HAUL-DT151 -TRNSYS-TRANS | 7400 | 84253 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Differential | 2027-09-23 | 2027-09-24 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000026471 | 23.09.2027 | 18000 | CCK-MP-HAUL-DT151 -FDRSYS-DIFFL | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Replace Hoses Differential System | 2027-09-23 | 2027-09-23 | 5 hrs | FY28 | 5 | 90010101 | B2 | 1000090155 | 23.09.2027 | 18000 | CCK-MP-HAUL-DT151 -FDRSYS-DIFFL-DIFHO | 7400 | 84253 | 28267
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Pump Brake Cooling | 2027-09-23 | 2027-09-23 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000023726 | 23.09.2027 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-HYFPP | 7400 | 84421 | 15542
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Replace Hoses Differential System | 2027-09-24 | 2027-09-24 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000090025 | 24.09.2027 | 18000 | CCK-MP-HAUL-DT127 -FDRSYS-DIFFL-DIFHO | 7400 | 83059 | 27545
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Replace Trans TCon System Hoses | 2027-09-24 | 2027-09-25 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090026 | 24.09.2027 | 18000 | CCK-MP-HAUL-DT127 -TRNSYS-TRANS-TRNHO | 7400 | 83059 | 27545
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Air Con Service & Overhaul | 2027-09-25 | 2027-09-26 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110640 | 25.09.2027 | 12 Monthly | CCK-MP-HAUL-DT771 -STRUCT-CABIN-AIRCN | 6800 | 84423 | 84423
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Water Cannon Maintenance | 2027-09-25 | 2027-09-25 | 3 hrs | FY28 | 3 | 90001682 | B1 | 1000018408 | 25.09.2027 | 6 Monthly | CCK-MP-SUPP-WC008 -STRUCT-WTANK-SPRAY | 3500 | 51417 | 5947
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Sepura SCC Microphone | 2027-09-26 | 2027-09-26 | 0.5 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289612 | 26.09.2027 | 12 Monthly | CCK-MP-SUPP-SV221 -COMMUN-RADIO | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Bulk Grease Tank Breather | 2027-09-26 | 2027-09-26 | 1 hr | FY28 | 1 | 90022533 | B1 | 1000236910 | 26.09.2027 | 6 Monthly | CCK-MP-SUPP-SV221 -GRSYST-GRTNK | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Wheel End LH | 2027-09-27 | 2027-09-28 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000023593 | 27.09.2027 | 24000 | CCK-MP-HAUL-DT054 -FDRSYS-FDRVE-FDRLH | 7400 | 88111 | 15701
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Auto Lube Pump | 2027-09-27 | 2027-09-27 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094825 | 27.09.2027 | 8000 | CCK-MP-HAUL-DT761 -GRSYST-ALBPP | 6800 | 78264 | 24911
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Pressure Reducing Valve | 2027-09-27 | 2027-09-27 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204791 | 27.09.2027 | 12000 | CCK-MP-HAUL-DT759 -BRKSYS-BRVLV-VVPRV | 6800 | 79716 | 12404
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Water Tank Cannon & Spray Sys Insp | 2027-09-27 | 2027-09-27 | 3 hrs | FY28 | 3 | 90036927 | B1 | 1000368892 | 27.09.2027 | 6 Monthly | CCK-MP-SUPP-WC224 -STRUCT-WTANK | 5000 | 70936 | 6229
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Airconditioner Service | 2027-09-27 | 2027-09-28 | 24 hrs | FY28 | 24 | 90017449 | B1 | 1000290434 | 27.09.2027 | 5500 | CCK-MP-SUPP-WC225 -STRUCT-CABIN-AIRCN | 5000 | 75244 | 10710
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Wheel End RH | 2027-09-28 | 2027-09-29 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000023594 | 28.09.2027 | 24000 | CCK-MP-HAUL-DT054 -FDRSYS-FDRVE-FDRRH | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Pump Brake Cooling | 2027-09-28 | 2027-09-28 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000023600 | 28.09.2027 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-HYFPP | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Brake Oil Cooler Front | 2027-09-28 | 2027-09-28 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000082850 | 28.09.2027 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BROCO-BROCF | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Brake Oil Cooler Rear | 2027-09-28 | 2027-09-28 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000082849 | 28.09.2027 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BROCO-BROCR | 7400 | 88111 | 15675
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Valve Retard & Brake Treadle | 2027-09-29 | 2027-09-29 | 5.5 hrs | FY28 | 5.5 | 90011345 | B1 | 1000094333 | 29.09.2027 | 25000 | CCK-MP-HAUL-DT752 -BRKSYS-BRVTR | 6800 | 80681 | 48041
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Differential | 2027-09-29 | 2027-09-30 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000025042 | 29.09.2027 | 18000 | CCK-MP-HAUL-DT127 -FDRSYS-DIFFL | 7400 | 83059 | 9436
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Operators Seat | 2027-09-30 | 2027-09-30 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000025973 | 30.09.2027 | 15000 | CCK-MP-HAUL-DT143 -STRUCT-CABIN-SEATS | 7400 | 88225 | 6200
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Engine Cat C175-16 | 2027-09-30 | 2027-10-03 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000155949 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -ENGINE | 7400 | 88657 | 88657
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Torque Converter | 2027-09-30 | 2027-10-01 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000116247 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -TRNSYS-TRQUE | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Motor Lube Axle Rear & Hoses | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271991 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-HYM01 | 7400 | 88657 | 25780
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Axle Lube Hyd Pump | 2027-09-30 | 2027-09-30 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000154010 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-HYPUM | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Overhaul Accumulator Brake LHF | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024984 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BACCM-FRLFT | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Overhaul Accumulator Brake RHF | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024985 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BACCM-FRRGT | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Overhaul Accumulator Brake Rear | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024986 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BACCM-BACCR | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Pump Brake Cooling | 2027-09-30 | 2027-09-30 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000024987 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-HYFPP | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Overhaul Valve Control Brake | 2027-09-30 | 2027-10-01 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000024988 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BRVLV | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Brake Oil Cooler Front | 2027-09-30 | 2027-09-30 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000083097 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BROCO-BROCF | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Brake Oil Cooler Rear | 2027-09-30 | 2027-09-30 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083096 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BROCO-BROCR | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Motor Brake Oil Cooling | 2027-09-30 | 2027-09-30 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000024989 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -BRKSYS-BROCO-HYMO1 | 7400 | 88651 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Hyd Pump Steering Main & Fan | 2027-09-30 | 2027-09-30 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000024992 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -STRSYS-STPMP | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Steering HMU | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000024993 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -STRSYS-STHMU | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Ovhl Accumulator Steering Front | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024996 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -STRSYS-STACC-SACCF | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Ovhl Accumulator Steering Middle | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024997 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -STRSYS-STACC-SACCM | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Ovhl Accumulator Steering Rear | 2027-09-30 | 2027-09-30 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024998 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -STRSYS-STACC-SACCR | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Rear Axle Linkages | 2027-09-30 | 2027-10-02 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000025009 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -STRUCT-CHASS-AXLIK | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Wheel Group Front RH | 2027-09-30 | 2027-10-01 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157225 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -STRUCT-AXLES-HUBRH | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Suspension RHF | 2027-09-30 | 2027-10-02 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067515 | 30.09.2027 | 28000 | CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYRF | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Replace Hoses Hoist System | 2027-09-30 | 2027-10-01 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083092 | 30.09.2027 | 24000 | CCK-MP-HAUL-DT126 -HYDSYS-HDHLF-HSTHO | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Spiders Pump Drive Shaft | 2027-09-30 | 2027-09-30 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000025034 | 30.09.2027 | 18000 | CCK-MP-HAUL-DT127 -ENGINE-PMPDR-DRSHT | 7400 | 83059 | 27545
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 5000Hr Valve Set | 2027-10-01 | 2027-10-01 | 12 hrs | FY28 | 24 | 90028725 | B1 | 1000289482 | 01.10.2027 | 5000 | CCK-MP-SUPP-WC3111-ENGINE | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Steering Accumulator LH | 2027-10-01 | 2027-10-01 | 2 hrs | FY28 | 2 | 90004022 | B2 | 1000079208 | 01.10.2027 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STACC-SACLH | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Steering Accumulator RH | 2027-10-01 | 2027-10-01 | 2 hrs | FY28 | 2 | 90004022 | B2 | 1000079209 | 01.10.2027 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STACC-SACRH | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Steering HMU | 2027-10-01 | 2027-10-01 | 8 hrs | FY28 | 8 | 90004004 | B2 | 1000079203 | 01.10.2027 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STHMU | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Steering Cylinder RH | 2027-10-01 | 2027-10-01 | 10 hrs | FY28 | 18 | 90004005 | B2 | 1000079205 | 01.10.2027 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STRCY-STCYR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Service Airconditioner | 2027-10-01 | 2027-10-01 | 12 hrs | FY28 | 12 | 90028728 | B1 | 1000289479 | 01.10.2027 | 5000 | CCK-MP-SUPP-WC3111-STRUCT-CABIN-AIRCN | 5600 | 51257 | 8333
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Spiders Pump Drive Shaft | 2027-10-01 | 2027-10-01 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000025739 | 01.10.2027 | 18000 | CCK-MP-HAUL-DT140 -ENGINE-PMPDR-DRSHT | 7400 | 86767 | 9442
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Replace Operator Cabin Dash Bulbs | 2027-10-02 | 2027-10-02 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158227 | 02.10.2027 | 3000 | CCK-MP-HAUL-DT762 -STRUCT-CABIN | 6800 | 76486 | 20565
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Spider Trans Driveshaft | 2027-10-02 | 2027-10-02 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154978 | 02.10.2027 | 6000 | CCK-MP-HAUL-DT150 -FDRSYS-DRSHT-UNVSL | 7400 | 86608 | 2171
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Hub & Spindle RH | 2027-10-03 | 2027-10-04 | 32 hrs | FY28 | 60 | 90011364 | B1 | 1000094989 | 03.10.2027 | 18000 | CCK-MP-HAUL-DT764 -STRUCT-AXLES-HUBRH | 6800 | 75315 | 9805
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Air Con Service & Overhaul | 2027-10-04 | 2027-10-05 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110631 | 04.10.2027 | 12 Monthly | CCK-MP-HAUL-DT762 -STRUCT-CABIN-AIRCN | 6800 | 76486 | 43303
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Replace Trans TCon System Hoses | 2027-10-05 | 2027-10-06 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090154 | 05.10.2027 | 18000 | CCK-MP-HAUL-DT151 -TRNSYS-TRANS-TRNHO | 7400 | 84253 | 9280
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl AOC Fan Motor Rear | 2027-10-05 | 2027-10-05 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024037 | 05.10.2027 | 12000 | CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-HYM02 | 7400 | 86846 | 3219
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Brake Slack Adjuster Rear | 2027-10-06 | 2027-10-06 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025499 | 06.10.2027 | 20000 | CCK-MP-HAUL-DT136 -BRKSYS-SLACK-SLACR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Drive Shaft Transmission | 2027-10-07 | 2027-10-07 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154985 | 07.10.2027 | 18000 | CCK-MP-HAUL-DT155 -FDRSYS-DRSHT | 7400 | 81407 | 10226
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Engine Cat C175-16 LMR | 2027-10-07 | 2027-10-10 | 84 hrs | FY28 | 137 | 90018364 | B1 | 1000156051 | 07.10.2027 | 24000 | CCK-MP-HAUL-DT157 -ENGINE | 7400 | 83041 | 15053
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Service Air Conditioner 12M | 2027-10-08 | 2027-10-09 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174109 | 08.10.2027 | 12 Monthly | CCK-MP-HAUL-DT054 -STRUCT-CABIN-AIRCN | 7400 | 88111 | 15675
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Initial Engine Valve Set | 2027-10-08 | 2027-10-08 | 12 hrs | FY28 | 24 | 90015765 | B1 | 1000269918 | 08.10.2027 | 250 | CCK-MP-SUPP-WC221 -ENGINE | 4300 | 56923 | 12761
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Hub & Spindle RH | 2027-10-09 | 2027-10-10 | 32 hrs | FY28 | 60 | 90011364 | B1 | 1000095148 | 09.10.2027 | 18000 | CCK-MP-HAUL-DT767 -STRUCT-AXLES-HUBRH | 6800 | 74312 | 9613
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Suspension LHF | 2027-10-09 | 2027-10-11 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067509 | 09.10.2027 | 28000 | CCK-MP-HAUL-DT100 -STRUCT-SUSPN-SCYLF | 7400 | 87135 | 19314
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Auto Lube Pump | 2027-10-09 | 2027-10-09 | 2 hrs | FY28 | 2 | 90002914 | B2 | 1000040563 | 09.10.2027 | 6000 | CCK-MP-SUPP-WC224 -GRSYST-ALBPP | 5000 | 71088 | 6229
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Inspect Rear Axle Housing | 2027-10-09 | 2027-10-09 | 1 hr | FY28 | 1 | 90019256 | B1 | 1000196434 | 09.10.2027 | 2000 | CCK-MP-SUPP-WC224 -STRUCT-RAXHO | 5000 | 71088 | 71088
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl AOC Fan Motor Rear | 2027-10-09 | 2027-10-09 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000026277 | 09.10.2027 | 12000 | CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYM02 | 7400 | 85452 | 18024
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Replace Operator Cabin Dash Bulbs | 2027-10-10 | 2027-10-10 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158229 | 10.10.2027 | 3000 | CCK-MP-HAUL-DT764 -STRUCT-CABIN | 6800 | 75315 | 21117
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Service Air Conditioner 12M | 2027-10-10 | 2027-10-11 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174160 | 10.10.2027 | 12 Monthly | CCK-MP-HAUL-DT095 -STRUCT-CABIN-AIRCN | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Brake Oil Cooler Front | 2027-10-11 | 2027-10-11 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000083078 | 11.10.2027 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BROCO-BROCF | 7400 | 87135 | 15281
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Brake Oil Cooler Rear | 2027-10-11 | 2027-10-11 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083077 | 11.10.2027 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BROCO-BROCR | 7400 | 87135 | 15281
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Operators Seat | 2027-10-11 | 2027-10-11 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000128125 | 11.10.2027 | 15000 | CCK-MP-HAUL-DT223 -STRUCT-CABIN-SEATS | 7400 | 54920 | 24735
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Sepura SCC Microphone | 2027-10-11 | 2027-10-11 | 0.5 hrs | FY28 | 0.5 | 90029002 | B1 | 1000289636 | 11.10.2027 | 12 Monthly | CCK-MP-SUPP-WC225 -COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Auto Lube Pump | 2027-10-11 | 2027-10-11 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285798 | 11.10.2027 | 8000 | CCK-MP-HAUL-DT160 -GRSYST-ALBPP | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Front Wheel Bearings LH | 2027-10-11 | 2027-10-12 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157178 | 11.10.2027 | 16000 | CCK-MP-HAUL-DT160 -STRUCT-AXLES-FWBLH | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Front Wheel Bearings RH | 2027-10-11 | 2027-10-12 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157266 | 11.10.2027 | 16000 | CCK-MP-HAUL-DT160 -STRUCT-AXLES-FWBRH | 7400 | 85085 | 7211
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Engine Midlife Complete | 2027-10-12 | 2027-10-14 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285521 | 12.10.2027 | 12500 | CCK-MP-HAUL-DT763 -ENGINE | 6800 | 74143 | 4528
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension LHF | 2027-10-12 | 2027-10-12 | 2 hrs | FY28 | 2 | 90038229 | B1 | 1000382496 | 12.10.2027 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension RHF | 2027-10-12 | 2027-10-12 | 2 hrs | FY28 | 2 | 90038229 | B1 | 1000382497 | 12.10.2027 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRF | 5000 | 75197 | 10710
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Torque Converter | 2027-10-12 | 2027-10-13 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000026863 | 12.10.2027 | 24000 | CCK-MP-HAUL-DT157 -TRNSYS-TRQUE | 7400 | 83026 | 15134
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 250hr Initial Valve Set | 2027-10-12 | 2027-10-12 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155952 | 12.10.2027 | 250 | CCK-MP-HAUL-DT126 -ENGINE | 7400 | 88657 | 88657
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Front Wheel Bearings LH | 2027-10-12 | 2027-10-13 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157150 | 12.10.2027 | 16000 | CCK-MP-HAUL-DT140 -STRUCT-AXLES-FWBLH | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Wheel Group Front LH | 2027-10-12 | 2027-10-13 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157123 | 12.10.2027 | 24000 | CCK-MP-HAUL-DT091 -STRUCT-AXLES-HUBLH | 7400 | 83859 | 15238
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Replace Auto Lube Pump | 2027-10-12 | 2027-10-12 | 4 hrs | FY28 | 4 | 90003064 | B2 | 1000239787 | 12.10.2027 | 6000 | CCK-MP-SUPP-WC009 -GRSYST-ALBPP | 1500 | 34052 | 3786
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Tyre Sense Battery | 2027-10-13 | 2027-10-13 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153182 | 13.10.2027 | 24 Monthly | CCK-MP-HAUL-DT757 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Tyre Sense Battery | 2027-10-13 | 2027-10-13 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153187 | 13.10.2027 | 24 Monthly | CCK-MP-HAUL-DT762 -MANGMT-TYRSN
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Water Tank Cannon & Spray Sys Insp | 2027-10-13 | 2027-10-13 | 3 hrs | FY28 | 3 | 90036927 | B1 | 1000368894 | 13.10.2027 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-WTANK | 5000 | 75244 | 75244
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Transmission | 2027-10-13 | 2027-10-14 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272343 | 13.10.2027 | 18000 | CCK-MP-HAUL-DT149 -TRNSYS-TRANS | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Transmission Oil Cooler | 2027-10-13 | 2027-10-13 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000083411 | 13.10.2027 | 18000 | CCK-MP-HAUL-DT149 -TRNSYS-TROLC | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Differential | 2027-10-13 | 2027-10-14 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000026339 | 13.10.2027 | 18000 | CCK-MP-HAUL-DT149 -FDRSYS-DIFFL | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Replace Trans TCon System Hoses | 2027-10-13 | 2027-10-14 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090148 | 13.10.2027 | 18000 | CCK-MP-HAUL-DT149 -TRNSYS-TRANS-TRNHO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Replace Hoses Differential System | 2027-10-13 | 2027-10-13 | 5 hrs | FY28 | 5 | 90010101 | B2 | 1000090149 | 13.10.2027 | 18000 | CCK-MP-HAUL-DT149 -FDRSYS-DIFFL-DIFHO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Tyre Sense Battery | 2027-10-13 | 2027-10-13 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153148 | 13.10.2027 | 24 Monthly | CCK-MP-HAUL-DT126 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Tyre Sense Battery | 2027-10-13 | 2027-10-13 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153119 | 13.10.2027 | 24 Monthly | CCK-MP-HAUL-DT088 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Tyre Sense Battery | 2027-10-13 | 2027-10-13 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153114 | 13.10.2027 | 24 Monthly | CCK-MP-HAUL-DT056 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Air Con Service & Overhaul | 2027-10-15 | 2027-10-16 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110623 | 15.10.2027 | 12 Monthly | CCK-MP-HAUL-DT754 -STRUCT-CABIN-AIRCN | 6800 | 83256 | 12630
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Steering RH | 2027-10-16 | 2027-10-16 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000026025 | 16.10.2027 | 15000 | CCK-MP-HAUL-DT5255-STRSYS-STRCY-STCYR | 7400 | 87580 | 6100
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Transmission Oil Cooler | 2027-10-17 | 2027-10-17 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000083202 | 17.10.2027 | 18000 | CCK-MP-HAUL-DT136 -TRNSYS-TROLC | 7400 | 87780 | 9254
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Drive Shaft Transmission | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000167057 | 17.10.2027 | 18000 | CCK-MP-HAUL-DT5314-FDRSYS-DRSHT | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Wheel Group Front LH | 2027-10-17 | 2027-10-18 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157143 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT135 -STRUCT-AXLES-HUBLH | 7400 | 82965 | 15252
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Radiator Engine Cooling | 2027-10-17 | 2027-10-18 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307480 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -ENGINE-COSYS-RADTR | 7400 | 89037 | 36530
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Pump Drive | 2027-10-17 | 2027-10-18 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000024150 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -ENGINE-PMPDR | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Wheel End LH | 2027-10-17 | 2027-10-18 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000024160 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -FDRSYS-FDRVE-FDRLH | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Wheel End RH | 2027-10-17 | 2027-10-18 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000024161 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -FDRSYS-FDRVE-FDRRH | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Motor Lube Axle Rear & Hoses | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271955 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM01 | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl AOC Fan Motor Rear | 2027-10-17 | 2027-10-17 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024163 | 17.10.2027 | 12000 | CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM02 | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Axle Lube Hyd Pump | 2027-10-17 | 2027-10-17 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000082919 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYPUM | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Overhaul Accumulator Brake LHF | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024164 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BACCM-FRLFT | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Overhaul Accumulator Brake RHF | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024165 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BACCM-FRRGT | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Overhaul Accumulator Brake Rear | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024166 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BACCM-BACCR | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Overhaul Valve Control Brake | 2027-10-17 | 2027-10-18 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000024168 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BRVLV | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Brake Oil Cooler Front | 2027-10-17 | 2027-10-17 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000082926 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BROCO-BROCF | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Brake Oil Cooler Rear | 2027-10-17 | 2027-10-17 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000082925 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BROCO-BROCR | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Motor Brake Oil Cooling | 2027-10-17 | 2027-10-17 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000024169 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -BRKSYS-BROCO-HYMO1 | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Hyd Pump Steering Main & Fan | 2027-10-17 | 2027-10-17 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000024172 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRSYS-STPMP | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Steering HMU | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000024173 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRSYS-STHMU | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Ovhl Accumulator Steering Front | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000116244 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRSYS-STACC-SACCF | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Ovhl Accumulator Steering Middle | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024177 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRSYS-STACC-SACCM | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Ovhl Accumulator Steering Rear | 2027-10-17 | 2027-10-17 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024178 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRSYS-STACC-SACCR | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Pump Hoist & Brake | 2027-10-17 | 2027-10-17 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000024180 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -HYDSYS-HOPMP | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Rear Axle Linkages | 2027-10-17 | 2027-10-19 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000024189 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRUCT-CHASS-AXLIK | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Wheel Group Front LH | 2027-10-17 | 2027-10-18 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157119 | 17.10.2027 | 24000 | CCK-MP-HAUL-DT088 -STRUCT-AXLES-HUBLH | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Cyl Steering LH | 2027-10-17 | 2027-10-17 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000024364 | 17.10.2027 | 15000 | CCK-MP-HAUL-DT091 -STRSYS-STRCY-STCYL | 7400 | 83859 | 6114
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Transmisson Calibration | 2027-10-18 | 2027-10-18 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298814 | 18.10.2027 | 4500 | CCK-MP-HAUL-DT5314-TRNSYS-TRANS | 7400 | 45898 | 950
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Suspension LHF | 2027-10-19 | 2027-10-21 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067589 | 19.10.2027 | 28000 | CCK-MP-HAUL-DT147 -STRUCT-SUSPN-SCYLF | 7400 | 84659 | 19041
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Differential | 2027-10-19 | 2027-10-20 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000167239 | 19.10.2027 | 18000 | CCK-MP-HAUL-DT5317-FDRSYS-DIFFL | 7400 | 45576 | 9163
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 250hr Initial Valve Set | 2027-10-19 | 2027-10-19 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156054 | 19.10.2027 | 250 | CCK-MP-HAUL-DT157 -ENGINE | 7400 | 83041 | 15053
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Steering Linkages | 2027-10-20 | 2027-10-20 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317595 | 20.10.2027 | 15000 | CCK-MP-HAUL-DT090 -STRSYS-STLTR | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Replace Steering System Hoses | 2027-10-20 | 2027-10-22 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000082969 | 20.10.2027 | 15000 | CCK-MP-HAUL-DT090 -STRSYS-STHLF-STRHO | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Steering Hyd Oil Cooler | 2027-10-20 | 2027-10-20 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000106982 | 20.10.2027 | 15000 | CCK-MP-HAUL-DT090 -STRSYS-STOCO | 7400 | 81670 | 5994
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Cyl Hoist LH | 2027-10-21 | 2027-10-21 | 17 hrs | FY28 | 33 | 90011357 | B1 | 1000094769 | 21.10.2027 | 25000 | CCK-MP-HAUL-DT760 -HYDSYS-HOCYL-HCYLL | 6800 | 80390 | 16984
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Wheel End LH | 2027-10-21 | 2027-10-22 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000026274 | 21.10.2027 | 24000 | CCK-MP-HAUL-DT148 -FDRSYS-FDRVE-FDRLH | 7400 | 85452 | 15062
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Replace Operator Cabin Dash Bulbs | 2027-10-22 | 2027-10-22 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158221 | 22.10.2027 | 3000 | CCK-MP-HAUL-DT756 -STRUCT-CABIN | 6800 | 78754 | 78754
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Tow Ball Insert | 2027-10-22 | 2027-10-22 | 12 hrs | FY28 | 24 | 90028421 | B1 | 1000283439 | 22.10.2027 | 20000 | CCK-MP-SUPP-PM0001-STRUCT-CHASS-TRMNT | 3400 | 48287 | 15216
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Operator Cabin Dash Bulbs | 2027-10-22 | 2027-10-22 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158216 | 22.10.2027 | 3000 | CCK-MP-HAUL-DT751 -STRUCT-CABIN | 6800 | 86211 | 11291
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Brake Slack Adjuster Front | 2027-10-22 | 2027-10-22 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026284 | 22.10.2027 | 20000 | CCK-MP-HAUL-DT148 -BRKSYS-SLACK-SLACF | 7400 | 85452 | 11002
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Brake Slack Adjuster Rear | 2027-10-22 | 2027-10-22 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026285 | 22.10.2027 | 20000 | CCK-MP-HAUL-DT148 -BRKSYS-SLACK-SLACR | 7400 | 85452 | 11002
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Brake Oil Cooler Front | 2027-10-22 | 2027-10-22 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000083173 | 22.10.2027 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BROCO-BROCF | 7400 | 85185 | 15131
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Brake Oil Cooler Rear | 2027-10-22 | 2027-10-22 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083172 | 22.10.2027 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BROCO-BROCR | 7400 | 85185 | 15131
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Motor Brake Oil Cooling | 2027-10-22 | 2027-10-22 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000025241 | 22.10.2027 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BROCO-HYMO1 | 7400 | 85185 | 15131
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Rear Axle Linkages | 2027-10-22 | 2027-10-24 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000025261 | 22.10.2027 | 24000 | CCK-MP-HAUL-DT130 -STRUCT-CHASS-AXLIK | 7400 | 85185 | 15131
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Wheel End RH | 2027-10-22 | 2027-10-23 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000024351 | 22.10.2027 | 24000 | CCK-MP-HAUL-DT091 -FDRSYS-FDRVE-FDRRH | 7400 | 83859 | 15032
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Cyl Steering LH | 2027-10-24 | 2027-10-24 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000023607 | 24.10.2027 | 15000 | CCK-MP-HAUL-DT054 -STRSYS-STRCY-STCYL | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Operators Seat | 2027-10-24 | 2027-10-24 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000023621 | 24.10.2027 | 15000 | CCK-MP-HAUL-DT054 -STRUCT-CABIN-SEATS | 7400 | 88111 | 768
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Replace Steering System Hoses | 2027-10-24 | 2027-10-26 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000082855 | 24.10.2027 | 15000 | CCK-MP-HAUL-DT054 -STRSYS-STHLF-STRHO | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Brake Slack Adjuster Front | 2027-10-24 | 2027-10-24 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026944 | 24.10.2027 | 20000 | CCK-MP-HAUL-DT158 -BRKSYS-SLACK-SLACF | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Brake Slack Adjuster Rear | 2027-10-24 | 2027-10-24 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026945 | 24.10.2027 | 20000 | CCK-MP-HAUL-DT158 -BRKSYS-SLACK-SLACR | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Front Wheel Bearings LH | 2027-10-24 | 2027-10-25 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157106 | 24.10.2027 | 16000 | CCK-MP-HAUL-DT055 -STRUCT-AXLES-FWBLH | 7400 | 84122 | 7332
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Suspension LHF | 2027-10-25 | 2027-10-27 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067397 | 25.10.2027 | 28000 | CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYLF | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Suspension RHF | 2027-10-25 | 2027-10-27 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067399 | 25.10.2027 | 28000 | CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYRF | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Suspension LHR | 2027-10-25 | 2027-10-26 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000023818 | 25.10.2027 | 28000 | CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYLR | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Suspension RHR | 2027-10-25 | 2027-10-26 | 22 hrs | FY28 | 39 | 90002409 | B2 | 1000023819 | 25.10.2027 | 28000 | CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYRR | 7400 | 91273 | 18727
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Pump Brake Cooling | 2027-10-25 | 2027-10-25 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000025755 | 25.10.2027 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-HYFPP | 7400 | 86767 | 14972
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Engine Midlife Complete | 2027-10-25 | 2027-10-26 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155924 | 25.10.2027 | 12000 | CCK-MP-HAUL-DT094 -ENGINE | 7400 | 88788 | 50851
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Cyl Steering LH | 2027-10-26 | 2027-10-26 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000095239 | 26.10.2027 | 15000 | CCK-MP-HAUL-DT769 -STRSYS-STRCY-STCYL | 6800 | 80508 | 21383
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Service Air Conditioner 12M | 2027-10-27 | 2027-10-28 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174117 | 27.10.2027 | 12 Monthly | CCK-MP-HAUL-DT090 -STRUCT-CABIN-AIRCN | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Hyd Pump Steering Main & Fan | 2027-10-28 | 2027-10-28 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000025956 | 28.10.2027 | 24000 | CCK-MP-HAUL-DT143 -STRSYS-STPMP | 7400 | 88225 | 14631
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Brake Slack Adjuster Front | 2027-10-28 | 2027-10-28 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000023792 | 28.10.2027 | 20000 | CCK-MP-HAUL-DT057 -BRKSYS-SLACK-SLACF | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Brake Slack Adjuster Rear | 2027-10-28 | 2027-10-28 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000023793 | 28.10.2027 | 20000 | CCK-MP-HAUL-DT057 -BRKSYS-SLACK-SLACR | 7400 | 91273 | 10672
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Air Con Service & Overhaul | 2027-10-29 | 2027-10-30 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110629 | 29.10.2027 | 12 Monthly | CCK-MP-HAUL-DT760 -STRUCT-CABIN-AIRCN | 6800 | 80390 | 23992
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Replace Operator Cabin Dash Bulbs | 2027-10-29 | 2027-10-29 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158235 | 29.10.2027 | 3000 | CCK-MP-HAUL-DT770 -STRUCT-CABIN | 6800 | 79305 | 79305
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Hub & Spindle LH | 2027-10-29 | 2027-10-30 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000094511 | 29.10.2027 | 18000 | CCK-MP-HAUL-DT755 -STRUCT-AXLES-HUBLH | 6800 | 84587 | 14338
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 5000Hr Valve Set | 2027-10-29 | 2027-10-29 | 12 hrs | FY28 | 24 | 90028725 | B1 | 1000289488 | 29.10.2027 | 5000 | CCK-MP-SUPP-WC3112-ENGINE | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl PTO Uni's | 2027-10-29 | 2027-10-29 | 4 hrs | FY28 | 4 | 90031093 | B1 | 1000307815 | 29.10.2027 | 5000 | CCK-MP-SUPP-WC3112-ENGINE-PMPDR-DRSHT | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Steering Accumulator LH | 2027-10-29 | 2027-10-29 | 2 hrs | FY28 | 2 | 90004022 | B2 | 1000079273 | 29.10.2027 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STACC-SACLH | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Steering Accumulator RH | 2027-10-29 | 2027-10-29 | 2 hrs | FY28 | 2 | 90004022 | B2 | 1000079274 | 29.10.2027 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STACC-SACRH | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Service Airconditioner | 2027-10-29 | 2027-10-29 | 12 hrs | FY28 | 12 | 90028728 | B1 | 1000289485 | 29.10.2027 | 5000 | CCK-MP-SUPP-WC3112-STRUCT-CABIN-AIRCN | 5600 | 52240 | 8166
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Transmisson Calibration | 2027-10-30 | 2027-10-30 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298667 | 30.10.2027 | 4500 | CCK-MP-HAUL-DT082 -TRNSYS-TRANS | 7400 | 84375 | 13167
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Grid Box Blower Motor LH | 2027-10-31 | 2027-10-31 | 10 hrs | FY28 | 10 | 90011331 | B1 | 1000094959 | 31.10.2027 | 25000 | CCK-MP-HAUL-DT764 -ELCTHV-HVGBM-GBMLH | 6800 | 75315 | 16287
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Wheel Motor RH | 2027-10-31 | 2027-11-02 | 45.5 hrs | FY28 | 83.5 | 90011336 | B1 | 1000094964 | 31.10.2027 | 25000 | CCK-MP-HAUL-DT764 -FDRSYS-WLMTR-WHMRH | 6800 | 75315 | 21117
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Wheel Motor Oil RH | 2027-10-31 | 2027-10-31 | 1 hr | FY28 | 1 | 90033606 | B1 | 1000338225 | 31.10.2027 | 25000 | CCK-MP-HAUL-DT764 -FDRSYS-WLMTR-WHMRH | 6800 | 75315 | 21117
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Engine Midlife Complete | 2027-11-01 | 2027-11-03 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285174 | 01.11.2027 | 12500 | CCK-MP-HAUL-DT756 -ENGINE | 6800 | 78754 | 288
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Cyl Steering LH | 2027-11-01 | 2027-11-01 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000094444 | 01.11.2027 | 15000 | CCK-MP-HAUL-DT754 -STRSYS-STRCY-STCYL | 6800 | 83256 | 6574
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Spider Trans Driveshaft | 2027-11-01 | 2027-11-01 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154946 | 01.11.2027 | 6000 | CCK-MP-HAUL-DT099 -FDRSYS-DRSHT-UNVSL | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Auto Lube Pump | 2027-11-01 | 2027-11-01 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285784 | 01.11.2027 | 8000 | CCK-MP-HAUL-DT140 -GRSYST-ALBPP | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Front Wheel Bearings RH | 2027-11-01 | 2027-11-02 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157238 | 01.11.2027 | 16000 | CCK-MP-HAUL-DT140 -STRUCT-AXLES-FWBRH | 7400 | 86767 | 6817
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Engine Midlife Complete | 2027-11-02 | 2027-11-04 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285522 | 02.11.2027 | 12500 | CCK-MP-HAUL-DT764 -ENGINE | 6800 | 75315 | 3766
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Replace Operator Cabin Dash Bulbs | 2027-11-02 | 2027-11-02 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158238 | 02.11.2027 | 3000 | CCK-MP-HAUL-DT773 -STRUCT-CABIN | 6800 | 75884 | 75884
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Auto Lube Pump | 2027-11-02 | 2027-11-02 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285632 | 02.11.2027 | 8000 | CCK-MP-HAUL-DT094 -GRSYST-ALBPP | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Transmisson Calibration | 2027-11-04 | 2027-11-04 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298735 | 04.11.2027 | 4500 | CCK-MP-HAUL-DT157 -TRNSYS-TRANS | 7400 | 83026 | 4183
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Hub & Spindle LH | 2027-11-06 | 2027-11-07 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000094882 | 06.11.2027 | 18000 | CCK-MP-HAUL-DT762 -STRUCT-AXLES-HUBLH | 6800 | 76486 | 9227
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Hub & Spindle RH | 2027-11-06 | 2027-11-07 | 32 hrs | FY28 | 60 | 90011364 | B1 | 1000094883 | 06.11.2027 | 18000 | CCK-MP-HAUL-DT762 -STRUCT-AXLES-HUBRH | 6800 | 76486 | 9227
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Cyl Suspension LHF | 2027-11-06 | 2027-11-08 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000094884 | 06.11.2027 | 18000 | CCK-MP-HAUL-DT762 -STRUCT-SUSPN-SCYLF | 6800 | 76486 | 9227
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Cyl Suspension RHF | 2027-11-06 | 2027-11-08 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000094885 | 06.11.2027 | 18000 | CCK-MP-HAUL-DT762 -STRUCT-SUSPN-SCYRF | 6800 | 76486 | 9227
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Service Air Conditioner 12M | 2027-11-07 | 2027-11-08 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174193 | 07.11.2027 | 12 Monthly | CCK-MP-HAUL-DT5314-STRUCT-CABIN-AIRCN | 7400 | 45898 | 45898
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Grid Box Blower Motor RH | 2027-11-08 | 2027-11-08 | 10 hrs | FY28 | 10 | 90011332 | B1 | 1000095066 | 08.11.2027 | 25000 | CCK-MP-HAUL-DT766 -ELCTHV-HVGBM-GBMRH | 6800 | 78074 | 17489
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Steering Bleed Down Manifold | 2027-11-08 | 2027-11-08 | 6.5 hrs | FY28 | 8 | 90011347 | B1 | 1000095077 | 08.11.2027 | 25000 | CCK-MP-HAUL-DT766 -STRSYS-STBDM | 6800 | 78074 | 17489
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Ovhl Accumulator Steering Front | 2027-11-08 | 2027-11-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023798 | 08.11.2027 | 24000 | CCK-MP-HAUL-DT057 -STRSYS-STACC-SACCF | 7400 | 91273 | 42405
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Ovhl Accumulator Steering Middle | 2027-11-08 | 2027-11-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023799 | 08.11.2027 | 24000 | CCK-MP-HAUL-DT057 -STRSYS-STACC-SACCM | 7400 | 91273 | 42405
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Brake Slack Adjuster Front | 2027-11-08 | 2027-11-08 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024360 | 08.11.2027 | 20000 | CCK-MP-HAUL-DT091 -BRKSYS-SLACK-SLACF | 7400 | 83859 | 10692
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Brake Slack Adjuster Rear | 2027-11-08 | 2027-11-08 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024361 | 08.11.2027 | 20000 | CCK-MP-HAUL-DT091 -BRKSYS-SLACK-SLACR | 7400 | 83859 | 10692
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Front Wheel Bearings LH | 2027-11-09 | 2027-11-10 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157164 | 09.11.2027 | 16000 | CCK-MP-HAUL-DT150 -STRUCT-AXLES-FWBLH | 7400 | 86608 | 6426
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Spider Trans Driveshaft | 2027-11-10 | 2027-11-10 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154992 | 10.11.2027 | 6000 | CCK-MP-HAUL-DT160 -FDRSYS-DRSHT-UNVSL | 7400 | 85085 | 2673
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Tyre Sense Battery | 2027-11-10 | 2027-11-10 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153160 | 10.11.2027 | 24 Monthly | CCK-MP-HAUL-DT148 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Spiders Pump Drive Shaft | 2027-11-11 | 2027-11-11 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000167234 | 11.11.2027 | 18000 | CCK-MP-HAUL-DT5317-ENGINE-PMPDR-DRSHT | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Replace Trans TCon System Hoses | 2027-11-11 | 2027-11-12 | 20 hrs | FY28 | 20 | 90010099 | B3 | 1000167277 | 11.11.2027 | 18000 | CCK-MP-HAUL-DT5317-TRNSYS-TRANS-TRNHO | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Transmission Oil Cooler | 2027-11-11 | 2027-11-11 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000167268 | 11.11.2027 | 18000 | CCK-MP-HAUL-DT5317-TRNSYS-TROLC | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Replace Hoses Differential System | 2027-11-11 | 2027-11-11 | 5 hrs | FY28 | 5 | 90010101 | B3 | 1000167278 | 11.11.2027 | 18000 | CCK-MP-HAUL-DT5317-FDRSYS-DIFFL-DIFHO | 7400 | 45576 | 8696
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Replace Operator Cabin Dash Bulbs | 2027-11-12 | 2027-11-12 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158222 | 12.11.2027 | 3000 | CCK-MP-HAUL-DT757 -STRUCT-CABIN | 6800 | 80700 | 80700
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Auto Lube Pump | 2027-11-12 | 2027-11-12 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095249 | 12.11.2027 | 8000 | CCK-MP-HAUL-DT769 -GRSYST-ALBPP | 6800 | 80508 | 7418
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Hyd Pump Steering Main | 2027-11-12 | 2027-11-12 | 6 hrs | FY28 | 6 | 90000896 | B2 | 1000033366 | 12.11.2027 | 15000 | CCK-MP-SUPP-WC225 -STRSYS-STPMP | 5000 | 75244 | 8627
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Cyl Suspension LHF | 2027-11-13 | 2027-11-15 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000094831 | 13.11.2027 | 18000 | CCK-MP-HAUL-DT761 -STRUCT-SUSPN-SCYLF | 6800 | 78336 | 14347
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Transmisson Calibration | 2027-11-13 | 2027-11-13 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298741 | 13.11.2027 | 4500 | CCK-MP-HAUL-DT222 -TRNSYS-TRANS | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Cyl Steering LH | 2027-11-14 | 2027-11-14 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000026024 | 14.11.2027 | 15000 | CCK-MP-HAUL-DT5255-STRSYS-STRCY-STCYL | 7400 | 87580 | 5564
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Ovhl Axle Housing Dogbone | 2027-11-14 | 2027-11-14 | 12 hrs | FY28 | 24 | 90002923 | B1 | 1000238425 | 14.11.2027 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-CHASS-TAGLK | 5000 | 75244 | 75244
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Operators Seat | 2027-11-14 | 2027-11-14 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000025008 | 14.11.2027 | 15000 | CCK-MP-HAUL-DT126 -STRUCT-CABIN-SEATS | 7400 | 88657 | 1218
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Tyre Sense Battery | 2027-11-15 | 2027-11-15 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153185 | 15.11.2027 | 24 Monthly | CCK-MP-HAUL-DT760 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Pump Hoist & Brake | 2027-11-15 | 2027-11-15 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000023865 | 15.11.2027 | 24000 | CCK-MP-HAUL-DT058 -HYDSYS-HOPMP | 7400 | 87864 | 14260
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Transmisson Calibration | 2027-11-16 | 2027-11-16 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298674 | 16.11.2027 | 4500 | CCK-MP-HAUL-DT097 -TRNSYS-TRANS | 7400 | 83804 | 17427
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Water Cannon Maintenance | 2027-11-16 | 2027-11-16 | 3 hrs | FY28 | 3 | 90001682 | B1 | 1000107576 | 16.11.2027 | 6 Monthly | CCK-MP-SUPP-WC009 -STRUCT-WTANK-SPRAY
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Repl Sepura SCC Microphone | 2027-11-16 | 2027-11-16 | 0.5 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289619 | 16.11.2027 | 12 Monthly | CCK-MP-SUPP-WC009 -COMMUN-RADIO
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Valve Flow Amplifier | 2027-11-17 | 2027-11-17 | 13 hrs | FY28 | 13.5 | 90011348 | B1 | 1000094336 | 17.11.2027 | 25000 | CCK-MP-HAUL-DT752 -STRSYS-STVLV | 6800 | 80681 | 31412
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Steering Hyd Oil Cooler | 2027-11-17 | 2027-11-17 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107026 | 17.11.2027 | 15000 | CCK-MP-HAUL-DT148 -STRSYS-STOCO | 7400 | 85451 | 5379
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Replace Operator Cabin Dash Bulbs | 2027-11-18 | 2027-11-18 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158232 | 18.11.2027 | 3000 | CCK-MP-HAUL-DT767 -STRUCT-CABIN | 6800 | 74312 | 19669
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Accumulator Hyd Steer Front | 2027-11-18 | 2027-11-18 | 7.5 hrs | FY28 | 11.5 | 90011352 | B1 | 1000095506 | 18.11.2027 | 25000 | CCK-MP-HAUL-DT774 -STRSYS-STACC-SACCF | 6800 | 81047 | 16446
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Accumulator Hyd Steering Rear | 2027-11-18 | 2027-11-18 | 7.5 hrs | FY28 | 11.5 | 90011353 | B1 | 1000095507 | 18.11.2027 | 25000 | CCK-MP-HAUL-DT774 -STRSYS-STACC-SACCR | 6800 | 81047 | 16446
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Radiator Fan Hoses | 2027-11-18 | 2027-11-18 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307499 | 18.11.2027 | 12000 | CCK-MP-HAUL-DT126 -ENGINE-COSYS-RADTR | 7400 | 88657 | 78969
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl AOC Fan Motor Rear | 2027-11-18 | 2027-11-18 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024983 | 18.11.2027 | 12000 | CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-HYM02 | 7400 | 88657 | 2403
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Transmisson Calibration | 2027-11-18 | 2027-11-18 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298673 | 18.11.2027 | 4500 | CCK-MP-HAUL-DT095 -TRNSYS-TRANS | 7400 | 88921 | 3967
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Hub & Spindle RH | 2027-11-19 | 2027-11-20 | 32 hrs | FY28 | 60 | 90011364 | B1 | 1000095095 | 19.11.2027 | 18000 | CCK-MP-HAUL-DT766 -STRUCT-AXLES-HUBRH | 6800 | 78074 | 10283
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Operator Cabin Dash Bulbs | 2027-11-19 | 2027-11-19 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158218 | 19.11.2027 | 3000 | CCK-MP-HAUL-DT753 -STRUCT-CABIN | 6800 | 85999 | 22050
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Cyl Suspension LHF | 2027-11-19 | 2027-11-21 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067453 | 19.11.2027 | 28000 | CCK-MP-HAUL-DT086 -STRUCT-SUSPN-SCYLF | 7400 | 86822 | 18310
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Inspect Rear Axle Housing | 2027-11-20 | 2027-11-20 | 1 hr | FY28 | 1 | 90019256 | B1 | 1000196435 | 20.11.2027 | 2000 | CCK-MP-SUPP-WC225 -STRUCT-RAXHO | 5000 | 75244 | 75244
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Service Air Conditioner 12M | 2027-11-20 | 2027-11-21 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174182 | 20.11.2027 | 12 Monthly | CCK-MP-HAUL-DT155 -STRUCT-CABIN-AIRCN | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Radiator Engine Cooling | 2027-11-20 | 2027-11-21 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307476 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -ENGINE-COSYS-RADTR | 7400 | 86846 | 31508
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Pump Drive | 2027-11-20 | 2027-11-21 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000024024 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -ENGINE-PMPDR | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Wheel End LH | 2027-11-20 | 2027-11-21 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000024034 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -FDRSYS-FDRVE-FDRLH | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Wheel End RH | 2027-11-20 | 2027-11-21 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000024035 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -FDRSYS-FDRVE-FDRRH | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Motor Lube Axle Rear & Hoses | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271953 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-HYM01 | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Axle Lube Hyd Pump | 2027-11-20 | 2027-11-20 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000082900 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-HYPUM | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Overhaul Accumulator Brake LHF | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024038 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BACCM-FRLFT | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Overhaul Accumulator Brake RHF | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024039 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BACCM-FRRGT | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Overhaul Accumulator Brake Rear | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024040 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BACCM-BACCR | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Pump Brake Cooling | 2027-11-20 | 2027-11-20 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000024041 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-HYFPP | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Overhaul Valve Control Brake | 2027-11-20 | 2027-11-21 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000024042 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BRVLV | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Brake Oil Cooler Front | 2027-11-20 | 2027-11-20 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000082907 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BROCO-BROCF | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Brake Oil Cooler Rear | 2027-11-20 | 2027-11-20 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000082906 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BROCO-BROCR | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Motor Brake Oil Cooling | 2027-11-20 | 2027-11-20 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000024043 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BROCO-HYMO1 | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Hyd Pump Steering Main & Fan | 2027-11-20 | 2027-11-20 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000024046 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -STRSYS-STPMP | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Steering HMU | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000024047 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -STRSYS-STHMU | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Ovhl Accumulator Steering Front | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024050 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -STRSYS-STACC-SACCF | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Ovhl Accumulator Steering Middle | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024051 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -STRSYS-STACC-SACCM | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Ovhl Accumulator Steering Rear | 2027-11-20 | 2027-11-20 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024052 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -STRSYS-STACC-SACCR | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Pump Hoist & Brake | 2027-11-20 | 2027-11-20 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000024054 | 20.11.2027 | 24000 | CCK-MP-HAUL-DT086 -HYDSYS-HOPMP | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Spider Trans Driveshaft | 2027-11-20 | 2027-11-20 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154930 | 20.11.2027 | 6000 | CCK-MP-HAUL-DT086 -FDRSYS-DRSHT-UNVSL | 7400 | 86822 | 2258
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Engine Midlife Complete | 2027-11-20 | 2027-11-21 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000156038 | 20.11.2027 | 12000 | CCK-MP-HAUL-DT150 -ENGINE | 7400 | 86608 | 78719
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Steering Brake Pump Compensator | 2027-11-21 | 2027-11-21 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204759 | 21.11.2027 | 6000 | CCK-MP-HAUL-DT755 -STRSYS-STPMP | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Pressure Reducing Valve | 2027-11-21 | 2027-11-21 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204787 | 21.11.2027 | 12000 | CCK-MP-HAUL-DT755 -BRKSYS-BRVLV-VVPRV | 6800 | 84587 | 9943
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Ovhl Accumulator Steering Middle | 2027-11-21 | 2027-11-21 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025505 | 21.11.2027 | 24000 | CCK-MP-HAUL-DT136 -STRSYS-STACC-SACCM | 7400 | 87780 | 14476
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Hoist Pump | 2027-11-21 | 2027-11-21 | 6 hrs | FY28 | 6 | 90000895 | B2 | 1000033300 | 21.11.2027 | 22000 | CCK-MP-SUPP-WC224 -HYDSYS-HOPMP | 5000 | 71088 | 15631
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Torque Converter | 2027-11-21 | 2027-11-22 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000024029 | 21.11.2027 | 24000 | CCK-MP-HAUL-DT086 -TRNSYS-TRQUE | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Rear Axle Linkages | 2027-11-21 | 2027-11-23 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000024063 | 21.11.2027 | 24000 | CCK-MP-HAUL-DT086 -STRUCT-CHASS-AXLIK | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Replace Hoses Hoist System | 2027-11-21 | 2027-11-22 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000082902 | 21.11.2027 | 24000 | CCK-MP-HAUL-DT086 -HYDSYS-HDHLF-HSTHO | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Replace Brake System Hoses | 2027-11-21 | 2027-11-23 | 46 hrs | FY28 | 90 | 90010129 | B3 | 1000082908 | 21.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BRHLF-BRHOS | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Brake Cooling System Hoses | 2027-11-21 | 2027-11-22 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000082909 | 21.11.2027 | 24000 | CCK-MP-HAUL-DT086 -BRKSYS-BRHLF-CBRHO | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Transmission | 2027-11-22 | 2027-11-23 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000271871 | 22.11.2027 | 18000 | CCK-MP-HAUL-DT056 -TRNSYS-TRANS | 7400 | 84421 | 8230
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Radiator Fan Hoses | 2027-11-23 | 2027-11-23 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307501 | 23.11.2027 | 12000 | CCK-MP-HAUL-DT127 -ENGINE-COSYS-RADTR | 7400 | 83059 | 54690
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Motor Lube Axle Hoses | 2027-11-23 | 2027-11-23 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000271994 | 23.11.2027 | 12000 | CCK-MP-HAUL-DT127 -FDRSYS-AXLEC-HYM01 | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl AOC Fan Motor Rear | 2027-11-23 | 2027-11-23 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000025046 | 23.11.2027 | 12000 | CCK-MP-HAUL-DT127 -FDRSYS-AXLEC-HYM02 | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Spider Trans Driveshaft | 2027-11-23 | 2027-11-23 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154952 | 23.11.2027 | 6000 | CCK-MP-HAUL-DT127 -FDRSYS-DRSHT-UNVSL | 7400 | 83059 | 9436
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Transmission Oil Cooler | 2027-11-23 | 2027-11-23 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000082993 | 23.11.2027 | 18000 | CCK-MP-HAUL-DT095 -TRNSYS-TROLC | 7400 | 88921 | 28299
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Steering Brake Pump Compensator | 2027-11-25 | 2027-11-25 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204762 | 25.11.2027 | 6000 | CCK-MP-HAUL-DT758 -STRSYS-STPMP | 6800 | 85895 | 10280
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Brake Slack Adjuster Front | 2027-11-25 | 2027-11-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025563 | 25.11.2027 | 20000 | CCK-MP-HAUL-DT137 -BRKSYS-SLACK-SLACF | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Brake Slack Adjuster Rear | 2027-11-25 | 2027-11-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025564 | 25.11.2027 | 20000 | CCK-MP-HAUL-DT137 -BRKSYS-SLACK-SLACR | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Brake Slack Adjuster Front | 2027-11-25 | 2027-11-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000127975 | 25.11.2027 | 20000 | CCK-MP-HAUL-DT221 -BRKSYS-SLACK-SLACF | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Brake Slack Adjuster Rear | 2027-11-25 | 2027-11-25 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000127976 | 25.11.2027 | 20000 | CCK-MP-HAUL-DT221 -BRKSYS-SLACK-SLACR | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Differential | 2027-11-26 | 2027-11-27 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000025747 | 26.11.2027 | 18000 | CCK-MP-HAUL-DT140 -FDRSYS-DIFFL | 7400 | 86767 | 8224
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Steering Linkages | 2027-11-27 | 2027-11-27 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317643 | 27.11.2027 | 15000 | CCK-MP-HAUL-DT155 -STRSYS-STLTR | 7400 | 81407 | 30632
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Replace Steering System Hoses | 2027-11-27 | 2027-11-29 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000091482 | 27.11.2027 | 15000 | CCK-MP-HAUL-DT155 -STRSYS-STHLF-STRHO | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Wheel End RH | 2027-11-27 | 2027-11-28 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000024603 | 27.11.2027 | 24000 | CCK-MP-HAUL-DT095 -FDRSYS-FDRVE-FDRRH | 7400 | 88921 | 14281
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Torque Converter Charge Pump | 2027-11-28 | 2027-11-28 | 6 hrs | FY28 | 6 | 90000901 | B2 | 1000033285 | 28.11.2027 | 22000 | CCK-MP-SUPP-WC224 -TRNSYS-TRPMP-TCCPP | 5000 | 71088 | 15631
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Hub & Spindle LH | 2027-11-28 | 2027-11-28 | 8 hrs | FY28 | 14 | 90000913 | B2 | 1000033301 | 28.11.2027 | 22000 | CCK-MP-SUPP-WC224 -STRUCT-AXLES-HUBLH | 5000 | 71088 | 15543
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Tyre Sense Battery | 2027-11-28 | 2027-11-28 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153141 | 28.11.2027 | 24 Monthly | CCK-MP-HAUL-DT091 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Steering Oil Cooler | 2027-11-29 | 2027-11-29 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000272949 | 29.11.2027 | 15000 | CCK-MP-SUPP-PM0001-STRSYS-STOCO | 3400 | 48287 | 9867
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Hyd Pump Steering & Brake | 2027-11-29 | 2027-11-30 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204430 | 29.11.2027 | 12000 | CCK-MP-HAUL-DT751 -STRSYS-STPMP | 6800 | 86211 | 3654
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Transmission Oil Cooler | 2027-11-29 | 2027-11-29 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000083354 | 29.11.2027 | 18000 | CCK-MP-HAUL-DT5255-TRNSYS-TROLC | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Spider Trans Driveshaft | 2027-11-29 | 2027-11-29 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154920 | 29.11.2027 | 6000 | CCK-MP-HAUL-DT055 -FDRSYS-DRSHT-UNVSL | 7400 | 84122 | 9073
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Engine Midlife Complete | 2027-11-29 | 2027-11-30 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155888 | 29.11.2027 | 12000 | CCK-MP-HAUL-DT058 -ENGINE | 7400 | 87864 | 87864
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Radiator Fan Hoses | 2027-11-29 | 2027-11-29 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307473 | 29.11.2027 | 12000 | CCK-MP-HAUL-DT058 -ENGINE-COSYS-RADTR | 7400 | 87864 | 29310
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Motor Lube Axle Hoses | 2027-11-29 | 2027-11-29 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000271950 | 29.11.2027 | 12000 | CCK-MP-HAUL-DT058 -FDRSYS-AXLEC-HYM01 | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl AOC Fan Motor Rear | 2027-11-29 | 2027-11-29 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000023848 | 29.11.2027 | 12000 | CCK-MP-HAUL-DT058 -FDRSYS-AXLEC-HYM02 | 7400 | 87864 | 1976
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Cyl Steering RH | 2027-11-30 | 2027-11-30 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000094869 | 30.11.2027 | 15000 | CCK-MP-HAUL-DT762 -STRSYS-STRCY-STCYR | 6800 | 76486 | 5778
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Tyre Sense Battery | 2027-11-30 | 2027-11-30 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153191 | 30.11.2027 | 24 Monthly | CCK-MP-HAUL-DT766 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Cyl Steering LH | 2027-11-30 | 2027-11-30 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000024174 | 30.11.2027 | 15000 | CCK-MP-HAUL-DT088 -STRSYS-STRCY-STCYL | 7400 | 89037 | 4765
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Cyl Steering RH | 2027-11-30 | 2027-11-30 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000024175 | 30.11.2027 | 15000 | CCK-MP-HAUL-DT088 -STRSYS-STRCY-STCYR | 7400 | 89037 | 4765
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Operators Seat | 2027-11-30 | 2027-11-30 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000024188 | 30.11.2027 | 15000 | CCK-MP-HAUL-DT088 -STRUCT-CABIN-SEATS | 7400 | 89037 | 4804
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Replace Steering System Hoses | 2027-11-30 | 2027-12-02 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000091394 | 30.11.2027 | 15000 | CCK-MP-HAUL-DT091 -STRSYS-STHLF-STRHO | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Brake Slack Adjuster Front | 2027-12-01 | 2027-12-01 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024864 | 01.12.2027 | 20000 | CCK-MP-HAUL-DT099 -BRKSYS-SLACK-SLACF | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Brake Slack Adjuster Rear | 2027-12-01 | 2027-12-01 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024865 | 01.12.2027 | 20000 | CCK-MP-HAUL-DT099 -BRKSYS-SLACK-SLACR | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Axle Lube Hyd Pump | 2027-12-02 | 2027-12-02 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000154017 | 02.12.2027 | 24000 | CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYPUM | 7400 | 83041 | 14090
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Tyre Sense Battery | 2027-12-02 | 2027-12-02 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153143 | 02.12.2027 | 24 Monthly | CCK-MP-HAUL-DT095 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Grid Box Blower Motor RH | 2027-12-03 | 2027-12-03 | 10 hrs | FY28 | 10 | 90011332 | B1 | 1000094801 | 03.12.2027 | 25000 | CCK-MP-HAUL-DT761 -ELCTHV-HVGBM-GBMRH | 6800 | 78336 | 16076
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Transmisson Calibration | 2027-12-03 | 2027-12-03 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298663 | 03.12.2027 | 4500 | CCK-MP-HAUL-DT055 -TRNSYS-TRANS | 7400 | 84122 | 15848
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Steering System Hoses | 2027-12-04 | 2027-12-06 | 54 hrs | FY28 | 106 | 90010133 | B3 | 1000272723 | 04.12.2027 | 15000 | CCK-MP-SUPP-PM0001-STRSYS-STHLF | 3400 | 48287 | 9818
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Wheel Group Front LH | 2027-12-04 | 2027-12-05 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157135 | 04.12.2027 | 24000 | CCK-MP-HAUL-DT100 -STRUCT-AXLES-HUBLH | 7400 | 87135 | 14184
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Cyl Suspension RHF | 2027-12-04 | 2027-12-06 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067519 | 04.12.2027 | 28000 | CCK-MP-HAUL-DT127 -STRUCT-SUSPN-SCYRF | 7400 | 83059 | 18116
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Tyre Sense Battery | 2027-12-05 | 2027-12-05 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153175 | 05.12.2027 | 24 Monthly | CCK-MP-HAUL-DT5255-MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Auto Lube Pump | 2027-12-05 | 2027-12-05 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285806 | 05.12.2027 | 8000 | CCK-MP-HAUL-DT5314-GRSYST-ALBPP | 7400 | 45898 | 14121
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Motor Brake Oil Cooling | 2027-12-05 | 2027-12-05 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000026877 | 05.12.2027 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BROCO-HYMO1 | 7400 | 83041 | 14033
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Spiders Pump Drive Shaft | 2027-12-05 | 2027-12-05 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000023836 | 05.12.2027 | 18000 | CCK-MP-HAUL-DT058 -ENGINE-PMPDR-DRSHT | 7400 | 87864 | 7850
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Differential | 2027-12-05 | 2027-12-06 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000023844 | 05.12.2027 | 18000 | CCK-MP-HAUL-DT058 -FDRSYS-DIFFL | 7400 | 87864 | 7850
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Replace Hoses Differential System | 2027-12-05 | 2027-12-05 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000081858 | 05.12.2027 | 18000 | CCK-MP-HAUL-DT058 -FDRSYS-DIFFL-DIFHO | 7400 | 87864 | 7715
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Replace Trans TCon System Hoses | 2027-12-05 | 2027-12-06 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000081852 | 05.12.2027 | 18000 | CCK-MP-HAUL-DT058 -TRNSYS-TRANS-TRNHO | 7400 | 87864 | 7691
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Transmisson Calibration | 2027-12-06 | 2027-12-06 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298742 | 06.12.2027 | 4500 | CCK-MP-HAUL-DT223 -TRNSYS-TRANS | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Pump Hoist & Brake | 2027-12-06 | 2027-12-06 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000026163 | 06.12.2027 | 24000 | CCK-MP-HAUL-DT146 -HYDSYS-HOPMP | 7400 | 83108 | 13849
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Spider Trans Driveshaft | 2027-12-07 | 2027-12-07 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154980 | 07.12.2027 | 6000 | CCK-MP-HAUL-DT151 -FDRSYS-DRSHT-UNVSL | 7400 | 84253 | 3168
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Spiders Pump Drive Shaft | 2027-12-07 | 2027-12-07 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000026727 | 07.12.2027 | 18000 | CCK-MP-HAUL-DT155 -ENGINE-PMPDR-DRSHT | 7400 | 81407 | 27996
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Air Con Service & Overhaul | 2027-12-08 | 2027-12-09 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110642 | 08.12.2027 | 12 Monthly | CCK-MP-HAUL-DT773 -STRUCT-CABIN-AIRCN | 6800 | 75884 | 22415
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Spider Trans Driveshaft | 2027-12-08 | 2027-12-08 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000155000 | 08.12.2027 | 6000 | CCK-MP-HAUL-DT223 -FDRSYS-DRSHT-UNVSL | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Cyl Hoist LH | 2027-12-08 | 2027-12-08 | 17 hrs | FY28 | 33 | 90015130 | B1 | 1000128589 | 08.12.2027 | 28000 | CCK-MP-HAUL-DT148 -HYDSYS-HOCYL-HCYLL | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Cyl Suspension LHF | 2027-12-08 | 2027-12-10 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067593 | 08.12.2027 | 28000 | CCK-MP-HAUL-DT148 -STRUCT-SUSPN-SCYLF | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Cyl Suspension RHR | 2027-12-08 | 2027-12-09 | 22 hrs | FY28 | 39 | 90002409 | B2 | 1000026312 | 08.12.2027 | 28000 | CCK-MP-HAUL-DT148 -STRUCT-SUSPN-SCYRR | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Auto Lube Pump | 2027-12-08 | 2027-12-08 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285630 | 08.12.2027 | 8000 | CCK-MP-HAUL-DT090 -GRSYST-ALBPP | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Front Wheel Bearings RH | 2027-12-08 | 2027-12-09 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157208 | 08.12.2027 | 16000 | CCK-MP-HAUL-DT090 -STRUCT-AXLES-FWBRH | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Transmisson Calibration | 2027-12-08 | 2027-12-08 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298727 | 08.12.2027 | 4500 | CCK-MP-HAUL-DT146 -TRNSYS-TRANS | 7400 | 83062 | 12458
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Replace Operator Cabin Dash Bulbs | 2027-12-09 | 2027-12-09 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158239 | 09.12.2027 | 3000 | CCK-MP-HAUL-DT774 -STRUCT-CABIN | 6800 | 81047 | 28490
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Service Air Conditioner 12M | 2027-12-09 | 2027-12-10 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174183 | 09.12.2027 | 12 Monthly | CCK-MP-HAUL-DT157 -STRUCT-CABIN-AIRCN | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Transmission | 2027-12-11 | 2027-12-12 | 22 hrs | FY28 | 39 | 90026996 | B1 | 1000272517 | 11.12.2027 | 18000 | CCK-MP-HAUL-DT5317-TRNSYS-TRANS | 7400 | 45576 | 9163
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Auto Lube Pump | 2027-12-13 | 2027-12-13 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285622 | 13.12.2027 | 8000 | CCK-MP-HAUL-DT054 -GRSYST-ALBPP | 7400 | 88111 | 5197
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Front Wheel Bearings RH | 2027-12-13 | 2027-12-14 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157192 | 13.12.2027 | 16000 | CCK-MP-HAUL-DT054 -STRUCT-AXLES-FWBRH | 7400 | 88110 | 4965
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Auto Lube Pump | 2027-12-14 | 2027-12-14 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285807 | 14.12.2027 | 8000 | CCK-MP-HAUL-DT5315-GRSYST-ALBPP | 7400 | 45392 | 20546
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Transmission Oil Cooler | 2027-12-16 | 2027-12-16 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000091402 | 16.12.2027 | 18000 | CCK-MP-HAUL-DT135 -TRNSYS-TROLC | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Drive Shaft Transmission | 2027-12-16 | 2027-12-16 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154957 | 16.12.2027 | 18000 | CCK-MP-HAUL-DT135 -FDRSYS-DRSHT | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Differential | 2027-12-16 | 2027-12-17 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000025423 | 16.12.2027 | 18000 | CCK-MP-HAUL-DT135 -FDRSYS-DIFFL | 7400 | 82965 | 8025
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Cyl Steering LH | 2027-12-17 | 2027-12-17 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000094550 | 17.12.2027 | 15000 | CCK-MP-HAUL-DT756 -STRSYS-STRCY-STCYL | 6800 | 78754 | 308
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Operator Cabin Dash Bulbs | 2027-12-17 | 2027-12-17 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158237 | 17.12.2027 | 3000 | CCK-MP-HAUL-DT772 -STRUCT-CABIN | 6800 | 85256 | 10385
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Steering HMU | 2027-12-18 | 2027-12-18 | 12 hrs | FY28 | 12 | 90000903 | B2 | 1000033295 | 18.12.2027 | 15000 | CCK-MP-SUPP-WC224 -STRSYS-STHMU | 5000 | 71088 | 8261
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Air Con Service & Overhaul | 2027-12-19 | 2027-12-20 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110634 | 19.12.2027 | 12 Monthly | CCK-MP-HAUL-DT765 -STRUCT-CABIN-AIRCN | 6800 | 78429 | 78429
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Spiders Pump Drive Shaft | 2027-12-19 | 2027-12-19 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000024971 | 19.12.2027 | 18000 | CCK-MP-HAUL-DT126 -ENGINE-PMPDR-DRSHT | 7400 | 88657 | 7775
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Transmission | 2027-12-19 | 2027-12-20 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272321 | 19.12.2027 | 18000 | CCK-MP-HAUL-DT130 -TRNSYS-TRANS | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Transmission Oil Cooler | 2027-12-19 | 2027-12-19 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000083164 | 19.12.2027 | 18000 | CCK-MP-HAUL-DT130 -TRNSYS-TROLC | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Replace Trans TCon System Hoses | 2027-12-19 | 2027-12-20 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090109 | 19.12.2027 | 18000 | CCK-MP-HAUL-DT130 -TRNSYS-TRANS-TRNHO | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Transmission | 2027-12-19 | 2027-12-20 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272323 | 19.12.2027 | 18000 | CCK-MP-HAUL-DT135 -TRNSYS-TRANS | 7400 | 82965 | 7974
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Brake Oil Cooler | 2027-12-20 | 2027-12-20 | 6 hrs | FY28 | 6 | 90018519 | B1 | 1000201178 | 20.12.2027 | 15000 | CCK-MP-SUPP-SV4104-BRKSYS-BROCO | 5100 | 23504 | 7410
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Engine Module | 2027-12-20 | 2027-12-24 | 102 hrs | FY28 | 226 | 90011318 | B1 | 1000094625 | 20.12.2027 | 25000 | CCK-MP-HAUL-DT758 -ENGINE | 6800 | 85895 | 15304
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Auto Lube Pump | 2027-12-21 | 2027-12-21 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095355 | 21.12.2027 | 8000 | CCK-MP-HAUL-DT771 -GRSYST-ALBPP | 6800 | 84423 | 6819
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Pressure Reducing Valve | 2027-12-21 | 2027-12-21 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204843 | 21.12.2027 | 12000 | CCK-MP-HAUL-DT771 -BRKSYS-BRVLV-VVPRV | 6800 | 84423 | 20975
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Replace Operator Cabin Dash Bulbs | 2027-12-21 | 2027-12-21 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158219 | 21.12.2027 | 3000 | CCK-MP-HAUL-DT754 -STRUCT-CABIN | 6800 | 83256 | 83256
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 WaterTank Cannon & Spray Sys Insp | 2027-12-21 | 2027-12-21 | 3 hrs | FY28 | 3 | 90036929 | B1 | 1000368896 | 21.12.2027 | 6 Monthly | CCK-MP-SUPP-WC3111-STRUCT-WTANK | 5600 | 28968 | 28968
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Auto Lube Pump | 2027-12-21 | 2027-12-21 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285635 | 21.12.2027 | 8000 | CCK-MP-HAUL-DT099 -GRSYST-ALBPP | 7400 | 87442 | 14730
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Replace Operator Cabin Dash Bulbs | 2027-12-22 | 2027-12-22 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158236 | 22.12.2027 | 3000 | CCK-MP-HAUL-DT771 -STRUCT-CABIN | 6800 | 84423 | 84423
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Operator Cabin Dash Bulbs | 2027-12-23 | 2027-12-23 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158234 | 23.12.2027 | 3000 | CCK-MP-HAUL-DT769 -STRUCT-CABIN | 6800 | 80508 | 80508
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Suspension LHF | 2027-12-23 | 2027-12-25 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000095414 | 23.12.2027 | 18000 | CCK-MP-HAUL-DT772 -STRUCT-SUSPN-SCYLF | 6800 | 85256 | 10385
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Service Air Conditioner 12M | 2027-12-23 | 2027-12-24 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000172995 | 23.12.2027 | 12 Monthly | CCK-MP-HAUL-DT5313-STRUCT-CABIN-AIRCN | 7400 | 44693 | 44693
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Operators Seat | 2027-12-24 | 2027-12-24 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000024882 | 24.12.2027 | 15000 | CCK-MP-HAUL-DT099 -STRUCT-CABIN-SEATS | 7400 | 87442 | 4777
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Operators Seat | 2027-12-24 | 2027-12-24 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000116243 | 24.12.2027 | 15000 | CCK-MP-HAUL-DT082 -STRUCT-CABIN-SEATS | 7400 | 84375 | 1223
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Replace Operator Cabin Dash Bulbs | 2027-12-25 | 2027-12-25 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158231 | 25.12.2027 | 3000 | CCK-MP-HAUL-DT766 -STRUCT-CABIN | 6800 | 78074 | 10283
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Torque Converter | 2027-12-25 | 2027-12-26 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000025483 | 25.12.2027 | 24000 | CCK-MP-HAUL-DT136 -TRNSYS-TRQUE | 7400 | 87780 | 13860
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Air Con Service & Overhaul | 2027-12-26 | 2027-12-27 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110633 | 26.12.2027 | 12 Monthly | CCK-MP-HAUL-DT764 -STRUCT-CABIN-AIRCN | 6800 | 75315 | 9805
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Transmisson Calibration | 2027-12-26 | 2027-12-26 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298726 | 26.12.2027 | 4500 | CCK-MP-HAUL-DT143 -TRNSYS-TRANS | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Drive Shaft Transmission | 2027-12-27 | 2027-12-27 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154975 | 27.12.2027 | 18000 | CCK-MP-HAUL-DT148 -FDRSYS-DRSHT | 7400 | 85452 | 7645
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Auto Lube Pump | 2027-12-27 | 2027-12-27 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285791 | 27.12.2027 | 8000 | CCK-MP-HAUL-DT150 -GRSYST-ALBPP | 7400 | 86656 | 5319
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Tyre Sense Battery | 2027-12-28 | 2027-12-28 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153190 | 28.12.2027 | 24 Monthly | CCK-MP-HAUL-DT765 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Spider Trans Driveshaft | 2027-12-29 | 2027-12-29 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000155236 | 29.12.2027 | 6000 | CCK-MP-HAUL-DT054 -FDRSYS-DRSHT-UNVSL | 7400 | 88111 | 1222
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Transmisson Calibration | 2027-12-29 | 2027-12-29 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298728 | 29.12.2027 | 4500 | CCK-MP-HAUL-DT147 -TRNSYS-TRANS | 7400 | 84659 | 716
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Transmisson Calibration | 2027-12-29 | 2027-12-29 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298795 | 29.12.2027 | 4500 | CCK-MP-HAUL-DT5255-TRNSYS-TRANS | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Brake Oil Cooler Front | 2027-12-30 | 2027-12-30 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000082869 | 30.12.2027 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BROCO-BROCF | 7400 | 84122 | 13600
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Brake Oil Cooler Rear | 2027-12-30 | 2027-12-30 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000082868 | 30.12.2027 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BROCO-BROCR | 7400 | 84122 | 11329
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Motor Brake Oil Cooling | 2027-12-30 | 2027-12-30 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000023665 | 30.12.2027 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BROCO-HYMO1 | 7400 | 84122 | 13600
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Auto Lube Pump | 2027-12-30 | 2027-12-30 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285627 | 30.12.2027 | 8000 | CCK-MP-HAUL-DT082 -GRSYST-ALBPP | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Wheel Group Front LH | 2027-12-30 | 2027-12-31 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157117 | 30.12.2027 | 24000 | CCK-MP-HAUL-DT086 -STRUCT-AXLES-HUBLH | 7400 | 86822 | 13482
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Wheel Motor Oil RH | 2027-12-31 | 2027-12-31 | 1 hr | FY28 | 1 | 90033606 | B1 | 1000338217 | 31.12.2027 | 25000 | CCK-MP-HAUL-DT760 -FDRSYS-WLMTR-WHMRH | 6800 | 80390 | 15657
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Wheel Motor RH | 2027-12-31 | 2028-01-02 | 45.5 hrs | FY28 | 83.5 | 90011336 | B1 | 1000094752 | 31.12.2027 | 25000 | CCK-MP-HAUL-DT760 -FDRSYS-WLMTR-WHMRH | 6800 | 80390 | 15657
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Radiator Assembly | 2027-12-31 | 2028-01-01 | 22 hrs | FY28 | 40 | 90003977 | B2 | 1000079178 | 31.12.2027 | 20000 | CCK-MP-SUPP-WC3111-ENGINE-COSYS-RADTR | 5600 | 51257 | 11941
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Brake Slack Adjuster Front | 2027-12-31 | 2027-12-31 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167009 | 31.12.2027 | 20000 | CCK-MP-HAUL-DT5314-BRKSYS-SLACK-SLACF | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Brake Slack Adjuster Rear | 2027-12-31 | 2027-12-31 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167010 | 31.12.2027 | 20000 | CCK-MP-HAUL-DT5314-BRKSYS-SLACK-SLACR | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Brake Slack Adjuster Front | 2027-12-31 | 2027-12-31 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026482 | 31.12.2027 | 20000 | CCK-MP-HAUL-DT151 -BRKSYS-SLACK-SLACF | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Brake Slack Adjuster Rear | 2027-12-31 | 2027-12-31 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026483 | 31.12.2027 | 20000 | CCK-MP-HAUL-DT151 -BRKSYS-SLACK-SLACR | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Transmisson Calibration | 2028-01-01 | 2028-01-01 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298816 | 01.01.2028 | 4500 | CCK-MP-HAUL-DT5316-TRNSYS-TRANS | 7400 | 45108 | 15135
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Air Con Service & Overhaul | 2028-01-02 | 2028-01-03 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110632 | 02.01.2028 | 12 Monthly | CCK-MP-HAUL-DT763 -STRUCT-CABIN-AIRCN | 6800 | 74143 | 21626
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Auto Lube Pump | 2028-01-02 | 2028-01-02 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094348 | 02.01.2028 | 8000 | CCK-MP-HAUL-DT752 -GRSYST-ALBPP | 6800 | 80681 | 6552
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Air Con Service & Overhaul | 2028-01-02 | 2028-01-03 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110611 | 02.01.2028 | 12 Monthly | CCK-MP-HAUL-DT751 -STRUCT-CABIN-AIRCN | 6800 | 86211 | 11291
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Operators Seat | 2028-01-02 | 2028-01-02 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000026435 | 02.01.2028 | 15000 | CCK-MP-HAUL-DT150 -STRUCT-CABIN-SEATS | 7400 | 86608 | 4191
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Drive Shaft Transmission | 2028-01-04 | 2028-01-04 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000167217 | 04.01.2028 | 18000 | CCK-MP-HAUL-DT5316-FDRSYS-DRSHT | 7400 | 45108 | 5582
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Spiders Pump Drive Shaft | 2028-01-04 | 2028-01-04 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000024151 | 04.01.2028 | 18000 | CCK-MP-HAUL-DT088 -ENGINE-PMPDR-DRSHT | 7400 | 89037 | 7099
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Spider Trans Driveshaft | 2028-01-04 | 2028-01-04 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154932 | 04.01.2028 | 6000 | CCK-MP-HAUL-DT088 -FDRSYS-DRSHT-UNVSL | 7400 | 89037 | 7099
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Hyd Pump Steering & Brake | 2028-01-05 | 2028-01-06 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204437 | 05.01.2028 | 12000 | CCK-MP-HAUL-DT757 -STRSYS-STPMP | 6800 | 80700 | 14601
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Hub & Spindle LH | 2028-01-05 | 2028-01-06 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000094617 | 05.01.2028 | 18000 | CCK-MP-HAUL-DT757 -STRUCT-AXLES-HUBLH | 6800 | 80700 | 8845
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Hoist RH | 2028-01-05 | 2028-01-05 | 17 hrs | FY28 | 33 | 90015131 | B1 | 1000128558 | 05.01.2028 | 28000 | CCK-MP-HAUL-DT097 -HYDSYS-HOCYL-HCYLR | 7400 | 83804 | 17428
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Wheel Group Front LH | 2028-01-05 | 2028-01-06 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157163 | 05.01.2028 | 24000 | CCK-MP-HAUL-DT149 -STRUCT-AXLES-HUBLH | 7400 | 86975 | 13875
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Cyl Suspension RHR | 2028-01-05 | 2028-01-06 | 22 hrs | FY28 | 39 | 90002409 | B2 | 1000024197 | 05.01.2028 | 28000 | CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYRR | 7400 | 89037 | 17080
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Service Airconditioner | 2028-01-05 | 2028-01-06 | 24 hrs | FY28 | 24 | 90029084 | B1 | 1000290659 | 05.01.2028 | 4500 | CCK-MP-SUPP-WC009 -STRUCT-CABIN-AIRCN | 1500 | 34052 | 2652
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Cyl Steering LH | 2028-01-06 | 2028-01-06 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000094868 | 06.01.2028 | 15000 | CCK-MP-HAUL-DT762 -STRSYS-STRCY-STCYL | 6800 | 76486 | 5076
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Engine Midlife Complete | 2028-01-06 | 2028-01-08 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285532 | 06.01.2028 | 12500 | CCK-MP-HAUL-DT774 -ENGINE | 6800 | 81047 | 3051
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Service Air Conditioner 12M | 2028-01-06 | 2028-01-07 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174161 | 06.01.2028 | 12 Monthly | CCK-MP-HAUL-DT097 -STRUCT-CABIN-AIRCN | 7400 | 83804 | 33534
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Brake Slack Adjuster Front | 2028-01-06 | 2028-01-06 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026350 | 06.01.2028 | 20000 | CCK-MP-HAUL-DT149 -BRKSYS-SLACK-SLACF | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Brake Slack Adjuster Rear | 2028-01-06 | 2028-01-06 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026351 | 06.01.2028 | 20000 | CCK-MP-HAUL-DT149 -BRKSYS-SLACK-SLACR | 7400 | 87258 | 9207
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Pressure Reducing Valve | 2028-01-07 | 2028-01-07 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204788 | 07.01.2028 | 12000 | CCK-MP-HAUL-DT756 -BRKSYS-BRVLV-VVPRV | 6800 | 78754 | 10095
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Seat Operators | 2028-01-07 | 2028-01-07 | 3 hrs | FY28 | 6 | 90004012 | B1 | 1000161836 | 07.01.2028 | 10000 | CCK-MP-SUPP-WC3111-STRUCT-CABIN-SEATS | 5600 | 51257 | 1832
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Steering LH | 2028-01-07 | 2028-01-07 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000024553 | 07.01.2028 | 15000 | CCK-MP-HAUL-DT094 -STRSYS-STRCY-STCYL | 7400 | 88788 | 4191
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Brake Slack Adjuster Front | 2028-01-07 | 2028-01-07 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024612 | 07.01.2028 | 20000 | CCK-MP-HAUL-DT095 -BRKSYS-SLACK-SLACF | 7400 | 88921 | 9465
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Brake Slack Adjuster Rear | 2028-01-07 | 2028-01-07 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024613 | 07.01.2028 | 20000 | CCK-MP-HAUL-DT095 -BRKSYS-SLACK-SLACR | 7400 | 88921 | 9465
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Hyd Pump Steering & Brake | 2028-01-08 | 2028-01-09 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204742 | 08.01.2028 | 12000 | CCK-MP-HAUL-DT762 -STRSYS-STPMP | 6800 | 76486 | 2043
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Steering Brake Pump Compensator | 2028-01-08 | 2028-01-08 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204769 | 08.01.2028 | 6000 | CCK-MP-HAUL-DT765 -STRSYS-STPMP | 6800 | 78429 | 4626
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Pressure Reducing Valve | 2028-01-08 | 2028-01-08 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204797 | 08.01.2028 | 12000 | CCK-MP-HAUL-DT765 -BRKSYS-BRVLV-VVPRV | 6800 | 78429 | 12529
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Replace Operator Cabin Dash Bulbs | 2028-01-08 | 2028-01-08 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158217 | 08.01.2028 | 3000 | CCK-MP-HAUL-DT752 -STRUCT-CABIN | 6800 | 80681 | 80681
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Steering Brake Pump Compensator | 2028-01-08 | 2028-01-08 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204776 | 08.01.2028 | 6000 | CCK-MP-HAUL-DT772 -STRSYS-STPMP | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Steering Brake Pump Compensator | 2028-01-09 | 2028-01-09 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204764 | 09.01.2028 | 6000 | CCK-MP-HAUL-DT760 -STRSYS-STPMP | 6800 | 80390 | 8061
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Replace Operator Cabin Dash Bulbs | 2028-01-09 | 2028-01-09 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158225 | 09.01.2028 | 3000 | CCK-MP-HAUL-DT760 -STRUCT-CABIN | 6800 | 80390 | 80390
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Pressure Reducing Valve | 2028-01-09 | 2028-01-09 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204792 | 09.01.2028 | 12000 | CCK-MP-HAUL-DT760 -BRKSYS-BRVLV-VVPRV | 6800 | 80390 | 27214
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Cyl Steering LH | 2028-01-09 | 2028-01-09 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000026486 | 09.01.2028 | 15000 | CCK-MP-HAUL-DT151 -STRSYS-STRCY-STCYL | 7400 | 84253 | 4338
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Cyl Suspension RHF | 2028-01-09 | 2028-01-11 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067475 | 09.01.2028 | 28000 | CCK-MP-HAUL-DT091 -STRUCT-SUSPN-SCYRF | 7400 | 83859 | 23319
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Tyre Sense Battery | 2028-01-10 | 2028-01-10 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153172 | 10.01.2028 | 24 Monthly | CCK-MP-HAUL-DT222 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Service Air Conditioner 12M | 2028-01-10 | 2028-01-11 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174189 | 10.01.2028 | 12 Monthly | CCK-MP-HAUL-DT222 -STRUCT-CABIN-AIRCN | 7400 | 55735 | 4006
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Cyl Suspension LHF | 2028-01-11 | 2028-01-13 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000094566 | 11.01.2028 | 18000 | CCK-MP-HAUL-DT756 -STRUCT-SUSPN-SCYLF | 6800 | 78754 | 7925
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Axle Lube Hyd Pump | 2028-01-11 | 2028-01-11 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000083223 | 11.01.2028 | 24000 | CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYPUM | 7400 | 84196 | 12732
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Air Con Service & Overhaul | 2028-01-12 | 2028-01-13 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110637 | 12.01.2028 | 12 Monthly | CCK-MP-HAUL-DT768 -STRUCT-CABIN-AIRCN | 6800 | 79837 | 79837
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Engine Cat C175-16 | 2028-01-12 | 2028-01-15 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000155889 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -ENGINE | 7400 | 84374 | 35900
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Radiator Engine Cooling | 2028-01-12 | 2028-01-13 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307474 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -ENGINE-COSYS-RADTR | 7400 | 84374 | 35900
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Motor Lube Axle Rear & Hoses | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271951 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYM01 | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl AOC Fan Motor Rear | 2028-01-12 | 2028-01-12 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000023974 | 12.01.2028 | 12000 | CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYM02 | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Axle Lube Hyd Pump | 2028-01-12 | 2028-01-12 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000082881 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYPUM | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Overhaul Accumulator Brake LHF | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023975 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BACCM-FRLFT | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Overhaul Accumulator Brake RHF | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023976 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BACCM-FRRGT | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Overhaul Accumulator Brake Rear | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023977 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BACCM-BACCR | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Overhaul Valve Control Brake | 2028-01-12 | 2028-01-13 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000023979 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BRVLV | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Motor Brake Oil Cooling | 2028-01-12 | 2028-01-12 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000023980 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BROCO-HYMO1 | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Hyd Pump Steering Main & Fan | 2028-01-12 | 2028-01-12 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000023983 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -STRSYS-STPMP | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Steering HMU | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000023984 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -STRSYS-STHMU | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Ovhl Accumulator Steering Front | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023987 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -STRSYS-STACC-SACCF | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Ovhl Accumulator Steering Middle | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023988 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -STRSYS-STACC-SACCM | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Ovhl Accumulator Steering Rear | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023989 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -STRSYS-STACC-SACCR | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Pump Hoist & Brake | 2028-01-12 | 2028-01-12 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000023991 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -HYDSYS-HOPMP | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Rear Axle Linkages | 2028-01-12 | 2028-01-14 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000024000 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -STRUCT-CHASS-AXLIK | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Wheel Group Front RH | 2028-01-12 | 2028-01-13 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157203 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -STRUCT-AXLES-HUBRH | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Replace Hoses Hoist System | 2028-01-12 | 2028-01-13 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000082883 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -HYDSYS-HDHLF-HSTHO | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Replace Brake System Hoses | 2028-01-12 | 2028-01-14 | 46 hrs | FY28 | 90 | 90010129 | B3 | 1000082889 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BRHLF-BRHOS | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Brake Cooling System Hoses | 2028-01-12 | 2028-01-13 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000082890 | 12.01.2028 | 24000 | CCK-MP-HAUL-DT082 -BRKSYS-BRHLF-CBRHO | 7400 | 84374 | 13167
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Replace Operator Cabin Dash Bulbs | 2028-01-13 | 2028-01-13 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158230 | 13.01.2028 | 3000 | CCK-MP-HAUL-DT765 -STRUCT-CABIN | 6800 | 78429 | 78429
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Suspension LHF | 2028-01-13 | 2028-01-15 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067561 | 13.01.2028 | 28000 | CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYLF | 7400 | 86767 | 17344
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Radiator Engine Cooling | 2028-01-13 | 2028-01-14 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307468 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -ENGINE-COSYS-RADTR | 7400 | 84421 | 36020
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Motor Lube Axle Rear & Hoses | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271945 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -FDRSYS-AXLEC-HYM01 | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl AOC Fan Motor Rear | 2028-01-13 | 2028-01-13 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000023722 | 13.01.2028 | 12000 | CCK-MP-HAUL-DT056 -FDRSYS-AXLEC-HYM02 | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Axle Lube Hyd Pump | 2028-01-13 | 2028-01-13 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000082482 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -FDRSYS-AXLEC-HYPUM | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Overhaul Accumulator Brake LHF | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023723 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BACCM-FRLFT | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Overhaul Accumulator Brake RHF | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023724 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BACCM-FRRGT | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Overhaul Accumulator Brake Rear | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000023725 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BACCM-BACCR | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Overhaul Valve Control Brake | 2028-01-13 | 2028-01-14 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000023727 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BRVLV | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Motor Brake Oil Cooling | 2028-01-13 | 2028-01-13 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000023728 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BROCO-HYMO1 | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Hyd Pump Steering Main & Fan | 2028-01-13 | 2028-01-13 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000023731 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRSYS-STPMP | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Steering HMU | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000023732 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRSYS-STHMU | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Ovhl Accumulator Steering Front | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023735 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRSYS-STACC-SACCF | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Ovhl Accumulator Steering Middle | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023736 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRSYS-STACC-SACCM | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Ovhl Accumulator Steering Rear | 2028-01-13 | 2028-01-13 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023737 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRSYS-STACC-SACCR | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Pump Hoist & Brake | 2028-01-13 | 2028-01-13 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000023739 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -HYDSYS-HOPMP | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Rear Axle Linkages | 2028-01-13 | 2028-01-15 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000023748 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRUCT-CHASS-AXLIK | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Wheel Group Front LH | 2028-01-13 | 2028-01-14 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157109 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRUCT-AXLES-HUBLH | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Wheel Group Front RH | 2028-01-13 | 2028-01-14 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157197 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -STRUCT-AXLES-HUBRH | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Replace Hoses Hoist System | 2028-01-13 | 2028-01-14 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000082484 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -HYDSYS-HDHLF-HSTHO | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Replace Brake System Hoses | 2028-01-13 | 2028-01-15 | 46 hrs | FY28 | 90 | 90010129 | B2 | 1000082490 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BRHLF-BRHOS | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Brake Cooling System Hoses | 2028-01-13 | 2028-01-14 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000082491 | 13.01.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BRHLF-CBRHO | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Overhaul Valve Control Brake | 2028-01-14 | 2028-01-15 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000025496 | 14.01.2028 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-BRVLV | 7400 | 87780 | 39696
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Auto Lube Pump | 2028-01-15 | 2028-01-15 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285794 | 15.01.2028 | 8000 | CCK-MP-HAUL-DT155 -GRSYST-ALBPP | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Front Wheel Bearings LH | 2028-01-15 | 2028-01-16 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157170 | 15.01.2028 | 16000 | CCK-MP-HAUL-DT155 -STRUCT-AXLES-FWBLH | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Front Wheel Bearings RH | 2028-01-15 | 2028-01-16 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157258 | 15.01.2028 | 16000 | CCK-MP-HAUL-DT155 -STRUCT-AXLES-FWBRH | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Operators Seat | 2028-01-16 | 2028-01-16 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000026897 | 16.01.2028 | 15000 | CCK-MP-HAUL-DT157 -STRUCT-CABIN-SEATS | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Service Air Conditioner 12M | 2028-01-17 | 2028-01-18 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174176 | 17.01.2028 | 12 Monthly | CCK-MP-HAUL-DT147 -STRUCT-CABIN-AIRCN | 7400 | 84659 | 12913
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Adjust Engine Valve Set | 2028-01-17 | 2028-01-17 | 6 hrs | FY28 | 6 | 90017451 | B1 | 1000290656 | 17.01.2028 | 3000 | CCK-MP-SUPP-WC008 -ENGINE | 3500 | 51417 | 5947
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Replace Steering System Hoses | 2028-01-17 | 2028-01-19 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000091526 | 17.01.2028 | 15000 | CCK-MP-HAUL-DT157 -STRSYS-STHLF-STRHO | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Steering Hyd Oil Cooler | 2028-01-17 | 2028-01-17 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107012 | 17.01.2028 | 15000 | CCK-MP-HAUL-DT157 -STRSYS-STOCO | 7400 | 83026 | 4183
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Cyl Suspension LHF | 2028-01-18 | 2028-01-20 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000094725 | 18.01.2028 | 18000 | CCK-MP-HAUL-DT759 -STRUCT-SUSPN-SCYLF | 6800 | 79716 | 8626
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Transmission | 2028-01-18 | 2028-01-19 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272359 | 18.01.2028 | 18000 | CCK-MP-HAUL-DT160 -TRNSYS-TRANS | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Transmission Oil Cooler | 2028-01-18 | 2028-01-18 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000091556 | 18.01.2028 | 18000 | CCK-MP-HAUL-DT160 -TRNSYS-TROLC | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Replace Trans TCon System Hoses | 2028-01-18 | 2028-01-19 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000091575 | 18.01.2028 | 18000 | CCK-MP-HAUL-DT160 -TRNSYS-TRANS-TRNHO | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Torque Converter | 2028-01-18 | 2028-01-19 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000025743 | 18.01.2028 | 24000 | CCK-MP-HAUL-DT140 -TRNSYS-TRQUE | 7400 | 86767 | 13213
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Auto Lube Pump | 2028-01-18 | 2028-01-18 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285631 | 18.01.2028 | 8000 | CCK-MP-HAUL-DT091 -GRSYST-ALBPP | 7400 | 83859 | 5241
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Replace Operator Cabin Dash Bulbs | 2028-01-19 | 2028-01-19 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158233 | 19.01.2028 | 3000 | CCK-MP-HAUL-DT768 -STRUCT-CABIN | 6800 | 79837 | 18344
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Pressure Reducing Valve | 2028-01-19 | 2028-01-19 | 4.5 hrs | FY28 | 4.5 | 90019929 | B1 | 1000204786 | 19.01.2028 | 12000 | CCK-MP-HAUL-DT754 -BRKSYS-BRVLV-VVPRV | 6800 | 83256 | 12630
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Overhaul Accumulator Brake RHF | 2028-01-19 | 2028-01-19 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000127970 | 19.01.2028 | 24000 | CCK-MP-HAUL-DT221 -BRKSYS-BACCM-FRRGT | 7400 | 57237 | 36715
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Replace Operator Seat | 2028-01-19 | 2028-01-19 | 3 hrs | FY28 | 6 | 90011567 | B1 | 1000098089 | 19.01.2028 | 6000 | CCK-MP-SUPP-WC220 -STRUCT-CABIN-SEATS | 4300 | 58137 | 5120
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Drive Shaft Transmission | 2028-01-19 | 2028-01-19 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154951 | 19.01.2028 | 18000 | CCK-MP-HAUL-DT126 -FDRSYS-DRSHT | 7400 | 88657 | 7138
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Auto Lube Pump | 2028-01-19 | 2028-01-19 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285629 | 19.01.2028 | 8000 | CCK-MP-HAUL-DT088 -GRSYST-ALBPP | 7400 | 89037 | 1086
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Transmisson Calibration | 2028-01-21 | 2028-01-21 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298721 | 21.01.2028 | 4500 | CCK-MP-HAUL-DT136 -TRNSYS-TRANS | 7400 | 87780 | 9256
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Cyl Steering LH | 2028-01-21 | 2028-01-21 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000167253 | 21.01.2028 | 15000 | CCK-MP-HAUL-DT5317-STRSYS-STRCY-STCYL | 7400 | 45576 | 4261
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Auto Lube Pump | 2028-01-21 | 2028-01-21 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285628 | 21.01.2028 | 8000 | CCK-MP-HAUL-DT086 -GRSYST-ALBPP | 7400 | 86846 | 5030
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 250hr Initial Valve Set | 2028-01-22 | 2028-01-22 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156102 | 22.01.2028 | 250 | CCK-MP-HAUL-DT5202-ENGINE | 7400 | 84333 | 13327
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Steering Link & Arm Rebush | 2028-01-22 | 2028-01-23 | 30 hrs | FY28 | 60 | 90003473 | B2 | 1000039682 | 22.01.2028 | 15000 | CCK-MP-SUPP-WC225 -STRSYS-STLTR | 5000 | 75244 | 7658
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 250hr Initial Valve Set | 2028-01-22 | 2028-01-22 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155988 | 22.01.2028 | 250 | CCK-MP-HAUL-DT138 -ENGINE | 7400 | 82982 | 35790
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Sepura SCC Microphone | 2028-01-23 | 2028-01-23 | 0.5 hrs | FY28 | 0.5 | 90029001 | B1 | 1000289629 | 23.01.2028 | 12 Monthly | CCK-MP-SUPP-WC3112-COMMUN-RADIO | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 WaterTank Cannon & Spray Sys Insp | 2028-01-23 | 2028-01-23 | 3 hrs | FY28 | 3 | 90036929 | B1 | 1000368898 | 23.01.2028 | 6 Monthly | CCK-MP-SUPP-WC3112-STRUCT-WTANK | 5600 | 30406 | 30406
777G WC | Onsite PM | Haul | Fortescue | WC2501 | WC2501 Repl Sepura SCC Microphone | 2028-01-23 | 2028-01-23 | 0.5 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289622 | 23.01.2028 | 12 Monthly | CCK-MP-SUPP-WC2501-COMMUN-RADIO
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Hoist & Rear Brake Pump | 2028-01-24 | 2028-01-24 | 7 hrs | FY28 | 7 | 90004008 | B2 | 1000079275 | 24.01.2028 | 20000 | CCK-MP-SUPP-WC3112-HYDSYS-HOPMP | 5600 | 52240 | 11771
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Replace Hoses Differential System | 2028-01-24 | 2028-01-24 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000090065 | 24.01.2028 | 18000 | CCK-MP-HAUL-DT055 -FDRSYS-DIFFL-DIFHO | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 250hr Initial Valve Set | 2028-01-24 | 2028-01-24 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155892 | 24.01.2028 | 250 | CCK-MP-HAUL-DT082 -ENGINE | 7400 | 84374 | 35900
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Cyl Hoist LH | 2028-01-24 | 2028-01-24 | 17 hrs | FY28 | 33 | 90015130 | B1 | 1000128545 | 24.01.2028 | 28000 | CCK-MP-HAUL-DT086 -HYDSYS-HOCYL-HCYLL | 7400 | 86846 | 16971
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Cyl Hoist RH | 2028-01-24 | 2028-01-24 | 17 hrs | FY28 | 33 | 90015131 | B1 | 1000128546 | 24.01.2028 | 28000 | CCK-MP-HAUL-DT086 -HYDSYS-HOCYL-HCYLR | 7400 | 86846 | 16971
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Steering Brake Pump Compensator | 2028-01-25 | 2028-01-25 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204767 | 25.01.2028 | 6000 | CCK-MP-HAUL-DT763 -STRSYS-STPMP | 6800 | 74143 | 14657
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Replace Operator Cabin Dash Bulbs | 2028-01-25 | 2028-01-25 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158228 | 25.01.2028 | 3000 | CCK-MP-HAUL-DT763 -STRUCT-CABIN | 6800 | 74143 | 74143
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Steering Brake Pump Compensator | 2028-01-25 | 2028-01-25 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204763 | 25.01.2028 | 6000 | CCK-MP-HAUL-DT759 -STRSYS-STPMP | 6800 | 79716 | 8626
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Replace Operator Cabin Dash Bulbs | 2028-01-25 | 2028-01-25 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158224 | 25.01.2028 | 3000 | CCK-MP-HAUL-DT759 -STRUCT-CABIN | 6800 | 79716 | 79716
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Drive Shaft Transmission | 2028-01-25 | 2028-01-25 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154969 | 25.01.2028 | 18000 | CCK-MP-HAUL-DT143 -FDRSYS-DRSHT | 7400 | 88225 | 6845
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Replace Operator Cabin Dash Bulbs | 2028-01-26 | 2028-01-26 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158226 | 26.01.2028 | 3000 | CCK-MP-HAUL-DT761 -STRUCT-CABIN | 6800 | 78336 | 19424
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Engine Midlife Complete | 2028-01-26 | 2028-01-28 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285527 | 26.01.2028 | 12500 | CCK-MP-HAUL-DT769 -ENGINE | 6800 | 80508 | 2589
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Replace Steering System Hoses | 2028-01-26 | 2028-01-28 | 54 hrs | FY28 | 106 | 90010133 | B2 | 1000128083 | 26.01.2028 | 15000 | CCK-MP-HAUL-DT222 -STRSYS-STHLF-STRHO | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Steering Hyd Oil Cooler | 2028-01-26 | 2028-01-26 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000128087 | 26.01.2028 | 15000 | CCK-MP-HAUL-DT222 -STRSYS-STOCO | 7400 | 55736 | 4006
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Cyl Steering RH | 2028-01-26 | 2028-01-26 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000128049 | 26.01.2028 | 15000 | CCK-MP-HAUL-DT222 -STRSYS-STRCY-STCYR | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Tyre Sense Battery | 2028-01-26 | 2028-01-26 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153166 | 26.01.2028 | 24 Monthly | CCK-MP-HAUL-DT157 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Operator Cabin Dash Bulbs | 2028-01-27 | 2028-01-27 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158223 | 27.01.2028 | 3000 | CCK-MP-HAUL-DT758 -STRUCT-CABIN | 6800 | 85895 | 23936
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Replace Trans TCon System Hoses | 2028-01-29 | 2028-01-30 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090064 | 29.01.2028 | 18000 | CCK-MP-HAUL-DT055 -TRNSYS-TRANS-TRNHO | 7400 | 84122 | 30645
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Auto Lube Pump | 2028-01-30 | 2028-01-30 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094613 | 30.01.2028 | 8000 | CCK-MP-HAUL-DT757 -GRSYST-ALBPP | 6800 | 80700 | 14095
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Pump Brake Cool Pump Drive | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 16 | 90026955 | B1 | 1000272693 | 30.01.2028 | 12000 | CCK-MP-SUPP-PM0001-BRKSYS-HYPPP | 3400 | 48287 | 48287
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Repl Sepura SCC Microphone | 2028-01-30 | 2028-01-30 | 0.5 hrs | FY28 | 0.5 | 90029000 | B1 | 1000289611 | 30.01.2028 | 12 Monthly | CCK-MP-SUPP-SV220 -COMMUN-RADIO | 5100 | 58303 | 58303
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Engine Cat C175-16 | 2028-01-30 | 2028-02-02 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000156015 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -ENGINE | 7400 | 84659 | 31850
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Radiator Engine Cooling | 2028-01-30 | 2028-01-31 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307524 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -ENGINE-COSYS-RADTR | 7400 | 84708 | 31850
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Pump Drive | 2028-01-30 | 2028-01-31 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000026198 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -ENGINE-PMPDR | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Torque Converter | 2028-01-30 | 2028-01-31 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000026203 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -TRNSYS-TRQUE | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Wheel End RH | 2028-01-30 | 2028-01-31 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000026209 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -FDRSYS-FDRVE-FDRRH | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Motor Lube Axle Rear & Hoses | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000272013 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYM01 | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl AOC Fan Motor Rear | 2028-01-30 | 2028-01-30 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000026211 | 30.01.2028 | 12000 | CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYM02 | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Overhaul Accumulator Brake LHF | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026212 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BACCM-FRLFT | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Overhaul Accumulator Brake RHF | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026213 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BACCM-FRRGT | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Overhaul Accumulator Brake Rear | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026214 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BACCM-BACCR | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Pump Brake Cooling | 2028-01-30 | 2028-01-30 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000026215 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-HYFPP | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Overhaul Valve Control Brake | 2028-01-30 | 2028-01-31 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000026216 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BRVLV | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Motor Brake Oil Cooling | 2028-01-30 | 2028-01-30 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000026217 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BROCO-HYMO1 | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Hyd Pump Steering Main & Fan | 2028-01-30 | 2028-01-30 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000026220 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -STRSYS-STPMP | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Steering HMU | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000026221 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -STRSYS-STHMU | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Ovhl Accumulator Steering Front | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026224 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -STRSYS-STACC-SACCF | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Ovhl Accumulator Steering Middle | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026225 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -STRSYS-STACC-SACCM | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Ovhl Accumulator Steering Rear | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026226 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -STRSYS-STACC-SACCR | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Rear Axle Linkages | 2028-01-30 | 2028-02-01 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000026238 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -STRUCT-CHASS-AXLIK | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Replace Hoses Hoist System | 2028-01-30 | 2028-01-31 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083396 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -HYDSYS-HDHLF-HSTHO | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Replace Brake System Hoses | 2028-01-30 | 2028-02-01 | 46 hrs | FY28 | 90 | 90010129 | B4 | 1000083402 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BRHLF-BRHOS | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Brake Cooling System Hoses | 2028-01-30 | 2028-01-31 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000083403 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -BRKSYS-BRHLF-CBRHO | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Drive Line Axle LH | 2028-01-30 | 2028-01-30 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124611 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -FDRSYS-DRLAX-AXLLH | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Drive Line Axle RH | 2028-01-30 | 2028-01-30 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124612 | 30.01.2028 | 24000 | CCK-MP-HAUL-DT147 -FDRSYS-DRLAX-AXLRH | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Differential | 2028-01-30 | 2028-01-31 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000023655 | 30.01.2028 | 18000 | CCK-MP-HAUL-DT055 -FDRSYS-DIFFL | 7400 | 84122 | 7096
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Tyre Sense Battery | 2028-01-31 | 2028-01-31 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153198 | 31.01.2028 | 24 Monthly | CCK-MP-HAUL-DT773 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Engine Midlife Complete | 2028-01-31 | 2028-02-01 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155906 | 31.01.2028 | 12000 | CCK-MP-HAUL-DT088 -ENGINE | 7400 | 89037 | 50219
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Operators Seat | 2028-01-31 | 2028-01-31 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000024630 | 31.01.2028 | 15000 | CCK-MP-HAUL-DT095 -STRUCT-CABIN-SEATS | 7400 | 88921 | 3966
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Pump Brake Cooling | 2028-02-01 | 2028-02-01 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000024357 | 01.02.2028 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-HYFPP | 7400 | 83859 | 12875
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Pump Hoist & Brake | 2028-02-01 | 2028-02-01 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000024370 | 01.02.2028 | 24000 | CCK-MP-HAUL-DT091 -HYDSYS-HOPMP | 7400 | 83859 | 12954
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Engine Cat C175-16 | 2028-02-01 | 2028-02-04 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000156009 | 01.02.2028 | 24000 | CCK-MP-HAUL-DT146 -ENGINE | 7400 | 83062 | 31809
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Grid Box Blower Motor LH | 2028-02-02 | 2028-02-02 | 10 hrs | FY28 | 10 | 90011331 | B1 | 1000095436 | 02.02.2028 | 25000 | CCK-MP-HAUL-DT773 -ELCTHV-HVGBM-GBMLH | 6800 | 75884 | 14707
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Drive Shaft Transmission | 2028-02-02 | 2028-02-02 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154959 | 02.02.2028 | 18000 | CCK-MP-HAUL-DT136 -FDRSYS-DRSHT | 7400 | 87780 | 13954
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Auto Lube Pump | 2028-02-03 | 2028-02-03 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094295 | 03.02.2028 | 8000 | CCK-MP-HAUL-DT751 -GRSYST-ALBPP | 6800 | 86211 | 22422
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Wheel End RH | 2028-02-03 | 2028-02-04 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000025749 | 03.02.2028 | 24000 | CCK-MP-HAUL-DT140 -FDRSYS-FDRVE-FDRRH | 7400 | 86767 | 12914
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Auto Lube Pump | 2028-02-03 | 2028-02-03 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285624 | 03.02.2028 | 8000 | CCK-MP-HAUL-DT056 -GRSYST-ALBPP | 7400 | 84421 | 4851
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Pump Hoist | 2028-02-04 | 2028-02-04 | 11.5 hrs | FY28 | 12 | 90011355 | B1 | 1000094873 | 04.02.2028 | 25000 | CCK-MP-HAUL-DT762 -HYDSYS-HOPMP | 6800 | 76486 | 14493
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Cyl Hoist LH | 2028-02-04 | 2028-02-04 | 17 hrs | FY28 | 33 | 90011357 | B1 | 1000094875 | 04.02.2028 | 25000 | CCK-MP-HAUL-DT762 -HYDSYS-HOCYL-HCYLL | 6800 | 76486 | 14493
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Wheel Group Front RH | 2028-02-04 | 2028-02-05 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157245 | 04.02.2028 | 24000 | CCK-MP-HAUL-DT146 -STRUCT-AXLES-HUBRH | 7400 | 83061 | 12458
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Suspension LHR | 2028-02-05 | 2028-02-06 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000026245 | 05.02.2028 | 28000 | CCK-MP-HAUL-DT147 -STRUCT-SUSPN-SCYLR | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Transmisson Calibration | 2028-02-05 | 2028-02-05 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298678 | 05.02.2028 | 4500 | CCK-MP-HAUL-DT127 -TRNSYS-TRANS | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Tyre Sense Battery | 2028-02-06 | 2028-02-06 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153173 | 06.02.2028 | 24 Monthly | CCK-MP-HAUL-DT223 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Service Air Conditioner 12M | 2028-02-06 | 2028-02-07 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174190 | 06.02.2028 | 12 Monthly | CCK-MP-HAUL-DT223 -STRUCT-CABIN-AIRCN | 7400 | 54920 | 3706
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Air Con Service & Overhaul | 2028-02-07 | 2028-02-08 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110624 | 07.02.2028 | 12 Monthly | CCK-MP-HAUL-DT755 -STRUCT-CABIN-AIRCN | 6800 | 84587 | 57456
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Engine Cat C175-16 | 2028-02-08 | 2028-02-11 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000161145 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -ENGINE | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Radiator Engine Cooling | 2028-02-08 | 2028-02-09 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307496 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -ENGINE-COSYS-RADTR | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Pump Drive | 2028-02-08 | 2028-02-09 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000024907 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -ENGINE-PMPDR | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Wheel End LH | 2028-02-08 | 2028-02-09 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000024917 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -FDRSYS-FDRVE-FDRLH | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Motor Lube Axle Rear & Hoses | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271989 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYM01 | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl AOC Fan Motor Rear | 2028-02-08 | 2028-02-08 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024920 | 08.02.2028 | 12000 | CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYM02 | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Axle Lube Hyd Pump | 2028-02-08 | 2028-02-08 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000083071 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYPUM | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Overhaul Accumulator Brake LHF | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024921 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BACCM-FRLFT | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Overhaul Accumulator Brake RHF | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024922 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BACCM-FRRGT | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Overhaul Accumulator Brake Rear | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024923 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BACCM-BACCR | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Overhaul Valve Control Brake | 2028-02-08 | 2028-02-09 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000024925 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BRVLV | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Motor Brake Oil Cooling | 2028-02-08 | 2028-02-08 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000024926 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BROCO-HYMO1 | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Hyd Pump Steering Main & Fan | 2028-02-08 | 2028-02-08 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000024929 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -STRSYS-STPMP | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Steering HMU | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000116246 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -STRSYS-STHMU | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Ovhl Accumulator Steering Front | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024933 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -STRSYS-STACC-SACCF | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Ovhl Accumulator Steering Middle | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024934 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -STRSYS-STACC-SACCM | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Ovhl Accumulator Steering Rear | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024935 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -STRSYS-STACC-SACCR | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Pump Hoist & Brake | 2028-02-08 | 2028-02-08 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000024937 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -HYDSYS-HOPMP | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Rear Axle Linkages | 2028-02-08 | 2028-02-10 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000024946 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -STRUCT-CHASS-AXLIK | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Replace Hoses Hoist System | 2028-02-08 | 2028-02-09 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083073 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -HYDSYS-HDHLF-HSTHO | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Replace Brake System Hoses | 2028-02-08 | 2028-02-10 | 46 hrs | FY28 | 90 | 90010129 | B3 | 1000083079 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -BRKSYS-BRHLF-BRHOS | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Drive Line Axle LH | 2028-02-08 | 2028-02-08 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000126190 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -FDRSYS-DRLAX-AXLLH | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Drive Line Axle RH | 2028-02-08 | 2028-02-08 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000126189 | 08.02.2028 | 24000 | CCK-MP-HAUL-DT100 -FDRSYS-DRLAX-AXLRH | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Transmission | 2028-02-08 | 2028-02-09 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272331 | 08.02.2028 | 18000 | CCK-MP-HAUL-DT140 -TRNSYS-TRANS | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Drive Shaft Transmission | 2028-02-08 | 2028-02-08 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154965 | 08.02.2028 | 18000 | CCK-MP-HAUL-DT140 -FDRSYS-DRSHT | 7400 | 86767 | 9442
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Replace Trans TCon System Hoses | 2028-02-08 | 2028-02-09 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090127 | 08.02.2028 | 18000 | CCK-MP-HAUL-DT140 -TRNSYS-TRANS-TRNHO | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Replace Hoses Differential System | 2028-02-08 | 2028-02-08 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000090128 | 08.02.2028 | 18000 | CCK-MP-HAUL-DT140 -FDRSYS-DIFFL-DIFHO | 7400 | 86767 | 6817
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Steering Brake Pump Compensator | 2028-02-09 | 2028-02-09 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204757 | 09.02.2028 | 6000 | CCK-MP-HAUL-DT753 -STRSYS-STPMP | 6800 | 85999 | 7576
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Replace Trans TCon System Hoses | 2028-02-09 | 2028-02-10 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090151 | 09.02.2028 | 18000 | CCK-MP-HAUL-DT150 -TRNSYS-TRANS-TRNHO | 7400 | 86608 | 33066
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Replace Hoses Differential System | 2028-02-09 | 2028-02-09 | 5 hrs | FY28 | 5 | 90010101 | B2 | 1000090152 | 09.02.2028 | 18000 | CCK-MP-HAUL-DT150 -FDRSYS-DIFFL-DIFHO | 7400 | 86608 | 33066
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Replace Trans TCon System Hoses | 2028-02-10 | 2028-02-11 | 20 hrs | FY28 | 20 | 90010099 | B3 | 1000166957 | 10.02.2028 | 18000 | CCK-MP-HAUL-DT5313-TRNSYS-TRANS-TRNHO | 7400 | 44693 | 25140
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Auto Lube Pump | 2028-02-10 | 2028-02-10 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285637 | 10.02.2028 | 8000 | CCK-MP-HAUL-DT126 -GRSYST-ALBPP | 7400 | 88657 | 14100
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Front Wheel Bearings RH | 2028-02-10 | 2028-02-11 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157194 | 10.02.2028 | 16000 | CCK-MP-HAUL-DT055 -STRUCT-AXLES-FWBRH | 7400 | 84122 | 4767
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 250hr Initial Valve Set | 2028-02-11 | 2028-02-11 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156018 | 11.02.2028 | 250 | CCK-MP-HAUL-DT147 -ENGINE | 7400 | 84659 | 31850
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Transmisson Calibration | 2028-02-11 | 2028-02-11 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298666 | 11.02.2028 | 4500 | CCK-MP-HAUL-DT058 -TRNSYS-TRANS | 7400 | 87864 | 1976
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Overhaul Service Tank Module | 2028-02-12 | 2028-02-12 | 1 hr | FY28 | 1 | 90028957 | B1 | 1000288854 | 12.02.2028 | 36000 | CCK-MP-SUPP-SV221 -STRUCT-SVTNK | 5100 | 64374 | 4253
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Suspension LHR | 2028-02-12 | 2028-02-13 | 32 hrs | FY28 | 50 | 90011367 | B1 | 1000094674 | 12.02.2028 | 25000 | CCK-MP-HAUL-DT758 -STRUCT-SUSPN-SCYLR | 6800 | 85895 | 14688
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Transmission Oil Cooler | 2028-02-12 | 2028-02-12 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000083430 | 12.02.2028 | 18000 | CCK-MP-HAUL-DT150 -TRNSYS-TROLC | 7400 | 86608 | 6426
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Air Con Service & Overhaul | 2028-02-13 | 2028-02-14 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110627 | 13.02.2028 | 12 Monthly | CCK-MP-HAUL-DT758 -STRUCT-CABIN-AIRCN | 6800 | 85895 | 34467
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Tyre Sense Battery | 2028-02-14 | 2028-02-14 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153186 | 14.02.2028 | 24 Monthly | CCK-MP-HAUL-DT761 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Wheel Group Front RH | 2028-02-14 | 2028-02-15 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157231 | 14.02.2028 | 24000 | CCK-MP-HAUL-DT135 -STRUCT-AXLES-HUBRH | 7400 | 82965 | 12818
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Suspension RHF | 2028-02-14 | 2028-02-16 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067543 | 14.02.2028 | 28000 | CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYRF | 7400 | 82965 | 12818
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 250hr Initial Valve Set | 2028-02-14 | 2028-02-14 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156012 | 14.02.2028 | 250 | CCK-MP-HAUL-DT146 -ENGINE | 7400 | 83062 | 31809
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Differential | 2028-02-14 | 2028-02-15 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000026405 | 14.02.2028 | 18000 | CCK-MP-HAUL-DT150 -FDRSYS-DIFFL | 7400 | 86656 | 6426
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Spider Trans Driveshaft | 2028-02-15 | 2028-02-15 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154996 | 15.02.2028 | 6000 | CCK-MP-HAUL-DT221 -FDRSYS-DRSHT-UNVSL | 7400 | 57237 | 5640
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Spiders Pump Drive Shaft | 2028-02-15 | 2028-02-15 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000166914 | 15.02.2028 | 18000 | CCK-MP-HAUL-DT5313-ENGINE-PMPDR-DRSHT | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Transmission | 2028-02-15 | 2028-02-16 | 22 hrs | FY28 | 39 | 90026996 | B1 | 1000272509 | 15.02.2028 | 18000 | CCK-MP-HAUL-DT5313-TRNSYS-TRANS | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Transmission Oil Cooler | 2028-02-15 | 2028-02-15 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000166948 | 15.02.2028 | 18000 | CCK-MP-HAUL-DT5313-TRNSYS-TROLC | 7400 | 44693 | 6773
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Tyre Sense Battery | 2028-02-16 | 2028-02-16 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153188 | 16.02.2028 | 24 Monthly | CCK-MP-HAUL-DT763 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Tyre Sense Battery | 2028-02-16 | 2028-02-16 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153180 | 16.02.2028 | 24 Monthly | CCK-MP-HAUL-DT755 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Spider Trans Driveshaft | 2028-02-16 | 2028-02-16 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154922 | 16.02.2028 | 6000 | CCK-MP-HAUL-DT056 -FDRSYS-DRSHT-UNVSL | 7400 | 84421 | 11711
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Auto Lube Pump | 2028-02-17 | 2028-02-17 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285636 | 17.02.2028 | 8000 | CCK-MP-HAUL-DT100 -GRSYST-ALBPP | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Brake Slack Adjuster Front | 2028-02-17 | 2028-02-17 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167249 | 17.02.2028 | 20000 | CCK-MP-HAUL-DT5317-BRKSYS-SLACK-SLACF | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Brake Slack Adjuster Rear | 2028-02-17 | 2028-02-17 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167250 | 17.02.2028 | 20000 | CCK-MP-HAUL-DT5317-BRKSYS-SLACK-SLACR | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Radiator Engine Cooling | 2028-02-17 | 2028-02-18 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307522 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -ENGINE-COSYS-RADTR | 7400 | 83108 | 66584
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Pump Drive | 2028-02-17 | 2028-02-18 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000026132 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -ENGINE-PMPDR | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Motor Lube Axle Rear & Hoses | 2028-02-17 | 2028-02-17 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000272011 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYM01 | 7400 | 83108 | 0
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl AOC Fan Motor Rear | 2028-02-17 | 2028-02-17 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000026145 | 17.02.2028 | 12000 | CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYM02 | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Axle Lube Hyd Pump | 2028-02-17 | 2028-02-17 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000154013 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYPUM | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Overhaul Accumulator Brake LHF | 2028-02-17 | 2028-02-17 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026146 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BACCM-FRLFT | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Overhaul Accumulator Brake RHF | 2028-02-17 | 2028-02-17 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026147 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BACCM-FRRGT | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Overhaul Accumulator Brake Rear | 2028-02-17 | 2028-02-17 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026148 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BACCM-BACCR | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Overhaul Valve Control Brake | 2028-02-17 | 2028-02-18 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000026150 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BRVLV | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Motor Brake Oil Cooling | 2028-02-17 | 2028-02-17 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000026151 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -BRKSYS-BROCO-HYMO1 | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Ovhl Accumulator Steering Front | 2028-02-17 | 2028-02-17 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026158 | 17.02.2028 | 24000 | CCK-MP-HAUL-DT146 -STRSYS-STACC-SACCF | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Spider Trans Driveshaft | 2028-02-17 | 2028-02-17 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154970 | 17.02.2028 | 6000 | CCK-MP-HAUL-DT146 -FDRSYS-DRSHT-UNVSL | 7400 | 83062 | 26
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Cyl Steering LH | 2028-02-18 | 2028-02-18 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000094974 | 18.02.2028 | 15000 | CCK-MP-HAUL-DT764 -STRSYS-STRCY-STCYL | 6800 | 75315 | 20592
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Cyl Steering RH | 2028-02-18 | 2028-02-18 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000094975 | 18.02.2028 | 15000 | CCK-MP-HAUL-DT764 -STRSYS-STRCY-STCYR | 6800 | 75315 | 20592
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Replace Steering System Hoses | 2028-02-18 | 2028-02-20 | 54 hrs | FY28 | 106 | 90010133 | B2 | 1000128152 | 18.02.2028 | 15000 | CCK-MP-HAUL-DT223 -STRSYS-STHLF-STRHO | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Steering Hyd Oil Cooler | 2028-02-18 | 2028-02-18 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000128156 | 18.02.2028 | 15000 | CCK-MP-HAUL-DT223 -STRSYS-STOCO | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Engine Cat C175-16 | 2028-02-18 | 2028-02-21 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000155871 | 18.02.2028 | 24000 | CCK-MP-HAUL-DT056 -ENGINE | 7400 | 84421 | 36020
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Wheel Group Front RH | 2028-02-18 | 2028-02-19 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157253 | 18.02.2028 | 24000 | CCK-MP-HAUL-DT150 -STRUCT-AXLES-HUBRH | 7400 | 86608 | 12303
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Tyre Sense Battery | 2028-02-19 | 2028-02-19 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153146 | 19.02.2028 | 24 Monthly | CCK-MP-HAUL-DT099 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Drive Shaft Transmission | 2028-02-19 | 2028-02-19 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000166977 | 19.02.2028 | 18000 | CCK-MP-HAUL-DT5313-FDRSYS-DRSHT | 7400 | 44693 | 25164
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Cyl Hoist RH | 2028-02-20 | 2028-02-20 | 17 hrs | FY28 | 33 | 90011358 | B1 | 1000094611 | 20.02.2028 | 25000 | CCK-MP-HAUL-DT757 -HYDSYS-HOCYL-HCYLR | 6800 | 80700 | 14647
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Auto Lube Pump | 2028-02-20 | 2028-02-20 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094772 | 20.02.2028 | 8000 | CCK-MP-HAUL-DT760 -GRSYST-ALBPP | 6800 | 80390 | 11271
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Air Con Service & Overhaul | 2028-02-20 | 2028-02-21 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110635 | 20.02.2028 | 12 Monthly | CCK-MP-HAUL-DT766 -STRUCT-CABIN-AIRCN | 6800 | 78074 | 78074
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Tyre Sense Battery | 2028-02-20 | 2028-02-20 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153194 | 20.02.2028 | 24 Monthly | CCK-MP-HAUL-DT769 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 250hr Initial Valve Set | 2028-02-20 | 2028-02-20 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000161149 | 20.02.2028 | 250 | CCK-MP-HAUL-DT100 -ENGINE | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Hyd Pump Steering Main & Fan | 2028-02-20 | 2028-02-20 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000026154 | 20.02.2028 | 24000 | CCK-MP-HAUL-DT146 -STRSYS-STPMP | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Steering HMU | 2028-02-20 | 2028-02-20 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000026155 | 20.02.2028 | 24000 | CCK-MP-HAUL-DT146 -STRSYS-STHMU | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Ovhl Accumulator Steering Middle | 2028-02-20 | 2028-02-20 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026159 | 20.02.2028 | 24000 | CCK-MP-HAUL-DT146 -STRSYS-STACC-SACCM | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Ovhl Accumulator Steering Rear | 2028-02-20 | 2028-02-20 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026160 | 20.02.2028 | 24000 | CCK-MP-HAUL-DT146 -STRSYS-STACC-SACCR | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Replace Hoses Hoist System | 2028-02-20 | 2028-02-21 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000091428 | 20.02.2028 | 24000 | CCK-MP-HAUL-DT146 -HYDSYS-HDHLF-HSTHO | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Drive Line Axle LH | 2028-02-20 | 2028-02-20 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124609 | 20.02.2028 | 24000 | CCK-MP-HAUL-DT146 -FDRSYS-DRLAX-AXLLH | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Drive Line Axle RH | 2028-02-20 | 2028-02-20 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124610 | 20.02.2028 | 24000 | CCK-MP-HAUL-DT146 -FDRSYS-DRLAX-AXLRH | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Transmisson Calibration | 2028-02-20 | 2028-02-20 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298737 | 20.02.2028 | 4500 | CCK-MP-HAUL-DT159 -TRNSYS-TRANS | 7400 | 90235 | 15586
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Operator Seat | 2028-02-21 | 2028-02-21 | 3 hrs | FY28 | 6 | 90011567 | B1 | 1000098153 | 21.02.2028 | 6000 | CCK-MP-SUPP-SV221 -STRUCT-CABIN-SEATS | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Transmission | 2028-02-21 | 2028-02-22 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272341 | 21.02.2028 | 18000 | CCK-MP-HAUL-DT148 -TRNSYS-TRANS | 7400 | 85451 | 10451
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Ovhl Accumulator Steering Rear | 2028-02-21 | 2028-02-21 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023674 | 21.02.2028 | 24000 | CCK-MP-HAUL-DT055 -STRSYS-STACC-SACCR | 7400 | 84122 | 12545
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Service Air Conditioner 12M | 2028-02-22 | 2028-02-23 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174184 | 22.02.2028 | 12 Monthly | CCK-MP-HAUL-DT158 -STRUCT-CABIN-AIRCN | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Transmisson Calibration | 2028-02-23 | 2028-02-23 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298662 | 23.02.2028 | 4500 | CCK-MP-HAUL-DT054 -TRNSYS-TRANS | 7400 | 88111 | 15675
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Air Con Service & Overhaul | 2028-02-23 | 2028-02-24 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110626 | 23.02.2028 | 12 Monthly | CCK-MP-HAUL-DT757 -STRUCT-CABIN-AIRCN | 6800 | 80700 | 25834
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Engine Midlife Complete | 2028-02-23 | 2028-02-25 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285524 | 23.02.2028 | 12500 | CCK-MP-HAUL-DT766 -ENGINE | 6800 | 78074 | 3021
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Pump Hoist | 2028-02-23 | 2028-02-23 | 11.5 hrs | FY28 | 12 | 90011355 | B1 | 1000094502 | 23.02.2028 | 25000 | CCK-MP-HAUL-DT755 -HYDSYS-HOPMP | 6800 | 84587 | 14505
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Tyre Sense Battery | 2028-02-23 | 2028-02-23 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153163 | 23.02.2028 | 24 Monthly | CCK-MP-HAUL-DT151 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Cyl Steering RH | 2028-02-24 | 2028-02-24 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000095028 | 24.02.2028 | 15000 | CCK-MP-HAUL-DT765 -STRSYS-STRCY-STCYR | 6800 | 78429 | 12529
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Service Air Conditioner 12M | 2028-02-24 | 2028-02-25 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174164 | 24.02.2028 | 12 Monthly | CCK-MP-HAUL-DT100 -STRUCT-CABIN-AIRCN | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Transmission Oil Cooler | 2028-02-24 | 2028-02-24 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000091446 | 24.02.2028 | 18000 | CCK-MP-HAUL-DT148 -TRNSYS-TROLC | 7400 | 85451 | 6450
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Operator Cabin Dash Bulbs | 2028-02-25 | 2028-02-25 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158220 | 25.02.2028 | 3000 | CCK-MP-HAUL-DT755 -STRUCT-CABIN | 6800 | 84587 | 84587
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Transmisson Calibration | 2028-02-25 | 2028-02-25 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298736 | 25.02.2028 | 4500 | CCK-MP-HAUL-DT158 -TRNSYS-TRANS | 7400 | 85964 | 11104
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Air Con Service & Overhaul | 2028-02-26 | 2028-02-27 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110641 | 26.02.2028 | 12 Monthly | CCK-MP-HAUL-DT772 -STRUCT-CABIN-AIRCN | 6800 | 85256 | 35729
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Steering Valve | 2028-02-26 | 2028-02-26 | 6 hrs | FY28 | 12 | 90000918 | B2 | 1000033296 | 26.02.2028 | 22000 | CCK-MP-SUPP-WC224 -STRSYS-STVLV | 5000 | 71088 | 14301
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Operators Seat | 2028-02-26 | 2028-02-26 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000026369 | 26.02.2028 | 15000 | CCK-MP-HAUL-DT149 -STRUCT-CABIN-SEATS | 7400 | 86975 | 3465
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Tyre Sense Battery | 2028-02-26 | 2028-02-26 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153142 | 26.02.2028 | 24 Monthly | CCK-MP-HAUL-DT094 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Hub & Spindle LH | 2028-02-27 | 2028-02-28 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000095253 | 27.02.2028 | 18000 | CCK-MP-HAUL-DT769 -STRUCT-AXLES-HUBLH | 6800 | 80508 | 7418
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Cyl Suspension LHF | 2028-02-27 | 2028-02-29 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000095255 | 27.02.2028 | 18000 | CCK-MP-HAUL-DT769 -STRUCT-SUSPN-SCYLF | 6800 | 80508 | 7418
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Auto Lube Pump | 2028-02-27 | 2028-02-27 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285792 | 27.02.2028 | 8000 | CCK-MP-HAUL-DT151 -GRSYST-ALBPP | 7400 | 84301 | 13358
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Auto Lube Pump | 2028-02-27 | 2028-02-27 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285789 | 27.02.2028 | 8000 | CCK-MP-HAUL-DT148 -GRSYST-ALBPP | 7400 | 85452 | 20768
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Transmission | 2028-02-27 | 2028-02-28 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272307 | 27.02.2028 | 18000 | CCK-MP-HAUL-DT094 -TRNSYS-TRANS | 7400 | 88788 | 5404
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Transmisson Calibration | 2028-02-27 | 2028-02-27 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298731 | 27.02.2028 | 4500 | CCK-MP-HAUL-DT150 -TRNSYS-TRANS | 7400 | 86608 | 14649
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Cyl Steering LH | 2028-02-27 | 2028-02-27 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000027014 | 27.02.2028 | 15000 | CCK-MP-HAUL-DT159 -STRSYS-STRCY-STCYL | 7400 | 90235 | 3490
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Cyl Steering RH | 2028-02-27 | 2028-02-27 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000027015 | 27.02.2028 | 15000 | CCK-MP-HAUL-DT159 -STRSYS-STRCY-STCYR | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Replace Steering System Hoses | 2028-02-27 | 2028-02-29 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000083539 | 27.02.2028 | 15000 | CCK-MP-HAUL-DT159 -STRSYS-STHLF-STRHO | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Steering Hyd Oil Cooler | 2028-02-27 | 2028-02-27 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107028 | 27.02.2028 | 15000 | CCK-MP-HAUL-DT159 -STRSYS-STOCO | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Transmisson Calibration | 2028-02-28 | 2028-02-28 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298665 | 28.02.2028 | 4500 | CCK-MP-HAUL-DT057 -TRNSYS-TRANS | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Transmisson Calibration | 2028-02-28 | 2028-02-28 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298677 | 28.02.2028 | 4500 | CCK-MP-HAUL-DT126 -TRNSYS-TRANS | 7400 | 88657 | 2432
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Accumulator Hyd Steer Front | 2028-03-01 | 2028-03-01 | 7.5 hrs | FY28 | 11.5 | 90011352 | B1 | 1000095188 | 01.03.2028 | 25000 | CCK-MP-HAUL-DT768 -STRSYS-STACC-SACCF | 6800 | 79837 | 14167
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Brake Slack Adjuster Front | 2028-03-01 | 2028-03-01 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167089 | 01.03.2028 | 20000 | CCK-MP-HAUL-DT5315-BRKSYS-SLACK-SLACF | 7400 | 45392 | 8391
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Brake Slack Adjuster Rear | 2028-03-01 | 2028-03-01 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167090 | 01.03.2028 | 20000 | CCK-MP-HAUL-DT5315-BRKSYS-SLACK-SLACR | 7400 | 45392 | 8391
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 250hr Initial Valve Set | 2028-03-01 | 2028-03-01 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155874 | 01.03.2028 | 250 | CCK-MP-HAUL-DT056 -ENGINE | 7400 | 84421 | 36020
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Auto Lube Pump | 2028-03-02 | 2028-03-02 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094719 | 02.03.2028 | 8000 | CCK-MP-HAUL-DT759 -GRSYST-ALBPP | 6800 | 79716 | 16971
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Tyre Sense Battery | 2028-03-03 | 2028-03-03 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153189 | 03.03.2028 | 24 Monthly | CCK-MP-HAUL-DT764 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Brake Accumulator Rear | 2028-03-03 | 2028-03-03 | 7 hrs | FY28 | 11 | 90011339 | B1 | 1000094543 | 03.03.2028 | 25000 | CCK-MP-HAUL-DT756 -BRKSYS-BRACC-BACCR | 6800 | 78754 | 13888
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Tyre Sense Battery | 2028-03-03 | 2028-03-03 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153153 | 03.03.2028 | 24 Monthly | CCK-MP-HAUL-DT137 -MANGMT-TYRSN
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Inspect Rear Axle Housing | 2028-03-03 | 2028-03-03 | 1 hr | FY28 | 1 | 90019256 | B1 | 1000196434 | 03.03.2028 | 2000 | CCK-MP-SUPP-WC224 -STRUCT-RAXHO | 5000 | 71088 | 71088
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Suspension RHR | 2028-03-04 | 2028-03-05 | 22 hrs | FY28 | 39 | 90002409 | B2 | 1000025982 | 04.03.2028 | 28000 | CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYRR | 7400 | 88225 | 16214
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Brake Oil Cooler Rear | 2028-03-04 | 2028-03-04 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083362 | 04.03.2028 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BROCO-BROCR | 7400 | 87580 | 8253
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Brake Manifold | 2028-03-05 | 2028-03-05 | 13.5 hrs | FY28 | 13.5 | 90029265 | B1 | 1000292157 | 05.03.2028 | 25000 | CCK-MP-HAUL-DT761 -BRKSYS-BRVLV | 6800 | 78336 | 14347
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Steering Bleed Down Manifold | 2028-03-05 | 2028-03-05 | 6.5 hrs | FY28 | 8 | 90011347 | B1 | 1000094812 | 05.03.2028 | 25000 | CCK-MP-HAUL-DT761 -STRSYS-STBDM | 6800 | 78336 | 14347
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Auto Lube Pump | 2028-03-05 | 2028-03-05 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285795 | 05.03.2028 | 8000 | CCK-MP-HAUL-DT157 -GRSYST-ALBPP | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Front Wheel Bearings RH | 2028-03-05 | 2028-03-06 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157260 | 05.03.2028 | 16000 | CCK-MP-HAUL-DT157 -STRUCT-AXLES-FWBRH | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Steering LH | 2028-03-06 | 2028-03-06 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000026222 | 06.03.2028 | 15000 | CCK-MP-HAUL-DT147 -STRSYS-STRCY-STCYL | 7400 | 84659 | 3326
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Brake Slack Adjuster Front | 2028-03-07 | 2028-03-07 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026020 | 07.03.2028 | 20000 | CCK-MP-HAUL-DT5255-BRKSYS-SLACK-SLACF | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Brake Slack Adjuster Rear | 2028-03-07 | 2028-03-07 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000026021 | 07.03.2028 | 20000 | CCK-MP-HAUL-DT5255-BRKSYS-SLACK-SLACR | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Auto Lube Pump | 2028-03-07 | 2028-03-07 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285809 | 07.03.2028 | 8000 | CCK-MP-HAUL-DT5317-GRSYST-ALBPP | 7400 | 45576 | 12321
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Steering Linkages | 2028-03-07 | 2028-03-07 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317639 | 07.03.2028 | 15000 | CCK-MP-HAUL-DT151 -STRSYS-STLTR | 7400 | 84253 | 13409
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Steering Linkages | 2028-03-07 | 2028-03-07 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317601 | 07.03.2028 | 15000 | CCK-MP-HAUL-DT095 -STRSYS-STLTR | 7400 | 88921 | 33241
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Tyre Sense Battery | 2028-03-08 | 2028-03-08 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153199 | 08.03.2028 | 24 Monthly | CCK-MP-HAUL-DT774 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Auto Lube Pump | 2028-03-08 | 2028-03-08 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285787 | 08.03.2028 | 8000 | CCK-MP-HAUL-DT146 -GRSYST-ALBPP | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Suspension LHR | 2028-03-08 | 2028-03-09 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000026179 | 08.03.2028 | 28000 | CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYLR | 7400 | 83062 | 16107
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Suspension RHR | 2028-03-08 | 2028-03-09 | 22 hrs | FY28 | 39 | 90002409 | B2 | 1000026180 | 08.03.2028 | 28000 | CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYRR | 7400 | 83062 | 16042
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Engine Midlife Complete | 2028-03-09 | 2028-03-11 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285526 | 09.03.2028 | 12500 | CCK-MP-HAUL-DT768 -ENGINE | 6800 | 79837 | 27373
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Air Con Service & Overhaul | 2028-03-09 | 2028-03-10 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110638 | 09.03.2028 | 12 Monthly | CCK-MP-HAUL-DT769 -STRUCT-CABIN-AIRCN | 6800 | 80508 | 36906
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Engine Cat C175-16 | 2028-03-09 | 2028-03-12 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000156003 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -ENGINE | 7400 | 88225 | 30720
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Radiator Engine Cooling | 2028-03-09 | 2028-03-10 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307516 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -ENGINE-COSYS-RADTR | 7400 | 88225 | 30720
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Pump Drive | 2028-03-09 | 2028-03-10 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000025934 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -ENGINE-PMPDR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Wheel End LH | 2028-03-09 | 2028-03-10 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000025944 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -FDRSYS-FDRVE-FDRLH | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Wheel End RH | 2028-03-09 | 2028-03-10 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000025945 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -FDRSYS-FDRVE-FDRRH | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Motor Lube Axle Rear & Hoses | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000272009 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYM01 | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl AOC Fan Motor Rear | 2028-03-09 | 2028-03-09 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000025947 | 09.03.2028 | 12000 | CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYM02 | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Axle Lube Hyd Pump | 2028-03-09 | 2028-03-09 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000083337 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYPUM | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Overhaul Accumulator Brake LHF | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025948 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BACCM-FRLFT | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Overhaul Accumulator Brake RHF | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025949 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BACCM-FRRGT | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Overhaul Accumulator Brake Rear | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025950 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BACCM-BACCR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Overhaul Valve Control Brake | 2028-03-09 | 2028-03-10 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000025952 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BRVLV | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Brake Oil Cooler Front | 2028-03-09 | 2028-03-09 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000083344 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BROCO-BROCF | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Brake Oil Cooler Rear | 2028-03-09 | 2028-03-09 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083343 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BROCO-BROCR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Motor Brake Oil Cooling | 2028-03-09 | 2028-03-09 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000025953 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BROCO-HYMO1 | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Steering HMU | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000025957 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -STRSYS-STHMU | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Ovhl Accumulator Steering Front | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025960 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -STRSYS-STACC-SACCF | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Ovhl Accumulator Steering Middle | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025961 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -STRSYS-STACC-SACCM | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Ovhl Accumulator Steering Rear | 2028-03-09 | 2028-03-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025962 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -STRSYS-STACC-SACCR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Pump Hoist & Brake | 2028-03-09 | 2028-03-09 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000025965 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -HYDSYS-HOPMP | 7400 | 88225 | 1004
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Rear Axle Linkages | 2028-03-09 | 2028-03-11 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000025974 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -STRUCT-CHASS-AXLIK | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Wheel Group Front LH | 2028-03-09 | 2028-03-10 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157155 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -STRUCT-AXLES-HUBLH | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Wheel Group Front RH | 2028-03-09 | 2028-03-10 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157243 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -STRUCT-AXLES-HUBRH | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Replace Hoses Hoist System | 2028-03-09 | 2028-03-10 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083339 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -HYDSYS-HDHLF-HSTHO | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Replace Brake System Hoses | 2028-03-09 | 2028-03-11 | 46 hrs | FY28 | 90 | 90010129 | B4 | 1000083345 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BRHLF-BRHOS | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Brake Cooling System Hoses | 2028-03-09 | 2028-03-10 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000083346 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-BRHLF-CBRHO | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Drive Line Axle LH | 2028-03-09 | 2028-03-09 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124607 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -FDRSYS-DRLAX-AXLLH | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Drive Line Axle RH | 2028-03-09 | 2028-03-09 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124608 | 09.03.2028 | 24000 | CCK-MP-HAUL-DT143 -FDRSYS-DRLAX-AXLRH | 7400 | 88225 | 11934
Panther 150T | Onsite PM | Haul | Fortescue | LL0010 | LL0010 12M NDT Inspection | 2028-03-10 | 2028-03-10 | 9 hrs | FY28 | 11 | 90038241 | B1 | 1000383086 | 10.03.2028 | 12 Monthly | CCK-MP-SUPP-LL0010 | 2000 | 587 | 587
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Engine Midlife Complete | 2028-03-10 | 2028-03-11 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155900 | 10.03.2028 | 12000 | CCK-MP-HAUL-DT086 -ENGINE | 7400 | 86822 | 24006
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Replace Operator Cabin Dash Bulbs | 2028-03-11 | 2028-03-11 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158227 | 11.03.2028 | 3000 | CCK-MP-HAUL-DT762 -STRUCT-CABIN | 6800 | 76486 | 20565
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Hoist LH | 2028-03-11 | 2028-03-11 | 17 hrs | FY28 | 33 | 90015130 | B1 | 1000128569 | 11.03.2028 | 28000 | CCK-MP-HAUL-DT130 -HYDSYS-HOCYL-HCYLL | 7400 | 85185 | 16330
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Transmisson Calibration | 2028-03-13 | 2028-03-13 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298669 | 13.03.2028 | 4500 | CCK-MP-HAUL-DT088 -TRNSYS-TRANS | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Service Air Conditioner 12M | 2028-03-13 | 2028-03-14 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174114 | 13.03.2028 | 12 Monthly | CCK-MP-HAUL-DT082 -STRUCT-CABIN-AIRCN | 7400 | 84375 | 35900
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Service Air Conditioner 12M | 2028-03-14 | 2028-03-15 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174169 | 14.03.2028 | 12 Monthly | CCK-MP-HAUL-DT136 -STRUCT-CABIN-AIRCN | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Auto Lube Pump | 2028-03-14 | 2028-03-14 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285625 | 14.03.2028 | 8000 | CCK-MP-HAUL-DT057 -GRSYST-ALBPP | 7400 | 91273 | 3875
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Steering LH | 2028-03-14 | 2028-03-14 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000023733 | 14.03.2028 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STRCY-STCYL | 7400 | 84421 | 17941
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Steering RH | 2028-03-14 | 2028-03-14 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000023734 | 14.03.2028 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STRCY-STCYR | 7400 | 84421 | 17941
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Tyre Sense Battery | 2028-03-14 | 2028-03-14 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153158 | 14.03.2028 | 24 Monthly | CCK-MP-HAUL-DT146 -MANGMT-TYRSN
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Cylinder Steering LH | 2028-03-15 | 2028-03-15 | 10 hrs | FY28 | 10 | 90018525 | B1 | 1000201179 | 15.03.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STRCY-STCYL | 5100 | 23504 | 9201
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Cylinder Steering RH | 2028-03-15 | 2028-03-15 | 8 hrs | FY28 | 14 | 90018526 | B1 | 1000201180 | 15.03.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STRCY-STCYR | 5100 | 23504 | 9201
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Auto Lube Pump | 2028-03-15 | 2028-03-15 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285801 | 15.03.2028 | 8000 | CCK-MP-HAUL-DT222 -GRSYST-ALBPP | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Spider Trans Driveshaft | 2028-03-15 | 2028-03-15 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154928 | 15.03.2028 | 6000 | CCK-MP-HAUL-DT082 -FDRSYS-DRSHT-UNVSL | 7400 | 84374 | 4829
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Cyl Steering LH | 2028-03-16 | 2028-03-16 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000026288 | 16.03.2028 | 15000 | CCK-MP-HAUL-DT148 -STRSYS-STRCY-STCYL | 7400 | 85451 | 1974
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Cyl Steering RH | 2028-03-16 | 2028-03-16 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000026289 | 16.03.2028 | 15000 | CCK-MP-HAUL-DT148 -STRSYS-STRCY-STCYR | 7400 | 85451 | 1974
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Replace Steering System Hoses | 2028-03-16 | 2028-03-18 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000091460 | 16.03.2028 | 15000 | CCK-MP-HAUL-DT148 -STRSYS-STHLF-STRHO | 7400 | 85451 | 1970
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Steering Bell Crank & Links | 2028-03-16 | 2028-03-17 | 20 hrs | FY28 | 36 | 90028566 | B1 | 1000317634 | 16.03.2028 | 30000 | CCK-MP-HAUL-DT148 -STRSYS-STLTR-STLAC | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Spiders Pump Drive Shaft | 2028-03-16 | 2028-03-16 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000024277 | 16.03.2028 | 18000 | CCK-MP-HAUL-DT090 -ENGINE-PMPDR-DRSHT | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Transmission | 2028-03-16 | 2028-03-17 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272303 | 16.03.2028 | 18000 | CCK-MP-HAUL-DT090 -TRNSYS-TRANS | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Drive Shaft Transmission | 2028-03-16 | 2028-03-16 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154935 | 16.03.2028 | 18000 | CCK-MP-HAUL-DT090 -FDRSYS-DRSHT | 7400 | 81670 | 17019
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Differential | 2028-03-16 | 2028-03-17 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000024285 | 16.03.2028 | 18000 | CCK-MP-HAUL-DT090 -FDRSYS-DIFFL | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Replace Hoses Differential System | 2028-03-16 | 2028-03-16 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000090080 | 16.03.2028 | 18000 | CCK-MP-HAUL-DT090 -FDRSYS-DIFFL-DIFHO | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Auto Lube Pump | 2028-03-17 | 2028-03-17 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285788 | 17.03.2028 | 8000 | CCK-MP-HAUL-DT147 -GRSYST-ALBPP | 7400 | 84664 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Operators Seat | 2028-03-17 | 2028-03-17 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000026237 | 17.03.2028 | 15000 | CCK-MP-HAUL-DT147 -STRUCT-CABIN-SEATS | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Service Air Conditioner 12M | 2028-03-17 | 2028-03-18 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174112 | 17.03.2028 | 12 Monthly | CCK-MP-HAUL-DT057 -STRUCT-CABIN-AIRCN | 7400 | 91273 | 10672
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Repl Pump Brake Charge & Cooling | 2028-03-17 | 2028-03-17 | 6 hrs | FY28 | 6 | 90037882 | B1 | 1000379763 | 17.03.2028 | 9000 | CCK-MP-SUPP-WC220 -BRKSYS-BRPMP | 4300 | 58137 | 1436
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Drive Shaft Transmission | 2028-03-17 | 2028-03-17 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154927 | 17.03.2028 | 18000 | CCK-MP-HAUL-DT058 -FDRSYS-DRSHT | 7400 | 87864 | 5769
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Operators Seat | 2028-03-18 | 2028-03-18 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000023810 | 18.03.2028 | 15000 | CCK-MP-HAUL-DT057 -STRUCT-CABIN-SEATS | 7400 | 91273 | 2803
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Replace Operator Cabin Dash Bulbs | 2028-03-19 | 2028-03-19 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158229 | 19.03.2028 | 3000 | CCK-MP-HAUL-DT764 -STRUCT-CABIN | 6800 | 75315 | 21117
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Auto Lube Pump | 2028-03-19 | 2028-03-19 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094454 | 19.03.2028 | 8000 | CCK-MP-HAUL-DT754 -GRSYST-ALBPP | 6800 | 83256 | 4996
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Auto Lube Pump | 2028-03-20 | 2028-03-20 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285633 | 20.03.2028 | 8000 | CCK-MP-HAUL-DT095 -GRSYST-ALBPP | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Hoist LH | 2028-03-20 | 2028-03-20 | 17 hrs | FY28 | 33 | 90015130 | B1 | 1000128541 | 20.03.2028 | 28000 | CCK-MP-HAUL-DT058 -HYDSYS-HOCYL-HCYLL | 7400 | 87864 | 15616
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Suspension LHF | 2028-03-20 | 2028-03-22 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067441 | 20.03.2028 | 28000 | CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYLF | 7400 | 87864 | 15544
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Suspension RHF | 2028-03-20 | 2028-03-22 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067443 | 20.03.2028 | 28000 | CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYRF | 7400 | 87864 | 15544
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Suspension LHR | 2028-03-20 | 2028-03-21 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000023881 | 20.03.2028 | 28000 | CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYLR | 7400 | 87864 | 15484
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Cyl Suspension RHF | 2028-03-21 | 2028-03-23 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000095150 | 21.03.2028 | 18000 | CCK-MP-HAUL-DT767 -STRUCT-SUSPN-SCYRF | 6800 | 74312 | 6563
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Transmisson Calibration | 2028-03-21 | 2028-03-21 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298722 | 21.03.2028 | 4500 | CCK-MP-HAUL-DT137 -TRNSYS-TRANS | 7400 | 84196 | 1006
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Tyre Sense Battery | 2028-03-21 | 2028-03-21 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153151 | 21.03.2028 | 24 Monthly | CCK-MP-HAUL-DT135 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Tyre Sense Battery | 2028-03-22 | 2028-03-22 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153192 | 22.03.2028 | 24 Monthly | CCK-MP-HAUL-DT767 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Wheel Motor RH | 2028-03-22 | 2028-03-24 | 45.5 hrs | FY28 | 83.5 | 90011336 | B1 | 1000095388 | 22.03.2028 | 25000 | CCK-MP-HAUL-DT772 -FDRSYS-WLMTR-WHMRH | 6800 | 85256 | 15694
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Wheel Motor Oil RH | 2028-03-22 | 2028-03-22 | 1 hr | FY28 | 1 | 90033606 | B1 | 1000338241 | 22.03.2028 | 25000 | CCK-MP-HAUL-DT772 -FDRSYS-WLMTR-WHMRH | 6800 | 85256 | 15694
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 250hr Initial Valve Set | 2028-03-22 | 2028-03-22 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156006 | 22.03.2028 | 250 | CCK-MP-HAUL-DT143 -ENGINE | 7400 | 88225 | 30720
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Spider Trans Driveshaft | 2028-03-23 | 2028-03-23 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154948 | 23.03.2028 | 6000 | CCK-MP-HAUL-DT100 -FDRSYS-DRSHT-UNVSL | 7400 | 87135 | 5703
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Spider Trans Driveshaft | 2028-03-23 | 2028-03-23 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154972 | 23.03.2028 | 6000 | CCK-MP-HAUL-DT147 -FDRSYS-DRSHT-UNVSL | 7400 | 84659 | 716
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Water Cannon Maintenance | 2028-03-23 | 2028-03-23 | 3 hrs | FY28 | 3 | 90001682 | B1 | 1000018408 | 23.03.2028 | 6 Monthly | CCK-MP-SUPP-WC008 -STRUCT-WTANK-SPRAY | 3500 | 51417 | 5947
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Suspension LHF | 2028-03-23 | 2028-03-25 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067485 | 23.03.2028 | 28000 | CCK-MP-HAUL-DT094 -STRUCT-SUSPN-SCYLF | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Suspension LHR | 2028-03-23 | 2028-03-24 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000024575 | 23.03.2028 | 28000 | CCK-MP-HAUL-DT094 -STRUCT-SUSPN-SCYLR | 7400 | 88788 | 15729
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Bulk Grease Tank Breather | 2028-03-24 | 2028-03-24 | 1 hr | FY28 | 1 | 90022533 | B1 | 1000236910 | 24.03.2028 | 6 Monthly | CCK-MP-SUPP-SV221 -GRSYST-GRTNK | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Brake Slack Adjuster Front | 2028-03-24 | 2028-03-24 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025434 | 24.03.2028 | 20000 | CCK-MP-HAUL-DT135 -BRKSYS-SLACK-SLACF | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Brake Slack Adjuster Rear | 2028-03-24 | 2028-03-24 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025435 | 24.03.2028 | 20000 | CCK-MP-HAUL-DT135 -BRKSYS-SLACK-SLACR | 7400 | 82965 | 8025
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Steering Bleed Down Manifold | 2028-03-25 | 2028-03-25 | 6.5 hrs | FY28 | 8 | 90011347 | B1 | 1000095183 | 25.03.2028 | 25000 | CCK-MP-HAUL-DT768 -STRSYS-STBDM | 6800 | 79837 | 13720
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Wheel Group Front RH | 2028-03-25 | 2028-03-26 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157263 | 25.03.2028 | 24000 | CCK-MP-HAUL-DT158 -STRUCT-AXLES-HUBRH | 7400 | 85964 | 12018
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Suspension RHF | 2028-03-25 | 2028-03-27 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067635 | 25.03.2028 | 28000 | CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYRF | 7400 | 85964 | 12018
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Water Tank Cannon & Spray Sys Insp | 2028-03-25 | 2028-03-25 | 3 hrs | FY28 | 3 | 90036927 | B1 | 1000368892 | 25.03.2028 | 6 Monthly | CCK-MP-SUPP-WC224 -STRUCT-WTANK | 5000 | 70936 | 6229
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Air Con Service & Overhaul | 2028-03-27 | 2028-03-28 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110613 | 27.03.2028 | 12 Monthly | CCK-MP-HAUL-DT753 -STRUCT-CABIN-AIRCN | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Air Con Service & Overhaul | 2028-03-27 | 2028-03-28 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110628 | 27.03.2028 | 12 Monthly | CCK-MP-HAUL-DT759 -STRUCT-CABIN-AIRCN | 6800 | 79716 | 28650
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Transmisson Calibration | 2028-03-27 | 2028-03-27 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298740 | 27.03.2028 | 4500 | CCK-MP-HAUL-DT221 -TRNSYS-TRANS | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Brake Slack Adjuster Front | 2028-03-27 | 2028-03-27 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025242 | 27.03.2028 | 20000 | CCK-MP-HAUL-DT130 -BRKSYS-SLACK-SLACF | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Brake Slack Adjuster Rear | 2028-03-27 | 2028-03-27 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025243 | 27.03.2028 | 20000 | CCK-MP-HAUL-DT130 -BRKSYS-SLACK-SLACR | 7400 | 85185 | 7959
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Grid Box Blower Motor LH | 2028-03-28 | 2028-03-28 | 10 hrs | FY28 | 10 | 90011331 | B1 | 1000094694 | 28.03.2028 | 25000 | CCK-MP-HAUL-DT759 -ELCTHV-HVGBM-GBMLH | 6800 | 79716 | 39497
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Wheel Motor Oil RH | 2028-03-28 | 2028-03-28 | 1 hr | FY28 | 1 | 90033606 | B1 | 1000338215 | 28.03.2028 | 25000 | CCK-MP-HAUL-DT759 -FDRSYS-WLMTR-WHMRH | 6800 | 79716 | 14332
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Wheel Motor RH | 2028-03-28 | 2028-03-30 | 45.5 hrs | FY28 | 83.5 | 90011336 | B1 | 1000094699 | 28.03.2028 | 25000 | CCK-MP-HAUL-DT759 -FDRSYS-WLMTR-WHMRH | 6800 | 79716 | 14332
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Transmisson Calibration | 2028-03-28 | 2028-03-28 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298675 | 28.03.2028 | 4500 | CCK-MP-HAUL-DT099 -TRNSYS-TRANS | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Engine Cat C175-16 | 2028-03-28 | 2028-03-31 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000155931 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -ENGINE | 7400 | 83732 | 33462
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Radiator Engine Cooling | 2028-03-28 | 2028-03-29 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307492 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -ENGINE-COSYS-RADTR | 7400 | 83804 | 33534
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Wheel End LH | 2028-03-28 | 2028-03-29 | 32.5 hrs | FY28 | 58.5 | 90002374 | B1 | 1000024728 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -FDRSYS-FDRVE-FDRLH | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Motor Lube Axle Rear & Hoses | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271985 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYM01 | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl AOC Fan Motor Rear | 2028-03-28 | 2028-03-28 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024731 | 28.03.2028 | 12000 | CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYM02 | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Axle Lube Hyd Pump | 2028-03-28 | 2028-03-28 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000083014 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYPUM | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Overhaul Accumulator Brake LHF | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024732 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BACCM-FRLFT | 7400 | 83756 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Overhaul Accumulator Brake RHF | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024733 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BACCM-FRRGT | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Overhaul Accumulator Brake Rear | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024734 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BACCM-BACCR | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Pump Brake Cooling | 2028-03-28 | 2028-03-28 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000024735 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-HYFPP | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Overhaul Valve Control Brake | 2028-03-28 | 2028-03-29 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000024736 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BRVLV | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Brake Oil Cooler Front | 2028-03-28 | 2028-03-28 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000083021 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BROCO-BROCF | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Brake Oil Cooler Rear | 2028-03-28 | 2028-03-28 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083020 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BROCO-BROCR | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Motor Brake Oil Cooling | 2028-03-28 | 2028-03-28 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000024737 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BROCO-HYMO1 | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Hyd Pump Steering Main & Fan | 2028-03-28 | 2028-03-28 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000024740 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRSYS-STPMP | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Steering HMU | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000024741 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRSYS-STHMU | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Ovhl Accumulator Steering Front | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024744 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRSYS-STACC-SACCF | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Ovhl Accumulator Steering Middle | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024745 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRSYS-STACC-SACCM | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Ovhl Accumulator Steering Rear | 2028-03-28 | 2028-03-28 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024746 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRSYS-STACC-SACCR | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Pump Hoist & Brake | 2028-03-28 | 2028-03-28 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000024748 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -HYDSYS-HOPMP | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Rear Axle Linkages | 2028-03-28 | 2028-03-30 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000024757 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRUCT-CHASS-AXLIK | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Wheel Group Front LH | 2028-03-28 | 2028-03-29 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157129 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -STRUCT-AXLES-HUBLH | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Replace Hoses Hoist System | 2028-03-28 | 2028-03-29 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083016 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -HYDSYS-HDHLF-HSTHO | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Replace Brake System Hoses | 2028-03-28 | 2028-03-30 | 46 hrs | FY28 | 90 | 90010129 | B3 | 1000083022 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BRHLF-BRHOS | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Brake Cooling System Hoses | 2028-03-28 | 2028-03-29 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000083023 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -BRKSYS-BRHLF-CBRHO | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Drive Line Axle LH | 2028-03-28 | 2028-03-28 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124587 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -FDRSYS-DRLAX-AXLLH | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Drive Line Axle RH | 2028-03-28 | 2028-03-28 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124588 | 28.03.2028 | 24000 | CCK-MP-HAUL-DT097 -FDRSYS-DRLAX-AXLRH | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Service Air Conditioner 12M | 2028-03-28 | 2028-03-29 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174110 | 28.03.2028 | 12 Monthly | CCK-MP-HAUL-DT055 -STRUCT-CABIN-AIRCN | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Suspension LHF | 2028-03-29 | 2028-03-31 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067573 | 29.03.2028 | 28000 | CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYLF | 7400 | 88225 | 15547
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Engine Midlife Complete | 2028-03-29 | 2028-03-30 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155918 | 29.03.2028 | 12000 | CCK-MP-HAUL-DT091 -ENGINE | 7400 | 83859 | 23814
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Radiator Fan Hoses | 2028-03-29 | 2028-03-29 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307485 | 29.03.2028 | 12000 | CCK-MP-HAUL-DT091 -ENGINE-COSYS-RADTR | 7400 | 83859 | 23814
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Motor Lube Axle Hoses | 2028-03-29 | 2028-03-29 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000271980 | 29.03.2028 | 12000 | CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYM01 | 7400 | 83859 | 23814
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Spider Trans Driveshaft | 2028-03-29 | 2028-03-29 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154936 | 29.03.2028 | 6000 | CCK-MP-HAUL-DT091 -FDRSYS-DRSHT-UNVSL | 7400 | 83859 | 5241
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Air Con Service & Overhaul | 2028-03-30 | 2028-03-31 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110636 | 30.03.2028 | 12 Monthly | CCK-MP-HAUL-DT767 -STRUCT-CABIN-AIRCN | 6800 | 74312 | 74312
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Replace Operator Cabin Dash Bulbs | 2028-03-31 | 2028-03-31 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158221 | 31.03.2028 | 3000 | CCK-MP-HAUL-DT756 -STRUCT-CABIN | 6800 | 78754 | 78754
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Operator Cabin Dash Bulbs | 2028-03-31 | 2028-03-31 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158216 | 31.03.2028 | 3000 | CCK-MP-HAUL-DT751 -STRUCT-CABIN | 6800 | 86211 | 11291
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Service Air Conditioner 12M | 2028-03-31 | 2028-04-01 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174170 | 31.03.2028 | 12 Monthly | CCK-MP-HAUL-DT137 -STRUCT-CABIN-AIRCN | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl AOC Fan Motor Rear | 2028-03-31 | 2028-03-31 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024542 | 31.03.2028 | 12000 | CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-HYM02 | 7400 | 88788 | 11570
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Steering HMU | 2028-03-31 | 2028-03-31 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000024552 | 31.03.2028 | 24000 | CCK-MP-HAUL-DT094 -STRSYS-STHMU | 7400 | 88788 | 42099
777G SV | Onsite PM | Haul | Fortescue | SV220 | 24 Monthly HP Grease Lines Replace | 2028-04-01 | 2028-04-01 | 3 hrs | FY28 | 3 | 90016826 | B1 | 1000152002 | 01.04.2028 | 24 Monthly | CCK-MP-SUPP-SV220 -MODULE | 5100 | 58259 | 16547
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Suspension RHF | 2028-04-01 | 2028-04-03 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067563 | 01.04.2028 | 28000 | CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYRF | 7400 | 86767 | 11747
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Spiders Pump Drive Shaft | 2028-04-01 | 2028-04-01 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000023710 | 01.04.2028 | 18000 | CCK-MP-HAUL-DT056 -ENGINE-PMPDR-DRSHT | 7400 | 84421 | 5642
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Cyl Steering LH | 2028-04-01 | 2028-04-01 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000024300 | 01.04.2028 | 15000 | CCK-MP-HAUL-DT090 -STRSYS-STRCY-STCYL | 7400 | 81670 | 2498
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Air Con Service & Overhaul | 2028-04-02 | 2028-04-03 | 36 hrs | FY28 | 36 | 90013265 | B1 | 1000110625 | 02.04.2028 | 12 Monthly | CCK-MP-HAUL-DT756 -STRUCT-CABIN-AIRCN | 6800 | 78754 | 19465
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Cyl Steering LH | 2028-04-02 | 2028-04-02 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000023670 | 02.04.2028 | 15000 | CCK-MP-HAUL-DT055 -STRSYS-STRCY-STCYL | 7400 | 84122 | 2699
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Wheel End LH | 2028-04-03 | 2028-04-04 | 32.5 hrs | FY28 | 58.5 | 90030708 | B1 | 1000128034 | 03.04.2028 | 24000 | CCK-MP-HAUL-DT222 -FDRSYS-FDRVE-FDRLH | 7400 | 55735 | 11599
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Brake Slack Adjuster Front | 2028-04-03 | 2028-04-03 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167169 | 03.04.2028 | 20000 | CCK-MP-HAUL-DT5316-BRKSYS-SLACK-SLACF | 7400 | 45108 | 7788
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Brake Slack Adjuster Rear | 2028-04-03 | 2028-04-03 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000167170 | 03.04.2028 | 20000 | CCK-MP-HAUL-DT5316-BRKSYS-SLACK-SLACR | 7400 | 45108 | 7788
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Pump Hoist | 2028-04-04 | 2028-04-04 | 4 hrs | FY28 | 4 | 90000260 | B2 | 1000018405 | 04.04.2028 | 9000 | CCK-MP-SUPP-WC008 -HYDSYS-HOPMP | 3500 | 51417 | 352
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Tyre Sense Battery | 2028-04-05 | 2028-04-05 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153184 | 05.04.2028 | 24 Monthly | CCK-MP-HAUL-DT759 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Spiders Pump Drive Shaft | 2028-04-06 | 2028-04-06 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000024530 | 06.04.2028 | 18000 | CCK-MP-HAUL-DT094 -ENGINE-PMPDR-DRSHT | 7400 | 88788 | 24241
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Transmission Oil Cooler | 2028-04-06 | 2028-04-06 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000082974 | 06.04.2028 | 18000 | CCK-MP-HAUL-DT094 -TRNSYS-TROLC | 7400 | 88788 | 5404
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Differential | 2028-04-06 | 2028-04-07 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000024538 | 06.04.2028 | 18000 | CCK-MP-HAUL-DT094 -FDRSYS-DIFFL | 7400 | 88788 | 5404
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Tyre Sense Battery | 2028-04-06 | 2028-04-06 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153168 | 06.04.2028 | 24 Monthly | CCK-MP-HAUL-DT159 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Replace Operator Cabin Dash Bulbs | 2028-04-07 | 2028-04-07 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158235 | 07.04.2028 | 3000 | CCK-MP-HAUL-DT770 -STRUCT-CABIN | 6800 | 79305 | 79305
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Transmission System Hoses | 2028-04-07 | 2028-04-07 | 4 hrs | FY28 | 4 | 90010493 | B2 | 1000238429 | 07.04.2028 | 11000 | CCK-MP-SUPP-WC225 -TRNSYS-TRANS-TRNHO | 5000 | 22459 | 10710
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Service Air Conditioner 12M | 2028-04-07 | 2028-04-08 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174175 | 07.04.2028 | 12 Monthly | CCK-MP-HAUL-DT146 -STRUCT-CABIN-AIRCN | 7400 | 83062 | 31809
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Wheel Motor RH | 2028-04-08 | 2028-04-10 | 45.5 hrs | FY28 | 83.5 | 90011336 | B1 | 1000094646 | 08.04.2028 | 25000 | CCK-MP-HAUL-DT758 -FDRSYS-WLMTR-WHMRH | 6800 | 85895 | 13645
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Wheel Motor Oil RH | 2028-04-08 | 2028-04-08 | 1 hr | FY28 | 1 | 90033606 | B1 | 1000338213 | 08.04.2028 | 25000 | CCK-MP-HAUL-DT758 -FDRSYS-WLMTR-WHMRH | 6800 | 85895 | 13645
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Suspension RHF | 2028-04-08 | 2028-04-10 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000094673 | 08.04.2028 | 18000 | CCK-MP-HAUL-DT758 -STRUCT-SUSPN-SCYRF | 6800 | 85895 | 6648
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 Repl Auto Lube Pump | 2028-04-08 | 2028-04-08 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285802 | 08.04.2028 | 8000 | CCK-MP-HAUL-DT223 -GRSYST-ALBPP | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Service Air Conditioner 12M | 2028-04-09 | 2028-04-10 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174174 | 09.04.2028 | 12 Monthly | CCK-MP-HAUL-DT143 -STRUCT-CABIN-AIRCN | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 250hr Initial Valve Set | 2028-04-09 | 2028-04-09 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155934 | 09.04.2028 | 250 | CCK-MP-HAUL-DT097 -ENGINE | 7400 | 83732 | 33462
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension LHF | 2028-04-09 | 2028-04-09 | 2 hrs | FY28 | 2 | 90038229 | B1 | 1000382496 | 09.04.2028 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension RHF | 2028-04-09 | 2028-04-09 | 2 hrs | FY28 | 2 | 90038229 | B1 | 1000382497 | 09.04.2028 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRF | 5000 | 75197 | 10710
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Cyl Suspension LHR | 2028-04-09 | 2028-04-10 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000027037 | 09.04.2028 | 28000 | CCK-MP-HAUL-DT159 -STRUCT-SUSPN-SCYLR | 7400 | 90235 | 15586
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Drive Shaft | 2028-04-10 | 2028-04-10 | 2 hrs | FY28 | 2 | 90011540 | B1 | 1000093089 | 10.04.2028 | 18000 | CCK-MP-SUPP-SV221 -FDRSYS-DRSHT | 5100 | 64374 | 23486
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Transmission | 2028-04-10 | 2028-04-11 | 26 hrs | FY28 | 50 | 90011535 | B1 | 1000093084 | 10.04.2028 | 18000 | CCK-MP-SUPP-SV221 -TRNSYS-TRANS | 5100 | 64374 | 9558
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Torque Converter | 2028-04-10 | 2028-04-10 | 14 hrs | FY28 | 26 | 90011534 | B1 | 1000093083 | 10.04.2028 | 18000 | CCK-MP-SUPP-SV221 -TRNSYS-TRQUE | 5100 | 64374 | 9558
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Water Tank Cannon & Spray Sys Insp | 2028-04-10 | 2028-04-10 | 3 hrs | FY28 | 3 | 90036927 | B1 | 1000368894 | 10.04.2028 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-WTANK | 5000 | 75244 | 75244
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Replace Operator Cabin Dash Bulbs | 2028-04-11 | 2028-04-11 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158238 | 11.04.2028 | 3000 | CCK-MP-HAUL-DT773 -STRUCT-CABIN | 6800 | 75884 | 75884
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Cyl Suspension LHF | 2028-04-12 | 2028-04-14 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067385 | 12.04.2028 | 28000 | CCK-MP-HAUL-DT054 -STRUCT-SUSPN-SCYLF | 7400 | 88111 | 15675
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Brake Manifold | 2028-04-12 | 2028-04-12 | 13.5 hrs | FY28 | 13.5 | 90029265 | B1 | 1000292149 | 12.04.2028 | 25000 | CCK-MP-HAUL-DT757 -BRKSYS-BRVLV | 6800 | 80700 | 13662
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Tyre Sense Battery | 2028-04-12 | 2028-04-12 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153174 | 12.04.2028 | 24 Monthly | CCK-MP-HAUL-DT5202-MANGMT-TYRSN
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Transmission | 2028-04-12 | 2028-04-12 | 12 hrs | FY28 | 24 | 90000268 | B2 | 1000018390 | 12.04.2028 | 18000 | CCK-MP-SUPP-WC008 -TRNSYS-TRANS | 3500 | 51417 | 11805
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Oil Cooler Trans | 2028-04-12 | 2028-04-12 | 6 hrs | FY28 | 6 | 90003040 | B2 | 1000239795 | 12.04.2028 | 18000 | CCK-MP-SUPP-WC008 -TRNSYS-TROLC | 3500 | 51417 | 51417
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Tyre Sense Battery | 2028-04-12 | 2028-04-12 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153118 | 12.04.2028 | 24 Monthly | CCK-MP-HAUL-DT086 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Service Air Conditioner 12M | 2028-04-12 | 2028-04-13 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174113 | 12.04.2028 | 12 Monthly | CCK-MP-HAUL-DT058 -STRUCT-CABIN-AIRCN | 7400 | 87864 | 1976
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Air Drier and Tank | 2028-04-13 | 2028-04-13 | 12 hrs | FY28 | 24 | 90004010 | B2 | 1000079211 | 13.04.2028 | 9000 | CCK-MP-SUPP-WC3111-PNEUMC-AIRDR | 5600 | 51257 | 8333
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Operators Seat | 2028-04-13 | 2028-04-13 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000025517 | 13.04.2028 | 15000 | CCK-MP-HAUL-DT136 -STRUCT-CABIN-SEATS | 7400 | 87780 | 1767
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Steering Bell Crank & Links | 2028-04-13 | 2028-04-14 | 20 hrs | FY28 | 36 | 90028566 | B1 | 1000317594 | 13.04.2028 | 30000 | CCK-MP-HAUL-DT088 -STRSYS-STLTR-STLAC | 7400 | 89037 | 17080
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Spiders Pump Drive Shaft | 2028-04-13 | 2028-04-13 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000026991 | 13.04.2028 | 18000 | CCK-MP-HAUL-DT159 -ENGINE-PMPDR-DRSHT | 7400 | 90235 | 5552
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Engine Cat C175-16 | 2028-04-14 | 2028-04-17 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000156057 | 14.04.2028 | 24000 | CCK-MP-HAUL-DT158 -ENGINE | 7400 | 85964 | 11614
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Inspect Rear Axle Housing | 2028-04-14 | 2028-04-14 | 1 hr | FY28 | 1 | 90019256 | B1 | 1000196435 | 14.04.2028 | 2000 | CCK-MP-SUPP-WC225 -STRUCT-RAXHO | 5000 | 75244 | 75244
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Wheel End RH | 2028-04-14 | 2028-04-15 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000026605 | 14.04.2028 | 24000 | CCK-MP-HAUL-DT153 -FDRSYS-FDRVE-FDRRH | 7400 | 84230 | 11477
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Suspension LHF | 2028-04-14 | 2028-04-16 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067513 | 14.04.2028 | 28000 | CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYLF | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Tyre Sense Battery | 2028-04-14 | 2028-04-14 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153149 | 14.04.2028 | 24 Monthly | CCK-MP-HAUL-DT127 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Operators Seat | 2028-04-15 | 2028-04-15 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000026171 | 15.04.2028 | 15000 | CCK-MP-HAUL-DT146 -STRUCT-CABIN-SEATS | 7400 | 83062 | 2282
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Auto Lube Pump | 2028-04-16 | 2028-04-16 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094931 | 16.04.2028 | 8000 | CCK-MP-HAUL-DT763 -GRSYST-ALBPP | 6800 | 74143 | 14657
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Hyd Pump Steering & Brake | 2028-04-16 | 2028-04-17 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204750 | 16.04.2028 | 12000 | CCK-MP-HAUL-DT770 -STRSYS-STPMP | 6800 | 79305 | 24817
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Hub & Spindle LH | 2028-04-16 | 2028-04-17 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000095306 | 16.04.2028 | 18000 | CCK-MP-HAUL-DT770 -STRUCT-AXLES-HUBLH | 6800 | 79305 | 24535
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Hub & Spindle RH | 2028-04-16 | 2028-04-17 | 32 hrs | FY28 | 60 | 90011364 | B1 | 1000095307 | 16.04.2028 | 18000 | CCK-MP-HAUL-DT770 -STRUCT-AXLES-HUBRH | 6800 | 79305 | 24535
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Cyl Suspension LHF | 2028-04-16 | 2028-04-18 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000095308 | 16.04.2028 | 18000 | CCK-MP-HAUL-DT770 -STRUCT-SUSPN-SCYLF | 6800 | 79305 | 14151
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Cyl Suspension RHF | 2028-04-16 | 2028-04-18 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000095309 | 16.04.2028 | 18000 | CCK-MP-HAUL-DT770 -STRUCT-SUSPN-SCYRF | 6800 | 79305 | 24975
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Auto Lube Pump | 2028-04-16 | 2028-04-16 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285796 | 16.04.2028 | 8000 | CCK-MP-HAUL-DT158 -GRSYST-ALBPP | 7400 | 85964 | 11104
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Pump Drive Driveshaft Unis | 2028-04-16 | 2028-04-16 | 2 hrs | FY28 | 2 | 90000911 | B2 | 1000033281 | 16.04.2028 | 11000 | CCK-MP-SUPP-WC224 -ENGINE-PMPDR-DRSHT | 5000 | 71088 | 2624
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Cyl Steering RH | 2028-04-17 | 2028-04-17 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000023608 | 17.04.2028 | 15000 | CCK-MP-HAUL-DT054 -STRSYS-STRCY-STCYR | 7400 | 88111 | 2567
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Auto Lube Pump | 2028-04-17 | 2028-04-17 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095037 | 17.04.2028 | 8000 | CCK-MP-HAUL-DT765 -GRSYST-ALBPP | 6800 | 78429 | 13600
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Steering LH | 2028-04-17 | 2028-04-17 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000026354 | 17.04.2028 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STRCY-STCYL | 7400 | 86975 | 17339
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Steering RH | 2028-04-17 | 2028-04-17 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000026355 | 17.04.2028 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STRCY-STCYR | 7400 | 86975 | 17339
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Brake Oil Cooler Rear | 2028-04-17 | 2028-04-17 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000091520 | 17.04.2028 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BROCO-BROCR | 7400 | 83041 | 11359
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Transmisson Calibration | 2028-04-17 | 2028-04-17 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298668 | 17.04.2028 | 4500 | CCK-MP-HAUL-DT086 -TRNSYS-TRANS | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Service Air Conditioner 12M | 2028-04-18 | 2028-04-19 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174163 | 18.04.2028 | 12 Monthly | CCK-MP-HAUL-DT099 -STRUCT-CABIN-AIRCN | 7400 | 87442 | 10255
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Tyre Sense Battery | 2028-04-19 | 2028-04-19 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153196 | 19.04.2028 | 24 Monthly | CCK-MP-HAUL-DT771 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Auto Lube Pump | 2028-04-19 | 2028-04-19 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094507 | 19.04.2028 | 8000 | CCK-MP-HAUL-DT755 -GRSYST-ALBPP | 6800 | 84587 | 13093
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Steering Linkages | 2028-04-19 | 2028-04-19 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317611 | 19.04.2028 | 15000 | CCK-MP-HAUL-DT127 -STRSYS-STLTR | 7400 | 83059 | 29032
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Replace Steering System Hoses | 2028-04-19 | 2028-04-21 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000083121 | 19.04.2028 | 15000 | CCK-MP-HAUL-DT127 -STRSYS-STHLF-STRHO | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Engine Cat C175-16 | 2028-04-20 | 2028-04-23 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000155973 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -ENGINE | 7400 | 87780 | 87780
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Radiator Engine Cooling | 2028-04-20 | 2028-04-21 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307506 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -ENGINE-COSYS-RADTR | 7400 | 87780 | 24460
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Pump Drive | 2028-04-20 | 2028-04-21 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000025478 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -ENGINE-PMPDR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Wheel End RH | 2028-04-20 | 2028-04-21 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000025489 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -FDRSYS-FDRVE-FDRRH | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Motor Lube Axle Rear & Hoses | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271999 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYM01 | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl AOC Fan Motor Rear | 2028-04-20 | 2028-04-20 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000025491 | 20.04.2028 | 12000 | CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYM02 | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Overhaul Accumulator Brake LHF | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025492 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-BACCM-FRLFT | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Overhaul Accumulator Brake RHF | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025493 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-BACCM-FRRGT | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Overhaul Accumulator Brake Rear | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025494 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-BACCM-BACCR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Motor Brake Oil Cooling | 2028-04-20 | 2028-04-20 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000025497 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-BROCO-HYMO1 | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Hyd Pump Steering Main & Fan | 2028-04-20 | 2028-04-20 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000025500 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -STRSYS-STPMP | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Steering HMU | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000025501 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -STRSYS-STHMU | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Ovhl Accumulator Steering Front | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025504 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -STRSYS-STACC-SACCF | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Ovhl Accumulator Steering Rear | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025506 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -STRSYS-STACC-SACCR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Pump Hoist & Brake | 2028-04-20 | 2028-04-20 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000025509 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -HYDSYS-HOPMP | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Rear Axle Linkages | 2028-04-20 | 2028-04-22 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000025518 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -STRUCT-CHASS-AXLIK | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Wheel Group Front LH | 2028-04-20 | 2028-04-21 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157145 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -STRUCT-AXLES-HUBLH | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Wheel Group Front RH | 2028-04-20 | 2028-04-21 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157233 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -STRUCT-AXLES-HUBRH | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Suspension RHF | 2028-04-20 | 2028-04-22 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067547 | 20.04.2028 | 28000 | CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYRF | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Replace Hoses Hoist System | 2028-04-20 | 2028-04-21 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083206 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -HYDSYS-HDHLF-HSTHO | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Replace Brake System Hoses | 2028-04-20 | 2028-04-22 | 46 hrs | FY28 | 90 | 90010129 | B4 | 1000083212 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-BRHLF-BRHOS | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Brake Cooling System Hoses | 2028-04-20 | 2028-04-21 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000083213 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -BRKSYS-BRHLF-CBRHO | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Drive Line Axle LH | 2028-04-20 | 2028-04-20 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000131757 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -FDRSYS-DRLAX-AXLLH | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Drive Line Axle RH | 2028-04-20 | 2028-04-20 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000131758 | 20.04.2028 | 24000 | CCK-MP-HAUL-DT136 -FDRSYS-DRLAX-AXLRH | 7400 | 87780 | 11471
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Replace Operator Cabin Dash Bulbs | 2028-04-21 | 2028-04-21 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158222 | 21.04.2028 | 3000 | CCK-MP-HAUL-DT757 -STRUCT-CABIN | 6800 | 80700 | 80700
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Steering Bleed Down Manifold | 2028-04-21 | 2028-04-21 | 6.5 hrs | FY28 | 8 | 90011347 | B1 | 1000095342 | 21.04.2028 | 25000 | CCK-MP-HAUL-DT771 -STRSYS-STBDM | 6800 | 84423 | 13551
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Auto Lube Pump | 2028-04-21 | 2028-04-21 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285804 | 21.04.2028 | 8000 | CCK-MP-HAUL-DT5255-GRSYST-ALBPP | 7400 | 87580 | 3331
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Steering LH | 2028-04-21 | 2028-04-21 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000026420 | 21.04.2028 | 15000 | CCK-MP-HAUL-DT150 -STRSYS-STRCY-STCYL | 7400 | 86608 | 872
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Steering RH | 2028-04-21 | 2028-04-21 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000026421 | 21.04.2028 | 15000 | CCK-MP-HAUL-DT150 -STRSYS-STRCY-STCYR | 7400 | 86608 | 0
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Grid Box Blower Motor RH | 2028-04-22 | 2028-04-22 | 10 hrs | FY28 | 10 | 90011332 | B1 | 1000095437 | 22.04.2028 | 25000 | CCK-MP-HAUL-DT773 -ELCTHV-HVGBM-GBMRH | 6800 | 75884 | 13217
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Brake Accumulator Rear | 2028-04-22 | 2028-04-22 | 7 hrs | FY28 | 11 | 90011339 | B1 | 1000094384 | 22.04.2028 | 25000 | CCK-MP-HAUL-DT753 -BRKSYS-BRACC-BACCR | 6800 | 85999 | 13422
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Operators Seat | 2028-04-22 | 2028-04-22 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000167101 | 22.04.2028 | 15000 | CCK-MP-HAUL-DT5315-STRUCT-CABIN-SEATS | 7400 | 45392 | 2340
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 HP Grease Gun, Hose & Burst Sleeve | 2028-04-23 | 2028-04-23 | 4 hrs | FY28 | 4 | 90022836 | B1 | 1000238751 | 23.04.2028 | 12 Monthly | CCK-MP-SUPP-SV221 -GRSYST-ALHLF | 5100 | 64374 | 64374
T264 | Onsite PM | Haul | Fortescue | DT5489 | DT5489 Overhaul Air Conditioner 24M | 2028-04-23 | 2028-04-25 | 48 hrs | FY28 | 48 | 90029460 | B1 | 1000372285 | 23.04.2028 | 24 Monthly | CCK-MP-HAUL-DT5489-STRUCT-CABIN-AIRCN | 3000 | 1 | 1
T264 | Onsite PM | Haul | Fortescue | DT5490 | DT5490 Overhaul Air Conditioner 24M | 2028-04-23 | 2028-04-25 | 48 hrs | FY28 | 48 | 90029460 | B1 | 1000372330 | 23.04.2028 | 24 Monthly | CCK-MP-HAUL-DT5490-STRUCT-CABIN-AIRCN | 3000 | 1 | 1
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Transmission | 2028-04-23 | 2028-04-24 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272351 | 23.04.2028 | 18000 | CCK-MP-HAUL-DT155 -TRNSYS-TRANS | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Steering Linkages | 2028-04-25 | 2028-04-25 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317587 | 25.04.2028 | 15000 | CCK-MP-HAUL-DT058 -STRSYS-STLTR | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Operators Seat | 2028-04-25 | 2028-04-25 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000023873 | 25.04.2028 | 15000 | CCK-MP-HAUL-DT058 -STRUCT-CABIN-SEATS | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Replace Steering System Hoses | 2028-04-25 | 2028-04-27 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000082532 | 25.04.2028 | 15000 | CCK-MP-HAUL-DT058 -STRSYS-STHLF-STRHO | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Steering Hyd Oil Cooler | 2028-04-25 | 2028-04-25 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107017 | 25.04.2028 | 15000 | CCK-MP-HAUL-DT058 -STRSYS-STOCO | 7400 | 87864 | 1976
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Overhaul Water Tank Module | 2028-04-26 | 2028-04-26 | 1 hr | FY28 | 1 | 90028960 | B1 | 1000289083 | 26.04.2028 | 40000 | CCK-MP-SUPP-WC3112-STRUCT-WTANK | 5600 | 30406 | 30406
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 250hr Initial Valve Set | 2028-04-26 | 2028-04-26 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156060 | 26.04.2028 | 250 | CCK-MP-HAUL-DT158 -ENGINE | 7400 | 85964 | 11614
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Brake Slack Adjuster Front | 2028-04-26 | 2028-04-26 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000027076 | 26.04.2028 | 20000 | CCK-MP-HAUL-DT160 -BRKSYS-SLACK-SLACF | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Brake Slack Adjuster Rear | 2028-04-26 | 2028-04-26 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000027077 | 26.04.2028 | 20000 | CCK-MP-HAUL-DT160 -BRKSYS-SLACK-SLACR | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Transmission | 2028-04-26 | 2028-04-27 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272305 | 26.04.2028 | 18000 | CCK-MP-HAUL-DT091 -TRNSYS-TRANS | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Transmission Oil Cooler | 2028-04-26 | 2028-04-26 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000091380 | 26.04.2028 | 18000 | CCK-MP-HAUL-DT091 -TRNSYS-TROLC | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Differential | 2028-04-26 | 2028-04-27 | 38 hrs | FY28 | 66 | 90014504 | B1 | 1000024349 | 26.04.2028 | 18000 | CCK-MP-HAUL-DT091 -FDRSYS-DIFFL | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Replace Trans TCon System Hoses | 2028-04-26 | 2028-04-27 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000091399 | 26.04.2028 | 18000 | CCK-MP-HAUL-DT091 -TRNSYS-TRANS-TRNHO | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Replace Hoses Differential System | 2028-04-26 | 2028-04-26 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000091400 | 26.04.2028 | 18000 | CCK-MP-HAUL-DT091 -FDRSYS-DIFFL-DIFHO | 7400 | 83859 | 5241
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Replace Operator Cabin Dash Bulbs | 2028-04-27 | 2028-04-27 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158232 | 27.04.2028 | 3000 | CCK-MP-HAUL-DT767 -STRUCT-CABIN | 6800 | 74312 | 19669
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Tyre Sense Battery | 2028-04-27 | 2028-04-27 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153183 | 27.04.2028 | 24 Monthly | CCK-MP-HAUL-DT758 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Tyre Sense Battery | 2028-04-27 | 2028-04-27 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000167054 | 27.04.2028 | 24 Monthly | CCK-MP-HAUL-DT5314-MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Suspension LHR | 2028-04-27 | 2028-04-28 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000025016 | 27.04.2028 | 28000 | CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYLR | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Cyl Suspension RHR | 2028-04-27 | 2028-04-28 | 22 hrs | FY28 | 39 | 90002409 | B2 | 1000025017 | 27.04.2028 | 28000 | CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYRR | 7400 | 88657 | 15402
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Operator Cabin Dash Bulbs | 2028-04-28 | 2028-04-28 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158218 | 28.04.2028 | 3000 | CCK-MP-HAUL-DT753 -STRUCT-CABIN | 6800 | 85999 | 22050
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Tyre Sense Battery | 2028-04-28 | 2028-04-28 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153117 | 28.04.2028 | 24 Monthly | CCK-MP-HAUL-DT082 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Transmission | 2028-04-29 | 2028-04-30 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272315 | 29.04.2028 | 18000 | CCK-MP-HAUL-DT100 -TRNSYS-TRANS | 7400 | 87135 | 5195
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Engine Midlife Complete | 2028-04-30 | 2028-05-02 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285175 | 30.04.2028 | 12500 | CCK-MP-HAUL-DT757 -ENGINE | 6800 | 80700 | 25834
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Auto Lube Pump | 2028-04-30 | 2028-04-30 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095302 | 30.04.2028 | 8000 | CCK-MP-HAUL-DT770 -GRSYST-ALBPP | 6800 | 79304 | 9634
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Cyl Steering LH | 2028-04-30 | 2028-04-30 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000094497 | 30.04.2028 | 15000 | CCK-MP-HAUL-DT755 -STRSYS-STRCY-STCYL | 6800 | 84587 | 1533
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Cyl Steering RH | 2028-04-30 | 2028-04-30 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000094498 | 30.04.2028 | 15000 | CCK-MP-HAUL-DT755 -STRSYS-STRCY-STCYR | 6800 | 84587 | 3265
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Tyre Sense Battery | 2028-04-30 | 2028-04-30 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000167294 | 30.04.2028 | 24 Monthly | CCK-MP-HAUL-DT5317-MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Operators Seat | 2028-05-01 | 2028-05-01 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000024756 | 01.05.2028 | 15000 | CCK-MP-HAUL-DT097 -STRUCT-CABIN-SEATS | 7400 | 83804 | 1377
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Front Wheel Bearings LH | 2028-05-01 | 2028-05-02 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157136 | 01.05.2028 | 16000 | CCK-MP-HAUL-DT126 -STRUCT-AXLES-FWBLH | 7400 | 88657 | 3048
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Cyl Suspension LHF | 2028-05-01 | 2028-05-03 | 43 hrs | FY28 | 84 | 90002408 | B1 | 1000067461 | 01.05.2028 | 28000 | CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYLF | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Cyl Suspension RHF | 2028-05-01 | 2028-05-03 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067463 | 01.05.2028 | 28000 | CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYRF | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Cyl Suspension LHR | 2028-05-01 | 2028-05-02 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000024196 | 01.05.2028 | 28000 | CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYLR | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Tyre Sense Battery | 2028-05-01 | 2028-05-01 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153140 | 01.05.2028 | 24 Monthly | CCK-MP-HAUL-DT090 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Hub & Spindle LH | 2028-05-02 | 2028-05-03 | 32 hrs | FY28 | 60 | 90011363 | B1 | 1000094405 | 02.05.2028 | 18000 | CCK-MP-HAUL-DT753 -STRUCT-AXLES-HUBLH | 6800 | 85999 | 6237
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Suspension RHF | 2028-05-02 | 2028-05-04 | 60 hrs | FY28 | 112 | 90011366 | B1 | 1000094408 | 02.05.2028 | 18000 | CCK-MP-HAUL-DT753 -STRUCT-SUSPN-SCYRF | 6800 | 85999 | 6237
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Transmisson Calibration | 2028-05-02 | 2028-05-02 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298732 | 02.05.2028 | 4500 | CCK-MP-HAUL-DT151 -TRNSYS-TRANS | 7400 | 84253 | 9530
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 250hr Initial Valve Set | 2028-05-03 | 2028-05-03 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155976 | 03.05.2028 | 250 | CCK-MP-HAUL-DT136 -ENGINE | 7400 | 87780 | 87780
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Tyre Sense Battery | 2028-05-05 | 2028-05-05 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153176 | 05.05.2028 | 24 Monthly | CCK-MP-HAUL-DT751 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Auto Lube Pump | 2028-05-05 | 2028-05-05 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285786 | 05.05.2028 | 8000 | CCK-MP-HAUL-DT143 -GRSYST-ALBPP | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Auto Lube Pump | 2028-05-05 | 2028-05-05 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285781 | 05.05.2028 | 8000 | CCK-MP-HAUL-DT136 -GRSYST-ALBPP | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Spider Trans Driveshaft | 2028-05-05 | 2028-05-05 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000155235 | 05.05.2028 | 6000 | CCK-MP-HAUL-DT5255-FDRSYS-DRSHT-UNVSL | 7400 | 87580 | 10729
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Operators Seat | 2028-05-05 | 2028-05-05 | 3 hrs | FY28 | 6 | 90003066 | B2 | 1000239792 | 05.05.2028 | 6000 | CCK-MP-SUPP-WC008 -STRUCT-CABIN-SEATS | 3500 | 51417 | 182
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Steering Hyd Oil Cooler | 2028-05-05 | 2028-05-05 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000106976 | 05.05.2028 | 15000 | CCK-MP-HAUL-DT055 -STRSYS-STOCO | 7400 | 84122 | 7001
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Steering Brake Pump Compensator | 2028-05-06 | 2028-05-06 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204770 | 06.05.2028 | 6000 | CCK-MP-HAUL-DT766 -STRSYS-STPMP | 6800 | 78074 | 7137
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Brake Slack Adjuster Rear | 2028-05-06 | 2028-05-06 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000023667 | 06.05.2028 | 20000 | CCK-MP-HAUL-DT055 -BRKSYS-SLACK-SLACR | 7400 | 84122 | 7001
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Auto Lube Pump | 2028-05-07 | 2028-05-07 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285785 | 07.05.2028 | 8000 | CCK-MP-HAUL-DT142 -GRSYST-ALBPP | 7400 | 87027 | 11970
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Cyl Suspension RHF | 2028-05-07 | 2028-05-09 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067571 | 07.05.2028 | 28000 | CCK-MP-HAUL-DT142 -STRUCT-SUSPN-SCYRF | 7400 | 87027 | 11005
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Front Wheel Bearings LH | 2028-05-07 | 2028-05-08 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157152 | 07.05.2028 | 16000 | CCK-MP-HAUL-DT142 -STRUCT-AXLES-FWBLH | 7400 | 87027 | 13221
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Auto Lube Pump | 2028-05-07 | 2028-05-07 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095408 | 07.05.2028 | 8000 | CCK-MP-HAUL-DT772 -GRSYST-ALBPP | 6800 | 85256 | 10385
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Engine Midlife Complete | 2028-05-07 | 2028-05-08 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155984 | 07.05.2028 | 12000 | CCK-MP-HAUL-DT137 -ENGINE | 7400 | 84196 | 49397
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Pump Drive | 2028-05-07 | 2028-05-08 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000025414 | 07.05.2028 | 24000 | CCK-MP-HAUL-DT135 -ENGINE-PMPDR | 7400 | 82965 | 11119
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Tyre Sense Battery | 2028-05-09 | 2028-05-09 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153179 | 09.05.2028 | 24 Monthly | CCK-MP-HAUL-DT754 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Pump Drive | 2028-05-09 | 2028-05-10 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000026924 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -ENGINE-PMPDR | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Wheel End RH | 2028-05-09 | 2028-05-10 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000026935 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -FDRSYS-FDRVE-FDRRH | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Motor Lube Axle Rear & Hoses | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000272029 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYM01 | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl AOC Fan Motor Rear | 2028-05-09 | 2028-05-09 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000026937 | 09.05.2028 | 12000 | CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYM02 | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Axle Lube Hyd Pump | 2028-05-09 | 2028-05-09 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000154018 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYPUM | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Overhaul Accumulator Brake LHF | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026938 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BACCM-FRLFT | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Overhaul Accumulator Brake RHF | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026939 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BACCM-FRRGT | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Overhaul Accumulator Brake Rear | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000026940 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BACCM-BACCR | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Pump Brake Cooling | 2028-05-09 | 2028-05-09 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000026941 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-HYFPP | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Overhaul Valve Control Brake | 2028-05-09 | 2028-05-10 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000026942 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BRVLV | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Brake Oil Cooler Front | 2028-05-09 | 2028-05-09 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000091543 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BROCO-BROCF | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Brake Oil Cooler Rear | 2028-05-09 | 2028-05-09 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000091542 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BROCO-BROCR | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Motor Brake Oil Cooling | 2028-05-09 | 2028-05-09 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000026943 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -BRKSYS-BROCO-HYMO1 | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Hyd Pump Steering Main & Fan | 2028-05-09 | 2028-05-09 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000026946 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -STRSYS-STPMP | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Steering HMU | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000026947 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -STRSYS-STHMU | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Ovhl Accumulator Steering Front | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026950 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -STRSYS-STACC-SACCF | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Ovhl Accumulator Steering Middle | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026951 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -STRSYS-STACC-SACCM | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Ovhl Accumulator Steering Rear | 2028-05-09 | 2028-05-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000026952 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -STRSYS-STACC-SACCR | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Pump Hoist & Brake | 2028-05-09 | 2028-05-09 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000026955 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -HYDSYS-HOPMP | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Rear Axle Linkages | 2028-05-09 | 2028-05-11 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000026964 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -STRUCT-CHASS-AXLIK | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Drive Line Axle LH | 2028-05-09 | 2028-05-09 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124625 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -FDRSYS-DRLAX-AXLLH | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Drive Line Axle RH | 2028-05-09 | 2028-05-09 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124626 | 09.05.2028 | 24000 | CCK-MP-HAUL-DT158 -FDRSYS-DRLAX-AXLRH | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Spider Trans Driveshaft | 2028-05-09 | 2028-05-09 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154988 | 09.05.2028 | 6000 | CCK-MP-HAUL-DT158 -FDRSYS-DRSHT-UNVSL | 7400 | 85964 | 11104
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Transmission Pump | 2028-05-10 | 2028-05-10 | 6 hrs | FY28 | 6 | 90003991 | B2 | 1000079248 | 10.05.2028 | 10000 | CCK-MP-SUPP-WC3112-TRNSYS-TRPMP-TMCPP | 5600 | 52240 | 2198
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Steering Bell Crank & Links | 2028-05-10 | 2028-05-11 | 20 hrs | FY28 | 36 | 90028566 | B1 | 1000317668 | 10.05.2028 | 30000 | CCK-MP-HAUL-DT5314-STRSYS-STLTR-STLAC | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Operators Seat | 2028-05-10 | 2028-05-10 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000167261 | 10.05.2028 | 15000 | CCK-MP-HAUL-DT5317-STRUCT-CABIN-SEATS | 7400 | 45576 | 12321
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Steering Linkages | 2028-05-11 | 2028-05-11 | 15 hrs | FY28 | 28 | 90028568 | B1 | 1000317631 | 11.05.2028 | 15000 | CCK-MP-HAUL-DT147 -STRSYS-STLTR | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Cyl Steering RH | 2028-05-11 | 2028-05-11 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000167254 | 11.05.2028 | 15000 | CCK-MP-HAUL-DT5317-STRSYS-STRCY-STCYR | 7400 | 45576 | 2004
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Air Drier and Tank | 2028-05-12 | 2028-05-12 | 12 hrs | FY28 | 24 | 90004010 | B2 | 1000079276 | 12.05.2028 | 9000 | CCK-MP-SUPP-WC3112-PNEUMC-AIRDR | 5600 | 52240 | 8166
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Replace Steering System Hoses | 2028-05-12 | 2028-05-14 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000083406 | 12.05.2028 | 15000 | CCK-MP-HAUL-DT147 -STRSYS-STHLF-STRHO | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Engine Cat C175-16 | 2028-05-12 | 2028-05-15 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000155877 | 12.05.2028 | 24000 | CCK-MP-HAUL-DT057 -ENGINE | 7400 | 91273 | 91273
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Pump Drive | 2028-05-12 | 2028-05-13 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000023772 | 12.05.2028 | 24000 | CCK-MP-HAUL-DT057 -ENGINE-PMPDR | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Torque Converter | 2028-05-12 | 2028-05-13 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000023777 | 12.05.2028 | 24000 | CCK-MP-HAUL-DT057 -TRNSYS-TRQUE | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Ovhl Accumulator Steering Rear | 2028-05-12 | 2028-05-12 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000023800 | 12.05.2028 | 24000 | CCK-MP-HAUL-DT057 -STRSYS-STACC-SACCR | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Rear Axle Linkages | 2028-05-12 | 2028-05-14 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000023811 | 12.05.2028 | 24000 | CCK-MP-HAUL-DT057 -STRUCT-CHASS-AXLIK | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Transmission Oil Cooler | 2028-05-12 | 2028-05-12 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000082480 | 12.05.2028 | 18000 | CCK-MP-HAUL-DT056 -TRNSYS-TROLC | 7400 | 84421 | 4851
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Auto Lube Pump | 2028-05-13 | 2028-05-13 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095090 | 13.05.2028 | 8000 | CCK-MP-HAUL-DT766 -GRSYST-ALBPP | 6800 | 78074 | 3021
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Steering LH | 2028-05-13 | 2028-05-13 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000024742 | 13.05.2028 | 15000 | CCK-MP-HAUL-DT097 -STRSYS-STRCY-STCYL | 7400 | 83804 | 1815
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Steering RH | 2028-05-13 | 2028-05-13 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000024743 | 13.05.2028 | 15000 | CCK-MP-HAUL-DT097 -STRSYS-STRCY-STCYR | 7400 | 83804 | 1815
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Radiator Engine Cooling | 2028-05-13 | 2028-05-14 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307470 | 13.05.2028 | 24000 | CCK-MP-HAUL-DT057 -ENGINE-COSYS-RADTR | 7400 | 91273 | 58459
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl AOC Fan Motor Rear | 2028-05-13 | 2028-05-13 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000023785 | 13.05.2028 | 12000 | CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYM02 | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Spider Trans Driveshaft | 2028-05-13 | 2028-05-13 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154924 | 13.05.2028 | 6000 | CCK-MP-HAUL-DT057 -FDRSYS-DRSHT-UNVSL | 7400 | 91273 | 3875
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Steering Hyd Oil Cooler | 2028-05-14 | 2028-05-14 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107004 | 14.05.2028 | 15000 | CCK-MP-HAUL-DT147 -STRSYS-STOCO | 7400 | 84659 | 16832
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Adjust Engine Valve Set | 2028-05-14 | 2028-05-14 | 12 hrs | FY28 | 24 | 90015766 | B1 | 1000269913 | 14.05.2028 | 4500 | CCK-MP-SUPP-WC220 -ENGINE | 4300 | 58137 | 14252
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Service Airconditioner | 2028-05-14 | 2028-05-15 | 24 hrs | FY28 | 24 | 90018538 | B2 | 1000269915 | 14.05.2028 | 4500 | CCK-MP-SUPP-WC220 -STRUCT-CABIN-AIRCN | 4300 | 58137 | 18617
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Tyre Sense Battery | 2028-05-14 | 2028-05-14 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153170 | 14.05.2028 | 24 Monthly | CCK-MP-HAUL-DT161 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Transmisson Calibration | 2028-05-15 | 2028-05-15 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298744 | 15.05.2028 | 4500 | CCK-MP-HAUL-DT5202-TRNSYS-TRANS | 7400 | 84333 | 975
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Ovhl Axle A Frame | 2028-05-15 | 2028-05-16 | 36 hrs | FY28 | 60 | 90002922 | B2 | 1000074506 | 15.05.2028 | 15000 | CCK-MP-SUPP-WC224 -STRUCT-CHASS-AFRME | 5000 | 71088 | 6229
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Brake Slack Adjuster Front | 2028-05-16 | 2028-05-16 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025758 | 16.05.2028 | 20000 | CCK-MP-HAUL-DT140 -BRKSYS-SLACK-SLACF | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Brake Slack Adjuster Rear | 2028-05-16 | 2028-05-16 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000025759 | 16.05.2028 | 20000 | CCK-MP-HAUL-DT140 -BRKSYS-SLACK-SLACR | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Service Air Conditioner 12M | 2028-05-17 | 2028-05-18 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174178 | 17.05.2028 | 12 Monthly | CCK-MP-HAUL-DT149 -STRUCT-CABIN-AIRCN | 7400 | 86975 | 9207
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Replace Operator Cabin Dash Bulbs | 2028-05-18 | 2028-05-18 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158239 | 18.05.2028 | 3000 | CCK-MP-HAUL-DT774 -STRUCT-CABIN | 6800 | 81047 | 28490
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Steering LH | 2028-05-18 | 2028-05-18 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000026618 | 18.05.2028 | 15000 | CCK-MP-HAUL-DT153 -STRSYS-STRCY-STCYL | 7400 | 84230 | 1779
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Cyl Steering LH | 2028-05-19 | 2028-05-19 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000095504 | 19.05.2028 | 15000 | CCK-MP-HAUL-DT774 -STRSYS-STRCY-STCYL | 6800 | 81047 | 3051
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Cyl Steering RH | 2028-05-19 | 2028-05-19 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000095505 | 19.05.2028 | 15000 | CCK-MP-HAUL-DT774 -STRSYS-STRCY-STCYR | 6800 | 81047 | 3051
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Steering RH | 2028-05-20 | 2028-05-20 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000026619 | 20.05.2028 | 15000 | CCK-MP-HAUL-DT153 -STRSYS-STRCY-STCYR | 7400 | 84230 | 1779
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Cyl Steering RH | 2028-05-20 | 2028-05-20 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000026751 | 20.05.2028 | 15000 | CCK-MP-HAUL-DT155 -STRSYS-STRCY-STCYR | 7400 | 81407 | 1746
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Transmission Pump | 2028-05-21 | 2028-05-21 | 4 hrs | FY28 | 4 | 90000897 | B2 | 1000033356 | 21.05.2028 | 11000 | CCK-MP-SUPP-WC225 -TRNSYS-TRPMP-TMCPP | 5000 | 75244 | 1997
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Relay Front | 2028-05-21 | 2028-05-21 | 2 hrs | FY28 | 2 | 90002915 | B2 | 1000040613 | 21.05.2028 | 11000 | CCK-MP-SUPP-WC225 -PNEUMC-BRVLR-SVBRF | 5000 | 75244 | 2013
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Operators Seat | 2028-05-21 | 2028-05-21 | 3 hrs | FY28 | 6 | 90002395 | B1 | 1000027095 | 21.05.2028 | 15000 | CCK-MP-HAUL-DT160 -STRUCT-CABIN-SEATS | 7400 | 85085 | 16709
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Auto Lube Pump | 2028-05-21 | 2028-05-21 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285623 | 21.05.2028 | 8000 | CCK-MP-HAUL-DT055 -GRSYST-ALBPP | 7400 | 84122 | 15901
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Transmisson Calibration | 2028-05-22 | 2028-05-22 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298730 | 22.05.2028 | 4500 | CCK-MP-HAUL-DT149 -TRNSYS-TRANS | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Service Air Conditioner 12M | 2028-05-22 | 2028-05-23 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174118 | 22.05.2028 | 12 Monthly | CCK-MP-HAUL-DT091 -STRUCT-CABIN-AIRCN | 7400 | 83859 | 23814
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Auto Lube Pump | 2028-05-23 | 2028-05-23 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285782 | 23.05.2028 | 8000 | CCK-MP-HAUL-DT137 -GRSYST-ALBPP | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Brake Slack Adjuster Front | 2028-05-23 | 2028-05-23 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000166929 | 23.05.2028 | 20000 | CCK-MP-HAUL-DT5313-BRKSYS-SLACK-SLACF | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Brake Slack Adjuster Rear | 2028-05-23 | 2028-05-23 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000166930 | 23.05.2028 | 20000 | CCK-MP-HAUL-DT5313-BRKSYS-SLACK-SLACR | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Brake Oil Cooler Front | 2028-05-23 | 2028-05-23 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000091389 | 23.05.2028 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BROCO-BROCF | 7400 | 83859 | 10692
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Brake Oil Cooler Rear | 2028-05-23 | 2028-05-23 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000091388 | 23.05.2028 | 24000 | CCK-MP-HAUL-DT091 -BRKSYS-BROCO-BROCR | 7400 | 83859 | 10692
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Auto Lube Pump | 2028-05-24 | 2028-05-24 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094560 | 24.05.2028 | 8000 | CCK-MP-HAUL-DT756 -GRSYST-ALBPP | 6800 | 78754 | 3428
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Auto Lube Pump | 2028-05-24 | 2028-05-24 | 2 hrs | FY28 | 2 | 90011565 | B1 | 1000093069 | 24.05.2028 | 9000 | CCK-MP-SUPP-SV220 -GRSYST-ALBPP | 5100 | 58259 | 8034
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Service Air Conditioner 12M | 2028-05-24 | 2028-05-25 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174192 | 24.05.2028 | 12 Monthly | CCK-MP-HAUL-DT5255-STRUCT-CABIN-AIRCN | 7400 | 87580 | 87580
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 250hr Initial Valve Set | 2028-05-25 | 2028-05-25 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155880 | 25.05.2028 | 250 | CCK-MP-HAUL-DT057 -ENGINE | 7400 | 91273 | 91273
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Steering System Hoses | 2028-05-25 | 2028-05-27 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000083368 | 25.05.2028 | 15000 | CCK-MP-HAUL-DT5255-STRSYS-STHLF-STRHO | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Steering Hyd Oil Cooler | 2028-05-25 | 2028-05-25 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107001 | 25.05.2028 | 15000 | CCK-MP-HAUL-DT5255-STRSYS-STOCO | 7400 | 87580 | 16634
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Cyl Steering LH | 2028-05-26 | 2028-05-26 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000095345 | 26.05.2028 | 15000 | CCK-MP-HAUL-DT771 -STRSYS-STRCY-STCYL | 6800 | 84423 | 2900
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Operator Cabin Dash Bulbs | 2028-05-26 | 2028-05-26 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158237 | 26.05.2028 | 3000 | CCK-MP-HAUL-DT772 -STRUCT-CABIN | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Auto Lube Pump | 2028-05-27 | 2028-05-27 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000095196 | 27.05.2028 | 8000 | CCK-MP-HAUL-DT768 -GRSYST-ALBPP | 6800 | 79837 | 12182
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Transmission | 2028-05-27 | 2028-05-28 | 22 hrs | FY28 | 39 | 90026996 | B1 | 1000272511 | 27.05.2028 | 18000 | CCK-MP-HAUL-DT5314-TRNSYS-TRANS | 7400 | 45898 | 950
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Spider Trans Driveshaft | 2028-05-28 | 2028-05-28 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154954 | 28.05.2028 | 6000 | CCK-MP-HAUL-DT130 -FDRSYS-DRSHT-UNVSL | 7400 | 85185 | 10692
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Steering Hyd Oil Cooler | 2028-05-28 | 2028-05-28 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107003 | 28.05.2028 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STOCO | 7400 | 83062 | 990
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Steering Bleed Down Manifold | 2028-05-30 | 2028-05-30 | 6.5 hrs | FY28 | 8 | 90011347 | B1 | 1000094441 | 30.05.2028 | 25000 | CCK-MP-HAUL-DT754 -STRSYS-STBDM | 6800 | 83256 | 12630
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Replace Operator Cabin Dash Bulbs | 2028-05-30 | 2028-05-30 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158219 | 30.05.2028 | 3000 | CCK-MP-HAUL-DT754 -STRUCT-CABIN | 6800 | 83256 | 83256
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl PTO Uni's & Driveshaft | 2028-05-30 | 2028-05-30 | 2 hrs | FY28 | 2 | 90031094 | B1 | 1000307814 | 30.05.2028 | 10000 | CCK-MP-SUPP-WC3111-ENGINE-PMPDR-DRSHT | 5600 | 51257 | 9904
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Steering Brake Pump Compensator | 2028-05-31 | 2028-05-31 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204775 | 31.05.2028 | 6000 | CCK-MP-HAUL-DT771 -STRSYS-STPMP | 6800 | 84423 | 18016
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Replace Operator Cabin Dash Bulbs | 2028-05-31 | 2028-05-31 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158236 | 31.05.2028 | 3000 | CCK-MP-HAUL-DT771 -STRUCT-CABIN | 6800 | 84423 | 84423
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Hyd Pump Steering & Brake | 2028-05-31 | 2028-06-01 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204431 | 31.05.2028 | 12000 | CCK-MP-HAUL-DT752 -STRSYS-STPMP | 6800 | 80681 | 13250
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Brake Manifold | 2028-05-31 | 2028-05-31 | 13.5 hrs | FY28 | 13.5 | 90029265 | B1 | 1000292143 | 31.05.2028 | 25000 | CCK-MP-HAUL-DT754 -BRKSYS-BRVLV | 6800 | 83256 | 12630
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Auto Lube Pump | 2028-05-31 | 2028-05-31 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285634 | 31.05.2028 | 8000 | CCK-MP-HAUL-DT097 -GRSYST-ALBPP | 7400 | 83804 | 2994
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Replace Operator Cabin Dash Bulbs | 2028-06-01 | 2028-06-01 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158234 | 01.06.2028 | 3000 | CCK-MP-HAUL-DT769 -STRUCT-CABIN | 6800 | 80508 | 80508
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Operator Seat | 2028-06-01 | 2028-06-01 | 3 hrs | FY28 | 6 | 90011567 | B1 | 1000098143 | 01.06.2028 | 6000 | CCK-MP-SUPP-WC221 -STRUCT-CABIN-SEATS | 4000 | 56923 | 4771
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Service Air Conditioner 12M | 2028-06-01 | 2028-06-02 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174177 | 01.06.2028 | 12 Monthly | CCK-MP-HAUL-DT148 -STRUCT-CABIN-AIRCN | 7400 | 85451 | 18023
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Steering Bleed Down Manifold | 2028-06-02 | 2028-06-02 | 6.5 hrs | FY28 | 8 | 90011347 | B1 | 1000095501 | 02.06.2028 | 25000 | CCK-MP-HAUL-DT774 -STRSYS-STBDM | 6800 | 81047 | 12760
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Air Conditioner 12M-Service | 2028-06-02 | 2028-06-03 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000272732 | 02.06.2028 | 12 Monthly | CCK-MP-SUPP-PM0001-STRUCT-CABIN-AIRCN | 3400 | 48287 | 48287
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Replace Operator Cabin Dash Bulbs | 2028-06-03 | 2028-06-03 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158231 | 03.06.2028 | 3000 | CCK-MP-HAUL-DT766 -STRUCT-CABIN | 6800 | 78074 | 10283
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Pump & Motor Sec Str | 2028-06-03 | 2028-06-03 | 6 hrs | FY28 | 6 | 90011558 | B1 | 1000093007 | 03.06.2028 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STEMG-SESPP | 5100 | 64374 | 8815
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Steering HMU | 2028-06-03 | 2028-06-03 | 12 hrs | FY28 | 12 | 90011553 | B1 | 1000093001 | 03.06.2028 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STHMU | 5100 | 64374 | 8815
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Valve Steering | 2028-06-03 | 2028-06-03 | 12 hrs | FY28 | 12 | 90011554 | B1 | 1000093002 | 03.06.2028 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STVLV | 5100 | 64374 | 8815
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Replace Cylinder Steering LH | 2028-06-03 | 2028-06-03 | 10 hrs | FY28 | 10 | 90011555 | B1 | 1000098077 | 03.06.2028 | 18000 | CCK-MP-SUPP-WC220 -STRSYS-STRCY-STCYL | 4300 | 58137 | 9516
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Accumulator Hyd Steer Front | 2028-06-04 | 2028-06-04 | 7.5 hrs | FY28 | 11.5 | 90011352 | B1 | 1000095135 | 04.06.2028 | 25000 | CCK-MP-HAUL-DT767 -STRSYS-STACC-SACCF | 6800 | 74312 | 1401
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Accumulator Hyd Steering Rear | 2028-06-04 | 2028-06-04 | 7.5 hrs | FY28 | 11.5 | 90011353 | B1 | 1000095136 | 04.06.2028 | 25000 | CCK-MP-HAUL-DT767 -STRSYS-STACC-SACCR | 6800 | 74312 | 1401
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Cyl Steering LH | 2028-06-04 | 2028-06-04 | 12 hrs | FY28 | 20 | 90002385 | B1 | 1000025567 | 04.06.2028 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STRCY-STCYL | 7400 | 84196 | 143
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Hyd Pump Steering & Brake | 2028-06-06 | 2028-06-07 | 28 hrs | FY28 | 38 | 90019919 | B1 | 1000204436 | 06.06.2028 | 12000 | CCK-MP-HAUL-DT756 -STRSYS-STPMP | 6800 | 78754 | 308
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Engine Module | 2028-06-06 | 2028-06-10 | 102 hrs | FY28 | 226 | 90011318 | B1 | 1000094413 | 06.06.2028 | 25000 | CCK-MP-HAUL-DT754 -ENGINE | 6800 | 83256 | 12630
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Cyl Suspension RHF | 2028-06-06 | 2028-06-08 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067455 | 06.06.2028 | 28000 | CCK-MP-HAUL-DT086 -STRUCT-SUSPN-SCYRF | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Cyl Suspension LHR | 2028-06-06 | 2028-06-07 | 22 hrs | FY28 | 39 | 90002409 | B1 | 1000024070 | 06.06.2028 | 28000 | CCK-MP-HAUL-DT086 -STRUCT-SUSPN-SCYLR | 7400 | 86822 | 14283
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Adjust Engine Valve Set | 2028-06-07 | 2028-06-07 | 12 hrs | FY28 | 24 | 90015645 | B1 | 1000269779 | 07.06.2028 | 4500 | CCK-MP-SUPP-SV221 -ENGINE | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Service Airconditioner | 2028-06-07 | 2028-06-08 | 24 hrs | FY28 | 24 | 90018538 | B2 | 1000269902 | 07.06.2028 | 4500 | CCK-MP-SUPP-SV221 -STRUCT-CABIN-AIRCN | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Auto Lube Pump | 2028-06-07 | 2028-06-07 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285638 | 07.06.2028 | 8000 | CCK-MP-HAUL-DT127 -GRSYST-ALBPP | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Front Wheel Bearings LH | 2028-06-07 | 2028-06-08 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157138 | 07.06.2028 | 16000 | CCK-MP-HAUL-DT127 -STRUCT-AXLES-FWBLH | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Pump Drive | 2028-06-07 | 2028-06-08 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000026396 | 07.06.2028 | 24000 | CCK-MP-HAUL-DT150 -ENGINE-PMPDR | 7400 | 86656 | 10014
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Brake Manifold | 2028-06-08 | 2028-06-08 | 13.5 hrs | FY28 | 13.5 | 90029265 | B1 | 1000292183 | 08.06.2028 | 25000 | CCK-MP-HAUL-DT774 -BRKSYS-BRVLV | 6800 | 81047 | 39470
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Transmisson Calibration | 2028-06-08 | 2028-06-08 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298667 | 08.06.2028 | 4500 | CCK-MP-HAUL-DT082 -TRNSYS-TRANS | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Radiator Engine Cooling | 2028-06-09 | 2028-06-10 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307508 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -ENGINE-COSYS-RADTR | 7400 | 84196 | 32285
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Pump Drive | 2028-06-09 | 2028-06-10 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000025543 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -ENGINE-PMPDR | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Motor Lube Axle Rear & Hoses | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000272001 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYM01 | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl AOC Fan Motor Rear | 2028-06-09 | 2028-06-09 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000025556 | 09.06.2028 | 12000 | CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYM02 | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Overhaul Accumulator Brake LHF | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025557 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BACCM-FRLFT | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Overhaul Accumulator Brake RHF | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025558 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BACCM-FRRGT | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Overhaul Accumulator Brake Rear | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000025559 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BACCM-BACCR | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Pump Brake Cooling | 2028-06-09 | 2028-06-09 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000025560 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-HYFPP | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Overhaul Valve Control Brake | 2028-06-09 | 2028-06-10 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000025561 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BRVLV | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Brake Oil Cooler Front | 2028-06-09 | 2028-06-09 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000083230 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BROCO-BROCF | 7400 | 84196 | 866
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Brake Oil Cooler Rear | 2028-06-09 | 2028-06-09 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083229 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BROCO-BROCR | 7400 | 84196 | 866
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Motor Brake Oil Cooling | 2028-06-09 | 2028-06-09 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000025562 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BROCO-HYMO1 | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Hyd Pump Steering Main & Fan | 2028-06-09 | 2028-06-09 | 17 hrs | FY28 | 17 | 90002383 | B1 | 1000025565 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -STRSYS-STPMP | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Steering HMU | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000025566 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -STRSYS-STHMU | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Ovhl Accumulator Steering Front | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025569 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -STRSYS-STACC-SACCF | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Ovhl Accumulator Steering Middle | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025570 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -STRSYS-STACC-SACCM | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Ovhl Accumulator Steering Rear | 2028-06-09 | 2028-06-09 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000025571 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -STRSYS-STACC-SACCR | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Rear Axle Linkages | 2028-06-09 | 2028-06-11 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000025582 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -STRUCT-CHASS-AXLIK | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Wheel Group Front RH | 2028-06-09 | 2028-06-10 | 28 hrs | FY28 | 54 | 90017287 | B1 | 1000157235 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -STRUCT-AXLES-HUBRH | 7400 | 84196 | 0
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Replace Hoses Hoist System | 2028-06-09 | 2028-06-10 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083225 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -HYDSYS-HDHLF-HSTHO | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Replace Brake System Hoses | 2028-06-09 | 2028-06-11 | 46 hrs | FY28 | 90 | 90010129 | B4 | 1000083231 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BRHLF-BRHOS | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Brake Cooling System Hoses | 2028-06-09 | 2028-06-10 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000083232 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -BRKSYS-BRHLF-CBRHO | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Drive Line Axle LH | 2028-06-09 | 2028-06-09 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124599 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -FDRSYS-DRLAX-AXLLH | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Drive Line Axle RH | 2028-06-09 | 2028-06-09 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124600 | 09.06.2028 | 24000 | CCK-MP-HAUL-DT137 -FDRSYS-DRLAX-AXLRH | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Spider Trans Driveshaft | 2028-06-09 | 2028-06-09 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154960 | 09.06.2028 | 6000 | CCK-MP-HAUL-DT137 -FDRSYS-DRSHT-UNVSL | 7400 | 84196 | 1006
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Tyre Sense Battery | 2028-06-10 | 2028-06-10 | 2 hrs | FY28 | 2 | 90017022 | B1 | 1000153112 | 10.06.2028 | 24 Monthly | CCK-MP-HAUL-DT054 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Pump Drive | 2028-06-10 | 2028-06-11 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000026726 | 10.06.2028 | 24000 | CCK-MP-HAUL-DT155 -ENGINE-PMPDR | 7400 | 81407 | 10315
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Steering LH | 2028-06-12 | 2028-06-12 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000095398 | 12.06.2028 | 15000 | CCK-MP-HAUL-DT772 -STRSYS-STRCY-STCYL | 6800 | 85256 | 2281
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Operators Seat | 2028-06-12 | 2028-06-12 | 4 hrs | FY28 | 4 | 90011360 | B1 | 1000095409 | 12.06.2028 | 15000 | CCK-MP-HAUL-DT772 -STRUCT-CABIN-SEATS | 6800 | 85256 | 17514
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Drive Shaft Transmission | 2028-06-12 | 2028-06-12 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154987 | 12.06.2028 | 18000 | CCK-MP-HAUL-DT157 -FDRSYS-DRSHT | 7400 | 83041 | 8363
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Wheel End RH | 2028-06-13 | 2028-06-14 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000024729 | 13.06.2028 | 24000 | CCK-MP-HAUL-DT097 -FDRSYS-FDRVE-FDRRH | 7400 | 83804 | 10189
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Transmission | 2028-06-13 | 2028-06-14 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272353 | 13.06.2028 | 18000 | CCK-MP-HAUL-DT157 -TRNSYS-TRANS | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Transmission Oil Cooler | 2028-06-13 | 2028-06-13 | 12 hrs | FY28 | 12 | 90010097 | B1 | 1000091512 | 13.06.2028 | 18000 | CCK-MP-HAUL-DT157 -TRNSYS-TROLC | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Auto Lube Pump | 2028-06-13 | 2028-06-13 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285626 | 13.06.2028 | 8000 | CCK-MP-HAUL-DT058 -GRSYST-ALBPP | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Front Wheel Bearings LH | 2028-06-13 | 2028-06-14 | 23 hrs | FY28 | 44 | 90017284 | B1 | 1000157112 | 13.06.2028 | 16000 | CCK-MP-HAUL-DT058 -STRUCT-AXLES-FWBLH | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Front Wheel Bearings RH | 2028-06-13 | 2028-06-14 | 23 hrs | FY28 | 44 | 90017285 | B1 | 1000157200 | 13.06.2028 | 16000 | CCK-MP-HAUL-DT058 -STRUCT-AXLES-FWBRH | 7400 | 87865 | 1976
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Cyl Suspension LHF | 2028-06-14 | 2028-06-16 | 60 hrs | FY28 | 112 | 90011365 | B1 | 1000095043 | 14.06.2028 | 18000 | CCK-MP-HAUL-DT765 -STRUCT-SUSPN-SCYLF | 6800 | 78429 | 5559
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Slack Adjuster Front | 2028-06-14 | 2028-06-14 | 2 hrs | FY28 | 2 | 90002910 | B2 | 1000040609 | 14.06.2028 | 11000 | CCK-MP-SUPP-WC225 -BRKSYS-SLACK-SLACF | 5000 | 75244 | 1432
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Engine Cat C175-16 | 2028-06-15 | 2028-06-18 | 84 hrs | FY28 | 137 | 90015881 | B1 | 1000155943 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -ENGINE | 7400 | 87442 | 32853
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Radiator Engine Cooling | 2028-06-15 | 2028-06-16 | 39 hrs | FY28 | 62 | 90031072 | B1 | 1000307494 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -ENGINE-COSYS-RADTR | 7400 | 87442 | 32853
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Pump Drive | 2028-06-15 | 2028-06-16 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000024844 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -ENGINE-PMPDR | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Torque Converter | 2028-06-15 | 2028-06-16 | 27 hrs | FY28 | 53 | 90002369 | B1 | 1000024849 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -TRNSYS-TRQUE | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Wheel End RH | 2028-06-15 | 2028-06-16 | 32.5 hrs | FY28 | 58.5 | 90007352 | B1 | 1000024855 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -FDRSYS-FDRVE-FDRRH | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Motor Lube Axle Rear & Hoses | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 8 | 90026943 | B1 | 1000271987 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYM01 | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl AOC Fan Motor Rear | 2028-06-15 | 2028-06-15 | 6 hrs | FY28 | 6 | 90002376 | B1 | 1000024857 | 15.06.2028 | 12000 | CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYM02 | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Axle Lube Hyd Pump | 2028-06-15 | 2028-06-15 | 4 hrs | FY28 | 4 | 90010102 | B1 | 1000083052 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYPUM | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Overhaul Accumulator Brake LHF | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024858 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BACCM-FRLFT | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Overhaul Accumulator Brake RHF | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024859 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BACCM-FRRGT | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Overhaul Accumulator Brake Rear | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 11 | 90002378 | B1 | 1000024860 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BACCM-BACCR | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Pump Brake Cooling | 2028-06-15 | 2028-06-15 | 9 hrs | FY28 | 17 | 90002379 | B1 | 1000024861 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-HYFPP | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Overhaul Valve Control Brake | 2028-06-15 | 2028-06-16 | 20 hrs | FY28 | 20 | 90002380 | B2 | 1000024862 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BRVLV | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Brake Oil Cooler Front | 2028-06-15 | 2028-06-15 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000083059 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BROCO-BROCF | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Brake Oil Cooler Rear | 2028-06-15 | 2028-06-15 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000083058 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BROCO-BROCR | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Motor Brake Oil Cooling | 2028-06-15 | 2028-06-15 | 3 hrs | FY28 | 3 | 90002381 | B1 | 1000024863 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BROCO-HYMO1 | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Steering HMU | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 8 | 90002384 | B1 | 1000024867 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -STRSYS-STHMU | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Ovhl Accumulator Steering Front | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024870 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -STRSYS-STACC-SACCF | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Ovhl Accumulator Steering Middle | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024871 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -STRSYS-STACC-SACCM | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Ovhl Accumulator Steering Rear | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 12 | 90002386 | B1 | 1000024872 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -STRSYS-STACC-SACCR | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Pump Hoist & Brake | 2028-06-15 | 2028-06-15 | 9 hrs | FY28 | 15 | 90002388 | B1 | 1000024874 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -HYDSYS-HOPMP | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Rear Axle Linkages | 2028-06-15 | 2028-06-17 | 57 hrs | FY28 | 113 | 90002396 | B1 | 1000024883 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -STRUCT-CHASS-AXLIK | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Wheel Group Front LH | 2028-06-15 | 2028-06-16 | 28 hrs | FY28 | 54 | 90017286 | B1 | 1000157133 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -STRUCT-AXLES-HUBLH | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Suspension RHF | 2028-06-15 | 2028-06-17 | 43 hrs | FY28 | 84 | 90002408 | B2 | 1000067507 | 15.06.2028 | 28000 | CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYRF | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Hoses Hoist System | 2028-06-15 | 2028-06-16 | 20 hrs | FY28 | 40 | 90010105 | B1 | 1000083054 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -HYDSYS-HDHLF-HSTHO | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Brake System Hoses | 2028-06-15 | 2028-06-17 | 46 hrs | FY28 | 90 | 90010129 | B3 | 1000083060 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BRHLF-BRHOS | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Brake Cooling System Hoses | 2028-06-15 | 2028-06-16 | 30 hrs | FY28 | 60 | 90010130 | B1 | 1000083061 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -BRKSYS-BRHLF-CBRHO | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Drive Line Axle LH | 2028-06-15 | 2028-06-15 | 2 hrs | FY28 | 4 | 90014919 | B1 | 1000124589 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -FDRSYS-DRLAX-AXLLH | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Drive Line Axle RH | 2028-06-15 | 2028-06-15 | 2 hrs | FY28 | 4 | 90014943 | B1 | 1000124590 | 15.06.2028 | 24000 | CCK-MP-HAUL-DT099 -FDRSYS-DRLAX-AXLRH | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Auto Lube Pump | 2028-06-15 | 2028-06-15 | 3 hrs | FY28 | 3 | 90002391 | B1 | 1000285805 | 15.06.2028 | 8000 | CCK-MP-HAUL-DT5313-GRSYST-ALBPP | 7400 | 44693 | 7599
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Radiator | 2028-06-15 | 2028-06-15 | 12 hrs | FY28 | 24 | 90000905 | B2 | 1000033279 | 15.06.2028 | 22000 | CCK-MP-SUPP-WC224 -ENGINE-COSYS-RADTR | 5000 | 71088 | 12650
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Auto Lube Pump | 2028-06-16 | 2028-06-16 | 2.5 hrs | FY28 | 2.5 | 90011370 | B1 | 1000094878 | 16.06.2028 | 8000 | CCK-MP-HAUL-DT762 -GRSYST-ALBPP | 6800 | 76486 | 10392
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Steering Bleed Down Manifold | 2028-06-17 | 2028-06-17 | 6.5 hrs | FY28 | 8 | 90011347 | B1 | 1000095130 | 17.06.2028 | 25000 | CCK-MP-HAUL-DT767 -STRSYS-STBDM | 6800 | 74312 | 38557
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Replace Operator Cabin Dash Bulbs | 2028-06-17 | 2028-06-17 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158217 | 17.06.2028 | 3000 | CCK-MP-HAUL-DT752 -STRUCT-CABIN | 6800 | 80681 | 80681
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Replace Operator Cabin Dash Bulbs | 2028-06-18 | 2028-06-18 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158225 | 18.06.2028 | 3000 | CCK-MP-HAUL-DT760 -STRUCT-CABIN | 6800 | 80390 | 80390
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Brake Manifold | 2028-06-18 | 2028-06-18 | 13.5 hrs | FY28 | 13.5 | 90029265 | B1 | 1000292165 | 18.06.2028 | 25000 | CCK-MP-HAUL-DT765 -BRKSYS-BRVLV | 6800 | 78429 | 12529
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Engine Module | 2028-06-18 | 2028-06-22 | 102 hrs | FY28 | 226 | 90011318 | B1 | 1000094678 | 18.06.2028 | 25000 | CCK-MP-HAUL-DT759 -ENGINE | 6800 | 79716 | 12763
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 WaterTank Cannon & Spray Sys Insp | 2028-06-18 | 2028-06-18 | 3 hrs | FY28 | 3 | 90036929 | B1 | 1000368896 | 18.06.2028 | 6 Monthly | CCK-MP-SUPP-WC3111-STRUCT-WTANK | 5600 | 28968 | 28968
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Service Air Conditioner 12M | 2028-06-18 | 2028-06-19 | 18 hrs | FY28 | 18 | 90018230 | B1 | 1000174194 | 18.06.2028 | 12 Monthly | CCK-MP-HAUL-DT5317-STRUCT-CABIN-AIRCN | 7400 | 45576 | 32701
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Cyl Steering RH | 2028-06-19 | 2028-06-19 | 9 hrs | FY28 | 15 | 90011351 | B1 | 1000095187 | 19.06.2028 | 15000 | CCK-MP-HAUL-DT768 -STRSYS-STRCY-STCYR | 6800 | 79837 | 2121
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Engine Midlife Complete | 2028-06-19 | 2028-06-20 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000155870 | 19.06.2028 | 12000 | CCK-MP-HAUL-DT055 -ENGINE | 7400 | 84122 | 54657
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Pump Drive | 2028-06-20 | 2028-06-21 | 20 hrs | FY28 | 39 | 90002365 | B1 | 1000027056 | 20.06.2028 | 24000 | CCK-MP-HAUL-DT160 -ENGINE-PMPDR | 7400 | 85085 | 10046
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Engine Midlife Complete | 2028-06-21 | 2028-06-23 | 49 hrs | FY28 | 76 | 90028571 | B1 | 1000285528 | 21.06.2028 | 12500 | CCK-MP-HAUL-DT770 -ENGINE | 6800 | 79305 | 1525
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 250hr Initial Valve Set | 2028-06-21 | 2028-06-21 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000156084 | 21.06.2028 | 250 | CCK-MP-HAUL-DT221 -ENGINE | 7400 | 57237 | 10386
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Service Airconditioner | 2028-06-21 | 2028-06-22 | 24 hrs | FY28 | 24 | 90029084 | B1 | 1000290654 | 21.06.2028 | 4500 | CCK-MP-SUPP-WC008 -STRUCT-CABIN-AIRCN | 3500 | 51417 | 5947
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Accumulator Hyd Steering Rear | 2028-06-22 | 2028-06-22 | 7.5 hrs | FY28 | 11.5 | 90011353 | B1 | 1000094871 | 22.06.2028 | 25000 | CCK-MP-HAUL-DT762 -STRSYS-STACC-SACCR | 6800 | 76486 | 11947
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Replace Operator Cabin Dash Bulbs | 2028-06-22 | 2028-06-22 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158230 | 22.06.2028 | 3000 | CCK-MP-HAUL-DT765 -STRUCT-CABIN | 6800 | 78429 | 78429
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Repl Bulk Grease Tank Breather | 2028-06-22 | 2028-06-22 | 1 hr | FY28 | 1 | 90022533 | B1 | 1000236909 | 22.06.2028 | 6 Monthly | CCK-MP-SUPP-SV220 -GRSYST-GRTNK | 5100 | 58259 | 58259
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Spiders Pump Drive Shaft | 2028-06-22 | 2028-06-22 | 4 hrs | FY28 | 4 | 90002366 | B1 | 1000128029 | 22.06.2028 | 18000 | CCK-MP-HAUL-DT222 -ENGINE-PMPDR-DRSHT | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Brake Slack Adjuster Front | 2028-06-22 | 2028-06-22 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024296 | 22.06.2028 | 20000 | CCK-MP-HAUL-DT090 -BRKSYS-SLACK-SLACF | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Brake Slack Adjuster Rear | 2028-06-22 | 2028-06-22 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000024297 | 22.06.2028 | 20000 | CCK-MP-HAUL-DT090 -BRKSYS-SLACK-SLACR | 7400 | 81670 | 5994
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Drive Shaft | 2028-06-24 | 2028-06-24 | 2 hrs | FY28 | 2 | 90011359 | B1 | 1000095248 | 24.06.2028 | 25000 | CCK-MP-HAUL-DT769 -HYDSYS-DRSHT | 6800 | 80508 | 12222
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Engine Midlife Complete | 2028-06-24 | 2028-06-25 | 40 hrs | FY28 | 62 | 90015886 | B1 | 1000167063 | 24.06.2028 | 12000 | CCK-MP-HAUL-DT5314-ENGINE | 7400 | 45898 | 22018
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Radiator Fan Hoses | 2028-06-24 | 2028-06-24 | 11 hrs | FY28 | 11 | 90031073 | B1 | 1000307689 | 24.06.2028 | 12000 | CCK-MP-HAUL-DT5314-ENGINE-COSYS-RADTR | 7400 | 45898 | 22018
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Replace Trans TCon System Hoses | 2028-06-24 | 2028-06-25 | 20 hrs | FY28 | 20 | 90010099 | B3 | 1000167037 | 24.06.2028 | 18000 | CCK-MP-HAUL-DT5314-TRNSYS-TRANS-TRNHO | 7400 | 45898 | 22018
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Motor Lube Axle Hoses | 2028-06-24 | 2028-06-24 | 4 hrs | FY28 | 4 | 90026944 | B1 | 1000272186 | 24.06.2028 | 12000 | CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYM01 | 7400 | 45898 | 22018
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Transmission | 2028-06-24 | 2028-06-25 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272349 | 24.06.2028 | 18000 | CCK-MP-HAUL-DT153 -TRNSYS-TRANS | 7400 | 84230 | 2506
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Steering Hyd Oil Cooler | 2028-06-24 | 2028-06-24 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107005 | 24.06.2028 | 15000 | CCK-MP-HAUL-DT150 -STRSYS-STOCO | 7400 | 86608 | 872
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Transmisson Calibration | 2028-06-25 | 2028-06-25 | 4 hrs | FY28 | 8 | 90029836 | B1 | 1000298674 | 25.06.2028 | 4500 | CCK-MP-HAUL-DT097 -TRNSYS-TRANS | 7400 | 83804 | 17427
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Engine Cat 3516B | 2028-06-26 | 2028-07-02 | 156 hrs | FY28 | 306 | 90017288 | B1 | 1000290428 | 26.06.2028 | 22000 | CCK-MP-SUPP-WC224 -ENGINE | 5000 | 71088 | 12650
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Airconditioner Overhaul | 2028-06-26 | 2028-06-28 | 48 hrs | FY28 | 48 | 90017507 | B1 | 1000290431 | 26.06.2028 | 11000 | CCK-MP-SUPP-WC224 -STRUCT-CABIN-AIRCN | 5000 | 71088 | 6229
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Brake Oil Cooler Front | 2028-06-26 | 2028-06-26 | 13 hrs | FY28 | 13 | 90010109 | B1 | 1000091455 | 26.06.2028 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BROCO-BROCF | 7400 | 85452 | 9949
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Brake Oil Cooler Rear | 2028-06-26 | 2028-06-26 | 13 hrs | FY28 | 13 | 90010108 | B1 | 1000091454 | 26.06.2028 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BROCO-BROCR | 7400 | 85452 | 9949
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Brake Slack Adjuster Front | 2028-06-27 | 2028-06-27 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000023603 | 27.06.2028 | 20000 | CCK-MP-HAUL-DT054 -BRKSYS-SLACK-SLACF | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Brake Slack Adjuster Rear | 2028-06-27 | 2028-06-27 | 4 hrs | FY28 | 4 | 90002382 | B1 | 1000023604 | 27.06.2028 | 20000 | CCK-MP-HAUL-DT054 -BRKSYS-SLACK-SLACR | 7400 | 88111 | 6138
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Tyre Sense Battery | 2028-06-27 | 2028-06-27 | 1 hr | FY28 | 1 | 90017025 | B1 | 1000153195 | 27.06.2028 | 24 Monthly | CCK-MP-HAUL-DT770 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Drive Shaft Transmission | 2028-06-27 | 2028-06-27 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154977 | 27.06.2028 | 18000 | CCK-MP-HAUL-DT149 -FDRSYS-DRSHT | 7400 | 87258 | 4012
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Transmission | 2028-06-27 | 2028-06-28 | 22 hrs | FY28 | 39 | 90026996 | B2 | 1000272309 | 27.06.2028 | 18000 | CCK-MP-HAUL-DT095 -TRNSYS-TRANS | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Drive Shaft Transmission | 2028-06-27 | 2028-06-27 | 8 hrs | FY28 | 16 | 90017195 | B1 | 1000154941 | 27.06.2028 | 18000 | CCK-MP-HAUL-DT095 -FDRSYS-DRSHT | 7400 | 88921 | 9465
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Replace Trans TCon System Hoses | 2028-06-27 | 2028-06-28 | 20 hrs | FY28 | 20 | 90010099 | B1 | 1000090085 | 27.06.2028 | 18000 | CCK-MP-HAUL-DT095 -TRNSYS-TRANS-TRNHO | 7400 | 88921 | 28299
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Replace Hoses Differential System | 2028-06-27 | 2028-06-27 | 5 hrs | FY28 | 5 | 90010101 | B1 | 1000090086 | 27.06.2028 | 18000 | CCK-MP-HAUL-DT095 -FDRSYS-DIFFL-DIFHO | 7400 | 88921 | 28299
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Steering Brake Pump Compensator | 2028-06-28 | 2028-06-28 | 6 hrs | FY28 | 7 | 90019922 | B1 | 1000204772 | 28.06.2028 | 6000 | CCK-MP-HAUL-DT768 -STRSYS-STPMP | 6800 | 79837 | 4916
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Replace Operator Cabin Dash Bulbs | 2028-06-28 | 2028-06-28 | 2 hrs | FY28 | 2 | 90017265 | B1 | 1000158233 | 28.06.2028 | 3000 | CCK-MP-HAUL-DT768 -STRUCT-CABIN | 6800 | 79837 | 18344
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 250hr Initial Valve Set | 2028-06-28 | 2028-06-28 | 8 hrs | FY28 | 16 | 90015884 | B1 | 1000155946 | 28.06.2028 | 250 | CCK-MP-HAUL-DT099 -ENGINE | 7400 | 87442 | 32853
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Repl Spider Trans Driveshaft | 2028-06-28 | 2028-06-28 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154998 | 28.06.2028 | 6000 | CCK-MP-HAUL-DT222 -FDRSYS-DRSHT-UNVSL | 7400 | 55735 | 4006
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Steering LH | 2028-06-29 | 2028-06-29 | 10 hrs | FY28 | 16 | 90011350 | B1 | 1000094391 | 29.06.2028 | 15000 | CCK-MP-HAUL-DT753 -STRSYS-STRCY-STCYL | 6800 | 85999 | 2148
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Grid Box Blower Motor RH | 2028-06-29 | 2028-06-29 | 10 hrs | FY28 | 10 | 90011332 | B1 | 1000094430 | 29.06.2028 | 25000 | CCK-MP-HAUL-DT754 -ELCTHV-HVGBM-GBMRH | 6800 | 83256 | 13643
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Adjust Engine Valve Set | 2028-06-30 | 2028-06-30 | 12 hrs | FY28 | 24 | 90015645 | B1 | 1000269773 | 30.06.2028 | 4500 | CCK-MP-SUPP-SV220 -ENGINE | 5100 | 58303 | 11037
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Service Airconditioner | 2028-06-30 | 2028-07-01 | 24 hrs | FY28 | 24 | 90018538 | B2 | 1000269776 | 30.06.2028 | 4500 | CCK-MP-SUPP-SV220 -STRUCT-CABIN-AIRCN | 5100 | 58259 | 16547
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Cyl Steering RH | 2028-06-30 | 2028-06-30 | 12 hrs | FY28 | 20 | 90002385 | B2 | 1000024554 | 30.06.2028 | 15000 | CCK-MP-HAUL-DT094 -STRSYS-STRCY-STCYR | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Replace Steering System Hoses | 2028-06-30 | 2028-07-02 | 54 hrs | FY28 | 106 | 90010133 | B1 | 1000082988 | 30.06.2028 | 15000 | CCK-MP-HAUL-DT094 -STRSYS-STHLF-STRHO | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Steering Hyd Oil Cooler | 2028-06-30 | 2028-06-30 | 9 hrs | FY28 | 9 | 90012866 | B2 | 1000107020 | 30.06.2028 | 15000 | CCK-MP-HAUL-DT094 -STRSYS-STOCO | 7400 | 88788 | 245
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Spider Trans Driveshaft | 2028-06-30 | 2028-06-30 | 6 hrs | FY28 | 12 | 90017211 | B1 | 1000154938 | 30.06.2028 | 6000 | CCK-MP-HAUL-DT094 -FDRSYS-DRSHT-UNVSL | 7400 | 88788 | 3009
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Steering Bell Crank & Links | 2028-06-30 | 2028-07-01 | 20 hrs | FY28 | 36 | 90028566 | B1 | 1000317600 | 30.06.2028 | 30000 | CCK-MP-HAUL-DT094 -STRSYS-STLTR-STLAC | 7400 | 88788 | 15729
| Onsite PM | Haul | Fortescue |  | FY29 - HAUL - COMPONENTS DURING PM | 2028-07-01 | 2029-06-30 |  | FY29
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Transmisson Calibration | 2028-07-01 | 2028-07-01 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298664 | 01.07.2028 | 4500 | CCK-MP-HAUL-DT056 -TRNSYS-TRANS | 7400 | 84421 | 8230
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Radiator Fan Hoses | 2028-07-01 | 2028-07-01 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307489 | 01.07.2028 | 12000 | CCK-MP-HAUL-DT095 -ENGINE-COSYS-RADTR | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Spider Trans Driveshaft | 2028-07-02 | 2028-07-02 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154942 | 02.07.2028 | 6000 | CCK-MP-HAUL-DT097 -FDRSYS-DRSHT-UNVSL | 7400 | 83804 | 3219
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Service Air Conditioner 12M | 2028-07-02 | 2028-07-03 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000172994 | 02.07.2028 | 12 Monthly | CCK-MP-HAUL-DT5315-STRUCT-CABIN-AIRCN | 7400 | 45392 | 45392
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 789C AHS Replace Proactive Coax | 2028-07-02 | 2028-07-02 | 12 hrs | FY29 | 12 | 90022477 | B2 | 1000235591 | 02.07.2028 | 24 Monthly | CCK-MP-SUPP-WC224 -COMMUN-FLMGT
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Hub & Spindle RH | 2028-07-02 | 2028-07-03 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000094777 | 02.07.2028 | 18000 | CCK-MP-HAUL-DT760 -STRUCT-AXLES-HUBRH | 6800 | 80390 | 5225
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Hyd Pump Steering & Brake | 2028-07-02 | 2028-07-03 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204749 | 02.07.2028 | 12000 | CCK-MP-HAUL-DT769 -STRSYS-STPMP | 6800 | 80508 | 15397
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Transmisson Calibration | 2028-07-03 | 2028-07-03 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298815 | 03.07.2028 | 4500 | CCK-MP-HAUL-DT5315-TRNSYS-TRANS | 7400 | 45392 | 8391
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Steering Brake Pump Compensator | 2028-07-03 | 2028-07-03 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204758 | 03.07.2028 | 6000 | CCK-MP-HAUL-DT754 -STRSYS-STPMP | 6800 | 83256 | 5013
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Cyl Suspension RHF | 2028-07-04 | 2028-07-06 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000094461 | 04.07.2028 | 18000 | CCK-MP-HAUL-DT754 -STRUCT-SUSPN-SCYRF | 6800 | 83256 | 4996
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Cyl Steering LH | 2028-07-04 | 2028-07-04 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000094709 | 04.07.2028 | 15000 | CCK-MP-HAUL-DT759 -STRSYS-STRCY-STCYL | 6800 | 79716 | 2497
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Replace Operator Cabin Dash Bulbs | 2028-07-04 | 2028-07-04 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158224 | 04.07.2028 | 3000 | CCK-MP-HAUL-DT759 -STRUCT-CABIN | 6800 | 79716 | 79716
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Replace Operator Cabin Dash Bulbs | 2028-07-04 | 2028-07-04 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158228 | 04.07.2028 | 3000 | CCK-MP-HAUL-DT763 -STRUCT-CABIN | 6800 | 74143 | 74143
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Steering Brake Pump Compensator | 2028-07-04 | 2028-07-04 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204771 | 04.07.2028 | 6000 | CCK-MP-HAUL-DT767 -STRSYS-STPMP | 6800 | 74312 | 4545
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Hyd Pump Steering & Brake | 2028-07-05 | 2028-07-06 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204741 | 05.07.2028 | 12000 | CCK-MP-HAUL-DT761 -STRSYS-STPMP | 6800 | 78336 | 10559
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Replace Operator Cabin Dash Bulbs | 2028-07-05 | 2028-07-05 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158226 | 05.07.2028 | 3000 | CCK-MP-HAUL-DT761 -STRUCT-CABIN | 6800 | 78336 | 19424
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Service Air Conditioner 12M | 2028-07-05 | 2028-07-06 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174168 | 05.07.2028 | 12 Monthly | CCK-MP-HAUL-DT135 -STRUCT-CABIN-AIRCN | 7400 | 82965 | 8025
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Operator Cabin Dash Bulbs | 2028-07-06 | 2028-07-06 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158223 | 06.07.2028 | 3000 | CCK-MP-HAUL-DT758 -STRUCT-CABIN | 6800 | 85895 | 23936
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Valve Steering | 2028-07-07 | 2028-07-07 | 12 hrs | FY29 | 12 | 90011554 | B1 | 1000093058 | 07.07.2028 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STVLV | 5100 | 58259 | 7425
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Repl Pump & Motor Sec Str | 2028-07-07 | 2028-07-07 | 6 hrs | FY29 | 6 | 90011558 | B1 | 1000093063 | 07.07.2028 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STEMG-SESPP | 5100 | 58259 | 7425
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Brake Slack Adjuster Rear Left | 2028-07-07 | 2028-07-07 | 6 hrs | FY29 | 6 | 90036703 | B1 | 1000368002 | 07.07.2028 | 18000 | CCK-MP-SUPP-SV220 -BRKSYS-SLACK-SLARL | 5100 | 58303 | 7425
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Brake Slack Adjuster Rear Right | 2028-07-07 | 2028-07-07 | 6 hrs | FY29 | 6 | 90036703 | B1 | 1000368003 | 07.07.2028 | 18000 | CCK-MP-SUPP-SV220 -BRKSYS-SLACK-SLARR | 5100 | 58303 | 7425
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Hoist LH | 2028-07-08 | 2028-07-08 | 17 hrs | FY29 | 33 | 90011357 | B1 | 1000094345 | 08.07.2028 | 25000 | CCK-MP-HAUL-DT752 -HYDSYS-HOCYL-HCYLL | 6800 | 80681 | 12045
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl AOC Fan Motor Rear | 2028-07-10 | 2028-07-10 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000167003 | 10.07.2028 | 12000 | CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYM02 | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Front Wheel Bearings LH | 2028-07-11 | 2028-07-12 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157110 | 11.07.2028 | 16000 | CCK-MP-HAUL-DT057 -STRUCT-AXLES-FWBLH | 7400 | 91273 | 454
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Front Wheel Bearings RH | 2028-07-11 | 2028-07-12 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157236 | 11.07.2028 | 16000 | CCK-MP-HAUL-DT138 -STRUCT-AXLES-FWBRH | 7400 | 82982 | 10615
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Overhaul Water Tank Module | 2028-07-11 | 2028-07-11 | 1 hr | FY29 | 1 | 90028960 | B1 | 1000289081 | 11.07.2028 | 40000 | CCK-MP-SUPP-WC3111-STRUCT-WTANK | 5600 | 28968 | 28968
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Steering Bell Crank & Links | 2028-07-11 | 2028-07-12 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317580 | 11.07.2028 | 30000 | CCK-MP-HAUL-DT054 -STRSYS-STLTR-STLAC | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Tyre Sense Battery | 2028-07-11 | 2028-07-11 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153150 | 11.07.2028 | 24 Monthly | CCK-MP-HAUL-DT130 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Transmisson Calibration | 2028-07-12 | 2028-07-12 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298663 | 12.07.2028 | 4500 | CCK-MP-HAUL-DT055 -TRNSYS-TRANS | 7400 | 84122 | 15848
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Steering Linkages | 2028-07-12 | 2028-07-12 | 15 hrs | FY29 | 28 | 90028568 | B1 | 1000317581 | 12.07.2028 | 15000 | CCK-MP-HAUL-DT055 -STRSYS-STLTR | 7400 | 84122 | 14732
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Replace Steering System Hoses | 2028-07-12 | 2028-07-14 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000082874 | 12.07.2028 | 15000 | CCK-MP-HAUL-DT055 -STRSYS-STHLF-STRHO | 7400 | 84122 | 7001
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Auto Lube Pump | 2028-07-12 | 2028-07-12 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000095514 | 12.07.2028 | 8000 | CCK-MP-HAUL-DT774 -GRSYST-ALBPP | 6800 | 81047 | 3051
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Tyre Sense Battery | 2028-07-14 | 2028-07-14 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000166974 | 14.07.2028 | 24 Monthly | CCK-MP-HAUL-DT5313-MANGMT-TYRSN
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Replace Operators Seat | 2028-07-14 | 2028-07-14 | 3 hrs | FY29 | 6 | 90003066 | B2 | 1000239793 | 14.07.2028 | 6000 | CCK-MP-SUPP-WC009 -STRUCT-CABIN-SEATS | 1500 | 34052 | 2652
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 250hr Initial Valve Set | 2028-07-14 | 2028-07-14 | 6 hrs | FY29 | 12 | 90017289 | B1 | 1000290438 | 14.07.2028 | 250 | CCK-MP-SUPP-WC224 -ENGINE | 5000 | 71088 | 12650
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Cyl Steering LH | 2028-07-14 | 2028-07-14 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000094603 | 14.07.2028 | 15000 | CCK-MP-HAUL-DT757 -STRSYS-STRCY-STCYL | 6800 | 80700 | 16936
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Cyl Steering RH | 2028-07-14 | 2028-07-14 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000094604 | 14.07.2028 | 15000 | CCK-MP-HAUL-DT757 -STRSYS-STRCY-STCYR | 6800 | 80700 | 16936
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Transmisson Calibration | 2028-07-15 | 2028-07-15 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298818 | 15.07.2028 | 4500 | CCK-MP-HAUL-DT5318-TRNSYS-TRANS | 7400 | 45240 | 9085
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Motor Lube Axle Rear & Hoses | 2028-07-15 | 2028-07-15 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272021 | 15.07.2028 | 24000 | CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYM01 | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl AOC Fan Motor Rear | 2028-07-15 | 2028-07-15 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000026475 | 15.07.2028 | 12000 | CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYM02 | 7400 | 84301 | 21869
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Pump Brake Cooling | 2028-07-15 | 2028-07-15 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000026479 | 15.07.2028 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-HYFPP | 7400 | 84301 | 43683
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Brake Oil Cooler Front | 2028-07-15 | 2028-07-15 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000083458 | 15.07.2028 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BROCO-BROCF | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Brake Oil Cooler Rear | 2028-07-15 | 2028-07-15 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000083457 | 15.07.2028 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BROCO-BROCR | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Hyd Pump Steering Main & Fan | 2028-07-15 | 2028-07-15 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000026484 | 15.07.2028 | 24000 | CCK-MP-HAUL-DT151 -STRSYS-STPMP | 7400 | 84253 | 9530
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Pump Hoist & Brake | 2028-07-15 | 2028-07-15 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000026493 | 15.07.2028 | 24000 | CCK-MP-HAUL-DT151 -HYDSYS-HOPMP | 7400 | 84301 | 9530
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Transmisson Calibration | 2028-07-16 | 2028-07-16 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298727 | 16.07.2028 | 4500 | CCK-MP-HAUL-DT146 -TRNSYS-TRANS | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Pump Drive | 2028-07-16 | 2028-07-17 | 20 hrs | FY29 | 39 | 90002365 | B1 | 1000027122 | 16.07.2028 | 24000 | CCK-MP-HAUL-DT161 -ENGINE-PMPDR | 7400 | 80609 | 9556
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Auto Lube Pump | 2028-07-16 | 2028-07-16 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285799 | 16.07.2028 | 8000 | CCK-MP-HAUL-DT161 -GRSYST-ALBPP | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Service Air Conditioner 12M | 2028-07-16 | 2028-07-17 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174195 | 16.07.2028 | 12 Monthly | CCK-MP-HAUL-DT5318-STRUCT-CABIN-AIRCN | 7400 | 45240 | 9085
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Radiator Engine Cooling | 2028-07-16 | 2028-07-17 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307542 | 16.07.2028 | 24000 | CCK-MP-HAUL-DT158 -ENGINE-COSYS-RADTR | 7400 | 85964 | 33728
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Steering Bell Crank & Links | 2028-07-17 | 2028-07-18 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317650 | 17.07.2028 | 30000 | CCK-MP-HAUL-DT159 -STRSYS-STLTR-STLAC | 7400 | 90235 | 15586
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Steering HMU | 2028-07-17 | 2028-07-17 | 12 hrs | FY29 | 12 | 90000903 | B2 | 1000033367 | 17.07.2028 | 15000 | CCK-MP-SUPP-WC225 -STRSYS-STHMU | 5000 | 75244 | 5214
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Air Con Service & Overhaul | 2028-07-17 | 2028-07-18 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110630 | 17.07.2028 | 12 Monthly | CCK-MP-HAUL-DT761 -STRUCT-CABIN-AIRCN | 6800 | 78336 | 23274
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Steering Brake Pump Compensator | 2028-07-17 | 2028-07-17 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204778 | 17.07.2028 | 6000 | CCK-MP-HAUL-DT774 -STRSYS-STPMP | 6800 | 81047 | 4812
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Tyre Sense Battery | 2028-07-18 | 2028-07-18 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153113 | 18.07.2028 | 24 Monthly | CCK-MP-HAUL-DT055 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Front Wheel Bearings LH | 2028-07-19 | 2028-07-20 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157114 | 19.07.2028 | 16000 | CCK-MP-HAUL-DT082 -STRUCT-AXLES-FWBLH | 7400 | 84374 | 28
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Suspension LHF | 2028-07-19 | 2028-07-21 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067613 | 19.07.2028 | 28000 | CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYLF | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Suspension LHR | 2028-07-19 | 2028-07-20 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000026641 | 19.07.2028 | 28000 | CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYLR | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Cyl Suspension RHR | 2028-07-19 | 2028-07-20 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000026642 | 19.07.2028 | 28000 | CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYRR | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Front Wheel Bearings LH | 2028-07-19 | 2028-07-20 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157176 | 19.07.2028 | 16000 | CCK-MP-HAUL-DT159 -STRUCT-AXLES-FWBLH | 7400 | 90235 | 16874
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Repl Sepura SCC Microphone | 2028-07-19 | 2028-07-19 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289618 | 19.07.2028 | 12 Monthly | CCK-MP-SUPP-WC008 -COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Transmisson Calibration | 2028-07-20 | 2028-07-20 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298817 | 20.07.2028 | 4500 | CCK-MP-HAUL-DT5317-TRNSYS-TRANS | 7400 | 45576 | 9163
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Steering Bell Crank & Links | 2028-07-20 | 2028-07-21 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317674 | 20.07.2028 | 30000 | CCK-MP-HAUL-DT5317-STRSYS-STLTR-STLAC | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Steering Hyd Oil Cooler | 2028-07-20 | 2028-07-20 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107015 | 20.07.2028 | 15000 | CCK-MP-HAUL-DT054 -STRSYS-STOCO | 7400 | 88111 | 0
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Drive Shaft | 2028-07-21 | 2028-07-21 | 2 hrs | FY29 | 2 | 90000271 | B2 | 1000018393 | 21.07.2028 | 18000 | CCK-MP-SUPP-WC008 -FDRSYS-DRSHT | 3500 | 51417 | 10677
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace C32 Engine | 2028-07-21 | 2028-07-25 | 98 hrs | FY29 | 386 | 90015632 | B1 | 1000201187 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-ENGINE | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Engine Radiator | 2028-07-21 | 2028-07-22 | 26 hrs | FY29 | 50 | 90018501 | B1 | 1000201203 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-ENGINE-COSYS-RADTR | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Engine Aftercooler | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 6 | 90018502 | B1 | 1000201202 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-ENGINE-INTEX-AFTER | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Torque Converter | 2028-07-21 | 2028-07-21 | 16 hrs | FY29 | 32 | 90018503 | B1 | 1000201225 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-TRNSYS-TRQUE | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Repl Trans & TCon Charge Pump | 2028-07-21 | 2028-07-21 | 4 hrs | FY29 | 4 | 90018505 | B1 | 1000201219 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-TRNSYS-TRPMP | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Final Drive LH | 2028-07-21 | 2028-07-22 | 20 hrs | FY29 | 38 | 90018512 | B1 | 1000201204 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-FDRSYS-FDRVE-FDRLH | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Final Drive RH | 2028-07-21 | 2028-07-22 | 20 hrs | FY29 | 38 | 90018513 | B1 | 1000201205 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-FDRSYS-FDRVE-FDRRH | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Drive Shaft | 2028-07-21 | 2028-07-21 | 2 hrs | FY29 | 2 | 90018509 | B1 | 1000201186 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-FDRSYS-DRSHT | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Differential | 2028-07-21 | 2028-07-22 | 20 hrs | FY29 | 38 | 90018510 | B1 | 1000201185 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-FDRSYS-DIFFL | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Valve Brake | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 12 | 90018518 | B1 | 1000201227 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-BRKSYS-BRVLV | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Repl Pump & Motor Sec Str | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 6 | 90011558 | B1 | 1000201217 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STEMG-SESPP | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Steering Linkages | 2028-07-21 | 2028-07-21 | 12 hrs | FY29 | 12 | 90018527 | B1 | 1000201223 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STLTR | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Steering Hoses & Lines | 2028-07-21 | 2028-07-21 | 8 hrs | FY29 | 8 | 90018532 | B1 | 1000201222 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STHLF | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Pump Steering | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 6 | 90018522 | B1 | 1000201218 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STPMP | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Steering HMU | 2028-07-21 | 2028-07-21 | 12 hrs | FY29 | 12 | 90018523 | B1 | 1000201221 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STHMU | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Valve Steering | 2028-07-21 | 2028-07-21 | 12 hrs | FY29 | 12 | 90018524 | B1 | 1000201229 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRSYS-STVLV | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Hydraulic Oil Cooler | 2028-07-21 | 2028-07-21 | 12 hrs | FY29 | 12 | 90018535 | B1 | 1000201209 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-HYDSYS-HDOCO | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Pump Hoist Lines | 2028-07-21 | 2028-07-21 | 8 hrs | FY29 | 8 | 90018534 | B1 | 1000201216 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-HYDSYS-HDHLF | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Repl Pump Hoist & Pump Brake Chrg | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 6 | 90037881 | B1 | 1000379760 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-HYDSYS-HOPMP | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Auto Lube Pump | 2028-07-21 | 2028-07-21 | 2 hrs | FY29 | 2 | 90018537 | B1 | 1000201177 | 21.07.2028 | 9000 | CCK-MP-SUPP-SV4104-GRSYST-ALBPP | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Hub and Spindle RH | 2028-07-21 | 2028-07-21 | 12 hrs | FY29 | 22 | 90018543 | B1 | 1000201208 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-AXLES-HUBRH | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Hub and Spindle LH | 2028-07-21 | 2028-07-21 | 12 hrs | FY29 | 22 | 90018542 | B1 | 1000201207 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-AXLES-HUBLH | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Overhaul Airconditioner | 2028-07-21 | 2028-07-22 | 24 hrs | FY29 | 24 | 90011566 | B2 | 1000229147 | 21.07.2028 | 9000 | CCK-MP-SUPP-SV4104-STRUCT-CABIN-AIRCN | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Refurbish A Frame | 2028-07-21 | 2028-07-22 | 18 hrs | FY29 | 36 | 90018540 | B1 | 1000201175 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-CHASS-AFRME | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Tag Link | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 6 | 90018541 | B1 | 1000201224 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-CHASS-TAGLK | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Cylinder Suspension LHR | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 10 | 90018546 | B1 | 1000201182 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-SUSPN-SCYLR | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Cylinder Suspension LHF | 2028-07-21 | 2028-07-21 | 14 hrs | FY29 | 26 | 90018544 | B1 | 1000201181 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-SUSPN-SCYLF | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Cylinder Suspension RHF | 2028-07-21 | 2028-07-21 | 14 hrs | FY29 | 26 | 90018545 | B1 | 1000201183 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-SUSPN-SCYRF | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Cylinder Suspension RHR | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 10 | 90018547 | B1 | 1000201184 | 21.07.2028 | 18000 | CCK-MP-SUPP-SV4104-STRUCT-SUSPN-SCYRR | 5100 | 23504 | 7410
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 WaterTank Cannon & Spray Sys Insp | 2028-07-21 | 2028-07-21 | 3 hrs | FY29 | 3 | 90036929 | B1 | 1000368898 | 21.07.2028 | 6 Monthly | CCK-MP-SUPP-WC3112-STRUCT-WTANK | 5600 | 30406 | 30406
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Radiator Engine Cooling | 2028-07-21 | 2028-07-22 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307528 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -ENGINE-COSYS-RADTR | 7400 | 87258 | 31553
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Pump Drive | 2028-07-21 | 2028-07-22 | 20 hrs | FY29 | 39 | 90002365 | B1 | 1000026330 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -ENGINE-PMPDR | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Wheel End LH | 2028-07-21 | 2028-07-22 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000026340 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -FDRSYS-FDRVE-FDRLH | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Wheel End RH | 2028-07-21 | 2028-07-22 | 32.5 hrs | FY29 | 58.5 | 90007352 | B1 | 1000026341 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -FDRSYS-FDRVE-FDRRH | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Motor Lube Axle Rear & Hoses | 2028-07-21 | 2028-07-21 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272017 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYM01 | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl AOC Fan Motor Rear | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000026343 | 21.07.2028 | 12000 | CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYM02 | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Overhaul Accumulator Brake LHF | 2028-07-21 | 2028-07-21 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026344 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BACCM-FRLFT | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Overhaul Accumulator Brake RHF | 2028-07-21 | 2028-07-21 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026345 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BACCM-FRRGT | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Overhaul Accumulator Brake Rear | 2028-07-21 | 2028-07-21 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026346 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BACCM-BACCR | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Pump Brake Cooling | 2028-07-21 | 2028-07-21 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000026347 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-HYFPP | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Overhaul Valve Control Brake | 2028-07-21 | 2028-07-22 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000026348 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BRVLV | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Brake Oil Cooler Front | 2028-07-21 | 2028-07-21 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000083420 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BROCO-BROCF | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Brake Oil Cooler Rear | 2028-07-21 | 2028-07-21 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000083419 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BROCO-BROCR | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Motor Brake Oil Cooling | 2028-07-21 | 2028-07-21 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000026349 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BROCO-HYMO1 | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Ovhl Accumulator Steering Front | 2028-07-21 | 2028-07-21 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026356 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -STRSYS-STACC-SACCF | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Pump Hoist & Brake | 2028-07-21 | 2028-07-21 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000026361 | 21.07.2028 | 24000 | CCK-MP-HAUL-DT149 -HYDSYS-HOPMP | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Auto Lube Pump | 2028-07-21 | 2028-07-21 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285790 | 21.07.2028 | 8000 | CCK-MP-HAUL-DT149 -GRSYST-ALBPP | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Replace Steering System Hoses | 2028-07-21 | 2028-07-23 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083102 | 21.07.2028 | 15000 | CCK-MP-HAUL-DT126 -STRSYS-STHLF-STRHO | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Steering Hyd Oil Cooler | 2028-07-21 | 2028-07-21 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107024 | 21.07.2028 | 15000 | CCK-MP-HAUL-DT126 -STRSYS-STOCO | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Steering Bell Crank & Links | 2028-07-21 | 2028-07-22 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317610 | 21.07.2028 | 30000 | CCK-MP-HAUL-DT126 -STRSYS-STLTR-STLAC | 7400 | 88657 | 15402
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl AOC Fan Motor Rear | 2028-07-22 | 2028-07-22 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000024605 | 22.07.2028 | 12000 | CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYM02 | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Spider Trans Driveshaft | 2028-07-24 | 2028-07-24 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154978 | 24.07.2028 | 6000 | CCK-MP-HAUL-DT150 -FDRSYS-DRSHT-UNVSL | 7400 | 86608 | 2171
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Hoist LH | 2028-07-24 | 2028-07-24 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128611 | 24.07.2028 | 28000 | CCK-MP-HAUL-DT5202-HYDSYS-HOCYL-HCYLL | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Hoist RH | 2028-07-24 | 2028-07-24 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128612 | 24.07.2028 | 28000 | CCK-MP-HAUL-DT5202-HYDSYS-HOCYL-HCYLR | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Suspension LHF | 2028-07-24 | 2028-07-26 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000111956 | 24.07.2028 | 28000 | CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYLF | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Suspension LHR | 2028-07-24 | 2028-07-25 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000111953 | 24.07.2028 | 28000 | CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYLR | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Suspension RHF | 2028-07-24 | 2028-07-26 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000111958 | 24.07.2028 | 28000 | CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYRF | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Suspension RHR | 2028-07-24 | 2028-07-25 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000111954 | 24.07.2028 | 28000 | CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYRR | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Suspension LHF | 2028-07-25 | 2028-07-27 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067553 | 25.07.2028 | 28000 | CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYLF | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Suspension RHR | 2028-07-25 | 2028-07-26 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000025655 | 25.07.2028 | 28000 | CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYRR | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Front Wheel Bearings RH | 2028-07-25 | 2028-07-26 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157264 | 25.07.2028 | 16000 | CCK-MP-HAUL-DT159 -STRUCT-AXLES-FWBRH | 7400 | 90235 | 1418
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Spiders Pump Drive Shaft | 2028-07-25 | 2028-07-25 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000024845 | 25.07.2028 | 18000 | CCK-MP-HAUL-DT099 -ENGINE-PMPDR-DRSHT | 7400 | 87442 | 3410
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Hoist LH | 2028-07-27 | 2028-07-27 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128543 | 27.07.2028 | 28000 | CCK-MP-HAUL-DT082 -HYDSYS-HOCYL-HCYLL | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Hoist RH | 2028-07-27 | 2028-07-27 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128544 | 27.07.2028 | 28000 | CCK-MP-HAUL-DT082 -HYDSYS-HOCYL-HCYLR | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Suspension LHF | 2028-07-27 | 2028-07-29 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067449 | 27.07.2028 | 28000 | CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYLF | 7400 | 84375 | 29
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Suspension RHF | 2028-07-27 | 2028-07-29 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067451 | 27.07.2028 | 28000 | CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYRF | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Suspension LHR | 2028-07-27 | 2028-07-28 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000024007 | 27.07.2028 | 28000 | CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYLR | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Steering Bell Crank & Links | 2028-07-27 | 2028-07-28 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317670 | 27.07.2028 | 30000 | CCK-MP-HAUL-DT5315-STRSYS-STLTR-STLAC | 7400 | 45392 | 11716
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Inspect Rear Axle Housing | 2028-07-27 | 2028-07-27 | 1 hr | FY29 | 1 | 90019256 | B1 | 1000196434 | 27.07.2028 | 2000 | CCK-MP-SUPP-WC224 -STRUCT-RAXHO | 5000 | 71088 | 71088
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Suspension LHF | 2028-07-28 | 2028-07-30 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067393 | 28.07.2028 | 28000 | CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYLF | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Suspension RHF | 2028-07-28 | 2028-07-30 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067395 | 28.07.2028 | 28000 | CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYRF | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Suspension LHR | 2028-07-28 | 2028-07-29 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000023755 | 28.07.2028 | 28000 | CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYLR | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Cyl Suspension RHR | 2028-07-28 | 2028-07-29 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000023756 | 28.07.2028 | 28000 | CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYRR | 7400 | 84421 | 13282
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Hyd Pump Steering & Brake | 2028-07-28 | 2028-07-29 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204744 | 28.07.2028 | 12000 | CCK-MP-HAUL-DT764 -STRSYS-STPMP | 6800 | 75315 | 9695
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Transmisson Calibration | 2028-07-28 | 2028-07-28 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298679 | 28.07.2028 | 4500 | CCK-MP-HAUL-DT130 -TRNSYS-TRANS | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Transmisson Calibration | 2028-07-28 | 2028-07-28 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298720 | 28.07.2028 | 4500 | CCK-MP-HAUL-DT135 -TRNSYS-TRANS | 7400 | 82965 | 7974
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Spider Trans Driveshaft | 2028-07-29 | 2028-07-29 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154984 | 29.07.2028 | 6000 | CCK-MP-HAUL-DT155 -FDRSYS-DRSHT-UNVSL | 7400 | 81407 | 10226
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Pump Drive | 2028-07-30 | 2028-07-31 | 20 hrs | FY29 | 39 | 90002365 | B1 | 1000026858 | 30.07.2028 | 24000 | CCK-MP-HAUL-DT157 -ENGINE-PMPDR | 7400 | 83041 | 9184
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Cyl Hoist LH | 2028-07-30 | 2028-07-30 | 17 hrs | FY29 | 33 | 90011357 | B1 | 1000094557 | 30.07.2028 | 25000 | CCK-MP-HAUL-DT756 -HYDSYS-HOCYL-HCYLL | 6800 | 78754 | 11297
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Cyl Hoist RH | 2028-07-30 | 2028-07-30 | 17 hrs | FY29 | 33 | 90011358 | B1 | 1000094558 | 30.07.2028 | 25000 | CCK-MP-HAUL-DT756 -HYDSYS-HOCYL-HCYLR | 6800 | 78754 | 11297
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Brake Accumulator Rear | 2028-07-30 | 2028-07-30 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000095285 | 30.07.2028 | 25000 | CCK-MP-HAUL-DT770 -BRKSYS-BRACC-BACCR | 6800 | 79305 | 62912
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Hyd Pump Steering & Brake | 2028-07-30 | 2028-07-31 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204753 | 30.07.2028 | 12000 | CCK-MP-HAUL-DT773 -STRSYS-STPMP | 6800 | 75884 | 10573
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Air Con Service & Overhaul | 2028-07-30 | 2028-07-31 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110643 | 30.07.2028 | 12 Monthly | CCK-MP-HAUL-DT774 -STRUCT-CABIN-AIRCN | 6800 | 81047 | 35545
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Suspension LHR | 2028-07-30 | 2028-07-31 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000025525 | 30.07.2028 | 28000 | CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYLR | 7400 | 87780 | 13439
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Suspension RHR | 2028-07-30 | 2028-07-31 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000025526 | 30.07.2028 | 28000 | CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYRR | 7400 | 87780 | 13439
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Brake Slack Adjuster Front | 2028-07-31 | 2028-07-31 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000026746 | 31.07.2028 | 20000 | CCK-MP-HAUL-DT155 -BRKSYS-SLACK-SLACF | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Brake Slack Adjuster Rear | 2028-07-31 | 2028-07-31 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000026747 | 31.07.2028 | 20000 | CCK-MP-HAUL-DT155 -BRKSYS-SLACK-SLACR | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Motor Lube Axle Hoses | 2028-08-01 | 2028-08-01 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000271948 | 01.08.2028 | 12000 | CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYM01 | 7400 | 91273 | 15565
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 789C AHS Replace Proactive Coax | 2028-08-01 | 2028-08-01 | 12 hrs | FY29 | 12 | 90022477 | B2 | 1000235593 | 01.08.2028 | 24 Monthly | CCK-MP-SUPP-WC225 -COMMUN-FLMGT
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Service Air Conditioner 12M | 2028-08-01 | 2028-08-02 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174167 | 01.08.2028 | 12 Monthly | CCK-MP-HAUL-DT130 -STRUCT-CABIN-AIRCN | 7400 | 85185 | 7959
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Cylinder Steering LH | 2028-08-02 | 2028-08-02 | 10 hrs | FY29 | 10 | 90011555 | B1 | 1000093003 | 02.08.2028 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STRCY-STCYL | 5100 | 64374 | 7976
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Cylinder Steering RH | 2028-08-02 | 2028-08-02 | 6 hrs | FY29 | 12 | 90011556 | B1 | 1000093004 | 02.08.2028 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STRCY-STCYR | 5100 | 64374 | 7976
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Cylinder Suspension LHF | 2028-08-02 | 2028-08-02 | 14 hrs | FY29 | 26 | 90011572 | B1 | 1000093019 | 02.08.2028 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-SUSPN-SCYLF | 5100 | 64374 | 7976
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Cylinder Suspension RHF | 2028-08-02 | 2028-08-03 | 23 hrs | FY29 | 44 | 90011573 | B1 | 1000093020 | 02.08.2028 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-SUSPN-SCYRF | 5100 | 64374 | 7976
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Cyl Steering LH | 2028-08-02 | 2028-08-02 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000095080 | 02.08.2028 | 15000 | CCK-MP-HAUL-DT766 -STRSYS-STRCY-STCYL | 6800 | 78074 | 3027
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Cyl Steering RH | 2028-08-02 | 2028-08-02 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000095081 | 02.08.2028 | 15000 | CCK-MP-HAUL-DT766 -STRSYS-STRCY-STCYR | 6800 | 78074 | 3027
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Transmission Oil Cooler | 2028-08-02 | 2028-08-02 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000083449 | 02.08.2028 | 18000 | CCK-MP-HAUL-DT151 -TRNSYS-TROLC | 7400 | 84253 | 3168
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Auto Lube Pump | 2028-08-03 | 2028-08-03 | 2 hrs | FY29 | 2 | 90002914 | B2 | 1000040611 | 03.08.2028 | 6000 | CCK-MP-SUPP-WC225 -GRSYST-ALBPP | 5000 | 75244 | 1997
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Sepura SCC Microphone | 2028-08-03 | 2028-08-03 | 0.5 hrs | FY29 | 0.5 | 90029001 | B1 | 1000289628 | 03.08.2028 | 12 Monthly | CCK-MP-SUPP-WC3111-COMMUN-RADIO | 5600 | 51257 | 51257
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Air Con Service & Overhaul | 2028-08-03 | 2028-08-04 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110612 | 03.08.2028 | 12 Monthly | CCK-MP-HAUL-DT752 -STRUCT-CABIN-AIRCN | 6800 | 80681 | 31412
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Cyl Suspension LHF | 2028-08-03 | 2028-08-05 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067569 | 03.08.2028 | 28000 | CCK-MP-HAUL-DT142 -STRUCT-SUSPN-SCYLF | 7400 | 87027 | 13221
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Operator Cabin Dash Bulbs | 2028-08-04 | 2028-08-04 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158220 | 04.08.2028 | 3000 | CCK-MP-HAUL-DT755 -STRUCT-CABIN | 6800 | 84587 | 84587
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Transmisson Calibration | 2028-08-04 | 2028-08-04 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298726 | 04.08.2028 | 4500 | CCK-MP-HAUL-DT143 -TRNSYS-TRANS | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Engine Cat C175-16 | 2028-08-04 | 2028-08-07 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000156027 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -ENGINE | 7400 | 86975 | 31553
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Torque Converter | 2028-08-04 | 2028-08-05 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000026335 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -TRNSYS-TRQUE | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Steering HMU | 2028-08-04 | 2028-08-04 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000026353 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -STRSYS-STHMU | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Ovhl Accumulator Steering Middle | 2028-08-04 | 2028-08-04 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026357 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -STRSYS-STACC-SACCM | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Ovhl Accumulator Steering Rear | 2028-08-04 | 2028-08-04 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026358 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -STRSYS-STACC-SACCR | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Rear Axle Linkages | 2028-08-04 | 2028-08-06 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000026370 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -STRUCT-CHASS-AXLIK | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Wheel Group Front RH | 2028-08-04 | 2028-08-05 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157251 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -STRUCT-AXLES-HUBRH | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Suspension RHF | 2028-08-04 | 2028-08-06 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067599 | 04.08.2028 | 28000 | CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYRF | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Replace Hoses Hoist System | 2028-08-04 | 2028-08-05 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000083415 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -HYDSYS-HDHLF-HSTHO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Replace Brake System Hoses | 2028-08-04 | 2028-08-06 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000083421 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BRHLF-BRHOS | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Brake Cooling System Hoses | 2028-08-04 | 2028-08-05 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000083422 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -BRKSYS-BRHLF-CBRHO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Drive Line Axle LH | 2028-08-04 | 2028-08-04 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124615 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -FDRSYS-DRLAX-AXLLH | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Drive Line Axle RH | 2028-08-04 | 2028-08-04 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124616 | 04.08.2028 | 24000 | CCK-MP-HAUL-DT149 -FDRSYS-DRLAX-AXLRH | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Service Air Conditioner 12M | 2028-08-05 | 2028-08-06 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174180 | 05.08.2028 | 12 Monthly | CCK-MP-HAUL-DT151 -STRUCT-CABIN-AIRCN | 7400 | 84253 | 21869
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Transmisson Calibration | 2028-08-07 | 2028-08-07 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298795 | 07.08.2028 | 4500 | CCK-MP-HAUL-DT5255-TRNSYS-TRANS | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Drive Shaft Transmission | 2028-08-07 | 2028-08-07 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000167377 | 07.08.2028 | 18000 | CCK-MP-HAUL-DT5318-FDRSYS-DRSHT | 7400 | 45240 | 2794
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Motor Lube Axle Hoses | 2028-08-07 | 2028-08-07 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272194 | 07.08.2028 | 12000 | CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYM01 | 7400 | 45240 | 21163
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Auto Lube Pump | 2028-08-07 | 2028-08-07 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094401 | 07.08.2028 | 8000 | CCK-MP-HAUL-DT753 -GRSYST-ALBPP | 6800 | 85999 | 2700
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Accumulator Hyd Steer Front | 2028-08-07 | 2028-08-07 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000094446 | 07.08.2028 | 25000 | CCK-MP-HAUL-DT754 -STRSYS-STACC-SACCF | 6800 | 83256 | 11369
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Transmission | 2028-08-07 | 2028-08-08 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272339 | 07.08.2028 | 18000 | CCK-MP-HAUL-DT147 -TRNSYS-TRANS | 7400 | 84659 | 716
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Replace Steering System Hoses | 2028-08-08 | 2028-08-10 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000082931 | 08.08.2028 | 15000 | CCK-MP-HAUL-DT088 -STRSYS-STHLF-STRHO | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Steering Hyd Oil Cooler | 2028-08-08 | 2028-08-08 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107019 | 08.08.2028 | 15000 | CCK-MP-HAUL-DT088 -STRSYS-STOCO | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Spider Trans Driveshaft | 2028-08-08 | 2028-08-08 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000167056 | 08.08.2028 | 6000 | CCK-MP-HAUL-DT5314-FDRSYS-DRSHT-UNVSL | 7400 | 45898 | 950
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Initial Engine Valve Set | 2028-08-08 | 2028-08-08 | 12 hrs | FY29 | 24 | 90015644 | B1 | 1000201199 | 08.08.2028 | 250 | CCK-MP-SUPP-SV4104-ENGINE | 5100 | 23504 | 7410
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Cyl Steering RH | 2028-08-09 | 2028-08-09 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000095240 | 09.08.2028 | 15000 | CCK-MP-HAUL-DT769 -STRSYS-STRCY-STCYR | 6800 | 80508 | 16026
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Transmisson Calibration | 2028-08-10 | 2028-08-10 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298816 | 10.08.2028 | 4500 | CCK-MP-HAUL-DT5316-TRNSYS-TRANS | 7400 | 45108 | 15135
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Grid Box Blower Motor LH | 2028-08-10 | 2028-08-10 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000095330 | 10.08.2028 | 25000 | CCK-MP-HAUL-DT771 -ELCTHV-HVGBM-GBMLH | 6800 | 84423 | 11482
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Grid Box Blower Motor RH | 2028-08-10 | 2028-08-10 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000095331 | 10.08.2028 | 25000 | CCK-MP-HAUL-DT771 -ELCTHV-HVGBM-GBMRH | 6800 | 84423 | 11212
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl AOC Fan Motor Rear | 2028-08-11 | 2028-08-11 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000167323 | 11.08.2028 | 12000 | CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYM02 | 7400 | 45240 | 21163
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Transmisson Calibration | 2028-08-12 | 2028-08-12 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298723 | 12.08.2028 | 4500 | CCK-MP-HAUL-DT138 -TRNSYS-TRANS | 7400 | 82982 | 6438
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Steering Bell Crank & Links | 2028-08-13 | 2028-08-14 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317672 | 13.08.2028 | 30000 | CCK-MP-HAUL-DT5316-STRSYS-STLTR-STLAC | 7400 | 45108 | 45108
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Auto Lube Pump | 2028-08-13 | 2028-08-13 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094666 | 13.08.2028 | 8000 | CCK-MP-HAUL-DT758 -GRSYST-ALBPP | 6800 | 85895 | 10280
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Engine Cat C175-16 | 2028-08-13 | 2028-08-16 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000156039 | 13.08.2028 | 24000 | CCK-MP-HAUL-DT151 -ENGINE | 7400 | 84253 | 21869
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Cyl Suspension LHF | 2028-08-14 | 2028-08-16 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067517 | 14.08.2028 | 28000 | CCK-MP-HAUL-DT127 -STRUCT-SUSPN-SCYLF | 7400 | 83059 | 12964
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Operator Seat | 2028-08-14 | 2028-08-14 | 3 hrs | FY29 | 6 | 90018539 | B1 | 1000201213 | 14.08.2028 | 6000 | CCK-MP-SUPP-SV4104-STRUCT-CABIN-SEATS | 5100 | 23504 | 1084
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Grid Box Blower Motor RH | 2028-08-14 | 2028-08-14 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000094907 | 14.08.2028 | 25000 | CCK-MP-HAUL-DT763 -ELCTHV-HVGBM-GBMRH | 6800 | 74143 | 11289
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Brake Manifold | 2028-08-14 | 2028-08-14 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292169 | 14.08.2028 | 25000 | CCK-MP-HAUL-DT767 -BRKSYS-BRVLV | 6800 | 74312 | 10840
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Hoist LH | 2028-08-14 | 2028-08-14 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128587 | 14.08.2028 | 28000 | CCK-MP-HAUL-DT147 -HYDSYS-HOCYL-HCYLL | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Hoist RH | 2028-08-14 | 2028-08-14 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128588 | 14.08.2028 | 28000 | CCK-MP-HAUL-DT147 -HYDSYS-HOCYL-HCYLR | 7400 | 84708 | 12913
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Transmission | 2028-08-14 | 2028-08-15 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272333 | 14.08.2028 | 18000 | CCK-MP-HAUL-DT142 -TRNSYS-TRANS | 7400 | 87027 | 9824
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Replace Hoses Differential System | 2028-08-14 | 2028-08-14 | 5 hrs | FY29 | 5 | 90010101 | B2 | 1000090134 | 14.08.2028 | 18000 | CCK-MP-HAUL-DT142 -FDRSYS-DIFFL-DIFHO | 7400 | 87027 | 27424
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Repl Sepura SCC Microphone | 2028-08-15 | 2028-08-15 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289617 | 15.08.2028 | 12 Monthly | CCK-MP-SUPP-SV4104-COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Pump Brake Cooling | 2028-08-16 | 2028-08-16 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000025951 | 16.08.2028 | 24000 | CCK-MP-HAUL-DT143 -BRKSYS-HYFPP | 7400 | 88225 | 8738
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Hub & Spindle LH | 2028-08-17 | 2028-08-18 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000095041 | 17.08.2028 | 18000 | CCK-MP-HAUL-DT765 -STRUCT-AXLES-HUBLH | 6800 | 78429 | 23008
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Hub & Spindle RH | 2028-08-17 | 2028-08-18 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000095042 | 17.08.2028 | 18000 | CCK-MP-HAUL-DT765 -STRUCT-AXLES-HUBRH | 6800 | 78429 | 4357
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Cyl Suspension RHF | 2028-08-17 | 2028-08-19 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000095044 | 17.08.2028 | 18000 | CCK-MP-HAUL-DT765 -STRUCT-SUSPN-SCYRF | 6800 | 78429 | 4357
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 250hr Initial Valve Set | 2028-08-17 | 2028-08-17 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156030 | 17.08.2028 | 250 | CCK-MP-HAUL-DT149 -ENGINE | 7400 | 86975 | 31553
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Tyre Sense Battery | 2028-08-17 | 2028-08-17 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153167 | 17.08.2028 | 24 Monthly | CCK-MP-HAUL-DT158 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Operators Seat | 2028-08-18 | 2028-08-18 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000024062 | 18.08.2028 | 15000 | CCK-MP-HAUL-DT086 -STRUCT-CABIN-SEATS | 7400 | 86822 | 14768
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Service Air Conditioner 12M | 2028-08-19 | 2028-08-20 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174111 | 19.08.2028 | 12 Monthly | CCK-MP-HAUL-DT056 -STRUCT-CABIN-AIRCN | 7400 | 84421 | 18034
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Suspension LHF | 2028-08-19 | 2028-08-21 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067585 | 19.08.2028 | 28000 | CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYLF | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Suspension RHF | 2028-08-19 | 2028-08-21 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067587 | 19.08.2028 | 28000 | CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYRF | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Replace Steering System Hoses | 2028-08-19 | 2028-08-21 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083444 | 19.08.2028 | 15000 | CCK-MP-HAUL-DT150 -STRSYS-STHLF-STRHO | 7400 | 86608 | 29495
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Replace Operator Cabin Dash Bulbs | 2028-08-19 | 2028-08-19 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158227 | 19.08.2028 | 3000 | CCK-MP-HAUL-DT762 -STRUCT-CABIN | 6800 | 76486 | 20565
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Tyre Sense Battery | 2028-08-19 | 2028-08-19 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153147 | 19.08.2028 | 24 Monthly | CCK-MP-HAUL-DT100 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Brake Slack Adjuster Front | 2028-08-20 | 2028-08-20 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000023666 | 20.08.2028 | 20000 | CCK-MP-HAUL-DT055 -BRKSYS-SLACK-SLACF | 7400 | 84122 | 7001
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Brake Manifold | 2028-08-20 | 2028-08-20 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000291939 | 20.08.2028 | 25000 | CCK-MP-HAUL-DT752 -BRKSYS-BRVLV | 6800 | 80681 | 36242
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Air Con Service & Overhaul | 2028-08-20 | 2028-08-21 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110639 | 20.08.2028 | 12 Monthly | CCK-MP-HAUL-DT770 -STRUCT-CABIN-AIRCN | 6800 | 79305 | 24535
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Engine Midlife Complete | 2028-08-20 | 2028-08-21 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000155864 | 20.08.2028 | 12000 | CCK-MP-HAUL-DT054 -ENGINE | 7400 | 88111 | 21034
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Grid Box Blower Motor RH | 2028-08-21 | 2028-08-21 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000094271 | 21.08.2028 | 25000 | CCK-MP-HAUL-DT751 -ELCTHV-HVGBM-GBMRH | 6800 | 86211 | 35380
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Brake Rotochamber Front | 2028-08-22 | 2028-08-22 | 2 hrs | FY29 | 2 | 90004017 | B2 | 1000079218 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-BRKSYS-BRCYL-ROTFR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Brake Rotochamber Left Hand Rear | 2028-08-22 | 2028-08-22 | 2 hrs | FY29 | 2 | 90004017 | B2 | 1000079219 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-BRKSYS-BRCYL-ROTLR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Brake Rotochamber Right Hand Rear | 2028-08-22 | 2028-08-22 | 2 hrs | FY29 | 2 | 90004017 | B2 | 1000079220 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-BRKSYS-BRCYL-ROTRR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Brake Oil Cooler Front | 2028-08-22 | 2028-08-22 | 6 hrs | FY29 | 6 | 90004002 | B2 | 1000079199 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-BRKSYS-BROCO-BROCF | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Brake Control Valves | 2028-08-22 | 2028-08-23 | 24 hrs | FY29 | 48 | 90004000 | B2 | 1000079197 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-BRKSYS-BRVLV | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Brake Slack Adjuster Front | 2028-08-22 | 2028-08-22 | 2 hrs | FY29 | 2 | 90004018 | B2 | 1000079221 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-BRKSYS-SLACK-SLACF | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Brake Slack Adjuster Rear | 2028-08-22 | 2028-08-22 | 2 hrs | FY29 | 2 | 90004019 | B2 | 1000079222 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-BRKSYS-SLACK-SLACR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Engine | 2028-08-22 | 2028-08-26 | 104 hrs | FY29 | 398 | 90028980 | B1 | 1000289477 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-ENGINE | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Aftercooler | 2028-08-22 | 2028-08-22 | 6 hrs | FY29 | 6 | 90004021 | B2 | 1000079177 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-ENGINE-INTEX-AFTER | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Pump Drive | 2028-08-22 | 2028-08-22 | 16 hrs | FY29 | 28 | 90003984 | B2 | 1000079179 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-ENGINE-PMPDR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Rear Axle Oil Pump | 2028-08-22 | 2028-08-22 | 2 hrs | FY29 | 2 | 90003996 | B2 | 1000079192 | 22.08.2028 | 10000 | CCK-MP-SUPP-WC3111-FDRSYS-AXLEC-HYPUM | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Rear Axle Cooling Fan Motor | 2028-08-22 | 2028-08-22 | 2 hrs | FY29 | 2 | 90003997 | B2 | 1000079193 | 22.08.2028 | 10000 | CCK-MP-SUPP-WC3111-FDRSYS-AXLEC-MTFAN | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Transmission Driveshaft | 2028-08-22 | 2028-08-22 | 8 hrs | FY29 | 14 | 90003993 | B2 | 1000079184 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-FDRSYS-DRSHT | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Final Drive LH | 2028-08-22 | 2028-08-22 | 14 hrs | FY29 | 26 | 90003995 | B1 | 1000079190 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-FDRSYS-FDRVE-FDRLH | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Final Drive RH | 2028-08-22 | 2028-08-22 | 14 hrs | FY29 | 26 | 90007346 | B1 | 1000079191 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-FDRSYS-FDRVE-FDRRH | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Overhaul Airconditioner | 2028-08-22 | 2028-08-23 | 24 hrs | FY29 | 24 | 90028727 | B1 | 1000289480 | 22.08.2028 | 10000 | CCK-MP-SUPP-WC3111-STRUCT-CABIN-AIRCN | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Suspension Cylinder LHF | 2028-08-22 | 2028-08-22 | 16 hrs | FY29 | 28 | 90004013 | B2 | 1000079212 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYLF | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Suspension Cylinder LHR | 2028-08-22 | 2028-08-22 | 16 hrs | FY29 | 28 | 90004014 | B2 | 1000079214 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYLR | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Suspension Cylinder RHF | 2028-08-22 | 2028-08-22 | 16 hrs | FY29 | 28 | 90004013 | B2 | 1000079213 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYRF | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Transmission | 2028-08-22 | 2028-08-23 | 28 hrs | FY29 | 52 | 90003988 | B2 | 1000079181 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-TRNSYS-TRANS | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Transmission Oil Cooler | 2028-08-22 | 2028-08-22 | 8 hrs | FY29 | 8 | 90003992 | B2 | 1000079216 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-TRNSYS-TROLC | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Torque Converter | 2028-08-22 | 2028-08-22 | 14 hrs | FY29 | 26 | 90003987 | B2 | 1000079180 | 22.08.2028 | 20000 | CCK-MP-SUPP-WC3111-TRNSYS-TRQUE | 5600 | 51257 | 8333
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Brake Accumulator Front | 2028-08-22 | 2028-08-22 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000095337 | 22.08.2028 | 25000 | CCK-MP-HAUL-DT771 -BRKSYS-BRACC-BACCF | 6800 | 84423 | 11258
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Hyd Pump Steering Main & Fan | 2028-08-22 | 2028-08-22 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000024866 | 22.08.2028 | 24000 | CCK-MP-HAUL-DT099 -STRSYS-STPMP | 7400 | 87442 | 8961
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Service Air Conditioner 12M | 2028-08-22 | 2028-08-23 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174165 | 22.08.2028 | 12 Monthly | CCK-MP-HAUL-DT126 -STRUCT-CABIN-AIRCN | 7400 | 88657 | 54006
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Auto Lube Pump | 2028-08-23 | 2028-08-23 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094984 | 23.08.2028 | 8000 | CCK-MP-HAUL-DT764 -GRSYST-ALBPP | 6800 | 75315 | 9805
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Service Air Conditioner 12M | 2028-08-23 | 2028-08-24 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174187 | 23.08.2028 | 12 Monthly | CCK-MP-HAUL-DT160 -STRUCT-CABIN-AIRCN | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Spider Trans Driveshaft | 2028-08-23 | 2028-08-23 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154946 | 23.08.2028 | 6000 | CCK-MP-HAUL-DT099 -FDRSYS-DRSHT-UNVSL | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Hoist LH | 2028-08-23 | 2028-08-23 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128563 | 23.08.2028 | 28000 | CCK-MP-HAUL-DT100 -HYDSYS-HOCYL-HCYLL | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Hoist RH | 2028-08-23 | 2028-08-23 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128564 | 23.08.2028 | 28000 | CCK-MP-HAUL-DT100 -HYDSYS-HOCYL-HCYLR | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Service Air Conditioner 12M | 2028-08-24 | 2028-08-25 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174116 | 24.08.2028 | 12 Monthly | CCK-MP-HAUL-DT088 -STRUCT-CABIN-AIRCN | 7400 | 89037 | 14711
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Cyl Suspension LHF | 2028-08-25 | 2028-08-27 | 60 hrs | FY29 | 112 | 90011365 | B1 | 1000095149 | 25.08.2028 | 18000 | CCK-MP-HAUL-DT767 -STRUCT-SUSPN-SCYLF | 6800 | 74312 | 7082
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Service Air Conditioner 12M | 2028-08-26 | 2028-08-27 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174185 | 26.08.2028 | 12 Monthly | CCK-MP-HAUL-DT159 -STRUCT-CABIN-AIRCN | 7400 | 90235 | 41100
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Pump Drive | 2028-08-26 | 2028-08-27 | 20 hrs | FY29 | 39 | 90002365 | B1 | 1000025868 | 26.08.2028 | 24000 | CCK-MP-HAUL-DT142 -ENGINE-PMPDR | 7400 | 87027 | 8755
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 250hr Initial Valve Set | 2028-08-26 | 2028-08-26 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156042 | 26.08.2028 | 250 | CCK-MP-HAUL-DT151 -ENGINE | 7400 | 84253 | 21869
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Service Air Conditioner 12M | 2028-08-27 | 2028-08-28 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174115 | 27.08.2028 | 12 Monthly | CCK-MP-HAUL-DT086 -STRUCT-CABIN-AIRCN | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Service Air Conditioner 12M | 2028-08-27 | 2028-08-28 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174179 | 27.08.2028 | 12 Monthly | CCK-MP-HAUL-DT150 -STRUCT-CABIN-AIRCN | 7400 | 86656 | 49988
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Replace Operator Cabin Dash Bulbs | 2028-08-27 | 2028-08-27 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158229 | 27.08.2028 | 3000 | CCK-MP-HAUL-DT764 -STRUCT-CABIN | 6800 | 75315 | 21117
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Transmisson Calibration | 2028-08-27 | 2028-08-27 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298738 | 27.08.2028 | 4500 | CCK-MP-HAUL-DT160 -TRNSYS-TRANS | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Service Air Conditioner 12M | 2028-08-29 | 2028-08-30 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174166 | 29.08.2028 | 12 Monthly | CCK-MP-HAUL-DT127 -STRUCT-CABIN-AIRCN | 7400 | 83059 | 27545
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Spiders Pump Drive Shaft | 2028-08-29 | 2028-08-29 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000027057 | 29.08.2028 | 18000 | CCK-MP-HAUL-DT160 -ENGINE-PMPDR-DRSHT | 7400 | 85085 | 2673
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Steering RH | 2028-08-29 | 2028-08-29 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000024869 | 29.08.2028 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STRCY-STCYR | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Tyre Sense Battery | 2028-08-29 | 2028-08-29 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153152 | 29.08.2028 | 24 Monthly | CCK-MP-HAUL-DT136 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Transmission | 2028-08-30 | 2028-08-31 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272325 | 30.08.2028 | 18000 | CCK-MP-HAUL-DT136 -TRNSYS-TRANS | 7400 | 87780 | 9256
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Steering Hyd Oil Cooler | 2028-09-01 | 2028-09-01 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000111982 | 01.09.2028 | 15000 | CCK-MP-HAUL-DT5202-STRSYS-STOCO | 7400 | 84333 | 14587
777G WC | Onsite PM | Haul | Fortescue | WC2501 | WC2501 Repl Pump Brake Charge & Cooling | 2028-09-01 | 2028-09-01 | 6 hrs | FY29 | 6 | 90037882 | B1 | 1000379767 | 01.09.2028 | 9000 | CCK-MP-SUPP-WC2501-BRKSYS-BRPMP | 2000 | 56945 | 4631
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Cyl Steering LH | 2028-09-01 | 2028-09-01 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000094815 | 01.09.2028 | 15000 | CCK-MP-HAUL-DT761 -STRSYS-STRCY-STCYL | 6800 | 78336 | 16076
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Cyl Steering RH | 2028-09-01 | 2028-09-01 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000026487 | 01.09.2028 | 15000 | CCK-MP-HAUL-DT151 -STRSYS-STRCY-STCYR | 7400 | 84253 | 260
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Spider Trans Driveshaft | 2028-09-01 | 2028-09-01 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154992 | 01.09.2028 | 6000 | CCK-MP-HAUL-DT160 -FDRSYS-DRSHT-UNVSL | 7400 | 85085 | 2673
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Motor Lube Axle Hoses | 2028-09-02 | 2028-09-02 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272192 | 02.09.2028 | 12000 | CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYM01 | 7400 | 45576 | 20480
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl AOC Fan Motor Rear | 2028-09-02 | 2028-09-02 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000167243 | 02.09.2028 | 12000 | CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYM02 | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Cyl Steering RH | 2028-09-03 | 2028-09-03 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000166934 | 03.09.2028 | 15000 | CCK-MP-HAUL-DT5313-STRSYS-STRCY-STCYR | 7400 | 44693 | 1116
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Wheel Group Front RH | 2028-09-05 | 2028-09-06 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157269 | 05.09.2028 | 24000 | CCK-MP-HAUL-DT161 -STRUCT-AXLES-HUBRH | 7400 | 80609 | 8581
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Cyl Steering LH | 2028-09-06 | 2028-09-06 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000166933 | 06.09.2028 | 15000 | CCK-MP-HAUL-DT5313-STRSYS-STRCY-STCYL | 7400 | 44693 | 14543
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Steering Bell Crank & Links | 2028-09-06 | 2028-09-07 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317666 | 06.09.2028 | 30000 | CCK-MP-HAUL-DT5313-STRSYS-STLTR-STLAC | 7400 | 44693 | 14543
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Differential | 2028-09-07 | 2028-09-08 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000026603 | 07.09.2028 | 18000 | CCK-MP-HAUL-DT153 -FDRSYS-DIFFL | 7400 | 84230 | 2506
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Replace Hoses Differential System | 2028-09-07 | 2028-09-07 | 5 hrs | FY29 | 5 | 90010101 | B2 | 1000090161 | 07.09.2028 | 18000 | CCK-MP-HAUL-DT153 -FDRSYS-DIFFL-DIFHO | 7400 | 84230 | 21906
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Replace Trans TCon System Hoses | 2028-09-07 | 2028-09-08 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090160 | 07.09.2028 | 18000 | CCK-MP-HAUL-DT153 -TRNSYS-TRANS-TRNHO | 7400 | 84230 | 21906
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Engine Midlife Complete | 2028-09-07 | 2028-09-08 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000167143 | 07.09.2028 | 12000 | CCK-MP-HAUL-DT5315-ENGINE | 7400 | 45392 | 20546
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Radiator Fan Hoses | 2028-09-07 | 2028-09-07 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307691 | 07.09.2028 | 12000 | CCK-MP-HAUL-DT5315-ENGINE-COSYS-RADTR | 7400 | 45392 | 20546
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Motor Lube Axle Hoses | 2028-09-07 | 2028-09-07 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272188 | 07.09.2028 | 12000 | CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYM01 | 7400 | 45392 | 20546
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Inspect Rear Axle Housing | 2028-09-07 | 2028-09-07 | 1 hr | FY29 | 1 | 90019256 | B1 | 1000196435 | 07.09.2028 | 2000 | CCK-MP-SUPP-WC225 -STRUCT-RAXHO | 5000 | 75244 | 75244
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 250Hr Initial Valve Set | 2028-09-07 | 2028-09-07 | 12 hrs | FY29 | 24 | 90028724 | B1 | 1000289481 | 07.09.2028 | 250 | CCK-MP-SUPP-WC3111-ENGINE | 5600 | 51257 | 8333
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Steering RH | 2028-09-07 | 2028-09-07 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000094392 | 07.09.2028 | 15000 | CCK-MP-HAUL-DT753 -STRSYS-STRCY-STCYR | 6800 | 85999 | 15852
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Differential | 2028-09-07 | 2028-09-08 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000104841 | 07.09.2028 | 18000 | CCK-MP-HAUL-DT126 -FDRSYS-DIFFL | 7400 | 88657 | 2432
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Replace Trans TCon System Hoses | 2028-09-07 | 2028-09-08 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090100 | 07.09.2028 | 18000 | CCK-MP-HAUL-DT126 -TRNSYS-TRANS-TRNHO | 7400 | 88657 | 39846
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Replace Hoses Differential System | 2028-09-07 | 2028-09-07 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090101 | 07.09.2028 | 18000 | CCK-MP-HAUL-DT126 -FDRSYS-DIFFL-DIFHO | 7400 | 88657 | 39846
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Rear Axle Linkages | 2028-09-08 | 2028-09-10 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000025072 | 08.09.2028 | 24000 | CCK-MP-HAUL-DT127 -STRUCT-CHASS-AXLIK | 7400 | 83059 | 27545
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Hyd Pump Steering Main & Fan | 2028-09-08 | 2028-09-08 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000026748 | 08.09.2028 | 24000 | CCK-MP-HAUL-DT155 -STRSYS-STPMP | 7400 | 81407 | 8471
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Operator Cabin Dash Bulbs | 2028-09-08 | 2028-09-08 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158216 | 08.09.2028 | 3000 | CCK-MP-HAUL-DT751 -STRUCT-CABIN | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Replace Operator Cabin Dash Bulbs | 2028-09-08 | 2028-09-08 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158221 | 08.09.2028 | 3000 | CCK-MP-HAUL-DT756 -STRUCT-CABIN | 6800 | 78754 | 78754
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Service Air Conditioner 12M | 2028-09-09 | 2028-09-10 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174119 | 09.09.2028 | 12 Monthly | CCK-MP-HAUL-DT094 -STRUCT-CABIN-AIRCN | 7400 | 88788 | 50851
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Transmission Oil Cooler | 2028-09-09 | 2028-09-09 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000083088 | 09.09.2028 | 18000 | CCK-MP-HAUL-DT126 -TRNSYS-TROLC | 7400 | 88657 | 2403
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Transmission Oil Cooler | 2028-09-10 | 2028-09-10 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000082518 | 10.09.2028 | 18000 | CCK-MP-HAUL-DT058 -TRNSYS-TROLC | 7400 | 87864 | 2167
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Tyre Sense Battery | 2028-09-10 | 2028-09-10 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000272719 | 10.09.2028 | 24 Monthly | CCK-MP-SUPP-PM0001-MANGMT-TYRSN
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Repl Sepura SCC Microphone | 2028-09-10 | 2028-09-10 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289620 | 10.09.2028 | 12 Monthly | CCK-MP-SUPP-WC220 -COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Cyl Steering LH | 2028-09-11 | 2028-09-11 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000024048 | 11.09.2028 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STRCY-STCYL | 7400 | 86846 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Spider Trans Driveshaft | 2028-09-11 | 2028-09-11 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154930 | 11.09.2028 | 6000 | CCK-MP-HAUL-DT086 -FDRSYS-DRSHT-UNVSL | 7400 | 86822 | 2258
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Cyl Steering RH | 2028-09-11 | 2028-09-11 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025568 | 11.09.2028 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STRCY-STCYR | 7400 | 84196 | 13819
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Radiator Fan Hoses | 2028-09-11 | 2028-09-11 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307741 | 11.09.2028 | 12000 | CCK-MP-SUPP-PM0001-ENGINE-COSYS-RADTR | 3400 | 48287 | 48287
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Drive Shaft Transmission | 2028-09-11 | 2028-09-11 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000272709 | 11.09.2028 | 18000 | CCK-MP-SUPP-PM0001-FDRSYS-DRSHT | 3400 | 48287 | 10223
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Wheel End 22:1 Ratio RH | 2028-09-11 | 2028-09-11 | 17.5 hrs | FY29 | 33.5 | 90026961 | B1 | 1000272714 | 11.09.2028 | 18000 | CCK-MP-SUPP-PM0001-FDRSYS-FDRVE-FDRRH | 3400 | 48287 | 48287
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Repl Sepura SCC Microphone | 2028-09-11 | 2028-09-11 | 0.5 hrs | FY29 | 0.5 | 90029002 | B1 | 1000289635 | 11.09.2028 | 12 Monthly | CCK-MP-SUPP-WC224 -COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Replace Steering System Hoses | 2028-09-12 | 2028-09-14 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000082912 | 12.09.2028 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STHLF-STRHO | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Steering Hyd Oil Cooler | 2028-09-12 | 2028-09-12 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107018 | 12.09.2028 | 15000 | CCK-MP-HAUL-DT086 -STRSYS-STOCO | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Steering Bell Crank & Links | 2028-09-12 | 2028-09-13 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317592 | 12.09.2028 | 30000 | CCK-MP-HAUL-DT086 -STRSYS-STLTR-STLAC | 7400 | 86822 | 14283
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Service Air Conditioner 12M | 2028-09-12 | 2028-09-13 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000172996 | 12.09.2028 | 12 Monthly | CCK-MP-HAUL-DT5316-STRUCT-CABIN-AIRCN | 7400 | 45108 | 45108
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Engine Midlife Complete | 2028-09-12 | 2028-09-13 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000167303 | 12.09.2028 | 12000 | CCK-MP-HAUL-DT5317-ENGINE | 7400 | 45576 | 20480
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Radiator Fan Hoses | 2028-09-12 | 2028-09-12 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307695 | 12.09.2028 | 12000 | CCK-MP-HAUL-DT5317-ENGINE-COSYS-RADTR | 7400 | 45576 | 20480
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Pump Brake Cooling | 2028-09-13 | 2028-09-13 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000024293 | 13.09.2028 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-HYFPP | 7400 | 81670 | 8305
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Torque Converter Charge Pump | 2028-09-13 | 2028-09-13 | 6 hrs | FY29 | 6 | 90000901 | B2 | 1000033357 | 13.09.2028 | 22000 | CCK-MP-SUPP-WC225 -TRNSYS-TRPMP-TCCPP | 5000 | 75244 | 11430
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Engine Midlife Complete | 2028-09-13 | 2028-09-15 | 49 hrs | FY29 | 76 | 90028571 | B1 | 1000285179 | 13.09.2028 | 12500 | CCK-MP-HAUL-DT761 -ENGINE | 6800 | 78336 | 23274
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Service Air Conditioner 12M | 2028-09-13 | 2028-09-14 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174172 | 13.09.2028 | 12 Monthly | CCK-MP-HAUL-DT140 -STRUCT-CABIN-AIRCN | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Transmission | 2028-09-14 | 2028-09-15 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272319 | 14.09.2028 | 18000 | CCK-MP-HAUL-DT127 -TRNSYS-TRANS | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Drive Shaft Transmission | 2028-09-14 | 2028-09-14 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154953 | 14.09.2028 | 18000 | CCK-MP-HAUL-DT127 -FDRSYS-DRSHT | 7400 | 83059 | 2333
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Grid Box Blower Motor RH | 2028-09-14 | 2028-09-14 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000094854 | 14.09.2028 | 25000 | CCK-MP-HAUL-DT762 -ELCTHV-HVGBM-GBMRH | 6800 | 76486 | 10392
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Brake Manifold | 2028-09-14 | 2028-09-14 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292159 | 14.09.2028 | 25000 | CCK-MP-HAUL-DT762 -BRKSYS-BRVLV | 6800 | 76486 | 10392
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Brake Accumulator Front | 2028-09-14 | 2028-09-14 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000094860 | 14.09.2028 | 25000 | CCK-MP-HAUL-DT762 -BRKSYS-BRACC-BACCF | 6800 | 76486 | 10392
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Steering HMU | 2028-09-14 | 2028-09-14 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094867 | 14.09.2028 | 25000 | CCK-MP-HAUL-DT762 -STRSYS-STHMU | 6800 | 76486 | 10392
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Spiders Pump Drive Shaft | 2028-09-15 | 2028-09-15 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000024025 | 15.09.2028 | 18000 | CCK-MP-HAUL-DT086 -ENGINE-PMPDR-DRSHT | 7400 | 86846 | 2216
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Spider Trans Driveshaft | 2028-09-15 | 2028-09-15 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000167136 | 15.09.2028 | 6000 | CCK-MP-HAUL-DT5315-FDRSYS-DRSHT-UNVSL | 7400 | 45392 | 2340
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl AOC Fan Motor Rear | 2028-09-15 | 2028-09-15 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000167083 | 15.09.2028 | 12000 | CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYM02 | 7400 | 45392 | 20546
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Cyl Steering LH | 2028-09-15 | 2028-09-15 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000095292 | 15.09.2028 | 15000 | CCK-MP-HAUL-DT770 -STRSYS-STRCY-STCYL | 6800 | 79305 | 15443
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Replace Operator Cabin Dash Bulbs | 2028-09-15 | 2028-09-15 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158235 | 15.09.2028 | 3000 | CCK-MP-HAUL-DT770 -STRUCT-CABIN | 6800 | 79305 | 79305
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Wheel Group Front RH | 2028-09-16 | 2028-09-17 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157205 | 16.09.2028 | 24000 | CCK-MP-HAUL-DT086 -STRUCT-AXLES-HUBRH | 7400 | 86822 | 8185
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Operators Seat | 2028-09-16 | 2028-09-16 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000026765 | 16.09.2028 | 15000 | CCK-MP-HAUL-DT155 -STRUCT-CABIN-SEATS | 7400 | 81407 | 42
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Steering Hoses Lines | 2028-09-16 | 2028-09-17 | 24 hrs | FY29 | 48 | 90003058 | B2 | 1000240004 | 16.09.2028 | 18000 | CCK-MP-SUPP-WC008 -STRSYS-STHLF | 3500 | 51417 | 51417
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Cylinder Steering LH | 2028-09-16 | 2028-09-16 | 8 hrs | FY29 | 14 | 90000275 | B2 | 1000018401 | 16.09.2028 | 9000 | CCK-MP-SUPP-WC008 -STRSYS-STRCY-STCYL | 3500 | 51417 | 352
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Cylinder Steering RH | 2028-09-16 | 2028-09-16 | 8 hrs | FY29 | 14 | 90000275 | B2 | 1000018402 | 16.09.2028 | 9000 | CCK-MP-SUPP-WC008 -STRSYS-STRCY-STCYR | 3500 | 51417 | 352
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Refurbish A Frame | 2028-09-16 | 2028-09-17 | 24 hrs | FY29 | 48 | 90003067 | B2 | 1000239909 | 16.09.2028 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-CHASS-AFRME | 3500 | 51417 | 10294
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 OverHaul Tag Link | 2028-09-16 | 2028-09-17 | 24 hrs | FY29 | 48 | 90003068 | B2 | 1000239783 | 16.09.2028 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-CHASS-TAGLK | 3500 | 51417 | 10294
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Cylinder Suspension LHF | 2028-09-16 | 2028-09-17 | 28 hrs | FY29 | 56 | 90003070 | B2 | 1000239912 | 16.09.2028 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-SUSPN-SCYLF | 3500 | 51417 | 10294
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Cylinder Suspension LHR | 2028-09-16 | 2028-09-17 | 26 hrs | FY29 | 50 | 90003071 | B2 | 1000240001 | 16.09.2028 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-SUSPN-SCYLR | 3500 | 51417 | 10294
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Cylinder Suspension RHF | 2028-09-16 | 2028-09-17 | 28 hrs | FY29 | 56 | 90003070 | B2 | 1000239915 | 16.09.2028 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-SUSPN-SCYRF | 3500 | 51417 | 10295
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Cylinder Suspension RHR | 2028-09-16 | 2028-09-17 | 26 hrs | FY29 | 50 | 90003071 | B2 | 1000239918 | 16.09.2028 | 18000 | CCK-MP-SUPP-WC008 -STRUCT-SUSPN-SCYRR | 3500 | 51417 | 10294
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Brake Relay Front | 2028-09-17 | 2028-09-17 | 2 hrs | FY29 | 2 | 90002915 | B2 | 1000040565 | 17.09.2028 | 11000 | CCK-MP-SUPP-WC224 -PNEUMC-BRVLR-SVBRF | 5000 | 71088 | 608
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Engine Module | 2028-09-17 | 2028-09-21 | 102 hrs | FY29 | 226 | 90011318 | B1 | 1000094214 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -ENGINE | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Wheel Motor LH | 2028-09-17 | 2028-09-19 | 45.5 hrs | FY29 | 83.5 | 90011335 | B1 | 1000094274 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -FDRSYS-WLMTR-WHMLH | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Wheel Motor Oil LH | 2028-09-17 | 2028-09-17 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338198 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -FDRSYS-WLMTR-WHMLH | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Wheel Motor RH | 2028-09-17 | 2028-09-19 | 45.5 hrs | FY29 | 83.5 | 90011336 | B1 | 1000094275 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -FDRSYS-WLMTR-WHMRH | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Wheel Motor Oil RH | 2028-09-17 | 2028-09-17 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338199 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -FDRSYS-WLMTR-WHMRH | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Brake Accumulator Front | 2028-09-17 | 2028-09-17 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000094277 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -BRKSYS-BRACC-BACCF | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Brake Accumulator Rear | 2028-09-17 | 2028-09-17 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000094278 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -BRKSYS-BRACC-BACCR | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Valve Retard & Brake Treadle | 2028-09-17 | 2028-09-17 | 5.5 hrs | FY29 | 5.5 | 90011345 | B1 | 1000094280 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -BRKSYS-BRVTR | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Replace Brake Cooling Hoses | 2028-09-17 | 2028-09-17 | 8.5 hrs | FY29 | 14.5 | 90011344 | B1 | 1000223871 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -BRKSYS-BRHLF | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Steering Bleed Down Manifold | 2028-09-17 | 2028-09-17 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094282 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -STRSYS-STBDM | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Steering HMU | 2028-09-17 | 2028-09-17 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094284 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -STRSYS-STHMU | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Accumulator Hyd Steer Front | 2028-09-17 | 2028-09-17 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000094287 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -STRSYS-STACC-SACCF | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Accumulator Hyd Steering Rear | 2028-09-17 | 2028-09-17 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000094288 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -STRSYS-STACC-SACCR | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Hoist LH | 2028-09-17 | 2028-09-17 | 17 hrs | FY29 | 33 | 90011357 | B1 | 1000094292 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -HYDSYS-HOCYL-HCYLL | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Drive Shaft | 2028-09-17 | 2028-09-17 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094294 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -HYDSYS-DRSHT | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Suspension LHR | 2028-09-17 | 2028-09-18 | 32 hrs | FY29 | 50 | 90011367 | B1 | 1000094303 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -STRUCT-SUSPN-SCYLR | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Suspension RHR | 2028-09-17 | 2028-09-18 | 32 hrs | FY29 | 50 | 90011368 | B1 | 1000094304 | 17.09.2028 | 25000 | CCK-MP-HAUL-DT751 -STRUCT-SUSPN-SCYRR | 6800 | 86211 | 11291
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Transmisson Calibration | 2028-09-17 | 2028-09-17 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298724 | 17.09.2028 | 4500 | CCK-MP-HAUL-DT140 -TRNSYS-TRANS | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl AOC Fan Motor Rear | 2028-09-17 | 2028-09-17 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000025751 | 17.09.2028 | 12000 | CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYM02 | 7400 | 86767 | 8224
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Axle Lube Hyd Pump | 2028-09-17 | 2028-09-17 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000083280 | 17.09.2028 | 24000 | CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYPUM | 7400 | 86767 | 8224
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Drive Shaft Transmission | 2028-09-18 | 2028-09-18 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154991 | 18.09.2028 | 18000 | CCK-MP-HAUL-DT159 -FDRSYS-DRSHT | 7400 | 90235 | 20303
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Brake Slack Adjuster Front | 2028-09-19 | 2028-09-19 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000026878 | 19.09.2028 | 20000 | CCK-MP-HAUL-DT157 -BRKSYS-SLACK-SLACF | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Brake Slack Adjuster Rear | 2028-09-19 | 2028-09-19 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000026879 | 19.09.2028 | 20000 | CCK-MP-HAUL-DT157 -BRKSYS-SLACK-SLACR | 7400 | 83041 | 4183
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Brake Rotochamber Front | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90004017 | B2 | 1000079283 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-BRKSYS-BRCYL-ROTFR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Brake Rotochamber Left Hand Rear | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90004017 | B2 | 1000079284 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-BRKSYS-BRCYL-ROTLR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Brake Rotochamber Right Hand Rear | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90004017 | B2 | 1000079285 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-BRKSYS-BRCYL-ROTRR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Brake Oil Cooler Front | 2028-09-19 | 2028-09-19 | 6 hrs | FY29 | 6 | 90004002 | B2 | 1000079264 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-BRKSYS-BROCO-BROCF | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Brake Control Valves | 2028-09-19 | 2028-09-20 | 24 hrs | FY29 | 48 | 90004000 | B2 | 1000079262 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-BRKSYS-BRVLV | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Brake Slack Adjustor Front | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90004018 | B2 | 1000079286 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-BRKSYS-SLACK-SLACF | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Brake Slack Adjustor Rear | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90004019 | B2 | 1000079287 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-BRKSYS-SLACK-SLACR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Engine | 2028-09-19 | 2028-09-23 | 104 hrs | FY29 | 398 | 90028980 | B1 | 1000289483 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-ENGINE | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Radiator Assembly | 2028-09-19 | 2028-09-20 | 22 hrs | FY29 | 40 | 90003977 | B2 | 1000079243 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-ENGINE-COSYS-RADTR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Pump Drive | 2028-09-19 | 2028-09-19 | 16 hrs | FY29 | 28 | 90003984 | B2 | 1000079244 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-ENGINE-PMPDR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl PTO Uni's & Driveshaft | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90031094 | B1 | 1000307816 | 19.09.2028 | 10000 | CCK-MP-SUPP-WC3112-ENGINE-PMPDR-DRSHT | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Rear Axle Oil Pump | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90003996 | B2 | 1000079257 | 19.09.2028 | 10000 | CCK-MP-SUPP-WC3112-FDRSYS-AXLEC-HYPUM | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Rear Axle Cooling Fan Motor | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90003997 | B2 | 1000079258 | 19.09.2028 | 10000 | CCK-MP-SUPP-WC3112-FDRSYS-AXLEC-MTFAN | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Differential | 2028-09-19 | 2028-09-20 | 22 hrs | FY29 | 34 | 90003994 | B2 | 1000079250 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-FDRSYS-DIFFL | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Transmission Driveshaft | 2028-09-19 | 2028-09-19 | 8 hrs | FY29 | 14 | 90003993 | B2 | 1000079249 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-FDRSYS-DRSHT | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Final Drive LH | 2028-09-19 | 2028-09-19 | 14 hrs | FY29 | 26 | 90003995 | B1 | 1000079255 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-FDRSYS-FDRVE-FDRLH | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Final Drive RH | 2028-09-19 | 2028-09-19 | 14 hrs | FY29 | 26 | 90007346 | B1 | 1000079256 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-FDRSYS-FDRVE-FDRRH | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Overhaul Airconditioner | 2028-09-19 | 2028-09-20 | 24 hrs | FY29 | 24 | 90028727 | B1 | 1000289486 | 19.09.2028 | 10000 | CCK-MP-SUPP-WC3112-STRUCT-CABIN-AIRCN | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Seat Operators | 2028-09-19 | 2028-09-19 | 3 hrs | FY29 | 6 | 90004012 | B1 | 1000161837 | 19.09.2028 | 10000 | CCK-MP-SUPP-WC3112-STRUCT-CABIN-SEATS | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Suspension Cylinder LHF | 2028-09-19 | 2028-09-19 | 16 hrs | FY29 | 28 | 90004013 | B2 | 1000079277 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYLF | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Suspension Cylinder LHR | 2028-09-19 | 2028-09-19 | 16 hrs | FY29 | 28 | 90004014 | B2 | 1000079279 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYLR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Suspension Cylinder RHF | 2028-09-19 | 2028-09-19 | 16 hrs | FY29 | 28 | 90004013 | B2 | 1000079278 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYRF | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Suspension Cylinder RHR | 2028-09-19 | 2028-09-19 | 16 hrs | FY29 | 28 | 90004014 | B2 | 1000079280 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYRR | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Transmission | 2028-09-19 | 2028-09-20 | 28 hrs | FY29 | 52 | 90003988 | B2 | 1000079246 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-TRNSYS-TRANS | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Transmission Oil Cooler | 2028-09-19 | 2028-09-19 | 8 hrs | FY29 | 8 | 90003992 | B2 | 1000079281 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-TRNSYS-TROLC | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl TC-Park Brake-Scavenge Pump | 2028-09-19 | 2028-09-19 | 6 hrs | FY29 | 6 | 90003990 | B2 | 1000079261 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-TRNSYS-TRPMP-TCCPP | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Replace Torque Converter | 2028-09-19 | 2028-09-19 | 14 hrs | FY29 | 26 | 90003987 | B2 | 1000079245 | 19.09.2028 | 20000 | CCK-MP-SUPP-WC3112-TRNSYS-TRQUE | 5600 | 52240 | 8166
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Brake Manifold | 2028-09-19 | 2028-09-19 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000291937 | 19.09.2028 | 25000 | CCK-MP-HAUL-DT751 -BRKSYS-BRVLV | 6800 | 86189 | 11291
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Accumulator Hyd Steer Front | 2028-09-19 | 2028-09-19 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000094976 | 19.09.2028 | 25000 | CCK-MP-HAUL-DT764 -STRSYS-STACC-SACCF | 6800 | 75315 | 31508
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Air Con Service & Overhaul | 2028-09-19 | 2028-09-20 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110640 | 19.09.2028 | 12 Monthly | CCK-MP-HAUL-DT771 -STRUCT-CABIN-AIRCN | 6800 | 84423 | 84423
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Replace Operator Cabin Dash Bulbs | 2028-09-19 | 2028-09-19 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158238 | 19.09.2028 | 3000 | CCK-MP-HAUL-DT773 -STRUCT-CABIN | 6800 | 75884 | 75884
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Drive Shaft Transmission | 2028-09-20 | 2028-09-20 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154921 | 20.09.2028 | 18000 | CCK-MP-HAUL-DT055 -FDRSYS-DRSHT | 7400 | 84122 | 2155
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Transmission | 2028-09-20 | 2028-09-21 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000271875 | 20.09.2028 | 18000 | CCK-MP-HAUL-DT058 -TRNSYS-TRANS | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Wheel End LH | 2028-09-20 | 2028-09-21 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000026010 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-FDRSYS-FDRVE-FDRLH | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Wheel End RH | 2028-09-20 | 2028-09-21 | 32.5 hrs | FY29 | 58.5 | 90007352 | B1 | 1000026011 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-FDRSYS-FDRVE-FDRRH | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Overhaul Valve Control Brake | 2028-09-20 | 2028-09-21 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000026018 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BRVLV | 7400 | 87580 | 33228
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Brake Oil Cooler Front | 2028-09-20 | 2028-09-20 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000083363 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BROCO-BROCF | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Pump Hoist & Brake | 2028-09-20 | 2028-09-20 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000026031 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-HYDSYS-HOPMP | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Wheel Group Front LH | 2028-09-20 | 2028-09-21 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157191 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-STRUCT-AXLES-HUBLH | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Wheel Group Front RH | 2028-09-20 | 2028-09-21 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157279 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-STRUCT-AXLES-HUBRH | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Brake System Hoses | 2028-09-20 | 2028-09-22 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000083364 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BRHLF-BRHOS | 7400 | 87580 | 58488
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Brake Cooling System Hoses | 2028-09-20 | 2028-09-21 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000083365 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-BRKSYS-BRHLF-CBRHO | 7400 | 87580 | 58488
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Drive Line Axle LH | 2028-09-20 | 2028-09-20 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124635 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-FDRSYS-DRLAX-AXLLH | 7400 | 87580 | 8253
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Drive Line Axle RH | 2028-09-20 | 2028-09-20 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124636 | 20.09.2028 | 24000 | CCK-MP-HAUL-DT5255-FDRSYS-DRLAX-AXLRH | 7400 | 87580 | 8253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Sepura SCC Microphone | 2028-09-20 | 2028-09-20 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289612 | 20.09.2028 | 12 Monthly | CCK-MP-SUPP-SV221 -COMMUN-RADIO | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Bulk Grease Tank Breather | 2028-09-20 | 2028-09-20 | 1 hr | FY29 | 1 | 90022533 | B1 | 1000236910 | 20.09.2028 | 6 Monthly | CCK-MP-SUPP-SV221 -GRSYST-GRTNK | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Brake Oil Cooler Front | 2028-09-21 | 2028-09-21 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000082489 | 21.09.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BROCO-BROCF | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Brake Oil Cooler Rear | 2028-09-21 | 2028-09-21 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000082488 | 21.09.2028 | 24000 | CCK-MP-HAUL-DT056 -BRKSYS-BROCO-BROCR | 7400 | 84421 | 17941
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Operators Seat | 2028-09-21 | 2028-09-21 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000025071 | 21.09.2028 | 15000 | CCK-MP-HAUL-DT127 -STRUCT-CABIN-SEATS | 7400 | 83059 | 0
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Tyre Sense Battery | 2028-09-21 | 2028-09-21 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000167374 | 21.09.2028 | 24 Monthly | CCK-MP-HAUL-DT5318-MANGMT-TYRSN
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Water Tank Cannon & Spray Sys Insp | 2028-09-21 | 2028-09-21 | 3 hrs | FY29 | 3 | 90036927 | B1 | 1000368892 | 21.09.2028 | 6 Monthly | CCK-MP-SUPP-WC224 -STRUCT-WTANK | 5000 | 70936 | 6229
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Cyl Steering RH | 2028-09-21 | 2028-09-21 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000095134 | 21.09.2028 | 15000 | CCK-MP-HAUL-DT767 -STRSYS-STRCY-STCYR | 6800 | 74312 | 15082
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Motor Lube Axle Rear & Hoses | 2028-09-21 | 2028-09-21 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272005 | 21.09.2028 | 24000 | CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYM01 | 7400 | 86767 | 8224
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Brake Oil Cooler | 2028-09-22 | 2028-09-22 | 6 hrs | FY29 | 6 | 90011549 | B1 | 1000092999 | 22.09.2028 | 15000 | CCK-MP-SUPP-SV221 -BRKSYS-BROCO | 5100 | 64374 | 4253
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Cyl Steering LH | 2028-09-22 | 2028-09-22 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000095027 | 22.09.2028 | 15000 | CCK-MP-HAUL-DT765 -STRSYS-STRCY-STCYL | 6800 | 78429 | 10743
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Suspension LHR | 2028-09-23 | 2028-09-24 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000025981 | 23.09.2028 | 28000 | CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYLR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Drive Shaft Transmission | 2028-09-24 | 2028-09-24 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000155003 | 24.09.2028 | 18000 | CCK-MP-HAUL-DT5202-FDRSYS-DRSHT | 7400 | 84333 | 1995
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Transmisson Calibration | 2028-09-24 | 2028-09-24 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298813 | 24.09.2028 | 4500 | CCK-MP-HAUL-DT5313-TRNSYS-TRANS | 7400 | 44693 | 6773
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Pump Hoist | 2028-09-24 | 2028-09-24 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000094820 | 24.09.2028 | 25000 | CCK-MP-HAUL-DT761 -HYDSYS-HOPMP | 6800 | 78336 | 10529
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Brake Manifold | 2028-09-24 | 2028-09-24 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292175 | 24.09.2028 | 25000 | CCK-MP-HAUL-DT770 -BRKSYS-BRVLV | 6800 | 79305 | 10265
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Overhaul Accumulator Brake Rear | 2028-09-26 | 2028-09-26 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000023851 | 26.09.2028 | 24000 | CCK-MP-HAUL-DT058 -BRKSYS-BACCM-BACCR | 7400 | 87864 | 7715
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Drive Shaft | 2028-09-26 | 2028-09-26 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094559 | 26.09.2028 | 25000 | CCK-MP-HAUL-DT756 -HYDSYS-DRSHT | 6800 | 78754 | 10095
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Radiator Engine Cooling | 2028-09-27 | 2028-09-28 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307696 | 27.09.2028 | 24000 | CCK-MP-HAUL-DT5318-ENGINE-COSYS-RADTR | 7400 | 45240 | 21163
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Auto Lube Pump | 2028-09-27 | 2028-09-27 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285810 | 27.09.2028 | 8000 | CCK-MP-HAUL-DT5318-GRSYST-ALBPP | 7400 | 45240 | 9085
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Overhaul Aux Control Cabinet | 2028-09-28 | 2028-09-29 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292328 | 28.09.2028 | 50000 | CCK-MP-HAUL-DT751 -ELCTLV-AUCAB | 6800 | 86211 | 25788
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Air Con Service & Overhaul | 2028-09-28 | 2028-09-29 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110631 | 28.09.2028 | 12 Monthly | CCK-MP-HAUL-DT762 -STRUCT-CABIN-AIRCN | 6800 | 76486 | 43303
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Spider Trans Driveshaft | 2028-09-28 | 2028-09-28 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154980 | 28.09.2028 | 6000 | CCK-MP-HAUL-DT151 -FDRSYS-DRSHT-UNVSL | 7400 | 84253 | 3168
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Transmisson Calibration | 2028-09-29 | 2028-09-29 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298737 | 29.09.2028 | 4500 | CCK-MP-HAUL-DT159 -TRNSYS-TRANS | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Transmisson Calibration | 2028-09-29 | 2028-09-29 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298739 | 29.09.2028 | 4500 | CCK-MP-HAUL-DT161 -TRNSYS-TRANS | 7400 | 80609 | 12241
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Replace Operator Cabin Dash Bulbs | 2028-09-29 | 2028-09-29 | 2 hrs | FY29 | 2 | 90017265 | B1 | 1000158222 | 29.09.2028 | 3000 | CCK-MP-HAUL-DT757 -STRUCT-CABIN | 6800 | 80700 | 80700
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Transmisson Calibration | 2028-09-30 | 2028-09-30 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298729 | 30.09.2028 | 4500 | CCK-MP-HAUL-DT148 -TRNSYS-TRANS | 7400 | 85451 | 10451
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Steering Linkages | 2028-10-01 | 2028-10-01 | 15 hrs | FY29 | 28 | 90028568 | B1 | 1000317677 | 01.10.2028 | 15000 | CCK-MP-SUPP-PM0001-STRSYS-STLTR | 3400 | 48287 | 6741
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Cyl Suspension RHF | 2028-10-01 | 2028-10-03 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000094938 | 01.10.2028 | 18000 | CCK-MP-HAUL-DT763 -STRUCT-SUSPN-SCYRF | 6800 | 74143 | 3401
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Auto Lube Pump | 2028-10-02 | 2028-10-02 | 2 hrs | FY29 | 2 | 90011565 | B1 | 1000093013 | 02.10.2028 | 9000 | CCK-MP-SUPP-SV221 -GRSYST-ALBPP | 5100 | 64374 | 14753
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Engine Midlife Complete | 2028-10-02 | 2028-10-04 | 49 hrs | FY29 | 76 | 90028571 | B1 | 1000285523 | 02.10.2028 | 12500 | CCK-MP-HAUL-DT765 -ENGINE | 6800 | 78429 | 23008
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Transmisson Calibration | 2028-10-02 | 2028-10-02 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298662 | 02.10.2028 | 4500 | CCK-MP-HAUL-DT054 -TRNSYS-TRANS | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Steering LH | 2028-10-03 | 2028-10-03 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000027146 | 03.10.2028 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STRCY-STCYL | 7400 | 80609 | 13960
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Operators Seat | 2028-10-03 | 2028-10-03 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000027161 | 03.10.2028 | 15000 | CCK-MP-HAUL-DT161 -STRUCT-CABIN-SEATS | 7400 | 80609 | 13960
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Spider Trans Driveshaft | 2028-10-03 | 2028-10-03 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154994 | 03.10.2028 | 6000 | CCK-MP-HAUL-DT161 -FDRSYS-DRSHT-UNVSL | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Spider Trans Driveshaft | 2028-10-03 | 2028-10-03 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000167296 | 03.10.2028 | 6000 | CCK-MP-HAUL-DT5317-FDRSYS-DRSHT-UNVSL | 7400 | 45576 | 8696
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Adjust Engine Valve Set | 2028-10-03 | 2028-10-03 | 12 hrs | FY29 | 24 | 90015766 | B1 | 1000269919 | 03.10.2028 | 4500 | CCK-MP-SUPP-WC221 -ENGINE | 4300 | 56923 | 12761
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Service Airconditioner | 2028-10-03 | 2028-10-04 | 24 hrs | FY29 | 24 | 90018538 | B2 | 1000269921 | 03.10.2028 | 4500 | CCK-MP-SUPP-WC221 -STRUCT-CABIN-AIRCN | 4000 | 56923 | 4347
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Valve Flow Amplifier | 2028-10-03 | 2028-10-03 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000094601 | 03.10.2028 | 25000 | CCK-MP-HAUL-DT757 -STRSYS-STVLV | 6800 | 80700 | 10435
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Steering HMU | 2028-10-03 | 2028-10-03 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094602 | 03.10.2028 | 25000 | CCK-MP-HAUL-DT757 -STRSYS-STHMU | 6800 | 80700 | 10435
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Drive Shaft | 2028-10-03 | 2028-10-03 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094612 | 03.10.2028 | 25000 | CCK-MP-HAUL-DT757 -HYDSYS-DRSHT | 6800 | 80700 | 10435
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Steering LH | 2028-10-03 | 2028-10-03 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000025246 | 03.10.2028 | 15000 | CCK-MP-HAUL-DT130 -STRSYS-STRCY-STCYL | 7400 | 85185 | 14144
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Torque Converter | 2028-10-04 | 2028-10-05 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000024723 | 04.10.2028 | 24000 | CCK-MP-HAUL-DT097 -TRNSYS-TRQUE | 7400 | 83804 | 7897
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Steering LH | 2028-10-04 | 2028-10-04 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000094656 | 04.10.2028 | 15000 | CCK-MP-HAUL-DT758 -STRSYS-STRCY-STCYL | 6800 | 85895 | 15304
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Transmisson Calibration | 2028-10-04 | 2028-10-04 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298736 | 04.10.2028 | 4500 | CCK-MP-HAUL-DT158 -TRNSYS-TRANS | 7400 | 85964 | 11104
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Sepura SCC Microphone | 2028-10-05 | 2028-10-05 | 0.5 hrs | FY29 | 0.5 | 90029002 | B1 | 1000289636 | 05.10.2028 | 12 Monthly | CCK-MP-SUPP-WC225 -COMMUN-RADIO
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 250Hr Initial Valve Set | 2028-10-05 | 2028-10-05 | 12 hrs | FY29 | 24 | 90028724 | B1 | 1000289487 | 05.10.2028 | 250 | CCK-MP-SUPP-WC3112-ENGINE | 5600 | 52240 | 8166
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Wheel Motor Oil LH | 2028-10-05 | 2028-10-05 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338212 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -FDRSYS-WLMTR-WHMLH | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Wheel Motor LH | 2028-10-05 | 2028-10-07 | 45.5 hrs | FY29 | 83.5 | 90011335 | B1 | 1000094645 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -FDRSYS-WLMTR-WHMLH | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Brake Manifold | 2028-10-05 | 2028-10-05 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292151 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -BRKSYS-BRVLV | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Steering Bleed Down Manifold | 2028-10-05 | 2028-10-05 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094653 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -STRSYS-STBDM | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Valve Flow Amplifier | 2028-10-05 | 2028-10-05 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000094654 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -STRSYS-STVLV | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Steering HMU | 2028-10-05 | 2028-10-05 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094655 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -STRSYS-STHMU | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Pump Hoist | 2028-10-05 | 2028-10-05 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000094661 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -HYDSYS-HOPMP | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Drive Shaft | 2028-10-05 | 2028-10-05 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094665 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -HYDSYS-DRSHT | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Suspension RHR | 2028-10-05 | 2028-10-06 | 32 hrs | FY29 | 50 | 90011368 | B1 | 1000094675 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -STRUCT-SUSPN-SCYRR | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Overhaul Aux Control Cabinet | 2028-10-05 | 2028-10-06 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292335 | 05.10.2028 | 50000 | CCK-MP-HAUL-DT758 -ELCTLV-AUCAB | 6800 | 85895 | 34467
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Brake Dual Relay Valves | 2028-10-05 | 2028-10-05 | 8.5 hrs | FY29 | 8.5 | 90021353 | B1 | 1000223478 | 05.10.2028 | 25000 | CCK-MP-HAUL-DT758 -BRKSYS-BRVRL | 6800 | 85895 | 10280
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Transmisson Calibration | 2028-10-06 | 2028-10-06 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298672 | 06.10.2028 | 4500 | CCK-MP-HAUL-DT094 -TRNSYS-TRANS | 7400 | 88788 | 5404
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Transmisson Calibration | 2028-10-06 | 2028-10-06 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298731 | 06.10.2028 | 4500 | CCK-MP-HAUL-DT150 -TRNSYS-TRANS | 7400 | 86608 | 14649
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Tyre Sense Battery | 2028-10-06 | 2028-10-06 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000167134 | 06.10.2028 | 24 Monthly | CCK-MP-HAUL-DT5315-MANGMT-TYRSN
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension LHF | 2028-10-06 | 2028-10-06 | 2 hrs | FY29 | 2 | 90038229 | B1 | 1000382496 | 06.10.2028 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 NDT Cylinder Suspension RHF | 2028-10-06 | 2028-10-06 | 2 hrs | FY29 | 2 | 90038229 | B1 | 1000382497 | 06.10.2028 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRF | 5000 | 75197 | 10710
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Transmisson Calibration | 2028-10-07 | 2028-10-07 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298665 | 07.10.2028 | 4500 | CCK-MP-HAUL-DT057 -TRNSYS-TRANS | 7400 | 91273 | 10672
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Water Tank Cannon & Spray Sys Insp | 2028-10-07 | 2028-10-07 | 3 hrs | FY29 | 3 | 90036927 | B1 | 1000368894 | 07.10.2028 | 6 Monthly | CCK-MP-SUPP-WC225 -STRUCT-WTANK | 5000 | 75244 | 75244
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Brake Accumulator Front | 2028-10-07 | 2028-10-07 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000094648 | 07.10.2028 | 25000 | CCK-MP-HAUL-DT758 -BRKSYS-BRACC-BACCF | 6800 | 85895 | 34467
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Brake Accumulator Rear | 2028-10-07 | 2028-10-07 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000094649 | 07.10.2028 | 25000 | CCK-MP-HAUL-DT758 -BRKSYS-BRACC-BACCR | 6800 | 85895 | 10259
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Transmission | 2028-10-07 | 2028-10-08 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272317 | 07.10.2028 | 18000 | CCK-MP-HAUL-DT126 -TRNSYS-TRANS | 7400 | 88657 | 2432
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Engine Cat C175-16 | 2028-10-07 | 2028-10-10 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000155967 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -ENGINE | 7400 | 82965 | 31710
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Radiator Engine Cooling | 2028-10-07 | 2028-10-08 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307504 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -ENGINE-COSYS-RADTR | 7400 | 82965 | 31127
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Wheel End LH | 2028-10-07 | 2028-10-08 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000025424 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -FDRSYS-FDRVE-FDRLH | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Wheel End RH | 2028-10-07 | 2028-10-08 | 32.5 hrs | FY29 | 58.5 | 90007352 | B1 | 1000025425 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -FDRSYS-FDRVE-FDRRH | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Motor Lube Axle Rear & Hoses | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000271997 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYM01 | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl AOC Fan Motor Rear | 2028-10-07 | 2028-10-07 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000025427 | 07.10.2028 | 12000 | CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYM02 | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Axle Lube Hyd Pump | 2028-10-07 | 2028-10-07 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000154012 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYPUM | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Overhaul Accumulator Brake LHF | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025428 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BACCM-FRLFT | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Overhaul Accumulator Brake RHF | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025429 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BACCM-FRRGT | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Overhaul Accumulator Brake Rear | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025430 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BACCM-BACCR | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Pump Brake Cooling | 2028-10-07 | 2028-10-07 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000025431 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-HYFPP | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Overhaul Valve Control Brake | 2028-10-07 | 2028-10-08 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000025432 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BRVLV | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Brake Oil Cooler Front | 2028-10-07 | 2028-10-07 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000091411 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BROCO-BROCF | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Brake Oil Cooler Rear | 2028-10-07 | 2028-10-07 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000091410 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BROCO-BROCR | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Motor Brake Oil Cooling | 2028-10-07 | 2028-10-07 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000025433 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BROCO-HYMO1 | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Hyd Pump Steering Main & Fan | 2028-10-07 | 2028-10-07 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000025436 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -STRSYS-STPMP | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Steering HMU | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000025437 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -STRSYS-STHMU | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Ovhl Accumulator Steering Front | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025440 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -STRSYS-STACC-SACCF | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Ovhl Accumulator Steering Middle | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025441 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -STRSYS-STACC-SACCM | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Ovhl Accumulator Steering Rear | 2028-10-07 | 2028-10-07 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025442 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -STRSYS-STACC-SACCR | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Pump Hoist & Brake | 2028-10-07 | 2028-10-07 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000025444 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -HYDSYS-HOPMP | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Auto Lube Pump | 2028-10-07 | 2028-10-07 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285780 | 07.10.2028 | 8000 | CCK-MP-HAUL-DT135 -GRSYST-ALBPP | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Rear Axle Linkages | 2028-10-07 | 2028-10-09 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000025453 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -STRUCT-CHASS-AXLIK | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Replace Hoses Hoist System | 2028-10-07 | 2028-10-08 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000091406 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -HYDSYS-HDHLF-HSTHO | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Replace Brake System Hoses | 2028-10-07 | 2028-10-09 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000091412 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BRHLF-BRHOS | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Brake Cooling System Hoses | 2028-10-07 | 2028-10-08 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000091413 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -BRKSYS-BRHLF-CBRHO | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Drive Line Axle LH | 2028-10-07 | 2028-10-07 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124597 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -FDRSYS-DRLAX-AXLLH | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Drive Line Axle RH | 2028-10-07 | 2028-10-07 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124598 | 07.10.2028 | 24000 | CCK-MP-HAUL-DT135 -FDRSYS-DRLAX-AXLRH | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Spider Trans Driveshaft | 2028-10-07 | 2028-10-07 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154956 | 07.10.2028 | 6000 | CCK-MP-HAUL-DT135 -FDRSYS-DRSHT-UNVSL | 7400 | 82965 | 1709
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Hyd Pump Steering & Brake | 2028-10-08 | 2028-10-09 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204435 | 08.10.2028 | 12000 | CCK-MP-HAUL-DT755 -STRSYS-STPMP | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Engine Midlife Complete | 2028-10-08 | 2028-10-10 | 49 hrs | FY29 | 76 | 90028571 | B1 | 1000285531 | 08.10.2028 | 12500 | CCK-MP-HAUL-DT773 -ENGINE | 6800 | 75884 | 22415
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Service Air Conditioner 12M | 2028-10-08 | 2028-10-09 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174109 | 08.10.2028 | 12 Monthly | CCK-MP-HAUL-DT054 -STRUCT-CABIN-AIRCN | 7400 | 88111 | 15675
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Steering Cylinder LH | 2028-10-09 | 2028-10-09 | 10 hrs | FY29 | 18 | 90004005 | B2 | 1000079269 | 09.10.2028 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STRCY-STCYL | 5600 | 52240 | 2873
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Steering Cylinder RH | 2028-10-09 | 2028-10-09 | 10 hrs | FY29 | 18 | 90004005 | B2 | 1000079270 | 09.10.2028 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STRCY-STCYR | 5600 | 52240 | 2873
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Air Con Service & Overhaul | 2028-10-09 | 2028-10-10 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110623 | 09.10.2028 | 12 Monthly | CCK-MP-HAUL-DT754 -STRUCT-CABIN-AIRCN | 6800 | 83256 | 12630
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Service Air Conditioner 12M | 2028-10-10 | 2028-10-11 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174160 | 10.10.2028 | 12 Monthly | CCK-MP-HAUL-DT095 -STRUCT-CABIN-AIRCN | 7400 | 88921 | 21880
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Engine Cat C175-16 | 2028-10-10 | 2028-10-13 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000155961 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -ENGINE | 7400 | 85185 | 49739
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Radiator Engine Cooling | 2028-10-10 | 2028-10-11 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307502 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -ENGINE-COSYS-RADTR | 7400 | 85185 | 60620
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Torque Converter | 2028-10-10 | 2028-10-11 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000025227 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -TRNSYS-TRQUE | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Wheel End RH | 2028-10-10 | 2028-10-11 | 32.5 hrs | FY29 | 58.5 | 90007352 | B1 | 1000025233 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -FDRSYS-FDRVE-FDRRH | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Motor Lube Axle Rear & Hoses | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000271995 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYM01 | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl AOC Fan Motor Rear | 2028-10-10 | 2028-10-10 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000025235 | 10.10.2028 | 12000 | CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYM02 | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Axle Lube Hyd Pump | 2028-10-10 | 2028-10-10 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000083166 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYPUM | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Overhaul Accumulator Brake LHF | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025236 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BACCM-FRLFT | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Overhaul Accumulator Brake RHF | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025237 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BACCM-FRRGT | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Overhaul Accumulator Brake Rear | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025238 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BACCM-BACCR | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Pump Brake Cooling | 2028-10-10 | 2028-10-10 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000025239 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-HYFPP | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Overhaul Valve Control Brake | 2028-10-10 | 2028-10-11 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000025240 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BRVLV | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Hyd Pump Steering Main & Fan | 2028-10-10 | 2028-10-10 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000025244 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -STRSYS-STPMP | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Steering HMU | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000025245 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -STRSYS-STHMU | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Ovhl Accumulator Steering Front | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025248 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -STRSYS-STACC-SACCF | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Ovhl Accumulator Steering Middle | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025249 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -STRSYS-STACC-SACCM | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Ovhl Accumulator Steering Rear | 2028-10-10 | 2028-10-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025250 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -STRSYS-STACC-SACCR | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Pump Hoist & Brake | 2028-10-10 | 2028-10-10 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000025252 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -HYDSYS-HOPMP | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Auto Lube Pump | 2028-10-10 | 2028-10-10 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285639 | 10.10.2028 | 8000 | CCK-MP-HAUL-DT130 -GRSYST-ALBPP | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Wheel Group Front LH | 2028-10-10 | 2028-10-11 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157141 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -STRUCT-AXLES-HUBLH | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Suspension RHF | 2028-10-10 | 2028-10-12 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067531 | 10.10.2028 | 28000 | CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYRF | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Replace Hoses Hoist System | 2028-10-10 | 2028-10-11 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000083168 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -HYDSYS-HDHLF-HSTHO | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Replace Brake System Hoses | 2028-10-10 | 2028-10-12 | 46 hrs | FY29 | 90 | 90010129 | B3 | 1000083174 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BRHLF-BRHOS | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Brake Cooling System Hoses | 2028-10-10 | 2028-10-11 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000083175 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -BRKSYS-BRHLF-CBRHO | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Drive Line Axle LH | 2028-10-10 | 2028-10-10 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124595 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -FDRSYS-DRLAX-AXLLH | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Drive Line Axle RH | 2028-10-10 | 2028-10-10 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124596 | 10.10.2028 | 24000 | CCK-MP-HAUL-DT130 -FDRSYS-DRLAX-AXLRH | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Suspension LHF | 2028-10-11 | 2028-10-13 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067497 | 11.10.2028 | 28000 | CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYLF | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Suspension RHF | 2028-10-11 | 2028-10-13 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067499 | 11.10.2028 | 28000 | CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYRF | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Cyl Suspension LHR | 2028-10-11 | 2028-10-12 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000024764 | 11.10.2028 | 28000 | CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYLR | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Front Wheel Bearings LH | 2028-10-12 | 2028-10-13 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157124 | 12.10.2028 | 16000 | CCK-MP-HAUL-DT094 -STRUCT-AXLES-FWBLH | 7400 | 88788 | 245
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Tyre Sense Battery | 2028-10-12 | 2028-10-12 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000167214 | 12.10.2028 | 24 Monthly | CCK-MP-HAUL-DT5316-MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Hyd Pump Steering & Brake | 2028-10-12 | 2028-10-13 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204438 | 12.10.2028 | 12000 | CCK-MP-HAUL-DT758 -STRSYS-STPMP | 6800 | 85895 | 10280
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl AOC Fan Motor Rear | 2028-10-13 | 2028-10-13 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000167163 | 13.10.2028 | 12000 | CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYM02 | 7400 | 45108 | 19566
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Cyl Suspension LHF | 2028-10-13 | 2028-10-15 | 60 hrs | FY29 | 112 | 90011365 | B1 | 1000094672 | 13.10.2028 | 18000 | CCK-MP-HAUL-DT758 -STRUCT-SUSPN-SCYLF | 6800 | 85895 | 3158
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Brake Manifold | 2028-10-13 | 2028-10-13 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292163 | 13.10.2028 | 25000 | CCK-MP-HAUL-DT764 -BRKSYS-BRVLV | 6800 | 75315 | 9805
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Steering HMU | 2028-10-13 | 2028-10-13 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094973 | 13.10.2028 | 25000 | CCK-MP-HAUL-DT764 -STRSYS-STHMU | 6800 | 75315 | 9805
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Service Air Conditioner 12M | 2028-10-14 | 2028-10-15 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174171 | 14.10.2028 | 12 Monthly | CCK-MP-HAUL-DT138 -STRUCT-CABIN-AIRCN | 7400 | 82982 | 35790
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Service Air Conditioner 12M | 2028-10-14 | 2028-10-15 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174181 | 14.10.2028 | 12 Monthly | CCK-MP-HAUL-DT153 -STRUCT-CABIN-AIRCN | 7400 | 84230 | 34787
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Steering Hoses & Lines | 2028-10-16 | 2028-10-16 | 8 hrs | FY29 | 8 | 90011560 | B1 | 1000093008 | 16.10.2028 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STHLF | 5100 | 64374 | 4253
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Steering Brake Pump Compensator | 2028-10-16 | 2028-10-16 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204755 | 16.10.2028 | 6000 | CCK-MP-HAUL-DT751 -STRSYS-STPMP | 6800 | 86211 | 3654
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Brake Manifold | 2028-10-16 | 2028-10-16 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292155 | 16.10.2028 | 25000 | CCK-MP-HAUL-DT760 -BRKSYS-BRVLV | 6800 | 80390 | 80390
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Accumulator Hyd Steering Rear | 2028-10-16 | 2028-10-16 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000094977 | 16.10.2028 | 25000 | CCK-MP-HAUL-DT764 -STRSYS-STACC-SACCR | 6800 | 75315 | 9742
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Overhaul Aux Control Cabinet | 2028-10-16 | 2028-10-17 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292529 | 16.10.2028 | 50000 | CCK-MP-HAUL-DT771 -ELCTLV-AUCAB | 6800 | 84423 | 30436
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Auto Lube Pump | 2028-10-17 | 2028-10-17 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285808 | 17.10.2028 | 8000 | CCK-MP-HAUL-DT5316-GRSYST-ALBPP | 7400 | 45108 | 45108
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Engine Midlife Complete | 2028-10-17 | 2028-10-19 | 49 hrs | FY29 | 76 | 90028571 | B1 | 1000285520 | 17.10.2028 | 12500 | CCK-MP-HAUL-DT762 -ENGINE | 6800 | 76486 | 22280
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Steering Bleed Down Manifold | 2028-10-18 | 2028-10-18 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094971 | 18.10.2028 | 25000 | CCK-MP-HAUL-DT764 -STRSYS-STBDM | 6800 | 75315 | 36707
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Spider Trans Driveshaft | 2028-10-18 | 2028-10-18 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154974 | 18.10.2028 | 6000 | CCK-MP-HAUL-DT148 -FDRSYS-DRSHT-UNVSL | 7400 | 85451 | 1970
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 250hr Initial Valve Set | 2028-10-19 | 2028-10-19 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000155970 | 19.10.2028 | 250 | CCK-MP-HAUL-DT135 -ENGINE | 7400 | 82965 | 31710
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Spider Trans Driveshaft | 2028-10-20 | 2028-10-20 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000155236 | 20.10.2028 | 6000 | CCK-MP-HAUL-DT054 -FDRSYS-DRSHT-UNVSL | 7400 | 88111 | 1222
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Cyl Steering RH | 2028-10-21 | 2028-10-21 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000023671 | 21.10.2028 | 15000 | CCK-MP-HAUL-DT055 -STRSYS-STRCY-STCYR | 7400 | 84122 | 13600
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Transmisson Calibration | 2028-10-21 | 2028-10-21 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298669 | 21.10.2028 | 4500 | CCK-MP-HAUL-DT088 -TRNSYS-TRANS | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Steering LH | 2028-10-21 | 2028-10-21 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000027080 | 21.10.2028 | 15000 | CCK-MP-HAUL-DT160 -STRSYS-STRCY-STCYL | 7400 | 85085 | 13594
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Steering RH | 2028-10-21 | 2028-10-21 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000027081 | 21.10.2028 | 15000 | CCK-MP-HAUL-DT160 -STRSYS-STRCY-STCYR | 7400 | 85037 | 13594
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Spiders Pump Drive Shaft | 2028-10-22 | 2028-10-22 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000027123 | 22.10.2028 | 18000 | CCK-MP-HAUL-DT161 -ENGINE-PMPDR-DRSHT | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Transmission Oil Cooler | 2028-10-22 | 2028-10-22 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000091578 | 22.10.2028 | 18000 | CCK-MP-HAUL-DT161 -TRNSYS-TROLC | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Differential | 2028-10-22 | 2028-10-23 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000027131 | 22.10.2028 | 18000 | CCK-MP-HAUL-DT161 -FDRSYS-DIFFL | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Replace Trans TCon System Hoses | 2028-10-22 | 2028-10-23 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000091597 | 22.10.2028 | 18000 | CCK-MP-HAUL-DT161 -TRNSYS-TRANS-TRNHO | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Replace Hoses Differential System | 2028-10-22 | 2028-10-22 | 5 hrs | FY29 | 5 | 90010101 | B2 | 1000091598 | 22.10.2028 | 18000 | CCK-MP-HAUL-DT161 -FDRSYS-DIFFL-DIFHO | 7400 | 80609 | 1574
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 250hr Initial Valve Set | 2028-10-22 | 2028-10-22 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000155964 | 22.10.2028 | 250 | CCK-MP-HAUL-DT130 -ENGINE | 7400 | 85185 | 49739
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Pressure Reducing Valve | 2028-10-23 | 2028-10-23 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204784 | 23.10.2028 | 12000 | CCK-MP-HAUL-DT752 -BRKSYS-BRVLV-VVPRV | 6800 | 80681 | 23618
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Air Con Service & Overhaul | 2028-10-23 | 2028-10-24 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110629 | 23.10.2028 | 12 Monthly | CCK-MP-HAUL-DT760 -STRUCT-CABIN-AIRCN | 6800 | 80390 | 23992
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Transmisson Calibration | 2028-10-24 | 2028-10-24 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298670 | 24.10.2028 | 4500 | CCK-MP-HAUL-DT090 -TRNSYS-TRANS | 7400 | 81670 | 5994
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Valve Flow Amplifier | 2028-10-25 | 2028-10-25 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000094548 | 25.10.2028 | 25000 | CCK-MP-HAUL-DT756 -STRSYS-STVLV | 6800 | 78754 | 35933
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Steering HMU | 2028-10-25 | 2028-10-25 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094549 | 25.10.2028 | 25000 | CCK-MP-HAUL-DT756 -STRSYS-STHMU | 6800 | 78754 | 61787
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Auto Lube Pump | 2028-10-25 | 2028-10-25 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000095461 | 25.10.2028 | 8000 | CCK-MP-HAUL-DT773 -GRSYST-ALBPP | 6800 | 75884 | 15103
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Drive Shaft Transmission | 2028-10-26 | 2028-10-26 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154933 | 26.10.2028 | 18000 | CCK-MP-HAUL-DT088 -FDRSYS-DRSHT | 7400 | 89037 | 18338
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Operators Seat | 2028-10-26 | 2028-10-26 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000026633 | 26.10.2028 | 15000 | CCK-MP-HAUL-DT153 -STRUCT-CABIN-SEATS | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Replace Steering System Hoses | 2028-10-26 | 2028-10-28 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083501 | 26.10.2028 | 15000 | CCK-MP-HAUL-DT153 -STRSYS-STHLF-STRHO | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Steering Hyd Oil Cooler | 2028-10-26 | 2028-10-26 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107008 | 26.10.2028 | 15000 | CCK-MP-HAUL-DT153 -STRSYS-STOCO | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Spider Trans Driveshaft | 2028-10-26 | 2028-10-26 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154982 | 26.10.2028 | 6000 | CCK-MP-HAUL-DT153 -FDRSYS-DRSHT-UNVSL | 7400 | 84230 | 2506
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Steering Bell Crank & Links | 2028-10-26 | 2028-10-27 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317642 | 26.10.2028 | 30000 | CCK-MP-HAUL-DT153 -STRSYS-STLTR-STLAC | 7400 | 84230 | 13523
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Spider Trans Driveshaft | 2028-10-26 | 2028-10-26 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000167216 | 26.10.2028 | 6000 | CCK-MP-HAUL-DT5316-FDRSYS-DRSHT-UNVSL | 7400 | 45108 | 1608
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Replace Auto Lube Pump | 2028-10-26 | 2028-10-26 | 4 hrs | FY29 | 4 | 90003064 | B2 | 1000239786 | 26.10.2028 | 6000 | CCK-MP-SUPP-WC008 -GRSYST-ALBPP | 3500 | 51417 | 3913
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Wheel End LH | 2028-10-26 | 2028-10-27 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000025232 | 26.10.2028 | 24000 | CCK-MP-HAUL-DT130 -FDRSYS-FDRVE-FDRLH | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Service Air Conditioner 12M | 2028-10-27 | 2028-10-28 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174117 | 27.10.2028 | 12 Monthly | CCK-MP-HAUL-DT090 -STRUCT-CABIN-AIRCN | 7400 | 81670 | 5994
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Hub & Spindle LH | 2028-10-27 | 2028-10-28 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000095518 | 27.10.2028 | 18000 | CCK-MP-HAUL-DT774 -STRUCT-AXLES-HUBLH | 6800 | 81047 | 3051
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Engine Midlife Complete | 2028-10-28 | 2028-10-29 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000167223 | 28.10.2028 | 12000 | CCK-MP-HAUL-DT5316-ENGINE | 7400 | 45108 | 19566
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Radiator Fan Hoses | 2028-10-28 | 2028-10-28 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307693 | 28.10.2028 | 12000 | CCK-MP-HAUL-DT5316-ENGINE-COSYS-RADTR | 7400 | 45108 | 19566
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Motor Lube Axle Hoses | 2028-10-28 | 2028-10-28 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272190 | 28.10.2028 | 12000 | CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYM01 | 7400 | 45108 | 19566
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Transmission | 2028-10-29 | 2028-10-30 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272327 | 29.10.2028 | 18000 | CCK-MP-HAUL-DT137 -TRNSYS-TRANS | 7400 | 84196 | 1006
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Cylinder Steering RH | 2028-10-29 | 2028-10-29 | 12 hrs | FY29 | 20 | 90002385 | B3 | 1000272729 | 29.10.2028 | 15000 | CCK-MP-SUPP-PM0001-STRSYS-STRCY-STCYR | 3400 | 48287 | 6741
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Auto Lube Pump | 2028-10-29 | 2028-10-29 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000095143 | 29.10.2028 | 8000 | CCK-MP-HAUL-DT767 -GRSYST-ALBPP | 6800 | 74312 | 7873
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Steering LH | 2028-10-30 | 2028-10-30 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000023796 | 30.10.2028 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STRCY-STCYL | 7400 | 91273 | 13167
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Steering RH | 2028-10-30 | 2028-10-30 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000023797 | 30.10.2028 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STRCY-STCYR | 7400 | 91273 | 13167
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Transmission Calibration | 2028-10-30 | 2028-10-30 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298905 | 30.10.2028 | 4500 | CCK-MP-SUPP-PM0001-TRNSYS-TRANS | 3400 | 48287 | 4072
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Steering LH | 2028-10-31 | 2028-10-31 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000025631 | 31.10.2028 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STRCY-STCYL | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Cyl Steering RH | 2028-10-31 | 2028-10-31 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025632 | 31.10.2028 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STRCY-STCYR | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Replace Steering System Hoses | 2028-10-31 | 2028-11-02 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083254 | 31.10.2028 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STHLF-STRHO | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Steering Hyd Oil Cooler | 2028-10-31 | 2028-10-31 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106996 | 31.10.2028 | 15000 | CCK-MP-HAUL-DT138 -STRSYS-STOCO | 7400 | 82982 | 13427
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Torque Converter | 2028-10-31 | 2028-11-01 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000026599 | 31.10.2028 | 24000 | CCK-MP-HAUL-DT153 -TRNSYS-TRQUE | 7400 | 84230 | 7415
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Auto Lube Pump | 2028-10-31 | 2028-10-31 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285793 | 31.10.2028 | 8000 | CCK-MP-HAUL-DT153 -GRSYST-ALBPP | 7400 | 84230 | 7415
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Replace Steering System Hoses | 2028-10-31 | 2028-11-02 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000111975 | 31.10.2028 | 15000 | CCK-MP-HAUL-DT5202-STRSYS-STHLF-STRHO | 7400 | 84333 | 13327
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Steering LH | 2028-10-31 | 2028-10-31 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000111936 | 31.10.2028 | 15000 | CCK-MP-HAUL-DT5202-STRSYS-STRCY-STCYL | 7400 | 84333 | 975
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Cyl Steering RH | 2028-10-31 | 2028-10-31 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000111937 | 31.10.2028 | 15000 | CCK-MP-HAUL-DT5202-STRSYS-STRCY-STCYR | 7400 | 84333 | 975
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Radiator Engine Cooling | 2028-11-01 | 2028-11-02 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307548 | 01.11.2028 | 24000 | CCK-MP-HAUL-DT161 -ENGINE-COSYS-RADTR | 7400 | 80609 | 68404
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Steering HMU | 2028-11-01 | 2028-11-01 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000027145 | 01.11.2028 | 24000 | CCK-MP-HAUL-DT161 -STRSYS-STHMU | 7400 | 80609 | 7381
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Engine Midlife Complete | 2028-11-01 | 2028-11-02 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000166983 | 01.11.2028 | 12000 | CCK-MP-HAUL-DT5313-ENGINE | 7400 | 44693 | 19408
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Radiator Fan Hoses | 2028-11-01 | 2028-11-01 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307687 | 01.11.2028 | 12000 | CCK-MP-HAUL-DT5313-ENGINE-COSYS-RADTR | 7400 | 44693 | 19408
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Motor Lube Axle Hoses | 2028-11-01 | 2028-11-01 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272184 | 01.11.2028 | 12000 | CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYM01 | 7400 | 44693 | 19408
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Repl Sepura SCC Microphone | 2028-11-01 | 2028-11-01 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289621 | 01.11.2028 | 12 Monthly | CCK-MP-SUPP-WC221 -COMMUN-RADIO
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Engine Cat 3516B | 2028-11-01 | 2028-11-07 | 156 hrs | FY29 | 306 | 90017288 | B1 | 1000290432 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -ENGINE | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Radiator | 2028-11-01 | 2028-11-01 | 12 hrs | FY29 | 24 | 90000905 | B2 | 1000033351 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -ENGINE-COSYS-RADTR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Pump Drive | 2028-11-01 | 2028-11-01 | 8 hrs | FY29 | 14 | 90000909 | B2 | 1000033352 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -ENGINE-PMPDR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Pump Drive Driveshaft Unis | 2028-11-01 | 2028-11-01 | 2 hrs | FY29 | 2 | 90000911 | B2 | 1000033353 | 01.11.2028 | 11000 | CCK-MP-SUPP-WC225 -ENGINE-PMPDR-DRSHT | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Torque Converter | 2028-11-01 | 2028-11-01 | 8 hrs | FY29 | 16 | 90000907 | B2 | 1000033354 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -TRNSYS-TRQUE | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Spiders Trans Drive Shaft | 2028-11-01 | 2028-11-01 | 4 hrs | FY29 | 4 | 90000910 | B2 | 1000033359 | 01.11.2028 | 11000 | CCK-MP-SUPP-WC225 -FDRSYS-DRSHT | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Differential | 2028-11-01 | 2028-11-01 | 6 hrs | FY29 | 12 | 90000908 | B2 | 1000033360 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -FDRSYS-DIFFL | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Axle Oil Cooler Fan Motor | 2028-11-01 | 2028-11-01 | 3 hrs | FY29 | 3 | 90002901 | B2 | 1000040601 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -FDRSYS-AXLEC-MTFAN | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Ovhl Brake Accumulator | 2028-11-01 | 2028-11-01 | 2 hrs | FY29 | 2 | 90002905 | B2 | 1000040603 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BACCM | 5500 | 10710 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Cooling Pump | 2028-11-01 | 2028-11-01 | 3 hrs | FY29 | 3 | 90002906 | B2 | 1000040604 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-HYFPP | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Treadle Valve | 2028-11-01 | 2028-11-01 | 4 hrs | FY29 | 4 | 90002907 | B2 | 1000040605 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRVTR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Oil Cooler Front | 2028-11-01 | 2028-11-01 | 4 hrs | FY29 | 4 | 90000915 | B2 | 1000033364 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BROCO-BROCF | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Rotochamber Front | 2028-11-01 | 2028-11-01 | 3 hrs | FY29 | 3 | 90002908 | B2 | 1000040606 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRCYL-ROTFR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Rotochamber LHR | 2028-11-01 | 2028-11-01 | 3 hrs | FY29 | 3 | 90002909 | B2 | 1000040607 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRCYL-ROTLR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Rotochamber RHR | 2028-11-01 | 2028-11-01 | 3 hrs | FY29 | 3 | 90002909 | B2 | 1000040608 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRCYL-ROTRR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Slack Adjuster Rear | 2028-11-01 | 2028-11-01 | 2 hrs | FY29 | 2 | 90002911 | B2 | 1000040610 | 01.11.2028 | 11000 | CCK-MP-SUPP-WC225 -BRKSYS-SLACK-SLACR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Ovhl Steering Accumulator Front | 2028-11-01 | 2028-11-01 | 6 hrs | FY29 | 6 | 90000919 | B2 | 1000040599 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRSYS-STACC-SACCF | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Ovhl Steering Accumulator Rear | 2028-11-01 | 2028-11-01 | 6 hrs | FY29 | 6 | 90000919 | B2 | 1000040600 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRSYS-STACC-SACCR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Hoist Pump | 2028-11-01 | 2028-11-01 | 6 hrs | FY29 | 6 | 90000895 | B2 | 1000033372 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -HYDSYS-HOPMP | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Overhaul Valve Hoist | 2028-11-01 | 2028-11-02 | 18 hrs | FY29 | 36 | 90018589 | B1 | 1000280878 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -HYDSYS-HOVLV | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Air Drier | 2028-11-01 | 2028-11-01 | 2 hrs | FY29 | 2 | 90002916 | B2 | 1000040612 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -PNEUMC-AIRDR | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Airconditioner Overhaul | 2028-11-01 | 2028-11-03 | 48 hrs | FY29 | 48 | 90017507 | B1 | 1000290435 | 01.11.2028 | 11000 | CCK-MP-SUPP-WC225 -STRUCT-CABIN-AIRCN | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Seat Assy | 2028-11-01 | 2028-11-01 | 3 hrs | FY29 | 6 | 90003494 | B2 | 1000039956 | 01.11.2028 | 11000 | CCK-MP-SUPP-WC225 -STRUCT-CABIN-SEATS | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Seat Belt | 2028-11-01 | 2028-11-01 | 1 hr | FY29 | 1 | 90002921 | B2 | 1000040615 | 01.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-CABIN-SBELT | 5000 | 75244 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Torque Converter System Hoses | 2028-11-01 | 2028-11-01 | 8 hrs | FY29 | 8 | 90010494 | B2 | 1000238427 | 01.11.2028 | 11000 | CCK-MP-SUPP-WC225 -TRNSYS-TRQUE-TRQHO | 5000 | 22459 | 10710
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Steering LH | 2028-11-03 | 2028-11-03 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000023985 | 03.11.2028 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STRCY-STCYL | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Cyl Steering RH | 2028-11-03 | 2028-11-03 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000023986 | 03.11.2028 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STRCY-STCYR | 7400 | 84375 | 558
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Replace Steering System Hoses | 2028-11-03 | 2028-11-05 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000082893 | 03.11.2028 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STHLF-STRHO | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Steering Hyd Oil Cooler | 2028-11-03 | 2028-11-03 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106979 | 03.11.2028 | 15000 | CCK-MP-HAUL-DT082 -STRSYS-STOCO | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Transmisson Calibration | 2028-11-04 | 2028-11-04 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298740 | 04.11.2028 | 4500 | CCK-MP-HAUL-DT221 -TRNSYS-TRANS | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Replace Steering System Hoses | 2028-11-04 | 2028-11-06 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000082494 | 04.11.2028 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STHLF-STRHO | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Steering Hyd Oil Cooler | 2028-11-04 | 2028-11-04 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106977 | 04.11.2028 | 15000 | CCK-MP-HAUL-DT056 -STRSYS-STOCO | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Steering Bell Crank & Links | 2028-11-04 | 2028-11-05 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317584 | 04.11.2028 | 30000 | CCK-MP-HAUL-DT056 -STRSYS-STLTR-STLAC | 7400 | 84421 | 13282
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Pump Hoist & Brake | 2028-11-04 | 2028-11-04 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000025573 | 04.11.2028 | 24000 | CCK-MP-HAUL-DT137 -HYDSYS-HOPMP | 7400 | 84196 | 10904
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Hub & Spindle RH | 2028-11-04 | 2028-11-05 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000095519 | 04.11.2028 | 18000 | CCK-MP-HAUL-DT774 -STRUCT-AXLES-HUBRH | 6800 | 81047 | 2655
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Cyl Suspension RHF | 2028-11-04 | 2028-11-06 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000095521 | 04.11.2028 | 18000 | CCK-MP-HAUL-DT774 -STRUCT-SUSPN-SCYRF | 6800 | 81047 | 20532
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Hoist LH | 2028-11-04 | 2028-11-04 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128573 | 04.11.2028 | 28000 | CCK-MP-HAUL-DT136 -HYDSYS-HOCYL-HCYLL | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Hoist RH | 2028-11-04 | 2028-11-04 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128574 | 04.11.2028 | 28000 | CCK-MP-HAUL-DT136 -HYDSYS-HOCYL-HCYLR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Suspension LHF | 2028-11-04 | 2028-11-06 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067545 | 04.11.2028 | 28000 | CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYLF | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Operators Seat | 2028-11-05 | 2028-11-05 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000025581 | 05.11.2028 | 15000 | CCK-MP-HAUL-DT137 -STRUCT-CABIN-SEATS | 7400 | 84196 | 18714
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Operators Seat | 2028-11-05 | 2028-11-05 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000166941 | 05.11.2028 | 15000 | CCK-MP-HAUL-DT5313-STRUCT-CABIN-SEATS | 7400 | 44693 | 13322
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Steering System Hoses | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 8 | 90010860 | B1 | 1000114720 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRSYS-STHLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Hyd Oil Tank | 2028-11-05 | 2028-11-05 | 6 hrs | FY29 | 6 | 90003498 | B2 | 1000040616 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -HYDSYS-HDTNK | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Operators cab Refurb | 2028-11-05 | 2028-11-06 | 24 hrs | FY29 | 24 | 90003501 | B2 | 1000040618 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-CABIN | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Hub & Spindle RH | 2028-11-05 | 2028-11-05 | 10 hrs | FY29 | 20 | 90020388 | B1 | 1000033374 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-AXLES-HUBRH | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Suspension Cylinder LHF | 2028-11-05 | 2028-11-05 | 14 hrs | FY29 | 26 | 90000894 | B2 | 1000067706 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Suspension Cylinder RHF | 2028-11-05 | 2028-11-05 | 14 hrs | FY29 | 26 | 90000894 | B2 | 1000067708 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Suspension Cylinder LHR | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 14 | 90002924 | B2 | 1000039711 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYLR | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Suspension Cylinder RHR | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 14 | 90002924 | B2 | 1000039724 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRUCT-SUSPN-SCYRR | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Steering Oil Tank | 2028-11-05 | 2028-11-05 | 6 hrs | FY29 | 6 | 90003499 | B2 | 1000040617 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -STRSYS-STTNK | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Repl Towing Pump | 2028-11-05 | 2028-11-05 | 2 hrs | FY29 | 2 | 90000899 | B2 | 1000040598 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -HYDSYS-TOWPP | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake System Air Lines | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 8 | 90010859 | B1 | 1000114712 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRHLF-BRAIR | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Front Brake System Hoses | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 8 | 90010858 | B1 | 1000114714 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRHLF-BRHOF | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Rear Brake System Hoses | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 8 | 90010856 | B1 | 1000114716 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRHLF-BRHOR | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Hoist System Hoses | 2028-11-05 | 2028-11-05 | 4 hrs | FY29 | 8 | 90010855 | B1 | 1000114718 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -HYDSYS-HDHLF-HSTHO | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Differential System Hoses | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 8 | 90013803 | B1 | 1000114751 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -FDRSYS-DIFFL-DIFHO | 5000 | 75197 | 10710
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Replace Brake Cooling Hoses | 2028-11-05 | 2028-11-05 | 8 hrs | FY29 | 8 | 90010865 | B1 | 1000114776 | 05.11.2028 | 22000 | CCK-MP-SUPP-WC225 -BRKSYS-BRHLF-BRHOC | 5000 | 75197 | 10710
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Engine Cat C175-16 | 2028-11-05 | 2028-11-08 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000155991 | 05.11.2028 | 24000 | CCK-MP-HAUL-DT140 -ENGINE | 7400 | 86695 | 31795
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Transmisson Calibration | 2028-11-05 | 2028-11-05 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298675 | 05.11.2028 | 4500 | CCK-MP-HAUL-DT099 -TRNSYS-TRANS | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Rear Axle Linkages | 2028-11-06 | 2028-11-08 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000026436 | 06.11.2028 | 24000 | CCK-MP-HAUL-DT150 -STRUCT-CHASS-AXLIK | 7400 | 86608 | 872
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Valve Retard & Brake Treadle | 2028-11-06 | 2028-11-06 | 5.5 hrs | FY29 | 5.5 | 90011345 | B1 | 1000094598 | 06.11.2028 | 25000 | CCK-MP-HAUL-DT757 -BRKSYS-BRVTR | 6800 | 80700 | 9078
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Steering Bleed Down Manifold | 2028-11-06 | 2028-11-06 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094600 | 06.11.2028 | 25000 | CCK-MP-HAUL-DT757 -STRSYS-STBDM | 6800 | 80700 | 9078
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Torque Converter | 2028-11-07 | 2028-11-08 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000025038 | 07.11.2028 | 24000 | CCK-MP-HAUL-DT127 -TRNSYS-TRQUE | 7400 | 83059 | 7188
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Service Air Conditioner 12M | 2028-11-07 | 2028-11-08 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174193 | 07.11.2028 | 12 Monthly | CCK-MP-HAUL-DT5314-STRUCT-CABIN-AIRCN | 7400 | 45898 | 45898
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Replace Cylinder Steering LH | 2028-11-07 | 2028-11-07 | 12 hrs | FY29 | 20 | 90002385 | B3 | 1000272728 | 07.11.2028 | 15000 | CCK-MP-SUPP-PM0001-STRSYS-STRCY-STCYL | 3400 | 48287 | 6741
777G SV | Onsite PM | Haul | Fortescue | SV221 | 24 Monthly HP Grease Lines Replace | 2028-11-07 | 2028-11-07 | 3 hrs | FY29 | 3 | 90016826 | B1 | 1000152003 | 07.11.2028 | 24 Monthly | CCK-MP-SUPP-SV221 -MODULE | 5100 | 64374 | 64374
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Hub & Spindle RH | 2028-11-07 | 2028-11-07 | 10 hrs | FY29 | 20 | 90020388 | B1 | 1000033302 | 07.11.2028 | 22000 | CCK-MP-SUPP-WC224 -STRUCT-AXLES-HUBRH | 5000 | 71056 | 10808
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Spiders Pump Drive Shaft | 2028-11-07 | 2028-11-07 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000024908 | 07.11.2028 | 18000 | CCK-MP-HAUL-DT100 -ENGINE-PMPDR-DRSHT | 7400 | 87135 | 863
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Transmission Oil Cooler | 2028-11-07 | 2028-11-07 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000083069 | 07.11.2028 | 18000 | CCK-MP-HAUL-DT100 -TRNSYS-TROLC | 7400 | 87135 | 19314
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Differential | 2028-11-07 | 2028-11-08 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000024916 | 07.11.2028 | 18000 | CCK-MP-HAUL-DT100 -FDRSYS-DIFFL | 7400 | 87135 | 914
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Replace Trans TCon System Hoses | 2028-11-07 | 2028-11-08 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090097 | 07.11.2028 | 18000 | CCK-MP-HAUL-DT100 -TRNSYS-TRANS-TRNHO | 7400 | 87135 | 19314
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Replace Hoses Differential System | 2028-11-07 | 2028-11-07 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090098 | 07.11.2028 | 18000 | CCK-MP-HAUL-DT100 -FDRSYS-DIFFL-DIFHO | 7400 | 87135 | 19314
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Front Wheel Bearings RH | 2028-11-08 | 2028-11-09 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157214 | 08.11.2028 | 16000 | CCK-MP-HAUL-DT095 -STRUCT-AXLES-FWBRH | 7400 | 88921 | 10426
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Ovhl Axle A Frame | 2028-11-08 | 2028-11-09 | 36 hrs | FY29 | 60 | 90002922 | B2 | 1000074508 | 08.11.2028 | 15000 | CCK-MP-SUPP-WC225 -STRUCT-CHASS-AFRME | 5000 | 75244 | 18684
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Grid Box Blower Motor LH | 2028-11-08 | 2028-11-08 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000094482 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -ELCTHV-HVGBM-GBMLH | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Grid Box Blower Motor RH | 2028-11-08 | 2028-11-08 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000094483 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -ELCTHV-HVGBM-GBMRH | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Wheel Motor LH | 2028-11-08 | 2028-11-10 | 45.5 hrs | FY29 | 83.5 | 90011335 | B1 | 1000094486 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -FDRSYS-WLMTR-WHMLH | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Wheel Motor Oil LH | 2028-11-08 | 2028-11-08 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338206 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -FDRSYS-WLMTR-WHMLH | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Wheel Motor RH | 2028-11-08 | 2028-11-10 | 45.5 hrs | FY29 | 83.5 | 90011336 | B1 | 1000094487 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -FDRSYS-WLMTR-WHMRH | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Wheel Motor Oil RH | 2028-11-08 | 2028-11-08 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338207 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -FDRSYS-WLMTR-WHMRH | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Brake Manifold | 2028-11-08 | 2028-11-08 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292145 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -BRKSYS-BRVLV | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Brake Accumulator Front | 2028-11-08 | 2028-11-08 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000094489 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -BRKSYS-BRACC-BACCF | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Brake Accumulator Rear | 2028-11-08 | 2028-11-08 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000094490 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -BRKSYS-BRACC-BACCR | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Valve Retard & Brake Treadle | 2028-11-08 | 2028-11-08 | 5.5 hrs | FY29 | 5.5 | 90011345 | B1 | 1000094492 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -BRKSYS-BRVTR | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Brake Cabinet Hoses | 2028-11-08 | 2028-11-09 | 32.5 hrs | FY29 | 62.5 | 90015041 | B1 | 1000126212 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -BRKSYS-BRHLF | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Brake Cooling Hoses | 2028-11-08 | 2028-11-08 | 8.5 hrs | FY29 | 14.5 | 90011344 | B1 | 1000223875 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -BRKSYS-BRHLF | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Steering Bleed Down Manifold | 2028-11-08 | 2028-11-08 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094494 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -STRSYS-STBDM | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Valve Flow Amplifier | 2028-11-08 | 2028-11-08 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000094495 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -STRSYS-STVLV | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Steering HMU | 2028-11-08 | 2028-11-08 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094496 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -STRSYS-STHMU | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Accumulator Hyd Steer Front | 2028-11-08 | 2028-11-08 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000094499 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -STRSYS-STACC-SACCF | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Accumulator Hyd Steering Rear | 2028-11-08 | 2028-11-08 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000094500 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -STRSYS-STACC-SACCR | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Drive Shaft | 2028-11-08 | 2028-11-08 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094506 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -HYDSYS-DRSHT | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Replace Pump Module Hosing | 2028-11-08 | 2028-11-08 | 15 hrs | FY29 | 27 | 90021389 | B1 | 1000223899 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -HYDSYS-HDHLF | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Cyl Suspension LHR | 2028-11-08 | 2028-11-09 | 32 hrs | FY29 | 50 | 90011367 | B1 | 1000094515 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -STRUCT-SUSPN-SCYLR | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Cyl Suspension RHR | 2028-11-08 | 2028-11-09 | 32 hrs | FY29 | 50 | 90011368 | B1 | 1000094516 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -STRUCT-SUSPN-SCYRR | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Overhaul Aux Control Cabinet | 2028-11-08 | 2028-11-09 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292332 | 08.11.2028 | 50000 | CCK-MP-HAUL-DT755 -ELCTLV-AUCAB | 6800 | 84587 | 28383
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Brake Dual Relay Valves | 2028-11-08 | 2028-11-08 | 8.5 hrs | FY29 | 8.5 | 90021353 | B1 | 1000223475 | 08.11.2028 | 25000 | CCK-MP-HAUL-DT755 -BRKSYS-BRVRL | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Pressure Reducing Valve | 2028-11-09 | 2028-11-09 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204841 | 09.11.2028 | 12000 | CCK-MP-HAUL-DT769 -BRKSYS-BRVLV-VVPRV | 6800 | 80508 | 12222
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Engine Cat C175-16 | 2028-11-09 | 2028-11-12 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000156069 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -ENGINE | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Radiator Engine Cooling | 2028-11-09 | 2028-11-10 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307546 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -ENGINE-COSYS-RADTR | 7400 | 85085 | 32389
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Torque Converter | 2028-11-09 | 2028-11-10 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000027061 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -TRNSYS-TRQUE | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Motor Lube Axle Rear & Hoses | 2028-11-09 | 2028-11-09 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272033 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYM01 | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl AOC Fan Motor Rear | 2028-11-09 | 2028-11-09 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000027069 | 09.11.2028 | 12000 | CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYM02 | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Pump Brake Cooling | 2028-11-09 | 2028-11-09 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000027073 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-HYFPP | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Overhaul Valve Control Brake | 2028-11-09 | 2028-11-10 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000027074 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BRVLV | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Motor Brake Oil Cooling | 2028-11-09 | 2028-11-09 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000027075 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BROCO-HYMO1 | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Hyd Pump Steering Main & Fan | 2028-11-09 | 2028-11-09 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000027078 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -STRSYS-STPMP | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Steering HMU | 2028-11-09 | 2028-11-09 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000027079 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -STRSYS-STHMU | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Pump Hoist & Brake | 2028-11-09 | 2028-11-09 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000027087 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -HYDSYS-HOPMP | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Auto Lube Pump | 2028-11-09 | 2028-11-09 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285798 | 09.11.2028 | 8000 | CCK-MP-HAUL-DT160 -GRSYST-ALBPP | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Rear Axle Linkages | 2028-11-09 | 2028-11-11 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000027096 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -STRUCT-CHASS-AXLIK | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Wheel Group Front LH | 2028-11-09 | 2028-11-10 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157179 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -STRUCT-AXLES-HUBLH | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Wheel Group Front RH | 2028-11-09 | 2028-11-10 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157267 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -STRUCT-AXLES-HUBRH | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Suspension RHF | 2028-11-09 | 2028-11-11 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067643 | 09.11.2028 | 28000 | CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYRF | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Replace Hoses Hoist System | 2028-11-09 | 2028-11-10 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000091560 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -HYDSYS-HDHLF-HSTHO | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Replace Brake System Hoses | 2028-11-09 | 2028-11-11 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000091566 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BRHLF-BRHOS | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Brake Cooling System Hoses | 2028-11-09 | 2028-11-10 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000091567 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BRHLF-CBRHO | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Drive Line Axle LH | 2028-11-09 | 2028-11-09 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124629 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -FDRSYS-DRLAX-AXLLH | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Drive Line Axle RH | 2028-11-09 | 2028-11-09 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124630 | 09.11.2028 | 24000 | CCK-MP-HAUL-DT160 -FDRSYS-DRLAX-AXLRH | 7400 | 85085 | 7211
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Repl Sepura SCC Microphone | 2028-11-10 | 2028-11-10 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289619 | 10.11.2028 | 12 Monthly | CCK-MP-SUPP-WC009 -COMMUN-RADIO
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Wheel Group Front LH | 2028-11-10 | 2028-11-11 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157151 | 10.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRUCT-AXLES-HUBLH | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Spider Trans Driveshaft | 2028-11-10 | 2028-11-10 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154950 | 10.11.2028 | 6000 | CCK-MP-HAUL-DT126 -FDRSYS-DRSHT-UNVSL | 7400 | 88657 | 132
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Hub & Spindle RH | 2028-11-12 | 2028-11-13 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000095254 | 12.11.2028 | 18000 | CCK-MP-HAUL-DT769 -STRUCT-AXLES-HUBRH | 6800 | 80508 | 2589
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Cyl Suspension RHF | 2028-11-12 | 2028-11-14 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000095256 | 12.11.2028 | 18000 | CCK-MP-HAUL-DT769 -STRUCT-SUSPN-SCYRF | 6800 | 80508 | 2589
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl AOC Fan Motor Rear | 2028-11-15 | 2028-11-15 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000023659 | 15.11.2028 | 12000 | CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYM02 | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Spider Trans Driveshaft | 2028-11-15 | 2028-11-15 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154968 | 15.11.2028 | 6000 | CCK-MP-HAUL-DT143 -FDRSYS-DRSHT-UNVSL | 7400 | 88225 | 7566
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Steering HMU | 2028-11-16 | 2028-11-16 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000026419 | 16.11.2028 | 24000 | CCK-MP-HAUL-DT150 -STRSYS-STHMU | 7400 | 86608 | 33066
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Wheel End LH | 2028-11-17 | 2028-11-18 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000023845 | 17.11.2028 | 24000 | CCK-MP-HAUL-DT058 -FDRSYS-FDRVE-FDRLH | 7400 | 87864 | 6793
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Accumulator Hyd Steering Rear | 2028-11-17 | 2028-11-17 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000095030 | 17.11.2028 | 25000 | CCK-MP-HAUL-DT765 -STRSYS-STACC-SACCR | 6800 | 78429 | 30957
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 250hr Initial Valve Set | 2028-11-17 | 2028-11-17 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000155994 | 17.11.2028 | 250 | CCK-MP-HAUL-DT140 -ENGINE | 7400 | 86695 | 31795
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Front Wheel Bearings RH | 2028-11-17 | 2028-11-18 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157222 | 17.11.2028 | 16000 | CCK-MP-HAUL-DT100 -STRUCT-AXLES-FWBRH | 7400 | 87135 | 12861
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Electrical Harness | 2028-11-18 | 2028-11-21 | 72 hrs | FY29 | 144 | 90021026 | B1 | 1000221290 | 18.11.2028 | 50000 | CCK-MP-HAUL-DT758 -ELCTLV-HARNS | 6800 | 85895 | 34467
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Overhaul Valve Control Brake | 2028-11-19 | 2028-11-20 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000023664 | 19.11.2028 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BRVLV | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Replace Hoses Hoist System | 2028-11-19 | 2028-11-20 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000082864 | 19.11.2028 | 24000 | CCK-MP-HAUL-DT055 -HYDSYS-HDHLF-HSTHO | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Replace Brake System Hoses | 2028-11-19 | 2028-11-21 | 46 hrs | FY29 | 90 | 90010129 | B2 | 1000082870 | 19.11.2028 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BRHLF-BRHOS | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Brake Cooling System Hoses | 2028-11-19 | 2028-11-20 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000082871 | 19.11.2028 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BRHLF-CBRHO | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Torque Converter | 2028-11-19 | 2028-11-20 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000026929 | 19.11.2028 | 24000 | CCK-MP-HAUL-DT158 -TRNSYS-TRQUE | 7400 | 85964 | 7168
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Service Air Conditioner 12M | 2028-11-20 | 2028-11-21 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174182 | 20.11.2028 | 12 Monthly | CCK-MP-HAUL-DT155 -STRUCT-CABIN-AIRCN | 7400 | 81407 | 5297
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 250hr Initial Valve Set | 2028-11-20 | 2028-11-20 | 6 hrs | FY29 | 12 | 90017289 | B1 | 1000290439 | 20.11.2028 | 250 | CCK-MP-SUPP-WC225 -ENGINE | 5000 | 75244 | 10710
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Valve Retard & Brake Treadle | 2028-11-20 | 2028-11-20 | 5.5 hrs | FY29 | 5.5 | 90011345 | B1 | 1000095499 | 20.11.2028 | 25000 | CCK-MP-HAUL-DT774 -BRKSYS-BRVTR | 6800 | 81047 | 9510
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Steering HMU | 2028-11-20 | 2028-11-20 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095503 | 20.11.2028 | 25000 | CCK-MP-HAUL-DT774 -STRSYS-STHMU | 6800 | 81047 | 9510
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Pump Hoist | 2028-11-20 | 2028-11-20 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000095509 | 20.11.2028 | 25000 | CCK-MP-HAUL-DT774 -HYDSYS-HOPMP | 6800 | 81047 | 34578
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Drive Shaft | 2028-11-20 | 2028-11-20 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000095513 | 20.11.2028 | 25000 | CCK-MP-HAUL-DT774 -HYDSYS-DRSHT | 6800 | 81047 | 35545
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Radiator Engine Cooling | 2028-11-21 | 2028-11-22 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307466 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -ENGINE-COSYS-RADTR | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Torque Converter | 2028-11-21 | 2028-11-22 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000023651 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -TRNSYS-TRQUE | 7400 | 84122 | 7001
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Wheel End LH | 2028-11-21 | 2028-11-22 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000023656 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -FDRSYS-FDRVE-FDRLH | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Wheel End RH | 2028-11-21 | 2028-11-22 | 32.5 hrs | FY29 | 58.5 | 90007352 | B1 | 1000023657 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -FDRSYS-FDRVE-FDRRH | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Pump Brake Cooling | 2028-11-21 | 2028-11-21 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000023663 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-HYFPP | 7400 | 84122 | 7001
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Hyd Pump Steering Main & Fan | 2028-11-21 | 2028-11-21 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000023668 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -STRSYS-STPMP | 7400 | 84122 | 7001
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Pump Hoist & Brake | 2028-11-21 | 2028-11-21 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000023676 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -HYDSYS-HOPMP | 7400 | 84122 | 7001
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Wheel Group Front LH | 2028-11-21 | 2028-11-22 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157107 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -STRUCT-AXLES-HUBLH | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Drive Line Axle LH | 2028-11-21 | 2028-11-21 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124269 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -FDRSYS-DRLAX-AXLLH | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Drive Line Axle RH | 2028-11-21 | 2028-11-21 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124270 | 21.11.2028 | 24000 | CCK-MP-HAUL-DT055 -FDRSYS-DRLAX-AXLRH | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Cyl Steering RH | 2028-11-21 | 2028-11-21 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000026223 | 21.11.2028 | 15000 | CCK-MP-HAUL-DT147 -STRSYS-STRCY-STCYR | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Brake Slack Adjuster Front | 2028-11-21 | 2028-11-21 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000025888 | 21.11.2028 | 20000 | CCK-MP-HAUL-DT142 -BRKSYS-SLACK-SLACF | 7400 | 87027 | 13221
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Brake Slack Adjuster Rear | 2028-11-21 | 2028-11-21 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000025889 | 21.11.2028 | 20000 | CCK-MP-HAUL-DT142 -BRKSYS-SLACK-SLACR | 7400 | 87027 | 18705
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 250hr Initial Valve Set | 2028-11-21 | 2028-11-21 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156072 | 21.11.2028 | 250 | CCK-MP-HAUL-DT160 -ENGINE | 7400 | 85085 | 7211
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Steering Brake Pump Compensator | 2028-11-22 | 2028-11-22 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204761 | 22.11.2028 | 6000 | CCK-MP-HAUL-DT757 -STRSYS-STPMP | 6800 | 80700 | 14601
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Suspension LHF | 2028-11-22 | 2028-11-24 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067633 | 22.11.2028 | 28000 | CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYLF | 7400 | 85964 | 11104
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 HP Grease Gun, Hose & Burst Sleeve | 2028-11-23 | 2028-11-23 | 4 hrs | FY29 | 4 | 90022836 | B1 | 1000238750 | 23.11.2028 | 12 Monthly | CCK-MP-SUPP-SV220 -GRSYST-ALHLF | 5100 | 58259 | 58259
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Spider Trans Driveshaft | 2028-11-24 | 2028-11-24 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154958 | 24.11.2028 | 6000 | CCK-MP-HAUL-DT136 -FDRSYS-DRSHT-UNVSL | 7400 | 87780 | 6584
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Transmisson Calibration | 2028-11-25 | 2028-11-25 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298668 | 25.11.2028 | 4500 | CCK-MP-HAUL-DT086 -TRNSYS-TRANS | 7400 | 86822 | 14283
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Adjust Engine Valve Set | 2028-11-25 | 2028-11-25 | 6 hrs | FY29 | 6 | 90017451 | B1 | 1000290656 | 25.11.2028 | 3000 | CCK-MP-SUPP-WC008 -ENGINE | 3500 | 51417 | 5947
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Steering Brake Pump Compensator | 2028-11-25 | 2028-11-25 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204766 | 25.11.2028 | 6000 | CCK-MP-HAUL-DT762 -STRSYS-STPMP | 6800 | 76486 | 2043
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Brake Manifold | 2028-11-25 | 2028-11-25 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292171 | 25.11.2028 | 25000 | CCK-MP-HAUL-DT768 -BRKSYS-BRVLV | 6800 | 79837 | 9153
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Pressure Reducing Valve | 2028-11-25 | 2028-11-25 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204840 | 25.11.2028 | 12000 | CCK-MP-HAUL-DT768 -BRKSYS-BRVLV-VVPRV | 6800 | 79837 | 13890
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Hoist LH | 2028-11-26 | 2028-11-26 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128519 | 26.11.2028 | 28000 | CCK-MP-HAUL-DT057 -HYDSYS-HOCYL-HCYLL | 7400 | 91273 | 950
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Cyl Hoist RH | 2028-11-26 | 2028-11-26 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128540 | 26.11.2028 | 28000 | CCK-MP-HAUL-DT057 -HYDSYS-HOCYL-HCYLR | 7400 | 91273 | 10672
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Hyd Pump Steering & Brake | 2028-11-26 | 2028-11-27 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204740 | 26.11.2028 | 12000 | CCK-MP-HAUL-DT760 -STRSYS-STPMP | 6800 | 80390 | 8061
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Hyd Pump Steering & Brake | 2028-11-26 | 2028-11-27 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204745 | 26.11.2028 | 12000 | CCK-MP-HAUL-DT765 -STRSYS-STPMP | 6800 | 78429 | 4626
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Hyd Pump Steering & Brake | 2028-11-26 | 2028-11-27 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204752 | 26.11.2028 | 12000 | CCK-MP-HAUL-DT772 -STRSYS-STPMP | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Brake Manifold | 2028-11-28 | 2028-11-28 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292167 | 28.11.2028 | 25000 | CCK-MP-HAUL-DT766 -BRKSYS-BRVLV | 6800 | 78074 | 10283
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Steering HMU | 2028-11-28 | 2028-11-28 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095079 | 28.11.2028 | 25000 | CCK-MP-HAUL-DT766 -STRSYS-STHMU | 6800 | 78074 | 10283
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Operators Seat | 2028-11-29 | 2028-11-29 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000025260 | 29.11.2028 | 15000 | CCK-MP-HAUL-DT130 -STRUCT-CABIN-SEATS | 7400 | 85185 | 12955
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Auto Lube Pump | 2028-11-30 | 2028-11-30 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285632 | 30.11.2028 | 8000 | CCK-MP-HAUL-DT094 -GRSYST-ALBPP | 7400 | 88788 | 15729
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Auto Lube Pump | 2028-11-30 | 2028-11-30 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094825 | 30.11.2028 | 8000 | CCK-MP-HAUL-DT761 -GRSYST-ALBPP | 6800 | 78264 | 24911
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Radiator Engine Cooling | 2028-11-30 | 2028-12-01 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307512 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -ENGINE-COSYS-RADTR | 7400 | 86767 | 75352
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Pump Drive | 2028-11-30 | 2028-12-01 | 20 hrs | FY29 | 39 | 90002365 | B1 | 1000025738 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -ENGINE-PMPDR | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Wheel End LH | 2028-11-30 | 2028-12-01 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000025748 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -FDRSYS-FDRVE-FDRLH | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Overhaul Valve Control Brake | 2028-11-30 | 2028-12-01 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000025756 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BRVLV | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Brake Oil Cooler Front | 2028-11-30 | 2028-11-30 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000083287 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BROCO-BROCF | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Brake Oil Cooler Rear | 2028-11-30 | 2028-11-30 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000083286 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BROCO-BROCR | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Motor Brake Oil Cooling | 2028-11-30 | 2028-11-30 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000025757 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BROCO-HYMO1 | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Hyd Pump Steering Main & Fan | 2028-11-30 | 2028-11-30 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000025760 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRSYS-STPMP | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Steering HMU | 2028-11-30 | 2028-11-30 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000025761 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRSYS-STHMU | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Ovhl Accumulator Steering Front | 2028-11-30 | 2028-11-30 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025764 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRSYS-STACC-SACCF | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Ovhl Accumulator Steering Middle | 2028-11-30 | 2028-11-30 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025765 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRSYS-STACC-SACCM | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Ovhl Accumulator Steering Rear | 2028-11-30 | 2028-11-30 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025766 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRSYS-STACC-SACCR | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Pump Hoist & Brake | 2028-11-30 | 2028-11-30 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000025768 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -HYDSYS-HOPMP | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Auto Lube Pump | 2028-11-30 | 2028-11-30 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285784 | 30.11.2028 | 8000 | CCK-MP-HAUL-DT140 -GRSYST-ALBPP | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Rear Axle Linkages | 2028-11-30 | 2028-12-02 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000025777 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRUCT-CHASS-AXLIK | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Wheel Group Front RH | 2028-11-30 | 2028-12-01 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157239 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -STRUCT-AXLES-HUBRH | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Replace Hoses Hoist System | 2028-11-30 | 2028-12-01 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000083282 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -HYDSYS-HDHLF-HSTHO | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Replace Brake System Hoses | 2028-11-30 | 2028-12-02 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000083288 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BRHLF-BRHOS | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Brake Cooling System Hoses | 2028-11-30 | 2028-12-01 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000083289 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -BRKSYS-BRHLF-CBRHO | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Drive Line Axle LH | 2028-11-30 | 2028-11-30 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124603 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -FDRSYS-DRLAX-AXLLH | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Drive Line Axle RH | 2028-11-30 | 2028-11-30 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124604 | 30.11.2028 | 24000 | CCK-MP-HAUL-DT140 -FDRSYS-DRLAX-AXLRH | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Spider Trans Driveshaft | 2028-11-30 | 2028-11-30 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154964 | 30.11.2028 | 6000 | CCK-MP-HAUL-DT140 -FDRSYS-DRSHT-UNVSL | 7400 | 86767 | 888
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Steering LH | 2028-11-30 | 2028-11-30 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000024931 | 30.11.2028 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STRCY-STCYL | 7400 | 87135 | 864
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Cyl Steering RH | 2028-11-30 | 2028-11-30 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000024932 | 30.11.2028 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STRCY-STCYR | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Replace Steering System Hoses | 2028-11-30 | 2028-12-02 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083083 | 30.11.2028 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STHLF-STRHO | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Steering Hyd Oil Cooler | 2028-11-30 | 2028-11-30 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106988 | 30.11.2028 | 15000 | CCK-MP-HAUL-DT100 -STRSYS-STOCO | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Steering Bell Crank & Links | 2028-11-30 | 2028-12-01 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317608 | 30.11.2028 | 30000 | CCK-MP-HAUL-DT100 -STRSYS-STLTR-STLAC | 7400 | 87135 | 12861
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Axle Lube Hyd Pump | 2028-12-01 | 2028-12-01 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000083432 | 01.12.2028 | 24000 | CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYPUM | 7400 | 86656 | 6426
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Overhaul Valve Control Brake | 2028-12-01 | 2028-12-02 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000026414 | 01.12.2028 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-BRVLV | 7400 | 86656 | 6426
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Pump Hoist & Brake | 2028-12-01 | 2028-12-01 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000026427 | 01.12.2028 | 24000 | CCK-MP-HAUL-DT150 -HYDSYS-HOPMP | 7400 | 86656 | 6426
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Transmisson Calibration | 2028-12-01 | 2028-12-01 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298734 | 01.12.2028 | 4500 | CCK-MP-HAUL-DT155 -TRNSYS-TRANS | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Brake Oil Cooler Front | 2028-12-02 | 2028-12-02 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000166953 | 02.12.2028 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BROCO-BROCF | 7400 | 44693 | 19408
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Air Con Service & Overhaul | 2028-12-02 | 2028-12-03 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110642 | 02.12.2028 | 12 Monthly | CCK-MP-HAUL-DT773 -STRUCT-CABIN-AIRCN | 6800 | 75884 | 22415
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Hyd Pump Steering Main & Fan | 2028-12-03 | 2028-12-03 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000026418 | 03.12.2028 | 24000 | CCK-MP-HAUL-DT150 -STRSYS-STPMP | 7400 | 86608 | 6426
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Hub & Spindle LH | 2028-12-03 | 2028-12-04 | 24 hrs | FY29 | 48 | 90004020 | B2 | 1000079194 | 03.12.2028 | 24000 | CCK-MP-SUPP-WC3111-STRUCT-AXLES-HUBLH | 5600 | 51257 | 10741
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Cyl Steering RH | 2028-12-03 | 2028-12-03 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000095452 | 03.12.2028 | 15000 | CCK-MP-HAUL-DT773 -STRSYS-STRCY-STCYR | 6800 | 75884 | 14026
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Overhaul Accumulator Brake LHF | 2028-12-03 | 2028-12-03 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000027070 | 03.12.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BACCM-FRLFT | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Overhaul Accumulator Brake RHF | 2028-12-03 | 2028-12-03 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000027071 | 03.12.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BACCM-FRRGT | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Overhaul Accumulator Brake Rear | 2028-12-03 | 2028-12-03 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000027072 | 03.12.2028 | 24000 | CCK-MP-HAUL-DT160 -BRKSYS-BACCM-BACCR | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Ovhl Accumulator Steering Front | 2028-12-03 | 2028-12-03 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000027082 | 03.12.2028 | 24000 | CCK-MP-HAUL-DT160 -STRSYS-STACC-SACCF | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Ovhl Accumulator Steering Middle | 2028-12-03 | 2028-12-03 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000027083 | 03.12.2028 | 24000 | CCK-MP-HAUL-DT160 -STRSYS-STACC-SACCM | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Ovhl Accumulator Steering Rear | 2028-12-03 | 2028-12-03 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000027084 | 03.12.2028 | 24000 | CCK-MP-HAUL-DT160 -STRSYS-STACC-SACCR | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Transmisson Calibration | 2028-12-04 | 2028-12-04 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298671 | 04.12.2028 | 4500 | CCK-MP-HAUL-DT091 -TRNSYS-TRANS | 7400 | 83859 | 5241
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Steering Bleed Down Manifold | 2028-12-04 | 2028-12-04 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094706 | 04.12.2028 | 25000 | CCK-MP-HAUL-DT759 -STRSYS-STBDM | 6800 | 79716 | 34865
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Brake Manifold | 2028-12-04 | 2028-12-04 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292177 | 04.12.2028 | 25000 | CCK-MP-HAUL-DT771 -BRKSYS-BRVLV | 6800 | 84423 | 9331
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Front Wheel Bearings LH | 2028-12-04 | 2028-12-05 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157174 | 04.12.2028 | 16000 | CCK-MP-HAUL-DT158 -STRUCT-AXLES-FWBLH | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Cyl Steering LH | 2028-12-05 | 2028-12-05 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000026750 | 05.12.2028 | 15000 | CCK-MP-HAUL-DT155 -STRSYS-STRCY-STCYL | 7400 | 81407 | 12608
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Overhaul Service Tank Module | 2028-12-05 | 2028-12-05 | 1 hr | FY29 | 1 | 90028957 | B1 | 1000288984 | 05.12.2028 | 36000 | CCK-MP-SUPP-SV4104-STRUCT-SVTNK | 5100 | 23504 | 23504
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Engine Cat C175-16 | 2028-12-05 | 2028-12-08 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000156021 | 05.12.2028 | 24000 | CCK-MP-HAUL-DT148 -ENGINE | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Radiator Engine Cooling | 2028-12-06 | 2028-12-07 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307530 | 06.12.2028 | 24000 | CCK-MP-HAUL-DT150 -ENGINE-COSYS-RADTR | 7400 | 86656 | 33066
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Cylinder Main Lift LH | 2028-12-06 | 2028-12-06 | 8 hrs | FY29 | 16 | 90026974 | B1 | 1000272843 | 06.12.2028 | 10000 | CCK-MP-SUPP-LL0007-HYDSYS-HDCYL-LICYL | 3400 | 15216 | 1628
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Cylinder Main Lift RH | 2028-12-06 | 2028-12-06 | 8 hrs | FY29 | 16 | 90026974 | B1 | 1000272844 | 06.12.2028 | 10000 | CCK-MP-SUPP-LL0007-HYDSYS-HDCYL-LICYR | 3400 | 15216 | 1450
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Motor Lube Axle Rear & Hoses | 2028-12-07 | 2028-12-07 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000271943 | 07.12.2028 | 24000 | CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYM01 | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Axle Lube Hyd Pump | 2028-12-07 | 2028-12-07 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000154007 | 07.12.2028 | 24000 | CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYPUM | 7400 | 84122 | 5883
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Rear Axle Linkages | 2028-12-07 | 2028-12-09 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000023685 | 07.12.2028 | 24000 | CCK-MP-HAUL-DT055 -STRUCT-CHASS-AXLIK | 7400 | 84122 | 30645
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Bearing Left Front | 2028-12-07 | 2028-12-08 | 38 hrs | FY29 | 64 | 90039058 | B1 | 1000390880 | 07.12.2028 | 10000 | CCK-MP-SUPP-LL0007-STRUCT-AXLLF | 3400 | 15216 | 1628
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Bearing Left Rear | 2028-12-07 | 2028-12-08 | 38 hrs | FY29 | 64 | 90039058 | B1 | 1000390882 | 07.12.2028 | 10000 | CCK-MP-SUPP-LL0007-STRUCT-AXLLR | 3400 | 15216 | 1628
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Bearing Right Front | 2028-12-07 | 2028-12-08 | 38 hrs | FY29 | 64 | 90039058 | B1 | 1000390886 | 07.12.2028 | 10000 | CCK-MP-SUPP-LL0007-STRUCT-AXLRF | 3400 | 15216 | 1628
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl RARS Bearing Right Rear | 2028-12-07 | 2028-12-08 | 38 hrs | FY29 | 16 | 90039058 | B1 | 1000390884 | 07.12.2028 | 10000 | CCK-MP-SUPP-LL0007-STRUCT-AXLRR | 3400 | 15216 | 1628
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Auto Lube Pump | 2028-12-07 | 2028-12-07 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285803 | 07.12.2028 | 8000 | CCK-MP-HAUL-DT5202-GRSYST-ALBPP | 7400 | 84333 | 6577
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl AOC Fan Motor Rear | 2028-12-07 | 2028-12-07 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000166923 | 07.12.2028 | 12000 | CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYM02 | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Overhaul Accumulator Brake Rear | 2028-12-07 | 2028-12-07 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000166926 | 07.12.2028 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BACCM-BACCR | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Brake Oil Cooler Rear | 2028-12-07 | 2028-12-07 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000166952 | 07.12.2028 | 24000 | CCK-MP-HAUL-DT5313-BRKSYS-BROCO-BROCR | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Transmisson Calibration | 2028-12-07 | 2028-12-07 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298676 | 07.12.2028 | 4500 | CCK-MP-HAUL-DT100 -TRNSYS-TRANS | 7400 | 87135 | 5195
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Drive Shaft Transmission | 2028-12-08 | 2028-12-08 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154923 | 08.12.2028 | 18000 | CCK-MP-HAUL-DT056 -FDRSYS-DRSHT | 7400 | 84421 | 4791
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Engine Midlife Complete | 2028-12-08 | 2028-12-09 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000155912 | 08.12.2028 | 12000 | CCK-MP-HAUL-DT090 -ENGINE | 7400 | 81670 | 81670
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Cyl Steering LH | 2028-12-08 | 2028-12-08 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000024616 | 08.12.2028 | 15000 | CCK-MP-HAUL-DT095 -STRSYS-STRCY-STCYL | 7400 | 88921 | 12649
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Cyl Steering RH | 2028-12-08 | 2028-12-08 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000024617 | 08.12.2028 | 15000 | CCK-MP-HAUL-DT095 -STRSYS-STRCY-STCYR | 7400 | 88921 | 12649
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Wheel Group Front LH | 2028-12-08 | 2028-12-09 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157165 | 08.12.2028 | 24000 | CCK-MP-HAUL-DT150 -STRUCT-AXLES-HUBLH | 7400 | 86608 | 6426
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 25000hr Ground Fault Test | 2028-12-08 | 2028-12-08 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226102 | 08.12.2028 | 25000 | CCK-MP-HAUL-DT757 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Hub & Spindle LH | 2028-12-08 | 2028-12-09 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000095147 | 08.12.2028 | 18000 | CCK-MP-HAUL-DT767 -STRUCT-AXLES-HUBLH | 6800 | 74312 | 318
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Operators Seat | 2028-12-08 | 2028-12-08 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000026303 | 08.12.2028 | 15000 | CCK-MP-HAUL-DT148 -STRUCT-CABIN-SEATS | 7400 | 85451 | 13242
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Replace Steering System Hoses | 2028-12-09 | 2028-12-11 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000091438 | 09.12.2028 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STHLF-STRHO | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Spider Trans Driveshaft | 2028-12-09 | 2028-12-09 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154970 | 09.12.2028 | 6000 | CCK-MP-HAUL-DT146 -FDRSYS-DRSHT-UNVSL | 7400 | 83062 | 26
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Service Air Conditioner 12M | 2028-12-09 | 2028-12-10 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174183 | 09.12.2028 | 12 Monthly | CCK-MP-HAUL-DT157 -STRUCT-CABIN-AIRCN | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Drive Shaft Transmission | 2028-12-10 | 2028-12-10 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154963 | 10.12.2028 | 18000 | CCK-MP-HAUL-DT138 -FDRSYS-DRSHT | 7400 | 82982 | 5094
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Spider Trans Driveshaft | 2028-12-10 | 2028-12-10 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000166976 | 10.12.2028 | 6000 | CCK-MP-HAUL-DT5313-FDRSYS-DRSHT-UNVSL | 7400 | 44693 | 6773
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Final Drive RH | 2028-12-10 | 2028-12-11 | 26 hrs | FY29 | 50 | 90011543 | B1 | 1000093963 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -FDRSYS-FDRVE-FDRRH | 5100 | 58303 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Valve Brake | 2028-12-10 | 2028-12-10 | 6 hrs | FY29 | 12 | 90011548 | B1 | 1000093054 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -BRKSYS-BRVLV | 5100 | 58303 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Steering Linkages | 2028-12-10 | 2028-12-10 | 12 hrs | FY29 | 24 | 90011557 | B1 | 1000093062 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STLTR | 5100 | 58259 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Operator Seat | 2028-12-10 | 2028-12-10 | 3 hrs | FY29 | 6 | 90011567 | B1 | 1000098152 | 10.12.2028 | 6000 | CCK-MP-SUPP-SV220 -STRUCT-CABIN-SEATS | 5100 | 58259 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Hub and Spindle LH | 2028-12-10 | 2028-12-10 | 12 hrs | FY29 | 22 | 90011570 | B1 | 1000093073 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-AXLES-HUBLH | 5100 | 58259 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Hub and Spindle RH | 2028-12-10 | 2028-12-10 | 12 hrs | FY29 | 22 | 90011571 | B1 | 1000093074 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-AXLES-HUBRH | 5100 | 58259 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Cylinder Suspension LHF | 2028-12-10 | 2028-12-10 | 14 hrs | FY29 | 26 | 90011572 | B1 | 1000093075 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-SUSPN-SCYLF | 5100 | 58259 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Cylinder Suspension RHF | 2028-12-10 | 2028-12-11 | 23 hrs | FY29 | 44 | 90011573 | B1 | 1000093076 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-SUSPN-SCYRF | 5100 | 58259 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Cylinder Suspension LHR | 2028-12-10 | 2028-12-10 | 6 hrs | FY29 | 10 | 90011574 | B1 | 1000093077 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-SUSPN-SCYLR | 5100 | 58259 | 5249
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Cylinder Suspension RHR | 2028-12-10 | 2028-12-10 | 6 hrs | FY29 | 10 | 90011575 | B1 | 1000093078 | 10.12.2028 | 18000 | CCK-MP-SUPP-SV220 -STRUCT-SUSPN-SCYRR | 5100 | 58259 | 5249
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Slack Adjuster Front | 2028-12-10 | 2028-12-10 | 2 hrs | FY29 | 2 | 90002910 | B2 | 1000040561 | 10.12.2028 | 11000 | CCK-MP-SUPP-WC224 -BRKSYS-SLACK-SLACF | 5000 | 71088 | 10363
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Slack Adjuster Rear | 2028-12-10 | 2028-12-10 | 2 hrs | FY29 | 2 | 90002911 | B2 | 1000040562 | 10.12.2028 | 11000 | CCK-MP-SUPP-WC224 -BRKSYS-SLACK-SLACR | 5000 | 71088 | 10363
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Transmisson Calibration | 2028-12-10 | 2028-12-10 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298732 | 10.12.2028 | 4500 | CCK-MP-HAUL-DT151 -TRNSYS-TRANS | 7400 | 84253 | 9530
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Steering LH | 2028-12-11 | 2028-12-11 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000026156 | 11.12.2028 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STRCY-STCYL | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Cyl Steering RH | 2028-12-11 | 2028-12-11 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000026157 | 11.12.2028 | 15000 | CCK-MP-HAUL-DT146 -STRSYS-STRCY-STCYR | 7400 | 83062 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Steering Bell Crank & Links | 2028-12-11 | 2028-12-12 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317630 | 11.12.2028 | 30000 | CCK-MP-HAUL-DT146 -STRSYS-STLTR-STLAC | 7400 | 83062 | 12458
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Hub & Spindle LH | 2028-12-11 | 2028-12-12 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000094299 | 11.12.2028 | 18000 | CCK-MP-HAUL-DT751 -STRUCT-AXLES-HUBLH | 6800 | 86211 | 20723
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Hub & Spindle RH | 2028-12-11 | 2028-12-12 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000094300 | 11.12.2028 | 18000 | CCK-MP-HAUL-DT751 -STRUCT-AXLES-HUBRH | 6800 | 86211 | 2446
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Suspension LHF | 2028-12-11 | 2028-12-13 | 60 hrs | FY29 | 112 | 90011365 | B1 | 1000094301 | 11.12.2028 | 18000 | CCK-MP-HAUL-DT751 -STRUCT-SUSPN-SCYLF | 6800 | 86211 | 20723
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Suspension RHF | 2028-12-11 | 2028-12-13 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000094302 | 11.12.2028 | 18000 | CCK-MP-HAUL-DT751 -STRUCT-SUSPN-SCYRF | 6800 | 86211 | 2446
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Operators Seat | 2028-12-12 | 2028-12-12 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000024567 | 12.12.2028 | 15000 | CCK-MP-HAUL-DT094 -STRUCT-CABIN-SEATS | 7400 | 88788 | 12373
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Hyd Pump Steering & Brake | 2028-12-12 | 2028-12-13 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204439 | 12.12.2028 | 12000 | CCK-MP-HAUL-DT759 -STRSYS-STPMP | 6800 | 79716 | 8626
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Hub & Spindle LH | 2028-12-12 | 2028-12-13 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000094723 | 12.12.2028 | 18000 | CCK-MP-HAUL-DT759 -STRUCT-AXLES-HUBLH | 6800 | 79716 | 2497
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Hub & Spindle RH | 2028-12-12 | 2028-12-13 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000094724 | 12.12.2028 | 18000 | CCK-MP-HAUL-DT759 -STRUCT-AXLES-HUBRH | 6800 | 79716 | 2497
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Hyd Pump Steering & Brake | 2028-12-12 | 2028-12-13 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204743 | 12.12.2028 | 12000 | CCK-MP-HAUL-DT763 -STRSYS-STPMP | 6800 | 74143 | 14657
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Air Con Service & Overhaul | 2028-12-13 | 2028-12-14 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110634 | 13.12.2028 | 12 Monthly | CCK-MP-HAUL-DT765 -STRUCT-CABIN-AIRCN | 6800 | 78429 | 78429
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl AOC Fan Motor Rear | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000027003 | 14.12.2028 | 12000 | CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYM02 | 7400 | 90235 | 18811
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Auto Lube Pump | 2028-12-14 | 2028-12-14 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285797 | 14.12.2028 | 8000 | CCK-MP-HAUL-DT159 -GRSYST-ALBPP | 7400 | 90235 | 15586
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Cyl Steering RH | 2028-12-16 | 2028-12-16 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000094816 | 16.12.2028 | 15000 | CCK-MP-HAUL-DT761 -STRSYS-STRCY-STCYR | 6800 | 78336 | 13970
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 250hr Initial Valve Set | 2028-12-17 | 2028-12-17 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156024 | 17.12.2028 | 250 | CCK-MP-HAUL-DT148 -ENGINE | 7400 | 85451 | 18023
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Pump Hoist | 2028-12-19 | 2028-12-19 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000095456 | 19.12.2028 | 25000 | CCK-MP-HAUL-DT773 -HYDSYS-HOPMP | 6800 | 75884 | 8753
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Engine Midlife Complete | 2028-12-20 | 2028-12-21 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000272955 | 20.12.2028 | 12000 | CCK-MP-SUPP-PM0001-ENGINE | 3400 | 48287 | 3257
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Auto Lube Pump | 2028-12-20 | 2028-12-20 | 2 hrs | FY29 | 2 | 90002914 | B2 | 1000040563 | 20.12.2028 | 6000 | CCK-MP-SUPP-WC224 -GRSYST-ALBPP | 5000 | 71088 | 6229
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Air Con Service & Overhaul | 2028-12-20 | 2028-12-21 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110633 | 20.12.2028 | 12 Monthly | CCK-MP-HAUL-DT764 -STRUCT-CABIN-AIRCN | 6800 | 75315 | 9805
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Cyl Steering RH | 2028-12-20 | 2028-12-20 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000095293 | 20.12.2028 | 15000 | CCK-MP-HAUL-DT770 -STRSYS-STRCY-STCYR | 6800 | 79305 | 13622
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Brake Slack Adjuster Front | 2028-12-22 | 2028-12-22 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000025053 | 22.12.2028 | 20000 | CCK-MP-HAUL-DT127 -BRKSYS-SLACK-SLACF | 7400 | 83059 | 2333
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Brake Slack Adjuster Rear | 2028-12-22 | 2028-12-22 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000025054 | 22.12.2028 | 20000 | CCK-MP-HAUL-DT127 -BRKSYS-SLACK-SLACR | 7400 | 83059 | 2333
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Tyre Sense Battery | 2028-12-22 | 2028-12-22 | 1 hr | FY29 | 1 | 90017025 | B1 | 1000153193 | 22.12.2028 | 24 Monthly | CCK-MP-HAUL-DT768 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Cyl Hoist LH | 2028-12-23 | 2028-12-23 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128575 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT137 -HYDSYS-HOCYL-HCYLL | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Cyl Hoist RH | 2028-12-23 | 2028-12-23 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128576 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT137 -HYDSYS-HOCYL-HCYLR | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Cyl Suspension LHF | 2028-12-23 | 2028-12-25 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067549 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT137 -STRUCT-SUSPN-SCYLF | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Cyl Suspension RHF | 2028-12-23 | 2028-12-25 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067551 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT137 -STRUCT-SUSPN-SCYRF | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Cyl Suspension LHR | 2028-12-23 | 2028-12-24 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000025589 | 23.12.2028 | 28000 | CCK-MP-HAUL-DT137 -STRUCT-SUSPN-SCYLR | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Repl Transmission | 2028-12-23 | 2028-12-24 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272371 | 23.12.2028 | 18000 | CCK-MP-HAUL-DT5202-TRNSYS-TRANS | 7400 | 84333 | 975
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Service Air Conditioner 12M | 2028-12-23 | 2028-12-24 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000172995 | 23.12.2028 | 12 Monthly | CCK-MP-HAUL-DT5313-STRUCT-CABIN-AIRCN | 7400 | 44693 | 44693
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Hub & Spindle LH | 2028-12-23 | 2028-12-24 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000094564 | 23.12.2028 | 18000 | CCK-MP-HAUL-DT756 -STRUCT-AXLES-HUBLH | 6800 | 78754 | 288
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Hub & Spindle RH | 2028-12-23 | 2028-12-24 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000094565 | 23.12.2028 | 18000 | CCK-MP-HAUL-DT756 -STRUCT-AXLES-HUBRH | 6800 | 78754 | 19462
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Tyre Sense Battery | 2028-12-23 | 2028-12-23 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153157 | 23.12.2028 | 24 Monthly | CCK-MP-HAUL-DT143 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 25000hr Ground Fault Test | 2028-12-24 | 2028-12-24 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226038 | 24.12.2028 | 25000 | CCK-MP-HAUL-DT753 -ELCTHV
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Operators Seat | 2028-12-24 | 2028-12-24 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000026501 | 24.12.2028 | 15000 | CCK-MP-HAUL-DT151 -STRUCT-CABIN-SEATS | 7400 | 84253 | 12192
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Engine Module | 2028-12-25 | 2028-12-29 | 102 hrs | FY29 | 226 | 90011318 | B1 | 1000094466 | 25.12.2028 | 25000 | CCK-MP-HAUL-DT755 -ENGINE | 6800 | 84587 | 9678
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Air Con Service & Overhaul | 2028-12-27 | 2028-12-28 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110611 | 27.12.2028 | 12 Monthly | CCK-MP-HAUL-DT751 -STRUCT-CABIN-AIRCN | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Hyd Pump Steering & Brake | 2028-12-27 | 2028-12-28 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204433 | 27.12.2028 | 12000 | CCK-MP-HAUL-DT753 -STRSYS-STPMP | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Air Con Service & Overhaul | 2028-12-27 | 2028-12-28 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110632 | 27.12.2028 | 12 Monthly | CCK-MP-HAUL-DT763 -STRUCT-CABIN-AIRCN | 6800 | 74143 | 21626
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Engine Module | 2028-12-29 | 2029-01-02 | 102 hrs | FY29 | 226 | 90011318 | B1 | 1000094307 | 29.12.2028 | 25000 | CCK-MP-HAUL-DT752 -ENGINE | 6800 | 80681 | 6574
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Hoist LH | 2028-12-29 | 2028-12-29 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128561 | 29.12.2028 | 28000 | CCK-MP-HAUL-DT099 -HYDSYS-HOCYL-HCYLL | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Suspension LHR | 2028-12-29 | 2028-12-30 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000024890 | 29.12.2028 | 28000 | CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYLR | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Suspension RHR | 2028-12-29 | 2028-12-30 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000024891 | 29.12.2028 | 28000 | CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYRR | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Steering Bell Crank & Links | 2028-12-30 | 2028-12-31 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317590 | 30.12.2028 | 30000 | CCK-MP-HAUL-DT082 -STRSYS-STLTR-STLAC | 7400 | 84374 | 11504
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Pressure Reducing Valve | 2028-12-30 | 2028-12-30 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204794 | 30.12.2028 | 12000 | CCK-MP-HAUL-DT762 -BRKSYS-BRVLV-VVPRV | 6800 | 76486 | 10392
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Steering LH | 2028-12-30 | 2028-12-30 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000025958 | 30.12.2028 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STRCY-STCYL | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Cyl Steering RH | 2028-12-30 | 2028-12-30 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025959 | 30.12.2028 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STRCY-STCYR | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Replace Steering System Hoses | 2028-12-30 | 2029-01-01 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083349 | 30.12.2028 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STHLF-STRHO | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Steering Hyd Oil Cooler | 2028-12-30 | 2028-12-30 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107000 | 30.12.2028 | 15000 | CCK-MP-HAUL-DT143 -STRSYS-STOCO | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Steering Bell Crank & Links | 2028-12-30 | 2028-12-31 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317628 | 30.12.2028 | 30000 | CCK-MP-HAUL-DT143 -STRSYS-STLTR-STLAC | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Transmisson Calibration | 2028-12-30 | 2028-12-30 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298730 | 30.12.2028 | 4500 | CCK-MP-HAUL-DT149 -TRNSYS-TRANS | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Steering LH | 2028-12-30 | 2028-12-30 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000025438 | 30.12.2028 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STRCY-STCYL | 7400 | 82965 | 12254
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Steering RH | 2028-12-30 | 2028-12-30 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025439 | 30.12.2028 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STRCY-STCYR | 7400 | 82965 | 12254
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Engine Cat C175-16 LMR | 2028-12-31 | 2029-01-03 | 84 hrs | FY29 | 137 | 90018364 | B1 | 1000167378 | 31.12.2028 | 24000 | CCK-MP-HAUL-DT5318-ENGINE | 7400 | 45240 | 6204
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Pressure Reducing Valve | 2028-12-31 | 2028-12-31 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204795 | 31.12.2028 | 12000 | CCK-MP-HAUL-DT763 -BRKSYS-BRVLV-VVPRV | 6800 | 74143 | 11011
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Replace Steering System Hoses | 2028-12-31 | 2029-01-02 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000091416 | 31.12.2028 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STHLF-STRHO | 7400 | 82965 | 12254
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Auto Lube Pump | 2029-01-02 | 2029-01-02 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285806 | 02.01.2029 | 8000 | CCK-MP-HAUL-DT5314-GRSYST-ALBPP | 7400 | 45898 | 14121
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Engine Module | 2029-01-02 | 2029-01-06 | 102 hrs | FY29 | 226 | 90011318 | B1 | 1000095367 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -ENGINE | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Grid Box Blower Motor LH | 2029-01-02 | 2029-01-02 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000095383 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -ELCTHV-HVGBM-GBMLH | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Wheel Motor LH | 2029-01-02 | 2029-01-04 | 45.5 hrs | FY29 | 83.5 | 90011335 | B1 | 1000095387 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -FDRSYS-WLMTR-WHMLH | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Wheel Motor Oil LH | 2029-01-02 | 2029-01-02 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338240 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -FDRSYS-WLMTR-WHMLH | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Brake Manifold | 2029-01-02 | 2029-01-02 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292179 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -BRKSYS-BRVLV | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Brake Accumulator Front | 2029-01-02 | 2029-01-02 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000095390 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -BRKSYS-BRACC-BACCF | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Brake Accumulator Rear | 2029-01-02 | 2029-01-02 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000095391 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -BRKSYS-BRACC-BACCR | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Valve Retard & Brake Treadle | 2029-01-02 | 2029-01-02 | 5.5 hrs | FY29 | 5.5 | 90011345 | B1 | 1000095393 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -BRKSYS-BRVTR | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Brake Cooling Hoses | 2029-01-02 | 2029-01-02 | 8.5 hrs | FY29 | 14.5 | 90011344 | B1 | 1000223892 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -BRKSYS-BRHLF | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Replace Brake Cabinet Hoses | 2029-01-02 | 2029-01-03 | 32.5 hrs | FY29 | 62.5 | 90015041 | B1 | 1000126519 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -BRKSYS-BRHLF | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Steering Bleed Down Manifold | 2029-01-02 | 2029-01-02 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000095395 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -STRSYS-STBDM | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Valve Flow Amplifier | 2029-01-02 | 2029-01-02 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000095396 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -STRSYS-STVLV | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Steering HMU | 2029-01-02 | 2029-01-02 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095397 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -STRSYS-STHMU | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Accumulator Hyd Steer Front | 2029-01-02 | 2029-01-02 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000095400 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -STRSYS-STACC-SACCF | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Accumulator Hyd Steering Rear | 2029-01-02 | 2029-01-02 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000095401 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -STRSYS-STACC-SACCR | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Pump Hoist | 2029-01-02 | 2029-01-02 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000095403 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -HYDSYS-HOPMP | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Hoist LH | 2029-01-02 | 2029-01-02 | 17 hrs | FY29 | 33 | 90011357 | B1 | 1000095405 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -HYDSYS-HOCYL-HCYLL | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Hoist RH | 2029-01-02 | 2029-01-02 | 17 hrs | FY29 | 33 | 90011358 | B1 | 1000095406 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -HYDSYS-HOCYL-HCYLR | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Drive Shaft | 2029-01-02 | 2029-01-02 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000095407 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -HYDSYS-DRSHT | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Suspension LHR | 2029-01-02 | 2029-01-03 | 32 hrs | FY29 | 50 | 90011367 | B1 | 1000095416 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -STRUCT-SUSPN-SCYLR | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Suspension RHR | 2029-01-02 | 2029-01-03 | 32 hrs | FY29 | 50 | 90011368 | B1 | 1000095417 | 02.01.2029 | 25000 | CCK-MP-HAUL-DT772 -STRUCT-SUSPN-SCYRR | 6800 | 85256 | 10385
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Overhaul Aux Control Cabinet | 2029-01-02 | 2029-01-03 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292530 | 02.01.2029 | 50000 | CCK-MP-HAUL-DT772 -ELCTLV-AUCAB | 6800 | 85256 | 29118
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Steering Hyd Oil Cooler | 2029-01-02 | 2029-01-02 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107025 | 02.01.2029 | 15000 | CCK-MP-HAUL-DT135 -STRSYS-STOCO | 7400 | 82941 | 12254
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Differential | 2029-01-04 | 2029-01-05 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000023718 | 04.01.2029 | 18000 | CCK-MP-HAUL-DT056 -FDRSYS-DIFFL | 7400 | 84421 | 867
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Replace Hoses Differential System | 2029-01-04 | 2029-01-04 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000081856 | 04.01.2029 | 18000 | CCK-MP-HAUL-DT056 -FDRSYS-DIFFL-DIFHO | 7400 | 84421 | 18034
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Motor Lube Axle Rear & Hoses | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000271981 | 04.01.2029 | 24000 | CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-HYM01 | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Transmisson Calibration | 2029-01-04 | 2029-01-04 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298814 | 04.01.2029 | 4500 | CCK-MP-HAUL-DT5314-TRNSYS-TRANS | 7400 | 45898 | 950
777F WC | Onsite PM | Haul | Fortescue | WC009 | WC009 Adjust Engine Valve Set | 2029-01-04 | 2029-01-04 | 6 hrs | FY29 | 6 | 90017451 | B1 | 1000290661 | 04.01.2029 | 3000 | CCK-MP-SUPP-WC009 -ENGINE | 1500 | 34052 | 10936
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 25000hr Ground Fault Test | 2029-01-04 | 2029-01-04 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226103 | 04.01.2029 | 25000 | CCK-MP-HAUL-DT758 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Brake Manifold | 2029-01-04 | 2029-01-04 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292161 | 04.01.2029 | 25000 | CCK-MP-HAUL-DT763 -BRKSYS-BRVLV | 6800 | 74143 | 33625
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Drive Shaft Transmission | 2029-01-05 | 2029-01-05 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154929 | 05.01.2029 | 18000 | CCK-MP-HAUL-DT082 -FDRSYS-DRSHT | 7400 | 84374 | 17432
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Radiator Engine Cooling | 2029-01-06 | 2029-01-07 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307482 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -ENGINE-COSYS-RADTR | 7400 | 81670 | 29126
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Pump Drive | 2029-01-06 | 2029-01-07 | 20 hrs | FY29 | 39 | 90002365 | B1 | 1000024276 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -ENGINE-PMPDR | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Torque Converter | 2029-01-06 | 2029-01-07 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000024281 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -TRNSYS-TRQUE | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Wheel End LH | 2029-01-06 | 2029-01-07 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000024286 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -FDRSYS-FDRVE-FDRLH | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Wheel End RH | 2029-01-06 | 2029-01-07 | 32.5 hrs | FY29 | 58.5 | 90007352 | B1 | 1000024287 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -FDRSYS-FDRVE-FDRRH | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Motor Lube Axle Rear & Hoses | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000271957 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYM01 | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl AOC Fan Motor Rear | 2029-01-06 | 2029-01-06 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000024289 | 06.01.2029 | 12000 | CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYM02 | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Axle Lube Hyd Pump | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000154008 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYPUM | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Overhaul Accumulator Brake LHF | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000024290 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BACCM-FRLFT | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Overhaul Accumulator Brake RHF | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000024291 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BACCM-FRRGT | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Overhaul Accumulator Brake Rear | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000024292 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BACCM-BACCR | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Overhaul Valve Control Brake | 2029-01-06 | 2029-01-07 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000024294 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BRVLV | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Brake Oil Cooler Front | 2029-01-06 | 2029-01-06 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000082964 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BROCO-BROCF | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Brake Oil Cooler Rear | 2029-01-06 | 2029-01-06 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000082963 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BROCO-BROCR | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Hyd Pump Steering Main & Fan | 2029-01-06 | 2029-01-06 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000024298 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -STRSYS-STPMP | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Steering HMU | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000024299 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -STRSYS-STHMU | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Ovhl Accumulator Steering Front | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000024302 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -STRSYS-STACC-SACCF | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Ovhl Accumulator Steering Middle | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000024303 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -STRSYS-STACC-SACCM | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Ovhl Accumulator Steering Rear | 2029-01-06 | 2029-01-06 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000024304 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -STRSYS-STACC-SACCR | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Pump Hoist & Brake | 2029-01-06 | 2029-01-06 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000024306 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -HYDSYS-HOPMP | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Auto Lube Pump | 2029-01-06 | 2029-01-06 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285630 | 06.01.2029 | 8000 | CCK-MP-HAUL-DT090 -GRSYST-ALBPP | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Rear Axle Linkages | 2029-01-06 | 2029-01-08 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000024316 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -STRUCT-CHASS-AXLIK | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Wheel Group Front RH | 2029-01-06 | 2029-01-07 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157209 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -STRUCT-AXLES-HUBRH | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Replace Hoses Hoist System | 2029-01-06 | 2029-01-07 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000082959 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -HYDSYS-HDHLF-HSTHO | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Replace Brake System Hoses | 2029-01-06 | 2029-01-08 | 46 hrs | FY29 | 90 | 90010129 | B3 | 1000082965 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BRHLF-BRHOS | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Brake Cooling System Hoses | 2029-01-06 | 2029-01-07 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000082966 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -BRKSYS-BRHLF-CBRHO | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Drive Line Axle LH | 2029-01-06 | 2029-01-06 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124563 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -FDRSYS-DRLAX-AXLLH | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Drive Line Axle RH | 2029-01-06 | 2029-01-06 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124565 | 06.01.2029 | 24000 | CCK-MP-HAUL-DT090 -FDRSYS-DRLAX-AXLRH | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Spider Trans Driveshaft | 2029-01-06 | 2029-01-06 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154934 | 06.01.2029 | 6000 | CCK-MP-HAUL-DT090 -FDRSYS-DRSHT-UNVSL | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Service Air Conditioner 12M | 2029-01-06 | 2029-01-07 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174161 | 06.01.2029 | 12 Monthly | CCK-MP-HAUL-DT097 -STRUCT-CABIN-AIRCN | 7400 | 83804 | 33534
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Tyre Sense Battery | 2029-01-06 | 2029-01-06 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153144 | 06.01.2029 | 24 Monthly | CCK-MP-HAUL-DT097 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Air Con Service & Overhaul | 2029-01-06 | 2029-01-07 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110637 | 06.01.2029 | 12 Monthly | CCK-MP-HAUL-DT768 -STRUCT-CABIN-AIRCN | 6800 | 79837 | 79837
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Tyre Sense Battery | 2029-01-06 | 2029-01-06 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153159 | 06.01.2029 | 24 Monthly | CCK-MP-HAUL-DT147 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Radiator Fan Hoses | 2029-01-06 | 2029-01-06 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307527 | 06.01.2029 | 12000 | CCK-MP-HAUL-DT148 -ENGINE-COSYS-RADTR | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Spiders Pump Drive Shaft | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000026265 | 06.01.2029 | 18000 | CCK-MP-HAUL-DT148 -ENGINE-PMPDR-DRSHT | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Differential | 2029-01-06 | 2029-01-07 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000026273 | 06.01.2029 | 18000 | CCK-MP-HAUL-DT148 -FDRSYS-DIFFL | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Motor Lube Axle Hoses | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272016 | 06.01.2029 | 12000 | CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYM01 | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Replace Trans TCon System Hoses | 2029-01-06 | 2029-01-07 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000091465 | 06.01.2029 | 18000 | CCK-MP-HAUL-DT148 -TRNSYS-TRANS-TRNHO | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Replace Hoses Differential System | 2029-01-06 | 2029-01-06 | 5 hrs | FY29 | 5 | 90010101 | B2 | 1000091466 | 06.01.2029 | 18000 | CCK-MP-HAUL-DT148 -FDRSYS-DIFFL-DIFHO | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Spider Trans Driveshaft | 2029-01-07 | 2029-01-07 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154926 | 07.01.2029 | 6000 | CCK-MP-HAUL-DT058 -FDRSYS-DRSHT-UNVSL | 7400 | 87864 | 5769
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Steering HMU | 2029-01-08 | 2029-01-08 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000023669 | 08.01.2029 | 24000 | CCK-MP-HAUL-DT055 -STRSYS-STHMU | 7400 | 84122 | 5992
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Steering Linkages | 2029-01-08 | 2029-01-08 | 15 hrs | FY29 | 28 | 90028568 | B1 | 1000317637 | 08.01.2029 | 15000 | CCK-MP-HAUL-DT150 -STRSYS-STLTR | 7400 | 86608 | 12300
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Pressure Reducing Valve | 2029-01-08 | 2029-01-08 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204789 | 08.01.2029 | 12000 | CCK-MP-HAUL-DT757 -BRKSYS-BRVLV-VVPRV | 6800 | 80700 | 7627
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Replace Trans TCon System Hoses | 2029-01-09 | 2029-01-10 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000081850 | 09.01.2029 | 18000 | CCK-MP-HAUL-DT056 -TRNSYS-TRANS-TRNHO | 7400 | 84421 | 17941
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Pressure Reducing Valve | 2029-01-09 | 2029-01-09 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204799 | 09.01.2029 | 12000 | CCK-MP-HAUL-DT767 -BRKSYS-BRVLV-VVPRV | 6800 | 74312 | 9613
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Brake Manifold | 2029-01-09 | 2029-01-09 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292173 | 09.01.2029 | 25000 | CCK-MP-HAUL-DT769 -BRKSYS-BRVLV | 6800 | 80508 | 33507
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Spider Trans Driveshaft | 2029-01-09 | 2029-01-09 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154966 | 09.01.2029 | 6000 | CCK-MP-HAUL-DT142 -FDRSYS-DRSHT-UNVSL | 7400 | 87027 | 11970
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Radiator Engine Cooling | 2029-01-10 | 2029-01-11 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307464 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -ENGINE-COSYS-RADTR | 7400 | 88111 | 31799
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Motor Lube Axle Rear & Hoses | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000271941 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYM01 | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl AOC Fan Motor Rear | 2029-01-10 | 2029-01-10 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000023596 | 10.01.2029 | 12000 | CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYM02 | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Axle Lube Hyd Pump | 2029-01-10 | 2029-01-10 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000082843 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYPUM | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Overhaul Accumulator Brake LHF | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000023597 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BACCM-FRLFT | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Overhaul Accumulator Brake RHF | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000023598 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BACCM-FRRGT | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Overhaul Accumulator Brake Rear | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000023599 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BACCM-BACCR | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Overhaul Valve Control Brake | 2029-01-10 | 2029-01-11 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000023601 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BRVLV | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Motor Brake Oil Cooling | 2029-01-10 | 2029-01-10 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000023602 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BROCO-HYMO1 | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Hyd Pump Steering Main & Fan | 2029-01-10 | 2029-01-10 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000023605 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -STRSYS-STPMP | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Steering HMU | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000023606 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -STRSYS-STHMU | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Ovhl Accumulator Steering Front | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000023609 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -STRSYS-STACC-SACCF | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Ovhl Accumulator Steering Middle | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000023610 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -STRSYS-STACC-SACCM | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Ovhl Accumulator Steering Rear | 2029-01-10 | 2029-01-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000023611 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -STRSYS-STACC-SACCR | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Auto Lube Pump | 2029-01-10 | 2029-01-10 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285622 | 10.01.2029 | 8000 | CCK-MP-HAUL-DT054 -GRSYST-ALBPP | 7400 | 88111 | 5197
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Rear Axle Linkages | 2029-01-10 | 2029-01-12 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000023622 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -STRUCT-CHASS-AXLIK | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Wheel Group Front RH | 2029-01-10 | 2029-01-11 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157193 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -STRUCT-AXLES-HUBRH | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Cyl Suspension RHF | 2029-01-10 | 2029-01-12 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067387 | 10.01.2029 | 28000 | CCK-MP-HAUL-DT054 -STRUCT-SUSPN-SCYRF | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Replace Hoses Hoist System | 2029-01-10 | 2029-01-11 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000082845 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -HYDSYS-HDHLF-HSTHO | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Replace Brake System Hoses | 2029-01-10 | 2029-01-12 | 46 hrs | FY29 | 90 | 90010129 | B2 | 1000082851 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BRHLF-BRHOS | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Brake Cooling System Hoses | 2029-01-10 | 2029-01-11 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000082852 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -BRKSYS-BRHLF-CBRHO | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Drive Line Axle LH | 2029-01-10 | 2029-01-10 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124267 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -FDRSYS-DRLAX-AXLLH | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Drive Line Axle RH | 2029-01-10 | 2029-01-10 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124268 | 10.01.2029 | 24000 | CCK-MP-HAUL-DT054 -FDRSYS-DRLAX-AXLRH | 7400 | 88111 | 6138
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Auto Lube Pump | 2029-01-11 | 2029-01-11 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285783 | 11.01.2029 | 8000 | CCK-MP-HAUL-DT138 -GRSYST-ALBPP | 7400 | 82982 | 5976
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Repl Auto Lube Pump | 2029-01-11 | 2029-01-11 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285807 | 11.01.2029 | 8000 | CCK-MP-HAUL-DT5315-GRSYST-ALBPP | 7400 | 45392 | 20546
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Front Wheel Bearings LH | 2029-01-12 | 2029-01-13 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157168 | 12.01.2029 | 16000 | CCK-MP-HAUL-DT153 -STRUCT-AXLES-FWBLH | 7400 | 84230 | 9760
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Cyl Steering LH | 2029-01-12 | 2029-01-12 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000094762 | 12.01.2029 | 15000 | CCK-MP-HAUL-DT760 -STRSYS-STRCY-STCYL | 6800 | 80390 | 13611
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Front Wheel Bearings LH | 2029-01-12 | 2029-01-13 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157166 | 12.01.2029 | 16000 | CCK-MP-HAUL-DT151 -STRUCT-AXLES-FWBLH | 7400 | 84253 | 12362
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Front Wheel Bearings RH | 2029-01-12 | 2029-01-13 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157254 | 12.01.2029 | 16000 | CCK-MP-HAUL-DT151 -STRUCT-AXLES-FWBRH | 7400 | 84253 | 21869
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Operators Seat | 2029-01-12 | 2029-01-12 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000024945 | 12.01.2029 | 15000 | CCK-MP-HAUL-DT100 -STRUCT-CABIN-SEATS | 7400 | 87135 | 19823
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 250hr Initial Valve Set | 2029-01-13 | 2029-01-13 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000167381 | 13.01.2029 | 250 | CCK-MP-HAUL-DT5318-ENGINE | 7400 | 45240 | 6204
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Drive Shaft Transmission | 2029-01-13 | 2029-01-13 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154973 | 13.01.2029 | 18000 | CCK-MP-HAUL-DT147 -FDRSYS-DRSHT | 7400 | 84708 | 716
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Drive Shaft Transmission | 2029-01-13 | 2029-01-13 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154949 | 13.01.2029 | 18000 | CCK-MP-HAUL-DT100 -FDRSYS-DRSHT | 7400 | 87135 | 17914
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Steering LH | 2029-01-14 | 2029-01-14 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000023859 | 14.01.2029 | 15000 | CCK-MP-HAUL-DT058 -STRSYS-STRCY-STCYL | 7400 | 87864 | 11626
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Cyl Steering RH | 2029-01-14 | 2029-01-14 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000023860 | 14.01.2029 | 15000 | CCK-MP-HAUL-DT058 -STRSYS-STRCY-STCYR | 7400 | 87864 | 11626
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Pressure Reducing Valve | 2029-01-14 | 2029-01-14 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204783 | 14.01.2029 | 12000 | CCK-MP-HAUL-DT751 -BRKSYS-BRVLV-VVPRV | 6800 | 86211 | 8088
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Auto Lube Pump | 2029-01-14 | 2029-01-14 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000095249 | 14.01.2029 | 8000 | CCK-MP-HAUL-DT769 -GRSYST-ALBPP | 6800 | 80508 | 7418
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valves Bypass LH Brake Cool | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026968 | B1 | 1000272839 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-BRKSYS-BRVLV-VLV01 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valves Bypass RH Brake Cool | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026968 | B1 | 1000272840 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-BRKSYS-BRVLV-VLV02 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valves Boost LH Brake Cool | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026969 | B1 | 1000272841 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-BRKSYS-BRVLV-VLV03 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valves Boost RH Brake Cool | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026969 | B1 | 1000272842 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-BRKSYS-BRVLV-VLV04 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Motor Hyd Pump Left | 2029-01-15 | 2029-01-15 | 4 hrs | FY29 | 8 | 90026976 | B1 | 1000272845 | 15.01.2029 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HDMOT-MOT01 | 3400 | 15216 | 0
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Motor Hyd Pump Right | 2029-01-15 | 2029-01-15 | 4 hrs | FY29 | 8 | 90026976 | B1 | 1000272846 | 15.01.2029 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HDMOT-MOT02 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Pump Hydraulic Main Left | 2029-01-15 | 2029-01-15 | 4 hrs | FY29 | 8 | 90026977 | B1 | 1000272847 | 15.01.2029 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HYDPP-HYP01 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Pump Hydraulic Main Right | 2029-01-15 | 2029-01-15 | 4 hrs | FY29 | 8 | 90026977 | B1 | 1000272848 | 15.01.2029 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HYDPP-HYP02 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valve Directnl Main Ctrl LH | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026981 | B1 | 1000272849 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-HYDSYS-HDVLV-HYV01 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valve Directnl Main Ctrl RH | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026981 | B1 | 1000272850 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-HYDSYS-HDVLV-HYV02 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valve Cyl Overcentre Left | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026982 | B1 | 1000272851 | 15.01.2029 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HDVLV-HYV09 | 3400 | 15216 | 0
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Repl Valve Cyl Overcentre Right | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026982 | B1 | 1000272852 | 15.01.2029 | 12000 | CCK-MP-SUPP-LL0007-HYDSYS-HDVLV-HYV10 | 3400 | 15216 | 0
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Valve Check Over Run LH | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026983 | B1 | 1000272853 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-HYDSYS-HDVLV-HYV19 | 3400 | 15216 | 15216
Panther 450T | Onsite PM | Haul | Fortescue | LL0007 | LL0007 Replace Valve Check Over Run RH | 2029-01-15 | 2029-01-15 | 2 hrs | FY29 | 2 | 90026983 | B1 | 1000272854 | 15.01.2029 | 24000 | CCK-MP-SUPP-LL0007-HYDSYS-HDVLV-HYV20 | 3400 | 15216 | 15216
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Pressure Reducing Valve | 2029-01-15 | 2029-01-15 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204785 | 15.01.2029 | 12000 | CCK-MP-HAUL-DT753 -BRKSYS-BRVLV-VVPRV | 6800 | 85999 | 20943
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Brake Accumulator Rear | 2029-01-15 | 2029-01-15 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000094596 | 15.01.2029 | 25000 | CCK-MP-HAUL-DT757 -BRKSYS-BRACC-BACCR | 6800 | 80700 | 8845
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Brake Cooling Hoses | 2029-01-15 | 2029-01-15 | 8.5 hrs | FY29 | 14.5 | 90011344 | B1 | 1000223878 | 15.01.2029 | 25000 | CCK-MP-HAUL-DT758 -BRKSYS-BRHLF | 6800 | 85895 | 10280
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Replace Pump Module Hosing | 2029-01-15 | 2029-01-15 | 15 hrs | FY29 | 27 | 90021389 | B1 | 1000223902 | 15.01.2029 | 25000 | CCK-MP-HAUL-DT758 -HYDSYS-HDHLF | 6800 | 85895 | 10280
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Transmisson Calibration | 2029-01-16 | 2029-01-16 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298667 | 16.01.2029 | 4500 | CCK-MP-HAUL-DT082 -TRNSYS-TRANS | 7400 | 84375 | 13167
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Cyl Steering RH | 2029-01-16 | 2029-01-16 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000024301 | 16.01.2029 | 15000 | CCK-MP-HAUL-DT090 -STRSYS-STRCY-STCYR | 7400 | 81670 | 11697
777G WC | Onsite PM | Haul | Fortescue | WC2501 | WC2501 Repl Sepura SCC Microphone | 2029-01-17 | 2029-01-17 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289622 | 17.01.2029 | 12 Monthly | CCK-MP-SUPP-WC2501-COMMUN-RADIO
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Sepura SCC Microphone | 2029-01-17 | 2029-01-17 | 0.5 hrs | FY29 | 0.5 | 90029001 | B1 | 1000289629 | 17.01.2029 | 12 Monthly | CCK-MP-SUPP-WC3112-COMMUN-RADIO | 5600 | 52240 | 8166
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Service Air Conditioner 12M | 2029-01-17 | 2029-01-18 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174176 | 17.01.2029 | 12 Monthly | CCK-MP-HAUL-DT147 -STRUCT-CABIN-AIRCN | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Transmission Oil Cooler | 2029-01-17 | 2029-01-17 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000083278 | 17.01.2029 | 18000 | CCK-MP-HAUL-DT140 -TRNSYS-TROLC | 7400 | 86767 | 17833
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Replace Steering System Hoses | 2029-01-18 | 2029-01-20 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083026 | 18.01.2029 | 15000 | CCK-MP-HAUL-DT097 -STRSYS-STHLF-STRHO | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Steering Hyd Oil Cooler | 2029-01-18 | 2029-01-18 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107022 | 18.01.2029 | 15000 | CCK-MP-HAUL-DT097 -STRSYS-STOCO | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Steering Bell Crank & Links | 2029-01-18 | 2029-01-19 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317604 | 18.01.2029 | 30000 | CCK-MP-HAUL-DT097 -STRSYS-STLTR-STLAC | 7400 | 83804 | 11742
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Spider Trans Driveshaft | 2029-01-19 | 2029-01-19 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154936 | 19.01.2029 | 6000 | CCK-MP-HAUL-DT091 -FDRSYS-DRSHT-UNVSL | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Auto Lube Pump | 2029-01-19 | 2029-01-19 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285635 | 19.01.2029 | 8000 | CCK-MP-HAUL-DT099 -GRSYST-ALBPP | 7400 | 87442 | 14730
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Steering HMU | 2029-01-20 | 2029-01-20 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095132 | 20.01.2029 | 25000 | CCK-MP-HAUL-DT767 -STRSYS-STHMU | 6800 | 74312 | 7873
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Transmisson Calibration | 2029-01-21 | 2029-01-21 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298735 | 21.01.2029 | 4500 | CCK-MP-HAUL-DT157 -TRNSYS-TRANS | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Steering Hyd Oil Cooler | 2029-01-21 | 2029-01-21 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107014 | 21.01.2029 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STOCO | 7400 | 80609 | 11737
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Brake Accumulator Front | 2029-01-21 | 2029-01-21 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000094542 | 21.01.2029 | 25000 | CCK-MP-HAUL-DT756 -BRKSYS-BRACC-BACCF | 6800 | 78754 | 7925
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Accumulator Hyd Steer Front | 2029-01-21 | 2029-01-21 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000094552 | 21.01.2029 | 25000 | CCK-MP-HAUL-DT756 -STRSYS-STACC-SACCF | 6800 | 78754 | 35070
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Differential | 2029-01-22 | 2029-01-23 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000023970 | 22.01.2029 | 18000 | CCK-MP-HAUL-DT082 -FDRSYS-DIFFL | 7400 | 84374 | 17432
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Replace Hoses Differential System | 2029-01-22 | 2029-01-22 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090068 | 22.01.2029 | 18000 | CCK-MP-HAUL-DT082 -FDRSYS-DIFFL-DIFHO | 7400 | 84374 | 35900
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Steering Hyd Oil Cooler | 2029-01-22 | 2029-01-22 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106983 | 22.01.2029 | 15000 | CCK-MP-HAUL-DT091 -STRSYS-STOCO | 7400 | 83859 | 5241
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 25000hr Ground Fault Test | 2029-01-22 | 2029-01-22 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000224453 | 22.01.2029 | 25000 | CCK-MP-HAUL-DT751 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Steering HMU | 2029-01-22 | 2029-01-22 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094814 | 22.01.2029 | 25000 | CCK-MP-HAUL-DT761 -STRSYS-STHMU | 6800 | 78336 | 33354
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Accumulator Hyd Steer Front | 2029-01-22 | 2029-01-22 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000094817 | 22.01.2029 | 25000 | CCK-MP-HAUL-DT761 -STRSYS-STACC-SACCF | 6800 | 78336 | 8321
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Steering RH | 2029-01-22 | 2029-01-22 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025247 | 22.01.2029 | 15000 | CCK-MP-HAUL-DT130 -STRSYS-STRCY-STCYR | 7400 | 85185 | 11817
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Repl Tyre Sense Battery | 2029-01-23 | 2029-01-23 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153116 | 23.01.2029 | 24 Monthly | CCK-MP-HAUL-DT058 -MANGMT-TYRSN
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Pressure Reducing Valve | 2029-01-23 | 2029-01-23 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204790 | 23.01.2029 | 12000 | CCK-MP-HAUL-DT758 -BRKSYS-BRVLV-VVPRV | 6800 | 85895 | 17961
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Cyl Suspension RHR | 2029-01-23 | 2029-01-24 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000025916 | 23.01.2029 | 28000 | CCK-MP-HAUL-DT142 -STRUCT-SUSPN-SCYRR | 7400 | 87027 | 9824
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Repl Sepura SCC Microphone | 2029-01-24 | 2029-01-24 | 0.5 hrs | FY29 | 0.5 | 90029000 | B1 | 1000289611 | 24.01.2029 | 12 Monthly | CCK-MP-SUPP-SV220 -COMMUN-RADIO | 5100 | 58303 | 58303
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Wheel End LH | 2029-01-25 | 2029-01-26 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000026406 | 25.01.2029 | 24000 | CCK-MP-HAUL-DT150 -FDRSYS-FDRVE-FDRLH | 7400 | 86656 | 5319
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Motor Lube Axle Rear & Hoses | 2029-01-25 | 2029-01-25 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272019 | 25.01.2029 | 24000 | CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYM01 | 7400 | 86656 | 5355
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl AOC Fan Motor Rear | 2029-01-25 | 2029-01-25 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000026409 | 25.01.2029 | 12000 | CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYM02 | 7400 | 86656 | 5355
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Pump Brake Cooling | 2029-01-25 | 2029-01-25 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000026413 | 25.01.2029 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-HYFPP | 7400 | 86656 | 5355
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Motor Brake Oil Cooling | 2029-01-25 | 2029-01-25 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000026415 | 25.01.2029 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-BROCO-HYMO1 | 7400 | 86656 | 5355
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Auto Lube Pump | 2029-01-25 | 2029-01-25 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285791 | 25.01.2029 | 8000 | CCK-MP-HAUL-DT150 -GRSYST-ALBPP | 7400 | 86656 | 5319
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Torque Converter | 2029-01-26 | 2029-01-27 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000166997 | 26.01.2029 | 24000 | CCK-MP-HAUL-DT5314-TRNSYS-TRQUE | 7400 | 45898 | 950
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 25000hr Ground Fault Test | 2029-01-26 | 2029-01-26 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000224454 | 26.01.2029 | 25000 | CCK-MP-HAUL-DT752 -ELCTHV
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Service Air Conditioner 12M | 2029-01-26 | 2029-01-27 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174173 | 26.01.2029 | 12 Monthly | CCK-MP-HAUL-DT142 -STRUCT-CABIN-AIRCN | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Auto Lube Pump | 2029-01-27 | 2029-01-27 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285627 | 27.01.2029 | 8000 | CCK-MP-HAUL-DT082 -GRSYST-ALBPP | 7400 | 84374 | 13167
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Wheel Group Front LH | 2029-01-28 | 2029-01-29 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157181 | 28.01.2029 | 24000 | CCK-MP-HAUL-DT161 -STRUCT-AXLES-HUBLH | 7400 | 80609 | 5614
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Pump Hoist | 2029-01-28 | 2029-01-28 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000094714 | 28.01.2029 | 25000 | CCK-MP-HAUL-DT759 -HYDSYS-HOPMP | 6800 | 79716 | 8626
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Replace Hoses Differential System | 2029-01-30 | 2029-01-30 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090074 | 30.01.2029 | 18000 | CCK-MP-HAUL-DT088 -FDRSYS-DIFFL-DIFHO | 7400 | 89037 | 36530
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 Transmisson Calibration | 2029-01-30 | 2029-01-30 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298741 | 30.01.2029 | 4500 | CCK-MP-HAUL-DT222 -TRNSYS-TRANS | 7400 | 55735 | 4006
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Brake Oil Cooler Front | 2029-01-30 | 2029-01-30 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000167193 | 30.01.2029 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BROCO-BROCF | 7400 | 45108 | 5582
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Brake Oil Cooler Rear | 2029-01-30 | 2029-01-30 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000167192 | 30.01.2029 | 24000 | CCK-MP-HAUL-DT5316-BRKSYS-BROCO-BROCR | 7400 | 45108 | 5582
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Radiator Engine Cooling | 2029-01-31 | 2029-02-01 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307540 | 31.01.2029 | 24000 | CCK-MP-HAUL-DT157 -ENGINE-COSYS-RADTR | 7400 | 83041 | 29465
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Repl Pressure Reducing Valve | 2029-01-31 | 2029-01-31 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204793 | 31.01.2029 | 12000 | CCK-MP-HAUL-DT761 -BRKSYS-BRVLV-VVPRV | 6800 | 78336 | 20667
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Pressure Reducing Valve | 2029-01-31 | 2029-01-31 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204845 | 31.01.2029 | 12000 | CCK-MP-HAUL-DT773 -BRKSYS-BRVLV-VVPRV | 6800 | 75884 | 10579
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Transmisson Calibration | 2029-02-01 | 2029-02-01 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298733 | 01.02.2029 | 4500 | CCK-MP-HAUL-DT153 -TRNSYS-TRANS | 7400 | 84230 | 2506
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Air Con Service & Overhaul | 2029-02-01 | 2029-02-02 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110624 | 01.02.2029 | 12 Monthly | CCK-MP-HAUL-DT755 -STRUCT-CABIN-AIRCN | 6800 | 84587 | 57456
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Transmission | 2029-02-02 | 2029-02-03 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272311 | 02.02.2029 | 18000 | CCK-MP-HAUL-DT097 -TRNSYS-TRANS | 7400 | 83804 | 17427
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Differential | 2029-02-02 | 2029-02-03 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000024727 | 02.02.2029 | 18000 | CCK-MP-HAUL-DT097 -FDRSYS-DIFFL | 7400 | 83804 | 17427
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Replace Trans TCon System Hoses | 2029-02-02 | 2029-02-03 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090088 | 02.02.2029 | 18000 | CCK-MP-HAUL-DT097 -TRNSYS-TRANS-TRNHO | 7400 | 83804 | 17427
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Differential | 2029-02-03 | 2029-02-04 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000024159 | 03.02.2029 | 18000 | CCK-MP-HAUL-DT088 -FDRSYS-DIFFL | 7400 | 89037 | 17080
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Replace Hoses Differential System | 2029-02-03 | 2029-02-03 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090089 | 03.02.2029 | 18000 | CCK-MP-HAUL-DT097 -FDRSYS-DIFFL-DIFHO | 7400 | 83804 | 17425
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Transmisson Calibration | 2029-02-04 | 2029-02-04 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298673 | 04.02.2029 | 4500 | CCK-MP-HAUL-DT095 -TRNSYS-TRANS | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Hoist LH | 2029-02-04 | 2029-02-04 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128591 | 04.02.2029 | 28000 | CCK-MP-HAUL-DT149 -HYDSYS-HOCYL-HCYLL | 7400 | 87258 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Hoist RH | 2029-02-04 | 2029-02-04 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128592 | 04.02.2029 | 28000 | CCK-MP-HAUL-DT149 -HYDSYS-HOCYL-HCYLR | 7400 | 87258 | 9207
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Cyl Suspension RHF | 2029-02-06 | 2029-02-08 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000094726 | 06.02.2029 | 18000 | CCK-MP-HAUL-DT759 -STRUCT-SUSPN-SCYRF | 6800 | 79716 | 2497
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Pressure Reducing Valve | 2029-02-06 | 2029-02-06 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204796 | 06.02.2029 | 12000 | CCK-MP-HAUL-DT764 -BRKSYS-BRVLV-VVPRV | 6800 | 75315 | 6502
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Pressure Reducing Valve | 2029-02-06 | 2029-02-06 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204798 | 06.02.2029 | 12000 | CCK-MP-HAUL-DT766 -BRKSYS-BRVLV-VVPRV | 6800 | 78074 | 11013
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Cyl Steering LH | 2029-02-07 | 2029-02-07 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000026882 | 07.02.2029 | 15000 | CCK-MP-HAUL-DT157 -STRSYS-STRCY-STCYL | 7400 | 83041 | 11339
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Cyl Steering RH | 2029-02-07 | 2029-02-07 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000026883 | 07.02.2029 | 15000 | CCK-MP-HAUL-DT157 -STRSYS-STRCY-STCYR | 7400 | 83041 | 11339
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Overhaul Aux Control Cabinet | 2029-02-07 | 2029-02-08 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292331 | 07.02.2029 | 50000 | CCK-MP-HAUL-DT754 -ELCTLV-AUCAB | 6800 | 83256 | 83256
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Air Con Service & Overhaul | 2029-02-07 | 2029-02-08 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110627 | 07.02.2029 | 12 Monthly | CCK-MP-HAUL-DT758 -STRUCT-CABIN-AIRCN | 6800 | 85895 | 34467
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Transmisson Calibration | 2029-02-08 | 2029-02-08 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298664 | 08.02.2029 | 4500 | CCK-MP-HAUL-DT056 -TRNSYS-TRANS | 7400 | 84421 | 8230
793F | Onsite PM | Haul | Fortescue | DT5315 | DT5315 Transmisson Calibration | 2029-02-10 | 2029-02-10 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298815 | 10.02.2029 | 4500 | CCK-MP-HAUL-DT5315-TRNSYS-TRANS | 7400 | 45392 | 8391
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Pressure Reducing Valve | 2029-02-10 | 2029-02-10 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204846 | 10.02.2029 | 12000 | CCK-MP-HAUL-DT774 -BRKSYS-BRVLV-VVPRV | 6800 | 81047 | 6986
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Steering LH | 2029-02-10 | 2029-02-10 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000025502 | 10.02.2029 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STRCY-STCYL | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Cyl Steering RH | 2029-02-10 | 2029-02-10 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025503 | 10.02.2029 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STRCY-STCYR | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Replace Steering System Hoses | 2029-02-10 | 2029-02-12 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083216 | 10.02.2029 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STHLF-STRHO | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Steering Hyd Oil Cooler | 2029-02-10 | 2029-02-10 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106994 | 10.02.2029 | 15000 | CCK-MP-HAUL-DT136 -STRSYS-STOCO | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Steering Bell Crank & Links | 2029-02-10 | 2029-02-11 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317618 | 10.02.2029 | 30000 | CCK-MP-HAUL-DT136 -STRSYS-STLTR-STLAC | 7400 | 87780 | 11471
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 25000hr Ground Fault Test | 2029-02-11 | 2029-02-11 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226039 | 11.02.2029 | 25000 | CCK-MP-HAUL-DT754 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 25000hr Ground Fault Test | 2029-02-11 | 2029-02-11 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226100 | 11.02.2029 | 25000 | CCK-MP-HAUL-DT755 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Engine Module | 2029-02-11 | 2029-02-15 | 102 hrs | FY29 | 226 | 90011318 | B1 | 1000094731 | 11.02.2029 | 25000 | CCK-MP-HAUL-DT760 -ENGINE | 6800 | 80390 | 8061
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Pump Hoist | 2029-02-11 | 2029-02-11 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000094767 | 11.02.2029 | 25000 | CCK-MP-HAUL-DT760 -HYDSYS-HOPMP | 6800 | 80390 | 8061
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Drive Shaft | 2029-02-11 | 2029-02-11 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094771 | 11.02.2029 | 25000 | CCK-MP-HAUL-DT760 -HYDSYS-DRSHT | 6800 | 80390 | 8061
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Steering HMU | 2029-02-12 | 2029-02-12 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095026 | 12.02.2029 | 25000 | CCK-MP-HAUL-DT765 -STRSYS-STHMU | 6800 | 78429 | 35352
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Engine Cat C175-16 | 2029-02-13 | 2029-02-16 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000156045 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -ENGINE | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Radiator Engine Cooling | 2029-02-13 | 2029-02-14 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307536 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -ENGINE-COSYS-RADTR | 7400 | 81407 | 30632
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Torque Converter | 2029-02-13 | 2029-02-14 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000026731 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -TRNSYS-TRQUE | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Wheel End LH | 2029-02-13 | 2029-02-14 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000026736 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -FDRSYS-FDRVE-FDRLH | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Wheel End RH | 2029-02-13 | 2029-02-14 | 32.5 hrs | FY29 | 58.5 | 90007352 | B1 | 1000026737 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -FDRSYS-FDRVE-FDRRH | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Motor Lube Axle Rear & Hoses | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272025 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYM01 | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl AOC Fan Motor Rear | 2029-02-13 | 2029-02-13 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000026739 | 13.02.2029 | 12000 | CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYM02 | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Axle Lube Hyd Pump | 2029-02-13 | 2029-02-13 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000154015 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYPUM | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Overhaul Accumulator Brake LHF | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026740 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-BACCM-FRLFT | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Overhaul Accumulator Brake RHF | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026741 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-BACCM-FRRGT | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Overhaul Accumulator Brake Rear | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026742 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-BACCM-BACCR | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Pump Brake Cooling | 2029-02-13 | 2029-02-13 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000026743 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-HYFPP | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Overhaul Valve Control Brake | 2029-02-13 | 2029-02-14 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000026744 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-BRVLV | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Motor Brake Oil Cooling | 2029-02-13 | 2029-02-13 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000116249 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-BROCO-HYMO1 | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Ovhl Accumulator Steering Front | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026752 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -STRSYS-STACC-SACCF | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Ovhl Accumulator Steering Middle | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026753 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -STRSYS-STACC-SACCM | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Ovhl Accumulator Steering Rear | 2029-02-13 | 2029-02-13 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026754 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -STRSYS-STACC-SACCR | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Auto Lube Pump | 2029-02-13 | 2029-02-13 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285794 | 13.02.2029 | 8000 | CCK-MP-HAUL-DT155 -GRSYST-ALBPP | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Rear Axle Linkages | 2029-02-13 | 2029-02-15 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000026766 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -STRUCT-CHASS-AXLIK | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Wheel Group Front LH | 2029-02-13 | 2029-02-14 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157171 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -STRUCT-AXLES-HUBLH | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Wheel Group Front RH | 2029-02-13 | 2029-02-14 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157259 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -STRUCT-AXLES-HUBRH | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Replace Hoses Hoist System | 2029-02-13 | 2029-02-14 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000091472 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -HYDSYS-HDHLF-HSTHO | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Replace Brake System Hoses | 2029-02-13 | 2029-02-15 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000091478 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-BRHLF-BRHOS | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Brake Cooling System Hoses | 2029-02-13 | 2029-02-14 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000091479 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -BRKSYS-BRHLF-CBRHO | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Drive Line Axle LH | 2029-02-13 | 2029-02-13 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124621 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -FDRSYS-DRLAX-AXLLH | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Drive Line Axle RH | 2029-02-13 | 2029-02-13 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124622 | 13.02.2029 | 24000 | CCK-MP-HAUL-DT155 -FDRSYS-DRLAX-AXLRH | 7400 | 81407 | 5297
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Brake Manifold | 2029-02-14 | 2029-02-14 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292147 | 14.02.2029 | 25000 | CCK-MP-HAUL-DT756 -BRKSYS-BRVLV | 6800 | 78754 | 7468
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Steering Bleed Down Manifold | 2029-02-14 | 2029-02-14 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094547 | 14.02.2029 | 25000 | CCK-MP-HAUL-DT756 -STRSYS-STBDM | 6800 | 78754 | 7468
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Air Con Service & Overhaul | 2029-02-14 | 2029-02-15 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110635 | 14.02.2029 | 12 Monthly | CCK-MP-HAUL-DT766 -STRUCT-CABIN-AIRCN | 6800 | 78074 | 78074
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Grid Box Blower Motor RH | 2029-02-15 | 2029-02-15 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000095384 | 15.02.2029 | 25000 | CCK-MP-HAUL-DT772 -ELCTHV-HVGBM-GBMRH | 6800 | 85256 | 9332
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Auto Lube Pump | 2029-02-16 | 2029-02-16 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285629 | 16.02.2029 | 8000 | CCK-MP-HAUL-DT088 -GRSYST-ALBPP | 7400 | 89037 | 1086
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl AOC Fan Motor Rear | 2029-02-16 | 2029-02-16 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000024353 | 16.02.2029 | 12000 | CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYM02 | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Auto Lube Pump | 2029-02-16 | 2029-02-16 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285631 | 16.02.2029 | 8000 | CCK-MP-HAUL-DT091 -GRSYST-ALBPP | 7400 | 83859 | 5241
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Replace Torque Conv System Hoses | 2029-02-16 | 2029-02-16 | 12 hrs | FY29 | 12 | 90010100 | B2 | 1000091401 | 16.02.2029 | 24000 | CCK-MP-HAUL-DT091 -TRNSYS-TRQUE-TRQHO | 7400 | 83859 | 5241
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Air Con Service & Overhaul | 2029-02-17 | 2029-02-18 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110626 | 17.02.2029 | 12 Monthly | CCK-MP-HAUL-DT757 -STRUCT-CABIN-AIRCN | 6800 | 80700 | 25834
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Suspension LHF | 2029-02-18 | 2029-02-20 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067597 | 18.02.2029 | 28000 | CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYLF | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Suspension LHR | 2029-02-18 | 2029-02-19 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000026377 | 18.02.2029 | 28000 | CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYLR | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Cyl Suspension RHR | 2029-02-18 | 2029-02-19 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000026378 | 18.02.2029 | 28000 | CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYRR | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Transmisson Calibration | 2029-02-19 | 2029-02-19 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298663 | 19.02.2029 | 4500 | CCK-MP-HAUL-DT055 -TRNSYS-TRANS | 7400 | 84122 | 15848
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl Auto Lube Pump | 2029-02-19 | 2029-02-19 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285628 | 19.02.2029 | 8000 | CCK-MP-HAUL-DT086 -GRSYST-ALBPP | 7400 | 86846 | 5030
793F | Onsite PM | Haul | Fortescue | DT5202 | DT5202 Service Air Conditioner 12M | 2029-02-19 | 2029-02-20 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174191 | 19.02.2029 | 12 Monthly | CCK-MP-HAUL-DT5202-STRUCT-CABIN-AIRCN | 7400 | 84333 | 13327
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Overhaul Service Tank Module | 2029-02-19 | 2029-02-19 | 1 hr | FY29 | 1 | 90028957 | B1 | 1000288852 | 19.02.2029 | 36000 | CCK-MP-SUPP-SV220 -STRUCT-SVTNK | 5100 | 58259 | 58259
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Engine Module | 2029-02-19 | 2029-02-23 | 102 hrs | FY29 | 226 | 90011318 | B1 | 1000094360 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -ENGINE | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Grid Box Blower Motor LH | 2029-02-19 | 2029-02-19 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000094376 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -ELCTHV-HVGBM-GBMLH | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Grid Box Blower Motor RH | 2029-02-19 | 2029-02-19 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000094377 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -ELCTHV-HVGBM-GBMRH | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Brake Manifold | 2029-02-19 | 2029-02-19 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292141 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -BRKSYS-BRVLV | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Brake Accumulator Front | 2029-02-19 | 2029-02-19 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000094383 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -BRKSYS-BRACC-BACCF | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Valve Retard & Brake Treadle | 2029-02-19 | 2029-02-19 | 5.5 hrs | FY29 | 5.5 | 90011345 | B1 | 1000094386 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -BRKSYS-BRVTR | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Brake Cooling Hoses | 2029-02-19 | 2029-02-19 | 8.5 hrs | FY29 | 14.5 | 90011344 | B1 | 1000223873 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -BRKSYS-BRHLF | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Brake Cabinet Hoses | 2029-02-19 | 2029-02-20 | 32.5 hrs | FY29 | 62.5 | 90015041 | B1 | 1000126210 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -BRKSYS-BRHLF | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Steering Bleed Down Manifold | 2029-02-19 | 2029-02-19 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094388 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -STRSYS-STBDM | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Valve Flow Amplifier | 2029-02-19 | 2029-02-19 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000094389 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -STRSYS-STVLV | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Steering HMU | 2029-02-19 | 2029-02-19 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094390 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -STRSYS-STHMU | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Pump Hoist | 2029-02-19 | 2029-02-19 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000094396 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -HYDSYS-HOPMP | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Hoist LH | 2029-02-19 | 2029-02-19 | 17 hrs | FY29 | 33 | 90011357 | B1 | 1000094398 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -HYDSYS-HOCYL-HCYLL | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Hoist RH | 2029-02-19 | 2029-02-19 | 17 hrs | FY29 | 33 | 90011358 | B1 | 1000094399 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -HYDSYS-HOCYL-HCYLR | 6800 | 85999 | 7770
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Drive Shaft | 2029-02-19 | 2029-02-19 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094400 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -HYDSYS-DRSHT | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Replace Pump Module Hosing | 2029-02-19 | 2029-02-19 | 15 hrs | FY29 | 27 | 90021389 | B1 | 1000223897 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -HYDSYS-HDHLF | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Suspension LHR | 2029-02-19 | 2029-02-20 | 32 hrs | FY29 | 50 | 90011367 | B1 | 1000094409 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -STRUCT-SUSPN-SCYLR | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Cyl Suspension RHR | 2029-02-19 | 2029-02-20 | 32 hrs | FY29 | 50 | 90011368 | B1 | 1000094410 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -STRUCT-SUSPN-SCYRR | 6800 | 85999 | 8040
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl 50A Aux Cabinet Relays | 2029-02-19 | 2029-02-19 | 0.5 hrs | FY29 | 0.5 | 90029280 | B1 | 1000292196 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -ELCTLV-AUCAB | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Brake Dual Relay Valves | 2029-02-19 | 2029-02-19 | 8.5 hrs | FY29 | 8.5 | 90021353 | B1 | 1000223473 | 19.02.2029 | 25000 | CCK-MP-HAUL-DT753 -BRKSYS-BRVRL | 6800 | 85999 | 7576
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Overhaul Water Tank Module | 2029-02-20 | 2029-02-20 | 1 hr | FY29 | 1 | 90029222 | B1 | 1000291657 | 20.02.2029 | 44000 | CCK-MP-SUPP-WC225 -STRUCT-WTANK | 5000 | 75244 | 75244
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Air Con Service & Overhaul | 2029-02-20 | 2029-02-21 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110641 | 20.02.2029 | 12 Monthly | CCK-MP-HAUL-DT772 -STRUCT-CABIN-AIRCN | 6800 | 85256 | 35729
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Front Wheel Bearings RH | 2029-02-20 | 2029-02-21 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157240 | 20.02.2029 | 16000 | CCK-MP-HAUL-DT142 -STRUCT-AXLES-FWBRH | 7400 | 87027 | 6635
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Cyl Steering LH | 2029-02-21 | 2029-02-21 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000025057 | 21.02.2029 | 15000 | CCK-MP-HAUL-DT127 -STRSYS-STRCY-STCYL | 7400 | 83059 | 11091
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Cyl Steering RH | 2029-02-21 | 2029-02-21 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025058 | 21.02.2029 | 15000 | CCK-MP-HAUL-DT127 -STRSYS-STRCY-STCYR | 7400 | 83059 | 11091
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Tyre Sense Battery | 2029-02-22 | 2029-02-22 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153115 | 22.02.2029 | 24 Monthly | CCK-MP-HAUL-DT057 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Transmisson Calibration | 2029-02-22 | 2029-02-22 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298818 | 22.02.2029 | 4500 | CCK-MP-HAUL-DT5318-TRNSYS-TRANS | 7400 | 45240 | 9085
930E | Onsite PM | Haul | Fortescue | DT762 | DT762 Repl Brake Accumulator Rear | 2029-02-22 | 2029-02-22 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000094861 | 22.02.2029 | 25000 | CCK-MP-HAUL-DT762 -BRKSYS-BRACC-BACCR | 6800 | 76486 | 31715
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Service Air Conditioner 12M | 2029-02-22 | 2029-02-23 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174184 | 22.02.2029 | 12 Monthly | CCK-MP-HAUL-DT158 -STRUCT-CABIN-AIRCN | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Transmisson Calibration | 2029-02-23 | 2029-02-23 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298727 | 23.02.2029 | 4500 | CCK-MP-HAUL-DT146 -TRNSYS-TRANS | 7400 | 83062 | 12458
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Auto Lube Pump | 2029-02-23 | 2029-02-23 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000095355 | 23.02.2029 | 8000 | CCK-MP-HAUL-DT771 -GRSYST-ALBPP | 6800 | 84423 | 6819
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Service Air Conditioner 12M | 2029-02-24 | 2029-02-25 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174164 | 24.02.2029 | 12 Monthly | CCK-MP-HAUL-DT100 -STRUCT-CABIN-AIRCN | 7400 | 87135 | 33202
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 250hr Initial Valve Set | 2029-02-25 | 2029-02-25 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156048 | 25.02.2029 | 250 | CCK-MP-HAUL-DT155 -ENGINE | 7400 | 81407 | 5297
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Drive Shaft Transmission | 2029-02-25 | 2029-02-25 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000155234 | 25.02.2029 | 18000 | CCK-MP-HAUL-DT5255-FDRSYS-DRSHT | 7400 | 87580 | 354
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Engine Cat C175-16 | 2029-02-27 | 2029-03-02 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000155955 | 27.02.2029 | 24000 | CCK-MP-HAUL-DT127 -ENGINE | 7400 | 83059 | 27545
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Transmisson Calibration | 2029-02-27 | 2029-02-27 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298817 | 27.02.2029 | 4500 | CCK-MP-HAUL-DT5317-TRNSYS-TRANS | 7400 | 45576 | 9163
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Cylinder Steering RH | 2029-02-27 | 2029-02-27 | 6 hrs | FY29 | 12 | 90011556 | B1 | 1000098132 | 27.02.2029 | 18000 | CCK-MP-SUPP-WC221 -STRSYS-STRCY-STCYR | 4000 | 56923 | 7376
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Engine Midlife Complete | 2029-02-27 | 2029-03-01 | 49 hrs | FY29 | 76 | 90028571 | B1 | 1000285525 | 27.02.2029 | 12500 | CCK-MP-HAUL-DT767 -ENGINE | 6800 | 74312 | 19669
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Steering Bell Crank & Links | 2029-02-27 | 2029-02-28 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317626 | 27.02.2029 | 30000 | CCK-MP-HAUL-DT142 -STRSYS-STLTR-STLAC | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Steering Hyd Oil Cooler | 2029-03-01 | 2029-03-01 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106999 | 01.03.2029 | 15000 | CCK-MP-HAUL-DT142 -STRSYS-STOCO | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Steering LH | 2029-03-01 | 2029-03-01 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000026948 | 01.03.2029 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STRCY-STCYL | 7400 | 85964 | 409
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Steering RH | 2029-03-01 | 2029-03-01 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000026949 | 01.03.2029 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STRCY-STCYR | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Operators Seat | 2029-03-01 | 2029-03-01 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000026963 | 01.03.2029 | 15000 | CCK-MP-HAUL-DT158 -STRUCT-CABIN-SEATS | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Replace Steering System Hoses | 2029-03-01 | 2029-03-03 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000091548 | 01.03.2029 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STHLF-STRHO | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Steering Hyd Oil Cooler | 2029-03-01 | 2029-03-01 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107013 | 01.03.2029 | 15000 | CCK-MP-HAUL-DT158 -STRSYS-STOCO | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Spider Trans Driveshaft | 2029-03-01 | 2029-03-01 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154988 | 01.03.2029 | 6000 | CCK-MP-HAUL-DT158 -FDRSYS-DRSHT-UNVSL | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Steering Bell Crank & Links | 2029-03-01 | 2029-03-02 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317648 | 01.03.2029 | 30000 | CCK-MP-HAUL-DT158 -STRSYS-STLTR-STLAC | 7400 | 85964 | 11104
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Grid Box Blower Motor LH | 2029-03-02 | 2029-03-02 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000094588 | 02.03.2029 | 25000 | CCK-MP-HAUL-DT757 -ELCTHV-HVGBM-GBMLH | 6800 | 80700 | 7627
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Pressure Reducing Valve | 2029-03-02 | 2029-03-02 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204842 | 02.03.2029 | 12000 | CCK-MP-HAUL-DT770 -BRKSYS-BRVLV-VVPRV | 6800 | 79305 | 6269
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Cyl Suspension RHF | 2029-03-03 | 2029-03-05 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000094779 | 03.03.2029 | 18000 | CCK-MP-HAUL-DT760 -STRUCT-SUSPN-SCYRF | 6800 | 80390 | 18688
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Auto Lube Pump | 2029-03-04 | 2029-03-04 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285624 | 04.03.2029 | 8000 | CCK-MP-HAUL-DT056 -GRSYST-ALBPP | 7400 | 84421 | 4851
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Replace Steering System Hoses | 2029-03-04 | 2029-03-06 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000082513 | 04.03.2029 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STHLF-STRHO | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Steering Hyd Oil Cooler | 2029-03-04 | 2029-03-04 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107016 | 04.03.2029 | 15000 | CCK-MP-HAUL-DT057 -STRSYS-STOCO | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Spider Trans Driveshaft | 2029-03-04 | 2029-03-04 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154924 | 04.03.2029 | 6000 | CCK-MP-HAUL-DT057 -FDRSYS-DRSHT-UNVSL | 7400 | 91273 | 3875
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Steering Bell Crank & Links | 2029-03-04 | 2029-03-05 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317586 | 04.03.2029 | 30000 | CCK-MP-HAUL-DT057 -STRSYS-STLTR-STLAC | 7400 | 91273 | 10672
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Air Con Service & Overhaul | 2029-03-04 | 2029-03-05 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110638 | 04.03.2029 | 12 Monthly | CCK-MP-HAUL-DT769 -STRUCT-CABIN-AIRCN | 6800 | 80508 | 36906
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Steering Brake Pump Compensator | 2029-03-04 | 2029-03-04 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204774 | 04.03.2029 | 6000 | CCK-MP-HAUL-DT770 -STRSYS-STPMP | 6800 | 79305 | 24817
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Transmission Oil Cooler | 2029-03-04 | 2029-03-04 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000083392 | 04.03.2029 | 18000 | CCK-MP-HAUL-DT147 -TRNSYS-TROLC | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Differential | 2029-03-04 | 2029-03-05 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000026207 | 04.03.2029 | 18000 | CCK-MP-HAUL-DT147 -FDRSYS-DIFFL | 7400 | 84708 | 16832
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Replace Trans TCon System Hoses | 2029-03-04 | 2029-03-05 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090145 | 04.03.2029 | 18000 | CCK-MP-HAUL-DT147 -TRNSYS-TRANS-TRNHO | 7400 | 84659 | 16832
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Replace Hoses Differential System | 2029-03-04 | 2029-03-04 | 5 hrs | FY29 | 5 | 90010101 | B2 | 1000090146 | 04.03.2029 | 18000 | CCK-MP-HAUL-DT147 -FDRSYS-DIFFL-DIFHO | 7400 | 84659 | 16832
Panther 150T | Onsite PM | Haul | Fortescue | LL0010 | LL0010 12M NDT Inspection | 2029-03-05 | 2029-03-05 | 9 hrs | FY29 | 11 | 90038241 | B1 | 1000383086 | 05.03.2029 | 12 Monthly | CCK-MP-SUPP-LL0010 | 2000 | 587 | 587
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Overhaul Accumulator Brake LHF | 2029-03-05 | 2029-03-05 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000023660 | 05.03.2029 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BACCM-FRLFT | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Overhaul Accumulator Brake RHF | 2029-03-05 | 2029-03-05 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000023661 | 05.03.2029 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BACCM-FRRGT | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Overhaul Accumulator Brake Rear | 2029-03-05 | 2029-03-05 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000023662 | 05.03.2029 | 24000 | CCK-MP-HAUL-DT055 -BRKSYS-BACCM-BACCR | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Ovhl Accumulator Steering Middle | 2029-03-05 | 2029-03-05 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000023673 | 05.03.2029 | 24000 | CCK-MP-HAUL-DT055 -STRSYS-STACC-SACCM | 7400 | 84122 | 30645
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Auto Lube Pump | 2029-03-06 | 2029-03-06 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094348 | 06.03.2029 | 8000 | CCK-MP-HAUL-DT752 -GRSYST-ALBPP | 6800 | 80681 | 6552
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 25000hr Ground Fault Test | 2029-03-06 | 2029-03-06 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226133 | 06.03.2029 | 25000 | CCK-MP-HAUL-DT771 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 25000hr Ground Fault Test | 2029-03-07 | 2029-03-07 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226135 | 07.03.2029 | 25000 | CCK-MP-HAUL-DT772 -ELCTHV
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Transmisson Calibration | 2029-03-07 | 2029-03-07 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298679 | 07.03.2029 | 4500 | CCK-MP-HAUL-DT130 -TRNSYS-TRANS | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Transmisson Calibration | 2029-03-07 | 2029-03-07 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298720 | 07.03.2029 | 4500 | CCK-MP-HAUL-DT135 -TRNSYS-TRANS | 7400 | 82965 | 7974
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Steering Bleed Down Manifold | 2029-03-09 | 2029-03-09 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000095236 | 09.03.2029 | 25000 | CCK-MP-HAUL-DT769 -STRSYS-STBDM | 6800 | 80508 | 7418
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Wheel Motor RH | 2029-03-10 | 2029-03-12 | 45.5 hrs | FY29 | 83.5 | 90011336 | B1 | 1000094381 | 10.03.2029 | 25000 | CCK-MP-HAUL-DT753 -FDRSYS-WLMTR-WHMRH | 6800 | 85999 | 7254
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Repl Wheel Motor Oil RH | 2029-03-10 | 2029-03-10 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338203 | 10.03.2029 | 25000 | CCK-MP-HAUL-DT753 -FDRSYS-WLMTR-WHMRH | 6800 | 85999 | 7254
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Wheel Group Front RH | 2029-03-11 | 2029-03-12 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157195 | 11.03.2029 | 24000 | CCK-MP-HAUL-DT055 -STRUCT-AXLES-HUBRH | 7400 | 84122 | 4767
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 250hr Initial Valve Set | 2029-03-11 | 2029-03-11 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000155958 | 11.03.2029 | 250 | CCK-MP-HAUL-DT127 -ENGINE | 7400 | 83059 | 27545
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Auto Lube Pump | 2029-03-11 | 2029-03-11 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285637 | 11.03.2029 | 8000 | CCK-MP-HAUL-DT126 -GRSYST-ALBPP | 7400 | 88657 | 14100
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Operators Seat | 2029-03-12 | 2029-03-12 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000024315 | 12.03.2029 | 15000 | CCK-MP-HAUL-DT090 -STRUCT-CABIN-SEATS | 7400 | 81670 | 10666
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Service Air Conditioner 12M | 2029-03-13 | 2029-03-14 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174114 | 13.03.2029 | 12 Monthly | CCK-MP-HAUL-DT082 -STRUCT-CABIN-AIRCN | 7400 | 84375 | 35900
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Operators Seat | 2029-03-13 | 2029-03-13 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000026039 | 13.03.2029 | 15000 | CCK-MP-HAUL-DT5255-STRUCT-CABIN-SEATS | 7400 | 87580 | 10729
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Transmisson Calibration | 2029-03-14 | 2029-03-14 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298726 | 14.03.2029 | 4500 | CCK-MP-HAUL-DT143 -TRNSYS-TRANS | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Service Air Conditioner 12M | 2029-03-14 | 2029-03-15 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174169 | 14.03.2029 | 12 Monthly | CCK-MP-HAUL-DT136 -STRUCT-CABIN-AIRCN | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Cyl Steering RH | 2029-03-15 | 2029-03-15 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000024365 | 15.03.2029 | 15000 | CCK-MP-HAUL-DT091 -STRSYS-STRCY-STCYR | 7400 | 83859 | 10692
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Steering LH | 2029-03-15 | 2029-03-15 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000025762 | 15.03.2029 | 15000 | CCK-MP-HAUL-DT140 -STRSYS-STRCY-STCYL | 7400 | 86767 | 10686
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Steering RH | 2029-03-15 | 2029-03-15 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000025763 | 15.03.2029 | 15000 | CCK-MP-HAUL-DT140 -STRSYS-STRCY-STCYR | 7400 | 86767 | 10686
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Service Air Conditioner 12M | 2029-03-17 | 2029-03-18 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174112 | 17.03.2029 | 12 Monthly | CCK-MP-HAUL-DT057 -STRUCT-CABIN-AIRCN | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Engine Midlife Complete | 2029-03-17 | 2029-03-18 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000156110 | 17.03.2029 | 12000 | CCK-MP-HAUL-DT5255-ENGINE | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Radiator Fan Hoses | 2029-03-17 | 2029-03-17 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307519 | 17.03.2029 | 12000 | CCK-MP-HAUL-DT5255-ENGINE-COSYS-RADTR | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Transmission | 2029-03-17 | 2029-03-18 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272473 | 17.03.2029 | 18000 | CCK-MP-HAUL-DT5255-TRNSYS-TRANS | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Motor Lube Axle Hoses | 2029-03-17 | 2029-03-17 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272148 | 17.03.2029 | 12000 | CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYM01 | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Trans TCon System Hoses | 2029-03-17 | 2029-03-18 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090139 | 17.03.2029 | 18000 | CCK-MP-HAUL-DT5255-TRNSYS-TRANS-TRNHO | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Replace Hoses Differential System | 2029-03-17 | 2029-03-17 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090140 | 17.03.2029 | 18000 | CCK-MP-HAUL-DT5255-FDRSYS-DIFFL-DIFHO | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Transmisson Calibration | 2029-03-17 | 2029-03-17 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298728 | 17.03.2029 | 4500 | CCK-MP-HAUL-DT147 -TRNSYS-TRANS | 7400 | 84659 | 716
793F | Onsite PM | Haul | Fortescue | DT100 | DT100 Repl Auto Lube Pump | 2029-03-17 | 2029-03-17 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285636 | 17.03.2029 | 8000 | CCK-MP-HAUL-DT100 -GRSYST-ALBPP | 7400 | 87135 | 12861
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Cyl Steering RH | 2029-03-18 | 2029-03-18 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000094551 | 18.03.2029 | 15000 | CCK-MP-HAUL-DT756 -STRSYS-STRCY-STCYR | 6800 | 78754 | 11883
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Replace Trans TCon System Hoses | 2029-03-18 | 2029-03-19 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000091421 | 18.03.2029 | 18000 | CCK-MP-HAUL-DT135 -TRNSYS-TRANS-TRNHO | 7400 | 82965 | 36862
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Ovhl Accumulator Steering Rear | 2029-03-20 | 2029-03-20 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000167017 | 20.03.2029 | 24000 | CCK-MP-HAUL-DT5314-STRSYS-STACC-SACCR | 7400 | 45898 | 29863
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Transmission | 2029-03-20 | 2029-03-21 | 22 hrs | FY29 | 39 | 90026996 | B1 | 1000272515 | 20.03.2029 | 18000 | CCK-MP-HAUL-DT5316-TRNSYS-TRANS | 7400 | 45108 | 15135
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Spider Trans Driveshaft | 2029-03-20 | 2029-03-20 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154954 | 20.03.2029 | 6000 | CCK-MP-HAUL-DT130 -FDRSYS-DRSHT-UNVSL | 7400 | 85185 | 10692
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Suspension RHF | 2029-03-21 | 2029-03-23 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067647 | 21.03.2029 | 28000 | CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYRF | 7400 | 80609 | 8581
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Transmisson Calibration | 2029-03-22 | 2029-03-22 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298723 | 22.03.2029 | 4500 | CCK-MP-HAUL-DT138 -TRNSYS-TRANS | 7400 | 82982 | 6438
930E | Onsite PM | Haul | Fortescue | DT753 | DT753 Air Con Service & Overhaul | 2029-03-22 | 2029-03-23 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110613 | 22.03.2029 | 12 Monthly | CCK-MP-HAUL-DT753 -STRUCT-CABIN-AIRCN | 6800 | 85999 | 7576
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Air Con Service & Overhaul | 2029-03-22 | 2029-03-23 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110628 | 22.03.2029 | 12 Monthly | CCK-MP-HAUL-DT759 -STRUCT-CABIN-AIRCN | 6800 | 79716 | 28650
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Operators Seat | 2029-03-24 | 2029-03-24 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000023747 | 24.03.2029 | 15000 | CCK-MP-HAUL-DT056 -STRUCT-CABIN-SEATS | 7400 | 84421 | 10436
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Cyl Hoist RH | 2029-03-24 | 2029-03-24 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128552 | 24.03.2029 | 28000 | CCK-MP-HAUL-DT091 -HYDSYS-HOCYL-HCYLR | 7400 | 83859 | 8499
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Replace Grease Line/Burst Sleeve | 2029-03-24 | 2029-03-24 | 2 hrs | FY29 | 2 | 90017071 | B1 | 1000201220 | 24.03.2029 | 104 Weekly | CCK-MP-SUPP-SV4104-MODULE
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Hyd Pump Steering & Brake | 2029-03-24 | 2029-03-25 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204746 | 24.03.2029 | 12000 | CCK-MP-HAUL-DT766 -STRSYS-STPMP | 6800 | 78074 | 7137
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Transmisson Calibration | 2029-03-24 | 2029-03-24 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298725 | 24.03.2029 | 4500 | CCK-MP-HAUL-DT142 -TRNSYS-TRANS | 7400 | 87027 | 9824
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Air Con Service & Overhaul | 2029-03-25 | 2029-03-26 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110636 | 25.03.2029 | 12 Monthly | CCK-MP-HAUL-DT767 -STRUCT-CABIN-AIRCN | 6800 | 74312 | 74312
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Auto Lube Pump | 2029-03-27 | 2029-03-27 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285789 | 27.03.2029 | 8000 | CCK-MP-HAUL-DT148 -GRSYST-ALBPP | 7400 | 85452 | 20768
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Service Air Conditioner 12M | 2029-03-28 | 2029-03-29 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174110 | 28.03.2029 | 12 Monthly | CCK-MP-HAUL-DT055 -STRUCT-CABIN-AIRCN | 7400 | 84122 | 30645
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Operators Seat | 2029-03-28 | 2029-03-28 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000024378 | 28.03.2029 | 15000 | CCK-MP-HAUL-DT091 -STRUCT-CABIN-SEATS | 7400 | 83859 | 23814
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Air Con Service & Overhaul | 2029-03-28 | 2029-03-29 | 36 hrs | FY29 | 36 | 90013265 | B1 | 1000110625 | 28.03.2029 | 12 Monthly | CCK-MP-HAUL-DT756 -STRUCT-CABIN-AIRCN | 6800 | 78754 | 19465
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Auto Lube Pump | 2029-03-28 | 2029-03-28 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285792 | 28.03.2029 | 8000 | CCK-MP-HAUL-DT151 -GRSYST-ALBPP | 7400 | 84301 | 13358
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Operators Seat | 2029-03-29 | 2029-03-29 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000167181 | 29.03.2029 | 15000 | CCK-MP-HAUL-DT5316-STRUCT-CABIN-SEATS | 7400 | 45108 | 10479
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Radiator Engine Cooling | 2029-03-30 | 2029-03-31 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307532 | 30.03.2029 | 24000 | CCK-MP-HAUL-DT151 -ENGINE-COSYS-RADTR | 7400 | 84301 | 54538
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Rear Axle Linkages | 2029-03-30 | 2029-04-01 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000026502 | 30.03.2029 | 24000 | CCK-MP-HAUL-DT151 -STRUCT-CHASS-AXLIK | 7400 | 84253 | 28291
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Service Air Conditioner 12M | 2029-03-31 | 2029-04-01 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174170 | 31.03.2029 | 12 Monthly | CCK-MP-HAUL-DT137 -STRUCT-CABIN-AIRCN | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Replace Steering System Hoses | 2029-04-01 | 2029-04-03 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083235 | 01.04.2029 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STHLF-STRHO | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Steering Hyd Oil Cooler | 2029-04-01 | 2029-04-01 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000106995 | 01.04.2029 | 15000 | CCK-MP-HAUL-DT137 -STRSYS-STOCO | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Spider Trans Driveshaft | 2029-04-01 | 2029-04-01 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154960 | 01.04.2029 | 6000 | CCK-MP-HAUL-DT137 -FDRSYS-DRSHT-UNVSL | 7400 | 84196 | 1006
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Steering Bell Crank & Links | 2029-04-01 | 2029-04-02 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317620 | 01.04.2029 | 30000 | CCK-MP-HAUL-DT137 -STRSYS-STLTR-STLAC | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Repl Operators Seat | 2029-04-01 | 2029-04-01 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000127987 | 01.04.2029 | 15000 | CCK-MP-HAUL-DT221 -STRUCT-CABIN-SEATS | 7400 | 57237 | 10386
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Overhaul Accumulator Brake LHF | 2029-04-01 | 2029-04-01 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026476 | 01.04.2029 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BACCM-FRLFT | 7400 | 84301 | 28267
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Overhaul Accumulator Brake RHF | 2029-04-01 | 2029-04-01 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026477 | 01.04.2029 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BACCM-FRRGT | 7400 | 84301 | 28267
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Overhaul Accumulator Brake Rear | 2029-04-01 | 2029-04-01 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026478 | 01.04.2029 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BACCM-BACCR | 7400 | 84301 | 28267
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Ovhl Accumulator Steering Middle | 2029-04-01 | 2029-04-01 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026489 | 01.04.2029 | 24000 | CCK-MP-HAUL-DT151 -STRSYS-STACC-SACCM | 7400 | 84301 | 28267
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Ovhl Accumulator Steering Rear | 2029-04-01 | 2029-04-01 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026490 | 01.04.2029 | 24000 | CCK-MP-HAUL-DT151 -STRSYS-STACC-SACCR | 7400 | 84301 | 28267
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Drive Line Axle LH | 2029-04-01 | 2029-04-01 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000126193 | 01.04.2029 | 24000 | CCK-MP-HAUL-DT151 -FDRSYS-DRLAX-AXLLH | 7400 | 84253 | 2068
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Drive Line Axle RH | 2029-04-01 | 2029-04-01 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000126194 | 01.04.2029 | 24000 | CCK-MP-HAUL-DT151 -FDRSYS-DRLAX-AXLRH | 7400 | 84253 | 2068
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Motor Lube Axle Hoses | 2029-04-03 | 2029-04-03 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000271984 | 03.04.2029 | 12000 | CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYM01 | 7400 | 88921 | 40108
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Motor Lube Axle Rear & Hoses | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272027 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYM01 | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl AOC Fan Motor Rear | 2029-04-04 | 2029-04-04 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000026871 | 04.04.2029 | 12000 | CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYM02 | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Overhaul Accumulator Brake LHF | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026872 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BACCM-FRLFT | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Overhaul Accumulator Brake RHF | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026873 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BACCM-FRRGT | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Overhaul Accumulator Brake Rear | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026874 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BACCM-BACCR | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Pump Brake Cooling | 2029-04-04 | 2029-04-04 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000026875 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-HYFPP | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Overhaul Valve Control Brake | 2029-04-04 | 2029-04-05 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000026876 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BRVLV | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Brake Oil Cooler Front | 2029-04-04 | 2029-04-04 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000091521 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BROCO-BROCF | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Hyd Pump Steering Main & Fan | 2029-04-04 | 2029-04-04 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000026880 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -STRSYS-STPMP | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Steering HMU | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000026881 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -STRSYS-STHMU | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Ovhl Accumulator Steering Front | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026884 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -STRSYS-STACC-SACCF | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Ovhl Accumulator Steering Middle | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026885 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -STRSYS-STACC-SACCM | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Ovhl Accumulator Steering Rear | 2029-04-04 | 2029-04-04 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026886 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -STRSYS-STACC-SACCR | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Pump Hoist & Brake | 2029-04-04 | 2029-04-04 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000026889 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -HYDSYS-HOPMP | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Auto Lube Pump | 2029-04-04 | 2029-04-04 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285795 | 04.04.2029 | 8000 | CCK-MP-HAUL-DT157 -GRSYST-ALBPP | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Rear Axle Linkages | 2029-04-04 | 2029-04-06 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000026898 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -STRUCT-CHASS-AXLIK | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Wheel Group Front RH | 2029-04-04 | 2029-04-05 | 28 hrs | FY29 | 54 | 90017287 | B1 | 1000157261 | 04.04.2029 | 24000 | CCK-MP-HAUL-DT157 -STRUCT-AXLES-HUBRH | 7400 | 83041 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Spider Trans Driveshaft | 2029-04-04 | 2029-04-04 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154986 | 04.04.2029 | 6000 | CCK-MP-HAUL-DT157 -FDRSYS-DRSHT-UNVSL | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Service Air Conditioner 12M | 2029-04-04 | 2029-04-05 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174188 | 04.04.2029 | 12 Monthly | CCK-MP-HAUL-DT221 -STRUCT-CABIN-AIRCN | 7400 | 57237 | 10386
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Auto Lube Pump | 2029-04-04 | 2029-04-04 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094613 | 04.04.2029 | 8000 | CCK-MP-HAUL-DT757 -GRSYST-ALBPP | 6800 | 80700 | 14095
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Replace Hoses Hoist System | 2029-04-05 | 2029-04-06 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000091516 | 05.04.2029 | 24000 | CCK-MP-HAUL-DT157 -HYDSYS-HDHLF-HSTHO | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Replace Brake System Hoses | 2029-04-05 | 2029-04-07 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000091522 | 05.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BRHLF-BRHOS | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Brake Cooling System Hoses | 2029-04-05 | 2029-04-06 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000091523 | 05.04.2029 | 24000 | CCK-MP-HAUL-DT157 -BRKSYS-BRHLF-CBRHO | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Drive Line Axle LH | 2029-04-05 | 2029-04-05 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124623 | 05.04.2029 | 24000 | CCK-MP-HAUL-DT157 -FDRSYS-DRLAX-AXLLH | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Drive Line Axle RH | 2029-04-05 | 2029-04-05 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124624 | 05.04.2029 | 24000 | CCK-MP-HAUL-DT157 -FDRSYS-DRLAX-AXLRH | 7400 | 83026 | 4183
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Wheel End LH | 2029-04-06 | 2029-04-07 | 32.5 hrs | FY29 | 58.5 | 90002374 | B1 | 1000026868 | 06.04.2029 | 24000 | CCK-MP-HAUL-DT157 -FDRSYS-FDRVE-FDRLH | 7400 | 83041 | 4138
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Auto Lube Pump | 2029-04-06 | 2029-04-06 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285809 | 06.04.2029 | 8000 | CCK-MP-HAUL-DT5317-GRSYST-ALBPP | 7400 | 45576 | 12321
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Transmisson Calibration | 2029-04-06 | 2029-04-06 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298738 | 06.04.2029 | 4500 | CCK-MP-HAUL-DT160 -TRNSYS-TRANS | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Repl Auto Lube Pump | 2029-04-07 | 2029-04-07 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285787 | 07.04.2029 | 8000 | CCK-MP-HAUL-DT146 -GRSYST-ALBPP | 7400 | 83108 | 12458
793F | Onsite PM | Haul | Fortescue | DT146 | DT146 Service Air Conditioner 12M | 2029-04-07 | 2029-04-08 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174175 | 07.04.2029 | 12 Monthly | CCK-MP-HAUL-DT146 -STRUCT-CABIN-AIRCN | 7400 | 83062 | 31809
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Auto Lube Pump | 2029-04-07 | 2029-04-07 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094295 | 07.04.2029 | 8000 | CCK-MP-HAUL-DT751 -GRSYST-ALBPP | 6800 | 86211 | 22422
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Steering LH | 2029-04-07 | 2029-04-07 | 12 hrs | FY29 | 20 | 90002385 | B1 | 1000024868 | 07.04.2029 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STRCY-STCYL | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Steering System Hoses | 2029-04-07 | 2029-04-09 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083064 | 07.04.2029 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STHLF-STRHO | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Steering Hyd Oil Cooler | 2029-04-07 | 2029-04-07 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107023 | 07.04.2029 | 15000 | CCK-MP-HAUL-DT099 -STRSYS-STOCO | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Steering Bell Crank & Links | 2029-04-07 | 2029-04-08 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317606 | 07.04.2029 | 30000 | CCK-MP-HAUL-DT099 -STRSYS-STLTR-STLAC | 7400 | 87442 | 10255
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Hub & Spindle RH | 2029-04-08 | 2029-04-09 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000095466 | 08.04.2029 | 18000 | CCK-MP-HAUL-DT773 -STRUCT-AXLES-HUBRH | 6800 | 75884 | 17674
793F | Onsite PM | Haul | Fortescue | DT138 | DT138 Repl Wheel Group Front LH | 2029-04-09 | 2029-04-10 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157149 | 09.04.2029 | 24000 | CCK-MP-HAUL-DT138 -STRUCT-AXLES-HUBLH | 7400 | 82982 | 4189
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Differential | 2029-04-09 | 2029-04-10 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000166919 | 09.04.2029 | 18000 | CCK-MP-HAUL-DT5313-FDRSYS-DIFFL | 7400 | 44693 | 17171
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Service Air Conditioner 12M | 2029-04-09 | 2029-04-10 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174174 | 09.04.2029 | 12 Monthly | CCK-MP-HAUL-DT143 -STRUCT-CABIN-AIRCN | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Spiders Pump Drive Shaft | 2029-04-09 | 2029-04-09 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000025223 | 09.04.2029 | 18000 | CCK-MP-HAUL-DT130 -ENGINE-PMPDR-DRSHT | 7400 | 85185 | 16330
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Transmisson Calibration | 2029-04-09 | 2029-04-09 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298721 | 09.04.2029 | 4500 | CCK-MP-HAUL-DT136 -TRNSYS-TRANS | 7400 | 87780 | 9256
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Service Air Conditioner 12M | 2029-04-12 | 2029-04-13 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174113 | 12.04.2029 | 12 Monthly | CCK-MP-HAUL-DT058 -STRUCT-CABIN-AIRCN | 7400 | 87864 | 1976
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Pressure Reducing Valve | 2029-04-12 | 2029-04-12 | 4.5 hrs | FY29 | 4.5 | 90019929 | B1 | 1000204844 | 12.04.2029 | 12000 | CCK-MP-HAUL-DT772 -BRKSYS-BRVLV-VVPRV | 6800 | 85256 | 10385
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Auto Lube Pump | 2029-04-13 | 2029-04-13 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285625 | 13.04.2029 | 8000 | CCK-MP-HAUL-DT057 -GRSYST-ALBPP | 7400 | 91273 | 3875
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Seat Assy | 2029-04-15 | 2029-04-15 | 3 hrs | FY29 | 6 | 90003494 | B2 | 1000039954 | 15.04.2029 | 11000 | CCK-MP-SUPP-WC224 -STRUCT-CABIN-SEATS | 5000 | 71088 | 8630
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Auto Lube Pump | 2029-04-15 | 2029-04-15 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285788 | 15.04.2029 | 8000 | CCK-MP-HAUL-DT147 -GRSYST-ALBPP | 7400 | 84664 | 12913
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Wheel Motor LH | 2029-04-17 | 2029-04-19 | 45.5 hrs | FY29 | 83.5 | 90011335 | B1 | 1000095281 | 17.04.2029 | 25000 | CCK-MP-HAUL-DT770 -FDRSYS-WLMTR-WHMLH | 6800 | 79305 | 6925
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Wheel Motor Oil LH | 2029-04-17 | 2029-04-17 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338236 | 17.04.2029 | 25000 | CCK-MP-HAUL-DT770 -FDRSYS-WLMTR-WHMLH | 6800 | 79305 | 6925
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Overhaul Aux Control Cabinet | 2029-04-17 | 2029-04-18 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292528 | 17.04.2029 | 50000 | CCK-MP-HAUL-DT770 -ELCTLV-AUCAB | 6800 | 79305 | 24535
T264 | Onsite PM | Haul | Fortescue | DT5489 | DT5489 Service Air Conditioner 12M | 2029-04-18 | 2029-04-18 | 12 hrs | FY29 | 12 | 90029300 | B1 | 1000372286 | 18.04.2029 | 12 Monthly | CCK-MP-HAUL-DT5489-STRUCT-CABIN-AIRCN | 3000 | 1 | 1
T264 | Onsite PM | Haul | Fortescue | DT5490 | DT5490 Service Air Conditioner 12M | 2029-04-18 | 2029-04-18 | 12 hrs | FY29 | 12 | 90029300 | B1 | 1000372331 | 18.04.2029 | 12 Monthly | CCK-MP-HAUL-DT5490-STRUCT-CABIN-AIRCN | 3000 | 1 | 1
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 HP Grease Gun, Hose & Burst Sleeve | 2029-04-18 | 2029-04-18 | 4 hrs | FY29 | 4 | 90022836 | B1 | 1000238751 | 18.04.2029 | 12 Monthly | CCK-MP-SUPP-SV221 -GRSYST-ALHLF | 5100 | 64374 | 64374
789C WC | Onsite PM | Haul | Fortescue | WC225 | WC225 Chassis Electrical System | 2029-04-18 | 2029-04-22 | 96 hrs | FY29 | 96 | 90013796 | B1 | 1000114722 | 18.04.2029 | 44000 | CCK-MP-SUPP-WC225 -ELCTLV-HARNS | 5000 | 75197 | 30501
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Steering Brake Pump Compensator | 2029-04-18 | 2029-04-18 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204756 | 18.04.2029 | 6000 | CCK-MP-HAUL-DT752 -STRSYS-STPMP | 6800 | 80681 | 13250
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Hyd Pump Steering & Brake | 2029-04-18 | 2029-04-19 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204751 | 18.04.2029 | 12000 | CCK-MP-HAUL-DT771 -STRSYS-STPMP | 6800 | 84423 | 18016
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Service Air Conditioner 12M | 2029-04-18 | 2029-04-19 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174163 | 18.04.2029 | 12 Monthly | CCK-MP-HAUL-DT099 -STRUCT-CABIN-AIRCN | 7400 | 87442 | 10255
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Axle Lube Hyd Pump | 2029-04-19 | 2029-04-19 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000082995 | 19.04.2029 | 24000 | CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYPUM | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Auto Lube Pump | 2029-04-19 | 2029-04-19 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285633 | 19.04.2029 | 8000 | CCK-MP-HAUL-DT095 -GRSYST-ALBPP | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Drive Line Axle LH | 2029-04-19 | 2029-04-19 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124585 | 19.04.2029 | 24000 | CCK-MP-HAUL-DT095 -FDRSYS-DRLAX-AXLLH | 7400 | 88921 | 28299
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Drive Line Axle RH | 2029-04-19 | 2029-04-19 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124586 | 19.04.2029 | 24000 | CCK-MP-HAUL-DT095 -FDRSYS-DRLAX-AXLRH | 7400 | 88921 | 3967
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Spider Trans Driveshaft | 2029-04-19 | 2029-04-19 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154940 | 19.04.2029 | 6000 | CCK-MP-HAUL-DT095 -FDRSYS-DRSHT-UNVSL | 7400 | 88921 | 3967
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Grid Box Blower Motor LH | 2029-04-19 | 2029-04-19 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000095277 | 19.04.2029 | 25000 | CCK-MP-HAUL-DT770 -ELCTHV-HVGBM-GBMLH | 6800 | 79305 | 6401
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Grid Box Blower Motor RH | 2029-04-19 | 2029-04-19 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000095278 | 19.04.2029 | 25000 | CCK-MP-HAUL-DT770 -ELCTHV-HVGBM-GBMRH | 6800 | 79305 | 6401
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Spider Trans Driveshaft | 2029-04-19 | 2029-04-19 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154976 | 19.04.2029 | 6000 | CCK-MP-HAUL-DT149 -FDRSYS-DRSHT-UNVSL | 7400 | 86975 | 9207
789C WC | Onsite PM | Haul | Fortescue | WC224 | WC224 Replace Differential | 2029-04-20 | 2029-04-20 | 6 hrs | FY29 | 12 | 90000908 | B2 | 1000033288 | 20.04.2029 | 22000 | CCK-MP-SUPP-WC224 -FDRSYS-DIFFL | 5000 | 71088 | 8572
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Cyl Suspension LHR | 2029-04-20 | 2029-04-21 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000026971 | 20.04.2029 | 28000 | CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYLR | 7400 | 85964 | 8094
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Brake Accumulator | 2029-04-21 | 2029-04-21 | 4 hrs | FY29 | 4 | 90004001 | B2 | 1000079198 | 21.04.2029 | 15000 | CCK-MP-SUPP-WC3111-BRKSYS-BACCM | 5500 | 14617 | 14617
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl PTO Uni's | 2029-04-21 | 2029-04-21 | 4 hrs | FY29 | 4 | 90031093 | B1 | 1000307813 | 21.04.2029 | 5000 | CCK-MP-SUPP-WC3111-ENGINE-PMPDR-DRSHT | 5600 | 51257 | 9904
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Steering Link & Arm Rebush | 2029-04-21 | 2029-04-21 | 14 hrs | FY29 | 22 | 90004007 | B2 | 1000079206 | 21.04.2029 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STLTR | 5600 | 51257 | 14617
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Steering Oil Cooler | 2029-04-21 | 2029-04-21 | 3 hrs | FY29 | 3 | 90004006 | B2 | 1000079207 | 21.04.2029 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STOLC | 5600 | 51257 | 14617
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Steering Pump | 2029-04-21 | 2029-04-21 | 4 hrs | FY29 | 4 | 90004003 | B2 | 1000079202 | 21.04.2029 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STPMP | 5600 | 51257 | 14617
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Steering Cylinder LH | 2029-04-21 | 2029-04-21 | 10 hrs | FY29 | 18 | 90004005 | B2 | 1000079204 | 21.04.2029 | 15000 | CCK-MP-SUPP-WC3111-STRSYS-STRCY-STCYL | 5600 | 51257 | 14617
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Radiator Fan Hoses | 2029-04-22 | 2029-04-22 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307487 | 22.04.2029 | 12000 | CCK-MP-HAUL-DT094 -ENGINE-COSYS-RADTR | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Drive Shaft Transmission | 2029-04-22 | 2029-04-22 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154939 | 22.04.2029 | 18000 | CCK-MP-HAUL-DT094 -FDRSYS-DRSHT | 7400 | 88788 | 245
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Replace Trans TCon System Hoses | 2029-04-22 | 2029-04-23 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090082 | 22.04.2029 | 18000 | CCK-MP-HAUL-DT094 -TRNSYS-TRANS-TRNHO | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Replace Hoses Differential System | 2029-04-22 | 2029-04-22 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090083 | 22.04.2029 | 18000 | CCK-MP-HAUL-DT094 -FDRSYS-DIFFL-DIFHO | 7400 | 88788 | 15729
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Operators Seat | 2029-04-22 | 2029-04-22 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000027029 | 22.04.2029 | 15000 | CCK-MP-HAUL-DT159 -STRUCT-CABIN-SEATS | 7400 | 90235 | 18567
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Suspension LHF | 2029-04-22 | 2029-04-24 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000116280 | 22.04.2029 | 28000 | CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYLF | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Suspension LHR | 2029-04-22 | 2029-04-23 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000025460 | 22.04.2029 | 28000 | CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYLR | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT135 | DT135 Repl Cyl Suspension RHR | 2029-04-22 | 2029-04-23 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000025461 | 22.04.2029 | 28000 | CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYRR | 7400 | 82965 | 8025
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl AOC Fan Motor Rear | 2029-04-23 | 2029-04-23 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000026013 | 23.04.2029 | 12000 | CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYM02 | 7400 | 87580 | 16634
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Cyl Suspension LHF | 2029-04-23 | 2029-04-25 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067505 | 23.04.2029 | 28000 | CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYLF | 7400 | 87442 | 7956
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Drive Shaft Transmission | 2029-04-24 | 2029-04-24 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154943 | 24.04.2029 | 18000 | CCK-MP-HAUL-DT097 -FDRSYS-DRSHT | 7400 | 83804 | 15765
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Transmisson Calibration | 2029-04-24 | 2029-04-24 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298678 | 24.04.2029 | 4500 | CCK-MP-HAUL-DT127 -TRNSYS-TRANS | 7400 | 83059 | 2333
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Steering Brake Pump Compensator | 2029-04-24 | 2029-04-24 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204760 | 24.04.2029 | 6000 | CCK-MP-HAUL-DT756 -STRSYS-STPMP | 6800 | 78754 | 308
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Auto Lube Pump | 2029-04-24 | 2029-04-24 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094772 | 24.04.2029 | 8000 | CCK-MP-HAUL-DT760 -GRSYST-ALBPP | 6800 | 80390 | 11271
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Valve Brake | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 12 | 90011548 | B1 | 1000092998 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -BRKSYS-BRVLV | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace C32 Engine | 2029-04-25 | 2029-04-29 | 98 hrs | FY29 | 386 | 90015632 | B1 | 1000269778 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -ENGINE | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Engine Radiator | 2029-04-25 | 2029-04-26 | 26 hrs | FY29 | 50 | 90011532 | B1 | 1000093081 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -ENGINE-COSYS-RADTR | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Engine Aftercooler | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 6 | 90011533 | B1 | 1000093082 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -ENGINE-INTEX-AFTER | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Differential | 2029-04-25 | 2029-04-26 | 20 hrs | FY29 | 38 | 90011541 | B1 | 1000092991 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -FDRSYS-DIFFL | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Final Drive LH | 2029-04-25 | 2029-04-26 | 26 hrs | FY29 | 50 | 90011542 | B1 | 1000092992 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -FDRSYS-FDRVE-FDRLH | 5100 | 64374 | 15010
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Final Drive RH | 2029-04-25 | 2029-04-26 | 26 hrs | FY29 | 50 | 90011543 | B1 | 1000092993 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -FDRSYS-FDRVE-FDRRH | 5100 | 64374 | 15010
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Pump Hoist Lines | 2029-04-25 | 2029-04-25 | 8 hrs | FY29 | 8 | 90011562 | B1 | 1000093010 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -HYDSYS-HDHLF | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Hydraulic Oil Cooler | 2029-04-25 | 2029-04-25 | 12 hrs | FY29 | 12 | 90011563 | B1 | 1000093011 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -HYDSYS-HDOCO | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Pump Hoist & Pump Brake Chrg | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 6 | 90037881 | B1 | 1000379673 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -HYDSYS-HOPMP | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Pump Steering | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 6 | 90011552 | B1 | 1000093000 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -STRSYS-STPMP | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Hub and Spindle LH | 2029-04-25 | 2029-04-25 | 12 hrs | FY29 | 22 | 90011570 | B1 | 1000093017 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-AXLES-HUBLH | 5100 | 64374 | 7976
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Hub and Spindle RH | 2029-04-25 | 2029-04-25 | 12 hrs | FY29 | 22 | 90011571 | B1 | 1000093018 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-AXLES-HUBRH | 5100 | 64374 | 7976
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Overhaul Airconditioner | 2029-04-25 | 2029-04-26 | 24 hrs | FY29 | 24 | 90011566 | B2 | 1000269901 | 25.04.2029 | 9000 | CCK-MP-SUPP-SV221 -STRUCT-CABIN-AIRCN | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Operator Seat | 2029-04-25 | 2029-04-25 | 3 hrs | FY29 | 6 | 90011567 | B1 | 1000098153 | 25.04.2029 | 6000 | CCK-MP-SUPP-SV221 -STRUCT-CABIN-SEATS | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Refurbish A Frame | 2029-04-25 | 2029-04-26 | 18 hrs | FY29 | 36 | 90011568 | B1 | 1000093015 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-CHASS-AFRME | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Tag Link | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 6 | 90011569 | B1 | 1000093091 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-CHASS-TAGLK | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Cylinder Suspension LHR | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 10 | 90011574 | B1 | 1000093021 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-SUSPN-SCYLR | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Replace Cylinder Suspension RHR | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 10 | 90011575 | B1 | 1000093022 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -STRUCT-SUSPN-SCYRR | 5100 | 64374 | 4253
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Repl Trans & TCon Charge Pump | 2029-04-25 | 2029-04-25 | 4 hrs | FY29 | 4 | 90011536 | B1 | 1000093085 | 25.04.2029 | 18000 | CCK-MP-SUPP-SV221 -TRNSYS-TRPMP | 5100 | 64374 | 4253
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Hoist RH | 2029-04-25 | 2029-04-25 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128570 | 25.04.2029 | 28000 | CCK-MP-HAUL-DT130 -HYDSYS-HOCYL-HCYLR | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Suspension LHF | 2029-04-25 | 2029-04-27 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067529 | 25.04.2029 | 28000 | CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYLF | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Suspension LHR | 2029-04-25 | 2029-04-26 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000025268 | 25.04.2029 | 28000 | CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYLR | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Cyl Suspension RHR | 2029-04-25 | 2029-04-26 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000025269 | 25.04.2029 | 28000 | CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYRR | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Front Wheel Bearings RH | 2029-04-25 | 2029-04-26 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157228 | 25.04.2029 | 16000 | CCK-MP-HAUL-DT130 -STRUCT-AXLES-FWBRH | 7400 | 85185 | 7959
793F | Onsite PM | Haul | Fortescue | DT222 | DT222 250hr Initial Valve Set | 2029-04-26 | 2029-04-26 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156090 | 26.04.2029 | 250 | CCK-MP-HAUL-DT222 -ENGINE | 7400 | 55735 | 3987
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Repl Brake Oil Cooler | 2029-04-26 | 2029-04-26 | 6 hrs | FY29 | 6 | 90011549 | B1 | 1000098073 | 26.04.2029 | 15000 | CCK-MP-SUPP-WC220 -BRKSYS-BROCO | 4300 | 58137 | 2661
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Grid Box Blower Motor LH | 2029-04-26 | 2029-04-26 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000094323 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -ELCTHV-HVGBM-GBMLH | 6800 | 80681 | 6604
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Grid Box Blower Motor RH | 2029-04-26 | 2029-04-26 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000094324 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -ELCTHV-HVGBM-GBMRH | 6800 | 80681 | 6604
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Wheel Motor LH | 2029-04-26 | 2029-04-28 | 45.5 hrs | FY29 | 83.5 | 90011335 | B1 | 1000094327 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -FDRSYS-WLMTR-WHMLH | 6800 | 80681 | 6525
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Wheel Motor Oil LH | 2029-04-26 | 2029-04-26 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338200 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -FDRSYS-WLMTR-WHMLH | 6800 | 80681 | 6525
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Wheel Motor RH | 2029-04-26 | 2029-04-28 | 45.5 hrs | FY29 | 83.5 | 90011336 | B1 | 1000094328 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -FDRSYS-WLMTR-WHMRH | 6800 | 80681 | 6525
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Wheel Motor Oil RH | 2029-04-26 | 2029-04-26 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338201 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -FDRSYS-WLMTR-WHMRH | 6800 | 80681 | 6525
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Steering Bleed Down Manifold | 2029-04-26 | 2029-04-26 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000094335 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -STRSYS-STBDM | 6800 | 80681 | 6552
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Hoist RH | 2029-04-26 | 2029-04-26 | 17 hrs | FY29 | 33 | 90011358 | B1 | 1000094346 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -HYDSYS-HOCYL-HCYLR | 6800 | 80681 | 6604
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Replace Pump Module Hosing | 2029-04-26 | 2029-04-26 | 15 hrs | FY29 | 27 | 90021389 | B1 | 1000223896 | 26.04.2029 | 25000 | CCK-MP-HAUL-DT752 -HYDSYS-HDHLF | 6800 | 80681 | 6552
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Brake Accumulator Front | 2029-04-27 | 2029-04-27 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000095284 | 27.04.2029 | 25000 | CCK-MP-HAUL-DT770 -BRKSYS-BRACC-BACCF | 6800 | 79305 | 32219
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Steering Bleed Down Manifold | 2029-04-27 | 2029-04-27 | 6.5 hrs | FY29 | 8 | 90011347 | B1 | 1000095289 | 27.04.2029 | 25000 | CCK-MP-HAUL-DT770 -STRSYS-STBDM | 6800 | 79305 | 33299
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Valve Flow Amplifier | 2029-04-27 | 2029-04-27 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000095290 | 27.04.2029 | 25000 | CCK-MP-HAUL-DT770 -STRSYS-STVLV | 6800 | 79305 | 33299
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 Repl Drive Shaft | 2029-04-27 | 2029-04-27 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000095301 | 27.04.2029 | 25000 | CCK-MP-HAUL-DT770 -HYDSYS-DRSHT | 6800 | 79305 | 6269
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Front Wheel Bearings LH | 2029-04-27 | 2029-04-28 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157104 | 27.04.2029 | 16000 | CCK-MP-HAUL-DT054 -STRUCT-AXLES-FWBLH | 7400 | 88110 | 6138
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Transmisson Calibration | 2029-04-27 | 2029-04-27 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298724 | 27.04.2029 | 4500 | CCK-MP-HAUL-DT140 -TRNSYS-TRANS | 7400 | 86767 | 6817
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Overhaul Aux Control Cabinet | 2029-04-28 | 2029-04-29 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292329 | 28.04.2029 | 50000 | CCK-MP-HAUL-DT752 -ELCTLV-AUCAB | 6800 | 80681 | 25668
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Replace Brake Cooling Hoses | 2029-04-29 | 2029-04-29 | 8.5 hrs | FY29 | 14.5 | 90011344 | B1 | 1000223872 | 29.04.2029 | 25000 | CCK-MP-HAUL-DT752 -BRKSYS-BRHLF | 6800 | 80681 | 6552
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Drive Shaft | 2029-04-29 | 2029-04-29 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000094347 | 29.04.2029 | 25000 | CCK-MP-HAUL-DT752 -HYDSYS-DRSHT | 6800 | 80681 | 6552
793F | Onsite PM | Haul | Fortescue | DT058 | DT058 Transmisson Calibration | 2029-04-30 | 2029-04-30 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298666 | 30.04.2029 | 4500 | CCK-MP-HAUL-DT058 -TRNSYS-TRANS | 7400 | 87864 | 1976
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Front Wheel Bearings RH | 2029-05-02 | 2029-05-03 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157226 | 02.05.2029 | 16000 | CCK-MP-HAUL-DT127 -STRUCT-AXLES-FWBRH | 7400 | 83059 | 15222
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Operators Seat | 2029-05-02 | 2029-05-02 | 3 hrs | FY29 | 6 | 90002395 | B1 | 1000167021 | 02.05.2029 | 15000 | CCK-MP-HAUL-DT5314-STRUCT-CABIN-SEATS | 7400 | 45898 | 13481
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Repl Cyl Hoist RH | 2029-05-02 | 2029-05-02 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000167208 | 02.05.2029 | 28000 | CCK-MP-HAUL-DT5316-HYDSYS-HOCYL-HCYLR | 7400 | 45108 | 7788
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Engine Cat C175-16 | 2029-05-04 | 2029-05-07 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000155925 | 04.05.2029 | 24000 | CCK-MP-HAUL-DT095 -ENGINE | 7400 | 88921 | 28299
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Transmisson Calibration | 2029-05-04 | 2029-05-04 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298813 | 04.05.2029 | 4500 | CCK-MP-HAUL-DT5313-TRNSYS-TRANS | 7400 | 44693 | 6773
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Auto Lube Pump | 2029-05-05 | 2029-05-05 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285811 | 05.05.2029 | 8000 | CCK-MP-SUPP-PM0001-GRSYST-ALBPP | 3400 | 48287 | 48287
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Auto Lube Pump | 2029-05-05 | 2029-05-05 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094719 | 05.05.2029 | 8000 | CCK-MP-HAUL-DT759 -GRSYST-ALBPP | 6800 | 79716 | 16971
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 Repl Pump Hoist & Brake | 2029-05-06 | 2029-05-06 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000024622 | 06.05.2029 | 24000 | CCK-MP-HAUL-DT095 -HYDSYS-HOPMP | 7400 | 88921 | 3614
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Steering Hyd Oil Cooler | 2029-05-07 | 2029-05-07 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000167042 | 07.05.2029 | 15000 | CCK-MP-HAUL-DT5314-STRSYS-STOCO | 7400 | 45898 | 9592
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Replace Steering System Hoses | 2029-05-07 | 2029-05-09 | 54 hrs | FY29 | 106 | 90010133 | B2 | 1000167036 | 07.05.2029 | 15000 | CCK-MP-HAUL-DT5314-STRSYS-STHLF-STRHO | 7400 | 45898 | 9592
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Cyl Hoist RH | 2029-05-07 | 2029-05-07 | 17 hrs | FY29 | 33 | 90011358 | B1 | 1000094505 | 07.05.2029 | 25000 | CCK-MP-HAUL-DT755 -HYDSYS-HOCYL-HCYLR | 6800 | 84587 | 6271
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Replace Steering System Hoses | 2029-05-07 | 2029-05-09 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083463 | 07.05.2029 | 15000 | CCK-MP-HAUL-DT151 -STRSYS-STHLF-STRHO | 7400 | 84253 | 9530
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 25000hr Ground Fault Test | 2029-05-08 | 2029-05-08 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226121 | 08.05.2029 | 25000 | CCK-MP-HAUL-DT760 -ELCTHV
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Radiator Fan Hoses | 2029-05-09 | 2029-05-09 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307545 | 09.05.2029 | 12000 | CCK-MP-HAUL-DT159 -ENGINE-COSYS-RADTR | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Transmission | 2029-05-09 | 2029-05-10 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272357 | 09.05.2029 | 18000 | CCK-MP-HAUL-DT159 -TRNSYS-TRANS | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Motor Lube Axle Hoses | 2029-05-09 | 2029-05-09 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000272032 | 09.05.2029 | 12000 | CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYM01 | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Replace Trans TCon System Hoses | 2029-05-09 | 2029-05-10 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090166 | 09.05.2029 | 18000 | CCK-MP-HAUL-DT159 -TRNSYS-TRANS-TRNHO | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Replace Hoses Differential System | 2029-05-09 | 2029-05-09 | 5 hrs | FY29 | 5 | 90010101 | B2 | 1000090167 | 09.05.2029 | 18000 | CCK-MP-HAUL-DT159 -FDRSYS-DIFFL-DIFHO | 7400 | 90235 | 15586
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Transmisson Calibration | 2029-05-09 | 2029-05-09 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298739 | 09.05.2029 | 4500 | CCK-MP-HAUL-DT161 -TRNSYS-TRANS | 7400 | 80609 | 12241
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Steering Linkages | 2029-05-09 | 2029-05-09 | 15 hrs | FY29 | 28 | 90028568 | B1 | 1000317653 | 09.05.2029 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STLTR | 7400 | 80609 | 24548
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Repl Hub & Spindle RH | 2029-05-09 | 2029-05-10 | 26 hrs | FY29 | 50 | 90026194 | B1 | 1000079195 | 09.05.2029 | 24000 | CCK-MP-SUPP-WC3111-STRUCT-AXLES-HUBRH | 5600 | 51257 | 8333
785D WC | Onsite PM | Haul | Fortescue | WC3111 | WC3111 Replace Transmission Pump | 2029-05-09 | 2029-05-09 | 6 hrs | FY29 | 6 | 90003991 | B2 | 1000079183 | 09.05.2029 | 10000 | CCK-MP-SUPP-WC3111-TRNSYS-TRPMP-TMCPP | 5600 | 51257 | 8333
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 25000hr Ground Fault Test | 2029-05-09 | 2029-05-09 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226122 | 09.05.2029 | 25000 | CCK-MP-HAUL-DT761 -ELCTHV
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Steering Hyd Oil Cooler | 2029-05-09 | 2029-05-09 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107006 | 09.05.2029 | 15000 | CCK-MP-HAUL-DT151 -STRSYS-STOCO | 7400 | 84253 | 9530
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Overhaul Accumulator Brake LHF | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026410 | 10.05.2029 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-BACCM-FRLFT | 7400 | 86656 | 31134
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Overhaul Accumulator Brake RHF | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026411 | 10.05.2029 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-BACCM-FRRGT | 7400 | 86656 | 60096
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Overhaul Accumulator Brake Rear | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000026412 | 10.05.2029 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-BACCM-BACCR | 7400 | 86656 | 31134
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Ovhl Accumulator Steering Front | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026422 | 10.05.2029 | 24000 | CCK-MP-HAUL-DT150 -STRSYS-STACC-SACCF | 7400 | 86608 | 60048
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Ovhl Accumulator Steering Middle | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026423 | 10.05.2029 | 24000 | CCK-MP-HAUL-DT150 -STRSYS-STACC-SACCM | 7400 | 86608 | 60048
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Ovhl Accumulator Steering Rear | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000026424 | 10.05.2029 | 24000 | CCK-MP-HAUL-DT150 -STRSYS-STACC-SACCR | 7400 | 86608 | 60048
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Replace Auto Lube Pump | 2029-05-10 | 2029-05-10 | 2 hrs | FY29 | 2 | 90011565 | B1 | 1000098087 | 10.05.2029 | 9000 | CCK-MP-SUPP-WC220 -GRSYST-ALBPP | 4300 | 58137 | 5434
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Cyl Hoist LH | 2029-05-10 | 2029-05-10 | 17 hrs | FY29 | 33 | 90011357 | B1 | 1000094504 | 10.05.2029 | 25000 | CCK-MP-HAUL-DT755 -HYDSYS-HOCYL-HCYLL | 6800 | 84587 | 6271
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Transmisson Calibration | 2029-05-10 | 2029-05-10 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298729 | 10.05.2029 | 4500 | CCK-MP-HAUL-DT148 -TRNSYS-TRANS | 7400 | 85451 | 10451
793F | Onsite PM | Haul | Fortescue | DT127 | DT127 Repl Pump Brake Cooling | 2029-05-12 | 2029-05-12 | 9 hrs | FY29 | 17 | 90002379 | B1 | 1000025050 | 12.05.2029 | 24000 | CCK-MP-HAUL-DT127 -BRKSYS-HYFPP | 7400 | 83059 | 3455
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Pump Hoist | 2029-05-12 | 2029-05-12 | 11.5 hrs | FY29 | 12 | 90011355 | B1 | 1000094555 | 12.05.2029 | 25000 | CCK-MP-HAUL-DT756 -HYDSYS-HOPMP | 6800 | 78754 | 5846
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Spiders Pump Drive Shaft | 2029-05-12 | 2029-05-12 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000023584 | 12.05.2029 | 18000 | CCK-MP-HAUL-DT054 -ENGINE-PMPDR-DRSHT | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Transmission | 2029-05-12 | 2029-05-13 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000271867 | 12.05.2029 | 18000 | CCK-MP-HAUL-DT054 -TRNSYS-TRANS | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Transmission Oil Cooler | 2029-05-12 | 2029-05-12 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000082841 | 12.05.2029 | 18000 | CCK-MP-HAUL-DT054 -TRNSYS-TROLC | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Repl Differential | 2029-05-12 | 2029-05-13 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000023592 | 12.05.2029 | 18000 | CCK-MP-HAUL-DT054 -FDRSYS-DIFFL | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Replace Trans TCon System Hoses | 2029-05-12 | 2029-05-13 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090061 | 12.05.2029 | 18000 | CCK-MP-HAUL-DT054 -TRNSYS-TRANS-TRNHO | 7400 | 88111 | 15675
793F | Onsite PM | Haul | Fortescue | DT054 | DT054 Replace Hoses Differential System | 2029-05-12 | 2029-05-12 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090062 | 12.05.2029 | 18000 | CCK-MP-HAUL-DT054 -FDRSYS-DIFFL-DIFHO | 7400 | 88111 | 15675
777G SV | Onsite PM | Haul | Fortescue | SV221 | SV221 Initial Engine Valve Set | 2029-05-13 | 2029-05-13 | 12 hrs | FY29 | 24 | 90015644 | B1 | 1000269900 | 13.05.2029 | 250 | CCK-MP-SUPP-SV221 -ENGINE | 5100 | 64374 | 4253
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Brake Accumulator Rear | 2029-05-13 | 2029-05-13 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000095232 | 13.05.2029 | 25000 | CCK-MP-HAUL-DT769 -BRKSYS-BRACC-BACCR | 6800 | 80508 | 56570
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Steering HMU | 2029-05-13 | 2029-05-13 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095238 | 13.05.2029 | 25000 | CCK-MP-HAUL-DT769 -STRSYS-STHMU | 6800 | 80508 | 31195
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Accumulator Hyd Steer Front | 2029-05-13 | 2029-05-13 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000095241 | 13.05.2029 | 25000 | CCK-MP-HAUL-DT769 -STRSYS-STACC-SACCF | 6800 | 80508 | 31198
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Accumulator Hyd Steering Rear | 2029-05-13 | 2029-05-13 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000095242 | 13.05.2029 | 25000 | CCK-MP-HAUL-DT769 -STRSYS-STACC-SACCR | 6800 | 80508 | 31198
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Engine Midlife Complete | 2029-05-13 | 2029-05-14 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000155954 | 13.05.2029 | 12000 | CCK-MP-HAUL-DT126 -ENGINE | 7400 | 88657 | 88657
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Motor Lube Axle Hoses | 2029-05-13 | 2029-05-13 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000271992 | 13.05.2029 | 12000 | CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-HYM01 | 7400 | 88657 | 25780
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Service Air Conditioner 12M | 2029-05-14 | 2029-05-15 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174186 | 14.05.2029 | 12 Monthly | CCK-MP-HAUL-DT161 -STRUCT-CABIN-AIRCN | 7400 | 80609 | 1574
930E | Onsite PM | Haul | Fortescue | DT758 | DT758 Repl Accumulator Hyd Steering Rear | 2029-05-14 | 2029-05-14 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000094659 | 14.05.2029 | 25000 | CCK-MP-HAUL-DT758 -STRSYS-STACC-SACCR | 6800 | 85895 | 6162
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Transmisson Calibration | 2029-05-14 | 2029-05-14 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298736 | 14.05.2029 | 4500 | CCK-MP-HAUL-DT158 -TRNSYS-TRANS | 7400 | 85964 | 11104
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Steering HMU | 2029-05-15 | 2029-05-15 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095185 | 15.05.2029 | 25000 | CCK-MP-HAUL-DT768 -STRSYS-STHMU | 6800 | 79837 | 30916
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Transmisson Calibration | 2029-05-16 | 2029-05-16 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298672 | 16.05.2029 | 4500 | CCK-MP-HAUL-DT094 -TRNSYS-TRANS | 7400 | 88788 | 5404
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Transmission | 2029-05-16 | 2029-05-17 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272345 | 16.05.2029 | 18000 | CCK-MP-HAUL-DT150 -TRNSYS-TRANS | 7400 | 86608 | 14649
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Drive Shaft Transmission | 2029-05-16 | 2029-05-16 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154979 | 16.05.2029 | 18000 | CCK-MP-HAUL-DT150 -FDRSYS-DRSHT | 7400 | 86656 | 14622
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Brake Oil Cooler Rear | 2029-05-16 | 2029-05-16 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000083438 | 16.05.2029 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-BROCO-BROCR | 7400 | 86656 | 3064
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Axle Lube Hyd Pump | 2029-05-16 | 2029-05-16 | 4 hrs | FY29 | 4 | 90010102 | B1 | 1000083527 | 16.05.2029 | 24000 | CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYPUM | 7400 | 90235 | 26756
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Brake Cooling System Hoses | 2029-05-16 | 2029-05-17 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000083536 | 16.05.2029 | 24000 | CCK-MP-HAUL-DT159 -BRKSYS-BRHLF-CBRHO | 7400 | 90235 | 55505
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Accumulator Hyd Steer Front | 2029-05-16 | 2029-05-16 | 7.5 hrs | FY29 | 11.5 | 90011352 | B1 | 1000095082 | 16.05.2029 | 25000 | CCK-MP-HAUL-DT766 -STRSYS-STACC-SACCF | 6800 | 78074 | 7137
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Accumulator Hyd Steering Rear | 2029-05-16 | 2029-05-16 | 7.5 hrs | FY29 | 11.5 | 90011353 | B1 | 1000095083 | 16.05.2029 | 25000 | CCK-MP-HAUL-DT766 -STRSYS-STACC-SACCR | 6800 | 78074 | 7137
930E | Onsite PM | Haul | Fortescue | DT768 | DT768 Repl Hyd Pump Steering & Brake | 2029-05-16 | 2029-05-17 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204748 | 16.05.2029 | 12000 | CCK-MP-HAUL-DT768 -STRSYS-STPMP | 6800 | 79837 | 4916
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Repl Auto Lube Pump | 2029-05-16 | 2029-05-16 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285796 | 16.05.2029 | 8000 | CCK-MP-HAUL-DT158 -GRSYST-ALBPP | 7400 | 85964 | 11104
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Transmisson Calibration | 2029-05-17 | 2029-05-17 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298665 | 17.05.2029 | 4500 | CCK-MP-HAUL-DT057 -TRNSYS-TRANS | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT095 | DT095 250hr Initial Valve Set | 2029-05-17 | 2029-05-17 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000155928 | 17.05.2029 | 250 | CCK-MP-HAUL-DT095 -ENGINE | 7400 | 88921 | 28299
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Service Air Conditioner 12M | 2029-05-17 | 2029-05-18 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174178 | 17.05.2029 | 12 Monthly | CCK-MP-HAUL-DT149 -STRUCT-CABIN-AIRCN | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Tyre Sense Battery | 2029-05-17 | 2029-05-17 | 2 hrs | FY29 | 2 | 90017022 | B1 | 1000153161 | 17.05.2029 | 24 Monthly | CCK-MP-HAUL-DT149 -MANGMT-TYRSN
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Transmisson Calibration | 2029-05-17 | 2029-05-17 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298677 | 17.05.2029 | 4500 | CCK-MP-HAUL-DT126 -TRNSYS-TRANS | 7400 | 88657 | 2432
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Adjust Engine Valve Set | 2029-05-18 | 2029-05-18 | 12 hrs | FY29 | 24 | 90015645 | B1 | 1000269773 | 18.05.2029 | 4500 | CCK-MP-SUPP-SV220 -ENGINE | 5100 | 58303 | 11037
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Engine Midlife complete | 2029-05-18 | 2029-05-20 | 58 hrs | FY29 | 70 | 90015646 | B1 | 1000269777 | 18.05.2029 | 9000 | CCK-MP-SUPP-SV220 -ENGINE | 5100 | 58303 | 11037
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Overhaul Airconditioner | 2029-05-18 | 2029-05-19 | 24 hrs | FY29 | 24 | 90011566 | B2 | 1000269775 | 18.05.2029 | 9000 | CCK-MP-SUPP-SV220 -STRUCT-CABIN-AIRCN | 5100 | 58259 | 16547
793F | Onsite PM | Haul | Fortescue | DT086 | DT086 Repl AOC Fan Motor Rear | 2029-05-19 | 2029-05-19 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000024037 | 19.05.2029 | 12000 | CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-HYM02 | 7400 | 86846 | 3219
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Adjuster Slack Brake Front | 2029-05-19 | 2029-05-19 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000272694 | 19.05.2029 | 20000 | CCK-MP-SUPP-PM0001-BRKSYS-SLACK-SLACF | 3400 | 48287 | 9867
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Repl Adjuster Slack Brake Rear | 2029-05-19 | 2029-05-19 | 4 hrs | FY29 | 4 | 90002382 | B1 | 1000272695 | 19.05.2029 | 20000 | CCK-MP-SUPP-PM0001-BRKSYS-SLACK-SLACR | 3400 | 48287 | 9867
793F | Onsite PM | Haul | Fortescue | DT223 | DT223 250hr Initial Valve Set | 2029-05-20 | 2029-05-20 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156096 | 20.05.2029 | 250 | CCK-MP-HAUL-DT223 -ENGINE | 7400 | 54920 | 3706
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Engine Cat C175-16 | 2029-05-20 | 2029-05-23 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000161146 | 20.05.2029 | 24000 | CCK-MP-HAUL-DT153 -ENGINE | 7400 | 84181 | 51293
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Engine Midlife Complete | 2029-05-20 | 2029-05-21 | 40 hrs | FY29 | 62 | 90015886 | B1 | 1000156056 | 20.05.2029 | 12000 | CCK-MP-HAUL-DT157 -ENGINE | 7400 | 83041 | 15053
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Repl Pump Hoist & Pump Brake Chrg | 2029-05-20 | 2029-05-20 | 6 hrs | FY29 | 6 | 90037880 | B1 | 1000379766 | 20.05.2029 | 18000 | CCK-MP-SUPP-WC221 -HYDSYS-HOPMP | 4000 | 56923 | 7326
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Steering Brake Pump Compensator | 2029-05-20 | 2029-05-20 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204773 | 20.05.2029 | 6000 | CCK-MP-HAUL-DT769 -STRSYS-STPMP | 6800 | 80508 | 15397
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Spider Trans Driveshaft | 2029-05-21 | 2029-05-21 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000154984 | 21.05.2029 | 6000 | CCK-MP-HAUL-DT155 -FDRSYS-DRSHT-UNVSL | 7400 | 81407 | 10226
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Repl Auto Lube Pump | 2029-05-21 | 2029-05-21 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285804 | 21.05.2029 | 8000 | CCK-MP-HAUL-DT5255-GRSYST-ALBPP | 7400 | 87580 | 3331
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Hyd Pump Steering & Brake | 2029-05-21 | 2029-05-22 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204434 | 21.05.2029 | 12000 | CCK-MP-HAUL-DT754 -STRSYS-STPMP | 6800 | 83256 | 5013
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Repl Transmission Oil Cooler | 2029-05-22 | 2029-05-22 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000082955 | 22.05.2029 | 18000 | CCK-MP-HAUL-DT090 -TRNSYS-TROLC | 7400 | 81670 | 15228
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Service Air Conditioner 12M | 2029-05-22 | 2029-05-23 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174118 | 22.05.2029 | 12 Monthly | CCK-MP-HAUL-DT091 -STRUCT-CABIN-AIRCN | 7400 | 83859 | 23814
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Steering RH | 2029-05-22 | 2029-05-22 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000094339 | 22.05.2029 | 15000 | CCK-MP-HAUL-DT752 -STRSYS-STRCY-STCYR | 6800 | 80681 | 11115
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Auto Lube Pump | 2029-05-22 | 2029-05-22 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094454 | 22.05.2029 | 8000 | CCK-MP-HAUL-DT754 -GRSYST-ALBPP | 6800 | 83256 | 4996
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 25000hr Ground Fault Test | 2029-05-22 | 2029-05-22 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226101 | 22.05.2029 | 25000 | CCK-MP-HAUL-DT756 -ELCTHV
930E | Onsite PM | Haul | Fortescue | DT767 | DT767 Repl Hyd Pump Steering & Brake | 2029-05-22 | 2029-05-23 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204747 | 22.05.2029 | 12000 | CCK-MP-HAUL-DT767 -STRSYS-STPMP | 6800 | 74312 | 4545
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Drive Line Axle LH | 2029-05-23 | 2029-05-23 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124627 | 23.05.2029 | 24000 | CCK-MP-HAUL-DT159 -FDRSYS-DRLAX-AXLLH | 7400 | 90235 | 3442
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Drive Line Axle RH | 2029-05-23 | 2029-05-23 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124628 | 23.05.2029 | 24000 | CCK-MP-HAUL-DT159 -FDRSYS-DRLAX-AXLRH | 7400 | 90235 | 26732
930E | Onsite PM | Haul | Fortescue | DT761 | DT761 Steering Brake Pump Compensator | 2029-05-23 | 2029-05-23 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204765 | 23.05.2029 | 6000 | CCK-MP-HAUL-DT761 -STRSYS-STPMP | 6800 | 78336 | 10559
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl AOC Fan Motor Rear | 2029-05-23 | 2029-05-23 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000026277 | 23.05.2029 | 12000 | CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYM02 | 7400 | 85452 | 18024
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Drive Line Axle RH | 2029-05-23 | 2029-05-23 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124614 | 23.05.2029 | 24000 | CCK-MP-HAUL-DT148 -FDRSYS-DRLAX-AXLRH | 7400 | 85451 | 3245
793F | Onsite PM | Haul | Fortescue | DT5255 | DT5255 Service Air Conditioner 12M | 2029-05-24 | 2029-05-25 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174192 | 24.05.2029 | 12 Monthly | CCK-MP-HAUL-DT5255-STRUCT-CABIN-AIRCN | 7400 | 87580 | 87580
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Spiders Pump Drive Shaft | 2029-05-24 | 2029-05-24 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000026199 | 24.05.2029 | 18000 | CCK-MP-HAUL-DT147 -ENGINE-PMPDR-DRSHT | 7400 | 84708 | 16832
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Engine Module | 2029-05-25 | 2029-05-29 | 102 hrs | FY29 | 226 | 90011318 | B1 | 1000095314 | 25.05.2029 | 25000 | CCK-MP-HAUL-DT771 -ENGINE | 6800 | 84423 | 5826
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Replace Brake Cooling Hoses | 2029-05-25 | 2029-05-25 | 8.5 hrs | FY29 | 14.5 | 90011344 | B1 | 1000223891 | 25.05.2029 | 25000 | CCK-MP-HAUL-DT771 -BRKSYS-BRHLF | 6800 | 84423 | 5826
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Cyl Hoist LH | 2029-05-25 | 2029-05-25 | 17 hrs | FY29 | 33 | 90011357 | B1 | 1000095352 | 25.05.2029 | 25000 | CCK-MP-HAUL-DT771 -HYDSYS-HOCYL-HCYLL | 6800 | 84423 | 4986
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Cyl Hoist RH | 2029-05-25 | 2029-05-25 | 17 hrs | FY29 | 33 | 90011358 | B1 | 1000095353 | 25.05.2029 | 25000 | CCK-MP-HAUL-DT771 -HYDSYS-HOCYL-HCYLR | 6800 | 84423 | 4986
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Repl Brake Cooling System Hoses | 2029-05-25 | 2029-05-26 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000091457 | 25.05.2029 | 24000 | CCK-MP-HAUL-DT148 -BRKSYS-BRHLF-CBRHO | 7400 | 85451 | 27203
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Motor Brake Oil Cooling | 2029-05-25 | 2029-05-25 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000026481 | 25.05.2029 | 24000 | CCK-MP-HAUL-DT151 -BRKSYS-BROCO-HYMO1 | 7400 | 84301 | 3168
793F | Onsite PM | Haul | Fortescue | DT151 | DT151 Repl Steering HMU | 2029-05-25 | 2029-05-25 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000026485 | 25.05.2029 | 24000 | CCK-MP-HAUL-DT151 -STRSYS-STHMU | 7400 | 84253 | 28327
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Suspension LHF | 2029-05-25 | 2029-05-27 | 43 hrs | FY29 | 84 | 90002408 | B1 | 1000067641 | 25.05.2029 | 28000 | CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYLF | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Suspension LHR | 2029-05-25 | 2029-05-26 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000027103 | 25.05.2029 | 28000 | CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYLR | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Cyl Suspension RHR | 2029-05-25 | 2029-05-26 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000027104 | 25.05.2029 | 28000 | CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYRR | 7400 | 85085 | 7211
793F | Onsite PM | Haul | Fortescue | DT157 | DT157 Repl Differential | 2029-05-26 | 2029-05-27 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000026867 | 26.05.2029 | 18000 | CCK-MP-HAUL-DT157 -FDRSYS-DIFFL | 7400 | 83041 | 15134
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Brake Manifold | 2029-05-26 | 2029-05-26 | 13.5 hrs | FY29 | 13.5 | 90029265 | B1 | 1000292153 | 26.05.2029 | 25000 | CCK-MP-HAUL-DT759 -BRKSYS-BRVLV | 6800 | 79716 | 2497
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Brake Oil Cooler Front | 2029-05-27 | 2029-05-27 | 13 hrs | FY29 | 13 | 90010109 | B1 | 1000082983 | 27.05.2029 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-BROCO-BROCF | 7400 | 88788 | 3009
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Brake Oil Cooler Rear | 2029-05-27 | 2029-05-27 | 13 hrs | FY29 | 13 | 90010108 | B1 | 1000082982 | 27.05.2029 | 24000 | CCK-MP-HAUL-DT094 -BRKSYS-BROCO-BROCR | 7400 | 88788 | 3009
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Replace Steering System Hoses | 2029-05-27 | 2029-05-29 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000083425 | 27.05.2029 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STHLF-STRHO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Steering Hyd Oil Cooler | 2029-05-27 | 2029-05-27 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107027 | 27.05.2029 | 15000 | CCK-MP-HAUL-DT149 -STRSYS-STOCO | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT149 | DT149 Repl Steering Bell Crank & Links | 2029-05-27 | 2029-05-28 | 20 hrs | FY29 | 36 | 90028566 | B1 | 1000317636 | 27.05.2029 | 30000 | CCK-MP-HAUL-DT149 -STRSYS-STLTR-STLAC | 7400 | 86975 | 9207
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Drive Line Axle LH | 2029-05-28 | 2029-05-28 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124318 | 28.05.2029 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-DRLAX-AXLLH | 7400 | 84374 | 26984
793F | Onsite PM | Haul | Fortescue | DT082 | DT082 Repl Drive Line Axle RH | 2029-05-28 | 2029-05-28 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124319 | 28.05.2029 | 24000 | CCK-MP-HAUL-DT082 -FDRSYS-DRLAX-AXLRH | 7400 | 84374 | 26984
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Overhaul Aux Control Cabinet | 2029-05-28 | 2029-05-29 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292532 | 28.05.2029 | 50000 | CCK-MP-HAUL-DT774 -ELCTLV-AUCAB | 6800 | 81047 | 28490
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Electrical Harness | 2029-05-29 | 2029-06-01 | 72 hrs | FY29 | 144 | 90021026 | B1 | 1000221295 | 29.05.2029 | 50000 | CCK-MP-HAUL-DT763 -ELCTLV-HARNS | 6800 | 74143 | 30934
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Repl Cyl Steering LH | 2029-05-29 | 2029-05-29 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000095451 | 29.05.2029 | 15000 | CCK-MP-HAUL-DT773 -STRSYS-STRCY-STCYL | 6800 | 75884 | 10573
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Spider Trans Driveshaft | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000167376 | 30.05.2029 | 6000 | CCK-MP-HAUL-DT5318-FDRSYS-DRSHT-UNVSL | 7400 | 45240 | 9085
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Cyl Suspension RHF | 2029-05-31 | 2029-06-02 | 43 hrs | FY29 | 84 | 90002408 | B2 | 1000067391 | 31.05.2029 | 28000 | CCK-MP-HAUL-DT055 -STRUCT-SUSPN-SCYRF | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Cyl Suspension LHR | 2029-05-31 | 2029-06-01 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000023692 | 31.05.2029 | 28000 | CCK-MP-HAUL-DT055 -STRUCT-SUSPN-SCYLR | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Cyl Suspension RHR | 2029-05-31 | 2029-06-01 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000023693 | 31.05.2029 | 28000 | CCK-MP-HAUL-DT055 -STRUCT-SUSPN-SCYRR | 7400 | 84122 | 7096
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Radiator Fan Hoses | 2029-05-31 | 2029-05-31 | 11 hrs | FY29 | 11 | 90031073 | B1 | 1000307481 | 31.05.2029 | 12000 | CCK-MP-HAUL-DT088 -ENGINE-COSYS-RADTR | 7400 | 89037 | 36530
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Transmission | 2029-05-31 | 2029-06-01 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272301 | 31.05.2029 | 18000 | CCK-MP-HAUL-DT088 -TRNSYS-TRANS | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Transmission Oil Cooler | 2029-05-31 | 2029-05-31 | 12 hrs | FY29 | 12 | 90010097 | B1 | 1000082917 | 31.05.2029 | 18000 | CCK-MP-HAUL-DT088 -TRNSYS-TROLC | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl Motor Lube Axle Hoses | 2029-05-31 | 2029-05-31 | 4 hrs | FY29 | 4 | 90026944 | B1 | 1000271956 | 31.05.2029 | 12000 | CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM01 | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Repl AOC Fan Motor Rear | 2029-05-31 | 2029-05-31 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000024163 | 31.05.2029 | 12000 | CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM02 | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT088 | DT088 Replace Trans TCon System Hoses | 2029-05-31 | 2029-06-01 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090073 | 31.05.2029 | 18000 | CCK-MP-HAUL-DT088 -TRNSYS-TRANS-TRNHO | 7400 | 89037 | 14711
793F | Onsite PM | Haul | Fortescue | DT5314 | DT5314 Repl Spider Trans Driveshaft | 2029-05-31 | 2029-05-31 | 6 hrs | FY29 | 12 | 90017211 | B1 | 1000167056 | 31.05.2029 | 6000 | CCK-MP-HAUL-DT5314-FDRSYS-DRSHT-UNVSL | 7400 | 45898 | 950
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Engine Midlife complete | 2029-05-31 | 2029-06-02 | 58 hrs | FY29 | 70 | 90015767 | B1 | 1000269916 | 31.05.2029 | 9000 | CCK-MP-SUPP-WC220 -ENGINE | 4300 | 58137 | 14252
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Adjust Engine Valve Set | 2029-05-31 | 2029-05-31 | 12 hrs | FY29 | 24 | 90015766 | B1 | 1000269913 | 31.05.2029 | 4500 | CCK-MP-SUPP-WC220 -ENGINE | 4300 | 58137 | 14252
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Overhaul Airconditioner | 2029-05-31 | 2029-06-01 | 24 hrs | FY29 | 24 | 90011566 | B2 | 1000269914 | 31.05.2029 | 9000 | CCK-MP-SUPP-WC220 -STRUCT-CABIN-AIRCN | 4300 | 58137 | 18617
793F | Onsite PM | Haul | Fortescue | DT126 | DT126 Repl Wheel Group Front LH | 2029-05-31 | 2029-06-01 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157137 | 31.05.2029 | 24000 | CCK-MP-HAUL-DT126 -STRUCT-AXLES-HUBLH | 7400 | 88657 | 3048
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 250hr Initial Valve Set | 2029-06-01 | 2029-06-01 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000161154 | 01.06.2029 | 250 | CCK-MP-HAUL-DT153 -ENGINE | 7400 | 84181 | 51293
793F | Onsite PM | Haul | Fortescue | DT148 | DT148 Service Air Conditioner 12M | 2029-06-01 | 2029-06-02 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174177 | 01.06.2029 | 12 Monthly | CCK-MP-HAUL-DT148 -STRUCT-CABIN-AIRCN | 7400 | 85451 | 18023
793F | Onsite PM | Haul | Fortescue | PM0001 | PM0001 Air Conditioner 12M-Service | 2029-06-02 | 2029-06-03 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000272732 | 02.06.2029 | 12 Monthly | CCK-MP-SUPP-PM0001-STRUCT-CABIN-AIRCN | 3400 | 48287 | 48287
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Hub & Spindle RH | 2029-06-02 | 2029-06-03 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000094618 | 02.06.2029 | 18000 | CCK-MP-HAUL-DT757 -STRUCT-AXLES-HUBRH | 6800 | 80700 | 16936
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Repl Cyl Suspension RHF | 2029-06-02 | 2029-06-04 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000094620 | 02.06.2029 | 18000 | CCK-MP-HAUL-DT757 -STRUCT-SUSPN-SCYRF | 6800 | 80700 | 16936
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Front Wheel Bearings LH | 2029-06-02 | 2029-06-03 | 23 hrs | FY29 | 44 | 90017284 | B1 | 1000157158 | 02.06.2029 | 16000 | CCK-MP-HAUL-DT147 -STRUCT-AXLES-FWBLH | 7400 | 84659 | 12913
793F | Onsite PM | Haul | Fortescue | DT147 | DT147 Repl Front Wheel Bearings RH | 2029-06-02 | 2029-06-03 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157246 | 02.06.2029 | 16000 | CCK-MP-HAUL-DT147 -STRUCT-AXLES-FWBRH | 7400 | 84659 | 700
793F | Onsite PM | Haul | Fortescue | DT158 | DT158 Replace Trans TCon System Hoses | 2029-06-02 | 2029-06-03 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000091553 | 02.06.2029 | 18000 | CCK-MP-HAUL-DT158 -TRNSYS-TRANS-TRNHO | 7400 | 85964 | 33728
793F | Onsite PM | Haul | Fortescue | DT090 | DT090 Transmisson Calibration | 2029-06-03 | 2029-06-03 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298670 | 03.06.2029 | 4500 | CCK-MP-HAUL-DT090 -TRNSYS-TRANS | 7400 | 81670 | 5994
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Auto Lube Pump | 2029-06-03 | 2029-06-03 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285786 | 03.06.2029 | 8000 | CCK-MP-HAUL-DT143 -GRSYST-ALBPP | 7400 | 88225 | 11934
793F | Onsite PM | Haul | Fortescue | DT5316 | DT5316 Replace Hoses Differential System | 2029-06-04 | 2029-06-04 | 5 hrs | FY29 | 5 | 90010101 | B3 | 1000167198 | 04.06.2029 | 18000 | CCK-MP-HAUL-DT5316-FDRSYS-DIFFL-DIFHO | 7400 | 45108 | 45108
930E | Onsite PM | Haul | Fortescue | DT774 | DT774 Repl Hyd Pump Steering & Brake | 2029-06-04 | 2029-06-05 | 28 hrs | FY29 | 38 | 90019919 | B1 | 1000204754 | 04.06.2029 | 12000 | CCK-MP-HAUL-DT774 -STRSYS-STPMP | 6800 | 81047 | 4812
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Replace Hoses Differential System | 2029-06-04 | 2029-06-04 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090110 | 04.06.2029 | 18000 | CCK-MP-HAUL-DT130 -FDRSYS-DIFFL-DIFHO | 7400 | 85185 | 33489
793F | Onsite PM | Haul | Fortescue | DT136 | DT136 Repl Auto Lube Pump | 2029-06-04 | 2029-06-04 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285781 | 04.06.2029 | 8000 | CCK-MP-HAUL-DT136 -GRSYST-ALBPP | 7400 | 87780 | 11471
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Torque Converter | 2029-06-05 | 2029-06-06 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000026401 | 05.06.2029 | 24000 | CCK-MP-HAUL-DT150 -TRNSYS-TRQUE | 7400 | 86608 | 872
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Replace Hoses Hoist System | 2029-06-05 | 2029-06-06 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000083434 | 05.06.2029 | 24000 | CCK-MP-HAUL-DT150 -HYDSYS-HDHLF-HSTHO | 7400 | 86608 | 0
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Drive Line Axle LH | 2029-06-05 | 2029-06-05 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124617 | 05.06.2029 | 24000 | CCK-MP-HAUL-DT150 -FDRSYS-DRLAX-AXLLH | 7400 | 86608 | 872
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Drive Line Axle RH | 2029-06-05 | 2029-06-05 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124618 | 05.06.2029 | 24000 | CCK-MP-HAUL-DT150 -FDRSYS-DRLAX-AXLRH | 7400 | 86608 | 872
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Brake Accumulator Front | 2029-06-05 | 2029-06-05 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000094966 | 05.06.2029 | 25000 | CCK-MP-HAUL-DT764 -BRKSYS-BRACC-BACCF | 6800 | 75315 | 5411
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Repl Brake Accumulator Rear | 2029-06-05 | 2029-06-05 | 7 hrs | FY29 | 11 | 90011339 | B1 | 1000094967 | 05.06.2029 | 25000 | CCK-MP-HAUL-DT764 -BRKSYS-BRACC-BACCR | 6800 | 75315 | 5411
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Brake Dual Relay Valves | 2029-06-05 | 2029-06-05 | 8.5 hrs | FY29 | 8.5 | 90021353 | B1 | 1000223772 | 05.06.2029 | 25000 | CCK-MP-HAUL-DT772 -BRKSYS-BRVRL | 6800 | 85256 | 31893
793F | Onsite PM | Haul | Fortescue | DT130 | DT130 Repl Differential | 2029-06-05 | 2029-06-06 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000025231 | 05.06.2029 | 18000 | CCK-MP-HAUL-DT130 -FDRSYS-DIFFL | 7400 | 85185 | 15131
793F | Onsite PM | Haul | Fortescue | DT056 | DT056 Repl Pump Drive | 2029-06-06 | 2029-06-07 | 20 hrs | FY29 | 39 | 90002365 | B1 | 1000023709 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT056 -ENGINE-PMPDR | 7400 | 84421 | 867
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Cylinder Steering LH | 2029-06-06 | 2029-06-06 | 10 hrs | FY29 | 10 | 90011555 | B1 | 1000093059 | 06.06.2029 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STRCY-STCYL | 5100 | 58259 | 2762
777G SV | Onsite PM | Haul | Fortescue | SV220 | SV220 Replace Cylinder Steering RH | 2029-06-06 | 2029-06-06 | 6 hrs | FY29 | 12 | 90011556 | B1 | 1000093060 | 06.06.2029 | 18000 | CCK-MP-SUPP-SV220 -STRSYS-STRCY-STCYR | 5100 | 58259 | 2762
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Engine Cat C175-16 | 2029-06-06 | 2029-06-09 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000155997 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -ENGINE | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Radiator Engine Cooling | 2029-06-06 | 2029-06-07 | 39 hrs | FY29 | 62 | 90031072 | B1 | 1000307514 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -ENGINE-COSYS-RADTR | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Torque Converter | 2029-06-06 | 2029-06-07 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000025873 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -TRNSYS-TRQUE | 7400 | 87027 | 3010
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Motor Lube Axle Rear & Hoses | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 8 | 90026943 | B1 | 1000272007 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYM01 | 7400 | 87027 | 18705
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl AOC Fan Motor Rear | 2029-06-06 | 2029-06-06 | 6 hrs | FY29 | 6 | 90002376 | B1 | 1000025881 | 06.06.2029 | 12000 | CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYM02 | 7400 | 87027 | 13221
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Overhaul Accumulator Brake LHF | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025882 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BACCM-FRLFT | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Overhaul Accumulator Brake RHF | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025883 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BACCM-FRRGT | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Overhaul Accumulator Brake Rear | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 11 | 90002378 | B1 | 1000025884 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BACCM-BACCR | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Overhaul Valve Control Brake | 2029-06-06 | 2029-06-07 | 20 hrs | FY29 | 20 | 90002380 | B2 | 1000025886 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BRVLV | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Motor Brake Oil Cooling | 2029-06-06 | 2029-06-06 | 3 hrs | FY29 | 3 | 90002381 | B1 | 1000025887 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BROCO-HYMO1 | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Hyd Pump Steering Main & Fan | 2029-06-06 | 2029-06-06 | 17 hrs | FY29 | 17 | 90002383 | B1 | 1000025890 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -STRSYS-STPMP | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Steering HMU | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 8 | 90002384 | B1 | 1000025891 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -STRSYS-STHMU | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Ovhl Accumulator Steering Front | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025894 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -STRSYS-STACC-SACCF | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Ovhl Accumulator Steering Middle | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025895 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -STRSYS-STACC-SACCM | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Ovhl Accumulator Steering Rear | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 12 | 90002386 | B1 | 1000025896 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -STRSYS-STACC-SACCR | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Pump Hoist & Brake | 2029-06-06 | 2029-06-06 | 9 hrs | FY29 | 15 | 90002388 | B1 | 1000025899 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -HYDSYS-HOPMP | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Auto Lube Pump | 2029-06-06 | 2029-06-06 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285785 | 06.06.2029 | 8000 | CCK-MP-HAUL-DT142 -GRSYST-ALBPP | 7400 | 87027 | 11970
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Rear Axle Linkages | 2029-06-06 | 2029-06-08 | 57 hrs | FY29 | 113 | 90002396 | B1 | 1000025908 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -STRUCT-CHASS-AXLIK | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Wheel Group Front LH | 2029-06-06 | 2029-06-07 | 28 hrs | FY29 | 54 | 90017286 | B1 | 1000157153 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -STRUCT-AXLES-HUBLH | 7400 | 87027 | 13221
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Replace Hoses Hoist System | 2029-06-06 | 2029-06-07 | 20 hrs | FY29 | 40 | 90010105 | B1 | 1000083320 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -HYDSYS-HDHLF-HSTHO | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Replace Brake System Hoses | 2029-06-06 | 2029-06-08 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000083326 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BRHLF-BRHOS | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Brake Cooling System Hoses | 2029-06-06 | 2029-06-07 | 30 hrs | FY29 | 60 | 90010130 | B1 | 1000083327 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -BRKSYS-BRHLF-CBRHO | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Drive Line Axle LH | 2029-06-06 | 2029-06-06 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124605 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -FDRSYS-DRLAX-AXLLH | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 Repl Drive Line Axle RH | 2029-06-06 | 2029-06-06 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124606 | 06.06.2029 | 24000 | CCK-MP-HAUL-DT142 -FDRSYS-DRLAX-AXLRH | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 Repl Engine Cat C175-16 | 2029-06-07 | 2029-06-10 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000155919 | 07.06.2029 | 24000 | CCK-MP-HAUL-DT094 -ENGINE | 7400 | 88788 | 50851
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Spiders Pump Drive Shaft | 2029-06-07 | 2029-06-07 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000026397 | 07.06.2029 | 18000 | CCK-MP-HAUL-DT150 -ENGINE-PMPDR-DRSHT | 7400 | 86656 | 14622
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Hub & Spindle LH | 2029-06-07 | 2029-06-08 | 24 hrs | FY29 | 48 | 90004020 | B2 | 1000079259 | 07.06.2029 | 24000 | CCK-MP-SUPP-WC3112-STRUCT-AXLES-HUBLH | 5600 | 52240 | 8166
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Hub & Spindle RH | 2029-06-07 | 2029-06-08 | 26 hrs | FY29 | 50 | 90026194 | B1 | 1000079260 | 07.06.2029 | 24000 | CCK-MP-SUPP-WC3112-STRUCT-AXLES-HUBRH | 5600 | 52240 | 8166
793F | Onsite PM | Haul | Fortescue | DT057 | DT057 Repl Front Wheel Bearings RH | 2029-06-08 | 2029-06-09 | 23 hrs | FY29 | 44 | 90017285 | B1 | 1000157198 | 08.06.2029 | 16000 | CCK-MP-HAUL-DT057 -STRUCT-AXLES-FWBRH | 7400 | 91273 | 10672
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Transmisson Calibration | 2029-06-08 | 2029-06-08 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298722 | 08.06.2029 | 4500 | CCK-MP-HAUL-DT137 -TRNSYS-TRANS | 7400 | 84196 | 1006
930E | Onsite PM | Haul | Fortescue | DT757 | DT757 Overhaul Aux Control Cabinet | 2029-06-08 | 2029-06-09 | 27.5 hrs | FY29 | 51.5 | 90029299 | B1 | 1000292334 | 08.06.2029 | 50000 | CCK-MP-HAUL-DT757 -ELCTLV-AUCAB | 6800 | 80700 | 25834
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Repl Steering Hyd Oil Cooler | 2029-06-09 | 2029-06-09 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000167362 | 09.06.2029 | 15000 | CCK-MP-HAUL-DT5318-STRSYS-STOCO | 7400 | 45240 | 21163
793F | Onsite PM | Haul | Fortescue | DT5318 | DT5318 Replace Steering System Hoses | 2029-06-09 | 2029-06-11 | 54 hrs | FY29 | 106 | 90010133 | B2 | 1000167356 | 09.06.2029 | 15000 | CCK-MP-HAUL-DT5318-STRSYS-STHLF-STRHO | 7400 | 45240 | 21163
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Adjust Engine Valve Set | 2029-06-09 | 2029-06-09 | 12 hrs | FY29 | 24 | 90015645 | B1 | 1000201197 | 09.06.2029 | 4500 | CCK-MP-SUPP-SV4104-ENGINE | 5100 | 23504 | 7410
777G SV | Onsite PM | Haul | Fortescue | SV4104 | SV4104 Service Airconditioner | 2029-06-09 | 2029-06-10 | 24 hrs | FY29 | 24 | 90018538 | B2 | 1000229148 | 09.06.2029 | 4500 | CCK-MP-SUPP-SV4104-STRUCT-CABIN-AIRCN | 5100 | 23504 | 7410
777F WC | Onsite PM | Haul | Fortescue | WC008 | WC008 Repl Sec Str Pump & Motor | 2029-06-10 | 2029-06-10 | 6 hrs | FY29 | 6 | 90000264 | B2 | 1000018404 | 10.06.2029 | 15000 | CCK-MP-SUPP-WC008 -STRSYS-STEMG-SESPP | 3500 | 51417 | 4731
777G WC | Onsite PM | Haul | Fortescue | WC220 | WC220 Replace Operator Seat | 2029-06-11 | 2029-06-11 | 3 hrs | FY29 | 6 | 90011567 | B1 | 1000098089 | 11.06.2029 | 6000 | CCK-MP-SUPP-WC220 -STRUCT-CABIN-SEATS | 4300 | 58137 | 5120
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Suspension RHR | 2029-06-11 | 2029-06-12 | 32 hrs | FY29 | 50 | 90011368 | B1 | 1000094357 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT752 -STRUCT-SUSPN-SCYRR | 6800 | 80681 | 5737
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Electrical Harness | 2029-06-11 | 2029-06-14 | 72 hrs | FY29 | 144 | 90021026 | B1 | 1000221323 | 11.06.2029 | 50000 | CCK-MP-HAUL-DT771 -ELCTLV-HARNS | 6800 | 84423 | 30436
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Valve Retard & Brake Treadle | 2029-06-11 | 2029-06-11 | 5.5 hrs | FY29 | 5.5 | 90011345 | B1 | 1000095340 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT771 -BRKSYS-BRVTR | 6800 | 84423 | 30436
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Replace Brake Cabinet Hoses | 2029-06-11 | 2029-06-12 | 32.5 hrs | FY29 | 62.5 | 90015041 | B1 | 1000126518 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT771 -BRKSYS-BRHLF | 6800 | 84423 | 5826
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Valve Flow Amplifier | 2029-06-11 | 2029-06-11 | 13 hrs | FY29 | 13.5 | 90011348 | B1 | 1000095343 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT771 -STRSYS-STVLV | 6800 | 84423 | 30436
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Steering HMU | 2029-06-11 | 2029-06-11 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000095344 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT771 -STRSYS-STHMU | 6800 | 84423 | 30436
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Drive Shaft | 2029-06-11 | 2029-06-11 | 2 hrs | FY29 | 2 | 90011359 | B1 | 1000095354 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT771 -HYDSYS-DRSHT | 6800 | 84423 | 30436
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Replace Pump Module Hosing | 2029-06-11 | 2029-06-11 | 15 hrs | FY29 | 27 | 90021389 | B1 | 1000223915 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT771 -HYDSYS-HDHLF | 6800 | 84423 | 30436
930E | Onsite PM | Haul | Fortescue | DT771 | DT771 Repl Brake Dual Relay Valves | 2029-06-11 | 2029-06-11 | 8.5 hrs | FY29 | 8.5 | 90021353 | B1 | 1000223771 | 11.06.2029 | 25000 | CCK-MP-HAUL-DT771 -BRKSYS-BRVRL | 6800 | 84423 | 30436
793F | Onsite PM | Haul | Fortescue | DT143 | DT143 Repl Spiders Pump Drive Shaft | 2029-06-11 | 2029-06-11 | 4 hrs | FY29 | 4 | 90002366 | B1 | 1000025935 | 11.06.2029 | 18000 | CCK-MP-HAUL-DT143 -ENGINE-PMPDR-DRSHT | 7400 | 88225 | 14631
930E | Onsite PM | Haul | Fortescue | DT752 | DT752 Repl Cyl Suspension LHR | 2029-06-12 | 2029-06-13 | 32 hrs | FY29 | 50 | 90011367 | B1 | 1000094356 | 12.06.2029 | 25000 | CCK-MP-HAUL-DT752 -STRUCT-SUSPN-SCYLR | 6800 | 80681 | 5737
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Steering LH | 2029-06-13 | 2029-06-13 | 10 hrs | FY29 | 16 | 90011350 | B1 | 1000094285 | 13.06.2029 | 15000 | CCK-MP-HAUL-DT751 -STRSYS-STRCY-STCYL | 6800 | 86211 | 11291
930E | Onsite PM | Haul | Fortescue | DT751 | DT751 Repl Cyl Steering RH | 2029-06-13 | 2029-06-13 | 9 hrs | FY29 | 15 | 90011351 | B1 | 1000094286 | 13.06.2029 | 15000 | CCK-MP-HAUL-DT751 -STRSYS-STRCY-STCYR | 6800 | 86211 | 11291
793F | Onsite PM | Haul | Fortescue | DT221 | DT221 Transmisson Calibration | 2029-06-14 | 2029-06-14 | 4 hrs | FY29 | 8 | 90029836 | B1 | 1000298740 | 14.06.2029 | 4500 | CCK-MP-HAUL-DT221 -TRNSYS-TRANS | 7400 | 57237 | 10386
785D WC | Onsite PM | Haul | Fortescue | WC3112 | WC3112 Repl Steering Link & Arm Rebush | 2029-06-14 | 2029-06-14 | 14 hrs | FY29 | 22 | 90004007 | B2 | 1000079271 | 14.06.2029 | 15000 | CCK-MP-SUPP-WC3112-STRSYS-STLTR | 5600 | 52240 | 14062
930E | Onsite PM | Haul | Fortescue | DT764 | DT764 Steering Brake Pump Compensator | 2029-06-15 | 2029-06-15 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204768 | 15.06.2029 | 6000 | CCK-MP-HAUL-DT764 -STRSYS-STPMP | 6800 | 75315 | 9695
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Hoist LH | 2029-06-15 | 2029-06-15 | 17 hrs | FY29 | 33 | 90015130 | B1 | 1000128579 | 15.06.2029 | 28000 | CCK-MP-HAUL-DT140 -HYDSYS-HOCYL-HCYLL | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Hoist RH | 2029-06-15 | 2029-06-15 | 17 hrs | FY29 | 33 | 90015131 | B1 | 1000128580 | 15.06.2029 | 28000 | CCK-MP-HAUL-DT140 -HYDSYS-HOCYL-HCYLR | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Suspension LHR | 2029-06-15 | 2029-06-16 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000025784 | 15.06.2029 | 28000 | CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYLR | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT140 | DT140 Repl Cyl Suspension RHR | 2029-06-15 | 2029-06-16 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000025785 | 15.06.2029 | 28000 | CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYRR | 7400 | 86767 | 6817
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Transmission | 2029-06-15 | 2029-06-16 | 22 hrs | FY29 | 39 | 90026996 | B2 | 1000272313 | 15.06.2029 | 18000 | CCK-MP-HAUL-DT099 -TRNSYS-TRANS | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Drive Shaft Transmission | 2029-06-15 | 2029-06-15 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154947 | 15.06.2029 | 18000 | CCK-MP-HAUL-DT099 -FDRSYS-DRSHT | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT091 | DT091 Repl Steering Linkages | 2029-06-16 | 2029-06-16 | 15 hrs | FY29 | 28 | 90028568 | B1 | 1000317597 | 16.06.2029 | 15000 | CCK-MP-HAUL-DT091 -STRSYS-STLTR | 7400 | 83859 | 5241
930E | Onsite PM | Haul | Fortescue | DT770 | DT770 25000hr Ground Fault Test | 2029-06-16 | 2029-06-16 | 1 hr | FY29 | 1 | 90021455 | B2 | 1000226131 | 16.06.2029 | 25000 | CCK-MP-HAUL-DT770 -ELCTHV
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 Repl Engine Cat C175-16 | 2029-06-17 | 2029-06-20 | 84 hrs | FY29 | 137 | 90015881 | B1 | 1000156063 | 17.06.2029 | 24000 | CCK-MP-HAUL-DT159 -ENGINE | 7400 | 90235 | 26732
930E | Onsite PM | Haul | Fortescue | DT760 | DT760 Repl Steering HMU | 2029-06-17 | 2029-06-17 | 9.3 hrs | FY29 | 9.3 | 90011349 | B1 | 1000094761 | 17.06.2029 | 25000 | CCK-MP-HAUL-DT760 -STRSYS-STHMU | 6800 | 80390 | 30811
930E | Onsite PM | Haul | Fortescue | DT773 | DT773 Steering Brake Pump Compensator | 2029-06-17 | 2029-06-17 | 6 hrs | FY29 | 7 | 90019922 | B1 | 1000204777 | 17.06.2029 | 6000 | CCK-MP-HAUL-DT773 -STRSYS-STPMP | 6800 | 75884 | 10573
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Service Air Conditioner 12M | 2029-06-18 | 2029-06-19 | 18 hrs | FY29 | 18 | 90018230 | B1 | 1000174194 | 18.06.2029 | 12 Monthly | CCK-MP-HAUL-DT5317-STRUCT-CABIN-AIRCN | 7400 | 45576 | 32701
793F | Onsite PM | Haul | Fortescue | DT142 | DT142 250hr Initial Valve Set | 2029-06-18 | 2029-06-18 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156000 | 18.06.2029 | 250 | CCK-MP-HAUL-DT142 -ENGINE | 7400 | 87027 | 27424
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Repl Cyl Suspension RHR | 2029-06-19 | 2029-06-20 | 22 hrs | FY29 | 39 | 90002409 | B2 | 1000026444 | 19.06.2029 | 28000 | CCK-MP-HAUL-DT150 -STRUCT-SUSPN-SCYRR | 7400 | 86608 | 6426
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Hub & Spindle LH | 2029-06-19 | 2029-06-20 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000094458 | 19.06.2029 | 18000 | CCK-MP-HAUL-DT754 -STRUCT-AXLES-HUBLH | 6800 | 83256 | 1995
930E | Onsite PM | Haul | Fortescue | DT754 | DT754 Repl Cyl Suspension LHF | 2029-06-19 | 2029-06-21 | 60 hrs | FY29 | 112 | 90011365 | B1 | 1000094460 | 19.06.2029 | 18000 | CCK-MP-HAUL-DT754 -STRUCT-SUSPN-SCYLF | 6800 | 83256 | 1995
930E | Onsite PM | Haul | Fortescue | DT763 | DT763 Repl Auto Lube Pump | 2029-06-19 | 2029-06-19 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094931 | 19.06.2029 | 8000 | CCK-MP-HAUL-DT763 -GRSYST-ALBPP | 6800 | 74143 | 14657
930E | Onsite PM | Haul | Fortescue | DT769 | DT769 Repl Brake Accumulator Front | 2029-06-19 | 2029-06-19 | 7 hrs | FY29 | 11 | 90011338 | B1 | 1000095231 | 19.06.2029 | 25000 | CCK-MP-HAUL-DT769 -BRKSYS-BRACC-BACCF | 6800 | 80508 | 30511
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Repl Differential | 2029-06-19 | 2029-06-20 | 38 hrs | FY29 | 66 | 90014504 | B1 | 1000024853 | 19.06.2029 | 18000 | CCK-MP-HAUL-DT099 -FDRSYS-DIFFL | 7400 | 87442 | 14781
793F | Onsite PM | Haul | Fortescue | DT055 | DT055 Repl Auto Lube Pump | 2029-06-20 | 2029-06-20 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285623 | 20.06.2029 | 8000 | CCK-MP-HAUL-DT055 -GRSYST-ALBPP | 7400 | 84122 | 15901
793F | Onsite PM | Haul | Fortescue | DT094 | DT094 250hr Initial Valve Set | 2029-06-20 | 2029-06-20 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000155922 | 20.06.2029 | 250 | CCK-MP-HAUL-DT094 -ENGINE | 7400 | 88788 | 50851
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Torque Converter | 2029-06-20 | 2029-06-21 | 27 hrs | FY29 | 53 | 90002369 | B1 | 1000027127 | 20.06.2029 | 24000 | CCK-MP-HAUL-DT161 -TRNSYS-TRQUE | 7400 | 80609 | 2649
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Hub & Spindle LH | 2029-06-20 | 2029-06-21 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000095094 | 20.06.2029 | 18000 | CCK-MP-HAUL-DT766 -STRUCT-AXLES-HUBLH | 6800 | 78074 | 17489
930E | Onsite PM | Haul | Fortescue | DT766 | DT766 Repl Cyl Suspension LHF | 2029-06-20 | 2029-06-22 | 60 hrs | FY29 | 112 | 90011365 | B1 | 1000095096 | 20.06.2029 | 18000 | CCK-MP-HAUL-DT766 -STRUCT-SUSPN-SCYLF | 6800 | 78074 | 17489
930E | Onsite PM | Haul | Fortescue | DT765 | DT765 Repl Auto Lube Pump | 2029-06-21 | 2029-06-21 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000095037 | 21.06.2029 | 8000 | CCK-MP-HAUL-DT765 -GRSYST-ALBPP | 6800 | 78429 | 13600
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Trans TCon System Hoses | 2029-06-21 | 2029-06-22 | 20 hrs | FY29 | 20 | 90010099 | B1 | 1000090094 | 21.06.2029 | 18000 | CCK-MP-HAUL-DT099 -TRNSYS-TRANS-TRNHO | 7400 | 87442 | 14731
793F | Onsite PM | Haul | Fortescue | DT099 | DT099 Replace Hoses Differential System | 2029-06-21 | 2029-06-21 | 5 hrs | FY29 | 5 | 90010101 | B1 | 1000090095 | 21.06.2029 | 18000 | CCK-MP-HAUL-DT099 -FDRSYS-DIFFL-DIFHO | 7400 | 87442 | 14729
793F | Onsite PM | Haul | Fortescue | DT137 | DT137 Repl Auto Lube Pump | 2029-06-22 | 2029-06-22 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285782 | 22.06.2029 | 8000 | CCK-MP-HAUL-DT137 -GRSYST-ALBPP | 7400 | 84196 | 9757
793F | Onsite PM | Haul | Fortescue | DT5313 | DT5313 Repl Cyl Suspension LHR | 2029-06-22 | 2029-06-23 | 22 hrs | FY29 | 39 | 90002409 | B1 | 1000166944 | 22.06.2029 | 28000 | CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYLR | 7400 | 44693 | 6676
930E | Onsite PM | Haul | Fortescue | DT755 | DT755 Repl Auto Lube Pump | 2029-06-22 | 2029-06-22 | 2.5 hrs | FY29 | 2.5 | 90011370 | B1 | 1000094507 | 22.06.2029 | 8000 | CCK-MP-HAUL-DT755 -GRSYST-ALBPP | 6800 | 84587 | 13093
793F | Onsite PM | Haul | Fortescue | DT155 | DT155 Repl Steering Hyd Oil Cooler | 2029-06-23 | 2029-06-23 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000107010 | 23.06.2029 | 15000 | CCK-MP-HAUL-DT155 -STRSYS-STOCO | 7400 | 81407 | 8629
793F | Onsite PM | Haul | Fortescue | DT160 | DT160 Repl Drive Shaft Transmission | 2029-06-24 | 2029-06-24 | 8 hrs | FY29 | 16 | 90017195 | B1 | 1000154993 | 24.06.2029 | 18000 | CCK-MP-HAUL-DT160 -FDRSYS-DRSHT | 7400 | 85085 | 18309
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Repl Cyl Steering RH | 2029-06-25 | 2029-06-25 | 12 hrs | FY29 | 20 | 90002385 | B2 | 1000027147 | 25.06.2029 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STRCY-STCYR | 7400 | 80609 | 8581
793F | Onsite PM | Haul | Fortescue | DT161 | DT161 Replace Steering System Hoses | 2029-06-25 | 2029-06-27 | 54 hrs | FY29 | 106 | 90010133 | B1 | 1000091592 | 25.06.2029 | 15000 | CCK-MP-HAUL-DT161 -STRSYS-STHLF-STRHO | 7400 | 80609 | 8581
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Repl Steering Hyd Oil Cooler | 2029-06-25 | 2029-06-25 | 9 hrs | FY29 | 9 | 90012866 | B2 | 1000167282 | 25.06.2029 | 15000 | CCK-MP-HAUL-DT5317-STRSYS-STOCO | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT5317 | DT5317 Replace Steering System Hoses | 2029-06-25 | 2029-06-27 | 54 hrs | FY29 | 106 | 90010133 | B2 | 1000167276 | 25.06.2029 | 15000 | CCK-MP-HAUL-DT5317-STRSYS-STHLF-STRHO | 7400 | 45576 | 8696
793F | Onsite PM | Haul | Fortescue | DT150 | DT150 Replace Brake System Hoses | 2029-06-27 | 2029-06-29 | 46 hrs | FY29 | 90 | 90010129 | B4 | 1000083440 | 27.06.2029 | 24000 | CCK-MP-HAUL-DT150 -BRKSYS-BRHLF-BRHOS | 7400 | 86608 | 49940
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Grid Box Blower Motor LH | 2029-06-27 | 2029-06-27 | 10 hrs | FY29 | 10 | 90011331 | B1 | 1000094535 | 27.06.2029 | 25000 | CCK-MP-HAUL-DT756 -ELCTHV-HVGBM-GBMLH | 6800 | 78754 | 4998
930E | Onsite PM | Haul | Fortescue | DT756 | DT756 Repl Grid Box Blower Motor RH | 2029-06-27 | 2029-06-27 | 10 hrs | FY29 | 10 | 90011332 | B1 | 1000094536 | 27.06.2029 | 25000 | CCK-MP-HAUL-DT756 -ELCTHV-HVGBM-GBMRH | 6800 | 78754 | 4998
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Wheel Motor LH | 2029-06-28 | 2029-06-30 | 45.5 hrs | FY29 | 83.5 | 90011335 | B1 | 1000094698 | 28.06.2029 | 25000 | CCK-MP-HAUL-DT759 -FDRSYS-WLMTR-WHMLH | 6800 | 79716 | 5816
930E | Onsite PM | Haul | Fortescue | DT759 | DT759 Repl Wheel Motor Oil LH | 2029-06-28 | 2029-06-28 | 1 hr | FY29 | 1 | 90033606 | B1 | 1000338214 | 28.06.2029 | 25000 | CCK-MP-HAUL-DT759 -FDRSYS-WLMTR-WHMLH | 6800 | 79716 | 5816
793F | Onsite PM | Haul | Fortescue | DT159 | DT159 250hr Initial Valve Set | 2029-06-29 | 2029-06-29 | 8 hrs | FY29 | 16 | 90015884 | B1 | 1000156066 | 29.06.2029 | 250 | CCK-MP-HAUL-DT159 -ENGINE | 7400 | 90235 | 26732
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Hub & Spindle LH | 2029-06-29 | 2029-06-30 | 32 hrs | FY29 | 60 | 90011363 | B1 | 1000095412 | 29.06.2029 | 18000 | CCK-MP-HAUL-DT772 -STRUCT-AXLES-HUBLH | 6800 | 85256 | 18043
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Hub & Spindle RH | 2029-06-29 | 2029-06-30 | 32 hrs | FY29 | 60 | 90011364 | B1 | 1000095413 | 29.06.2029 | 18000 | CCK-MP-HAUL-DT772 -STRUCT-AXLES-HUBRH | 6800 | 85256 | 2281
930E | Onsite PM | Haul | Fortescue | DT772 | DT772 Repl Cyl Suspension RHF | 2029-06-29 | 2029-07-01 | 60 hrs | FY29 | 112 | 90011366 | B1 | 1000095415 | 29.06.2029 | 18000 | CCK-MP-HAUL-DT772 -STRUCT-SUSPN-SCYRF | 6800 | 85256 | 2281
793F | Onsite PM | Haul | Fortescue | DT097 | DT097 Repl Auto Lube Pump | 2029-06-30 | 2029-06-30 | 3 hrs | FY29 | 3 | 90002391 | B1 | 1000285634 | 30.06.2029 | 8000 | CCK-MP-HAUL-DT097 -GRSYST-ALBPP | 7400 | 83804 | 2994
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Drive Line Axle LH | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 4 | 90014919 | B1 | 1000124619 | 30.06.2029 | 24000 | CCK-MP-HAUL-DT153 -FDRSYS-DRLAX-AXLLH | 7400 | 84230 | 2424
793F | Onsite PM | Haul | Fortescue | DT153 | DT153 Repl Drive Line Axle RH | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 4 | 90014943 | B1 | 1000124620 | 30.06.2029 | 24000 | CCK-MP-HAUL-DT153 -FDRSYS-DRLAX-AXLRH | 7400 | 84230 | 2424
777G WC | Onsite PM | Haul | Fortescue | WC221 | WC221 Replace Cylinder Steering LH | 2029-06-30 | 2029-06-30 | 10 hrs | FY29 | 10 | 90011555 | B1 | 1000098131 | 30.06.2029 | 18000 | CCK-MP-SUPP-WC221 -STRSYS-STRCY-STCYL | 4000 | 56923 | 6023

## Measurement Points
Functional Location | Description of measuring point | Meas/TotCountrRdg _ | Counter reading | Annual estimate
CCK-MP-LOAD-WL7162-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 25874 | 16226 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BRACC | Brake Accumulator RH | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BRACC | Brake Accumulator LH | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-TRTRF | Transmission Transfer Case | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-TRQUE | Torque Converter | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-TRPMP | Transmission Pump | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-TROLC | Transmission Oil Cooler | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-TRANS | Transmission | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-PMPDR-TORCP | Torsional Coupling | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-PMPDR-RRPDR | Gearbox Pump Drive Rear | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-PMPDR-FRPDR | Gearbox Pump Drive Front | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT05 | Drive Shaft Rear Pump Dr-Front Pump Dr | 25829 | 2192 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT04 | Drive Shaft Park Brake to Front Diff | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT03 | Drive Shaft Transfer GBox to Park Brake | 25829 | 2088 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 25829 | 9393 | 6100
CCK-MP-LOAD-WL7162-TRNSYS-DRSHT-SHT01 | Drive Shaft Torque Conv to Transmission | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CHASS-LINKR | Bucket Linkage Right | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CHASS-LINKL | Bucket Linkage Left | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CHASS-LIARM | Chassis Lift Arm | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CHASS-BELCR | Chassis Bell Crank | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CHASS-BELCL | Chassis Bell Crank | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CHASS-ARTIC | Chassis Articulation | 25829 | 14610 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CABIN-SEATS | Cabin Operators Seat | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-STRUCT-BUCKT | Bucket | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STVLV | Steering Valve | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STRCY-STCYR | Steering Cylinder RH | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STRCY-STCYL | Steering Cylinder LH | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STPMP-STP03 | Steering Pump Secondary | 25829 | 2443 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STPMP-STP02 | Steering & Brake Oil Cooler Pump | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STPMP-STP01 | Steering Pump | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STOCO | Steering Oil Cooler | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STNVS | Steering Neutralizer Valves | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STIPV | Steering STIC Control | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-STRSYS-STHLF-STRHO | Steering System Hoses | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-PACCM | Hydraulic Pilot Accumulator | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP06 | Hyd Pump Fan Axle & Imp Oil Cooler | 25829 | 2192 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP05 | Pump Hyd Pilot & Axle Cooling | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP04 | Pump Axle Oil Cooler Rear | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP03 | Pump Axle Oil Cooler Front | 25829 | 2192 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP02 | Hydraulic Pump Implement RH | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYP01 | Hydraulic Pump Implement LH | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 25829 | 2268 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDMT-HYM03 | Hyd Motor Axle Cooler Rear | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDMT-HYM02 | Hyd Motor Axle Cooler Front | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDMT-HYM01 | Hyd Motor Fan Axle Oil Cooler Front | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HYDMT-HDCFM | Fan Motor Cooling Main | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDVLV-MCVVR | Main Control Valve Block RH | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDVLV-MCVVL | Main Control Valve Block LH | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDOCO | Hydraulic Oil Cooler | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-PILHO | Pilot System hoses | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH | 25829 | 10405 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-GRSYST-ALBPP | Grease Auto Lube Pump | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-RRDIF | Rear Differential | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-HDOCA-HYOCR | Oil Cooler Axle Rear | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-HDOCA-HYOCF | Oil Cooler Axle Front | 25829 | 968 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FRDIF | Front Differential | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 25829 | 2192 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 25829 | 2192 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-INTEX-TBORF | Turbocharger R/H Front | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-INTEX-MUFF | Muffler | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-INTEX-AFTER | Engine Aftercooler | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-FUSYS-FULTP | Engine Fuel Transfer Pump | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-FUSYS-FUINJ | Engine Fuel Injectors | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-COSYS-WTRPP | Engine Water Pump | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-COSYS-THERM | Engine Thermostats | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-COSYS-RADTR | Engine Radiator | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ENGINE-COSYS-COFAN | Engine Fan Cooling System | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-ENGINE | Engine Assembly | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ELCTLV-START-STMRH | Starter Motor R/H | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ELCTLV-START-STMLH | Starter Motor L/H | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-ELCTLV-CHARG-BATTY | Electrical Batteries | 25829 | 12962 | 6100
CCK-MP-LOAD-WL7162-ELCTLV-CHARG-ALTER | Electrical Alternator 24V | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-SRVBK-SVBRR | Brake Service RH Rear | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-SRVBK-SVBRF | Brake Service RH Front | 25829 | 2192 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-SRVBK-SVBLR | Brake Service LH Rear | 25829 | 2515 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-SRVBK-SVBLF | Brake Service LH Front | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BRPRK | Brake Park Assembly | 25829 | 2179 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BRPMP-BRP01 | Hyd Pump Brake | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BROCC | Brake Oil Cooler | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BRHLF-BRKHO | Brake System Hoses Lines & Fittings | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BRACC-BACCR | Accumulator Rear Service Brake | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162-BRKSYS-BRACC-BACCF | Accumulator Front Service Brake | 25829 | 7473 | 6100
CCK-MP-LOAD-WL7162 | Caterpillar 994K Wheel Loader WL7162 | 25829 | 25829 | 6100
CCK-MP-LOAD-WL7104-PNEUMC-PNHLF | Pneumatic System Hoses & Fittings | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-ENGINE-COSYS-CSHLF | Engine Coolant Hoses | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STRCY-STCYL | Steering Cylinder LH | 26203 | 26203 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-TRTRF | Transmission Transfer Case | 64060 | 4741 | 4000
CCK-MP-LOAD-WL7104-GRSYST-FFGHO | Front Frame - Grease Hoses | 64060 | 8512 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-TRQUE | Torque Converter | 64060 | 13091 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-TRPMP | Pump Transmission Charge | 64060 | 4736 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-TROLC | Transmission Oil Cooler | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 64060 | 7889 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-TRHLF | Trans System Hoses. Lines and Fittings | 64060 | 35189 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-TRANS | Transmission | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 64060 | 9837 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 64060 | 3453 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 64060 | 7889 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 64060 | 7889 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 64060 | 6713 | 4000
CCK-MP-LOAD-WL7104-TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 64060 | 39855 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CHASS-REFRM | Rear Frame | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CHASS-LNKGE | Linkage | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CHASS-LIARM | Lift Arm | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CHASS-FRFRM | Front Frame | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CHASS-ARTIC | Articulation | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CABIN-SEATS | Operators Seat | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CABIN-SBELT | Seat Belt | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CABIN-AIRCN | Air Conditioning System | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRUCT-CABIN | Operators Cabin | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-BUCKT-BWELM | Bucket Wear Elements | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-STRUCT-BUCKT | Bucket | 64060 | 19195 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STVLV | Valve Steering | 64060 | 45225 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STTNK | Stering and brake tank | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STRCY-STCYR | Cylinder Steering RH | 64060 | 8512 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STRCY-STCYL | Cylinder Steering LH | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STPMP-STP04 | Steering Pump Secondary | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STPMP-STP02 | Steering Pump RH | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STPMP-STP01 | Steering Pump LH | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STNVS | Steering Neutralizer Valves | 64060 | 4741 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STIPV | STIC Steering Pilot Valve | 64060 | 9837 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STHLF-STRHO | Steering System Hoses | 64060 | 4741 | 4000
CCK-MP-LOAD-WL7104-STRSYS-STBOC | Steering And Brake Oil Cooler | 64060 | 45225 | 4000
CCK-MP-LOAD-WL7104-PNEUMC-START | Starter Motor Air | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-PNEUMC | Main Airhoses/Relay | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-PACCM | Pilot Accumulator | 64060 | 19195 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 64060 | 3297 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 64060 | 3297 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 64060 | 3297 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 64060 | 3297 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 64060 | 5258 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 64060 | 8938 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDTNK-HYT01 | Hydraulic Tank | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDOCO | Oil Cooler Hydraulic | 64060 | 10963 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-PILHO | Pilot System Hoses | 64060 | 25280 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 64060 | 8512 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 64060 | 5258 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 64060 | 5258 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-GRSYST-GRINJ | Auto Lube Injectors | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-GRSYST-ALBPP | Auto Lube Pump | 64060 | 15309 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-RRDIF | Rear Differential | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FRDIF | Front Differential | 64060 | 14276 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 64060 | 1219 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 64060 | 3817 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 63615 | 6713 | 4000
CCK-MP-LOAD-WL7104-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-LUBSY-OILPP | Oil Pump Engine | 64060 | 39855 | 4000
CCK-MP-LOAD-WL7104-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 64060 | 39855 | 4000
CCK-MP-LOAD-WL7104-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-INTEX-TBORF | Turbocharger RH Front | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-INTEX-EXHST | Exhaust Mufflers | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-ENGINE-INTEX-AFTER | Aftercooler | 64060 | 39855 | 4000
CCK-MP-LOAD-WL7104-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-FUSYS-FUINJ | Fuel Injectors | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-FNHUB | Engine Fan Hub | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-COSYS-WTRPP | Water Pump Engine | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-COSYS-THERM | Thermostats-Regulators | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-COSYS-RADTR | Radiator Coolant | 64060 | 22080 | 6300
CCK-MP-LOAD-WL7104-ENGINE-COSYS-RADTR | Radiator Engine | 64060 | 10963 | 4000
CCK-MP-LOAD-WL7104-ENGINE-COSYS-COFAN | Fan Cooling System | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7104-ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ENGINE-COMPR | Air Compressor | 64060 | 34908 | 4000
CCK-MP-LOAD-WL7104-ENGINE | Engine Assembly Caterpillar 3516B | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ELCTLV-HARNS | Electrical Harness Low Voltage | 64060 | 6713 | 4000
CCK-MP-LOAD-WL7104-ELCTLV-CHARG-ALTER | Alternator 24V RH | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-ELCTLV-CHARG-ALTEL | Alternator 24V LH | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 64060 | 45707 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 64060 | 34908 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 64060 | 45707 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 64060 | 34908 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-BRPRK | Park Brake Assembly | 64060 | 6713 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-BRPMP-BRP01 | Brake Pump | 64060 | 3143 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-BROCC | Brake Oil Cooler | 64060 | 4741 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-BRHLF-BRKHO | Brake System Hoses | 64060 | 8512 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 64060 | 25280 | 4000
CCK-MP-LOAD-WL7104-BRKSYS-BRACC-BACCF | Front Brake Accumulator | 64060 | 25280 | 4000
CCK-MP-LOAD-WL7104 | Caterpillar 994H Wheel Loader WL7104 | 64060 | 64060 | 4000
CCK-MP-LOAD-WL7103-PNEUMC-PNHLF | Pneumatic System Hoses & Fittings | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-ENGINE-COSYS-CSHLF | Engine Cooling Sys Hoses and Fittings | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 33806 | 33806 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 33158 | 3040 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-TRTRF | Transmission Transfer Case | 72865 | 3040 | 6000
CCK-MP-LOAD-WL7103-GRSYST-FFGHO | Front Frame - Grease Hoses | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-TRQUE | Torque Converter | 72865 | 9061 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-TRPMP | Pump Transmission Charge | 72865 | 6666 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-TROLC | Transmission Oil Cooler | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 72865 | 14006 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-TRHLF | Trans System Hoses. Lines and Fittings | 72865 | 45376 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-TRANS | Transmission | 72865 | 11793 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 72865 | 3040 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 72865 | 3040 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 72865 | 5406 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 72865 | 16811 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 72865 | 6385 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 72865 | 3040 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CHASS-REFRM | Rear Frame | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CHASS-LNKGE | Linkage | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CHASS-LIARM | Lift Arm | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CHASS-FRFRM | Front Frame | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CHASS-ARTIC | Articulation | 72865 | 11776 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CABIN-SEATS | Operators Seat | 72865 | 1168 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CABIN-SBELT | Seat Belt | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CABIN-AIRCN | Air Conditioning System | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRUCT-CABIN | Operators Cabin | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRUCT-BUCKT-BWELM | Bucket Wear Elements | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRUCT-BUCKT | Bucket | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STVLV | Valve Steering | 72865 | 48293 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STTNK | Stering and brake tank | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STRCY-STCYR | Cylinder Steering RH | 72865 | 4648 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STRCY-STCYL | Cylinder Steering LH | 72865 | 8691 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP04 | Steering Pump Secondary | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP02 | Steering Pump RH | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STPMP-STP01 | Steering Pump LH | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STNVS | Steering Neutralizer Valves | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STIPV | STIC Steering Pilot Valve | 72865 | 16811 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STHLF-STRHO | Steering System Hoses | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-STRSYS-STBOC | Steering And Brake Oil Cooler | 72865 | 48293 | 6000
CCK-MP-LOAD-WL7103-PNEUMC-START | Starter Motor Air | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 72865 | 30393 | 6000
CCK-MP-LOAD-WL7103-PNEUMC | Main Airhoses/Relay | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-PACCM | Pilot Accumulator | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 72865 | 16811 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 72865 | 3047 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 72865 | 3040 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDTNK-HYT01 | Hydraulic Tank | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDOCO | Oil Cooler Hydraulic | 72865 | 13547 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-PILHO | Pilot System Hoses | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 72865 | 13547 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 72865 | 2579 | 6000
CCK-MP-LOAD-WL7103-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 72865 | 2579 | 6000
CCK-MP-LOAD-WL7103-GRSYST-GRINJ | Auto Lube Injectors | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-GRSYST-ALBPP | Auto Lube Pump | 72865 | 15227 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-RRDIF | Rear Differential | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FRDIF | Front Differential | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 72865 | 12024 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 72865 | 5748 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 72865 | 16267 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 72865 | 30393 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 72865 | 30393 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 72865 | 30393 | 6000
CCK-MP-LOAD-WL7103-FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 72865 | 30393 | 6000
CCK-MP-LOAD-WL7103-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-LUBSY-OILPP | Oil Pump Engine | 72865 | 48293 | 6000
CCK-MP-LOAD-WL7103-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 72865 | 48293 | 6000
CCK-MP-LOAD-WL7103-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 72865 | 841 | 6000
CCK-MP-LOAD-WL7103-ENGINE-INTEX-TBORF | Turbocharger RH Front | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-INTEX-EXHST | Exhaust Mufflers | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-ENGINE-INTEX-AFTER | Aftercooler | 72865 | 48293 | 6000
CCK-MP-LOAD-WL7103-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-FUSYS-FUINJ | Fuel Injectors | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-FNHUB | Engine Fan Hub | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-COSYS-WTRPP | Water Pump Engine | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-COSYS-THERM | Thermostats-Regulators | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-COSYS-RADTR | Radiator Coolant | 72865 | 12069 | 6300
CCK-MP-LOAD-WL7103-ENGINE-COSYS-RADTR | Radiator Engine | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-ENGINE-COSYS-COFAN | Fan Cooling System | 72865 | 72865 | 6000
CCK-MP-LOAD-WL7103-ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ENGINE-COMPR | Air Compressor | 72865 | 48293 | 6000
CCK-MP-LOAD-WL7103-ENGINE | Engine Assembly Caterpillar 3516B | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ELCTLV-HARNS | Electrical Harness Low Voltage | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-ELCTLV-CHARG-ALTER | Alternator 24V RH | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-ELCTLV-CHARG-ALTEL | Alternator 24V LH | 72865 | 2571 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 72865 | 39994 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 72865 | 45376 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 72865 | 39994 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 72865 | 45376 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-BRPRK | Park Brake Assembly | 72865 | 3040 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 72865 | 12306 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-BRPMP-BRP01 | Brake Pump | 72865 | 16267 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-BROCC | Brake Oil Cooler | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-BRHLF-BRKHO | Brake System Hoses | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103-BRKSYS-BRACC-BACCF | Front Brake Accumulator | 72865 | 12069 | 6000
CCK-MP-LOAD-WL7103 | Caterpillar 994H Wheel Loader WL7103 | 72865 | 72865 | 6000
CCK-MP-LOAD-WL269 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 74601 | 11909 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRACC | Brake Accumulator RH | 36389 | 36389 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRACC | Brake Accumulator LH | 36389 | 36389 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-TRTRF | Transmission Transfer Case | 74583 | 8060 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 74583 | 24556 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 74583 | 24556 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 74583 | 24556 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 74583 | 24556 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-TRQUE | WL269 Torque Converter | 74583 | 13004 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-TRPMP | WL269 Transmission Charge Pump | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-TROLC | WL269 Transmission Oil Cooler | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-TRHLF-TRNHO | WL269 Transmission System Hoses | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-TRHLF | WL269 Trans System Hoses, Lines and Fi | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-TRANS | WL269 Transmission | 74583 | 8060 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-PMPDR-RRPDR | WL269 Pump Drive Gearbox Rear | 74583 | 8437 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-PMPDR-FRPDR | WL269 Pump Drive Gearbox Front | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-PMPDR | WL269 Pump Drive Gearboxes | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-UCTRB | WL269 D-Shaft Upper Centre Bearing | 74583 | 8437 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-TORCP | WL269 D-Shaft Torsional Coupling | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT06 | WL269 D-Shaft Front Pump Drive To Cntr | 74583 | 4006 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT05 | WL269 D-Shaft Rear Pump Drive To Cntr B | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT04 | WL269 D-Shaft Cntr Bearing to Front Dif | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT03 | WL269 D-Shaft Transmission to Cntr Bear | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT02 | WL269 D-Shaft Transmission to Rear Diff | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-SHT01 | WL269 D-Shaft T/C to Transmission | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT-LCTRB | WL269 D-Shaft Lower Centre Bearing | 74583 | 36389 | 6000
CCK-MP-LOAD-WL269 -TRNSYS-DRSHT | WL269 Drive Shafts | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -TRNSYS | WL269 Transmission System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-STLAD | WL269 Steps and Ladders | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-PNLGU | WL269 Panels and Guards | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-PLHAN | WL269 Platforms and Handrails | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-ROPSS | WL269 Chassis Rollover Protective Struc | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-REFRM | WL269 Chassis Rear Frame | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-LNKGE | WL269 Chassis Linkage | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-LIARM | WL269 Chassis Lift Arm | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-LEVER | WL269 Chassis Lever | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-FRFRM | WL269 Chassis Front Frame | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-CWEIG | WL269 Chassis Counterweight | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS-ARTIC | WL269 Chassis Articulation | 74583 | 8058 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CHASS | WL269 Chassis | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN-SEATS | WL269 Cabin Operators Seat | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN-SBELT | WL269 Cabin Seat Belt | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN-GLASS | WL269 Cabin Glass | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN-CABPR | WL269 Cabin Pressurisation System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN-CABES | WL269 Cabin Entertainment System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN-CABCO | WL269 Cabin Controls | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN-AIRCN | WL269 Cabin Air Conditioning System | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -STRUCT-CABIN | WL269 Cabin Operators | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT-BUCKT | WL269 Bucket | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRUCT | WL269 Structure | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STVLV | WL269 Steering Valve | 74583 | 5236 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STTNK | WL269 Steering and Brake Oil Tank | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STRCY-STCYR | WL269 Steering Cylinder RH | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STRCY-STCYL | WL269 Steering Cylinder LH | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STRCY | WL269 Steering Cylinder | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP04 | WL269 Steering Pump Secondary | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP03 | WL269 Steering & Brake Oil Cooler Pump | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP02 | WL269 Steering Pump RH | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STPMP-STP01 | WL269 Steering Pump LH | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STPMP | WL269 Steering System Pumps | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STNVS | WL269 Steering Neutralizer Valves | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STIPV | WL269 Steering STIC Pilot Valve | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STHLF-STRHO | WL269 Steering System Hoses | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STHLF | WL269 Steering System Hoses and Fitting | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRSYS-STBOC | WL269 Steering And Brake Oil Cooler | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -STRSYS | WL269 Steering System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -PNEUMC-START | WL269 Pneumatic Starter Motor | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -PNEUMC-PNTNK-AIT03 | WL269 Pneumatic Air Tank Expansion RH | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -PNEUMC-PNTNK-AIT02 | WL269 Pneumatic Tank Expansion LH | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -PNEUMC-PNTNK-AIT01 | WL269 Pneumatic Tank Main Starting | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -PNEUMC-PNTNK | WL269 Pneumatic System Tanks | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -PNEUMC-PNHLF | WL269 Pneumatic System Hoses & Fittings | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -PNEUMC | WL269 Pneumatic System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -MANGMT-UMMMC | WL269 Management Mine Monitoring and Co | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -MANGMT-UMMC | WL269 Management Machine System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -MANGMT-UMENG | WL269 Management Engine System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -MANGMT | WL269 Unit Management | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-PACCM | WL269 Hydraulic Pilot Accumulator | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP04 | WL269 Hydraulic Pump Hydraulic Pilot & | 74583 | 8060 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP03 | WL269 Hydraulic Pump Implement Centre | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP02 | WL269 Hydraulic Pump Implement RH | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HYDPP-HYP01 | WL269 Hydraulic Pump Implement LH | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HYDPP | WL269 Hydraulic Pumps | 74583 | 38890 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDVLV-HYV02 | WL269 Hydraulic Valve Implement Control | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDVLV-HYV01 | WL269 Hydraulic Valve Implement Control | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDVLV | WL269 Hydraulic Valves | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDTNK-HYT03 | WL269 Hydraulic Tank Expansion RH | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDTNK-HYT02 | WL269 Hydraulic Tank Expansion LH | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDTNK-HYT01 | WL269 Hydraulic Tank Main | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDTNK | WL269 Hydraulic Oil Tanks | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDOCO | WL269 Hydraulic Oil Cooler | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-PILHO | WL269 Pilot System Hoses | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDHLF-HYDHO | WL269 Hydraulic System Hoses | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDHLF | WL269 Hydraulic System Hoses & Fittings | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-HCYLR | WL269 Cylinder Hoist RH High Lift | 74583 | 7630 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-HCYLL | WL269 Cylinder Hoist LH High Lift | 74583 | 1701 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-BUCYR | WL269 Cylinder Bucket RH High Lift | 74583 | 8680 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDCYL-BUCYL | WL269 Cylinder Bucket LH High Lift | 74583 | 8459 | 6000
CCK-MP-LOAD-WL269 -HYDSYS-HDCYL | WL269 Hydraulic Cylinders | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -HYDSYS | WL269 Hydraulic System | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -GRSYST-GRTNK | WL269 Grease Resevoir | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -GRSYST-GRINJ | WL269 Grease Injectors | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -GRSYST-ALHLF | WL269 Grease Auto Lube Hoses & Fittings | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -GRSYST-ALELC | WL269 Grease Auto Lube Electrical | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -GRSYST-ALCON | WL269 Grease Auto Lube Controller | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -GRSYST-ALBPP | WL269 Grease Auto Lube Pump | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -GRSYST | WL269 Grease Lubrication System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FRSUPP-FSMAN-EXTIN | WL269 Fire Suppression Hand Held Exting | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FRSUPP-FSMAN | WL269 Fire Suppression Manual | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FRSUPP-FSAUT-FFOAM | WL269 Fire Suppression Foam | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FRSUPP-FSAUT | WL269 Fire Suppression Automatic | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FRSUPP-FSALM | WL269 Fire Suppression System Alarm | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FRSUPP | WL269 Fire Suppression System | 74583 | 24556 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-WHTYR-POS04 | WL269 Tyre Position 4 | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-WHTYR-POS03 | WL269 Tyre Position 3 | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-WHTYR-POS02 | WL269 Tyre Position 2 | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-WHTYR-POS01 | WL269 Tyre Position 1 | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-WHTYR | WL269 Wheels & Tyres and Rims | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-RRDIF-TRNON | WL269 Rear Axle Housing Trunnion | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-RRDIF | WL269 Rear Differential | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FRDIF | WL269 Front Differential | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR04 | WL269 Final Drive Position 4 | 74583 | 13398 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR03 | WL269 Final Drive Position 3 | 74596 | 9638 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR02 | WL269 Final Drive Position 2 | 74583 | 8142 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE-FDR01 | WL269 Final Drive Position 1 | 74583 | 5000 | 6000
CCK-MP-LOAD-WL269 -FDRSYS-FDRVE | WL269 Final Drives | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -FDRSYS | WL269 Final Drive System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-LUBSY-PREPP | WL269 Engine Prelube Oil Pump | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-LUBSY-OILPP | WL269 Engine Oil Pump | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-LUBSY-ENOLC | WL269 Engine Oil Cooler | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-LUBSY | WL269 Engine Lubrication System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX-TBORR | WL269 Engine Turbocharger RH Rear | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX-TBORF | WL269 Engine Turbocharger RH Front | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX-TBOLR | WL269 Engine Turbocharger LH Rear | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX-TBOLF | WL269 Engine Turbocharger LH Front | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX-EXHST | WL269 Engine Exhaust System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX-AIRFL | WL269 Engine Air Filtration System | 74583 | 24556 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX-AFTER | WL269 Engine Aftercooler | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-INTEX | WL269 Engine Intake and Exhaust System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-FUSYS-FULTP | WL269 Engine Fuel Transfer Pump | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-FUSYS-FULTK | WL269 Engine Fuel Tank | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-FUSYS-FULPP | WL269 Engine Fuel Priming Pump | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-FUSYS-FUINJ | WL269 Engine Fuel Injectors | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-FUSYS-FUHLF | WL269 Engine Fuel System Hoses and Fitt | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-FUSYS | WL269 Engine Fuel System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-FNHUB | WL269 Engine Fan Hub | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS-WTRPP | WL269 Engine Water Pump | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS-THERM | WL269 Engine Thermostats-Regulators | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS-RADTR | WL269 Engine Radiator | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS-CSHLF | WL269 Engine Cooling Sys Hoses and Fitt | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS-COFAN | WL269 Engine Fan Cooling System | 74583 | 24556 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS-BELTS | WL269 Engine Belts and Idler Pulleys | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS-ACWEP | WL269 Engine Water Pump Aftercooler | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COSYS | WL269 Engine Cooling System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ENGINE-COMPR | WL269 Air Compressor | 74583 | 16689 | 6000
CCK-MP-LOAD-WL269 -ENGINE | WL269 Engine Assembly Caterpillar 3516B | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ELCTLV-LIGHT | WL269 Electrical Lighting Low Voltage | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ELCTLV-HARNS | WL269 Electrical Harness Low Voltage | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -ELCTLV-CONTL | WL269 Electrical Controls Low Voltage | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ELCTLV-CHARG-BATTY | WL269 Electrical Batteries | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -ELCTLV-CHARG-ALTER | WL269 Electrical Alternator 24V RH | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ELCTLV-CHARG-ALTEL | WL269 Electrical Alternator 24V LH | 74583 | 8436 | 6000
CCK-MP-LOAD-WL269 -ELCTLV-CHARG | WL269 Electrical Charging System Low Vo | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -ELCTLV | WL269 Electrical System Low Voltage 24V | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -COMMUN-RADIO | WL269 Two Way Radio | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -COMMUN-FLMGT | WL269 Fleet Management | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -COMMUN | WL269 Communications | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-SRVBK-SVBRR | WL269 Brake Service RH Rear | 74583 | 61496 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-SRVBK-SVBRF | WL269 Brake Service RH Front | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-SRVBK-SVBLR | WL269 Brake Service LH Rear | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-SRVBK-SVBLF | WL269 Brake Service LH Front | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-SRVBK | WL269 Service Brakes | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRPRK | WL269 Brake Park Assembly | 74561 | 8060 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRPMP-BRP02 | WL269 Brake Cooling Pump | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRPMP-BRP01 | WL269 Brake Pump | 74583 | 8437 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRPMP | WL269 Braking System Pumps | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BROCC | WL269 Brake Oil Cooler | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRHLF-BRKHO | WL269 Brake System Hoses | 74583 | 5623 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRHLF | WL269 Brake System Hoses and Fittings | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRCOT | WL269 Brake Cooling Oil Tank | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRACC-BACCR | WL269 Brake Accumulator Rear | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRACC-BACCF | WL269 Brake Accumulator Front | 74583 | 16942 | 6000
CCK-MP-LOAD-WL269 -BRKSYS-BRACC | WL269 Brake Accumulators | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 -BRKSYS | WL269 Braking System | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 | WL269 Lube & Mechanical Services | 74583 | 74583 | 6000
CCK-MP-LOAD-WL269 | Caterpillar 994H Wheel Loader WL269 | 74583 | 74583 | 6000
CCK-MP-LOAD-WL267 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 74466 | 12680 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRACC | Brake Accumulator RH | 21055 | 21055 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRACC | Brake Accumulator LH | 21055 | 21055 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-TRTRF | Transmission Transfer Case | 74441 | 14588 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-TRQUE | WL267 Torque Converter | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-TRPMP | WL267 Transmission Charge Pump | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-TROLC | WL267 Transmission Oil Cooler | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-TRHLF-TRNHO | WL267 Transmission System Hoses | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-TRHLF | WL267 Trans System Hoses, Lines and Fi | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-TRANS | WL267 Transmission | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-PMPDR-RRPDR | WL267 Pump Drive Gearbox Rear | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-PMPDR-FRPDR | WL267 Pump Drive Gearbox Front | 74441 | 10237 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-PMPDR | WL267 Pump Drive Gearboxes | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-UCTRB | WL267 D-Shaft Upper Centre Bearing | 74441 | 9732 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-TORCP | WL267 D-Shaft Torsional Coupling | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT06 | WL267 D-Shaft Front Pump Drive To Cntr | 74441 | 10237 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT05 | WL267 D-Shaft Rear Pump Drive To Cntr B | 74441 | 10237 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT04 | WL267 D-Shaft Cntr Bearing to Front Dif | 74441 | 9741 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT03 | WL267 D-Shaft Transmission to Cntr Bear | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT02 | WL267 D-Shaft Transmission to Rear Diff | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-SHT01 | WL267 D-Shaft T/C to Transmission | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT-LCTRB | WL267 D-Shaft Lower Centre Bearing | 74441 | 38232 | 6000
CCK-MP-LOAD-WL267 -TRNSYS-DRSHT | WL267 Drive Shafts | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -TRNSYS | WL267 Transmission System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-STLAD | WL267 Steps and Ladders | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-PNLGU | WL267 Panels and Guards | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-PLHAN | WL267 Platforms and Handrails | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-ROPSS | WL267 Chassis Rollover Protective Struc | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-REFRM | WL267 Chassis Rear Frame | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-LNKGE | WL267 Chassis Linkage | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-LIARM | WL267 Chassis Lift Arm | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-LEVER | WL267 Chassis Lever | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-FRFRM | WL267 Chassis Front Frame | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-CWEIG | WL267 Chassis Counterweight | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS-ARTIC | WL267 Chassis Articulation | 74441 | 13352 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CHASS | WL267 Chassis | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN-SEATS | WL267 Cabin Operators Seat | 74441 | 1115 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN-SBELT | WL267 Cabin Seat Belt | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN-GLASS | WL267 Cabin Glass | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN-CABPR | WL267 Cabin Pressurisation System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN-CABES | WL267 Cabin Entertainment System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN-CABCO | WL267 Cabin Controls | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN-AIRCN | WL267 Cabin Air Conditioning System | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -STRUCT-CABIN | WL267 Cabin Operators | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT-BUCKT | WL267 Bucket | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRUCT | WL267 Structure | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STVLV | WL267 Steering Valve | 74441 | 14157 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STTNK | WL267 Steering and Brake Oil Tank | 74441 | 42578 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STRCY-STCYR | WL267 Steering Cylinder RH | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STRCY-STCYL | WL267 Steering Cylinder LH | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STRCY | WL267 Steering Cylinder | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP04 | WL267 Steering Pump Secondary | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP03 | WL267 Steering & Brake Oil Cooler Pump | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP02 | WL267 Steering Pump RH | 74441 | 31558 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STPMP-STP01 | WL267 Steering Pump LH | 74441 | 9741 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STPMP | WL267 Steering System Pumps | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STNVS | WL267 Steering Neutralizer Valves | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STIPV | WL267 Steering STIC Pilot Valve | 74441 | 24025 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STHLF-STRHO | WL267 Steering System Hoses | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STHLF | WL267 Steering System Hoses and Fitting | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRSYS-STBOC | WL267 Steering And Brake Oil Cooler | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -STRSYS | WL267 Steering System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -PNEUMC-START | WL267 Pneumatic Starter Motor | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -PNEUMC-PNTNK-AIT03 | WL267 Pneumatic Air Tank Expansion RH | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -PNEUMC-PNTNK-AIT02 | WL267 Pneumatic Tank Expansion LH | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -PNEUMC-PNTNK-AIT01 | WL267 Pneumatic Tank Main Starting | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -PNEUMC-PNTNK | WL267 Pneumatic System Tanks | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -PNEUMC-PNHLF | WL267 Pneumatic System Hoses & Fittings | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -PNEUMC | WL267 Pneumatic System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -MANGMT-UMMMC | WL267 Management Mine Monitoring and Co | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -MANGMT-UMMC | WL267 Management Machine System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -MANGMT-UMENG | WL267 Management Engine System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -MANGMT | WL267 Unit Management | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-PACCM | WL267 Hydraulic Pilot Accumulator | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP04 | WL267 Hydraulic Pump Hydraulic Pilot & | 74441 | 10738 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP03 | WL267 Hydraulic Pump Implement Centre | 74441 | 10237 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP02 | WL267 Hydraulic Pump Implement RH | 74441 | 10237 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HYDPP-HYP01 | WL267 Hydraulic Pump Implement LH | 74441 | 10237 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HYDPP | WL267 Hydraulic Pumps | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDVLV-HYV02 | WL267 Hydraulic Valve Implement Control | 74441 | 11777 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDVLV-HYV01 | WL267 Hydraulic Valve Implement Control | 74441 | 14181 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDVLV | WL267 Hydraulic Valves | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDTNK-HYT03 | WL267 Hydraulic Tank Expansion RH | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDTNK-HYT02 | WL267 Hydraulic Tank Expansion LH | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDTNK-HYT01 | WL267 Hydraulic Tank Main | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDTNK | WL267 Hydraulic Oil Tanks | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDOCO | WL267 Hydraulic Oil Cooler | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-PILHO | WL267 Pilot System Hoses | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDHLF-HYDHO | WL267 Hydraulic System Hoses | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDHLF | WL267 Hydraulic System Hoses & Fittings | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-HCYLR | WL267 Cylinder Hoist RH High Lift | 74441 | 1831 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-HCYLL | WL267 Cylinder Hoist LH High Lift | 74441 | 1113 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-BUCYR | WL267 Cylinder Bucket RH High Lift | 74441 | 719 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDCYL-BUCYL | WL267 Cylinder Bucket LH High Lift | 74441 | 719 | 6000
CCK-MP-LOAD-WL267 -HYDSYS-HDCYL | WL267 Hydraulic Cylinders | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -HYDSYS | WL267 Hydraulic System | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -GRSYST-GRTNK | WL267 Grease Resevoir | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -GRSYST-GRINJ | WL267 Grease Injectors | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -GRSYST-ALHLF | WL267 Grease Auto Lube Hoses & Fittings | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -GRSYST-ALELC | WL267 Grease Auto Lube Electrical | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -GRSYST-ALCON | WL267 Grease Auto Lube Controller | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -GRSYST-ALBPP | WL267 Grease Auto Lube Pump | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -GRSYST | WL267 Grease Lubrication System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FRSUPP-FSMAN-EXTIN | WL267 Fire Suppression Hand Held Exting | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FRSUPP-FSMAN | WL267 Fire Suppression Manual | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FRSUPP-FSAUT-FFOAM | WL267 Fire Suppression Foam | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FRSUPP-FSAUT | WL267 Fire Suppression Automatic | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FRSUPP-FSALM | WL267 Fire Suppression System Alarm | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FRSUPP | WL267 Fire Suppression System | 74441 | 27231 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-WHTYR-POS04 | WL267 Tyre Position 4 | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-WHTYR-POS03 | WL267 Tyre Position 3 | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-WHTYR-POS02 | WL267 Tyre Position 2 | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-WHTYR-POS01 | WL267 Tyre Position 1 | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-WHTYR | WL267 Wheels & Tyres and Rims | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-RRDIF-TRNON | WL267 Rear Axle Housing Trunnion | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-RRDIF | WL267 Rear Differential | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FRDIF | WL267 Front Differential | 74441 | 10738 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR04 | WL267 Final Drive Position 4 | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR03 | WL267 Final Drive Position 3 | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR02 | WL267 Final Drive Position 2 | 74441 | 15269 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE-FDR01 | WL267 Final Drive Position 1 | 74441 | 10738 | 6000
CCK-MP-LOAD-WL267 -FDRSYS-FDRVE | WL267 Final Drives | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -FDRSYS | WL267 Final Drive System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-LUBSY-PREPP | WL267 Engine Prelube Oil Pump | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-LUBSY-OILPP | WL267 Engine Oil Pump | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-LUBSY-ENOLC | WL267 Engine Oil Cooler | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-LUBSY | WL267 Engine Lubrication System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX-TBORR | WL267 Engine Turbocharger RH Rear | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX-TBORF | WL267 Engine Turbocharger RH Front | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX-TBOLR | WL267 Engine Turbocharger LH Rear | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX-TBOLF | WL267 Engine Turbocharger LH Front | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX-EXHST | WL267 Engine Exhaust System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX-AIRFL | WL267 Engine Air Filtration System | 74441 | 27231 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX-AFTER | WL267 Engine Aftercooler | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-INTEX | WL267 Engine Intake and Exhaust System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-FUSYS-FULTP | WL267 Engine Fuel Transfer Pump | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-FUSYS-FULTK | WL267 Engine Fuel Tank | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-FUSYS-FULPP | WL267 Engine Fuel Priming Pump | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-FUSYS-FUINJ | WL267 Engine Fuel Injectors | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-FUSYS-FUHLF | WL267 Engine Fuel System Hoses and Fitt | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-FUSYS | WL267 Engine Fuel System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-FNHUB | WL267 Engine Fan Hub | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS-WTRPP | WL267 Engine Water Pump | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS-THERM | WL267 Engine Thermostats-Regulators | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS-RADTR | WL267 Engine Radiator | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS-CSHLF | WL267 Engine Cooling Sys Hoses and Fitt | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS-COFAN | WL267 Engine Fan Cooling System | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS-BELTS | WL267 Engine Belts and Idler Pulleys | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS-ACWEP | WL267 Engine Water Pump Aftercooler | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COSYS | WL267 Engine Cooling System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE-COMPR | WL267 Air Compressor | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ENGINE | WL267 Engine Assembly Caterpillar 3516B | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ELCTLV-LIGHT | WL267 Electrical Lighting Low Voltage | 74441 | 49129 | 6000
CCK-MP-LOAD-WL267 -ELCTLV-HARNS | WL267 Electrical Harness Low Voltage | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ELCTLV-CONTL | WL267 Electrical Controls Low Voltage | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ELCTLV-CHARG-BATTY | WL267 Electrical Batteries | 74441 | 16379 | 6000
CCK-MP-LOAD-WL267 -ELCTLV-CHARG-ALTER | WL267 Electrical Alternator 24V RH | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ELCTLV-CHARG-ALTEL | WL267 Electrical Alternator 24V LH | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -ELCTLV-CHARG | WL267 Electrical Charging System Low Vo | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -ELCTLV | WL267 Electrical System Low Voltage 24V | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -COMMUN-RADIO | WL267 Two Way Radio | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -COMMUN-FLMGT | WL267 Fleet Management | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -COMMUN | WL267 Communications | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-SRVBK-SVBRR | WL267 Brake Service RH Rear | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-SRVBK-SVBRF | WL267 Brake Service RH Front | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-SRVBK-SVBLR | WL267 Brake Service LH Rear | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-SRVBK-SVBLF | WL267 Brake Service LH Front | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-SRVBK | WL267 Service Brakes | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRPRK | WL267 Brake Park Assembly | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRPMP-BRP02 | WL267 Brake Cooling Pump | 74441 | 19742 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRPMP-BRP01 | WL267 Brake Pump | 74441 | 2987 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRPMP | WL267 Braking System Pumps | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BROCC | WL267 Brake Oil Cooler | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRHLF-BRKHO | WL267 Brake System Hoses | 74441 | 8258 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRHLF | WL267 Brake System Hoses and Fittings | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRCOT | WL267 Brake Cooling Oil Tank | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRACC-BACCR | WL267 Brake Accumulator Rear | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRACC-BACCF | WL267 Brake Accumulator Front | 74441 | 21055 | 6000
CCK-MP-LOAD-WL267 -BRKSYS-BRACC | WL267 Brake Accumulators | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 -BRKSYS | WL267 Braking System | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 | WL267 Lubrication & Mechanical Services | 74441 | 74441 | 6000
CCK-MP-LOAD-WL267 | Caterpillar 994H Wheel Loader WL267 | 74441 | 74441 | 6000
CCK-MP-LOAD-WL266 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 74378 | 13784 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRACC | Brake Accumulator RH | 12308 | 12308 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRACC | Brake Accumulator LH | 12308 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-TRTRF | Transmission Transfer Case | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-TRQUE | WL266 Torque Converter | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-TRPMP | WL266 Transmission Charge Pump | 74342 | 7121 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-TROLC | WL266 Transmission Oil Cooler | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-TRHLF-TRNHO | WL266 Transmission System Hoses | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-TRHLF | WL266 Trans System Hoses/Lines & Fitt | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-TRANS | WL266 Transmission | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-PMPDR-RRPDR | WL266 Pump Drive Gearbox Rear | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-PMPDR-FRPDR | WL266 Pump Drive Gearbox Front | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-PMPDR | WL266 Pump Drive Gearboxes | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-UCTRB | WL266 D-Shaft Upper Centre Bearing | 74342 | 18157 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-TORCP | WL266 D-Shaft Torsional Coupling | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT06 | WL266 D-Shaft Front Pump Drive To Cntr | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT05 | WL266 D-Shaft Rear Pump Drive To Cntr B | 74342 | 18157 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT04 | WL266 D-Shaft Cntr Bearing to Front Diff | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT03 | WL266 D-Shaft Transmission to Cntr Brg | 74342 | 14189 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT02 | WL266 D-Shaft Transmission to Rear Diff | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-SHT01 | WL266 D-Shaft T/C to Transmission | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT-LCTRB | WL266 D-Shaft Lower Centre Bearing | 74342 | 41183 | 6000
CCK-MP-LOAD-WL266 -TRNSYS-DRSHT | WL266 Drive Shafts | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -TRNSYS | WL266 Transmission System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-STLAD | WL266 Steps and Ladders | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-PNLGU | WL266 Panels and Guards | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-PLHAN | WL266 Platforms and Handrails | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-ROPSS | WL266 Chassis Rollover Protective Struct | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-REFRM | WL266 Chassis Rear Frame | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-LNKGE | WL266 Chassis Linkage | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-LIARM | WL266 Chassis Lift Arm | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-LEVER | WL266 Chassis Lever | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-FRFRM | WL266 Chassis Front Frame | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-CWEIG | WL266 Chassis Counterweight | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS-ARTIC | WL266 Chassis Articulation | 74342 | 16795 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CHASS | WL266 Chassis | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN-SEATS | WL266 Cabin Operators Seat | 74342 | 5199 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN-SBELT | WL266 Cabin Seat Belt | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN-GLASS | WL266 Cabin Glass | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN-CABPR | WL266 Cabin Pressurisation System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN-CABES | WL266 Cabin Entertainment System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN-CABCO | WL266 Cabin Controls | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN-AIRCN | WL266 Cabin Air Conditioning System | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -STRUCT-CABIN | WL266 Cabin Operators | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRUCT-BUCKT | WL266 Bucket | 74342 | 39250 | 6000
CCK-MP-LOAD-WL266 -STRUCT | WL266 Structure | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STVLV | WL266 Steering Valve | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STTNK | WL266 Steering and Brake Oil Tank | 74342 | 44965 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STRCY-STCYR | WL266 Steering Cylinder RH | 74342 | 5601 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STRCY-STCYL | WL266 Steering Cylinder LH | 74342 | 18157 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STRCY | WL266 Steering Cylinder | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP04 | WL266 Steering Pump Secondary | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP03 | WL266 Steering & Brake Oil Cooler Pump | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP02 | WL266 Steering Pump RH | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STPMP-STP01 | WL266 Steering Pump LH | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STPMP | WL266 Steering System Pumps | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STNVS | WL266 Steering Neutralizer Valves | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STIPV | WL266 Steering STIC Pilot Valve | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STHLF-STRHO | WL266 Steering System Hoses | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STHLF | WL266 Steering System Hoses and Fitting | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRSYS-STBOC | WL266 Steering And Brake Oil Cooler | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -STRSYS | WL266 Steering System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -PNEUMC-START | WL266 Pneumatic Starter Motor | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -PNEUMC-PNTNK-AIT03 | WL266 Pneumatic Air Tank Expansion RH | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -PNEUMC-PNTNK-AIT02 | WL266 Pneumatic Tank Expansion LH | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -PNEUMC-PNTNK-AIT01 | WL266 Pneumatic Tank Main Starting | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -PNEUMC-PNTNK | WL266 Pneumatic System Tanks | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -PNEUMC-PNHLF | WL266 Pneumatic System Hoses & Fittings | 74342 | 44965 | 6000
CCK-MP-LOAD-WL266 -PNEUMC | WL266 Pneumatic System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -MANGMT-UMMMC | WL266 Management Mine Monitoring and Con | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -MANGMT-UMMC | WL266 Management Machine System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -MANGMT-UMENG | WL266 Management Engine System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -MANGMT | WL266 Unit Management | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-PACCM | WL266 Hydraulic Pilot Accumulator | 74342 | 23533 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP04 | WL266 Hydraulic Pump Hyd Pilot & Cool | 74342 | 7121 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP03 | WL266 Hydraulic Pump Implement Centre | 74342 | 2546 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP02 | WL266 Hydraulic Pump Implement RH | 74342 | 2546 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HYDPP-HYP01 | WL266 Hydraulic Pump Implement LH | 74342 | 2546 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HYDPP | WL266 Hydraulic Pumps | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDVLV-HYV02 | WL266 Hydraulic Valve Implement Control | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDVLV-HYV01 | WL266 Hydraulic Valve Implement Control | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDVLV | WL266 Hydraulic Valves | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDTNK-HYT03 | WL266 Hydraulic Tank Expansion RH | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDTNK-HYT02 | WL266 Hydraulic Tank Expansion LH | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDTNK-HYT01 | WL266 Hydraulic Tank Main | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDTNK | WL266 Hydraulic Oil Tanks | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDOCO | WL266 Hydraulic Oil Cooler | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-PILHO | WL266 Pilot System Hoses | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDHLF-HYDHO | WL266 Hydraulic System Hoses | 74342 | 30142 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDHLF | WL266 Hydraulic System Hoses & Fittings | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-HCYLR | WL266 Cylinder Hoist RH High Lift | 74342 | 1243 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-HCYLL | WL266 Cylinder Hoist LH High Lift | 74342 | 1243 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-BUCYR | WL266 Cylinder Bucket RH High Lift | 74342 | 1701 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDCYL-BUCYL | WL266 Cylinder Bucket LH High Lift | 74342 | 3995 | 6000
CCK-MP-LOAD-WL266 -HYDSYS-HDCYL | WL266 Hydraulic Cylinders | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -HYDSYS | WL266 Hydraulic System | 74342 | 31864 | 6000
CCK-MP-LOAD-WL266 -GRSYST-GRTNK | WL266 Grease Reservoir | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -GRSYST-GRINJ | WL266 Grease Injectors | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -GRSYST-ALHLF | WL266 Grease Auto Lube Hoses & Fittings | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -GRSYST-ALELC | WL266 Grease Auto Lube Electrical | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -GRSYST-ALCON | WL266 Grease Auto Lube Controller | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -GRSYST-ALBPP | WL266 Grease Auto Lube Pump | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -GRSYST | WL266 Grease Lubrication System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FRSUPP-FSMAN-EXTIN | WL266 Fire Suppression Hand Held Exting | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FRSUPP-FSMAN | WL266 Fire Suppression Manual | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FRSUPP-FSAUT-FFOAM | WL266 Fire Suppression Foam | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FRSUPP-FSAUT | WL266 Fire Suppression Automatic | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FRSUPP-FSALM | WL266 Fire Suppression System Alarm | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FRSUPP | WL266 Fire Suppression System | 74342 | 41183 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-WHTYR-POS04 | WL266 Tyre Position 4 | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-WHTYR-POS03 | WL266 Tyre Position 3 | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-WHTYR-POS02 | WL266 Tyre Position 2 | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-WHTYR-POS01 | WL266 Tyre Position 1 | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-WHTYR | WL266 Wheels & Tyres and Rims | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-RRDIF-TRNON | WL266 Rear Axle Housing Trunnion | 74342 | 18157 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-RRDIF | WL266 Rear Differential | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FRDIF | WL266 Front Differential | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR04 | WL266 Final Drive Position 4 | 74342 | 5199 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR03 | WL266 Final Drive Position 3 | 74342 | 1701 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR02 | WL266 Final Drive Position 2 | 74342 | 7305 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE-FDR01 | WL266 Final Drive Position 1 | 74342 | 11828 | 6000
CCK-MP-LOAD-WL266 -FDRSYS-FDRVE | WL266 Final Drives | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -FDRSYS | WL266 Final Drive System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-LUBSY-PREPP | WL266 Engine Prelube Oil Pump | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-LUBSY-OILPP | WL266 Engine Oil Pump | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-LUBSY-ENOLC | WL266 Engine Oil Cooler | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-LUBSY | WL266 Engine Lubrication System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX-TBORR | WL266 Engine Turbocharger RH Rear | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX-TBORF | WL266 Engine Turbocharger RH Front | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX-TBOLR | WL266 Engine Turbocharger LH Rear | 74342 | 1174 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX-TBOLF | WL266 Engine Turbocharger LH Front | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX-EXHST | WL266 Engine Exhaust System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX-AIRFL | WL266 Engine Air Filtration System | 74342 | 30142 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX-AFTER | WL266 Engine Aftercooler | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-INTEX | WL266 Engine Intake and Exhaust System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-FUSYS-FULTP | WL266 Engine Fuel Transfer Pump | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-FUSYS-FULTK | WL266 Engine Fuel Tank | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-FUSYS-FULPP | WL266 Engine Fuel Priming Pump | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-FUSYS-FUINJ | WL266 Engine Fuel Injectors | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-FUSYS-FUHLF | WL266 Engine Fuel System Hoses and Fitt | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-FUSYS | WL266 Engine Fuel System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-FNHUB | WL266 Engine Fan Hub | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS-WTRPP | WL266 Engine Water Pump | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS-THERM | WL266 Engine Thermostats-Regulators | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS-RADTR | WL266 Engine Radiator | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS-CSHLF | WL266 Engine Cooling Sys Hoses and Fitt | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS-COFAN | WL266 Engine Fan Cooling System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS-BELTS | WL266 Engine Belts and Idler Pulleys | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS-ACWEP | WL266 Engine Water Pump Aftercooler | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COSYS | WL266 Engine Cooling System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE-COMPR | WL266 Air Compressor | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ENGINE | WL266 Engine Assembly Caterpillar 3516B | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ELCTLV-LIGHT | WL266 Electrical Lighting Low Voltage | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ELCTLV-HARNS | WL266 Electrical Harness Low Voltage | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ELCTLV-CONTL | WL266 Electrical Controls Low Voltage | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ELCTLV-CHARG-BATTY | WL266 Electrical Batteries | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ELCTLV-CHARG-ALTER | WL266 Electrical Alternator 24V RH | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ELCTLV-CHARG-ALTEL | WL266 Electrical Alternator 24V LH | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -ELCTLV-CHARG | WL266 Electrical Charging System Low Vo | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -ELCTLV | WL266 Electrical System Low Voltage 24V | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -COMMUN-RADIO | WL266 Two Way Radio | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -COMMUN-FLMGT | WL266 Fleet Management | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -COMMUN | WL266 Communications | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-SRVBK-SVBRR | WL266 Brake Service RH Rear | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-SRVBK-SVBRF | WL266 Brake Service RH Front | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-SRVBK-SVBLR | WL266 Brake Service LH Rear | 74342 | 59074 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-SRVBK-SVBLF | WL266 Brake Service LH Front | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-SRVBK | WL266 Service Brakes | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRPRK | WL266 Brake Park Assembly | 74342 | 24646 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRPMP-BRP02 | WL266 Brake Cooling Pump | 74342 | 16796 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRPMP-BRP01 | WL266 Brake Pump | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRPMP | WL266 Braking System Pumps | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BROCC | WL266 Brake Oil Cooler | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRHLF-BRKHO | WL266 Brake System Hoses | 74342 | 30142 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRHLF | WL266 Brake System Hoses and Fittings | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRCOT | WL266 Brake Cooling Oil Tank | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRACC-BACCR | WL266 Brake Accumulator Rear | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRACC-BACCF | WL266 Brake Accumulator Front | 74342 | 12308 | 6000
CCK-MP-LOAD-WL266 -BRKSYS-BRACC | WL266 Brake Accumulators | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 -BRKSYS | WL266 Braking System | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 | WL266 Lube & Mechanical Services | 74342 | 74342 | 6000
CCK-MP-LOAD-WL266 | Caterpillar 994H Wheel Loader WL266 | 74342 | 74342 | 6000
CCK-MP-LOAD-WL261 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 77085 | 17001 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRACC | Brake Accumulator RH | 30681 | 30681 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRACC | Brake Accumulator LH | 30681 | 30681 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-TRTRF | Transmission Transfer Case | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 77065 | 30681 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 77065 | 30681 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 77065 | 30681 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 77065 | 30681 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-TRQUE | WL261 Torque Converter | 77065 | 16650 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-TRPMP | WL261 Transmission Charge Pump | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-TROLC | WL261 Transmission Oil Cooler | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-TRHLF-TRNHO | WL261 Transmission System Hoses | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-TRHLF | WL261 Trans System Hoses, Lines and Fi | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-TRANS | WL261 Transmission | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-PMPDR-RRPDR | WL261 Pump Drive Gearbox Rear | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-PMPDR-FRPDR | WL261 Pump Drive Gearbox Front | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-PMPDR | WL261 Pump Drive Gearboxes | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-UCTRB | WL261 D-Shaft Upper Centre Bearing | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-TORCP | WL261 D-Shaft Torsional Coupling | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT06 | WL261 D-Shaft Front Pump Drive To Cntr | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT05 | WL261 D-Shaft Rear Pump Drive To Cntr B | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT04 | WL261 D-Shaft Cntr Bearing to Front Dif | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT03 | WL261 D-Shaft Transmission to Cntr Bear | 77065 | 19291 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT02 | WL261 D-Shaft Transmission to Rear Diff | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-SHT01 | WL261 D-Shaft T/C to Transmission | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT-LCTRB | WL261 D-Shaft Lower Centre Bearing | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -TRNSYS-DRSHT | WL261 Drive Shafts | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -TRNSYS | WL261 Transmission System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-STLAD | WL261 Steps and Ladders | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-PNLGU | WL261 Panels and Guards | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-PLHAN | WL261 Platforms and Handrails | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-ROPSS | WL261 Chassis Rollover Protective Struc | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-REFRM | WL261 Chassis Rear Frame | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-LNKGE | WL261 Chassis Linkage | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-LIARM | WL261 Chassis Lift Arm | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-LEVER | WL261 Chassis Lever | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-FRFRM | WL261 Chassis Front Frame | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-CWEIG | WL261 Chassis Counterweight | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS-ARTIC | WL261 Chassis Articulation | 77065 | 13461 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CHASS | WL261 Chassis | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN-SEATS | WL261 Cabin Operators Seat | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN-SBELT | WL261 Cabin Seat Belt | 77065 | 41775 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN-GLASS | WL261 Cabin Glass | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN-CABPR | WL261 Cabin Pressurisation System | 77065 | 41775 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN-CABES | WL261 Cabin Entertainment System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN-CABCO | WL261 Cabin Controls | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN-AIRCN | WL261 Cabin Air Conditioning System | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -STRUCT-CABIN | WL261 Cabin Operators | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT-BUCKT | WL261 Bucket | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRUCT | WL261 Structure | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STVLV | WL261 Steering Valve | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STTNK | WL261 Steering and Brake Oil Tank | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STRCY-STCYR | WL261 Steering Cylinder RH | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STRCY-STCYL | WL261 Steering Cylinder LH | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STRCY | WL261 Steering Cylinder | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP04 | WL261 Steering Pump Secondary | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP03 | WL261 Steering and Brake Oil Cooler Pum | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP02 | WL261 Steering Pump RH | 77065 | 19291 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STPMP-STP01 | WL261 Steering Pump LH | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STPMP | WL261 Steering System Pumps | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STNVS | WL261 Steering Neutralizer Valves | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STIPV | WL261 Steering STIC Pilot Valve | 77065 | 36172 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STHLF-STRHO | WL261 Steering System Hoses | 77065 | 19291 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STHLF | WL261 Steering System Hoses and Fitting | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRSYS-STBOC | WL261 Steering And Brake Oil Cooler | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -STRSYS | WL261 Steering System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -PNEUMC-START | WL261 Pneumatic Starter Motor | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -PNEUMC-PNTNK-AIT03 | WL261 Pneumatic Air Tank Expansion RH | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -PNEUMC-PNTNK-AIT02 | WL261 Pneumatic Tank Expansion LH | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -PNEUMC-PNTNK-AIT01 | WL261 Pneumatic Tank Main Starting | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -PNEUMC-PNTNK | WL261 Pneumatic System Tanks | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -PNEUMC-PNHLF | WL261 Pneumatic System Hoses & Fittings | 77065 | 43701 | 6000
CCK-MP-LOAD-WL261 -PNEUMC | WL261 Pneumatic System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -MANGMT-UMMMC | WL261 Management Mine Monitoring and Co | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -MANGMT-UMMC | WL261 Management Machine System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -MANGMT-UMENG | WL261 Management Engine System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -MANGMT | WL261 Unit Management | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-PACCM | WL261 Hydraulic Pilot Accumulator | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP04 | WL261 Hydraulic Pump Hydraulic Pilot & | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP03 | WL261 Hydraulic Pump Implement Centre | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP02 | WL261 Hydraulic Pump Implement RH | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HYDPP-HYP01 | WL261 Hydraulic Pump Implement LH | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HYDPP | WL261 Hydraulic Pumps | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDVLV-HYV02 | WL261 Hydraulic Valve Implement Control | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDVLV-HYV01 | WL261 Hydraulic Valve Implement Control | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDVLV | WL261 Hydraulic Valves | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDTNK-HYT03 | WL261 Hydraulic Tank Expansion RH | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDTNK-HYT02 | WL261 Hydraulic Tank Expansion LH | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDTNK-HYT01 | WL261 Hydraulic Tank Main | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDTNK | WL261 Hydraulic Oil Tanks | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDOCO | WL261 Hydraulic Oil Cooler | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-PILHO | WL261 Pilot System Hoses | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDHLF-HYDHO | WL261 Hydraulic System Hoses | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDHLF | WL261 Hydraulic System Hoses & Fittings | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-HCYLR | WL261 Cylinder Hoist RH High Lift | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-HCYLL | WL261 Cylinder Hoist LH High Lift | 77065 | 4775 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-BUCYR | WL261 Cylinder Bucket RH High Lift | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDCYL-BUCYL | WL261 Cylinder Bucket LH High Lift | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -HYDSYS-HDCYL | WL261 Hydraulic Cylinders | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -HYDSYS | WL261 Hydraulic System | 77065 | 30681 | 6000
CCK-MP-LOAD-WL261 -GRSYST-GRTNK | WL261 Grease Resevoir | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -GRSYST-GRINJ | WL261 Grease Injectors | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -GRSYST-ALHLF | WL261 Grease Auto Lube Hoses & Fittings | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -GRSYST-ALELC | WL261 Grease Auto Lube Electrical | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -GRSYST-ALCON | WL261 Grease Auto Lube Controller | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -GRSYST-ALBPP | WL261 Grease Auto Lube Pump | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -GRSYST | WL261 Grease Lubrication System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FRSUPP-FSMAN-EXTIN | WL261 Fire Suppression Hand Held Exting | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FRSUPP-FSMAN | WL261 Fire Suppression Manual | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FRSUPP-FSAUT-FFOAM | WL261 Fire Suppression Foam | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FRSUPP-FSAUT | WL261 Fire Suppression Automatic | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FRSUPP-FSALM | WL261 Fire Suppression System Alarm | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FRSUPP | WL261 Fire Suppression System | 77065 | 30681 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-WHTYR-POS04 | WL261 Tyre Position 4 | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-WHTYR-POS03 | WL261 Tyre Position 3 | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-WHTYR-POS02 | WL261 Tyre Position 2 | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-WHTYR-POS01 | WL261 Tyre Position 1 | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-WHTYR | WL261 Wheels & Tyres and Rims | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-RRDIF-TRNON | WL261 Rear Axle Housing Trunnion | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-RRDIF | WL261 Rear Differential | 77065 | 19291 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FRDIF | WL261 Front Differential | 77065 | 19291 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR04 | WL261 Final Drive Position 4 | 77065 | 12939 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR03 | WL261 Final Drive Position 3 | 77065 | 3904 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR02 | WL261 Final Drive Position 2 | 77065 | 6591 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE-FDR01 | WL261 Final Drive Position 1 | 77065 | 12939 | 6000
CCK-MP-LOAD-WL261 -FDRSYS-FDRVE | WL261 Final Drives | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -FDRSYS | WL261 Final Drive System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-LUBSY-PREPP | WL261 Engine Prelube Oil Pump | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-LUBSY-OILPP | WL261 Engine Oil Pump | 77065 | 46542 | 6000
CCK-MP-LOAD-WL261 -ENGINE-LUBSY-ENOLC | WL261 Engine Oil Cooler | 77065 | 46542 | 6000
CCK-MP-LOAD-WL261 -ENGINE-LUBSY | WL261 Engine Lubrication System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX-TBORR | WL261 Engine Turbocharger RH Rear | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX-TBORF | WL261 Engine Turbocharger RH Front | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX-TBOLR | WL261 Engine Turbocharger LH Rear | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX-TBOLF | WL261 Engine Turbocharger LH Front | 77065 | 1948 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX-EXHST | WL261 Engine Exhaust System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX-AIRFL | WL261 Engine Air Filtration System | 77065 | 30681 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX-AFTER | WL261 Engine Aftercooler | 77065 | 46542 | 6000
CCK-MP-LOAD-WL261 -ENGINE-INTEX | WL261 Engine Intake and Exhaust System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-FUSYS-FULTP | WL261 Engine Fuel Transfer Pump | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-FUSYS-FULTK | WL261 Engine Fuel Tank | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-FUSYS-FULPP | WL261 Engine Fuel Priming Pump | 77065 | 46542 | 6000
CCK-MP-LOAD-WL261 -ENGINE-FUSYS-FUINJ | WL261 Engine Fuel Injectors | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-FUSYS-FUHLF | WL261 Engine Fuel System Hoses and Fitt | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-FUSYS | WL261 Engine Fuel System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-FNHUB | WL261 Engine Fan Hub | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS-WTRPP | WL261 Engine Water Pump | 76889 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS-THERM | WL261 Engine Thermostats-Regulators | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS-RADTR | WL261 Engine Radiator | 76567 | 22498 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS-CSHLF | WL261 Engine Cooling Sys Hoses and Fitt | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS-COFAN | WL261 Engine Fan Cooling System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS-BELTS | WL261 Engine Belts and Idler Pulleys | 77065 | 67166 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS-ACWEP | WL261 Engine Water Pump Aftercooler | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COSYS | WL261 Engine Cooling System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ENGINE-COMPR | WL261 Air Compressor | 77065 | 67166 | 6000
CCK-MP-LOAD-WL261 -ENGINE | WL261 Engine Assembly Caterpillar 3516B | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ELCTLV-LIGHT | WL261 Electrical Lighting Low Voltage | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ELCTLV-HARNS | WL261 Electrical Harness Low Voltage | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ELCTLV-CONTL | WL261 Electrical Controls Low Voltage | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ELCTLV-CHARG-BATTY | WL261 Electrical Batteries | 77065 | 13476 | 6000
CCK-MP-LOAD-WL261 -ELCTLV-CHARG-ALTER | WL261 Electrical Alternator 24V RH | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ELCTLV-CHARG-ALTEL | WL261 Electrical Alternator 24V LH | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -ELCTLV-CHARG | WL261 Electrical Charging System Low Vo | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -ELCTLV | WL261 Electrical System Low Voltage 24V | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -COMMUN-RADIO | WL261 Two Way Radio | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -COMMUN-FLMGT | WL261 Fleet Management | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -COMMUN | WL261 Communications | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-SRVBK-SVBRR | WL261 Brake Service RH Rear | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-SRVBK-SVBRF | WL261 Brake Service RH Front | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-SRVBK-SVBLR | WL261 Brake Service LH Rear | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-SRVBK-SVBLF | WL261 Brake Service LH Front | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-SRVBK | WL261 Service Brakes | 77065 | 41775 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRPRK | WL261 Brake Park Assembly | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRPMP-BRP02 | WL261 Brake Cooling Pump | 77065 | 3344 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRPMP-BRP01 | WL261 Brake Pump | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRPMP | WL261 Braking System Pumps | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BROCC | WL261 Brake Oil Cooler | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRHLF-BRKHO | WL261 Brake System Hoses | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRHLF | WL261 Brake System Hoses and Fittings | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRCOT | WL261 Brake Cooling Oil Tank | 77065 | 50514 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRACC-BACCR | WL261 Brake Accumulator Rear | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRACC-BACCF | WL261 Brake Accumulator Front | 77065 | 11736 | 6000
CCK-MP-LOAD-WL261 -BRKSYS-BRACC | WL261 Brake Accumulators | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 -BRKSYS | WL261 Braking System | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 | WL261 Lube & Mechanical Services | 77065 | 77065 | 6000
CCK-MP-LOAD-WL261 | Caterpillar 994H Wheel Loader WL261 | 77065 | 77065 | 6000
CCK-MP-LOAD-WL260 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 75566 | 12924 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRACC | Brake Accumulator RH | 28419 | 28419 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRACC | Brake Accumulator LH | 22246 | 22246 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-TRTRF | Transmission Transfer Case | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-TRQUE | WL260 Torque Converter | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-TRPMP | WL260 Transmission Charge Pump | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-TROLC | WL260 Transmission Oil Cooler | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-TRHLF-TRNHO | WL260 Transmission System Hoses | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-TRHLF | WL260 Trans System Hoses, Lines and Fit | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-TRANS | WL260 Transmission | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-PMPDR-RRPDR | WL260 Pump Drive Gearbox Rear | 75558 | 4503 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-PMPDR-FRPDR | WL260 Pump Drive Gearbox Front | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-PMPDR | WL260 Pump Drive Gearboxes | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-UCTRB | WL260 D-Shaft Upper Centre Bearing | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-TORCP | WL260 D-Shaft Torsional Coupling | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT06 | WL260 D-Shaft Front Pump Drive To Cntr | 75558 | 4503 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT05 | WL260 D-Shaft Rear Pump Drive To Cntr B | 75558 | 4503 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT04 | WL260 D-Shaft Cntr Bearing to Front Dif | 75558 | 4503 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT03 | WL260 D-Shaft Transmission to Cntr Bear | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT02 | WL260 D-Shaft Transmission to Rear Diff | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-SHT01 | WL260 D-Shaft T/C to Transmission | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT-LCTRB | WL260 D-Shaft Lower Centre Bearing | 75558 | 4503 | 6000
CCK-MP-LOAD-WL260 -TRNSYS-DRSHT | WL260 Drive Shafts | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -TRNSYS | WL260 Transmission System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-STLAD | WL260 Steps and Ladders | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-PNLGU | WL260 Panels and Guards | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-PLHAN | WL260 Platforms and Handrails | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-ROPSS | WL260 Chassis Rollover Protective Struc | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-REFRM | WL260 Chassis Rear Frame | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-LNKGE | WL260 Chassis Linkage | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-LIARM | WL260 Chassis Lift Arm | 75558 | 22246 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-LEVER | WL260 Chassis Lever | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-FRFRM | WL260 Chassis Front Frame | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-CWEIG | WL260 Chassis Counterweight | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS-ARTIC | WL260 Chassis Articulation | 75558 | 18081 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CHASS | WL260 Chassis | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN-SEATS | WL260 Cabin Operators Seat | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN-SBELT | WL260 Cabin Seat Belt | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN-GLASS | WL260 Cabin Glass | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN-CABPR | WL260 Cabin Pressurisation System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN-CABES | WL260 Cabin Entertainment System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN-CABCO | WL260 Cabin Controls | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN-AIRCN | WL260 Cabin Air Conditioning System | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -STRUCT-CABIN | WL260 Cabin Operators | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT-BUCKT | WL260 Bucket | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRUCT | WL260 Structure | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STVLV | WL260 Steering Valve | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STTNK | WL260 Steering and Brake Oil Tank | 75558 | 22246 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STRCY-STCYR | WL260 Steering Cylinder RH | 75558 | 5908 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STRCY-STCYL | WL260 Steering Cylinder LH | 75558 | 4819 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STRCY | WL260 Steering Cylinder | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP04 | WL260 Steering Pump Secondary | 75558 | 7480 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP03 | WL260 Steering and Brake Oil Cooler Pum | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP02 | WL260 Steering Pump RH | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STPMP-STP01 | WL260 Steering Pump LH | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STPMP | WL260 Steering System Pumps | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STNVS | WL260 Steering Neutralizer Valves | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STIPV | WL260 Steering STIC Pilot Valve | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STHLF-STRHO | WL260 Steering System Hoses | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STHLF | WL260 Steering System Hoses and Fitting | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRSYS-STBOC | WL260 Steering And Brake Oil Cooler | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -STRSYS | WL260 Steering System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -PNEUMC-START | WL260 Pneumatic Starter Motor | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -PNEUMC-PNTNK-AIT03 | WL260 Pneumatic Air Tank Expansion RH | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -PNEUMC-PNTNK-AIT02 | WL260 Pneumatic Tank Expansion LH | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -PNEUMC-PNTNK-AIT01 | WL260 Pneumatic Tank Main Starting | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -PNEUMC-PNTNK | WL260 Pneumatic System Tanks | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -PNEUMC-PNHLF | WL260 Pneumatic System Hoses & Fittings | 75558 | 22246 | 6000
CCK-MP-LOAD-WL260 -PNEUMC | WL260 Pneumatic System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -MANGMT-UMMMC | WL260 Management Mine Monitoring and Co | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -MANGMT-UMMC | WL260 Management Machine System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -MANGMT-UMENG | WL260 Management Engine System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -MANGMT | WL260 Unit Management | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-PACCM | WL260 Hydraulic Pilot Accumulator | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP04 | WL260 Hydraulic Pump Hydraulic Pilot & | 75542 | 3411 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP03 | WL260 Hydraulic Pump Implement Centre | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP02 | WL260 Hydraulic Pump Implement RH | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HYDPP-HYP01 | WL260 Hydraulic Pump Implement LH | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HYDPP | WL260 Hydraulic Pumps | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDVLV-HYV02 | WL260 Hydraulic Valve Implement Control | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDVLV-HYV01 | WL260 Hydraulic Valve Implement Control | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDVLV | WL260 Hydraulic Valves | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDTNK-HYT03 | WL260 Hydraulic Tank Expansion RH | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDTNK-HYT02 | WL260 Hydraulic Tank Expansion LH | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDTNK-HYT01 | WL260 Hydraulic Tank Main | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDTNK | WL260 Hydraulic Oil Tanks | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDOCO | WL260 Hydraulic Oil Cooler | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-PILHO | WL260 Pilot System Hoses | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDHLF-HYDHO | WL260 Hydraulic System Hoses | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDHLF | WL260 Hydraulic System Hoses & Fittings | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-HCYLR | WL260 Cylinder Hoist RH High Lift | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-HCYLL | WL260 Cylinder Hoist LH High Lift | 75558 | 814 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-BUCYR | WL260 Cylinder Bucket RH High Lift | 75558 | 7107 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDCYL-BUCYL | WL260 Cylinder Bucket LH High Lift | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -HYDSYS-HDCYL | WL260 Hydraulic Cylinders | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -HYDSYS | WL260 Hydraulic System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -GRSYST-GRTNK | WL260 Grease Resevoir | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -GRSYST-GRINJ | WL260 Grease Injectors | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -GRSYST-ALHLF | WL260 Grease Auto Lube Hoses & Fittings | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -GRSYST-ALELC | WL260 Grease Auto Lube Electrical | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -GRSYST-ALCON | WL260 Grease Auto Lube Controller | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -GRSYST-ALBPP | WL260 Grease Auto Lube Pump | 75553 | 3406 | 6000
CCK-MP-LOAD-WL260 -GRSYST | WL260 Grease Lubrication System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FRSUPP-FSMAN-EXTIN | WL260 Fire Suppression Hand Held Exting | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FRSUPP-FSMAN | WL260 Fire Suppression Manual | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FRSUPP-FSAUT-FFOAM | WL260 Fire Suppression Foam | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FRSUPP-FSAUT | WL260 Fire Suppression Automatic | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FRSUPP-FSALM | WL260 Fire Suppression System Alarm | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FRSUPP | WL260 Fire Suppression System | 75558 | 22246 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-WHTYR-POS04 | WL260 Tyre Position 4 | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-WHTYR-POS03 | WL260 Tyre Position 3 | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-WHTYR-POS02 | WL260 Tyre Position 2 | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-WHTYR-POS01 | WL260 Tyre Position 1 | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-WHTYR | WL260 Wheels & Tyres and Rims | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-RRDIF-TRNON | WL260 Rear Axle Housing Trunnion | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-RRDIF | WL260 Rear Differential | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FRDIF | WL260 Front Differential | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR04 | WL260 Final Drive Position 4 | 75558 | 12904 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR03 | WL260 Final Drive Position 3 | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR02 | WL260 Final Drive Position 2 | 75558 | 528 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE-FDR01 | WL260 Final Drive Position 1 | 75558 | 9452 | 6000
CCK-MP-LOAD-WL260 -FDRSYS-FDRVE | WL260 Final Drives | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -FDRSYS | WL260 Final Drive System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-LUBSY-PREPP | WL260 Engine Prelube Oil Pump | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -ENGINE-LUBSY-OILPP | WL260 Engine Oil Pump | 75558 | 43831 | 6000
CCK-MP-LOAD-WL260 -ENGINE-LUBSY-ENOLC | WL260 Engine Oil Cooler | 75558 | 43831 | 6000
CCK-MP-LOAD-WL260 -ENGINE-LUBSY | WL260 Engine Lubrication System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX-TBORR | WL260 Engine Turbocharger RH Rear | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX-TBORF | WL260 Engine Turbocharger RH Front | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX-TBOLR | WL260 Engine Turbocharger LH Rear | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX-TBOLF | WL260 Engine Turbocharger LH Front | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX-EXHST | WL260 Engine Exhaust System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX-AIRFL | WL260 Engine Air Filtration System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX-AFTER | WL260 Engine Aftercooler | 75558 | 43831 | 6000
CCK-MP-LOAD-WL260 -ENGINE-INTEX | WL260 Engine Intake and Exhaust System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-FUSYS-FULTP | WL260 Engine Fuel Transfer Pump | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-FUSYS-FULTK | WL260 Engine Fuel Tank | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-FUSYS-FULPP | WL260 Engine Fuel Priming Pump | 75558 | 43831 | 6000
CCK-MP-LOAD-WL260 -ENGINE-FUSYS-FUINJ | WL260 Engine Fuel Injectors | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-FUSYS-FUHLF | WL260 Engine Fuel System Hoses and Fitt | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-FUSYS | WL260 Engine Fuel System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-FNHUB | WL260 Engine Fan Hub | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS-WTRPP | WL260 Engine Water Pump | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS-THERM | WL260 Engine Thermostats-Regulators | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS-RADTR | WL260 Engine Radiator | 75558 | 3411 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS-CSHLF | WL260 Engine Cooling Sys Hoses and Fitt | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS-COFAN | WL260 Engine Fan Cooling System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS-BELTS | WL260 Engine Belts and Idler Pulleys | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS-ACWEP | WL260 Engine Water Pump Aftercooler | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COSYS | WL260 Engine Cooling System | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ENGINE-COMPR | WL260 Air Compressor | 75558 | 32966 | 6000
CCK-MP-LOAD-WL260 -ENGINE | WL260 Engine Assembly Caterpillar 3516B | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -ELCTLV-LIGHT | WL260 Electrical Lighting Low Voltage | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ELCTLV-HARNS | WL260 Electrical Harness Low Voltage | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -ELCTLV-CONTL | WL260 Electrical Controls Low Voltage | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ELCTLV-CHARG-BATTY | WL260 Electrical Batteries | 75558 | 9814 | 6000
CCK-MP-LOAD-WL260 -ELCTLV-CHARG-ALTER | WL260 Electrical Alternator 24V RH | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ELCTLV-CHARG-ALTEL | WL260 Electrical Alternator 24V LH | 75558 | 38 | 6000
CCK-MP-LOAD-WL260 -ELCTLV-CHARG | WL260 Electrical Charging System Low Vo | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -ELCTLV | WL260 Electrical System Low Voltage 24V | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -COMMUN-RADIO | WL260 Two Way Radio | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -COMMUN-FLMGT | WL260 Fleet Management | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -COMMUN | WL260 Communications | 75558 | 75558 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-SRVBK-SVBRR | WL260 Brake Service RH Rear | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-SRVBK-SVBRF | WL260 Brake Service RH Front | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-SRVBK-SVBLR | WL260 Brake Service LH Rear | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-SRVBK-SVBLF | WL260 Brake Service LH Front | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-SRVBK | WL260 Service Brakes | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRPRK | WL260 Brake Park Assembly | 75566 | 4503 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRPMP-BRP02 | WL260 Brake Cooling Pump | 75566 | 3411 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRPMP-BRP01 | WL260 Brake Pump | 75566 | 10899 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRPMP | WL260 Braking System Pumps | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BROCC | WL260 Brake Oil Cooler | 75566 | 3411 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRHLF-BRKHO | WL260 Brake System Hoses | 75566 | 9814 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRHLF | WL260 Brake System Hoses and Fittings | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRCOT | WL260 Brake Cooling Oil Tank | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRACC-BACCR | WL260 Brake Accumulator Rear | 75566 | 9814 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRACC-BACCF | WL260 Brake Accumulator Front | 75566 | 9814 | 6000
CCK-MP-LOAD-WL260 -BRKSYS-BRACC | WL260 Brake Accumulators | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 -BRKSYS | WL260 Braking System | 75566 | 75566 | 6000
CCK-MP-LOAD-WL260 | WL260 Lube & Mechanical Services | 75546 | 75546 | 6000
CCK-MP-LOAD-WL260 | Caterpillar 994H Wheel Loader WL260 | 75566 | 75566 | 6000
CCK-MP-LOAD-WL022 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 80537 | 14420 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRACC | Brake Accumulator RH | 15801 | 15801 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRACC | Brake Accumulator LH | 15801 | 15801 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-TRTRF | Transmission Transfer Case | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -GRSYST-FFGHO | Front Frame - Grease Hoses | 80515 | 57915 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 80515 | 26409 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 80515 | 26409 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 80515 | 26409 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -PNEUMC | Main Airhoses/Relay | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STTNK | Stering and brake tank | 80515 | 57915 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDTNK-HYT01 | WL022 Hydraulic Tank | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -ELCTLV-HARNS | Electrical Harness Low Voltage | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 80515 | 35795 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STHLF-STRHO | Steering System Hoses | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 80515 | 7474 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 80515 | 7474 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STNVS | Steering Neutralizer Valves | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -ENGINE-FNHUB | Engine Fan Hub | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -STRUCT-BUCKT | Bucket | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CHASS-LNKGE | Linkage | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CHASS-LIARM | Lift Arm | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CHASS-ARTIC | Articulation | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CHASS-REFRM | Rear Frame | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CHASS-FRFRM | Front Frame | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CABIN-SBELT | Seat Belt | 80515 | 57915 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CABIN-SEATS | Operators Seat | 80515 | 395 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CABIN-AIRCN | Air Conditioning System | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -STRUCT-CABIN | Operators Cabin | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -GRSYST-ALBPP | Auto Lube Pump | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -GRSYST-GRINJ | Auto Lube Injectors | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -PNEUMC-START | Starter Motor Air | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-PACCM | Pilot Accumulator | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH Extend High Lift | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH Extend High Lift | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH Extend High Lift | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH Extend High Lift | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STBOC | Steering And Brake Oil Cooler | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STRCY-STCYR | Cylinder Steering RH | 80515 | 10370 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STRCY-STCYL | Cylinder Steering LH | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STIPV | STIC Steering Pilot Valve | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STVLV | Valve Steering | 80515 | 68853 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 80515 | 21545 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STPMP-STP02 | Steering Pump RH | 80515 | 5719 | 6000
CCK-MP-LOAD-WL022 -STRSYS-STPMP-STP01 | Steering Pump LH | 80515 | 24304 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BROCC | Brake Oil Cooler | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 80515 | 10370 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRACC-BACCF | Front Brake Accumulator | 80515 | 10370 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 80515 | 1155 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRPMP-BRP01 | Brake Pump | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-BRPRK | Park Brake Assembly | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 80515 | 57915 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 80515 | 57915 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 80515 | 65569 | 6000
CCK-MP-LOAD-WL022 -BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 80515 | 65569 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 80515 | 1209 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 80515 | 1209 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 80515 | 19593 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 80515 | 3082 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-RRDIF | Rear Differential | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -FDRSYS-FRDIF | Front Differential | 80515 | 3082 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 80515 | 24232 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 80515 | 1155 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 80537 | 7470 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 80537 | 1654 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 80537 | 7470 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 80537 | 7470 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 80537 | 7470 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-TROLC | Transmission Oil Cooler | 80537 | 24232 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-TRPMP | Pump Transmission Charge | 80537 | 7470 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-TRQUE | Torque Converter | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 -TRNSYS-TRANS | Transmission | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 -ELCTLV-CHARG-ALTER | Alternator 24V RH | 80537 | 7470 | 6000
CCK-MP-LOAD-WL022 -ELCTLV-CHARG-ALTEL | Alternator 24V LH | 80537 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -ENGINE-INTEX-AFTER | Aftercooler | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -ENGINE-INTEX-TBORR | Turbocharger RH Rear | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-INTEX-TBORF | Turbocharger RH Front | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-INTEX-TBOLF | Turbocharger LH Front | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-COSYS-THERM | Thermostats-Regulators | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-COSYS-COFAN | Fan Cooling System | 80515 | 80515 | 6000
CCK-MP-LOAD-WL022 -ENGINE-COSYS-RADTR | Radiator Coolant | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 -ENGINE-COSYS-RADTR | Radiator Engine | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 -ENGINE-COSYS-WTRPP | Water Pump Engine | 80515 | 7470 | 6000
CCK-MP-LOAD-WL022 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 80515 | 46804 | 6000
CCK-MP-LOAD-WL022 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 80515 | 15801 | 6000
CCK-MP-LOAD-WL022 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 80515 | 57915 | 6000
CCK-MP-LOAD-WL022 -ENGINE-COMPR | Air Compressor | 80515 | 57915 | 6000
CCK-MP-LOAD-WL022 -ENGINE | WL022 Engine Assembly Caterpillar 3516B | 80537 | 15801 | 6000
CCK-MP-LOAD-WL022 | WL022 Lubrication & Mechanical Services | 80537 | 80537 | 6000
CCK-MP-LOAD-WL022 | Caterpillar 994H Wheel Loader WL022 | 80537 | 80537 | 6000
CCK-MP-LOAD-WL021 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 79997 | 12982 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRACC | Brake Accumulator RH | 19277 | 19277 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRACC | Brake Accumulator LH | 19658 | 19658 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STRCY-STCYR | Cylinder Steering RH | 38502 | 38502 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STRCY-STCYL | Cylinder Steering LH | 41674 | 41674 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP02 | Steering Pump RH | 38502 | 38502 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 38502 | 9601 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-RRDIF | Rear Differential | 38502 | 38502 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FRDIF | Front Differential | 43294 | 43294 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 38502 | 38502 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 41373 | 41373 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 38502 | 38502 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 40013 | 40013 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-TRTRF | Transmission Transfer Case | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -GRSYST-FFGHO | Front Frame - Grease Hoses | 79974 | 33627 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 79974 | 14269 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 79974 | 14269 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 79974 | 14269 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 79974 | 14269 | 6000
CCK-MP-LOAD-WL021 -PNEUMC | Main Airhoses/Relay | 79974 | 38502 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STTNK | Stering and brake tank | 79914 | 19277 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDTNK-HYT01 | WL021 Hydraulic Tank | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -ELCTLV-HARNS | Electrical Harness Low Voltage | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STHLF-STRHO | Steering System Hoses | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STNVS | Steering Neutralizer Valves | 79974 | 21107 | 6000
CCK-MP-LOAD-WL021 -ENGINE-FNHUB | Engine Fan Hub | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -STRUCT-BUCKT-BWELM | Bucket Wear Elements | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRUCT-BUCKT | Bucket | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CHASS-LNKGE | Linkage | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CHASS-LIARM | Lift Arm | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CHASS-ARTIC | Articulation | 79974 | 14537 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CHASS-REFRM | Rear Frame | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CHASS-FRFRM | Front Frame | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CABIN-SBELT | Seat Belt | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CABIN-SEATS | Operators Seat | 79974 | 5126 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CABIN-AIRCN | Air Conditioning System | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -STRUCT-CABIN | Operators Cabin | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -GRSYST-ALBPP | Auto Lube Pump | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -GRSYST-GRINJ | Auto Lube Injectors | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -PNEUMC-START | Starter Motor Air | 79974 | 4607 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-PACCM | Pilot Accumulator | 79974 | 32530 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH Extend High Lift | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH Extend High Lift | 79974 | 7368 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH Extend High Lift | 79974 | 6827 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH Extend High Lift | 79974 | 1272 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 79974 | 20 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STBOC | Steering And Brake Oil Cooler | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STRCY-STCYR | Cylinder Steering RH | 79974 | 3198 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STRCY-STCYL | Cylinder Steering LH | 79974 | 3198 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STIPV | STIC Steering Pilot Valve | 79974 | 9602 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STVLV | Valve Steering | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 79974 | 9602 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP02 | Steering Pump RH | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -STRSYS-STPMP-STP01 | Steering Pump LH | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BROCC | Brake Oil Cooler | 79974 | 19658 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRACC-BACCF | Front Brake Accumulator | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRPMP-BRP01 | Brake Pump | 79974 | 11410 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-BRPRK | Park Brake Assembly | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-WHTYR-POS04 | Wheel & Tyre Position 4 | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-WHTYR-POS03 | Wheel & Tyre Position 3 | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-WHTYR-POS02 | Wheel & Tyre Position 2 | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-WHTYR-POS01 | Wheel & Tyre Position 1 | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-RRDIF | Rear Differential | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -FDRSYS-FRDIF | Front Differential | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 79974 | 3457 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 79997 | 9601 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 79997 | 9602 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 79997 | 9601 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 79997 | 9602 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 79997 | 3457 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 79997 | 3457 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 79997 | 11410 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-TROLC | Transmission Oil Cooler | 79997 | 24580 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-TRPMP | Pump Transmission Charge | 79997 | 9602 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-TRQUE | Torque Converter | 79997 | 3457 | 6000
CCK-MP-LOAD-WL021 -TRNSYS-TRANS | Transmission | 79997 | 3457 | 6000
CCK-MP-LOAD-WL021 -ELCTLV-CHARG-ALTER | Alternator 24V RH | 79997 | 9601 | 6000
CCK-MP-LOAD-WL021 -ELCTLV-CHARG-ALTEL | Alternator 24V LH | 79997 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -ENGINE-INTEX-AFTER | Aftercooler | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -ENGINE-INTEX-TBORR | Turbocharger RH Rear | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-INTEX-TBORF | Turbocharger RH Front | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-INTEX-TBOLF | Turbocharger LH Front | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-COSYS-THERM | Thermostats-Regulators | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-COSYS-COFAN | Fan Cooling System | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -ENGINE-COSYS-RADTR | Radiator Coolant | 79997 | 61894 | 6000
CCK-MP-LOAD-WL021 -ENGINE-COSYS-RADTR | Radiator Engine | 79997 | 24580 | 6000
CCK-MP-LOAD-WL021 -ENGINE-COSYS-WTRPP | Water Pump Engine | 79974 | 9601 | 6000
CCK-MP-LOAD-WL021 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 79974 | 79974 | 6000
CCK-MP-LOAD-WL021 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 79974 | 19277 | 6000
CCK-MP-LOAD-WL021 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 79974 | 61871 | 6000
CCK-MP-LOAD-WL021 -ENGINE-COMPR | Air Compressor | 79974 | 11069 | 6000
CCK-MP-LOAD-WL021 -ENGINE | Engine Assembly Caterpillar 3516B | 79997 | 19277 | 6000
CCK-MP-LOAD-WL021 | WL021 Lubrication & Mechanical Services | 79937 | 79937 | 6000
CCK-MP-LOAD-WL021 | Caterpillar 994H Wheel Loader WL021 | 79997 | 79997 | 6000
CCK-MP-LOAD-WL017 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 56947 | 7292 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDVLV-HYV02 | WL017 Valve Hyraulic control LH | 56923 | 12726 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDTNK | WL017 Hydraulic Tank | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 56923 | 12702 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STHLF | Steering System Hoses | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-BRHLF | Brake System Hoses | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -TRNSYS-TRHLF | Trans System Hoses | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP06 | Pump Hydralic Imp Tandem RH | 56923 | 12774 | 3100
CCK-MP-LOAD-WL017 -MANGMT-UMMMC | Mine Monitoring and Control | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -MANGMT-UMTRM | Transmission Management System | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -FRSUPP-FSALM | Fire System Alarm | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-BUCKT-BWELM | Bucket Wear Elements & GET | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-BUCKT | Bucket | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS-LEVER | Lever | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS-LNKGE | Linkage | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS-LIARM | Lift Arm | 56923 | 26692 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS-ARTIC | Articulation Hitch | 56923 | 10400 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS-CWEIG | Counterweight | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS-REFRM | Rear Frame | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS-FRFRM | Front Frame | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CHASS | Chassis | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CABIN-SBELT | Seat Belt | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CABIN-SEATS | Seat Operators | 56923 | 9177 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -STRUCT-CABIN-AIRCN | Air Conditioning System | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -GRSYST-ALCON | Controller Auto Lube | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -GRSYST-ALBPP | Pump Auto Lube | 56923 | 15813 | 3100
CCK-MP-LOAD-WL017 -GRSYST-GRTNK | Resevoir Auto Lube | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -GRSYST-GRINJ | Injectors Auto Lube | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -GRSYST | Auto Lube System Service | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDVLV-HYV01 | Valve Hydraulic Control | 56923 | 12726 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDOCO | Cooler Hydraulic Oil | 56923 | 12798 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDMT-HYM03 | Motor Hydraulic Axle Cooler Rear | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDMT-HYM02 | Motor Hydraulic Axle Cooler Front | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-BUCYR | Cylinder Tilt R/H | 56923 | 7268 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-BUCYL | Cylinder Tilt L/H | 56923 | 7268 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-HCYLR | Cylinder Lift R/H | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HDCYL-HCYLL | Cylinder Lift L/H | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP05 | Pump Hydraulic Axle Cooler | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Fan | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Steering & Fan | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot & Axle Cooling | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement | 56923 | 12774 | 3100
CCK-MP-LOAD-WL017 -HYDSYS | Hydraulic System | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 56923 | 12798 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 56923 | 12822 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STOCO | Oil Cooler Steering | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STCON | Controls Steering | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STVLV | Valve Steering | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STPMP-SESPP | Pump Secondary Steering | 56923 | 7268 | 3100
CCK-MP-LOAD-WL017 -STRSYS-STPMP | Pump Steering Centre | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-BRACC-ACC02 | Accumulator Brake Right | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-BRACC-ACC01 | Accumulator Brake Left | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-BRPMP | Pump Brake | 56923 | 2643 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-BRPRK | Park Brake Assembly | 56923 | 21903 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 56923 | 17424 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 56923 | 17424 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 56923 | 17413 | 3100
CCK-MP-LOAD-WL017 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 56923 | 17413 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 56923 | 17424 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 56923 | 17424 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 56923 | 1897 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 56923 | 17413 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-HDOCA-HYOCR | Cooler Hydraulic Oil Axle Rear | 56923 | 37614 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-HDOCA-HYOCF | Cooler Hydraulic Oil Axle Front | 56923 | 18034 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-RRDIF-TRNON | Trunnions Rear Axle Oscillation | 56923 | 17424 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-RRDIF | Rear Differential | 56923 | 17424 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-FRDIF | Front Differential | 56923 | 17413 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-CTRBR | Centre Bearing Drive Shaft | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 56923 | 3247 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -FDRSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -TRNSYS-TROLC | Cooler Transmission Oil | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -TRNSYS-TRPMP | Pump Transmission | 56923 | 1114 | 3100
CCK-MP-LOAD-WL017 -TRNSYS-TRTRF | Transmission Transfer Case | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -TRNSYS-TRQUE | Torque Converter | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -TRNSYS-TRANS | Transmission | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -ELCTLV-START-STMRH | Starter Motor R/H | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ELCTLV-START-STMLH | Starter Motor L/H | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ELCTLV-CHARG-BATTY | Batteries | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 -ELCTLV-CHARG-ALTER | Alternator 24V | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE-FUSYS-FUINJ | Injectors Fuel | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE-FUSYS-FULPP | Pump Fuel Priming | 56923 | 37527 | 3100
CCK-MP-LOAD-WL017 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -ENGINE-INTEX-AFTER | Aftercooler Engine | 56923 | 37527 | 3100
CCK-MP-LOAD-WL017 -ENGINE-INTEX-TBOR | Turbocharger R/H | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE-INTEX-TBOL | Turbocharger L/H | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE-COSYS-THERM | Thermostats/Regulators | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE-COSYS-COFAN | Fan Cooling System | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -ENGINE-COSYS-RADTR | Coolant Engine | 56923 | 7866 | 3700
CCK-MP-LOAD-WL017 -ENGINE-COSYS-RADTR | Radiator Engine | 56923 | 7866 | 3100
CCK-MP-LOAD-WL017 -ENGINE-COSYS-WTRPP | Pump Engine Water | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE-LUBSY-OILPP | Pump Engine Oil | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 -ENGINE | Engine Assembly Caterpillar C32 | 56923 | 689 | 3100
CCK-MP-LOAD-WL017 | WL017 Lube & Mechanical Services | 56923 | 56923 | 3100
CCK-MP-LOAD-WL017 | Caterpillar 993K Wheel Loader WL017 | 56923 | 56923 | 3100
CCK-MP-LOAD-WL004 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 64020 | 8411 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDTNK | Hydraulic Tank | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -ELCTLV-HARNS | Electrical Harness Low Voltage | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -STRSYS-STHLF | Steering System Hoses | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-BRHLF | Brake System Hoses | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -TRNSYS-TRHLF | Trans System Hoses, Lines and Fittings | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP06 | Pump Hydraulic Imp Tandem RH | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -ENGINE-COSYS-RADTR | Coolant Engine | 64003 | 15676 | 3700
CCK-MP-LOAD-WL004 -STRSYS-STCON | Steering Control | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-RRDIF-TRNON | Trunnions Rear Axle Oscillation | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -STRSYS-STOCO | Oil Cooler Steering | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -STRSYS-STPMP-SESPP | Pump Secondary Steering | 64003 | 2839 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-BRACC-ACC02 | Accumulator Brake Right | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-BRACC-ACC01 | Accumulator Brake Left | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-HDOCA-HYOCR | Oil Cooler Axle Rear | 64003 | 47018 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-HDOCA-HYOCF | Oil Cooler Axle Front | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-DRSHT-CTRBR | Centre Bearing Drive Shaft | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 | WL004 Lube & Mechanical Services | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -TRNSYS-TRTRF | Transmission Transfer Case | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -TRNSYS-TRQUE | Torque Converter | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -TRNSYS-TRPMP | Pump Transmission | 64003 | 527 | 3100
CCK-MP-LOAD-WL004 -TRNSYS-TROLC | Transmission Oil Cooler | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -TRNSYS-TRANS | Transmission | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CHASS-LNKGE | Linkage | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CHASS-LIARM | Lift Arm | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CHASS-LEVER | Lever | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CHASS-ARTIC | Articulation | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CABIN-SEATS | Operators Seat | 64003 | 4210 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CABIN-SBELT | Seat Belt | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -STRUCT-CABIN-AIRCN | Air Conditioning System | 64003 | 30472 | 3100
CCK-MP-LOAD-WL004 -STRUCT-BUCKT | Bucket | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 64003 | 21455 | 3100
CCK-MP-LOAD-WL004 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -STRSYS-STPMP | Pumps Steering Centre | 63992 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP05 | Pump Hydraulic Axle Cooler | 64003 | 57460 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Fan | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Steering & Fan | 63992 | 16994 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot & Axle Cooling | 63992 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement | 63992 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDMT-HYM03 | Motor Hydraulic Axle Cooler Rear | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDMT-HYM02 | Motor Hydraulic Axle Cooler Front | 63992 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 63992 | 8684 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDVLV-HYV04 | Valve Hydraulic | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDVLV-HYV03 | Valve Hydraulic | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDVLV-HYV02 | Valve Hydraulic | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDVLV-HYV01 | Valve Hydraulic | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 64003 | 16510 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist R/H | 64003 | 4401 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist L/H | 64003 | 7915 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket R/H | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket L/H | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -GRSYST-GRINJ | Auto Lube Injectors | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -GRSYST-ALBPP | Auto Lube Pump | 64003 | 8390 | 3100
CCK-MP-LOAD-WL004 -GRSYST | Auto Lube System Service | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-RRDIF | Rear Axle Oscillation Group | 64003 | 30307 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-RRDIF | Rear Differential | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-FRDIF | Front Differential | 64003 | 5465 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 64003 | 2839 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 64006 | 26785 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 64006 | 8113 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 64006 | 8394 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-DRSHT | Input Drive Shafts Group | 64006 | 64006 | 3100
CCK-MP-LOAD-WL004 -FDRSYS-DRSHT | Drive Shafts Group | 64006 | 64006 | 3100
CCK-MP-LOAD-WL004 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -ENGINE-INTEX-TBOR | Turbocharger R/H | 64003 | 8669 | 3100
CCK-MP-LOAD-WL004 -ENGINE-INTEX-TBOL | Turbocharger L/H | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 64006 | 15676 | 3100
CCK-MP-LOAD-WL004 -ENGINE-INTEX-AFTER | Aftercooler Engine | 64003 | 64003 | 3100
CCK-MP-LOAD-WL004 -ENGINE-FUSYS-FULPP | Fuel Transfer Pump | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -ENGINE-COSYS-WTRPP | Water Pump Engine | 64003 | 8684 | 3100
CCK-MP-LOAD-WL004 -ENGINE-COSYS-THERM | Thermostats/Regulators | 64003 | 15676 | 3100
CCK-MP-LOAD-WL004 -ENGINE-COSYS-RADTR | Radiator Engine | 64006 | 15676 | 3100
CCK-MP-LOAD-WL004 -ENGINE-COSYS-COFAN | Fan Cooling System | 64003 | 8669 | 3100
CCK-MP-LOAD-WL004 -ENGINE | Engine Assembly Caterpillar C32 | 64006 | 15676 | 3100
CCK-MP-LOAD-WL004 -ELCTLV-START-STMUP | Starter Motor Upper | 64006 | 8684 | 3100
CCK-MP-LOAD-WL004 -ELCTLV-START-STMLO | Starter Motor Lower | 64006 | 8684 | 3100
CCK-MP-LOAD-WL004 -ELCTLV-CHARG-ALTER | Alternator 24V | 64006 | 8730 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 64006 | 2839 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 64006 | 8016 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 64006 | 15676 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 64006 | 8394 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-BRPRK | Park Brake Assembly | 64006 | 18462 | 3100
CCK-MP-LOAD-WL004 -BRKSYS-BRPMP | Pump Brake | 64006 | 15676 | 3100
CCK-MP-LOAD-WL004 | Caterpillar 993K Wheel Loader WL004 | 64006 | 64006 | 3100
CCK-MP-DOZR-WD204 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 83662 | 16258 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BACCM | Brake Accumulator Front RH | 38735 | 38735 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BACCM | Brake Accumulator Front LH | 38735 | 38735 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDHLF-HDHMH | WD204 Hydraulic System Hoses Main | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDHLF-HDHPS | WD204 Hyd System Hoses Pilot Sys | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -TRNSYS-TRHLF | WD204 Trans System Hoses Lines Fittings | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -TRNSYS-TRTRF | WD204 Transmission Transfer Case | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -TRNSYS-TRQUE | WD204 Torque Converter | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -TRNSYS-TRPMP | WD204 Pump Transmission | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -TRNSYS-TROLC | WD204 Transmission Oil Cooler | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -TRNSYS-TRANS | WD204 Transmission | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -TRNSYS | WD204 Transmission System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-STLAD | WD204 Steps and Ladders | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-PNLGU | WD204 Panels and Guards | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-PLHAN | WD204 Platforms and Handrails | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-TRNON | WD204 Trunnion | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-ROPSS | WD204 Roll Over Protective Structure | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-REFRM | WD204 Rear Frame | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-PUARM | WD204 Push Arm | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-LNKGE | WD204 Link Stabilizer | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-FRFRM | WD204 Front Frame | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-CWEIG | WD204 Counterweight | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS-ARTIC | WD204 Articulation | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CHASS | WD204 Chassis | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN-SEATS | WD204 Operators Seat | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN-SBELT | WD204 Seat Belt | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN-GLASS | WD204 Glass | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN-CABPR | WD204 Cabin Pressurisation System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN-CABES | WD204 Cabin Entertainment System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN-CABCO | WD204 Cabin Controls | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN-AIRCN | WD204 Air Conditioning System | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -STRUCT-CABIN | WD204 Operators Cabin | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -STRUCT-BLADE | WD204 Blade | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRUCT | WD204 Structure | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STVLV-VLV04 | WD204 Valve Steering Neutraliser R/H | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STVLV-VLV03 | WD204 Valve Steering Neutraliser L/H | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STVLV-VLV02 | WD204 Valve Steering Pilot (STIC Steeri | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STVLV-VLV01 | WD204 Valve Steering Control | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STVLV | WD204 Valve Steering | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STTNK | WD204 Tank Steering | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STRCY-STCYR | WD204 Cylinder Steering R/H | 83628 | 18934 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STRCY-STCYL | WD204 Cylinder Steering L/H | 83628 | 4368 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STRCY | WD204 Cylinders Steering | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STPMP-STP03 | WD204 Pump Steering Secondary / Emergen | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STPMP-STP02 | WD204 Pump Steering Pilot / Axle Oil Co | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STPMP-STP01 | WD204 Pump Steering Main | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STPMP | WD204 Pumps Steering | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STHLF | WD204 Steering System Hoses Lines and F | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -STRSYS-STCON | WD204 Steering Controls | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -STRSYS | WD204 Steering System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -MANGMT-UMMMC | WD204 Mine Monitoring and Control | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -MANGMT-UMMC | WD204 Machine Management System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -MANGMT-UMENG | WD204 Engine Management System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -MANGMT | WD204 Unit Management | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HYDPP-HYP03 | WD204 Pump Hydraulic Fan | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HYDPP-HYP02 | WD204 Pump Hydraulic Pilot | 83628 | 28053 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HYDPP-HYP01 | WD204 Pump Hydraulic Implement | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HYDPP | WD204 Pumps Hydraulic | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HYDMT-HYM02 | WD204 Motor / Pump Axle Cooling | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HYDMT-HYM01 | WD204 Motor Hydraulic Fan High Temp | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HYDMT | WD204 Hydraulic Motors | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV08 | WD204 Valve Solenoid Hydraulic Lockout | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV07 | WD204 Valve Pilot Relief | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV06 | WD204 Valve Make Up Hydraulic Fan | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV05 | WD204 Valve Demand Hydraulic Fan | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV04 | WD204 Valve Hydraulic Fan | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV03 | WD204 Valve Hydraulic Manual Lowering C | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV02 | WD204 Valve Hydraulic Dual Tilt Control | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV-HYV01 | WD204 Valve Hydraulic Main Control | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDVLV | WD204 Valves Hydraulic | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDTNK | WD204 Tank Hydraulic | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDOCO | WD204 Oil Cooler Hydraulic | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDHLF | WD204 Hydraulic System Hoses Lines Fitt | 83628 | 38735 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDCYL-BTCYR | WD204 Cylinder Blade Tilt R/H | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDCYL-BTCYL | WD204 Cylinder Blade Tilt L/H | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDCYL-BLCYR | WD204 Cylinder Blade Lift R/H | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDCYL-BLCYL | WD204 Cylinder Blade Lift L/H | 83628 | 3711 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDCYL | WD204 Cylinders Hydraulic | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS-HDCON | WD204 Controls Hydraulic | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -HYDSYS | WD204 Hydraulic System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -GRSYST-GRTNK | WD204 Auto Lube Reservoir | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -GRSYST-GRINJ | WD204 Auto Lube Injectors | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -GRSYST-ALHLF | WD204 Auto Lube Hoses Lines Fittings | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -GRSYST-ALELC | WD204 Auto Lube Electrical | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -GRSYST-ALCON | WD204 Auto Lube Controller | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -GRSYST-ALBPP | WD204 Auto Lube Pump | 83628 | 30378 | 6300
CCK-MP-DOZR-WD204 -GRSYST | WD204 Grease Lubrication System | 83628 | 4244 | 6300
CCK-MP-DOZR-WD204 -FRSUPP-FSMAN-EXTIN | WD204 Hand Held Fire Extinguisher | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FRSUPP-FSMAN | WD204 Fire Suppression Manual | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FRSUPP-FSAUT-FFOAM | WD204 Fire Suppression Foam | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FRSUPP-FSAUT | WD204 Fire Suppression Automatic | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FRSUPP-FSALM | WD204 Fire System Alarm | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FRSUPP | WD204 Fire Suppression System | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-WHTYR-POS04 | WD204 Tyre Position 4 | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-WHTYR-POS03 | WD204 Tyre Position 3 | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-WHTYR-POS02 | WD204 Tyre Position 2 | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-WHTYR-POS01 | WD204 Tyre Position 1 | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-WHTYR | WD204 Wheels Tyres and Rims | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-RRDIF-TRNON | WD204 Trunnions Rear Differential | 83628 | 4677 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-RRDIF | WD204 Rear Differential | 83628 | 4677 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-FRDIF | WD204 Front Differential | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR04 | WD204 Final Drive Position 4 | 83628 | 16224 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR03 | WD204 Final Drive Position 3 | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR02 | WD204 Final Drive Position 2 | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-FDRVE-FDR01 | WD204 Final Drive Position 1 | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-FDRVE | WD204 Final Drives | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT04 | WD204 Drive Shaft Cntr Bearing to Front | 83628 | 19866 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT03 | WD204 Drive Shaft Transmission to Cntr | 83628 | 2002 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT02 | WD204 Drive Shaft Transmission to Rear | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-DRSHT-SHT01 | WD204 Drive Shaft T/C to Transmission | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-DRSHT | WD204 Drive Shafts | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-AXLEC-TVLVR | WD204 Thermal Bypass Valve Rear Axle Co | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-AXLEC-TVLVF | WD204 Thermal Bypass Valve Front Axle C | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-AXLEC-OILCR | WD204 Oil Cooler Axle Rear | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-AXLEC-OILCF | WD204 Oil Cooler Axle Front | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -FDRSYS-AXLEC | WD204 Axle Cooling | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -FDRSYS | WD204 Final Drive System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE-LUBSY-OILPP | WD204 Oil Pump Engine | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -ENGINE-LUBSY-ENOLC | WD204 Oil Cooler Engine | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -ENGINE-LUBSY | WD204 Engine Lubrication System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE-INTEX-TBORH | WD204 Turbocharger R/H | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ENGINE-INTEX-TBOLH | WD204 Turbocharger L/H | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ENGINE-INTEX-EXHST | WD204 Exhaust System | 83628 | 45483 | 6300
CCK-MP-DOZR-WD204 -ENGINE-INTEX-AIRFL | WD204 Air Filtration System | 83628 | 28312 | 6300
CCK-MP-DOZR-WD204 -ENGINE-INTEX-AFTER | WD204 Aftercooler | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -ENGINE-INTEX | WD204 Intake and Exhaust System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE-FUSYS-FULTP | WD204 Fuel Transfer Pump | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ENGINE-FUSYS-FULTK | WD204 Fuel Tank | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE-FUSYS-FULPP | WD204 Fuel Priming Pump | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -ENGINE-FUSYS-FUINJ | WD204 Fuel Injectors | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ENGINE-FUSYS-FUHLF | WD204 Fuel System Hoses Lines and Fitti | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE-FUSYS | WD204 Fuel System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE-COSYS-WTRPP | WD204 Water Pump Engine | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ENGINE-COSYS-THERM | WD204 Thermostats/Regulators | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ENGINE-COSYS-RADTR | WD204 Radiator Engine | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -ENGINE-COSYS-CSHLF | WD204 Cooling System Hoses Lines and Fi | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ENGINE-COSYS-COFAN | WD204 Cooling Fan | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE-COSYS-BELTS | WD204 Engine Belts | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -ENGINE-COSYS | WD204 Engine Cooling System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ENGINE | WD204 Engine Assembly Caterpillar C32 | 83628 | 15298 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-START-STMRH | WD204 Starter Motor R/H | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-START-STMLH | WD204 Starter Motor L/H | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-START | WD204 Starting System Low Voltage | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-LIGHT | WD204 Lighting Low Voltage | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-HARNS | WD204 Electrical Harness Low Voltage | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-CONTL | WD204 Electrical Controls Low Voltage | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-CHARG-BATTY | WD204 Batteries | 83628 | 25307 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-CHARG-ALTER | WD204 Alternator 24V | 83628 | 3767 | 6300
CCK-MP-DOZR-WD204 -ELCTLV-CHARG | WD204 Charging System Low Voltage | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -ELCTLV | WD204 Electrical System Low Voltage 24V | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -COMMUN-RADIO | WD204 Two Way Radio | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -COMMUN-FLMGT | WD204 Fleet Management | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -COMMUN | WD204 Communications | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-SRVBK-SVBRR | WD204 Service Brake R/H Rear | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-SRVBK-SVBRF | WD204 Service Brake R/H Front | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-SRVBK-SVBLR | WD204 Service Brake L/H Rear | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-SRVBK-SVBLF | WD204 Service Brake L/H Front | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-SRVBK | WD204 Service Brake | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV-VLV07 | WD204 Parking Brake Control Valve | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV-VLV06 | WD204 Brake Manifold Rear | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV-VLV05 | WD204 Brake Manifold Front | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV-VLV04 | WD204 Brake Pump Check Valve | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV-VLV03 | WD204 Park Brake Release Check Valve | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV-VLV02 | WD204 Brake Accumulator Charging Valve | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV-VLV01 | WD204 Service Brake Control Valve | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRVLV | WD204 Valves Brake | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRPRK | WD204 Park Brake Assembly | 83628 | 854 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRPMP | WD204 Pump Brake | 83628 | 7365 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BRHLF | WD204 Brake System Hoses Lines and Fitt | 83583 | 7365 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BACCM-BACCR | WD204 Brake Accumulator Rear | 83628 | 38735 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BACCM-BACCF | WD204 Brake Accumulator Front | 83628 | 38735 | 6300
CCK-MP-DOZR-WD204 -BRKSYS-BACCM | WD204 Brake Accumulators | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 -BRKSYS | WD204 Braking System | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 | WD204 Mechanical & Lube Services | 83628 | 83628 | 6300
CCK-MP-DOZR-WD204 | Caterpillar 854K Wheel Dozer, WD204 | 83628 | 83628 | 6300
CCK-MP-DOZR-WD203 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 80917 | 13611 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BACCM | Brake Accumulator Front RH | 23335 | 23335 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BACCM | Brake Accumulator Front LH | 27939 | 27939 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDHLF-HDHMH | WD203 Hydraulic System Hoses Main | 80898 | 13604 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDHLF-HDHPS | WD203 Hyd System Hoses Pilot Sys | 80898 | 13604 | 6300
CCK-MP-DOZR-WD203 -TRNSYS-TRHLF | WD203 Trans System Hoses Lines Fittings | 80875 | 23335 | 6300
CCK-MP-DOZR-WD203 -TRNSYS-TRTRF | WD203 Transmission Transfer Case | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -TRNSYS-TRQUE | WD203 Torque Converter | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -TRNSYS-TRPMP | WD203 Pump Transmission | 80875 | 10669 | 6300
CCK-MP-DOZR-WD203 -TRNSYS-TROLC | WD203 Transmission Oil Cooler | 80875 | 10669 | 6300
CCK-MP-DOZR-WD203 -TRNSYS-TRANS | WD203 Transmission | 80875 | 10670 | 6300
CCK-MP-DOZR-WD203 -TRNSYS | WD203 Transmission System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-STLAD | WD203 Steps and Ladders | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-PNLGU | WD203 Panels and Guards | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-PLHAN | WD203 Platforms and Handrails | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-TRNON | WD203 Trunnion | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-ROPSS | WD203 Roll Over Protective Structure | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-REFRM | WD203 Rear Frame | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-PUARM | WD203 Push Arm | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-LNKGE | WD203 Link Stabilizer | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-FRFRM | WD203 Front Frame | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-CWEIG | WD203 Counterweight | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS-ARTIC | WD203 Articulation | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CHASS | WD203 Chassis | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN-SEATS | WD203 Operators Seat | 80875 | 6377 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN-SBELT | WD203 Seat Belt | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN-GLASS | WD203 Glass | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN-CABPR | WD203 Cabin Pressurisation System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN-CABES | WD203 Cabin Entertainment System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN-CABCO | WD203 Cabin Controls | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN-AIRCN | WD203 Air Conditioning System | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -STRUCT-CABIN | WD203 Operators Cabin | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRUCT-BLADE | WD203 Blade | 80875 | 36295 | 6300
CCK-MP-DOZR-WD203 -STRUCT | WD203 Structure | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STVLV-VLV04 | WD203 Valve Steering Neutraliser R/H | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STVLV-VLV03 | WD203 Valve Steering Neutraliser L/H | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STVLV-VLV02 | WD203 Valve Steering Pilot (STIC Steeri | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STVLV-VLV01 | WD203 Valve Steering Control | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STVLV | WD203 Valve Steering | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STTNK | WD203 Tank Steering | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STRCY-STCYR | WD203 Cylinder Steering R/H | 80875 | 12492 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STRCY-STCYL | WD203 Cylinder Steering L/H | 80875 | 4483 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STRCY | WD203 Cylinders Steering | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STPMP-STP03 | WD203 Pump Steering Secondary / Emergen | 80875 | 10670 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STPMP-STP02 | WD203 Pump Steering Pilot / Axle Oil Co | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STPMP-STP01 | WD203 Pump Steering Main | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STPMP | WD203 Pumps Steering | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STHLF | WD203 Steering System Hoses Lines and F | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -STRSYS-STCON | WD203 Steering Controls | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -STRSYS | WD203 Steering System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -MANGMT-UMMMC | WD203 Mine Monitoring and Control | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -MANGMT-UMMC | WD203 Machine Management System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -MANGMT-UMENG | WD203 Engine Management System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -MANGMT | WD203 Unit Management | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HYDPP-HYP03 | WD203 Pump Hydraulic Fan | 80875 | 4797 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HYDPP-HYP02 | WD203 Pump Hydraulic Pilot | 80875 | 31528 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HYDPP-HYP01 | WD203 Pump Hydraulic Implement | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HYDPP | WD203 Pumps Hydraulic | 80875 | 62261 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HYDMT-HYM02 | WD203 Motor / Pump Axle Cooling | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HYDMT-HYM01 | WD203 Motor Hydraulic Fan High Temp | 80875 | 10670 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HYDMT | WD203 Hydraulic Motors | 80875 | 67189 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV08 | WD203 Valve Solenoid Hydraulic Lockout | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV07 | WD203 Valve Pilot Relief | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV06 | WD203 Valve Make Up Hydraulic Fan | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV05 | WD203 Valve Demand Hydraulic Fan | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV04 | WD203 Valve Hydraulic Fan | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV03 | WD203 Valve Hydraulic Manual Lowering C | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV02 | WD203 Valve Hydraulic Dual Tilt Control | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV-HYV01 | WD203 Valve Hydraulic Main Control | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDVLV | WD203 Valves Hydraulic | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDTNK | WD203 Tank Hydraulic | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDOCO | WD203 Oil Cooler Hydraulic | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDHLF | WD203 Hydraulic System Hoses Lines Fitt | 80875 | 31528 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDCYL-BTCYR | WD203 Cylinder Blade Tilt R/H | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDCYL-BTCYL | WD203 Cylinder Blade Tilt L/H | 80875 | 11509 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDCYL-BLCYR | WD203 Cylinder Blade Lift R/H | 80875 | 23335 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDCYL-BLCYL | WD203 Cylinder Blade Lift L/H | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDCYL | WD203 Cylinders Hydraulic | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS-HDCON | WD203 Controls Hydraulic | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -HYDSYS | WD203 Hydraulic System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -GRSYST-GRTNK | WD203 Auto Lube Reservoir | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -GRSYST-GRINJ | WD203 Auto Lube Injectors | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -GRSYST-ALHLF | WD203 Auto Lube Hoses Lines Fittings | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -GRSYST-ALELC | WD203 Auto Lube Electrical | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -GRSYST-ALCON | WD203 Auto Lube Controller | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -GRSYST-ALBPP | WD203 Auto Lube Pump | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -GRSYST | WD203 Grease Lubrication System | 80875 | 10669 | 6300
CCK-MP-DOZR-WD203 -FRSUPP-FSMAN-EXTIN | WD203 Hand Held Fire Extinguisher | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FRSUPP-FSMAN | WD203 Fire Suppression Manual | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FRSUPP-FSAUT-FFOAM | WD203 Fire Suppression Foam | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FRSUPP-FSAUT | WD203 Fire Suppression Automatic | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FRSUPP-FSALM | WD203 Fire System Alarm | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FRSUPP | WD203 Fire Suppression System | 80875 | 23335 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-WHTYR-POS04 | WD203 Tyre Position 4 | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-WHTYR-POS03 | WD203 Tyre Position 3 | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-WHTYR-POS02 | WD203 Tyre Position 2 | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-WHTYR-POS01 | WD203 Tyre Position 1 | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-WHTYR | WD203 Wheels Tyres and Rims | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-RRDIF-TRNON | WD203 Trunnions Rear Differential | 80875 | 10669 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-RRDIF | WD203 Rear Differential | 80875 | 10669 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-FRDIF | WD203 Front Differential | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-FDRVE-FDR04 | WD203 Final Drive Position 4 | 80875 | 9561 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-FDRVE-FDR03 | WD203 Final Drive Position 3 | 80875 | 12738 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-FDRVE-FDR02 | WD203 Final Drive Position 2 | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-FDRVE-FDR01 | WD203 Final Drive Position 1 | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-FDRVE | WD203 Final Drives | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT04 | WD203 Drive Shaft Cntr Bearing to Front | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT03 | WD203 Drive Shaft Transmission to Cntr | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT02 | WD203 Drive Shaft Transmission to Rear | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-DRSHT-SHT01 | WD203 Drive Shaft T/C to Transmission | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-DRSHT | WD203 Drive Shafts | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-AXLEC-TVLVR | WD203 Thermal Bypass Valve Rear Axle Co | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-AXLEC-TVLVF | WD203 Thermal Bypass Valve Front Axle C | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-AXLEC-OILCR | WD203 Oil Cooler Axle Rear | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-AXLEC-OILCF | WD203 Oil Cooler Axle Front | 80875 | 10670 | 6300
CCK-MP-DOZR-WD203 -FDRSYS-AXLEC | WD203 Axle Cooling | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -FDRSYS | WD203 Final Drive System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-LUBSY-OILPP | WD203 Oil Pump Engine | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-LUBSY-ENOLC | WD203 Oil Cooler Engine | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-LUBSY | WD203 Engine Lubrication System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-INTEX-TBORH | WD203 Turbocharger R/H | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-INTEX-TBOLH | WD203 Turbocharger L/H | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-INTEX-EXHST | WD203 Exhaust System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-INTEX-AIRFL | WD203 Air Filtration System | 80875 | 44315 | 6300
CCK-MP-DOZR-WD203 -ENGINE-INTEX-AFTER | WD203 Aftercooler | 80875 | 10669 | 6300
CCK-MP-DOZR-WD203 -ENGINE-INTEX | WD203 Intake and Exhaust System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-FUSYS-FULTP | WD203 Fuel Transfer Pump | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -ENGINE-FUSYS-FULTK | WD203 Fuel Tank | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-FUSYS-FULPP | WD203 Fuel Priming Pump | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-FUSYS-FUINJ | WD203 Fuel Injectors | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-FUSYS-FUHLF | WD203 Fuel System Hoses Lines and Fitti | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-FUSYS | WD203 Fuel System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-COSYS-WTRPP | WD203 Water Pump Engine | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-COSYS-THERM | WD203 Thermostats/Regulators | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-COSYS-RADTR | WD203 Radiator Engine | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-COSYS-CSHLF | WD203 Cooling System Hoses Lines and Fi | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-COSYS-COFAN | WD203 Cooling Fan | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE-COSYS-BELTS | WD203 Engine Belts | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ENGINE-COSYS | WD203 Engine Cooling System | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ENGINE | WD203 Engine Assembly Caterpillar C32 | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-START-STMRH | WD203 Starter Motor R/H | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-START-STMLH | WD203 Starter Motor L/H | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-START | WD203 Starting System Low Voltage | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-LIGHT | WD203 Lighting Low Voltage | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-HARNS | WD203 Electrical Harness Low Voltage | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-CONTL | WD203 Electrical Controls Low Voltage | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-CHARG-BATTY | WD203 Batteries | 80875 | 23335 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-CHARG-ALTER | WD203 Alternator 24V | 80875 | 995 | 6300
CCK-MP-DOZR-WD203 -ELCTLV-CHARG | WD203 Charging System Low Voltage | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -ELCTLV | WD203 Electrical System Low Voltage 24V | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -COMMUN-RADIO | WD203 Two Way Radio | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -COMMUN-FLMGT | WD203 Fleet Management | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -COMMUN | WD203 Communications | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-SRVBK-SVBRR | WD203 Service Brake R/H Rear | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-SRVBK-SVBRF | WD203 Service Brake R/H Front | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-SRVBK-SVBLR | WD203 Service Brake L/H Rear | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-SRVBK-SVBLF | WD203 Service Brake L/H Front | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-SRVBK | WD203 Service Brake | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV-VLV07 | WD203 Parking Brake Control Valve | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV-VLV06 | WD203 Brake Manifold Rear | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV-VLV05 | WD203 Brake Manifold Front | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV-VLV04 | WD203 Brake Pump Check Valve | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV-VLV03 | WD203 Park Brake Release Check Valve | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV-VLV02 | WD203 Brake Accumulator Charging Valve | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV-VLV01 | WD203 Service Brake Control Valve | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRVLV | WD203 Valves Brake | 80875 | 80875 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRPRK | WD203 Park Brake Assembly | 80875 | 1817 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRPMP | WD203 Pump Brake | 80875 | 10669 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BRHLF | WD203 Brake System Hoses Lines and Fitt | 80875 | 13604 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BACCM-BACCR | WD203 Brake Accumulator Rear | 80875 | 23335 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BACCM-BACCF | WD203 Brake Accumulator Front | 80898 | 27939 | 6300
CCK-MP-DOZR-WD203 -BRKSYS-BACCM | WD203 Brake Accumulators | 80898 | 80898 | 6300
CCK-MP-DOZR-WD203 -BRKSYS | WD203 Braking System | 80898 | 80898 | 6300
CCK-MP-DOZR-WD203 | WD203 Mechanical & Lube Services | 80898 | 80898 | 6300
CCK-MP-DOZR-WD203 | Caterpillar 854K Wheel Dozer, WD203 | 80898 | 80898 | 6300
CCK-MP-DOZR-WD202 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 79930 | 15755 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BACCM | Brake Accumulator Front RH | 21666 | 21666 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BACCM | Brake Accumulator Front LH | 21666 | 21666 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDHLF-HDHMH | WD202 Hydraulic System Hoses Main | 79930 | 10962 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDHLF-HDHPS | WD202 Hyd System Hoses Pilot Sys | 79930 | 10962 | 6300
CCK-MP-DOZR-WD202 -TRNSYS-TRHLF | WD202 Trans System Hoses Lines Fittings | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 | WD202 Mechanical & Lube Services | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -TRNSYS-TRTRF | WD202 Transmission Transfer Case | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -TRNSYS-TRQUE | WD202 Torque Converter | 79903 | 806 | 6300
CCK-MP-DOZR-WD202 -TRNSYS-TRPMP | WD202 Pump Transmission | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -TRNSYS-TROLC | WD202 Transmission Oil Cooler | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -TRNSYS-TRANS | WD202 Transmission | 79903 | 9020 | 6300
CCK-MP-DOZR-WD202 -TRNSYS | WD202 Transmission System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-STLAD | WD202 Steps and Ladders | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-PNLGU | WD202 Panels and Guards | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-PLHAN | WD202 Platforms and Handrails | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-TRNON | WD202 Trunnion | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-ROPSS | WD202 Roll Over Protective Structure | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-REFRM | WD202 Rear Frame | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-PUARM | WD202 Push Arm | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-LNKGE | WD202 Link Stabilizer | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-FRFRM | WD202 Front Frame | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-CWEIG | WD202 Counterweight | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS-ARTIC | WD202 Articulation | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CHASS | WD202 Chassis | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN-SEATS | WD202 Operators Seat | 79903 | 3832 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN-SBELT | WD202 Seat Belt | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN-GLASS | WD202 Glass | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN-CABPR | WD202 Cabin Pressurisation System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN-CABES | WD202 Cabin Entertainment System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN-CABCO | WD202 Cabin Controls | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN-AIRCN | WD202 Air Conditioning System | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -STRUCT-CABIN | WD202 Operators Cabin | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT-BLADE | WD202 Blade | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRUCT | WD202 Structure | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STVLV-VLV04 | WD202 Valve Steering Neutraliser R/H | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STVLV-VLV03 | WD202 Valve Steering Neutraliser L/H | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STVLV-VLV02 | WD202 Valve Steering Pilot (STIC Steeri | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STVLV-VLV01 | WD202 Valve Steering Control | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STVLV | WD202 Valve Steering | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STTNK | WD202 Tank Steering | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STRCY-STCYR | WD202 Cylinder Steering R/H | 79903 | 4247 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STRCY-STCYL | WD202 Cylinder Steering L/H | 79903 | 4247 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STRCY | WD202 Cylinders Steering | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STPMP-STP03 | WD202 Pump Steering Secondary / Emergen | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STPMP-STP02 | WD202 Pump Steering Pilot / Axle Oil Co | 79903 | 15755 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STPMP-STP01 | WD202 Pump Steering Main | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STPMP | WD202 Pumps Steering | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STHLF | WD202 Steering System Hoses Lines and F | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -STRSYS-STCON | WD202 Steering Controls | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -STRSYS | WD202 Steering System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -MANGMT-UMMMC | WD202 Mine Monitoring and Control | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -MANGMT-UMMC | WD202 Machine Management System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -MANGMT-UMENG | WD202 Engine Management System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -MANGMT | WD202 Unit Management | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HYDPP-HYP03 | WD202 Pump Hydraulic Fan | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HYDPP-HYP02 | WD202 Pump Hydraulic Pilot | 79903 | 28576 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HYDPP-HYP01 | WD202 Pump Hydraulic Implement | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HYDPP | WD202 Pumps Hydraulic | 79903 | 64363 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HYDMT-HYM02 | WD202 Motor / Pump Axle Cooling | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HYDMT-HYM01 | WD202 Motor Hydraulic Fan High Temp | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HYDMT | WD202 Hydraulic Motors | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV08 | WD202 Valve Solenoid Hydraulic Lockout | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV07 | WD202 Valve Pilot Relief | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV06 | WD202 Valve Make Up Hydraulic Fan | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV05 | WD202 Valve Demand Hydraulic Fan | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV04 | WD202 Valve Hydraulic Fan | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV03 | WD202 Valve Hydraulic Manual Lowering C | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV02 | WD202 Valve Hydraulic Dual Tilt Control | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV-HYV01 | WD202 Valve Hydraulic Main Control | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDVLV | WD202 Valves Hydraulic | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDTNK | WD202 Tank Hydraulic | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDOCO | WD202 Oil Cooler Hydraulic | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDHLF | WD202 Hydraulic System Hoses Lines Fitt | 79903 | 40688 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDCYL-BTCYR | WD202 Cylinder Blade Tilt R/H | 79903 | 21729 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDCYL-BTCYL | WD202 Cylinder Blade Tilt L/H | 79903 | 21729 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDCYL-BLCYR | WD202 Cylinder Blade Lift R/H | 79903 | 1877 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDCYL-BLCYL | WD202 Cylinder Blade Lift L/H | 79903 | 11940 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDCYL | WD202 Cylinders Hydraulic | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS-HDCON | WD202 Controls Hydraulic | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -HYDSYS | WD202 Hydraulic System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -GRSYST-GRTNK | WD202 Auto Lube Reservoir | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -GRSYST-GRINJ | WD202 Auto Lube Injectors | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -GRSYST-ALHLF | WD202 Auto Lube Hoses Lines Fittings | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -GRSYST-ALELC | WD202 Auto Lube Electrical | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -GRSYST-ALCON | WD202 Auto Lube Controller | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -GRSYST-ALBPP | WD202 Auto Lube Pump | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -GRSYST | WD202 Grease Lubrication System | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FRSUPP-FSMAN-EXTIN | WD202 Hand Held Fire Extinguisher | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FRSUPP-FSMAN | WD202 Fire Suppression Manual | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FRSUPP-FSAUT-FFOAM | WD202 Fire Suppression Foam | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FRSUPP-FSAUT | WD202 Fire Suppression Automatic | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FRSUPP-FSALM | WD202 Fire System Alarm | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FRSUPP | WD202 Fire Suppression System | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-WHTYR-POS04 | WD202 Tyre Position 4 | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-WHTYR-POS03 | WD202 Tyre Position 3 | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-WHTYR-POS02 | WD202 Tyre Position 2 | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-WHTYR-POS01 | WD202 Tyre Position 1 | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-WHTYR | WD202 Wheels Tyres and Rims | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-RRDIF-TRNON | WD202 Trunnions Rear Differential | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-RRDIF | WD202 Rear Differential | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-FRDIF | WD202 Front Differential | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-FDRVE-FDR04 | WD202 Final Drive Position 4 | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-FDRVE-FDR03 | WD202 Final Drive Position 3 | 79903 | 1627 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-FDRVE-FDR02 | WD202 Final Drive Position 2 | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-FDRVE-FDR01 | WD202 Final Drive Position 1 | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-FDRVE | WD202 Final Drives | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT04 | WD202 Drive Shaft Cntr Bearing to Front | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT03 | WD202 Drive Shaft Transmission to Cntr | 79903 | 3832 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT02 | WD202 Drive Shaft Transmission to Rear | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-DRSHT-SHT01 | WD202 Drive Shaft T/C to Transmission | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-DRSHT | WD202 Drive Shafts | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-AXLEC-TVLVR | WD202 Thermal Bypass Valve Rear Axle Co | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-AXLEC-TVLVF | WD202 Thermal Bypass Valve Front Axle C | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-AXLEC-OILCR | WD202 Oil Cooler Axle Rear | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-AXLEC-OILCF | WD202 Oil Cooler Axle Front | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -FDRSYS-AXLEC | WD202 Axle Cooling | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -FDRSYS | WD202 Final Drive System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-LUBSY-OILPP | WD202 Oil Pump Engine | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-LUBSY-ENOLC | WD202 Oil Cooler Engine | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-LUBSY | WD202 Engine Lubrication System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-INTEX-TBORH | WD202 Turbocharger R/H | 79903 | 1806 | 6300
CCK-MP-DOZR-WD202 -ENGINE-INTEX-TBOLH | WD202 Turbocharger L/H | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ENGINE-INTEX-EXHST | WD202 Exhaust System | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -ENGINE-INTEX-AIRFL | WD202 Air Filtration System | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -ENGINE-INTEX-AFTER | WD202 Aftercooler | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -ENGINE-INTEX | WD202 Intake and Exhaust System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-FUSYS-FULTP | WD202 Fuel Transfer Pump | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ENGINE-FUSYS-FULTK | WD202 Fuel Tank | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-FUSYS-FULPP | WD202 Fuel Priming Pump | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-FUSYS-FUINJ | WD202 Fuel Injectors | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ENGINE-FUSYS-FUHLF | WD202 Fuel System Hoses Lines and Fitti | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-FUSYS | WD202 Fuel System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-COSYS-WTRPP | WD202 Water Pump Engine | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ENGINE-COSYS-THERM | WD202 Thermostats/Regulators | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ENGINE-COSYS-RADTR | WD202 Radiator Engine | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -ENGINE-COSYS-CSHLF | WD202 Cooling System Hoses Lines and Fi | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ENGINE-COSYS-COFAN | WD202 Cooling Fan | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-COSYS-BELTS | WD202 Engine Belts | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE-COSYS | WD202 Engine Cooling System | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ENGINE | WD202 Engine Assembly Caterpillar C32 | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-START-STMRH | WD202 Starter Motor R/H | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-START-STMLH | WD202 Starter Motor L/H | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-START | WD202 Starting System Low Voltage | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-LIGHT | WD202 Lighting Low Voltage | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-HARNS | WD202 Electrical Harness Low Voltage | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-CONTL | WD202 Electrical Controls Low Voltage | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-CHARG-BATTY | WD202 Batteries | 79903 | 21205 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-CHARG-ALTER | WD202 Alternator 24V | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -ELCTLV-CHARG | WD202 Charging System Low Voltage | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -ELCTLV | WD202 Electrical System Low Voltage 24V | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -COMMUN-RADIO | WD202 Two Way Radio | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -COMMUN-FLMGT | WD202 Fleet Management | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -COMMUN | WD202 Communications | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-SRVBK-SVBRR | WD202 Service Brake R/H Rear | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-SRVBK-SVBRF | WD202 Service Brake R/H Front | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-SRVBK-SVBLR | WD202 Service Brake L/H Rear | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-SRVBK-SVBLF | WD202 Service Brake L/H Front | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-SRVBK | WD202 Service Brake | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV-VLV07 | WD202 Parking Brake Control Valve | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV-VLV06 | WD202 Brake Manifold Rear | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV-VLV05 | WD202 Brake Manifold Front | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV-VLV04 | WD202 Brake Pump Check Valve | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV-VLV03 | WD202 Park Brake Release Check Valve | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV-VLV02 | WD202 Brake Accumulator Charging Valve | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV-VLV01 | WD202 Service Brake Control Valve | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRVLV | WD202 Valves Brake | 79903 | 79903 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRPRK | WD202 Park Brake Assembly | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRPMP | WD202 Pump Brake | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BRHLF | WD202 Brake System Hoses Lines and Fitt | 79903 | 10962 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BACCM-BACCR | WD202 Brake Accumulator Rear | 79903 | 21666 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BACCM-BACCF | WD202 Brake Accumulator Front | 79930 | 21666 | 6300
CCK-MP-DOZR-WD202 -BRKSYS-BACCM | WD202 Brake Accumulators | 79930 | 79930 | 6300
CCK-MP-DOZR-WD202 -BRKSYS | WD202 Braking System | 79930 | 79930 | 6300
CCK-MP-DOZR-WD202 | WD202 Mechanical & Lube Services | 79930 | 79930 | 6300
CCK-MP-DOZR-WD202 | Caterpillar 854K Wheel Dozer, WD202 | 79930 | 79930 | 6300
CCK-MP-DOZR-WD201 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 81169 | 15756 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BACCM | Brake Accumulator Front RH | 39870 | 39870 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BACCM | Brake Accumulator Front LH | 39870 | 39870 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDHLF-HDHMH | WD201 Hydraulic System Hoses Main | 81106 | 12720 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDHLF-HDHPS | WD201 Hyd System Hoses Pilot Sys | 81106 | 12720 | 6300
CCK-MP-DOZR-WD201 -TRNSYS-TRHLF | WD201 Trans System Hoses Lines Fittings | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 | WD201 Mechanical & Lube Services | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -TRNSYS-TRTRF | WD201 Transmission Transfer Case | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -TRNSYS-TRQUE | WD201 Torque Converter | 81082 | 17929 | 6300
CCK-MP-DOZR-WD201 -TRNSYS-TRPMP | WD201 Pump Transmission | 81082 | 2675 | 6300
CCK-MP-DOZR-WD201 -TRNSYS-TROLC | WD201 Transmission Oil Cooler | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -TRNSYS-TRANS | WD201 Transmission | 81082 | 2675 | 6300
CCK-MP-DOZR-WD201 -TRNSYS | WD201 Transmission System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-STLAD | WD201 Steps and Ladders | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-PNLGU | WD201 Panels and Guards | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-PLHAN | WD201 Platforms and Handrails | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-TRNON | WD201 Trunnion | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-ROPSS | WD201 Roll Over Protective Structure | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-REFRM | WD201 Rear Frame | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-PUARM | WD201 Push Arm | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-LNKGE | WD201 Link Stabilizer | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-FRFRM | WD201 Front Frame | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-CWEIG | WD201 Counterweight | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS-ARTIC | WD201 Articulation | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CHASS | WD201 Chassis | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN-SEATS | WD201 Operators Seat | 81082 | 1968 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN-SBELT | WD201 Seat Belt | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN-GLASS | WD201 Glass | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN-CABPR | WD201 Cabin Pressurisation System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN-CABES | WD201 Cabin Entertainment System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN-CABCO | WD201 Cabin Controls | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN-AIRCN | WD201 Air Conditioning System | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -STRUCT-CABIN | WD201 Operators Cabin | 81082 | 5046 | 6300
CCK-MP-DOZR-WD201 -STRUCT-BLADE | WD201 Blade | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRUCT | WD201 Structure | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STVLV-VLV04 | WD201 Valve Steering Neutraliser R/H | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STVLV-VLV03 | WD201 Valve Steering Neutraliser L/H | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STVLV-VLV02 | WD201 Valve Steering Pilot (STIC Steeri | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STVLV-VLV01 | WD201 Valve Steering Control | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STVLV | WD201 Valve Steering | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STTNK | WD201 Tank Steering | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STRCY-STCYR | WD201 Cylinder Steering R/H | 81082 | 9810 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STRCY-STCYL | WD201 Cylinder Steering L/H | 81082 | 17929 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STRCY | WD201 Cylinders Steering | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP03 | WD201 Pump Steering Secondary / Emergen | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP02 | WD201 Pump Steering Pilot / Axle Oil Co | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STPMP-STP01 | WD201 Pump Steering Main | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STPMP | WD201 Pumps Steering | 81082 | 64312 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STHLF | WD201 Steering System Hoses Lines and F | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -STRSYS-STCON | WD201 Steering Controls | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -STRSYS | WD201 Steering System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -MANGMT-UMMMC | WD201 Mine Monitoring and Control | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -MANGMT-UMMC | WD201 Machine Management System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -MANGMT-UMENG | WD201 Engine Management System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -MANGMT | WD201 Unit Management | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HYDPP-HYP03 | WD201 Pump Hydraulic Fan | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HYDPP-HYP02 | WD201 Pump Hydraulic Pilot | 81082 | 29587 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HYDPP-HYP01 | WD201 Pump Hydraulic Implement | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HYDPP | WD201 Pumps Hydraulic | 81082 | 64312 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HYDMT-HYM02 | WD201 Motor / Pump Axle Cooling | 81082 | 14552 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HYDMT-HYM01 | WD201 Motor Hydraulic Fan High Temp | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HYDMT | WD201 Hydraulic Motors | 81082 | 62721 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV08 | WD201 Valve Solenoid Hydraulic Lockout | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV07 | WD201 Valve Pilot Relief | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV06 | WD201 Valve Make Up Hydraulic Fan | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV05 | WD201 Valve Demand Hydraulic Fan | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV04 | WD201 Valve Hydraulic Fan | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV03 | WD201 Valve Hydraulic Manual Lowering C | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV02 | WD201 Valve Hydraulic Dual Tilt Control | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV-HYV01 | WD201 Valve Hydraulic Main Control | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDVLV | WD201 Valves Hydraulic | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDTNK | WD201 Tank Hydraulic | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDOCO | WD201 Oil Cooler Hydraulic | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDHLF | WD201 Hydraulic System Hoses Lines Fitt | 81082 | 39870 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BTCYR | WD201 Cylinder Blade Tilt R/H | 81082 | 9810 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BTCYL | WD201 Cylinder Blade Tilt L/H | 81082 | 21309 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BLCYR | WD201 Cylinder Blade Lift R/H | 81082 | 12747 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDCYL-BLCYL | WD201 Cylinder Blade Lift L/H | 81082 | 4073 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDCYL | WD201 Cylinders Hydraulic | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS-HDCON | WD201 Controls Hydraulic | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -HYDSYS | WD201 Hydraulic System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -GRSYST-GRTNK | WD201 Auto Lube Reservoir | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -GRSYST-GRINJ | WD201 Auto Lube Injectors | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -GRSYST-ALHLF | WD201 Auto Lube Hoses Lines Fittings | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -GRSYST-ALELC | WD201 Auto Lube Electrical | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -GRSYST-ALCON | WD201 Auto Lube Controller | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -GRSYST-ALBPP | WD201 Auto Lube Pump | 81082 | 33400 | 6300
CCK-MP-DOZR-WD201 -GRSYST | WD201 Grease Lubrication System | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -FRSUPP-FSMAN-EXTIN | WD201 Hand Held Fire Extinguisher | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FRSUPP-FSMAN | WD201 Fire Suppression Manual | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FRSUPP-FSAUT-FFOAM | WD201 Fire Suppression Foam | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FRSUPP-FSAUT | WD201 Fire Suppression Automatic | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FRSUPP-FSALM | WD201 Fire System Alarm | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FRSUPP | WD201 Fire Suppression System | 81082 | 42365 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-WHTYR-POS04 | WD201 Tyre Position 4 | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-WHTYR-POS03 | WD201 Tyre Position 3 | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-WHTYR-POS02 | WD201 Tyre Position 2 | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-WHTYR-POS01 | WD201 Tyre Position 1 | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-WHTYR | WD201 Wheels Tyres and Rims | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-RRDIF-TRNON | WD201 Trunnions Rear Differential | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-RRDIF | WD201 Rear Differential | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-FRDIF | WD201 Front Differential | 81082 | 17330 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-FDRVE-FDR04 | WD201 Final Drive Position 4 | 81082 | 17929 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-FDRVE-FDR03 | WD201 Final Drive Position 3 | 81082 | 763 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-FDRVE-FDR02 | WD201 Final Drive Position 2 | 81082 | 17330 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-FDRVE-FDR01 | WD201 Final Drive Position 1 | 81082 | 23621 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-FDRVE | WD201 Final Drives | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT04 | WD201 Drive Shaft Cntr Bearing to Front | 81082 | 18673 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT03 | WD201 Drive Shaft Transmission to Cntr | 81082 | 18673 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT02 | WD201 Drive Shaft Transmission to Rear | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-DRSHT-SHT01 | WD201 Drive Shaft T/C to Transmission | 81082 | 34277 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-DRSHT | WD201 Drive Shafts | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-AXLEC-TVLVR | WD201 Thermal Bypass Valve Rear Axle Co | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-AXLEC-TVLVF | WD201 Thermal Bypass Valve Front Axle C | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-AXLEC-OILCR | WD201 Oil Cooler Axle Rear | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-AXLEC-OILCF | WD201 Oil Cooler Axle Front | 81082 | 17929 | 6300
CCK-MP-DOZR-WD201 -FDRSYS-AXLEC | WD201 Axle Cooling | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -FDRSYS | WD201 Final Drive System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE-LUBSY-OILPP | WD201 Oil Pump Engine | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-LUBSY-ENOLC | WD201 Oil Cooler Engine | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-LUBSY | WD201 Engine Lubrication System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE-INTEX-TBORH | WD201 Turbocharger R/H | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-INTEX-TBOLH | WD201 Turbocharger L/H | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-INTEX-EXHST | WD201 Exhaust System | 81082 | 39870 | 6300
CCK-MP-DOZR-WD201 -ENGINE-INTEX-AIRFL | WD201 Air Filtration System | 81082 | 28558 | 6300
CCK-MP-DOZR-WD201 -ENGINE-INTEX-AFTER | WD201 Aftercooler | 81082 | 17929 | 6300
CCK-MP-DOZR-WD201 -ENGINE-INTEX | WD201 Intake and Exhaust System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE-FUSYS-FULTP | WD201 Fuel Transfer Pump | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-FUSYS-FULTK | WD201 Fuel Tank | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE-FUSYS-FULPP | WD201 Fuel Priming Pump | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-FUSYS-FUINJ | WD201 Fuel Injectors | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-FUSYS-FUHLF | WD201 Fuel System Hoses Lines and Fitti | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE-FUSYS | WD201 Fuel System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE-COSYS-WTRPP | WD201 Water Pump Engine | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-COSYS-THERM | WD201 Thermostats/Regulators | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-COSYS-RADTR | WD201 Radiator Engine | 81082 | 17929 | 6300
CCK-MP-DOZR-WD201 -ENGINE-COSYS-CSHLF | WD201 Cooling System Hoses Lines and Fi | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-COSYS-COFAN | WD201 Cooling Fan | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE-COSYS-BELTS | WD201 Engine Belts | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ENGINE-COSYS | WD201 Engine Cooling System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ENGINE | WD201 Engine Assembly Caterpillar C32 | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-START-STMRH | WD201 Starter Motor R/H | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-START-STMLH | WD201 Starter Motor L/H | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-START | WD201 Starting System Low Voltage | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-LIGHT | WD201 Lighting Low Voltage | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-HARNS | WD201 Electrical Harness Low Voltage | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-CONTL | WD201 Electrical Controls Low Voltage | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-CHARG-BATTY | WD201 Batteries | 81082 | 14733 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-CHARG-ALTER | WD201 Alternator 24V | 81082 | 4550 | 6300
CCK-MP-DOZR-WD201 -ELCTLV-CHARG | WD201 Charging System Low Voltage | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -ELCTLV | WD201 Electrical System Low Voltage 24V | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -COMMUN-RADIO | WD201 Two Way Radio | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -COMMUN-FLMGT | WD201 Fleet Management | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -COMMUN | WD201 Communications | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-SRVBK-SVBRR | WD201 Service Brake R/H Rear | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-SRVBK-SVBRF | WD201 Service Brake R/H Front | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-SRVBK-SVBLR | WD201 Service Brake L/H Rear | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-SRVBK-SVBLF | WD201 Service Brake L/H Front | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-SRVBK | WD201 Service Brake | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV-VLV07 | WD201 Parking Brake Control Valve | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV-VLV06 | WD201 Brake Manifold Rear | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV-VLV05 | WD201 Brake Manifold Front | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV-VLV04 | WD201 Brake Pump Check Valve | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV-VLV03 | WD201 Park Brake Release Check Valve | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV-VLV02 | WD201 Brake Accumulator Charging Valve | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV-VLV01 | WD201 Service Brake Control Valve | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRVLV | WD201 Valves Brake | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRPRK | WD201 Park Brake Assembly | 81082 | 2675 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRPMP | WD201 Pump Brake | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BRHLF | WD201 Brake System Hoses Lines and Fitt | 81082 | 12720 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BACCM-BACCR | WD201 Brake Accumulator Rear | 81082 | 39870 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BACCM-BACCF | WD201 Brake Accumulator Front | 81082 | 39870 | 6300
CCK-MP-DOZR-WD201 -BRKSYS-BACCM | WD201 Brake Accumulators | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 -BRKSYS | WD201 Braking System | 81082 | 81082 | 6300
CCK-MP-DOZR-WD201 | Caterpillar 854K Wheel Dozer, WD201 | 81106 | 81106 | 6300
CCK-MP-DOZR-WD007 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 76541 | 15900 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BACCM | Brake Accumulator Front RH | 35779 | 35779 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BACCM | Brake Accumulator Front LH | 35779 | 35779 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDHLF-HDHMH | WD007 Hydraulic System Hoses Main | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDHLF-HDHPS | WD007 Hyd System Hoses Pilot Sys | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 76489 | 35779 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STHLF | Steering System Hoses Lines and Fittings | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-RRDIF-TRNON | Trunnions Rear Differential | 76489 | 13479 | 6300
CCK-MP-DOZR-WD007 -MANGMT-UMMMC | Mine Monitoring and Control | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -MANGMT-UMMC | Machine Management System | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -MANGMT-UMENG | Engine Management System | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FRSUPP | Fire Suppression System | 76489 | 38781 | 6300
CCK-MP-DOZR-WD007 -STRUCT-BLADE | Blade Trunions | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-BLADE | Blade | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-TRNON | Trunnion | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-LNKGE | Link Stabilizer | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-PUARM | Push Arm | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-ARTIC | Articulation | 76489 | 28320 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-CWEIG | Counterweight | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-REFRM | Rear Frame | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CHASS-FRFRM | Front Frame | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CABIN-SBELT | Seat Belt | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CABIN-SEATS | WD007 Operators Seat | 76489 | 892 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 76489 | 20596 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CABIN-AIRCN | Air Conditioning System | 76489 | 20596 | 6300
CCK-MP-DOZR-WD007 -STRUCT-CABIN | Operators Cabin | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -GRSYST-ALBPP | Auto Lube Pump | 76489 | 33943 | 6300
CCK-MP-DOZR-WD007 -GRSYST-GRINJ | Auto Lube Injectors | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -GRSYST | Auto Lube System Service | 76489 | 20596 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV08 | Valve Solenoid Hydraulic Lockout | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV07 | Valve Pilot Relief | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV06 | Valve Make Up Hydraulic Fan | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV05 | Valve Demand Hydraulic Fan | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV04 | Valve Hydraulic Fan | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV03 | Valve Hydraulic Manual Lowering Control | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV02 | Valve Hydraulic Dual Tilt Control | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDVLV-HYV01 | Valve Hydraulic Main Control | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HYDMT-HYM02 | Motor / Pump Axle Cooling | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 76489 | 17049 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 76489 | 17049 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Fan | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot | 76489 | 28330 | 6300
CCK-MP-DOZR-WD007 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -HYDSYS | Hydraulic System | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 76489 | 20596 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STVLV-VLV04 | Valve Steering Neutraliser R/H | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STVLV-VLV03 | Valve Steering Neutraliser L/H | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STVLV-VLV02 | Valve Steering Pilot (STIC Steering) | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STVLV-VLV01 | Valve Steering Control | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STPMP-STP03 | Pump Steering Secondary / Emergency | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STPMP-STP02 | Pump Steering Pilot / Axle Oil Cooling | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -STRSYS-STPMP-STP01 | Pump Steering Main | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRVLV-VLV07 | Parking Brake Control Valve | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRVLV-VLV06 | Brake Manifold Rear | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRVLV-VLV05 | Brake Manifold Front | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRVLV-VLV04 | Brake Pump Check Valve | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRVLV-VLV03 | Park Brake Release Check Valve | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRVLV-VLV02 | Brake Accumulator Charging Valve | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRVLV-VLV01 | Service Brake Control Valve | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRPMP | Pump Brake | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BRPRK | Park Brake Assembly | 76489 | 39894 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 76489 | 35779 | 6300
CCK-MP-DOZR-WD007 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 76489 | 35779 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-AXLEC-TVLVR | Axle Cooling Thermal Bypass Valve Rear | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-AXLEC-TVLVF | Axle Cooling Thermal Bypass Valve Front | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-AXLEC-OILCR | Axle Oil Cooler Rear | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-AXLEC-OILCF | Axle Oil Cooler Front | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-AXLEC | Axle Cooler Pump / Motor | 76489 | 76489 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 76489 | 13479 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 76489 | 13479 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 76489 | 13800 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 76489 | 8036 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-RRDIF | Rear Differential | 76513 | 8036 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-FRDIF | Front Differential | 76513 | 8036 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 76513 | 9013 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 76513 | 20488 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -FDRSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -TRNSYS-TROLC | Transmission Oil Cooler | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -TRNSYS-TRPMP | Pump Transmission | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -TRNSYS-TRTRF | Transmission Transfer Case | 76513 | 76513 | 6300
CCK-MP-DOZR-WD007 -TRNSYS-TRANS | Transmission | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -TRNSYS-TRQUE | Torque Converter | 76513 | 20596 | 6300
CCK-MP-DOZR-WD007 -ELCTLV-START-STMRH | Starter Motor R/H | 76513 | 892 | 6300
CCK-MP-DOZR-WD007 -ELCTLV-START-STMLH | Starter Motor L/H | 76513 | 892 | 6300
CCK-MP-DOZR-WD007 -ELCTLV-CHARG-BATTY | Batteries | 76513 | 19484 | 6300
CCK-MP-DOZR-WD007 -ELCTLV-CHARG-ALTER | Alternator 24V | 76513 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 76489 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 76489 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 76489 | 12682 | 6300
CCK-MP-DOZR-WD007 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 76513 | 28320 | 6300
CCK-MP-DOZR-WD007 -ENGINE-INTEX-AFTER | Aftercooler | 76489 | 8208 | 6300
CCK-MP-DOZR-WD007 -ENGINE-INTEX-TBORH | Turbocharger R/H | 76489 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 76489 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-COSYS-CSHLF | Cooling System Hoses | 76513 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-COSYS-THERM | Thermostats/Regulators | 76489 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-COSYS-COFAN | Cooling Fan | 76513 | 76513 | 6300
CCK-MP-DOZR-WD007 -ENGINE-COSYS-RADTR | Radiator Coolant | 76513 | 51585 | 6300
CCK-MP-DOZR-WD007 -ENGINE-COSYS-RADTR | Radiator Engine | 76513 | 8208 | 6300
CCK-MP-DOZR-WD007 -ENGINE-COSYS-WTRPP | Water Pump Engine | 76489 | 892 | 6300
CCK-MP-DOZR-WD007 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 76489 | 12682 | 6300
CCK-MP-DOZR-WD007 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 76489 | 12682 | 6300
CCK-MP-DOZR-WD007 -ENGINE | Engine Assembly Caterpillar C32 | 76513 | 12682 | 6300
CCK-MP-DOZR-WD007 | WD007 Lube & Mechanical Services | 76513 | 76513 | 6300
CCK-MP-DOZR-WD007 | Caterpillar 854K Wheel Dozer WD007 | 76513 | 76513 | 6300
CCK-MP-DOZR-WD006 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 69424 | 13565 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BACCM | Brake Accumulator Front RH | 27177 | 27177 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BACCM | Brake Accumulator Front LH | 27177 | 27177 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDHLF-HDHMH | WD006 Hydraulic System Hoses Main | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDHLF-HDHPS | WD006 Hyd System Hoses Pilot Sys | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 69386 | 46327 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STHLF | Steering System Hoses Lines and Fittings | 69386 | 10255 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 69386 | 10255 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-RRDIF-TRNON | Trunnions Rear Differential | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -MANGMT-UMMMC | Mine Monitoring and Control | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -MANGMT-UMMC | Machine Management System | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -MANGMT-UMENG | Engine Management System | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FRSUPP | Fire Suppression System | 69386 | 24173 | 6300
CCK-MP-DOZR-WD006 -STRUCT-BLADE | Blade Trunions | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-BLADE | Blade | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-TRNON | Trunnion | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-LNKGE | Link Stabilizer | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-PUARM | Push Arm | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-ARTIC | Articulation | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-CWEIG | Counterweight | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-REFRM | Rear Frame | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CHASS-FRFRM | Front Frame | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CABIN-SBELT | Seat Belt | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CABIN-SEATS | WD006 Operators Seat | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CABIN-AIRCN | Air Conditioning System | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -STRUCT-CABIN | Operators Cabin | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -GRSYST-ALBPP | Auto Lube Pump | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -GRSYST-GRINJ | Auto Lube Injectors | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -GRSYST | Auto Lube System Service | 69386 | 12336 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV08 | Valve Solenoid Hydraulic Lockout | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV07 | Valve Pilot Relief | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV06 | Valve Make Up Hydraulic Fan | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV05 | Valve Demand Hydraulic Fan | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV04 | Valve Hydraulic Fan | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV03 | Valve Hydraulic Manual Lowering Control | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV02 | Valve Hydraulic Dual Tilt Control | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDVLV-HYV01 | Valve Hydraulic Main Control | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HYDMT-HYM02 | Motor / Pump Axle Cooling | 69386 | 10327 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 69386 | 13435 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 69386 | 11492 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Fan | 69386 | 13427 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot | 69386 | 33468 | 6300
CCK-MP-DOZR-WD006 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement | 69386 | 13427 | 6300
CCK-MP-DOZR-WD006 -HYDSYS | Hydraulic System | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 69386 | 11492 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STVLV-VLV04 | Valve Steering Neutraliser R/H | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STVLV-VLV03 | Valve Steering Neutraliser L/H | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STVLV-VLV02 | Valve Steering Pilot (STIC Steering) | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STVLV-VLV01 | Valve Steering Control | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STPMP-STP03 | Pump Steering Secondary / Emergency | 69386 | 10255 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STPMP-STP02 | Pump Steering Pilot / Axle Oil Cooling | 69386 | 13427 | 6300
CCK-MP-DOZR-WD006 -STRSYS-STPMP-STP01 | Pump Steering Main | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRVLV-VLV07 | Parking Brake Control Valve | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRVLV-VLV06 | Brake Manifold Rear | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRVLV-VLV05 | Brake Manifold Front | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRVLV-VLV04 | Brake Pump Check Valve | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRVLV-VLV03 | Park Brake Release Check Valve | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRVLV-VLV02 | Brake Accumulator Charging Valve | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRVLV-VLV01 | Service Brake Control Valve | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRPMP | Pump Brake | 69386 | 13427 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BRPRK | Park Brake Assembly | 69386 | 7027 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-AXLEC-TVLVR | Axle Cooling Thermal Bypass Valve Rear | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-AXLEC-TVLVF | Axle Cooling Thermal Bypass Valve Front | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-AXLEC-OILCR | Axle Oil Cooler Rear | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-AXLEC-OILCF | Axle Oil Cooler Front | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-AXLEC | Axle Cooler Pump / Motor | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 69386 | 4749 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-RRDIF | Rear Differential | 69386 | 10255 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-FRDIF | Front Differential | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -FDRSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -TRNSYS-TROLC | Transmission Oil Cooler | 69386 | 10255 | 6300
CCK-MP-DOZR-WD006 -TRNSYS-TRPMP | Pump Transmission | 69386 | 8416 | 6300
CCK-MP-DOZR-WD006 -TRNSYS-TRTRF | Transmission Transfer Case | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -TRNSYS-TRANS | Transmission | 69386 | 10255 | 6300
CCK-MP-DOZR-WD006 -TRNSYS-TRQUE | Torque Converter | 69386 | 8416 | 6300
CCK-MP-DOZR-WD006 -ELCTLV-START-STMRH | Starter Motor R/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ELCTLV-START-STMLH | Starter Motor L/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ELCTLV-CHARG-BATTY | Batteries | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ELCTLV-CHARG-ALTER | Alternator 24V | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 69386 | 24173 | 6300
CCK-MP-DOZR-WD006 -ENGINE-INTEX-AFTER | Aftercooler | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-INTEX-TBORH | Turbocharger R/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-COSYS-CSHLF | Cooling System Hoses | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-COSYS-THERM | Thermostats/Regulators | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-COSYS-COFAN | Cooling Fan | 69386 | 69386 | 6300
CCK-MP-DOZR-WD006 -ENGINE-COSYS-RADTR | Radiator Coolant | 69386 | 24173 | 6300
CCK-MP-DOZR-WD006 -ENGINE-COSYS-RADTR | Radiator Engine | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-COSYS-WTRPP | Water Pump Engine | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 -ENGINE | Engine Assembly Caterpillar C32 | 69386 | 4123 | 6300
CCK-MP-DOZR-WD006 | WD006 Lube & Mechanical Services | 69286 | 69286 | 6300
CCK-MP-DOZR-WD006 | Caterpillar 854K Wheel Dozer WD006 | 69386 | 69386 | 6300
CCK-MP-GRDR-GR7107-HYDSYS-HDACC | Blade Cushion Accumulator RH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDACC | Blade Cushion Accumulator LH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-BRACC | Brake Accumulator RH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-BRACC | Brake Accumulator LH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CHASS-ARTIC | GR7107 Articulation | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ENGINE-FUSYS-FULCO | GR7107 Cooler Fuel | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ENGINE-INTEX-TBORH | GR7107 Turbocharger Right | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-ELCTLV-START-STMRH | GR7107 Starter Motor Right | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-BRPMP | GR7107 Pump Brake | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-TRNSYS-TRQUE | GR7107 Torque Converter | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-TRNSYS-TRPMP | GR7107 Pump Transmission | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-TRNSYS-TROLC | GR7107 Oil Cooler Transmission | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-TRNSYS-TRANS | GR7107 Transmission | 24399 | 1508 | 5500
CCK-MP-GRDR-GR7107-STRUCT-RIPPR | GR7107 Ripper | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-STRUCT-DRWBR | GR7107 Drawbar Group | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CIRCL-CDBXR | GR7107 Gearbox Circle Drive Rear | 24399 | 820 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CIRCL-CDBXF | GR7107 Gearbox Circle Drive Front | 24399 | 820 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CIRCL-BLMBR | GR7107 Bracket Blade Mounting RH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CIRCL-BLMBL | GR7107 Bracket Blade Mounting LH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CIRCL | GR7107 Circle Assembly | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CABIN-SEATS | GR7107 Operators Seat | 24399 | 9406 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CABIN-SBELT | GR7107 Seat Belt | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CABIN-AIRCN | GR7107 Air Conditioning System | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRUCT-CABIN | GR7107 Operators Cabin | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-STRUCT-BLADE | GR7107 Blade | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRUCT-AXLES-HUBRH | GR7107 Hub and Spindle RH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRUCT-AXLES-HUBLH | GR7107 Hub and Spindle LH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRUCT-AXLES | GR7107 Axle Assembly | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRSYS-STRCY-STCYR | GR7107 Cylinder Steering RH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRSYS-STRCY-STCYL | GR7107 Cylinder Steering LH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRSYS-STLTR | GR7107 Steering Linkages & Tie Rods | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRSYS-STEMG-SESPP | GR7107 Pump Secondary Steering | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-HYSTP | GR7107 Pump Steering | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-HYIMP | GR7107 Pump Implement | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-FANPP | GR7107 Pump Fan Motor & Brakes | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HYDPP-DIFFL | GR7107 Pump Differential Lock | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDOCO | GR7107 Oil Cooler Hydraulic | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDMOT-MOT03 | GR7107 Hydraulic Fan Motor | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDMOT-MOT02 | GR7107 Hydraulic Motor Circle Drive Rear | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDMOT-MOT01 | GR7107 Hydraulic Motor Circle Drive Fron | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-STRSYS-STHLF | GR7107 Steering System Hoses | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-TRNSYS-POHLF | GR7107 Powertrain System Hoses | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDHLF | GR7107 Hydraulic System Hoses | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-BRHLF | GR7107 Brake System Hoses | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYR | GR7107 Cylinder Wheel Lean Right | 24399 | 3609 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-WLCYL | GR7107 Cylinder Wheel Lean Left | 24399 | 3609 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-SSCYL | GR7107 Cylinder Side Shift | 24399 | 4589 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-RICYL | GR7107 Cylinder Ripper Lift | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-CSCYL | GR7107 Cylinder Centre Shift | 24399 | 173 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYR | GR7107 Cylinder Blade Tip Right | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BTCYL | GR7107 Cylinder Blade Tip Left | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BLCYR | GR7107 Cylinder Blade Lift RH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-BLCYL | GR7107 Cylinder Blade Lift LH | 24399 | 1941 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYR | GR7107 Cylinder Articulation RH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL-ARCYL | GR7107 Cylinder Articulation LH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCYL | GR7107 Cylinders Hydraulic | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCVL-BK5RH | GR7107 Valve Group Bank 5 RH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-HYDSYS-HDCVL-BK5LH | GR7107 Valve Group Bank 5 LH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-GRSYST-ALBPP | GR7107 Auto Lube Pump | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FRSUPP | GR7107 Fire Suppression System | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-TDRAX-TDARH | GR7107 Tandem Assembly Right | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-TDRAX-TDALH | GR7107 Tandem Assembly Left | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-FDRVE-FDRRH | GR7107 Final Drive RH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-FDRVE-FDRLH | GR7107 Final Drive LH | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-DRSHT-SHT02 | GR7107 Driveshaft - Trans to Torque Conv | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-DRSHT-SHT01 | GR7107 Driveshaft - Trans to Diff | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-DRLAX-AXLRH | GR7107 Drive Line Axle RH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-DRLAX-AXLLH | GR7107 Drive Line Axle LH | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-DIFFL | GR7107 Differential/Bevel Gear | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ENGINE-LUBSY-OILPP | GR7107 Oil Pump Engine | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ENGINE-LUBSY-ENOLC | GR7107 Oil Cooler Engine | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-ENGINE-INTEX-TBOLH | GR7107 Turbocharger Left | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-ENGINE-INTEX-EXHST | GR7107 Exhaust System | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ENGINE-INTEX-AFTER | GR7107 Aftercooler | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ENGINE-FUSYS-FULTP | GR7107 Pump Fuel Transfer | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-ENGINE-FUSYS-FULPP | GR7107 Pump Fuel Priming | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-ENGINE-FUSYS-FUINJ | GR7107 Fuel Injectors | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-ENGINE-COSYS-WTRPP | GR7107 Water Pump Engine | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-ENGINE-COSYS-THERM | GR7107 Thermostats/Regulators | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-ENGINE-COSYS-RADTR | GR7107 Radiator Engine | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ENGINE-COSYS-COFAN | GR7107 Fan Cooling System | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-ENGINE | GR7107 Engine Assembly Caterpillar | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ELCTLV-START-STMLH | GR7107 Starter Motor Left | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-ELCTLV-HARNS | GR7107 Electrical Harness | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-ELCTLV-CONTL | GR7107 Electrical Controls Low Voltage | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-ELCTLV-CHARG-BATTY | GR7107 Batteries | 24399 | 17929 | 5500
CCK-MP-GRDR-GR7107-ELCTLV-CHARG-ALTER | GR7107 Alternator 24Volt | 24399 | 2761 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBRR | GR7107 Service Brake RH Rear | 24399 | 13118 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBRF | GR7107 Service Brake RH Front | 24399 | 13118 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBLR | GR7107 Service Brake LH Rear | 24399 | 13118 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-SRVBK-SVBLF | GR7107 Service Brake LH Front | 24399 | 13118 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-SLACK-SLACR | GR7107 Brake Slack Adjuster Right | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-SLACK-SLACL | GR7107 Brake Slack Adjuster Left | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-CHAIN-CHNRR | GR7107 Drive Chain RH Rear | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-CHAIN-CHNRF | GR7107 Drive Chain RH Front | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-CHAIN-CHNLR | GR7107 Drive Chain LH Rear | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-FDRSYS-CHAIN-CHNLF | GR7107 Drive Chain LH Front | 24399 | 9687 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-BRPRK | GR7107 Park Brake Assembly | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-BRCON | GR7107 Valve Brake Control | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-BRACC-ACC02 | GR7107 Brake Accumulator Right | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107-BRKSYS-BRACC-ACC01 | GR7107 Brake Accumulator Left | 24399 | 24399 | 5500
CCK-MP-GRDR-GR7107 | Caterpillar 24 Grader GR7107 | 24399 | 24399 | 5500
CCK-MP-GRDR-GR123 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-BRACC | Brake Accumulator RH | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-BRACC | Brake Accumulator LH | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -STRUCT-CHASS-ARTIC | Chassis Articulation | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ELCTLV-START-STRMR | GR123 Starter Motor | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ELCTLV-CHARG-ALTER | GR123 Alternator 24Volt | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ENGINE-FUSYS-FUINJ | GR123 Fuel Injectors | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ENGINE-FUSYS-FULTP | GR123 Pump Fuel Transfer | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ENGINE-INTEX-TURBO | GR123 Turbocharger | 50884 | 363 | 5200
CCK-MP-GRDR-GR123 -ENGINE-COSYS-THERM | GR123 Thermostats/Regulators | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ENGINE-COSYS-WTRPP | GR123 Water Pump Engine | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 50884 | 12356 | 5200
CCK-MP-GRDR-GR123 -STRUCT-CABIN | Operators Cabin | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Right | 50884 | 13188 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-SLACK-SLACL | Brake Slack Adjuster Left | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ENGINE-INTEX-AFTER | Aftercooler | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 50884 | 10664 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 50884 | 10664 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 50884 | 10664 | 5200
CCK-MP-GRDR-GR123 -ELCTLV-HARNS | Electrical Harness | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -STRUCT-BLADE | Blade | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -STRUCT-CIRCL-CDBXR | Gearbox Circle Drive Rear | 50884 | 7795 | 5200
CCK-MP-GRDR-GR123 -STRUCT-CIRCL-CDBXF | Gearbox Circle Drive Front | 50884 | 10664 | 5200
CCK-MP-GRDR-GR123 -STRUCT-CIRCL-BLMBR | Bracket Blade Mounting R/H | 50884 | 26071 | 5200
CCK-MP-GRDR-GR123 -STRUCT-CIRCL-BLMBL | Bracket Blade Mounting L/H | 50884 | 26071 | 5200
CCK-MP-GRDR-GR123 -STRUCT-DRWBR | Drawbar Group | 50884 | 10664 | 5200
CCK-MP-GRDR-GR123 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -STRUCT-AXLES | Axle Assembly | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -STRUCT-CABIN-SEATS | Operators Seat | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -GRSYST | Grease Lubrication System | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDMOT-MOT03 | Hydraulic Fan Motor & Brakes | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDMOT-MOT02 | Hydraulic Motor Circle Drive Rear | 50884 | 4452 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HDMOT-MOT01 | Hydraulic Motor Circle Drive Front | 50884 | 29821 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-DIFFL | Pump Differential Lock | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-FANPP | Pump Fan Motor & Brakes | 50884 | 6039 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-HYSTP | Pump Steering | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -HYDSYS-HYDPP-HYIMP | Pump Implement | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -STRSYS-STLTR | Steering Linkages and Tie Rods | 50884 | 30057 | 5200
CCK-MP-GRDR-GR123 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-FDRVE-FDRRH | Final Drive RH | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-FDRVE-FDRLH | Final Drive LH | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-DIFFL | Differential/Bevel Gear | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -TRNSYS-TRPMP | Pump Transmission | 50884 | 1244 | 5200
CCK-MP-GRDR-GR123 -TRNSYS-TRANS | Transmission | 50884 | 1244 | 5200
CCK-MP-GRDR-GR123 -TRNSYS-TRQUE | Torque Converter | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ENGINE-COSYS-RADTR | Radiator Engine | 50884 | 3151 | 5200
CCK-MP-GRDR-GR123 -ENGINE | Engine Assembly, Caterpillar | 50884 | 9251 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-DRSHT-SHT02 | Driveshaft - Trans to Torque Conv | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -FDRSYS-DRSHT-SHT01 | Driveshaft - Trans to Diff | 50884 | 6392 | 5200
CCK-MP-GRDR-GR123 -TRNSYS-TROLC | Oil Cooler Transmission | 50884 | 1244 | 5200
CCK-MP-GRDR-GR123 -ENGINE-INTEX-EXHST | Exhaust System | 50884 | 26630 | 5200
CCK-MP-GRDR-GR123 | GR123 Lube & Mechanical Services | 50884 | 50884 | 5200
CCK-MP-GRDR-GR123 | Caterpillar 24M Motor Grader, GR123 | 50884 | 50884 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRACC | Brake Accumulator RH | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRACC | Brake Accumulator LH | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -TRNSYS-TRQUE | GR122 Torque Converter | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -TRNSYS-TRPMP | GR122 Pump Transmission | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -TRNSYS-TROLC | GR122 Oil Cooler Transmission | 68036 | 1749 | 5200
CCK-MP-GRDR-GR122 -TRNSYS-TRANS | GR122 Transmission | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -TRNSYS | GR122 Transmission System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-STLAD-SLFXD | GR122 Fixed Steps and Ladders | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -STRUCT-STLAD-SLAUT | GR122 Automatic Access Systems | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-STLAD | GR122 Steps and Ladders | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-RIPPR-RIGET | GR122 Ripper Wear Elements (GET) | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-RIPPR | GR122 Ripper | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -STRUCT-PNLGU | GR122 Panels and Guards | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -STRUCT-PLHAN | GR122 Platforms and Handrails | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-DRWBR | GR122 Drawbar Group | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CIRCL-CDBXR | GR122 Gearbox Circle Drive Rear | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CIRCL-CDBXF | GR122 Gearbox Circle Drive Front | 68036 | 15776 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CIRCL-BLMBR | GR122 Bracket Blade Mounting R/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CIRCL-BLMBL | GR122 Bracket Blade Mounting L/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CIRCL | GR122 Circle Assembly | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CHASS-ROPSS | GR122 Rollover Protective Structure | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CHASS-REFRM | GR122 Rear Frame | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CHASS-FRFRM | GR122 Front Frame | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CHASS-ARTIC | GR122 Articulation | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CHASS | GR122 Chassis | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN-SEATS | GR122 Operators Seat | 68036 | 924 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN-SBELT | GR122 Seat Belt | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN-GLASS | GR122 Glass | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN-CABPR | GR122 Cabin Pressurisation System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN-CABES | GR122 Cabin Entertainment System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN-CABCO | GR122 Cabin Controls | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN-AIRCN | GR122 Air Conditioning System | 68036 | 15776 | 5200
CCK-MP-GRDR-GR122 -STRUCT-CABIN | GR122 Operators Cabin | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -STRUCT-BLADE-MOLDB | GR122 Moldboard Skin | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRUCT-BLADE-BLGET | GR122 Blade Wear Elements (GET) | 68036 | 41753 | 5200
CCK-MP-GRDR-GR122 -STRUCT-BLADE | GR122 Blade | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT-AXLES-HUBRH | GR122 Hub and Spindle R/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT-AXLES-HUBLH | GR122 Hub and Spindle L/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT-AXLES | GR122 Axle Assembly | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRUCT | GR122 Structure | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STRCY-STCYR | GR122 Cylinder Steering R/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STRCY-STCYL | GR122 Cylinder Steering L/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STRCY | GR122 Cylinders Steering | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STLTR | GR122 Steering Linkages and Tie Rods | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STHLF | GR122 Steering System Hoses Lines and F | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STEMG-SESPP | GR122 Pump Secondary Steering | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STEMG | GR122 Emergency Steering System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRSYS-STCON | GR122 Controls Steering | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -STRSYS | GR122 Steering System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -MANGMT-UMTRM | GR122 Transmission Management System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -MANGMT-UMMMC | GR122 Mine Monitoring and Control | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -MANGMT-UMENG | GR122 Engine Management System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -MANGMT | GR122 Unit Management | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-HYSTP | GR122 Pump Steering | 68036 | 8511 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-HYIMP | GR122 Pump Implement | 68036 | 8511 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-FANPP | GR122 Pump Fan Motor & Brakes | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HYDPP-DIFFL | GR122 Pump Differential Lock | 68036 | 1749 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HYDPP | GR122 Pumps Hydraulic | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDTNK | GR122 Tank Hydraulic | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDOCO | GR122 Oil Cooler | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDMOT-MOT03 | GR122 Hydraulic Fan Motor | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDMOT-MOT02 | GR122 Hydraulic Motor Circle Drive Rear | 68036 | 35546 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDMOT-MOT01 | GR122 Hydraulic Motor Circle Drive Fron | 68036 | 35546 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDMOT | GR122 Motors Hydraulic | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-STRNG | GR122 Steering System Hoses | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-PWTRN | GR122 Powertrain System Hoses | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-HYDSH | GR122 Hydraulic System Hoses | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDHLF-BRKS | GR122 Brake System Hoses | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDHLF | GR122 Hydraulic System Hoses Lines Fitt | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-WLCYR | GR122 Cylinder Wheel Lean Right | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-WLCYL | GR122 Cylinder Wheel Lean Left | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-SSCYL | GR122 Cylinder Side Shift | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-RLCYR | GR122 Cylinder Ripper Lift Right | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-RLCYL | GR122 Cylinder Ripper Lift Left | 68036 | 12467 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-CSCYL | GR122 Cylinder Centre Shift | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-BTCYR | GR122 Cylinder Blade Tip Right | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-BTCYL | GR122 Cylinder Blade Tip Left | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-BLCYR | GR122 Cylinder Blade Lift R/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-BLCYL | GR122 Cylinder Blade Lift L/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-ARCYR | GR122 Cylinder Articulation R/H | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL-ARCYL | GR122 Cylinder Articulation L/H | 68036 | 22600 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCYL | GR122 Cylinders Hydraulic | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCVL-BK5RH | GR122 Valve Group Bank 5 RH | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCVL-BK5LH | GR122 Valve Group Bank 5 LH | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDCVL | GR122 Implement Control Valve Hydraulic | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS-HDACC | GR122 Accumulators Blade | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -HYDSYS | GR122 Hydraulic System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -GRSYST-GRTNK | GR122 Auto Lube Reservoir | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -GRSYST-GRINJ | GR122 Auto Lube Injectors | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -GRSYST-ALHLF | GR122 Auto Lube Hoses Lines Fittings | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -GRSYST-ALELC | GR122 Auto Lube Electrical | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -GRSYST-ALCON | GR122 Auto Lube Controller | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -GRSYST-ALBPP | GR122 Auto Lube Pump | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -GRSYST | GR122 Grease Lubrication System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FRSUPP-FSMAN-EXTIN | GR122 Hand Held Fire Extinguisher | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FRSUPP-FSMAN | GR122 Fire Suppression Manual | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FRSUPP-FSAUT-FFOAM | GR122 Fire Suppression Foam | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FRSUPP-FSAUT | GR122 Fire Suppression Automatic | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FRSUPP-FSALM | GR122 Fire System Alarm | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FRSUPP | GR122 Fire Suppression System | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-WHTYR-POS06 | GR122 Tyre & Rim Pos 6 | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-WHTYR-POS05 | GR122 Tyre & Rim Pos 5 | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-WHTYR-POS04 | GR122 Tyre & Rim Pos 4 | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-WHTYR-POS03 | GR122 Tyre & Rim Pos 3 | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-WHTYR-POS02 | GR122 Tyre & Rim Pos 2 | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-WHTYR-POS01 | GR122 Tyre & Rim Pos 1 | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-WHTYR | GR122 Wheels Tyres and Rims | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-TDRAX-TDARH | GR122 Tandem Assembly - Right | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-TDRAX-TDALH | GR122 Tandem Assembly - Left | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-TDRAX | GR122 Tandem Drive Axles | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-FDRVE-FDRRH | GR122 Final Drive RH | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-FDRVE-FDRLH | GR122 Final Drive LH | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-FDRVE | GR122 Final Drives | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-DRSHT-SHT02 | GR122 Driveshaft - Trans to Torque Conv | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-DRSHT-SHT01 | GR122 Driveshaft - Trans to Diff | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-DRSHT | GR122 Driveshaft | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -FDRSYS-DIFFL | GR122 Differential/Bevel Gear | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -FDRSYS | GR122 Final Drive System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE-LUBSY-OILPP | GR122 Oil Pump Engine | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-LUBSY-ENOLC | GR122 Oil Cooler Engine | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-LUBSY | GR122 Engine Lubrication System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE-INTEX-TURBO | GR122 Turbocharger | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-INTEX-EXHST | GR122 Exhaust System | 68036 | 31137 | 5200
CCK-MP-GRDR-GR122 -ENGINE-INTEX-AIRFL | GR122 Air Filtration System | 68036 | 19930 | 5200
CCK-MP-GRDR-GR122 -ENGINE-INTEX-AFTER | GR122 Aftercooler | 68036 | 1749 | 5200
CCK-MP-GRDR-GR122 -ENGINE-INTEX | GR122 Intake and Exhaust System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE-FUSYS-FULTP | GR122 Pump Fuel Transfer | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-FUSYS-FULTK | GR122 Fuel Tank | 68036 | 25631 | 5200
CCK-MP-GRDR-GR122 -ENGINE-FUSYS-FULPP | GR122 Pump Fuel Priming | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-FUSYS-FUINJ | GR122 Fuel Injectors | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-FUSYS-FUHLF | GR122 Fuel System Hoses Lines and Fitti | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE-FUSYS | GR122 Fuel System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE-COSYS-WTRPP | GR122 Water Pump Engine | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-COSYS-THERM | GR122 Thermostats/Regulators | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ENGINE-COSYS-RADTR | GR122 Radiator Engine | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -ENGINE-COSYS-CSHLF | GR122 Cooling System Hoses Lines and Fi | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE-COSYS-COFAN | GR122 Fan Cooling System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE-COSYS | GR122 Engine Cooling System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ENGINE | GR122 Engine Assembly, Caterpillar | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-START-STRMR | GR122 Starter Motor | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-START | GR122 Electrical Starting System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-LIGHT | GR122 Lighting Low Voltage | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-HARNS | GR122 Electrical Harness | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-CONTL | GR122 Electrical Controls Low Voltage | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-CHARG-BATTY | GR122 Batteries | 68036 | 15776 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-CHARG-ALTER | GR122 Alternator 24Volt | 68036 | 1754 | 5200
CCK-MP-GRDR-GR122 -ELCTLV-CHARG | GR122 Charging System | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -ELCTLV | GR122 Electrical System Low Voltage 24V | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -COMMUN-RADIO | GR122 Two Way Radio | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -COMMUN-FLMGT | GR122 Fleet Management | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -COMMUN | GR122 Communications | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBRR | GR122 Service Brake R/H Rear | 68036 | 575 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBRF | GR122 Service Brake R/H Front | 68036 | 15776 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBLR | GR122 Service Brake L/H Rear | 68036 | 924 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SRVBK-SVBLF | GR122 Service Brake L/H Front | 68036 | 924 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SRVBK | GR122 Service Brakes | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SLACK-SLACR | GR122 Brake Slack Adjuster Right | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SLACK-SLACL | GR122 Brake Slack Adjuster Left | 68036 | 10615 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-SLACK | GR122 Brake Slack Adjuster | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRPRK | GR122 Park Brake Assembly | 68036 | 68036 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRHLF | GR122 Brake System Hoses Lines and Fitt | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRCON | GR122 Valve Brake Control | 68040 | 10615 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRACC-ACC02 | GR122 Brake Accumulator Right | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRACC-ACC01 | GR122 Brake Accumulator Left | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -BRKSYS-BRACC | GR122 Brake Accumulators | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 -BRKSYS | GR122 Braking System | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 | GR122 Lube & Mechanical Services | 68040 | 68040 | 5200
CCK-MP-GRDR-GR122 | Caterpillar 24M Motor Grader, GR122 | 68040 | 68040 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRACC | Brake Accumulator RH | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRACC | Brake Accumulator LH | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -TRNSYS-TRQUE | GR121 Torque Converter | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -TRNSYS-TRPMP | GR121 Pump Transmission | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -TRNSYS-TROLC | GR121 Oil Cooler Transmission | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -TRNSYS-TRANS | GR121 Transmission | 67029 | 6190 | 5200
CCK-MP-GRDR-GR121 -TRNSYS | GR121 Transmission System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-STLAD-SLFXD | GR121 Fixed Steps and Ladders | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-STLAD-SLAUT | GR121 Automatic Access Systems | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-STLAD | GR121 Steps and Ladders | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-RIPPR-RIGET | GR121 Ripper Wear Elements (GET) | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-RIPPR | GR121 Ripper | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-PNLGU | GR121 Panels and Guards | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-PLHAN | GR121 Platforms and Handrails | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-DRWBR | GR121 Drawbar Group | 67029 | 10194 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CIRCL-CDBXR | GR121 Gearbox Circle Drive Rear | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CIRCL-CDBXF | GR121 Gearbox Circle Drive Front | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CIRCL-BLMBR | GR121 Bracket Blade Mounting R/H | 67029 | 47997 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CIRCL-BLMBL | GR121 Bracket Blade Mounting L/H | 67029 | 47997 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CIRCL | GR121 Circle Assembly | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CHASS-ROPSS | GR121 Rollover Protective Structure | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CHASS-REFRM | GR121 Rear Frame | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CHASS-FRFRM | GR121 Front Frame | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CHASS-ARTIC | GR121 Articulation | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CHASS | GR121 Chassis | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN-SEATS | GR121 Operators Seat | 67029 | 12377 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN-SBELT | GR121 Seat Belt | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN-GLASS | GR121 Glass | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN-CABPR | GR121 Cabin Pressurisation System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN-CABES | GR121 Cabin Entertainment System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN-CABCO | GR121 Cabin Controls | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN-AIRCN | GR121 Air Conditioning System | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -STRUCT-CABIN | GR121 Operators Cabin | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-BLADE-MOLDB | GR121 Moldboard Skin | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-BLADE-BLGET | GR121 Blade Wear Elements (GET) | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRUCT-BLADE | GR121 Blade | 67029 | 24890 | 5200
CCK-MP-GRDR-GR121 -STRUCT-AXLES-HUBRH | GR121 Hub and Spindle R/H | 67029 | 50 | 5200
CCK-MP-GRDR-GR121 -STRUCT-AXLES-HUBLH | GR121 Hub and Spindle L/H | 67029 | 50 | 5200
CCK-MP-GRDR-GR121 -STRUCT-AXLES | GR121 Axle Assembly | 67029 | 50 | 5200
CCK-MP-GRDR-GR121 -STRUCT | GR121 Structure | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STRCY-STCYR | GR121 Cylinder Steering R/H | 67029 | 50 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STRCY-STCYL | GR121 Cylinder Steering L/H | 67029 | 50 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STRCY | GR121 Cylinders Steering | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STLTR | GR121 Steering Linkages and Tie Rods | 67029 | 16101 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STHLF | GR121 Steering System Hoses Lines and F | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STEMG-SESPP | GR121 Pump Secondary Steering | 67029 | 35586 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STEMG | GR121 Emergency Steering System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -STRSYS-STCON | GR121 Controls Steering | 67029 | 27332 | 5200
CCK-MP-GRDR-GR121 -STRSYS | GR121 Steering System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -MANGMT-UMTRM | GR121 Transmission Management System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -MANGMT-UMMMC | GR121 Mine Monitoring and Control | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -MANGMT-UMENG | GR121 Engine Management System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -MANGMT | GR121 Unit Management | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-HYSTP | GR121 Pump Steering | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-HYIMP | GR121 Pump Implement | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-FANPP | GR121 Pump Fan Motor & Brakes | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HYDPP-DIFFL | GR121 Pump Differential Lock | 67029 | 16173 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HYDPP | GR121 Pumps Hydraulic | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDTNK | GR121 Tank Hydraulic | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDOCO | GR121 Oil Cooler | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDMOT-MOT03 | GR121 Hydraulic Fan Motor | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDMOT-MOT02 | GR121 Hydraulic Motor Circle Drive Rear | 67029 | 35584 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDMOT-MOT01 | GR121 Hydraulic Motor Circle Drive Fron | 67029 | 32191 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDMOT | GR121 Motors Hydraulic | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-STRNG | GR121 Steering System Hoses | 67029 | 10194 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-PWTRN | GR121 Powertrain System Hoses | 67029 | 10194 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-HYDSH | GR121 Hydraulic System Hoses | 67029 | 10194 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDHLF-BRKS | GR121 Brake System Hoses | 67029 | 10194 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDHLF | GR121 Hydraulic System Hoses Lines Fitt | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-WLCYR | GR121 Cylinder Wheel Lean Right | 67029 | 1559 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-WLCYL | GR121 Cylinder Wheel Lean Left | 67029 | 1559 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-SSCYL | GR121 Cylinder Side Shift | 67029 | 15507 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-RLCYR | GR121 Cylinder Ripper Lift Right | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-RLCYL | GR121 Cylinder Ripper Lift Left | 67029 | 52712 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-CSCYL | GR121 Cylinder Centre Shift | 67029 | 15507 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-BTCYR | GR121 Cylinder Blade Tip Right | 67029 | 24962 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-BTCYL | GR121 Cylinder Blade Tip Left | 67029 | 24904 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-BLCYR | GR121 Cylinder Blade Lift R/H | 67029 | 34295 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-BLCYL | GR121 Cylinder Blade Lift L/H | 67029 | 61745 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-ARCYR | GR121 Cylinder Articulation R/H | 67029 | 1063 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL-ARCYL | GR121 Cylinder Articulation L/H | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCYL | GR121 Cylinders Hydraulic | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCVL-BK5RH | GR121 Valve Group Bank 5 RH | 67029 | 24962 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCVL-BK5LH | GR121 Valve Group Bank 5 LH | 67029 | 24962 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDCVL | GR121 Implement Control Valve Hydraulic | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS-HDACC | GR121 Accumulators Blade | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -HYDSYS | GR121 Hydraulic System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -GRSYST-GRTNK | GR121 Auto Lube Reservoir | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -GRSYST-GRINJ | GR121 Auto Lube Injectors | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -GRSYST-ALHLF | GR121 Auto Lube Hoses Lines Fittings | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -GRSYST-ALELC | GR121 Auto Lube Electrical | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -GRSYST-ALCON | GR121 Auto Lube Controller | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -GRSYST-ALBPP | GR121 Auto Lube Pump | 67029 | 25162 | 5200
CCK-MP-GRDR-GR121 -GRSYST | GR121 Grease Lubrication System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FRSUPP-FSMAN-EXTIN | GR121 Hand Held Fire Extinguisher | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FRSUPP-FSMAN | GR121 Fire Suppression Manual | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FRSUPP-FSAUT-FFOAM | GR121 Fire Suppression Foam | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FRSUPP-FSAUT | GR121 Fire Suppression Automatic | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FRSUPP-FSALM | GR121 Fire System Alarm | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FRSUPP | GR121 Fire Suppression System | 67029 | 34054 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-WHTYR-POS06 | GR121 Tyre & Rim Pos 6 | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-WHTYR-POS05 | GR121 Tyre & Rim Pos 5 | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-WHTYR-POS04 | GR121 Tyre & Rim Pos 4 | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-WHTYR-POS03 | GR121 Tyre & Rim Pos 3 | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-WHTYR-POS02 | GR121 Tyre & Rim Pos 2 | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-WHTYR-POS01 | GR121 Tyre & Rim Pos 1 | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-WHTYR | GR121 Wheels Tyres and Rims | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-TDRAX-TDARH | GR121 Tandem Assembly - Right | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-TDRAX-TDALH | GR121 Tandem Assembly - Left | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-TDRAX | GR121 Tandem Drive Axles | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-FDRVE-FDRRH | GR121 Final Drive RH | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-FDRVE-FDRLH | GR121 Final Drive LH | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-FDRVE | GR121 Final Drives | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-DRSHT-SHT02 | GR121 Driveshaft - Trans to Torque Conv | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-DRSHT-SHT01 | GR121 Driveshaft - Trans to Diff | 67029 | 10195 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-DRSHT | GR121 Driveshaft | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -FDRSYS-DIFFL | GR121 Differential/Bevel Gear | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -FDRSYS | GR121 Final Drive System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-LUBSY-OILPP | GR121 Oil Pump Engine | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-LUBSY-ENOLC | GR121 Oil Cooler Engine | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-LUBSY | GR121 Engine Lubrication System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-INTEX-TURBO | GR121 Turbocharger | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-INTEX-EXHST | GR121 Exhaust System | 67029 | 32434 | 5200
CCK-MP-GRDR-GR121 -ENGINE-INTEX-AIRFL | GR121 Air Filtration System | 67029 | 24948 | 5200
CCK-MP-GRDR-GR121 -ENGINE-INTEX-AFTER | GR121 Aftercooler | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-INTEX | GR121 Intake and Exhaust System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-FUSYS-FULTP | GR121 Pump Fuel Transfer | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-FUSYS-FULTK | GR121 Fuel Tank | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-FUSYS-FULPP | GR121 Pump Fuel Priming | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-FUSYS-FUINJ | GR121 Fuel Injectors | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-FUSYS-FUHLF | GR121 Fuel System Hoses Lines and Fitti | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-FUSYS | GR121 Fuel System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-COSYS-WTRPP | GR121 Water Pump Engine | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-COSYS-THERM | GR121 Thermostats/Regulators | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-COSYS-RADTR | GR121 Radiator Engine | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ENGINE-COSYS-CSHLF | GR121 Cooling System Hoses Lines and Fi | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-COSYS-COFAN | GR121 Fan Cooling System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE-COSYS | GR121 Engine Cooling System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ENGINE | GR121 Engine Assembly Caterpillar | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-START-STRMR | GR121 Starter Motor | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-START | GR121 Electrical Starting System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-LIGHT | GR121 Lighting Low Voltage | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-HARNS | GR121 Electrical Harness | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-CONTL | GR121 Electrical Controls Low Voltage | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-CHARG-BATTY | GR121 Batteries | 67029 | 13935 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-CHARG-ALTER | GR121 Alternator 24Volt | 67029 | 5487 | 5200
CCK-MP-GRDR-GR121 -ELCTLV-CHARG | GR121 Charging System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -ELCTLV | GR121 Electrical System Low Voltage 24V | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -COMMUN-RADIO | GR121 Two Way Radio | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -COMMUN-FLMGT | GR121 Fleet Management | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -COMMUN | GR121 Communications | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBRR | GR121 Service Brake R/H Rear | 67029 | 19812 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBRF | GR121 Service Brake R/H Front | 67029 | 19812 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBLR | GR121 Service Brake L/H Rear | 67029 | 16173 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SRVBK-SVBLF | GR121 Service Brake L/H Front | 67029 | 8307 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SRVBK | GR121 Service Brakes | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SLACK-SLACR | GR121 Brake Slack Adjuster Right | 67029 | 16173 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SLACK-SLACL | GR121 Brake Slack Adjuster Left | 67029 | 16101 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-SLACK | GR121 Brake Slack Adjuster | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRPRK | GR121 Park Brake Assembly | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRHLF | GR121 Brake System Hoses Lines and Fitt | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRCON | GR121 Valve Brake Control | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRACC-ACC02 | GR121 Brake Accumulator Right | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRACC-ACC01 | GR121 Brake Accumulator Left | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS-BRACC | GR121 Brake Accumulators | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 -BRKSYS | GR121 Braking System | 67029 | 67029 | 5200
CCK-MP-GRDR-GR121 | GR121 Lube & Mechanical Services | 66625 | 66625 | 5200
CCK-MP-GRDR-GR121 | Caterpillar 24M Motor Grader, GR121 | 67029 | 67029 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRACC | Brake Accumulator RH | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRACC | Brake Accumulator LH | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -TRNSYS-TRQUE | GR120 Torque Converter | 60265 | 7142 | 5200
CCK-MP-GRDR-GR120 -TRNSYS-TRPMP | GR120 Pump Transmission | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -TRNSYS-TROLC | GR120 Oil Cooler Transmission | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -TRNSYS-TRANS | GR120 Transmission | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -TRNSYS | GR120 Transmission System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-STLAD-SLFXD | GR120 Fixed Steps and Ladders | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-STLAD-SLAUT | GR120 Automatic Access Systems | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-STLAD | GR120 Steps and Ladders | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-RIPPR-RIGET | GR120 Ripper Wear Elements (GET) | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-RIPPR | GR120 Ripper | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-PNLGU | GR120 Panels and Guards | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-PLHAN | GR120 Platforms and Handrails | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-DRWBR | GR120 Drawbar Group | 60265 | 8767 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CIRCL-CDBXR | GR120 Gearbox Circle Drive Rear | 60265 | 11145 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CIRCL-CDBXF | GR120 Gearbox Circle Drive Front | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CIRCL-BLMBR | GR120 Bracket Blade Mounting R/H | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CIRCL-BLMBL | GR120 Bracket Blade Mounting L/H | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CIRCL | GR120 Circle Assembly | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CHASS-ROPSS | GR120 Rollover Protective Structure | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CHASS-REFRM | GR120 Rear Frame | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CHASS-FRFRM | GR120 Front Frame | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CHASS-ARTIC | GR120 Articulation | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CHASS | GR120 Chassis | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN-SEATS | GR120 Operators Seat | 60265 | 8768 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN-SBELT | GR120 Seat Belt | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN-GLASS | GR120 Glass | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN-CABPR | GR120 Cabin Pressurisation System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN-CABES | GR120 Cabin Entertainment System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN-CABCO | GR120 Cabin Controls | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN-AIRCN | GR120 Air Conditioning System | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -STRUCT-CABIN | GR120 Operators Cabin | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-BLADE-MOLDB | GR120 Moldboard Skin | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-BLADE-BLGET | GR120 Blade Wear Elements (GET) | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRUCT-BLADE | GR120 Blade | 60265 | 22702 | 5200
CCK-MP-GRDR-GR120 -STRUCT-AXLES-HUBRH | GR120 Hub and Spindle R/H | 60265 | 11647 | 5200
CCK-MP-GRDR-GR120 -STRUCT-AXLES-HUBLH | GR120 Hub and Spindle L/H | 60265 | 11647 | 5200
CCK-MP-GRDR-GR120 -STRUCT-AXLES | GR120 Axle Assembly | 60265 | 4188 | 5200
CCK-MP-GRDR-GR120 -STRUCT | GR120 Structure | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STRCY-STCYR | GR120 Cylinder Steering R/H | 60265 | 11653 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STRCY-STCYL | GR120 Cylinder Steering L/H | 60265 | 11653 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STRCY | GR120 Cylinders Steering | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STLTR | GR120 Steering Linkages and Tie Rods | 60265 | 19363 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STHLF | GR120 Steering System Hoses Lines and F | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STEMG-SESPP | GR120 Pump Secondary Steering | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STEMG | GR120 Emergency Steering System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRSYS-STCON | GR120 Controls Steering | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -STRSYS | GR120 Steering System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -MANGMT-UMTRM | GR120 Transmission Management System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -MANGMT-UMMMC | GR120 Mine Monitoring and Control | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -MANGMT-UMENG | GR120 Engine Management System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -MANGMT | GR120 Unit Management | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-HYSTP | GR120 Pump Steering | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-HYIMP | GR120 Pump Implement | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-FANPP | GR120 Pump Fan Motor & Brakes | 60265 | 559 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HYDPP-DIFFL | GR120 Pump Differential Lock | 60265 | 8768 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HYDPP | GR120 Pumps Hydraulic | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDTNK | GR120 Tank Hydraulic | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDOCO | GR120 Oil Cooler | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDMOT-MOT03 | GR120 Hydraulic Fan Motor | 60265 | 8770 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDMOT-MOT02 | GR120 Hydraulic Motor Circle Drive Rear | 60265 | 35437 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDMOT-MOT01 | GR120 Hydraulic Motor Circle Drive Fron | 60265 | 33122 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDMOT | GR120 Motors Hydraulic | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-STRNG | GR120 Steering System Hoses | 60265 | 8770 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-PWTRN | GR120 Powertrain System Hoses | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-HYDSH | GR120 Hydraulic System Hoses | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDHLF-BRKS | GR120 Brake System Hoses | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDHLF | GR120 Hydraulic System Hoses Lines Fitt | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-WLCYR | GR120 Cylinder Wheel Lean Right | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-WLCYL | GR120 Cylinder Wheel Lean Left | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-SSCYL | GR120 Cylinder Side Shift | 60265 | 27412 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-RLCYR | GR120 Cylinder Ripper Lift Right | 60265 | 31303 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-RLCYL | GR120 Cylinder Ripper Lift Left | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-CSCYL | GR120 Cylinder Centre Shift | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-BTCYR | GR120 Cylinder Blade Tip Right | 60265 | 22855 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-BTCYL | GR120 Cylinder Blade Tip Left | 60265 | 48256 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-BLCYR | GR120 Cylinder Blade Lift R/H | 60265 | 6921 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-BLCYL | GR120 Cylinder Blade Lift L/H | 60265 | 18461 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-ARCYR | GR120 Cylinder Articulation R/H | 60265 | 178 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL-ARCYL | GR120 Cylinder Articulation L/H | 60265 | 5747 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCYL | GR120 Cylinders Hydraulic | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCVL-BK5RH | GR120 Valve Group Bank 5 RH | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCVL-BK5LH | GR120 Valve Group Bank 5 LH | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDCVL | GR120 Implement Control Valve Hydraulic | 60265 | 6595 | 5200
CCK-MP-GRDR-GR120 -HYDSYS-HDACC | GR120 Accumulators Blade | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -HYDSYS | GR120 Hydraulic System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -GRSYST-GRTNK | GR120 Auto Lube Reservoir | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -GRSYST-GRINJ | GR120 Auto Lube Injectors | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -GRSYST-ALHLF | GR120 Auto Lube Hoses Lines Fittings | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -GRSYST-ALELC | GR120 Auto Lube Electrical | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -GRSYST-ALCON | GR120 Auto Lube Controller | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -GRSYST-ALBPP | GR120 Auto Lube Pump | 60265 | 4760 | 5200
CCK-MP-GRDR-GR120 -GRSYST | GR120 Grease Lubrication System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FRSUPP-FSMAN-EXTIN | GR120 Hand Held Fire Extinguisher | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FRSUPP-FSMAN | GR120 Fire Suppression Manual | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FRSUPP-FSAUT-FFOAM | GR120 Fire Suppression Foam | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FRSUPP-FSAUT | GR120 Fire Suppression Automatic | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FRSUPP-FSALM | GR120 Fire System Alarm | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FRSUPP | GR120 Fire Suppression System | 60265 | 28550 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-WHTYR-POS06 | GR120 Tyre & Rim Pos 6 | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-WHTYR-POS05 | GR120 Tyre & Rim Pos 5 | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-WHTYR-POS04 | GR120 Tyre & Rim Pos 4 | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-WHTYR-POS03 | GR120 Tyre & Rim Pos 3 | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-WHTYR-POS02 | GR120 Tyre & Rim Pos 2 | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-WHTYR-POS01 | GR120 Tyre & Rim Pos 1 | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-WHTYR | GR120 Wheels Tyres and Rims | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-TDRAX-TDARH | GR120 Tandem Assembly - Right | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-TDRAX-TDALH | GR120 Tandem Assembly - Left | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-TDRAX | GR120 Tandem Drive Axles | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-FDRVE-FDRRH | GR120 Final Drive RH | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-FDRVE-FDRLH | GR120 Final Drive LH | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-FDRVE | GR120 Final Drives | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-DRSHT-SHT02 | GR120 Driveshaft - Trans to Torque Conv | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-DRSHT-SHT01 | GR120 Driveshaft - Trans to Diff | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-DRSHT | GR120 Driveshaft | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -FDRSYS-DIFFL | GR120 Differential/Bevel Gear | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -FDRSYS | GR120 Final Drive System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-LUBSY-OILPP | GR120 Oil Pump Engine | 60265 | 8767 | 5200
CCK-MP-GRDR-GR120 -ENGINE-LUBSY-ENOLC | GR120 Oil Cooler Engine | 60265 | 8767 | 5200
CCK-MP-GRDR-GR120 -ENGINE-LUBSY | GR120 Engine Lubrication System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-INTEX-TURBO | GR120 Turbocharger | 60265 | 1413 | 5200
CCK-MP-GRDR-GR120 -ENGINE-INTEX-EXHST | GR120 Exhaust System | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -ENGINE-INTEX-AIRFL | GR120 Air Filtration System | 60265 | 15385 | 5200
CCK-MP-GRDR-GR120 -ENGINE-INTEX-AFTER | GR120 Aftercooler | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -ENGINE-INTEX | GR120 Intake and Exhaust System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-FUSYS-FULTP | GR120 Pump Fuel Transfer | 60265 | 1413 | 5200
CCK-MP-GRDR-GR120 -ENGINE-FUSYS-FULTK | GR120 Fuel Tank | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-FUSYS-FULPP | GR120 Pump Fuel Priming | 60265 | 8767 | 5200
CCK-MP-GRDR-GR120 -ENGINE-FUSYS-FUINJ | GR120 Fuel Injectors | 60265 | 1413 | 5200
CCK-MP-GRDR-GR120 -ENGINE-FUSYS-FUHLF | GR120 Fuel System Hoses Lines and Fitti | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-FUSYS | GR120 Fuel System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-COSYS-WTRPP | GR120 Water Pump Engine | 60265 | 1413 | 5200
CCK-MP-GRDR-GR120 -ENGINE-COSYS-THERM | GR120 Thermostats/Regulators | 60265 | 1413 | 5200
CCK-MP-GRDR-GR120 -ENGINE-COSYS-RADTR | GR120 Radiator Engine | 60265 | 18931 | 5200
CCK-MP-GRDR-GR120 -ENGINE-COSYS-CSHLF | GR120 Cooling System Hoses Lines and Fi | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-COSYS-COFAN | GR120 Fan Cooling System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE-COSYS | GR120 Engine Cooling System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ENGINE | GR120 Engine Assembly Caterpillar | 60265 | 8767 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-START-STRMR | GR120 Starter Motor | 60265 | 1413 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-START | GR120 Electrical Starting System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-LIGHT | GR120 Lighting Low Voltage | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-HARNS | GR120 Electrical Harness | 60265 | 8768 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-CONTL | GR120 Electrical Controls Low Voltage | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-CHARG-BATTY | GR120 Batteries | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-CHARG-ALTER | GR120 Alternator 24Volt | 60265 | 1413 | 5200
CCK-MP-GRDR-GR120 -ELCTLV-CHARG | GR120 Charging System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -ELCTLV | GR120 Electrical System Low Voltage 24V | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -COMMUN-RADIO | GR120 Two Way Radio | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -COMMUN-FLMGT | GR120 Fleet Management | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -COMMUN | GR120 Communications | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBRR | GR120 Service Brake R/H Rear | 60265 | 7045 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBRF | GR120 Service Brake R/H Front | 60265 | 5097 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBLR | GR120 Service Brake L/H Rear | 60265 | 4679 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SRVBK-SVBLF | GR120 Service Brake L/H Front | 60265 | 8767 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SRVBK | GR120 Service Brakes | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SLACK-SLACR | GR120 Brake Slack Adjuster Right | 60265 | 8768 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SLACK-SLACL | GR120 Brake Slack Adjuster Left | 60265 | 8770 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-SLACK | GR120 Brake Slack Adjuster | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRPRK | GR120 Park Brake Assembly | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRHLF | GR120 Brake System Hoses Lines and Fitt | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRCON | GR120 Valve Brake Control | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRACC-ACC02 | GR120 Brake Accumulator Right | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRACC-ACC01 | GR120 Brake Accumulator Left | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS-BRACC | GR120 Brake Accumulators | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 -BRKSYS | GR120 Braking System | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 | GR120 Lubrication & Mechanical Services | 60265 | 60265 | 5200
CCK-MP-GRDR-GR120 | Caterpillar 24M Motor Grader, GR120 | 60265 | 60265 | 5200
CCK-MP-GRDR-GR103 -HYDSYS-HDMOT-MOCDG | GR103 Motor Circle Drive Gearbox | 38302 | 38302 | 1000
CCK-MP-GRDR-GR015 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -ELCTLV-HARNS | Electrical Harness | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-DRWBR | Drawbar | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CABIN | Cabin | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRUCT-RIPPR | Ripper | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRUCT-BLADE-MOLDB | Moldboard Skin | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRUCT-BLADE | Blade Lift Trunnions | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRUCT-BLADE | Blade | 42638 | 19526 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CIRCL | Circle Assembly | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-AXLES | GR015 Front Axle Assembly | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CHASS-ARTIC | Articulation | 42638 | 36810 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CABIN-SBELT | Seat Belt | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CABIN-SEATS | Operators Seat | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRUCT-CABIN-AIRCN | Air Conditioning System | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -GRSYST-ALBPP | Auto Lube Pump | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -GRSYST-GRINJ | Auto Lube Injectors | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -GRSYST | Grease Lubrication System | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator R/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator L/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 42638 | 3447 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation R/H | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-ARCYL | Cylinder Articulation L/H | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 42638 | 19541 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -HYDSYS-HYDPP-HYISP | Pump Implement and Steering | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRSYS-STMTR | Steering Metering Pump | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -STRSYS-STLTR | Steering Linkages and Tie Rods | 42638 | 23374 | 3200
CCK-MP-GRDR-GR015 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-BRPRK | Park Brake Assembly | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-BRPMP | Pump Brake / Hydraulic Fan | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-BKOCO | Oil Cooler Brake / Hydraulic Fan | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 42638 | 24213 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-TDRAX-TDARH | Tandem Drive Chains R/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-TDRAX-TDARH | Tandem Drive Assembly R/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-TDRAX-TDALH | Tandem Drive Chains L/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-TDRAX-TDALH | Tandem Drive Assembly L/H | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -FDRSYS-DIFFL | Differential and Bevel Gear | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -TRNSYS-TRPMP | Pump Transmission | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -TRNSYS-TROLC | Transmission Oil Cooler | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -TRNSYS-TRANS | Transmission | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -TRNSYS | Drive Shaft | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ELCTLV-START-STRMR | Starter Motor | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ELCTLV-CHARG-ALTER | Alternator 24V | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ENGINE-INTEX-EXHST | Exhaust Muffler | 42638 | 12705 | 3200
CCK-MP-GRDR-GR015 -ENGINE-INTEX-AFTER | Aftercooler | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -ENGINE-INTEX-TURBO | Turbocharger | 42638 | 438 | 3200
CCK-MP-GRDR-GR015 -ENGINE-COSYS-THERM | Thermostats/Regulators | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ENGINE-COSYS-COFAN | Fan Cooling System | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -ENGINE-COSYS-RADTR | Radiator Coolant | 42638 | 12705 | 3700
CCK-MP-GRDR-GR015 -ENGINE-COSYS-RADTR | Radiator Engine | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ENGINE-COSYS-WTRPP | Water Pump Engine | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -ENGINE-LUBSY | Engine Lubrication System | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 -ENGINE | Engine Assembly Caterpillar C13 ASERT | 42638 | 2788 | 3200
CCK-MP-GRDR-GR015 | GR015 Lube & Mechanical Services | 42638 | 42638 | 3200
CCK-MP-GRDR-GR015 | Caterpillar 16M Motor Grader GR015 | 42638 | 42638 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 44181 | 3732 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 44181 | 3732 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 44181 | 3732 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 44181 | 3732 | 3200
CCK-MP-GRDR-GR014 -ELCTLV-HARNS | Electrical Harness | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRUCT-DRWBR | Drawbar | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CABIN | Cabin | 44181 | 14563 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 44162 | 278 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRUCT-RIPPR | Ripper | 44181 | 14563 | 3200
CCK-MP-GRDR-GR014 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRUCT-BLADE-MOLDB | Moldboard Skin | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRUCT-BLADE | Blade Lift Trunnions | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRUCT-BLADE | Blade | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 44181 | 8479 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CIRCL | Circle Assembly | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRUCT-AXLES | GR014 Front Axle Assembly | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CHASS-ARTIC | Articulation | 44181 | 36503 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CABIN-SBELT | Seat Belt | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CABIN-SEATS | Operators Seat | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 82639 | 82639 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 44181 | 8479 | 3200
CCK-MP-GRDR-GR014 -STRUCT-CABIN-AIRCN | Air Conditioning System | 44181 | 8479 | 3200
CCK-MP-GRDR-GR014 -GRSYST-ALBPP | Auto Lube Pump | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -GRSYST-GRINJ | Auto Lube Injectors | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -GRSYST | Grease Lubrication System | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator R/H | 44494 | 44494 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator L/H | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 44181 | 14563 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 44181 | 2613 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 44181 | 14910 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation R/H | 44181 | 4016 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-ARCYL | Cylinder Articulation L/H | 44181 | 4016 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 44181 | 5639 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 44181 | 8489 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 44181 | 8479 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 44181 | 8479 | 3200
CCK-MP-GRDR-GR014 -HYDSYS-HYDPP-HYISP | Pump Implement and Steering | 44181 | 8489 | 3200
CCK-MP-GRDR-GR014 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRSYS-STMTR | Steering Metering Pump | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -STRSYS-STLTR | Steering Linkages and Tie Rods | 44181 | 21046 | 3200
CCK-MP-GRDR-GR014 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-BRPRK | Park Brake Assembly | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-BRPMP | Pump Brake / Hydraulic Fan | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-BKOCO | Oil Cooler Brake / Hydraulic Fan | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 44181 | 14563 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 44181 | 14563 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-TDRAX-TDARH | Tandem Drive Chains R/H | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-TDRAX-TDARH | Tandem Drive Assembly R/H | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-TDRAX-TDALH | Tandem Drive Chains L/H | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-TDRAX-TDALH | Tandem Drive Assembly L/H | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -FDRSYS-DIFFL | Differential and Bevel Gear | 44181 | 8479 | 3200
CCK-MP-GRDR-GR014 -TRNSYS-TRPMP | Pump Transmission | 44181 | 36104 | 3200
CCK-MP-GRDR-GR014 -TRNSYS-TROLC | Transmission Oil Cooler | 44181 | 32209 | 3200
CCK-MP-GRDR-GR014 -TRNSYS-TRANS | Transmission | 44181 | 290 | 3200
CCK-MP-GRDR-GR014 -TRNSYS | Drive Shaft | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ELCTLV-START-STRMR | Starter Motor | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ELCTLV-CHARG-ALTER | Alternator 24V | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-INTEX-EXHST | Exhaust Muffler | 44181 | 14563 | 3200
CCK-MP-GRDR-GR014 -ENGINE-INTEX-AFTER | Aftercooler | 44181 | 14563 | 3200
CCK-MP-GRDR-GR014 -ENGINE-INTEX-TURBO | Turbocharger | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-COSYS-THERM | Thermostats/Regulators | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-COSYS-COFAN | Fan Cooling System | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -ENGINE-COSYS-RADTR | Radiator Coolant | 44181 | 14563 | 3700
CCK-MP-GRDR-GR014 -ENGINE-COSYS-RADTR | Radiator Engine | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-COSYS-WTRPP | Water Pump Engine | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -ENGINE-LUBSY | Engine Lubrication System | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 -ENGINE | Engine Assembly Caterpillar C13 ASERT | 44181 | 297 | 3200
CCK-MP-GRDR-GR014 | GR014 Lube & Mechanical Services | 44181 | 44181 | 3200
CCK-MP-GRDR-GR014 | Caterpillar 16M Motor Grader GR014 | 44181 | 44181 | 3200
CCK-MP-GRDR-GR012 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 72375 | 72375 | 6400
CCK-MP-GRDR-GR012 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 72375 | 72375 | 6400
CCK-MP-GRDR-GR012 -BRKSYS-BRACC | Brake Accumulator RH | 72375 | 72375 | 6400
CCK-MP-GRDR-GR012 -BRKSYS-BRACC | Brake Accumulator LH | 72375 | 72375 | 6400
CCK-MP-GRDR-GR012 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 72353 | 16770 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 72353 | 16770 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 74287 | 6847 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 74287 | 6847 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 74287 | 6847 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 74287 | 6847 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 72353 | 16770 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -MANGMT-UMTRM | Transmission Management System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CIRCL-BLMBR | Bracket Blade Mounting R/H | 72353 | 16770 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CIRCL-BLMBL | Bracket Blade Mounting L/H | 72353 | 16770 | 5200
CCK-MP-GRDR-GR012 -STRUCT-DRWBR | Trunnions Blade Lift | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -STRUCT-DRWBR | Drawbar Group | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 72353 | 52317 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCVL-BK5RH | Valve Hyd Control R/H | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCVL-BK5LH | Valve Hyd Control | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HYDPP-DIFFL | Pump Diff lock | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HYDPP-HYSTP | Pump Steering | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HYDPP-HYIMP | Pump Implement | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-BRCON | Valve Brake Control | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-SLACK-SLACR | Slack Adjuster Brake Right | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-SLACK-SLACL | Slack Adjuster Brake Left | 72353 | 176 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-DRSHT-SHT02 | Driveshaft - Trans to Torque Conv | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-DRSHT-SHT01 | Driveshaft - Trans to Diff | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CIRCL-CDBXR | Gearbox Circle Drive Rear | 72353 | 652 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-WLCYR | Cylinder Wheel Lean Right | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift Right | 72353 | 17566 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt Right | 72353 | 4786 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDMOT-MOT03 | Hydraulic Fan Motor | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDMOT-MOT02 | Hydraulic Motor Circle Drive Rear | 72353 | 32772 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-BRACC-ACC02 | Brake Accumulator Right | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-BRACC-ACC01 | Brake Accumulator Left | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -TRNSYS-TRQUE | Torque Converter | 72353 | 2512 | 5200
CCK-MP-GRDR-GR012 | GR012 Lube & Mechanical Services | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE | Engine Assembly, Caterpillar C18 | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -COMMUN-RADIO | Two Way Radio | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -MANGMT-UMMMC | Mine Monitoring and Control | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -MANGMT-UMENG | Engine Management System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FRSUPP-FSMAN | Fire Suppression Manual | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FRSUPP-FSAUT | Fire Suppression Automatic | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FRSUPP-FSALM | Fire System Alarm | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-STLAD-SLFXD | Fixed Steps and Ladders | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-STLAD-SLAUT | Automatic Access Systems | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-STLAD | Steps and Ladders | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-RIPPR | Ripper | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -STRUCT-PNLGU | Panels and Guards | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-PLHAN | Platforms and Handrails | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CIRCL-CDBXF | Gearbox Circle Drive | 72353 | 652 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CIRCL | Circle Assembly | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CHASS-ROPSS | Rolling Object Protective Structure | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CHASS-REFRM | Rear Frame | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CHASS-FRFRM | Front Frame | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CHASS-ARTIC | Articulation | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CHASS | Chassis | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN-SEATS | Operators Seat | 72353 | 15438 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN-SBELT | Seat Belt | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN-GLASS | Glass | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN-CABES | Cabin Entertainment System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN-CABCO | Cabin Controls | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN-AIRCN | Air Conditioning System | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -STRUCT-CABIN | Operators Cabin | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -STRUCT-BLADE-MOLDB | Moldboard Skin | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRUCT-BLADE | Blade | 72353 | 20354 | 5200
CCK-MP-GRDR-GR012 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -STRUCT-AXLES | Axle Assembly | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -GRSYST-GRTNK | Auto Lube Resevoir | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -GRSYST-GRINJ | Auto Lube Injectors | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -GRSYST-ALHLF | Auto Lube Hoses Lines Fittings | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -GRSYST-ALELC | Auto Lube Electrical | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -GRSYST-ALCON | Auto Lube Controller | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -GRSYST-ALBPP | Auto Lube Pump | 72353 | 27067 | 5200
CCK-MP-GRDR-GR012 -PNEUMC-PNTNK | Air Tank | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -PNEUMC-PNHLF | Pneumatic System Hoses Lines Fittings | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HYDPP-HYISP | Pump Implement and Steering | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HYDPP-FANPP | Pump Fan Motor | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HYDPP | Pumps Hydraulic | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDTNK | Tank Hydraulic | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDMOT-MOT01 | Motor Circle Drive Gearbox | 72353 | 32772 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDMOT | Motors Hydraulic | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 72353 | 5520 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 72353 | 28838 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 72353 | 7572 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation R/H | 72353 | 48891 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL-ARCYL | Cylinder Articulation L/H | 72353 | 1339 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCYL | Cylinders Hydraulic | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDCVL | Implement Control Valves Hydraulic | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -HYDSYS-HDACC | Accumlators Blade | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STRCY | Cylinders Steering | 72353 | 5520 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STLTR | Steering Linkages and Tie Rods | 72353 | 27067 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STHLF | Steering System Hoses Lines and Fittings | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STEMG | Emergency Steering System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STCON | Controls Steering | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -STRSYS-STACC | Accumulator Steering | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 72353 | 1541 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 72353 | 1753 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-SRVBK | Service Brake | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-ROTOC | Park Brake Rotochamber | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-BRVTR | Valve Brake Treadle | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-BRVLR | Valve Brake Relay | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-BRPRK | Park Brake Assembly | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-WHTYR | Wheels, Tyres and Rims | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-TDRAX | Tandem Drive Axles | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-TDRAX-TDARH | Tandem Drive Assembly R/H | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-TDRAX-TDALH | Tandem Drive Assembly L/H | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 72353 | 6847 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 72353 | 6847 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-FDRVE | Final Drives | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -FDRSYS-DIFFL | Differential and Bevel Gear | 72353 | 6847 | 5200
CCK-MP-GRDR-GR012 -TRNSYS-TRPMP | Pump Transmission | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -TRNSYS-TROLC | Oil Cooler Transmission | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -TRNSYS-TRANS | Transmission | 72353 | 181 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-START-STRMR | Starter Motor | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-START | Electrical Starting System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-LIGHT | Lighting Low Voltage | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-HARNS | Electrical Harness | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-CONTL | Electrical Controls Low Voltage | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-CHARG-BATTY | Batteries | 72353 | 12098 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-CHARG-ALTER | Alternator 24V | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ELCTLV-CHARG | Charging System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-LUBSY | Engine Lubrication System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE-INTEX-TURBO | Turbocharger | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-INTEX-EXHST | Exhaust System | 72353 | 16770 | 5200
CCK-MP-GRDR-GR012 -ENGINE-INTEX-AIRFL | Air Filtration System | 72353 | 32096 | 5200
CCK-MP-GRDR-GR012 -ENGINE-INTEX-AFTER | Aftercooler | 72353 | 27067 | 5200
CCK-MP-GRDR-GR012 -ENGINE-INTEX | Intake and Exhaust System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE-FUSYS-FULTK | Fuel Tank | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE-FUSYS-FULPP | Pump Fuel Transfer | 72375 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 72375 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-FUSYS-FUHLF | Fuel System Hoses, Lines and Fittings | 72375 | 72375 | 5200
CCK-MP-GRDR-GR012 -ENGINE-FUSYS | Fuel System | 72375 | 72375 | 5200
CCK-MP-GRDR-GR012 -ENGINE-COSYS-WTRPP | Water Pump Engine | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-COSYS-THERM | Thermostats/Regulators | 72353 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-COSYS-RADTR | Radiator Engine | 72375 | 348 | 5200
CCK-MP-GRDR-GR012 -ENGINE-COSYS-CSHLF | Cooling System Hoses, Lines and Fittings | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE-COSYS-COFAN | Fan Cooling System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE-COSYS | Engine Cooling System | 72353 | 72353 | 5200
CCK-MP-GRDR-GR012 -ENGINE-COMPR | Air Compressor | 72375 | 60892 | 5200
CCK-MP-GRDR-GR012 | Caterpillar 24M Motor Grader, GR012 | 72375 | 72375 | 5200
CCK-MP-DOZR-DZ8235-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 23834 | 9619 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYIP2 | DZ8235 Pump Hydraulic Implement 2 | 23802 | 13909 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYDVC | DZ8235 Pump Hydraulic Variable Charge | 23802 | 13909 | 5000
CCK-MP-DOZR-DZ8235-TRNSYS-TRQUE | DZ8235 Torque Converter | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-TRNSYS-TRPMP | DZ8235 Pump Trans & TConverter Charge | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-TRNSYS-TROLC | DZ8235 Oil Cooler Transmission | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-TRNSYS-TRANS-BEVEL | DZ8235 Bevel Gear | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-TRNSYS-TRANS | DZ8235 Transmission | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-TRNSYS-DRSHT | DZ8235 Drive Shaft | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-TKFRR | DZ8235 Track Frame Right Hand | 23802 | 7343 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-TKFRL | DZ8235 Track Frame Left Hand | 23802 | 7343 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-PIVOT | DZ8235 Pivot Shaft | 23802 | 7343 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-LDSFR | DZ8235 Rollers Load Single Flange RH | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-LDSFL | DZ8235 Rollers Load Single Flange LH | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-LDDFR | DZ8235 Rollers Load Double Flange RH | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-LDDFL | DZ8235 Rollers Load Double Flange LH | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-IDRHR | DZ8235 Idler Track Right Hand Rear | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-IDRHF | DZ8235 Idler Track Right Hand Front | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-IDLHR | DZ8235 Idler Track Left Hand Rear | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-IDLHF | DZ8235 Idler Track Left Hand Front | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-ADJRH | DZ8235 Track Adjuster Right Hand | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-UNDER-ADJLH | DZ8235 Track Adjuster Left Hand | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-RIPPR | DZ8235 Ripper | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CHASS-TRNON | DZ8235 Trunnions | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CHASS-PUARM | DZ8235 Push Arms | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CHASS-LNKGE | DZ8235 Link Stabiliser | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CHASS-EQUAL | DZ8235 Equaliser Bar | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CABIN-SEATS | DZ8235 Operators Seat | 23802 | 5679 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CABIN-SBELT | DZ8235 Seat Belt | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CABIN-AIRCN | DZ8235 Air Conditioning System | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-CABIN | DZ8235 Operators Cabin | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-STRUCT-BLADE | DZ8235 Blade | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYIP1 | DZ8235 Pump Hydraulic Implement 1 | 23802 | 13909 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HYDPP-HYFPP | DZ8235 Pump Hydraulic Fan | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDTNK | DZ8235 Tank Hydraulic | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDOCO | DZ8235 Oil Cooler Hydraulic | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-RTCYR | DZ8235 Cylinder Ripper Tilt Right Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-RTCYL | DZ8235 Cylinder Ripper Tilt Left Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-RPUCY | DZ8235 Cylinder Ripper Pin Puller | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-RLCYR | DZ8235 Cylinder Ripper Lift Right Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-RLCYL | DZ8235 Cylinder Ripper Lift Left Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-BTCYR | DZ8235 Cylinder Blade Tilt Right Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-BTCYL | DZ8235 Cylinder Blade Tilt Left Hand | 23802 | 4112 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-BLCYR | DZ8235 Cylinder Blade Lift Right Hand | 23802 | 6195 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCYL-BLCYL | DZ8235 Cylinder Blade Lift Left Hand | 23802 | 1067 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCVL | DZ8235 Implement Valves Hydraulic | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCON | DZ8235 Implement Control Hydraulic | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-HYDSYS-HDCFM | DZ8235 Fan Cooling Motor Hydraulic | 23802 | 3602 | 5000
CCK-MP-DOZR-DZ8235-GRSYST-GRINJ | DZ8235 Auto Lube Injectors | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-GRSYST-ALBPP | DZ8235 Auto Lube Pump | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-FRSUPP | DZ8235 Fire Suppression System | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-FDRSYS-TRKRH | DZ8235 Track Assembly Right Hand | 23802 | 2943 | 5000
CCK-MP-DOZR-DZ8235-FDRSYS-TRKLH | DZ8235 Track Assembly Left Hand | 23802 | 2943 | 5000
CCK-MP-DOZR-DZ8235-FDRSYS-SEGRH | DZ8235 Segments Right Hand | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-FDRSYS-SEGLH | DZ8235 Segments Left Hand | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-FDRSYS-FDRRH | DZ8235 Final Drive Right Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-FDRSYS-FDRLH | DZ8235 Final Drive Left Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-LUBSY-PREPP | DZ8235 Oil Pump Pre Lube Engine | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-LUBSY-OILPP | DZ8235 Oil Pump Engine | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-LUBSY-ENOLC | DZ8235 Oil Cooler Engine | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-INTEX-TBORH | DZ8235 Turbocharger Right Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-INTEX-TBOLH | DZ8235 Turbocharger Left Hand | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-INTEX-AFTER | DZ8235 Aftercooler | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-FUSYS-FULTP | DZ8235 Fuel Transfer Pump | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-FUSYS-FUINJ | DZ8235 Fuel Injectors | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-COSYS-WTRPP | DZ8235 Water Pump Engine | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-COSYS-THERM | DZ8235 Thermostats & Regulators | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-COSYS-RADTR | DZ8235 Radiator Engine | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE-COSYS-COFAN | DZ8235 Fan Cooling System | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ENGINE | DZ8235 Engine Assembly Caterpillar C27 | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ELCTLV-START-STRMR | DZ8235 Starter Motor | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-ELCTLV-CHARG-BATTY | DZ8235 Batteries | 23802 | 10706 | 5000
CCK-MP-DOZR-DZ8235-ELCTLV-CHARG-ALTER | DZ8235 Alternator 24V | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-BRKSTR-STVLV | DZ8235 Valve Hydraulic Steering | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-BRKSTR-SCABR | DZ8235 Steering Clutch & Brake Assy RH | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-BRKSTR-SCABL | DZ8235 Steering Clutch & Brake Assy LH | 23802 | 10459 | 5000
CCK-MP-DOZR-DZ8235-BRKSTR-HYSPP | DZ8235 Pump Hydraulic Steering | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8235 | DZ8235 Caterpillar D10T2 Dozer | 23802 | 23802 | 5000
CCK-MP-DOZR-DZ8234-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 26667 | 8635 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYIP2 | DZ8234 Pump Hydraulic Implement 2 | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYDVC | DZ8234 Pump Hydraulic Variable Charge | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-TRNSYS-TRQUE | DZ8234 Torque Converter | 26629 | 14816 | 5000
CCK-MP-DOZR-DZ8234-TRNSYS-TRPMP | DZ8234 Pump Trans & TConverter Charge | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-TRNSYS-TROLC | DZ8234 Oil Cooler Transmission | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-TRNSYS-TRANS-BEVEL | DZ8234 Bevel Gear | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-TRNSYS-TRANS | DZ8234 Transmission | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-TRNSYS-DRSHT | DZ8234 Drive Shaft | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-TKFRR | DZ8234 Track Frame Right Hand | 26629 | 7157 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-TKFRL | DZ8234 Track Frame Left Hand | 26629 | 7157 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-PIVOT | DZ8234 Pivot Shaft | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-LDSFR | DZ8234 Rollers Load Single Flange RH | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-LDSFL | DZ8234 Rollers Load Single Flange LH | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-LDDFR | DZ8234 Rollers Load Double Flange RH | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-LDDFL | DZ8234 Rollers Load Double Flange LH | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-IDRHR | DZ8234 Idler Track Right Hand Rear | 26629 | 16358 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-IDRHF | DZ8234 Idler Track Right Hand Front | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-IDLHR | DZ8234 Idler Track Left Hand Rear | 26629 | 16358 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-IDLHF | DZ8234 Idler Track Left Hand Front | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-ADJRH | DZ8234 Track Adjuster Right Hand | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-UNDER-ADJLH | DZ8234 Track Adjuster Left Hand | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-RIPPR | DZ8234 Ripper | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CHASS-TRNON | DZ8234 Trunnions | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CHASS-PUARM | DZ8234 Push Arms | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CHASS-LNKGE | DZ8234 Link Stabiliser | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CHASS-EQUAL | DZ8234 Equaliser Bar | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CABIN-SEATS | DZ8234 Operators Seat | 26629 | 8321 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CABIN-SBELT | DZ8234 Seat Belt | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CABIN-AIRCN | DZ8234 Air Conditioning System | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-CABIN | DZ8234 Operators Cabin | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-STRUCT-BLADE | DZ8234 Blade | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYIP1 | DZ8234 Pump Hydraulic Implement 1 | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HYDPP-HYFPP | DZ8234 Pump Hydraulic Fan | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDTNK | DZ8234 Tank Hydraulic | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDOCO | DZ8234 Oil Cooler Hydraulic | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-RTCYR | DZ8234 Cylinder Ripper Tilt Right Hand | 26629 | 13947 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-RTCYL | DZ8234 Cylinder Ripper Tilt Left Hand | 26629 | 13947 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-RPUCY | DZ8234 Cylinder Ripper Pin Puller | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-RLCYR | DZ8234 Cylinder Ripper Lift Right Hand | 26629 | 11685 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-RLCYL | DZ8234 Cylinder Ripper Lift Left Hand | 26629 | 11685 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BTCYR | DZ8234 Cylinder Blade Tilt Right Hand | 26629 | 11685 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BTCYL | DZ8234 Cylinder Blade Tilt Left Hand | 26629 | 11685 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BLCYR | DZ8234 Cylinder Blade Lift Right Hand | 26629 | 4367 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCYL-BLCYL | DZ8234 Cylinder Blade Lift Left Hand | 26629 | 5612 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCVL | DZ8234 Implement Valves Hydraulic | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCON | DZ8234 Implement Control Hydraulic | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-HYDSYS-HDCFM | DZ8234 Fan Cooling Motor Hydraulic | 26629 | 3301 | 5000
CCK-MP-DOZR-DZ8234-GRSYST-GRINJ | DZ8234 Auto Lube Injectors | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-GRSYST-ALBPP | DZ8234 Auto Lube Pump | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-FRSUPP | DZ8234 Fire Suppression System | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-FDRSYS-TRKRH | DZ8234 Track Assembly Right Hand | 26629 | 7155 | 5000
CCK-MP-DOZR-DZ8234-FDRSYS-TRKLH | DZ8234 Track Assembly Left Hand | 26629 | 7155 | 5000
CCK-MP-DOZR-DZ8234-FDRSYS-SEGRH | DZ8234 Segments Right Hand | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-FDRSYS-SEGLH | DZ8234 Segments Left Hand | 26629 | 26629 | 5000
CCK-MP-DOZR-DZ8234-FDRSYS-FDRRH | DZ8234 Final Drive Right Hand | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-FDRSYS-FDRLH | DZ8234 Final Drive Left Hand | 26629 | 12967 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-LUBSY-PREPP | DZ8234 Oil Pump Pre-Lube Engine | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-LUBSY-OILPP | DZ8234 Oil Pump Engine | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-LUBSY-ENOLC | DZ8234 Oil Cooler Engine | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-INTEX-TBORH | DZ8234 Turbocharger Right Hand | 26641 | 5187 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-INTEX-TBOLH | DZ8234 Turbocharger Left Hand | 26641 | 5187 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-INTEX-AFTER | DZ8234 Aftercooler | 26641 | 12967 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-FUSYS-FULTP | DZ8234 Fuel Transfer Pump | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-FUSYS-FUINJ | DZ8234 Fuel Injectors | 26641 | 5187 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-COSYS-WTRPP | DZ8234 Water Pump Engine | 26641 | 5187 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-COSYS-THERM | DZ8234 Thermostats & Regulators | 26641 | 5187 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-COSYS-RADTR | DZ8234 Radiator Engine | 26641 | 12967 | 5000
CCK-MP-DOZR-DZ8234-ENGINE-COSYS-COFAN | DZ8234 Fan Cooling System | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ8234-ENGINE | DZ8234 Engine Assembly Caterpillar C27 | 26641 | 14816 | 5000
CCK-MP-DOZR-DZ8234-ELCTLV-START-STRMR | DZ8234 Starter Motor | 26641 | 5187 | 5000
CCK-MP-DOZR-DZ8234-ELCTLV-CHARG-BATTY | DZ8234 Batteries | 26641 | 10511 | 5000
CCK-MP-DOZR-DZ8234-ELCTLV-CHARG-ALTER | DZ8234 Alternator 24V | 26641 | 5187 | 5000
CCK-MP-DOZR-DZ8234-BRKSTR-STVLV | DZ8234 Valve Hydraulic Steering | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ8234-BRKSTR-SCABR | DZ8234 Steering Clutch & Brake Assy RH | 26641 | 12967 | 5000
CCK-MP-DOZR-DZ8234-BRKSTR-SCABL | DZ8234 Steering Clutch & Brake Assy LH | 26641 | 12967 | 5000
CCK-MP-DOZR-DZ8234-BRKSTR-HYSPP | DZ8234 Pump Hydraulic Steering | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ8234 | DZ8234 Caterpillar D10T2 Dozer | 26641 | 26641 | 5000
CCK-MP-DOZR-DZ184 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 67674 | 8753 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-PIVOT | DZ184 Pivot Shaft | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -TRNSYS-TRQUE | DZ184 Torque Converter | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -TRNSYS-TRPMP | DZ184 Pump Trans & Torque Converter Cha | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -TRNSYS-TROLC | DZ184 Oil Cooler Transmission | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -TRNSYS-TRANS-BEVEL | DZ184 Bevel Gear | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -TRNSYS-TRANS | DZ184 Transmission | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -TRNSYS | DZ184 Transmission System | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-TKFRR | DZ184 Track Frame R/H | 67674 | 12208 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-TKFRL | DZ184 Track Frame L/H | 67674 | 12208 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-LDSFR | DZ184 Rollers Load Single Flange Right | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-LDSFL | DZ184 Rollers Load Single Flange Left H | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-LDDFR | DZ184 Rollers Load Double Flange Right | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-LDDFL | DZ184 Rollers Load Double Flange Left H | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-IDRHR | DZ184 Idler Track R/H Rear | 67674 | 20823 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-IDRHF | DZ184 Idler Track R/H Front | 67674 | 58404 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-IDLHR | DZ184 Idler Track L/H Rear | 67674 | 58404 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-IDLHF | DZ184 Idler Track L/H Front | 67674 | 58404 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-ADJRH | DZ184 Track Adjuster R/H | 67674 | 39791 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER-ADJLH | DZ184 Track Adjuster L/H | 67657 | 3276 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-UNDER | DZ184 Undercarriage | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-STLAD-SLFXD | DZ184 Fixed Steps and Ladders | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-STLAD | DZ184 Steps and Ladders | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-RIPPR-RIGET | DZ184 Ripper Wear Elements (GET) | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-RIPPR | DZ184 Ripper | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-PNLGU | DZ184 Panels and Guards | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-PLHAN | DZ184 Platforms and Handrails | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CHASS-TRNON | DZ184 Trunnions | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CHASS-ROPSS | DZ184 Roll Over Protective Structure | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CHASS-PUARM | DZ184 Push Arms | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CHASS-LNKGE | DZ184 Link Stabiliser | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CHASS-EQUAL | DZ184 Equaliser Bar | 67674 | 12208 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CHASS | DZ184 Chassis | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN-SEATS | DZ184 Operators Seat | 67674 | 5213 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN-SBELT | DZ184 Seat Belt | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN-GLASS | DZ184 Glass | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN-CABPR | DZ184 Cabin Pressurisation System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN-CABES | DZ184 Cabin Entertainment System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN-CABCO | DZ184 Cabin Controls | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN-AIRCN | DZ184 Air Conditioning System | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-CABIN | DZ184 Operators Cabin | 67674 | 22343 | 5000
CCK-MP-DOZR-DZ184 -STRUCT-BLADE | DZ184 Blade | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -STRUCT | DZ184 Structure | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -MANGMT-UMMMC | DZ184 Mine Monitoring and Control | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -MANGMT-UMENG | DZ184 Engine Management System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -MANGMT | DZ184 Unit Management | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HYDPP-HYIPP | DZ184 Pump Hydraulic Implement | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HYDPP-HYFPP | DZ184 Pump Hydraulic Fan | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HYDPP | DZ184 Pumps Hydraulic | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDTNK | DZ184 Tank Hydraulic | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDOCO | DZ184 Oil Cooler Hydraulic | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDHLF | DZ184 Hydraulic System Hoses Lines Fitt | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-RTCYR | DZ184 Cylinder Ripper Tilt RH | 67674 | 12825 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-RTCYL | DZ184 Cylinder Ripper Tilt LH | 67674 | 3050 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-RPUCY | DZ184 Cylinder Ripper Pin Puller | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-RLCYR | DZ184 Cylinder Ripper Lift RH | 67674 | 12208 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-RLCYL | DZ184 Cylinder Ripper Lift LH | 67674 | 12825 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-BTCYR | DZ184 Cylinder Blade Tilt RH | 67674 | 10071 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-BTCYL | DZ184 Cylinder Blade Tilt LH | 67674 | 4346 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-BLCYR | DZ184 Cylinder Blade Lift RH | 67674 | 215 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL-BLCYL | DZ184 Cylinder Blade Lift LH | 67674 | 3474 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCYL | DZ184 Cylinders Hydraulic | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCVL | DZ184 Implement Valves Hydraulic | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCON | DZ184 Implement Control Hydraulic | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS-HDCFM | DZ184 Fan Cooling Motor Hydraulic | 67674 | 3050 | 5000
CCK-MP-DOZR-DZ184 -HYDSYS | DZ184 Hydraulic System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -GRSYST-GRTNK | DZ184 Auto Lube Resevoir | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -GRSYST-GRINJ | DZ184 Auto Lube Injectors | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -GRSYST-ALHLF | DZ184 Auto Lube Hoses Lines Fittings | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -GRSYST-ALELC | DZ184 Auto Lube Electrical | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -GRSYST-ALCON | DZ184 Auto Lube Controller | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -GRSYST-ALBPP | DZ184 Auto Lube Pump | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -GRSYST | DZ184 Grease Lubrication System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FRSUPP-FSMAN-EXTIN | DZ184 Hand Held Fire Extinguisher | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FRSUPP-FSMAN | DZ184 Fire Suppression Manual | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FRSUPP-FSAUT-FFOAM | DZ184 Fire Suppression Foam | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FRSUPP-FSAUT | DZ184 Fire Suppression Automatic | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FRSUPP-FSALM | DZ184 Fire System Alarm | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FRSUPP | DZ184 Fire Suppression System | 67674 | 35268 | 5000
CCK-MP-DOZR-DZ184 -FDRSYS-TRKRH | DZ184 Track Assembly R/H | 67674 | 3293 | 5000
CCK-MP-DOZR-DZ184 -FDRSYS-TRKLH | DZ184 Track Assembly L/H | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -FDRSYS-SEGRH | DZ184 Segments R/H | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FDRSYS-SEGLH | DZ184 Segments L/H | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -FDRSYS-FDRRH | DZ184 Final Drive R/H | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -FDRSYS-FDRLH | DZ184 Final Drive L/H | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -FDRSYS | DZ184 Final Drive System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-LUBSY-PREPP | DZ184 Oil Pump Pre-Lube Engine | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-LUBSY-OILPP | DZ184 Oil Pump Engine | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-LUBSY-ENOLC | DZ184 Oil Cooler Engine | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-LUBSY | DZ184 Engine Lubrication System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-INTEX-TBORH | DZ184 Turbocharger R/H | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-INTEX-TBOLH | DZ184 Turbocharger L/H | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-INTEX-EXHST | DZ184 Exhaust System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-INTEX-AIRFL | DZ184 Air Filtration System | 67674 | 22343 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-INTEX-AFTER | DZ184 Aftercooler | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-INTEX | DZ184 Intake and Exhaust System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-FUSYS-FULTP | DZ184 Fuel Transfer Pump | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-FUSYS-FULTK | DZ184 Fuel Tank | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-FUSYS-FUINJ | DZ184 Fuel Injectors | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-FUSYS-FUHLF | DZ184 Fuel System Hoses, Lines and Fitt | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-FUSYS | DZ184 Fuel System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-COSYS-WTRPP | DZ184 Water Pump Engine | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-COSYS-THERM | DZ184 Thermostats/Regulators | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-COSYS-RADTR | DZ184 Radiator Engine | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-COSYS-CSHLF | DZ184 Cooling System Hoses, Lines and F | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-COSYS-COFAN | DZ184 Fan Cooling System | 67674 | 22343 | 5000
CCK-MP-DOZR-DZ184 -ENGINE-COSYS | DZ184 Engine Cooling System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ENGINE | DZ184 Engine Assembly, Caterpillar C27 | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-START-STRMR | DZ184 Starter Motor | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-START | DZ184 Electrical Starting System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-LIGHT | DZ184 Lighting Low Voltage | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-HARNS | DZ184 Electrical Harness | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-CONTL | DZ184 Electrical Controls Low Voltage | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-CHARG-BATTY | DZ184 Batteries | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-CHARG-ALTER | DZ184 Alternator 24V | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV-CHARG | DZ184 Charging System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -ELCTLV | DZ184 Electrical System Low Voltage 24V | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -COMMUN-RADIO | DZ184 Two Way Radio | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -COMMUN-FLMGT | DZ184 Fleet Management | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -COMMUN | DZ184 Communications | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -BRKSTR-STVLV | DZ184 Valve Hydraulic Steering | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -BRKSTR-STHLF | DZ184 Steering System Hoses Lines and F | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -BRKSTR-STCON | DZ184 Controls Steering | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -BRKSTR-SCABR | DZ184 Steering Clutch and Brake Assembl | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -BRKSTR-SCABL | DZ184 Steering Clutch and Brake Assembl | 67674 | 8628 | 5000
CCK-MP-DOZR-DZ184 -BRKSTR-HYSPP | DZ184 Pump Hydraulic Steering | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 -BRKSTR | DZ184 Brake and Steering System | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 | DZ184 Mechanical & Lube Services | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ184 | Caterpillar D10T Dozer, DZ184 | 67674 | 67674 | 5000
CCK-MP-DOZR-DZ183 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 65816 | 8507 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-PIVOT | DZ183 Pivot Shaft | 65794 | 22779 | 5000
CCK-MP-DOZR-DZ183 -TRNSYS-TRQUE | DZ183 Torque Converter | 65794 | 2939 | 5000
CCK-MP-DOZR-DZ183 -TRNSYS-TRPMP | DZ183 Pump Trans & Torque Converter Cha | 65794 | 9873 | 5000
CCK-MP-DOZR-DZ183 -TRNSYS-TROLC | DZ183 Oil Cooler Transmission | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -TRNSYS-TRANS-BEVEL | DZ183 Bevel Gear | 65794 | 53339 | 5000
CCK-MP-DOZR-DZ183 -TRNSYS-TRANS | DZ183 Transmission | 65794 | 12584 | 5000
CCK-MP-DOZR-DZ183 -TRNSYS | DZ183 Transmission System | 65794 | 34266 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-TKFRR | DZ183 Track Frame R/H | 65794 | 11778 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-TKFRL | DZ183 Track Frame L/H | 65794 | 11778 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-LDSFR | DZ183 Rollers Load Single Flange Right | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-LDSFL | DZ183 Rollers Load Single Flange Left H | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-LDDFR | DZ183 Rollers Load Double Flange Right | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-LDDFL | DZ183 Rollers Load Double Flange Left H | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-IDRHR | DZ183 Idler Track R/H Rear | 65794 | 53339 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-IDRHF | DZ183 Idler Track R/H Front | 65794 | 53339 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-IDLHR | DZ183 Idler Track L/H Rear | 65794 | 52902 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-IDLHF | DZ183 Idler Track L/H Front | 65794 | 53339 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-ADJRH | DZ183 Track Adjuster R/H | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER-ADJLH | DZ183 Track Adjuster L/H | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-UNDER | DZ183 Undercarriage | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-STLAD-SLFXD | DZ183 Fixed Steps and Ladders | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-STLAD | DZ183 Steps and Ladders | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-RIPPR-RIGET | DZ183 Ripper Wear Elements (GET) | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-RIPPR | DZ183 Ripper | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-PNLGU | DZ183 Panels and Guards | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-PLHAN | DZ183 Platforms and Handrails | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CHASS-TRNON | DZ183 Trunnions | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CHASS-ROPSS | DZ183 Roll Over Protective Structure | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CHASS-PUARM | DZ183 Push Arms | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CHASS-LNKGE | DZ183 Link Stabiliser | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CHASS-EQUAL | DZ183 Equaliser Bar | 65794 | 15994 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CHASS | DZ183 Chassis | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN-SEATS | DZ183 Operators Seat | 65794 | 4209 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN-SBELT | DZ183 Seat Belt | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN-GLASS | DZ183 Glass | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN-CABPR | DZ183 Cabin Pressurisation System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN-CABES | DZ183 Cabin Entertainment System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN-CABCO | DZ183 Cabin Controls | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN-AIRCN | DZ183 Air Conditioning System | 65794 | 25789 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-CABIN | DZ183 Operators Cabin | 65794 | 4741 | 5000
CCK-MP-DOZR-DZ183 -STRUCT-BLADE | DZ183 Blade | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -STRUCT | DZ183 Structure | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -MANGMT-UMMMC | DZ183 Mine Monitoring and Control | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -MANGMT-UMENG | DZ183 Engine Management System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -MANGMT | DZ183 Unit Management | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HYDPP-HYIPP | DZ183 Pump Hydraulic Implement | 65794 | 3119 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HYDPP-HYFPP | DZ183 Pump Hydraulic Fan | 65794 | 7056 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HYDPP | DZ183 Pumps Hydraulic | 65794 | 53339 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDTNK | DZ183 Tank Hydraulic | 65794 | 6009 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDOCO | DZ183 Oil Cooler Hydraulic | 65820 | 19069 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDHLF | DZ183 Hydraulic System Hoses Lines Fitt | 65794 | 25789 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-RTCYR | DZ183 Cylinder Ripper Tilt RH | 65794 | 12584 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-RTCYL | DZ183 Cylinder Ripper Tilt LH | 65794 | 12584 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-RPUCY | DZ183 Cylinder Ripper Pin Puller | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-RLCYR | DZ183 Cylinder Ripper Lift RH | 65794 | 12584 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-RLCYL | DZ183 Cylinder Ripper Lift LH | 65794 | 12584 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-BTCYR | DZ183 Cylinder Blade Tilt RH | 65794 | 9294 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-BTCYL | DZ183 Cylinder Blade Tilt LH | 65794 | 16765 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-BLCYR | DZ183 Cylinder Blade Lift RH | 65794 | 2328 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL-BLCYL | DZ183 Cylinder Blade Lift LH | 65794 | 13113 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCYL | DZ183 Cylinders Hydraulic | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCVL | DZ183 Implement Valves Hydraulic | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCON | DZ183 Implement Control Hydraulic | 65794 | 25789 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS-HDCFM | DZ183 Fan Cooling Motor Hydraulic | 65794 | 2328 | 5000
CCK-MP-DOZR-DZ183 -HYDSYS | DZ183 Hydraulic System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -GRSYST-GRTNK | DZ183 Auto Lube Resevoir | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -GRSYST-GRINJ | DZ183 Auto Lube Injectors | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -GRSYST-ALHLF | DZ183 Auto Lube Hoses Lines Fittings | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -GRSYST-ALELC | DZ183 Auto Lube Electrical | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -GRSYST-ALCON | DZ183 Auto Lube Controller | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -GRSYST-ALBPP | DZ183 Auto Lube Pump | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -GRSYST | DZ183 Grease Lubrication System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FRSUPP-FSMAN-EXTIN | DZ183 Hand Held Fire Extinguisher | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FRSUPP-FSMAN | DZ183 Fire Suppression Manual | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FRSUPP-FSAUT-FFOAM | DZ183 Fire Suppression Foam | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FRSUPP-FSAUT | DZ183 Fire Suppression Automatic | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FRSUPP-FSALM | DZ183 Fire System Alarm | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FRSUPP | DZ183 Fire Suppression System | 65794 | 25789 | 5000
CCK-MP-DOZR-DZ183 -FDRSYS-TRKRH | DZ183 Track Assembly R/H | 65794 | 21220 | 5000
CCK-MP-DOZR-DZ183 -FDRSYS-TRKLH | DZ183 Track Assembly L/H | 65794 | 21220 | 5000
CCK-MP-DOZR-DZ183 -FDRSYS-SEGRH | DZ183 Segments R/H | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FDRSYS-SEGLH | DZ183 Segments L/H | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -FDRSYS-FDRRH | DZ183 Final Drive R/H | 65794 | 12144 | 5000
CCK-MP-DOZR-DZ183 -FDRSYS-FDRLH | DZ183 Final Drive L/H | 65794 | 12144 | 5000
CCK-MP-DOZR-DZ183 -FDRSYS | DZ183 Final Drive System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-LUBSY-PREPP | DZ183 Oil Pump Pre-Lube Engine | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-LUBSY-OILPP | DZ183 Oil Pump Engine | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-LUBSY-ENOLC | DZ183 Oil Cooler Engine | 65794 | 33454 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-LUBSY | DZ183 Engine Lubrication System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-INTEX-TBORH | DZ183 Turbocharger R/H | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-INTEX-TBOLH | DZ183 Turbocharger L/H | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-INTEX-EXHST | DZ183 Exhaust System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-INTEX-AIRFL | DZ183 Air Filtration System | 65794 | 25789 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-INTEX-AFTER | DZ183 Aftercooler | 65794 | 12584 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-INTEX | DZ183 Intake and Exhaust System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-FUSYS-FULTP | DZ183 Fuel Transfer Pump | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-FUSYS-FULTK | DZ183 Fuel Tank | 65794 | 12584 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-FUSYS-FUINJ | DZ183 Fuel Injectors | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-FUSYS-FUHLF | DZ183 Fuel System Hoses, Lines and Fitt | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-FUSYS | DZ183 Fuel System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-COSYS-WTRPP | DZ183 Water Pump Engine | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-COSYS-THERM | DZ183 Thermostats/Regulators | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-COSYS-RADTR | DZ183 Radiator Engine | 65794 | 14763 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-COSYS-CSHLF | DZ183 Cooling System Hoses, Lines and F | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-COSYS-COFAN | DZ183 Fan Cooling System | 65794 | 25789 | 5000
CCK-MP-DOZR-DZ183 -ENGINE-COSYS | DZ183 Engine Cooling System | 65794 | 65794 | 5000
CCK-MP-DOZR-DZ183 -ENGINE | DZ183 Engine Assembly, Caterpillar C27 | 65794 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-START-STRMR | DZ183 Starter Motor | 65807 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-START | DZ183 Electrical Starting System | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-LIGHT | DZ183 Lighting Low Voltage | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-HARNS | DZ183 Electrical Harness | 65807 | 25802 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-CONTL | DZ183 Electrical Controls Low Voltage | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-CHARG-BATTY | DZ183 Batteries | 65807 | 12584 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-CHARG-ALTER | DZ183 Alternator 24V | 65807 | 1433 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV-CHARG | DZ183 Charging System | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -ELCTLV | DZ183 Electrical System Low Voltage 24V | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -COMMUN-RADIO | DZ183 Two Way Radio | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -COMMUN-FLMGT | DZ183 Fleet Management | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -COMMUN | DZ183 Communications | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -BRKSTR-STVLV | DZ183 Valve Hydraulic Steering | 65807 | 25802 | 5000
CCK-MP-DOZR-DZ183 -BRKSTR-STHLF | DZ183 Steering System Hoses Lines and F | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -BRKSTR-STCON | DZ183 Controls Steering | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -BRKSTR-SCABR | DZ183 Steering Clutch and Brake Assembl | 65807 | 12144 | 5000
CCK-MP-DOZR-DZ183 -BRKSTR-SCABL | DZ183 Steering Clutch and Brake Assembl | 65807 | 12144 | 5000
CCK-MP-DOZR-DZ183 -BRKSTR-HYSPP | DZ183 Pump Hydraulic Steering | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 -BRKSTR | DZ183 Brake and Steering System | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 | DZ183 Mechanical & Lube Services | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ183 | Caterpillar D10T Dozer, DZ183 | 65807 | 65807 | 5000
CCK-MP-DOZR-DZ181 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 66307 | 8805 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-PIVOT | DZ181 Pivot Shaft | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -TRNSYS-TRQUE | DZ181 Torque Converter | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -TRNSYS-TRPMP | DZ181 Pump Trans & Torque Converter Cha | 66297 | 5876 | 5000
CCK-MP-DOZR-DZ181 -TRNSYS-TROLC | DZ181 Oil Cooler Transmission | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -TRNSYS-TRANS-BEVEL | DZ181 Bevel Gear | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -TRNSYS-TRANS | DZ181 Transmission | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -TRNSYS | DZ181 Transmission System | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-TKFRR | DZ181 Track Frame R/H | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-TKFRL | DZ181 Track Frame L/H | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-LDSFR | DZ181 Rollers Load Single Flange Right | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-LDSFL | DZ181 Rollers Load Single Flange Left H | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-LDDFR | DZ181 Rollers Load Double Flange Right | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-LDDFL | DZ181 Rollers Load Double Flange Left H | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-IDRHR | DZ181 Idler Track R/H Rear | 66297 | 21479 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-IDRHF | DZ181 Idler Track R/H Front | 66297 | 57626 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-IDLHR | DZ181 Idler Track L/H Rear | 66297 | 34445 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-IDLHF | DZ181 Idler Track L/H Front | 66297 | 34445 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-ADJRH | DZ181 Track Adjuster R/H | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER-ADJLH | DZ181 Track Adjuster L/H | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-UNDER | DZ181 Undercarriage | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-STLAD-SLFXD | DZ181 Fixed Steps and Ladders | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-STLAD | DZ181 Steps and Ladders | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-RIPPR-RIGET | DZ181 Ripper Wear Elements (GET) | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-RIPPR | DZ181 Ripper | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-PNLGU | DZ181 Panels and Guards | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-PLHAN | DZ181 Platforms and Handrails | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CHASS-TRNON | DZ181 Trunnions | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CHASS-ROPSS | DZ181 Roll Over Protective Structure | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CHASS-PUARM | DZ181 Push Arms | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CHASS-LNKGE | DZ181 Link Stabiliser | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CHASS-EQUAL | DZ181 Equaliser Bar | 66297 | 9861 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CHASS | DZ181 Chassis | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN-SEATS | DZ181 Operators Seat | 66297 | 691 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN-SBELT | DZ181 Seat Belt | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN-GLASS | DZ181 Glass | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN-CABPR | DZ181 Cabin Pressurisation System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN-CABES | DZ181 Cabin Entertainment System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN-CABCO | DZ181 Cabin Controls | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN-AIRCN | DZ181 Air Conditioning System | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-CABIN | DZ181 Operators Cabin | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -STRUCT-BLADE | DZ181 Blade | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -STRUCT | DZ181 Structure | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -MANGMT-UMMMC | DZ181 Mine Monitoring and Control | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -MANGMT-UMENG | DZ181 Engine Management System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -MANGMT | DZ181 Unit Management | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HYDPP-HYIPP | DZ181 Pump Hydraulic Implement | 66297 | 1907 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HYDPP-HYFPP | DZ181 Pump Hydraulic Fan | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HYDPP | DZ181 Pumps Hydraulic | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDTNK | DZ181 Tank Hydraulic | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDOCO | DZ181 Oil Cooler Hydraulic | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDHLF | DZ181 Hydraulic System Hoses Lines Fitt | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-RTCYR | DZ181 Cylinder Ripper Tilt RH | 66297 | 15797 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-RTCYL | DZ181 Cylinder Ripper Tilt LH | 66297 | 19841 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-RPUCY | DZ181 Cylinder Ripper Pin Puller | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-RLCYR | DZ181 Cylinder Ripper Lift RH | 66297 | 7203 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-RLCYL | DZ181 Cylinder Ripper Lift LH | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-BTCYR | DZ181 Cylinder Blade Tilt RH | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-BTCYL | DZ181 Cylinder Blade Tilt LH | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-BLCYR | DZ181 Cylinder Blade Lift RH | 66297 | 6103 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL-BLCYL | DZ181 Cylinder Blade Lift LH | 66297 | 11065 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCYL | DZ181 Cylinders Hydraulic | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCVL | DZ181 Implement Valves Hydraulic | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCON | DZ181 Implement Control Hydraulic | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS-HDCFM | DZ181 Fan Cooling Motor Hydraulic | 66297 | 4853 | 5000
CCK-MP-DOZR-DZ181 -HYDSYS | DZ181 Hydraulic System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -GRSYST-GRTNK | DZ181 Auto Lube Resevoir | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -GRSYST-GRINJ | DZ181 Auto Lube Injectors | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -GRSYST-ALHLF | DZ181 Auto Lube Hoses Lines Fittings | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -GRSYST-ALELC | DZ181 Auto Lube Electrical | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -GRSYST-ALCON | DZ181 Auto Lube Controller | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -GRSYST-ALBPP | DZ181 Auto Lube Pump | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -GRSYST | DZ181 Grease Lubrication System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FRSUPP-FSMAN-EXTIN | DZ181 Hand Held Fire Extinguisher | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FRSUPP-FSMAN | DZ181 Fire Suppression Manual | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FRSUPP-FSAUT-FFOAM | DZ181 Fire Suppression Foam | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FRSUPP-FSAUT | DZ181 Fire Suppression Automatic | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FRSUPP-FSALM | DZ181 Fire System Alarm | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FRSUPP | DZ181 Fire Suppression System | 66297 | 28539 | 5000
CCK-MP-DOZR-DZ181 -FDRSYS-TRKRH | DZ181 Track Assembly R/H | 66297 | 5874 | 5000
CCK-MP-DOZR-DZ181 -FDRSYS-TRKLH | DZ181 Track Assembly L/H | 66297 | 5874 | 5000
CCK-MP-DOZR-DZ181 -FDRSYS-SEGRH | DZ181 Segments R/H | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FDRSYS-SEGLH | DZ181 Segments L/H | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -FDRSYS-FDRRH | DZ181 Final Drive R/H | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -FDRSYS-FDRLH | DZ181 Final Drive L/H | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -FDRSYS | DZ181 Final Drive System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-LUBSY-PREPP | DZ181 Oil Pump Pre-Lube Engine | 66297 | 40683 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-LUBSY-OILPP | DZ181 Oil Pump Engine | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-LUBSY-ENOLC | DZ181 Oil Cooler Engine | 66297 | 40683 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-LUBSY | DZ181 Engine Lubrication System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-INTEX-TBORH | DZ181 Turbocharger R/H | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-INTEX-TBOLH | DZ181 Turbocharger L/H | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-INTEX-EXHST | DZ181 Exhaust System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-INTEX-AIRFL | DZ181 Air Filtration System | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-INTEX-AFTER | DZ181 Aftercooler | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-INTEX | DZ181 Intake and Exhaust System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-FUSYS-FULTP | DZ181 Fuel Transfer Pump | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-FUSYS-FULTK | DZ181 Fuel Tank | 66297 | 5874 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-FUSYS-FUINJ | DZ181 Fuel Injectors | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-FUSYS-FUHLF | DZ181 Fuel System Hoses, Lines and Fitt | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-FUSYS | DZ181 Fuel System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-COSYS-WTRPP | DZ181 Water Pump Engine | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-COSYS-THERM | DZ181 Thermostats/Regulators | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-COSYS-RADTR | DZ181 Radiator Engine | 66297 | 14318 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-COSYS-CSHLF | DZ181 Cooling System Hoses, Lines and F | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-COSYS-COFAN | DZ181 Fan Cooling System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE-COSYS | DZ181 Engine Cooling System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ENGINE | DZ181 Engine Assembly, Caterpillar C27 | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-START-STRMR | DZ181 Starter Motor | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-START | DZ181 Electrical Starting System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-LIGHT | DZ181 Lighting Low Voltage | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-HARNS | DZ181 Electrical Harness | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-CONTL | DZ181 Electrical Controls Low Voltage | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-CHARG-BATTY | DZ181 Batteries | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-CHARG-ALTER | DZ181 Alternator 24V | 66297 | 2402 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV-CHARG | DZ181 Charging System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -ELCTLV | DZ181 Electrical System Low Voltage 24V | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -COMMUN-RADIO | DZ181 Two Way Radio | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -COMMUN-FLMGT | DZ181 Fleet Management | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -COMMUN | DZ181 Communications | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -BRKSTR-STVLV | DZ181 Valve Hydraulic Steering | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -BRKSTR-STHLF | DZ181 Steering System Hoses Lines and F | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -BRKSTR-STCON | DZ181 Controls Steering | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -BRKSTR-SCABR | DZ181 Steering Clutch and Brake Assembl | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -BRKSTR-SCABL | DZ181 Steering Clutch and Brake Assembl | 66297 | 12007 | 5000
CCK-MP-DOZR-DZ181 -BRKSTR-HYSPP | DZ181 Pump Hydraulic Steering | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 -BRKSTR | DZ181 Brake and Steering System | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 | DZ181 Mechanical & Lube Services | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ181 | Caterpillar D10T Dozer, DZ181 | 66297 | 66297 | 5000
CCK-MP-DOZR-DZ180 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 63223 | 8685 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-PIVOT | DZ180 Pivot Shaft | 63195 | 25826 | 5000
CCK-MP-DOZR-DZ180 -TRNSYS-TRQUE | DZ180 Torque Converter | 63195 | 11095 | 5000
CCK-MP-DOZR-DZ180 -TRNSYS-TRPMP | DZ180 Pump Trans & Torque Converter Cha | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -TRNSYS-TROLC | DZ180 Oil Cooler Transmission | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -TRNSYS-TRANS-BEVEL | DZ180 Bevel Gear | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -TRNSYS-TRANS | DZ180 Transmission | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -TRNSYS | DZ180 Transmission System | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-TKFRR | DZ180 Track Frame R/H | 63195 | 12632 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-TKFRL | DZ180 Track Frame L/H | 63195 | 12632 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-LDSFR | DZ180 Rollers Load Single Flange Right | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-LDSFL | DZ180 Rollers Load Single Flange Left H | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-LDDFR | DZ180 Rollers Load Double Flange Right | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-LDDFL | DZ180 Rollers Load Double Flange Left H | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-IDRHR | DZ180 Idler Track R/H Rear | 63195 | 52932 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-IDRHF | DZ180 Idler Track R/H Front | 63195 | 52932 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-IDLHR | DZ180 Idler Track L/H Rear | 63195 | 50590 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-IDLHF | DZ180 Idler Track L/H Front | 63195 | 23604 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-ADJRH | DZ180 Track Adjuster R/H | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER-ADJLH | DZ180 Track Adjuster L/H | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-UNDER | DZ180 Undercarriage | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-STLAD-SLFXD | DZ180 Fixed Steps and Ladders | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-STLAD | DZ180 Steps and Ladders | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-RIPPR-RIGET | DZ180 Ripper Wear Elements (GET) | 63195 | 33756 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-RIPPR | DZ180 Ripper | 63195 | 33756 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-PNLGU | DZ180 Panels and Guards | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-PLHAN | DZ180 Platforms and Handrails | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CHASS-TRNON | DZ180 Trunnions | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CHASS-ROPSS | DZ180 Roll Over Protective Structure | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CHASS-PUARM | DZ180 Push Arms | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CHASS-LNKGE | DZ180 Link Stabiliser | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CHASS-EQUAL | DZ180 Equaliser Bar | 63195 | 14959 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CHASS | DZ180 Chassis | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN-SEATS | DZ180 Operators Seat | 63195 | 1342 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN-SBELT | DZ180 Seat Belt | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN-GLASS | DZ180 Glass | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN-CABPR | DZ180 Cabin Pressurisation System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN-CABES | DZ180 Cabin Entertainment System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN-CABCO | DZ180 Cabin Controls | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN-AIRCN | DZ180 Air Conditioning System | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-CABIN | DZ180 Operators Cabin | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -STRUCT-BLADE | DZ180 Blade | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -STRUCT | DZ180 Structure | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -MANGMT-UMMMC | DZ180 Mine Monitoring and Control | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -MANGMT-UMENG | DZ180 Engine Management System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -MANGMT | DZ180 Unit Management | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HYDPP-HYIPP | DZ180 Pump Hydraulic Implement | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HYDPP-HYFPP | DZ180 Pump Hydraulic Fan | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HYDPP | DZ180 Pumps Hydraulic | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDTNK | DZ180 Tank Hydraulic | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDOCO | DZ180 Oil Cooler Hydraulic | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDHLF | DZ180 Hydraulic System Hoses Lines Fitt | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-RTCYR | DZ180 Cylinder Ripper Tilt RH | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-RTCYL | DZ180 Cylinder Ripper Tilt LH | 63195 | 16409 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-RPUCY | DZ180 Cylinder Ripper Pin Puller | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-RLCYR | DZ180 Cylinder Ripper Lift RH | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-RLCYL | DZ180 Cylinder Ripper Lift LH | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BTCYR | DZ180 Cylinder Blade Tilt RH | 63195 | 11095 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BTCYL | DZ180 Cylinder Blade Tilt LH | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BLCYR | DZ180 Cylinder Blade Lift RH | 63195 | 3729 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL-BLCYL | DZ180 Cylinder Blade Lift LH | 63195 | 3729 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCYL | DZ180 Cylinders Hydraulic | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCVL | DZ180 Implement Valves Hydraulic | 63195 | 33831 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCON | DZ180 Implement Control Hydraulic | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS-HDCFM | DZ180 Fan Cooling Motor Hydraulic | 63195 | 1456 | 5000
CCK-MP-DOZR-DZ180 -HYDSYS | DZ180 Hydraulic System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -GRSYST-GRTNK | DZ180 Auto Lube Resevoir | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -GRSYST-GRINJ | DZ180 Auto Lube Injectors | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -GRSYST-ALHLF | DZ180 Auto Lube Hoses Lines Fittings | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -GRSYST-ALELC | DZ180 Auto Lube Electrical | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -GRSYST-ALCON | DZ180 Auto Lube Controller | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -GRSYST-ALBPP | DZ180 Auto Lube Pump | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -GRSYST | DZ180 Grease Lubrication System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FRSUPP-FSMAN-EXTIN | DZ180 Hand Held Fire Extinguisher | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FRSUPP-FSMAN | DZ180 Fire Suppression Manual | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FRSUPP-FSAUT-FFOAM | DZ180 Fire Suppression Foam | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FRSUPP-FSAUT | DZ180 Fire Suppression Automatic | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FRSUPP-FSALM | DZ180 Fire System Alarm | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FRSUPP | DZ180 Fire Suppression System | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -FDRSYS-TRKRH | DZ180 Track Assembly R/H | 63195 | 5948 | 5000
CCK-MP-DOZR-DZ180 -FDRSYS-TRKLH | DZ180 Track Assembly L/H | 63195 | 5948 | 5000
CCK-MP-DOZR-DZ180 -FDRSYS-SEGRH | DZ180 Segments R/H | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FDRSYS-SEGLH | DZ180 Segments L/H | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -FDRSYS-FDRRH | DZ180 Final Drive R/H | 63195 | 15197 | 5000
CCK-MP-DOZR-DZ180 -FDRSYS-FDRLH | DZ180 Final Drive L/H | 63195 | 8038 | 5000
CCK-MP-DOZR-DZ180 -FDRSYS | DZ180 Final Drive System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-LUBSY-PREPP | DZ180 Oil Pump Pre-Lube Engine | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-LUBSY-OILPP | DZ180 Oil Pump Engine | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-LUBSY-ENOLC | DZ180 Oil Cooler Engine | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-LUBSY | DZ180 Engine Lubrication System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-INTEX-TBORH | DZ180 Turbocharger R/H | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-INTEX-TBOLH | DZ180 Turbocharger L/H | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-INTEX-EXHST | DZ180 Exhaust System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-INTEX-AIRFL | DZ180 Air Filtration System | 63195 | 20727 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-INTEX-AFTER | DZ180 Aftercooler | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-INTEX | DZ180 Intake and Exhaust System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-FUSYS-FULTP | DZ180 Fuel Transfer Pump | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-FUSYS-FULTK | DZ180 Fuel Tank | 63195 | 33831 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-FUSYS-FUINJ | DZ180 Fuel Injectors | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-FUSYS-FUHLF | DZ180 Fuel System Hoses, Lines and Fitt | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-FUSYS | DZ180 Fuel System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-COSYS-WTRPP | DZ180 Water Pump Engine | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-COSYS-THERM | DZ180 Thermostats/Regulators | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-COSYS-RADTR | DZ180 Radiator Engine | 63195 | 9998 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-COSYS-CSHLF | DZ180 Cooling System Hoses, Lines and F | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-COSYS-COFAN | DZ180 Fan Cooling System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE-COSYS | DZ180 Engine Cooling System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ENGINE | DZ180 Engine Assembly, Caterpillar C27 | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-START-STRMR | DZ180 Starter Motor | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-START | DZ180 Electrical Starting System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-LIGHT | DZ180 Lighting Low Voltage | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-HARNS | DZ180 Electrical Harness | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-CONTL | DZ180 Electrical Controls Low Voltage | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-CHARG-BATTY | DZ180 Batteries | 63195 | 14010 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-CHARG-ALTER | DZ180 Alternator 24V | 63195 | 7949 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV-CHARG | DZ180 Charging System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -ELCTLV | DZ180 Electrical System Low Voltage 24V | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -COMMUN-RADIO | DZ180 Two Way Radio | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -COMMUN-FLMGT | DZ180 Fleet Management | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -COMMUN | DZ180 Communications | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -BRKSTR-STVLV | DZ180 Valve Hydraulic Steering | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -BRKSTR-STHLF | DZ180 Steering System Hoses Lines and F | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -BRKSTR-STCON | DZ180 Controls Steering | 63195 | 33831 | 5000
CCK-MP-DOZR-DZ180 -BRKSTR-SCABR | DZ180 Steering Clutch and Brake Assembl | 63195 | 9998 | 5000
CCK-MP-DOZR-DZ180 -BRKSTR-SCABL | DZ180 Steering Clutch and Brake Assembl | 63195 | 7626 | 5000
CCK-MP-DOZR-DZ180 -BRKSTR-HYSPP | DZ180 Pump Hydraulic Steering | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 -BRKSTR | DZ180 Brake and Steering System | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 | DZ180 Mechanical & Lube Services | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ180 | Caterpillar D10T Dozer, DZ180 | 63195 | 63195 | 5000
CCK-MP-DOZR-DZ178 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 54754 | 6596 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-PIVOT | DZ178 Pivot Shaft | 54741 | 22197 | 5000
CCK-MP-DOZR-DZ178 -COMMUN-RADIO | DZ178 Two Way Radio | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -COMMUN-FLMGT | DZ178 Fleet Management | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -COMMUN | DZ178 Communications | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -MANGMT-UMMMC | DZ178 Mine Monitoring and Control | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -MANGMT-UMENG | DZ178 Engine Management System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -MANGMT | DZ178 Unit Management | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FRSUPP-FSALM | DZ178 Fire System Alarm | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FRSUPP-FSMAN-EXTIN | DZ178 Hand Held Fire Extinguisher | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FRSUPP-FSMAN | DZ178 Fire Suppression Manual | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FRSUPP-FSAUT-FFOAM | DZ178 Fire Suppression Foam | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FRSUPP-FSAUT | DZ178 Fire Suppression Automatic | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FRSUPP | DZ178 Fire Suppression System | 54741 | 16983 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-RIPPR-RIGET | DZ178 Ripper Wear Elements (GET) | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-RIPPR | DZ178 Ripper | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-BLADE | DZ178 Blade | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-PLHAN | DZ178 Platforms and Handrails | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-STLAD-SLFXD | DZ178 Fixed Steps and Ladders | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-STLAD | DZ178 Steps and Ladders | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-PNLGU | DZ178 Panels and Guards | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-LDDFR | DZ178 Rollers Load Double Flange Right | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-LDSFR | DZ178 Rollers Load Single Flange Right | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-LDDFL | DZ178 Rollers Load Double Flange Left H | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-LDSFL | DZ178 Rollers Load Single Flange Left H | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-IDRHR | DZ178 Idler Track R/H Rear | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-IDRHF | DZ178 Idler Track R/H Front | 54741 | 27037 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-ADJRH | DZ178 Track Adjuster R/H | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-TKFRR | DZ178 Track Frame R/H | 54741 | 4806 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-IDLHR | DZ178 Idler Track L/H Rear | 54741 | 20147 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-IDLHF | DZ178 Idler Track L/H Front | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-ADJLH | DZ178 Track Adjuster L/H | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER-TKFRL | DZ178 Track Frame L/H | 54741 | 4806 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-UNDER | DZ178 Undercarriage | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CHASS-TRNON | DZ178 Trunnions | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CHASS-LNKGE | DZ178 Link Stabiliser | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CHASS-PUARM | DZ178 Push Arms | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CHASS-EQUAL | DZ178 Equaliser Bar | 54741 | 22416 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CHASS-ROPSS | DZ178 Roll Over Protective Structure | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CHASS | DZ178 Chassis | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN-SBELT | DZ178 Seat Belt | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN-GLASS | DZ178 Glass | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN-SEATS | DZ178 Operators Seat | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN-CABES | DZ178 Cabin Entertainment System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN-CABCO | DZ178 Cabin Controls | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN-CABPR | DZ178 Cabin Pressurisation System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN-AIRCN | DZ178 Air Conditioning System | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -STRUCT-CABIN | DZ178 Operators Cabin | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -STRUCT | DZ178 Structure | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -GRSYST-ALHLF | DZ178 Auto Lube Hoses Lines Fittings | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -GRSYST-ALELC | DZ178 Auto Lube Electrical | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -GRSYST-ALCON | DZ178 Auto Lube Controller | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -GRSYST-ALBPP | DZ178 Auto Lube Pump | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -GRSYST-GRTNK | DZ178 Auto Lube Resevoir | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -GRSYST-GRINJ | DZ178 Auto Lube Injectors | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -GRSYST | DZ178 Grease Lubrication System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDHLF | DZ178 Hydraulic System Hoses Lines Fitt | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCFM | DZ178 Fan Cooling Motor Hydraulic | 54741 | 433 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDOCO | DZ178 Oil Cooler Hydraulic | 54741 | 7755 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDTNK | DZ178 Tank Hydraulic | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-RPUCY | DZ178 Cylinder Ripper Pin Puller | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-RTCYR | DZ178 Cylinder Ripper Tilt RH | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-RTCYL | DZ178 Cylinder Ripper Tilt LH | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-RLCYR | DZ178 Cylinder Ripper Lift RH | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-RLCYL | DZ178 Cylinder Ripper Lift LH | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-BTCYR | DZ178 Cylinder Blade Tilt RH | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-BTCYL | DZ178 Cylinder Blade Tilt LH | 54741 | 4806 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-BLCYR | DZ178 Cylinder Blade Lift RH | 54741 | 1969 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL-BLCYL | DZ178 Cylinder Blade Lift LH | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCYL | DZ178 Cylinders Hydraulic | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCON | DZ178 Implement Control Hydraulic | 54741 | 30542 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HDCVL | DZ178 Implement Valves Hydraulic | 54741 | 19370 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HYDPP-HYIPP | DZ178 Pump Hydraulic Implement | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HYDPP-HYFPP | DZ178 Pump Hydraulic Fan | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS-HYDPP | DZ178 Pumps Hydraulic | 54741 | 19370 | 5000
CCK-MP-DOZR-DZ178 -HYDSYS | DZ178 Hydraulic System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -BRKSTR-STHLF | DZ178 Steering System Hoses Lines and F | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -BRKSTR-STCON | DZ178 Controls Steering | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -BRKSTR-SCABR | DZ178 Steering Clutch and Brake Assembl | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -BRKSTR-SCABL | DZ178 Steering Clutch and Brake Assembl | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -BRKSTR-STVLV | DZ178 Valve Hydraulic Steering | 54741 | 30542 | 5000
CCK-MP-DOZR-DZ178 -BRKSTR-HYSPP | DZ178 Pump Hydraulic Steering | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -BRKSTR | DZ178 Brake and Steering System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FDRSYS-TRKRH | DZ178 Track Assembly R/H | 54741 | 2735 | 5000
CCK-MP-DOZR-DZ178 -FDRSYS-SEGRH | DZ178 Segments R/H | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FDRSYS-FDRRH | DZ178 Final Drive R/H | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -FDRSYS-TRKLH | DZ178 Track Assembly L/H | 54741 | 2735 | 5000
CCK-MP-DOZR-DZ178 -FDRSYS-SEGLH | DZ178 Segments L/H | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -FDRSYS-FDRLH | DZ178 Final Drive L/H | 54741 | 5886 | 5000
CCK-MP-DOZR-DZ178 -FDRSYS | DZ178 Final Drive System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -TRNSYS-TRPMP | DZ178 Pump Trans & Torque Converter Cha | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -TRNSYS-TROLC | DZ178 Oil Cooler Transmission | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -TRNSYS-TRANS-BEVEL | DZ178 Bevel Gear | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -TRNSYS-TRANS | DZ178 Transmission | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -TRNSYS-TRQUE | DZ178 Torque Converter | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -TRNSYS | DZ178 Transmission System | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-START-STRMR | DZ178 Starter Motor | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-START | DZ178 Electrical Starting System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-CHARG-BATTY | DZ178 Batteries | 54741 | 4781 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-CHARG-ALTER | DZ178 Alternator 24V | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-CHARG | DZ178 Charging System | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-LIGHT | DZ178 Lighting Low Voltage | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-CONTL | DZ178 Electrical Controls Low Voltage | 54741 | 54741 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV-HARNS | DZ178 Electrical Harness | 54752 | 30553 | 5000
CCK-MP-DOZR-DZ178 -ELCTLV | DZ178 Electrical System Low Voltage 24V | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-FUSYS-FUHLF | DZ178 Fuel System Hoses, Lines and Fitt | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-FUSYS-FUINJ | DZ178 Fuel Injectors | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-FUSYS-FULTP | DZ178 Fuel Transfer Pump | 54752 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-FUSYS-FULTK | DZ178 Fuel Tank | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-FUSYS | DZ178 Fuel System | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-INTEX-EXHST | DZ178 Exhaust System | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-INTEX-AFTER | DZ178 Aftercooler | 54752 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-INTEX-TBORH | DZ178 Turbocharger R/H | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-INTEX-TBOLH | DZ178 Turbocharger L/H | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-INTEX-AIRFL | DZ178 Air Filtration System | 54752 | 16983 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-INTEX | DZ178 Intake and Exhaust System | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-COSYS-CSHLF | DZ178 Cooling System Hoses, Lines and F | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-COSYS-THERM | DZ178 Thermostats/Regulators | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-COSYS-COFAN | DZ178 Fan Cooling System | 54752 | 30553 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-COSYS-RADTR | DZ178 Radiator Engine | 54752 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-COSYS-WTRPP | DZ178 Water Pump Engine | 54741 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-COSYS | DZ178 Engine Cooling System | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-LUBSY-PREPP | DZ178 Oil Pump Pre-Lube Engine | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-LUBSY-ENOLC | DZ178 Oil Cooler Engine | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-LUBSY-OILPP | DZ178 Oil Pump Engine | 54752 | 3721 | 5000
CCK-MP-DOZR-DZ178 -ENGINE-LUBSY | DZ178 Engine Lubrication System | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ178 -ENGINE | DZ178 Engine Assembly, Caterpillar C27 | 54752 | 3721 | 5000
CCK-MP-DOZR-DZ178 | DZ178 Mechanical & Lube Services | 54448 | 54448 | 5000
CCK-MP-DOZR-DZ178 | Caterpillar D10T Dozer, DZ178 | 54752 | 54752 | 5000
CCK-MP-DOZR-DZ176 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 69727 | 8828 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-PIVOT | DZ176 Pivot Shaft | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -TRNSYS-TRQUE | DZ176 Torque Converter | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -TRNSYS-TRPMP | DZ176 Pump Trans & Torque Converter Cha | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -TRNSYS-TROLC | DZ176 Oil Cooler Transmission | 69680 | 44725 | 5000
CCK-MP-DOZR-DZ176 -TRNSYS-TRANS-BEVEL | DZ176 Bevel Gear | 69680 | 55512 | 5000
CCK-MP-DOZR-DZ176 -TRNSYS-TRANS | DZ176 Transmission | 69680 | 4667 | 5000
CCK-MP-DOZR-DZ176 -TRNSYS | DZ176 Transmission System | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-TKFRR | DZ176 Track Frame R/H | 69680 | 7159 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-TKFRL | DZ176 Track Frame L/H | 69680 | 7159 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-LDSFR | DZ176 Rollers Load Single Flange Right | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-LDSFL | DZ176 Rollers Load Single Flange Left H | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-LDDFR | DZ176 Rollers Load Double Flange Right | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-LDDFL | DZ176 Rollers Load Double Flange Left H | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-IDRHR | DZ176 Idler Track R/H Rear | 69680 | 12930 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-IDRHF | DZ176 Idler Track R/H Front | 69680 | 12930 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-IDLHR | DZ176 Idler Track L/H Rear | 69680 | 12930 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-IDLHF | DZ176 Idler Track L/H Front | 69680 | 12930 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-ADJRH | DZ176 Track Adjuster R/H | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER-ADJLH | DZ176 Track Adjuster L/H | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-UNDER | DZ176 Undercarriage | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-STLAD-SLFXD | DZ176 Fixed Steps and Ladders | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-STLAD | DZ176 Steps and Ladders | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-RIPPR-RIGET | DZ176 Ripper Wear Elements (GET) | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-RIPPR | DZ176 Ripper | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-PNLGU | DZ176 Panels and Guards | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-PLHAN | DZ176 Platforms and Handrails | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CHASS-TRNON | DZ176 Trunnions | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CHASS-ROPSS | DZ176 Roll Over Protective Structure | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CHASS-PUARM | DZ176 Push Arms | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CHASS-LNKGE | DZ176 Link Stabiliser | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CHASS-EQUAL | DZ176 Equaliser Bar | 69680 | 10953 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CHASS | DZ176 Chassis | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN-SEATS | DZ176 Operators Seat | 69680 | 2541 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN-SBELT | DZ176 Seat Belt | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN-GLASS | DZ176 Glass | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN-CABPR | DZ176 Cabin Pressurisation System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN-CABES | DZ176 Cabin Entertainment System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN-CABCO | DZ176 Cabin Controls | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN-AIRCN | DZ176 Air Conditioning System | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-CABIN | DZ176 Operators Cabin | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -STRUCT-BLADE | DZ176 Blade | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -STRUCT | DZ176 Structure | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -MANGMT-UMMMC | DZ176 Mine Monitoring and Control | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -MANGMT-UMENG | DZ176 Engine Management System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -MANGMT | DZ176 Unit Management | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HYDPP-HYIPP | DZ176 Pump Hydraulic Implement | 69680 | 5908 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HYDPP-HYFPP | DZ176 Pump Hydraulic Fan | 69680 | 8485 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HYDPP | DZ176 Pumps Hydraulic | 69680 | 56595 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDTNK | DZ176 Tank Hydraulic | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDOCO | DZ176 Oil Cooler Hydraulic | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDHLF | DZ176 Hydraulic System Hoses Lines Fitt | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-RTCYR | DZ176 Cylinder Ripper Tilt RH | 69680 | 3205 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-RTCYL | DZ176 Cylinder Ripper Tilt LH | 69680 | 3205 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-RPUCY | DZ176 Cylinder Ripper Pin Puller | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-RLCYR | DZ176 Cylinder Ripper Lift RH | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-RLCYL | DZ176 Cylinder Ripper Lift LH | 69680 | 8943 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BTCYR | DZ176 Cylinder Blade Tilt RH | 69680 | 9755 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BTCYL | DZ176 Cylinder Blade Tilt LH | 69680 | 8485 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BLCYR | DZ176 Cylinder Blade Lift RH | 69680 | 4914 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL-BLCYL | DZ176 Cylinder Blade Lift LH | 69680 | 8485 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCYL | DZ176 Cylinders Hydraulic | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCVL | DZ176 Implement Valves Hydraulic | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCON | DZ176 Implement Control Hydraulic | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS-HDCFM | DZ176 Fan Cooling Motor Hydraulic | 69680 | 1080 | 5000
CCK-MP-DOZR-DZ176 -HYDSYS | DZ176 Hydraulic System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -GRSYST-GRTNK | DZ176 Auto Lube Resevoir | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -GRSYST-GRINJ | DZ176 Auto Lube Injectors | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -GRSYST-ALHLF | DZ176 Auto Lube Hoses Lines Fittings | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -GRSYST-ALELC | DZ176 Auto Lube Electrical | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -GRSYST-ALCON | DZ176 Auto Lube Controller | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -GRSYST-ALBPP | DZ176 Auto Lube Pump | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -GRSYST | DZ176 Grease Lubrication System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FRSUPP-FSMAN-EXTIN | DZ176 Hand Held Fire Extinguisher | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FRSUPP-FSMAN | DZ176 Fire Suppression Manual | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FRSUPP-FSAUT-FFOAM | DZ176 Fire Suppression Foam | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FRSUPP-FSAUT | DZ176 Fire Suppression Automatic | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FRSUPP-FSALM | DZ176 Fire System Alarm | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FRSUPP | DZ176 Fire Suppression System | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -FDRSYS-TRKRH | DZ176 Track Assembly R/H | 69680 | 7159 | 5000
CCK-MP-DOZR-DZ176 -FDRSYS-TRKLH | DZ176 Track Assembly L/H | 69680 | 7159 | 5000
CCK-MP-DOZR-DZ176 -FDRSYS-SEGRH | DZ176 Segments R/H | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FDRSYS-SEGLH | DZ176 Segments L/H | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -FDRSYS-FDRRH | DZ176 Final Drive R/H | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -FDRSYS-FDRLH | DZ176 Final Drive L/H | 69680 | 7159 | 5000
CCK-MP-DOZR-DZ176 -FDRSYS | DZ176 Final Drive System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-LUBSY-PREPP | DZ176 Oil Pump Pre-Lube Engine | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-LUBSY-OILPP | DZ176 Oil Pump Engine | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-LUBSY-ENOLC | DZ176 Oil Cooler Engine | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-LUBSY | DZ176 Engine Lubrication System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-INTEX-TBORH | DZ176 Turbocharger R/H | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-INTEX-TBOLH | DZ176 Turbocharger L/H | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-INTEX-EXHST | DZ176 Exhaust System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-INTEX-AIRFL | DZ176 Air Filtration System | 69680 | 30968 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-INTEX-AFTER | DZ176 Aftercooler | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-INTEX | DZ176 Intake and Exhaust System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-FUSYS-FULTP | DZ176 Fuel Transfer Pump | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-FUSYS-FULTK | DZ176 Fuel Tank | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-FUSYS-FUINJ | DZ176 Fuel Injectors | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-FUSYS-FUHLF | DZ176 Fuel System Hoses, Lines and Fitt | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-FUSYS | DZ176 Fuel System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-COSYS-WTRPP | DZ176 Water Pump Engine | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-COSYS-THERM | DZ176 Thermostats/Regulators | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-COSYS-RADTR | DZ176 Radiator Engine | 69680 | 16621 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-COSYS-CSHLF | DZ176 Cooling System Hoses, Lines and F | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-COSYS-COFAN | DZ176 Fan Cooling System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE-COSYS | DZ176 Engine Cooling System | 69680 | 69680 | 5000
CCK-MP-DOZR-DZ176 -ENGINE | DZ176 Engine Assembly, Caterpillar C27 | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-START-STRMR | DZ176 Starter Motor | 69680 | 784 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-START | DZ176 Electrical Starting System | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-LIGHT | DZ176 Lighting Low Voltage | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-HARNS | DZ176 Electrical Harness | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-CONTL | DZ176 Electrical Controls Low Voltage | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-CHARG-BATTY | DZ176 Batteries | 69693 | 9755 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-CHARG-ALTER | DZ176 Alternator 24V | 69693 | 784 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV-CHARG | DZ176 Charging System | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -ELCTLV | DZ176 Electrical System Low Voltage 24V | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -COMMUN-RADIO | DZ176 Two Way Radio | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -COMMUN-FLMGT | DZ176 Fleet Management | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -COMMUN | DZ176 Communications | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -BRKSTR-STVLV | DZ176 Valve Hydraulic Steering | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -BRKSTR-STHLF | DZ176 Steering System Hoses Lines and F | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -BRKSTR-STCON | DZ176 Controls Steering | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -BRKSTR-SCABR | DZ176 Steering Clutch and Brake Assembl | 69693 | 16621 | 5000
CCK-MP-DOZR-DZ176 -BRKSTR-SCABL | DZ176 Steering Clutch and Brake Assembl | 69693 | 5898 | 5000
CCK-MP-DOZR-DZ176 -BRKSTR-HYSPP | DZ176 Pump Hydraulic Steering | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 -BRKSTR | DZ176 Brake and Steering System | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 | DZ176 Mechanical & Lube Services | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ176 | Caterpillar D10T Dozer, DZ176 | 69693 | 69693 | 5000
CCK-MP-DOZR-DZ175 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 71849 | 8969 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-PIVOT | DZ175 Pivot Shaft | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -TRNSYS-TRQUE | DZ175 Torque Converter | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -TRNSYS-TRPMP | DZ175 Pump Trans & Torque Converter Cha | 71802 | 10261 | 5000
CCK-MP-DOZR-DZ175 -TRNSYS-TROLC | DZ175 Oil Cooler Transmission | 71802 | 46628 | 5000
CCK-MP-DOZR-DZ175 -TRNSYS-TRANS-BEVEL | DZ175 Bevel Gear | 71802 | 58805 | 5000
CCK-MP-DOZR-DZ175 -TRNSYS-TRANS | DZ175 Transmission | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -TRNSYS | DZ175 Transmission System | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-TKFRR | DZ175 Track Frame R/H | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-TKFRL | DZ175 Track Frame L/H | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-LDSFR | DZ175 Rollers Load Single Flange Right | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-LDSFL | DZ175 Rollers Load Single Flange Left H | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-LDDFR | DZ175 Rollers Load Double Flange Right | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-LDDFL | DZ175 Rollers Load Double Flange Left H | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-IDRHR | DZ175 Idler Track R/H Rear | 71802 | 61483 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-IDRHF | DZ175 Idler Track R/H Front | 71802 | 61483 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-IDLHR | DZ175 Idler Track L/H Rear | 71802 | 61483 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-IDLHF | DZ175 Idler Track L/H Front | 71802 | 61483 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-ADJRH | DZ175 Track Adjuster R/H | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER-ADJLH | DZ175 Track Adjuster L/H | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-UNDER | DZ175 Undercarriage | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-STLAD-SLFXD | DZ175 Fixed Steps and Ladders | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-STLAD | DZ175 Steps and Ladders | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-RIPPR-RIGET | DZ175 Ripper Wear Elements (GET) | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-RIPPR | DZ175 Ripper | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-PNLGU | DZ175 Panels and Guards | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-PLHAN | DZ175 Platforms and Handrails | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CHASS-TRNON | DZ175 Trunnions | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CHASS-ROPSS | DZ175 Roll Over Protective Structure | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CHASS-PUARM | DZ175 Push Arms | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CHASS-LNKGE | DZ175 Link Stabiliser | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CHASS-EQUAL | DZ175 Equaliser Bar | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CHASS | DZ175 Chassis | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN-SEATS | DZ175 Operators Seat | 71802 | 6554 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN-SBELT | DZ175 Seat Belt | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN-GLASS | DZ175 Glass | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN-CABPR | DZ175 Cabin Pressurisation System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN-CABES | DZ175 Cabin Entertainment System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN-CABCO | DZ175 Cabin Controls | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN-AIRCN | DZ175 Air Conditioning System | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-CABIN | DZ175 Operators Cabin | 71802 | 37918 | 5000
CCK-MP-DOZR-DZ175 -STRUCT-BLADE | DZ175 Blade | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -STRUCT | DZ175 Structure | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -MANGMT-UMMMC | DZ175 Mine Monitoring and Control | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -MANGMT-UMENG | DZ175 Engine Management System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -MANGMT | DZ175 Unit Management | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HYDPP-HYIPP | DZ175 Pump Hydraulic Implement | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HYDPP-HYFPP | DZ175 Pump Hydraulic Fan | 71802 | 8775 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HYDPP | DZ175 Pumps Hydraulic | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDTNK | DZ175 Tank Hydraulic | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDOCO | DZ175 Oil Cooler Hydraulic | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDHLF | DZ175 Hydraulic System Hoses Lines Fitt | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-RTCYR | DZ175 Cylinder Ripper Tilt RH | 71802 | 8774 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-RTCYL | DZ175 Cylinder Ripper Tilt LH | 71802 | 8774 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-RPUCY | DZ175 Cylinder Ripper Pin Puller | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-RLCYR | DZ175 Cylinder Ripper Lift RH | 71802 | 8774 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-RLCYL | DZ175 Cylinder Ripper Lift LH | 71802 | 8774 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-BTCYR | DZ175 Cylinder Blade Tilt RH | 71802 | 583 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-BTCYL | DZ175 Cylinder Blade Tilt LH | 71802 | 24 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-BLCYR | DZ175 Cylinder Blade Lift RH | 71802 | 24 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL-BLCYL | DZ175 Cylinder Blade Lift LH | 71802 | 3554 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCYL | DZ175 Cylinders Hydraulic | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCVL | DZ175 Implement Valves Hydraulic | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCON | DZ175 Implement Control Hydraulic | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS-HDCFM | DZ175 Fan Cooling Motor Hydraulic | 71802 | 1271 | 5000
CCK-MP-DOZR-DZ175 -HYDSYS | DZ175 Hydraulic System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -GRSYST-GRTNK | DZ175 Auto Lube Resevoir | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -GRSYST-GRINJ | DZ175 Auto Lube Injectors | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -GRSYST-ALHLF | DZ175 Auto Lube Hoses Lines Fittings | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -GRSYST-ALELC | DZ175 Auto Lube Electrical | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -GRSYST-ALCON | DZ175 Auto Lube Controller | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -GRSYST-ALBPP | DZ175 Auto Lube Pump | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -GRSYST | DZ175 Grease Lubrication System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -FRSUPP-FSMAN-EXTIN | DZ175 Hand Held Fire Extinguisher | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -FRSUPP-FSMAN | DZ175 Fire Suppression Manual | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -FRSUPP-FSAUT-FFOAM | DZ175 Fire Suppression Foam | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -FRSUPP-FSAUT | DZ175 Fire Suppression Automatic | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -FRSUPP-FSALM | DZ175 Fire System Alarm | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -FRSUPP | DZ175 Fire Suppression System | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -FDRSYS-TRKRH | DZ175 Track Assembly R/H | 71802 | 3049 | 5000
CCK-MP-DOZR-DZ175 -FDRSYS-TRKLH | DZ175 Track Assembly L/H | 71802 | 3049 | 5000
CCK-MP-DOZR-DZ175 -FDRSYS-SEGRH | DZ175 Segments R/H | 71802 | 28185 | 5000
CCK-MP-DOZR-DZ175 -FDRSYS-SEGLH | DZ175 Segments L/H | 71802 | 28185 | 5000
CCK-MP-DOZR-DZ175 -FDRSYS-FDRRH | DZ175 Final Drive R/H | 71802 | 5706 | 5000
CCK-MP-DOZR-DZ175 -FDRSYS-FDRLH | DZ175 Final Drive L/H | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -FDRSYS | DZ175 Final Drive System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-LUBSY-PREPP | DZ175 Oil Pump Pre-Lube Engine | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-LUBSY-OILPP | DZ175 Oil Pump Engine | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-LUBSY-ENOLC | DZ175 Oil Cooler Engine | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-LUBSY | DZ175 Engine Lubrication System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-INTEX-TBORH | DZ175 Turbocharger R/H | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-INTEX-TBOLH | DZ175 Turbocharger L/H | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-INTEX-EXHST | DZ175 Exhaust System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-INTEX-AIRFL | DZ175 Air Filtration System | 71802 | 18875 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-INTEX-AFTER | DZ175 Aftercooler | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-INTEX | DZ175 Intake and Exhaust System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-FUSYS-FULTP | DZ175 Fuel Transfer Pump | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-FUSYS-FULTK | DZ175 Fuel Tank | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-FUSYS-FUINJ | DZ175 Fuel Injectors | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-FUSYS-FUHLF | DZ175 Fuel System Hoses, Lines and Fitt | 71802 | 34215 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-FUSYS | DZ175 Fuel System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-COSYS-WTRPP | DZ175 Water Pump Engine | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-COSYS-THERM | DZ175 Thermostats/Regulators | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-COSYS-RADTR | DZ175 Radiator Engine | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-COSYS-CSHLF | DZ175 Cooling System Hoses, Lines and F | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-COSYS-COFAN | DZ175 Fan Cooling System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE-COSYS | DZ175 Engine Cooling System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ENGINE | DZ175 Engine Assembly, Caterpillar C27 | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-START-STRMR | DZ175 Starter Motor | 71802 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-START | DZ175 Electrical Starting System | 71802 | 71802 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-LIGHT | DZ175 Lighting Low Voltage | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-HARNS | DZ175 Electrical Harness | 71827 | 34240 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-CONTL | DZ175 Electrical Controls Low Voltage | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-CHARG-BATTY | DZ175 Batteries | 71827 | 6554 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-CHARG-ALTER | DZ175 Alternator 24V | 71827 | 4957 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV-CHARG | DZ175 Charging System | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -ELCTLV | DZ175 Electrical System Low Voltage 24V | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -COMMUN-RADIO | DZ175 Two Way Radio | 71827 | 4957 | 5000
CCK-MP-DOZR-DZ175 -COMMUN-FLMGT | DZ175 Fleet Management | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -COMMUN | DZ175 Communications | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -BRKSTR-STVLV | DZ175 Valve Hydraulic Steering | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -BRKSTR-STHLF | DZ175 Steering System Hoses Lines and F | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -BRKSTR-STCON | DZ175 Controls Steering | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -BRKSTR-SCABR | DZ175 Steering Clutch and Brake Assembl | 71827 | 4957 | 5000
CCK-MP-DOZR-DZ175 -BRKSTR-SCABL | DZ175 Steering Clutch and Brake Assembl | 71827 | 4957 | 5000
CCK-MP-DOZR-DZ175 -BRKSTR-HYSPP | DZ175 Pump Hydraulic Steering | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 -BRKSTR | DZ175 Brake and Steering System | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 | DZ175 Mechanical & Lube Services | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ175 | Caterpillar D10T Dozer, DZ175 | 71827 | 71827 | 5000
CCK-MP-DOZR-DZ174 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 65454 | 9964 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-PIVOT | DZ174 Pivot Shaft | 65414 | 33976 | 5000
CCK-MP-DOZR-DZ174 -TRNSYS-TRQUE | DZ174 Torque Converter | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -TRNSYS-TRPMP | DZ174 Pump Trans & Torque Converter Cha | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -TRNSYS-TROLC | DZ174 Oil Cooler Transmission | 65414 | 43944 | 5000
CCK-MP-DOZR-DZ174 -TRNSYS-TRANS-BEVEL | DZ174 Bevel Gear | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -TRNSYS-TRANS | DZ174 Transmission | 65414 | 10038 | 5000
CCK-MP-DOZR-DZ174 -TRNSYS | DZ174 Transmission System | 65414 | 20488 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-TKFRR | DZ174 Track Frame R/H | 65414 | 8319 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-TKFRL | DZ174 Track Frame L/H | 65414 | 8319 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-LDSFR | DZ174 Rollers Load Single Flange Right | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-LDSFL | DZ174 Rollers Load Single Flange Left H | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-LDDFR | DZ174 Rollers Load Double Flange Right | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-LDDFL | DZ174 Rollers Load Double Flange Left H | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-IDRHR | DZ174 Idler Track R/H Rear | 65414 | 21295 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-IDRHF | DZ174 Idler Track R/H Front | 65414 | 53945 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-IDLHR | DZ174 Idler Track L/H Rear | 65414 | 21295 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-IDLHF | DZ174 Idler Track L/H Front | 65414 | 53945 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-ADJRH | DZ174 Track Adjuster R/H | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER-ADJLH | DZ174 Track Adjuster L/H | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-UNDER | DZ174 Undercarriage | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-STLAD-SLFXD | DZ174 Fixed Steps and Ladders | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-STLAD | DZ174 Steps and Ladders | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-RIPPR-RIGET | DZ174 Ripper Wear Elements (GET) | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-RIPPR | DZ174 Ripper | 65414 | 33976 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-PNLGU | DZ174 Panels and Guards | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-PLHAN | DZ174 Platforms and Handrails | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CHASS-TRNON | DZ174 Trunnions | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CHASS-ROPSS | DZ174 Roll Over Protective Structure | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CHASS-PUARM | DZ174 Push Arms | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CHASS-LNKGE | DZ174 Link Stabiliser | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CHASS-EQUAL | DZ174 Equaliser Bar | 65414 | 4916 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CHASS | DZ174 Chassis | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN-SEATS | DZ174 Operators Seat | 65414 | 534 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN-SBELT | DZ174 Seat Belt | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN-GLASS | DZ174 Glass | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN-CABPR | DZ174 Cabin Pressurisation System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN-CABES | DZ174 Cabin Entertainment System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN-CABCO | DZ174 Cabin Controls | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN-AIRCN | DZ174 Air Conditioning System | 65414 | 20488 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-CABIN | DZ174 Operators Cabin | 65414 | 33976 | 5000
CCK-MP-DOZR-DZ174 -STRUCT-BLADE | DZ174 Blade | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -STRUCT | DZ174 Structure | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -MANGMT-UMMMC | DZ174 Mine Monitoring and Control | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -MANGMT-UMENG | DZ174 Engine Management System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -MANGMT | DZ174 Unit Management | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HYDPP-HYIPP | DZ174 Pump Hydraulic Implement | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HYDPP-HYFPP | DZ174 Pump Hydraulic Fan | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HYDPP | DZ174 Pumps Hydraulic | 65414 | 54040 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDTNK | DZ174 Tank Hydraulic | 65414 | 47680 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDOCO | DZ174 Oil Cooler Hydraulic | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDHLF | DZ174 Hydraulic System Hoses Lines Fitt | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-RTCYR | DZ174 Cylinder Ripper Tilt RH | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-RTCYL | DZ174 Cylinder Ripper Tilt LH | 65414 | 20488 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-RPUCY | DZ174 Cylinder Ripper Pin Puller | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-RLCYR | DZ174 Cylinder Ripper Lift RH | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-RLCYL | DZ174 Cylinder Ripper Lift LH | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-BTCYR | DZ174 Cylinder Blade Tilt RH | 65414 | 4928 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-BTCYL | DZ174 Cylinder Blade Tilt LH | 65414 | 15860 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-BLCYR | DZ174 Cylinder Blade Lift RH | 65414 | 538 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL-BLCYL | DZ174 Cylinder Blade Lift LH | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCYL | DZ174 Cylinders Hydraulic | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCVL | DZ174 Implement Valves Hydraulic | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCON | DZ174 Implement Control Hydraulic | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS-HDCFM | DZ174 Fan Cooling Motor Hydraulic | 65414 | 1172 | 5000
CCK-MP-DOZR-DZ174 -HYDSYS | DZ174 Hydraulic System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -GRSYST-GRTNK | DZ174 Auto Lube Resevoir | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -GRSYST-GRINJ | DZ174 Auto Lube Injectors | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -GRSYST-ALHLF | DZ174 Auto Lube Hoses Lines Fittings | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -GRSYST-ALELC | DZ174 Auto Lube Electrical | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -GRSYST-ALCON | DZ174 Auto Lube Controller | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -GRSYST-ALBPP | DZ174 Auto Lube Pump | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -GRSYST | DZ174 Grease Lubrication System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FRSUPP-FSMAN-EXTIN | DZ174 Hand Held Fire Extinguisher | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FRSUPP-FSMAN | DZ174 Fire Suppression Manual | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FRSUPP-FSAUT-FFOAM | DZ174 Fire Suppression Foam | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FRSUPP-FSAUT | DZ174 Fire Suppression Automatic | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FRSUPP-FSALM | DZ174 Fire System Alarm | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FRSUPP | DZ174 Fire Suppression System | 65414 | 33659 | 5000
CCK-MP-DOZR-DZ174 -FDRSYS-TRKRH | DZ174 Track Assembly R/H | 65414 | 531 | 5000
CCK-MP-DOZR-DZ174 -FDRSYS-TRKLH | DZ174 Track Assembly L/H | 65414 | 531 | 5000
CCK-MP-DOZR-DZ174 -FDRSYS-SEGRH | DZ174 Segments R/H | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FDRSYS-SEGLH | DZ174 Segments L/H | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -FDRSYS-FDRRH | DZ174 Final Drive R/H | 65414 | 8319 | 5000
CCK-MP-DOZR-DZ174 -FDRSYS-FDRLH | DZ174 Final Drive L/H | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -FDRSYS | DZ174 Final Drive System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-LUBSY-PREPP | DZ174 Oil Pump Pre-Lube Engine | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-LUBSY-OILPP | DZ174 Oil Pump Engine | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-LUBSY-ENOLC | DZ174 Oil Cooler Engine | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-LUBSY | DZ174 Engine Lubrication System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-INTEX-TBORH | DZ174 Turbocharger R/H | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-INTEX-TBOLH | DZ174 Turbocharger L/H | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-INTEX-EXHST | DZ174 Exhaust System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-INTEX-AIRFL | DZ174 Air Filtration System | 65414 | 20488 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-INTEX-AFTER | DZ174 Aftercooler | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-INTEX | DZ174 Intake and Exhaust System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-FUSYS-FULTP | DZ174 Fuel Transfer Pump | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-FUSYS-FULTK | DZ174 Fuel Tank | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-FUSYS-FUINJ | DZ174 Fuel Injectors | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-FUSYS-FUHLF | DZ174 Fuel System Hoses, Lines and Fitt | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-FUSYS | DZ174 Fuel System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-COSYS-WTRPP | DZ174 Water Pump Engine | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-COSYS-THERM | DZ174 Thermostats/Regulators | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-COSYS-RADTR | DZ174 Radiator Engine | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-COSYS-CSHLF | DZ174 Cooling System Hoses, Lines and F | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-COSYS-COFAN | DZ174 Fan Cooling System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE-COSYS | DZ174 Engine Cooling System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ENGINE | DZ174 Engine Assembly, Caterpillar C27 | 65414 | 12899 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-START-STRMR | DZ174 Starter Motor | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-START | DZ174 Electrical Starting System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-LIGHT | DZ174 Lighting Low Voltage | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-HARNS | DZ174 Electrical Harness | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-CONTL | DZ174 Electrical Controls Low Voltage | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-CHARG-BATTY | DZ174 Batteries | 65414 | 7316 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-CHARG-ALTER | DZ174 Alternator 24V | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV-CHARG | DZ174 Charging System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -ELCTLV | DZ174 Electrical System Low Voltage 24V | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -COMMUN-RADIO | DZ174 Two Way Radio | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -COMMUN-FLMGT | DZ174 Fleet Management | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -COMMUN | DZ174 Communications | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -BRKSTR-STVLV | DZ174 Valve Hydraulic Steering | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -BRKSTR-STHLF | DZ174 Steering System Hoses Lines and F | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -BRKSTR-STCON | DZ174 Controls Steering | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -BRKSTR-SCABR | DZ174 Steering Clutch and Brake Assembl | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -BRKSTR-SCABL | DZ174 Steering Clutch and Brake Assembl | 65414 | 7187 | 5000
CCK-MP-DOZR-DZ174 -BRKSTR-HYSPP | DZ174 Pump Hydraulic Steering | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 -BRKSTR | DZ174 Brake and Steering System | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 | DZ174 Mechanical & Lube Services | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ174 | Caterpillar D10T Dozer, DZ174 | 65414 | 65414 | 5000
CCK-MP-DOZR-DZ173 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 68788 | 9989 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-PIVOT | DZ173 Pivot Shaft | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -TRNSYS-TRQUE | Torque Converter | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -TRNSYS-TROLC | Oil Cooler Transmission | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -TRNSYS-TRANS-BEVEL | Bevel Gear | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -TRNSYS-TRANS | Transmission | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -TRNSYS | Transmission System | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-TKFRR | Track Frame R/H | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-TKFRL | Track Frame L/H | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 68788 | 14934 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 68788 | 13165 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 68788 | 56889 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 68788 | 13165 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-UNDER | Undercarriage | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-STLAD-SLFXD | Fixed Steps and Ladders | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-STLAD | Steps and Ladders | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-RIPPR | Ripper | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-PNLGU | Panels and Guards | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-PLHAN | Platforms and Handrails | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CHASS-TRNON | Trunnions | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CHASS-PUARM | Push Arms | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CHASS-LNKGE | Link Stabiliser | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CHASS-EQUAL | Equaliser Bar | 68788 | 17174 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CHASS | Chassis | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN-SEATS | Operators Seat | 68788 | 11495 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN-SBELT | Seat Belt | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN-GLASS | Glass | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN-CABES | Cabin Entertainment System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN-CABCO | Cabin Controls | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN-AIRCN | Air Conditioning System | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-CABIN | Operators Cabin | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -STRUCT-BLADE | Blade | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -STRUCT | Structure | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -MANGMT-UMMMC | Mine Monitoring and Control | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -MANGMT-UMENG | Engine Management System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -MANGMT | Unit Management | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 68788 | 1691 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 68788 | 14973 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HYDPP | Pumps Hydraulic | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDTNK | Tank Hydraulic | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 68788 | 25219 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-RTCYR | DZ173 Cylinder Ripper Tilt RH | 68788 | 6232 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-RTCYL | DZ173 Cylinder Ripper Tilt LH | 68788 | 14477 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-RLCYR | DZ173 Cylinder Ripper Lift RH | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-RLCYL | DZ173 Cylinder Ripper Lift LH | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-BTCYR | DZ173 Cylinder Blade Tilt RH | 68788 | 6210 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-BTCYL | DZ173 Cylinder Blade Tilt LH | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-BLCYR | DZ173 Cylinder Blade Lift RH | 68711 | 433 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL-BLCYL | DZ173 Cylinder Blade Lift LH | 68788 | 3254 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCYL | Cylinders Hydraulic | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCVL | Implement Valves Hydraulic | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCON | Implement Control Hydraulic | 68788 | 25219 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 68788 | 994 | 5000
CCK-MP-DOZR-DZ173 -HYDSYS | Hydraulic System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -GRSYST-GRTNK | Auto Lube Resevoir | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -GRSYST-GRINJ | Auto Lube Injectors | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -GRSYST-ALHLF | Auto Lube Hoses Lines Fittings | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -GRSYST-ALELC | Auto Lube Electrical | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -GRSYST-ALCON | Auto Lube Controller | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -GRSYST-ALBPP | Auto Lube Pump | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -GRSYST | Grease Lubrication System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -FRSUPP-FSMAN | Fire Suppression Manual | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -FRSUPP-FSAUT | Fire Suppression Automatic | 35769 | 35769 | 5000
CCK-MP-DOZR-DZ173 -FRSUPP-FSALM | Fire System Alarm | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -FRSUPP | Fire Suppression System | 68788 | 26271 | 5000
CCK-MP-DOZR-DZ173 -FDRSYS-TRKRH | Track Assembly R/H | 68788 | 2884 | 5000
CCK-MP-DOZR-DZ173 -FDRSYS-TRKLH | Track Assembly L/H | 68788 | 2884 | 5000
CCK-MP-DOZR-DZ173 -FDRSYS-SEGRH | Segments R/H | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -FDRSYS-SEGLH | Segments L/H | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -FDRSYS-FDRRH | Final Drive R/H | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -FDRSYS-FDRLH | Final Drive L/H | 68788 | 7762 | 5000
CCK-MP-DOZR-DZ173 -FDRSYS | Final Drive System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-INTEX-TBORH | Turbocharger R/H | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-INTEX-EXHST | Exhaust System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-INTEX-AIRFL | Air Filtration System | 68788 | 25219 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-INTEX-AFTER | Aftercooler | 68788 | 16178 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-FUSYS-FULTK | Fuel Tank | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-FUSYS-FUHLF | "Fuel System Hoses, Lines and Fittings" | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-FUSYS | Fuel System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-COSYS-WTRPP | Water Pump Engine | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-COSYS-THERM | Thermostats/Regulators | 59012 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-COSYS-RADTR | Radiator Engine | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-COSYS-CSHLF | "Cooling System Hoses, Lines and Fitting | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-COSYS-COFAN | Fan Cooling System | 68788 | 25219 | 5000
CCK-MP-DOZR-DZ173 -ENGINE-COSYS | Engine Cooling System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ENGINE | DZ173 Engine Assembly, Caterpillar C27 | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-START-STRMR | Starter Motor | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-START | Electrical Starting System | 35769 | 35769 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-LIGHT | Lighting Low Voltage | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-HARNS | Electrical Harness | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-CONTL | Electrical Controls Low Voltage | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-CHARG-BATTY | Batteries | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-CHARG-ALTER | Alternator 24V | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV-CHARG | Charging System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -ELCTLV | Electrical System Low Voltage 24V | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -COMMUN-RADIO | Two Way Radio | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -COMMUN-FLMGT | Fleet Management | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -COMMUN | Communications | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -BRKSTR-STVLV | Valve Hydraulic Steering | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -BRKSTR-STHLF | Steering System Hoses Lines and Fittings | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -BRKSTR-STCON | Controls Steering | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 68788 | 11848 | 5000
CCK-MP-DOZR-DZ173 -BRKSTR-HYSPP | Pump Hydraulic Steering | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 -BRKSTR | Brake and Steering System | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 | Radiator Engine | 68788 | 68788 | 5900
CCK-MP-DOZR-DZ173 | DZ173 Mechanical & Lube Services | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ173 | Caterpillar D10T Dozer, DZ173 | 68788 | 68788 | 5000
CCK-MP-DOZR-DZ172 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 68272 | 8326 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-PIVOT | DZ172 Pivot Shaft | 68264 | 11071 | 5000
CCK-MP-DOZR-DZ172 -TRNSYS-TRQUE | DZ172 Torque Converter | 68264 | 7030 | 5000
CCK-MP-DOZR-DZ172 -TRNSYS-TRPMP | DZ172 Pump Trans & Torque Converter Cha | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -TRNSYS-TROLC | DZ172 Oil Cooler Transmission | 68264 | 32042 | 5000
CCK-MP-DOZR-DZ172 -TRNSYS-TRANS-BEVEL | DZ172 Bevel Gear | 68264 | 55418 | 5000
CCK-MP-DOZR-DZ172 -TRNSYS-TRANS | DZ172 Transmission | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -TRNSYS | DZ172 Transmission System | 68264 | 16489 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-TKFRR | DZ172 Track Frame R/H | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-TKFRL | DZ172 Track Frame L/H | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-LDSFR | DZ172 Rollers Load Single Flange Right | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-LDSFL | DZ172 Rollers Load Single Flange Left H | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-LDDFR | DZ172 Rollers Load Double Flange Right | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-LDDFL | DZ172 Rollers Load Double Flange Left H | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-IDRHR | DZ172 Idler Track R/H Rear | 68264 | 23769 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-IDRHF | DZ172 Idler Track R/H Front | 68264 | 23769 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-IDLHR | DZ172 Idler Track L/H Rear | 68264 | 23769 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-IDLHF | DZ172 Idler Track L/H Front | 68264 | 23769 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-ADJRH | DZ172 Track Adjuster R/H | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER-ADJLH | DZ172 Track Adjuster L/H | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-UNDER | DZ172 Undercarriage | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-STLAD-SLFXD | DZ172 Fixed Steps and Ladders | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-STLAD | DZ172 Steps and Ladders | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-RIPPR-RIGET | DZ172 Ripper Wear Elements (GET) | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-RIPPR | DZ172 Ripper | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-PNLGU | DZ172 Panels and Guards | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-PLHAN | DZ172 Platforms and Handrails | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CHASS-TRNON | DZ172 Trunnions | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CHASS-ROPSS | DZ172 Roll Over Protective Structure | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CHASS-PUARM | DZ172 Push Arms | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CHASS-LNKGE | DZ172 Link Stabiliser | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CHASS-EQUAL | DZ172 Equaliser Bar | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CHASS | DZ172 Chassis | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN-SEATS | DZ172 Operators Seat | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN-SBELT | DZ172 Seat Belt | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN-GLASS | DZ172 Glass | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN-CABPR | DZ172 Cabin Pressurisation System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN-CABES | DZ172 Cabin Entertainment System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN-CABCO | DZ172 Cabin Controls | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN-AIRCN | DZ172 Air Conditioning System | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-CABIN | DZ172 Operators Cabin | 68264 | 16489 | 5000
CCK-MP-DOZR-DZ172 -STRUCT-BLADE | DZ172 Blade | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -STRUCT | DZ172 Structure | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -MANGMT-UMMMC | DZ172 Mine Monitoring and Control | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -MANGMT-UMENG | DZ172 Engine Management System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -MANGMT | DZ172 Unit Management | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HYDPP-HYIPP | DZ172 Pump Hydraulic Implement | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HYDPP-HYFPP | DZ172 Pump Hydraulic Fan | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HYDPP | DZ172 Pumps Hydraulic | 68264 | 55418 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDTNK | DZ172 Tank Hydraulic | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDOCO | DZ172 Oil Cooler Hydraulic | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDHLF | DZ172 Hydraulic System Hoses Lines Fitt | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-RTCYR | DZ172 Cylinder Ripper Tilt RH | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-RTCYL | DZ172 Cylinder Ripper Tilt LH | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-RPUCY | DZ172 Cylinder Ripper Pin Puller | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-RLCYR | DZ172 Cylinder Ripper Lift RH | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-RLCYL | DZ172 Cylinder Ripper Lift LH | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BTCYR | DZ172 Cylinder Blade Tilt RH | 68264 | 9054 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BTCYL | DZ172 Cylinder Blade Tilt LH | 68264 | 7647 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BLCYR | DZ172 Cylinder Blade Lift RH | 68264 | 9054 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL-BLCYL | DZ172 Cylinder Blade Lift LH | 68264 | 9056 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCYL | DZ172 Cylinders Hydraulic | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCVL | DZ172 Implement Valves Hydraulic | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCON | DZ172 Implement Control Hydraulic | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS-HDCFM | DZ172 Fan Cooling Motor Hydraulic | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -HYDSYS | DZ172 Hydraulic System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -GRSYST-GRTNK | DZ172 Auto Lube Resevoir | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -GRSYST-GRINJ | DZ172 Auto Lube Injectors | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -GRSYST-ALHLF | DZ172 Auto Lube Hoses Lines Fittings | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -GRSYST-ALELC | DZ172 Auto Lube Electrical | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -GRSYST-ALCON | DZ172 Auto Lube Controller | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -GRSYST-ALBPP | DZ172 Auto Lube Pump | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -GRSYST | DZ172 Grease Lubrication System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FRSUPP-FSMAN-EXTIN | DZ172 Hand Held Fire Extinguisher | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FRSUPP-FSMAN | DZ172 Fire Suppression Manual | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FRSUPP-FSAUT-FFOAM | DZ172 Fire Suppression Foam | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FRSUPP-FSAUT | DZ172 Fire Suppression Automatic | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FRSUPP-FSALM | DZ172 Fire System Alarm | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FRSUPP | DZ172 Fire Suppression System | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -FDRSYS-TRKRH | DZ172 Track Assembly R/H | 68264 | 261 | 5000
CCK-MP-DOZR-DZ172 -FDRSYS-TRKLH | DZ172 Track Assembly L/H | 68264 | 261 | 5000
CCK-MP-DOZR-DZ172 -FDRSYS-SEGRH | DZ172 Segments R/H | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FDRSYS-SEGLH | DZ172 Segments L/H | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -FDRSYS-FDRRH | DZ172 Final Drive R/H | 68264 | 4271 | 5000
CCK-MP-DOZR-DZ172 -FDRSYS-FDRLH | DZ172 Final Drive L/H | 68245 | 6824 | 5000
CCK-MP-DOZR-DZ172 -FDRSYS | DZ172 Final Drive System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-LUBSY-PREPP | DZ172 Oil Pump Pre-Lube Engine | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-LUBSY-OILPP | DZ172 Oil Pump Engine | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-LUBSY-ENOLC | DZ172 Oil Cooler Engine | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-LUBSY | DZ172 Engine Lubrication System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-INTEX-TBORH | DZ172 Turbocharger R/H | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-INTEX-TBOLH | DZ172 Turbocharger L/H | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-INTEX-EXHST | DZ172 Exhaust System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-INTEX-AIRFL | DZ172 Air Filtration System | 68264 | 12811 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-INTEX-AFTER | DZ172 Aftercooler | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-INTEX | DZ172 Intake and Exhaust System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-FUSYS-FULTP | DZ172 Fuel Transfer Pump | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-FUSYS-FULTK | DZ172 Fuel Tank | 68264 | 29872 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-FUSYS-FUINJ | DZ172 Fuel Injectors | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-FUSYS-FUHLF | DZ172 Fuel System Hoses, Lines and Fitt | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-FUSYS | DZ172 Fuel System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-COSYS-WTRPP | DZ172 Water Pump Engine | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-COSYS-THERM | DZ172 Thermostats/Regulators | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-COSYS-RADTR | DZ172 Radiator Engine | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-COSYS-CSHLF | DZ172 Cooling System Hoses, Lines and F | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-COSYS-COFAN | DZ172 Fan Cooling System | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ENGINE-COSYS | DZ172 Engine Cooling System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ENGINE | DZ172 Engine Assembly, Caterpillar C27 | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-START-STRMR | DZ172 Starter Motor | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-START | DZ172 Electrical Starting System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-LIGHT | DZ172 Lighting Low Voltage | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-HARNS | DZ172 Electrical Harness | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-CONTL | DZ172 Electrical Controls Low Voltage | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-CHARG-BATTY | DZ172 Batteries | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-CHARG-ALTER | DZ172 Alternator 24V | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV-CHARG | DZ172 Charging System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -ELCTLV | DZ172 Electrical System Low Voltage 24V | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -COMMUN-RADIO | DZ172 Two Way Radio | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -COMMUN-FLMGT | DZ172 Fleet Management | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -COMMUN | DZ172 Communications | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -BRKSTR-STVLV | DZ172 Valve Hydraulic Steering | 68264 | 29872 | 5000
CCK-MP-DOZR-DZ172 -BRKSTR-STHLF | DZ172 Steering System Hoses Lines and F | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -BRKSTR-STCON | DZ172 Controls Steering | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -BRKSTR-SCABR | DZ172 Steering Clutch and Brake Assembl | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -BRKSTR-SCABL | DZ172 Steering Clutch and Brake Assembl | 68264 | 6824 | 5000
CCK-MP-DOZR-DZ172 -BRKSTR-HYSPP | DZ172 Pump Hydraulic Steering | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 -BRKSTR | DZ172 Brake and Steering System | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 | DZ172 Mechanical & Lube Services | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ172 | Caterpillar D10T Dozer, DZ172 | 68264 | 68264 | 5000
CCK-MP-DOZR-DZ171 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 67979 | 9119 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-PIVOT | DZ171 Pivot Shaft | 67979 | 18630 | 5000
CCK-MP-DOZR-DZ171 -TRNSYS-TRQUE | DZ171 Torque Converter | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -TRNSYS-TRPMP | DZ171 Pump Trans & Torque Converter Cha | 67979 | 18654 | 5000
CCK-MP-DOZR-DZ171 -TRNSYS-TROLC | DZ171 Oil Cooler Transmission | 67979 | 41877 | 5000
CCK-MP-DOZR-DZ171 -TRNSYS-TRANS-BEVEL | DZ171 Bevel Gear | 67979 | 54204 | 5000
CCK-MP-DOZR-DZ171 -TRNSYS-TRANS | DZ171 Transmission | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -TRNSYS | DZ171 Transmission System | 67979 | 8290 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-TKFRR | DZ171 Track Frame R/H | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-TKFRL | DZ171 Track Frame L/H | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-LDSFR | DZ171 Rollers Load Single Flange Right | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-LDSFL | DZ171 Rollers Load Single Flange Left H | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-LDDFR | DZ171 Rollers Load Double Flange Right | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-LDDFL | DZ171 Rollers Load Double Flange Left H | 67979 | 34550 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-IDRHR | DZ171 Idler Track R/H Rear | 67979 | 15898 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-IDRHF | DZ171 Idler Track R/H Front | 67979 | 55427 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-IDLHR | DZ171 Idler Track L/H Rear | 67979 | 27485 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-IDLHF | DZ171 Idler Track L/H Front | 67979 | 41032 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-ADJRH | DZ171 Track Adjuster R/H | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER-ADJLH | DZ171 Track Adjuster L/H | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-UNDER | DZ171 Undercarriage | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-STLAD-SLFXD | DZ171 Fixed Steps and Ladders | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-STLAD | DZ171 Steps and Ladders | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-RIPPR-RIGET | DZ171 Ripper Wear Elements (GET) | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-RIPPR | DZ171 Ripper | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-PNLGU | DZ171 Panels and Guards | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-PLHAN | DZ171 Platforms and Handrails | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CHASS-TRNON | DZ171 Trunnions | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CHASS-ROPSS | DZ171 Roll Over Protective Structure | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CHASS-PUARM | DZ171 Push Arms | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CHASS-LNKGE | DZ171 Link Stabiliser | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CHASS-EQUAL | DZ171 Equaliser Bar | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CHASS | DZ171 Chassis | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN-SEATS | DZ171 Operators Seat | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN-SBELT | DZ171 Seat Belt | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN-GLASS | DZ171 Glass | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN-CABPR | DZ171 Cabin Pressurisation System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN-CABES | DZ171 Cabin Entertainment System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN-CABCO | DZ171 Cabin Controls | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN-AIRCN | DZ171 Air Conditioning System | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-CABIN | DZ171 Operators Cabin | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -STRUCT-BLADE | DZ171 Blade | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -STRUCT | DZ171 Structure | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -MANGMT-UMMMC | DZ171 Mine Monitoring and Control | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -MANGMT-UMENG | DZ171 Engine Management System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -MANGMT | DZ171 Unit Management | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HYDPP-HYIPP | DZ171 Pump Hydraulic Implement | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HYDPP-HYFPP | DZ171 Pump Hydraulic Fan | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HYDPP | DZ171 Pumps Hydraulic | 67979 | 55427 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDTNK | DZ171 Tank Hydraulic | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDOCO | DZ171 Oil Cooler Hydraulic | 67979 | 18654 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDHLF | DZ171 Hydraulic System Hoses Lines Fitt | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-RTCYR | DZ171 Cylinder Ripper Tilt RH | 67979 | 18630 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-RTCYL | DZ171 Cylinder Ripper Tilt LH | 67979 | 850 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-RPUCY | DZ171 Cylinder Ripper Pin Puller | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-RLCYR | DZ171 Cylinder Ripper Lift RH | 67979 | 18630 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-RLCYL | DZ171 Cylinder Ripper Lift LH | 67979 | 10671 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-BTCYR | DZ171 Cylinder Blade Tilt RH | 67979 | 850 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-BTCYL | DZ171 Cylinder Blade Tilt LH | 67979 | 10671 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-BLCYR | DZ171 Cylinder Blade Lift RH | 67979 | 3604 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL-BLCYL | DZ171 Cylinder Blade Lift LH | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCYL | DZ171 Cylinders Hydraulic | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCVL | DZ171 Implement Valves Hydraulic | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCON | DZ171 Implement Control Hydraulic | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS-HDCFM | DZ171 Fan Cooling Motor Hydraulic | 67979 | 850 | 5000
CCK-MP-DOZR-DZ171 -HYDSYS | DZ171 Hydraulic System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -GRSYST-GRTNK | DZ171 Auto Lube Resevoir | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -GRSYST-GRINJ | DZ171 Auto Lube Injectors | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -GRSYST-ALHLF | DZ171 Auto Lube Hoses Lines Fittings | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -GRSYST-ALELC | DZ171 Auto Lube Electrical | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -GRSYST-ALCON | DZ171 Auto Lube Controller | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -GRSYST-ALBPP | DZ171 Auto Lube Pump | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -GRSYST | DZ171 Grease Lubrication System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -FRSUPP-FSMAN-EXTIN | DZ171 Hand Held Fire Extinguisher | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -FRSUPP-FSMAN | DZ171 Fire Suppression Manual | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -FRSUPP-FSAUT-FFOAM | DZ171 Fire Suppression Foam | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -FRSUPP-FSAUT | DZ171 Fire Suppression Automatic | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -FRSUPP-FSALM | DZ171 Fire System Alarm | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -FRSUPP | DZ171 Fire Suppression System | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -FDRSYS-TRKRH | DZ171 Track Assembly R/H | 67979 | 1996 | 5000
CCK-MP-DOZR-DZ171 -FDRSYS-TRKLH | DZ171 Track Assembly L/H | 67979 | 15898 | 5000
CCK-MP-DOZR-DZ171 -FDRSYS-SEGRH | DZ171 Segments R/H | 67979 | 47798 | 5000
CCK-MP-DOZR-DZ171 -FDRSYS-SEGLH | DZ171 Segments L/H | 67979 | 47798 | 5000
CCK-MP-DOZR-DZ171 -FDRSYS-FDRRH | DZ171 Final Drive R/H | 67979 | 18654 | 5000
CCK-MP-DOZR-DZ171 -FDRSYS-FDRLH | DZ171 Final Drive L/H | 67979 | 18654 | 5000
CCK-MP-DOZR-DZ171 -FDRSYS | DZ171 Final Drive System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-LUBSY-PREPP | DZ171 Oil Pump Pre-Lube Engine | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-LUBSY-OILPP | DZ171 Oil Pump Engine | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-LUBSY-ENOLC | DZ171 Oil Cooler Engine | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-LUBSY | DZ171 Engine Lubrication System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-INTEX-TBORH | DZ171 Turbocharger R/H | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-INTEX-TBOLH | DZ171 Turbocharger L/H | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-INTEX-EXHST | DZ171 Exhaust System | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-INTEX-AIRFL | DZ171 Air Filtration System | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-INTEX-AFTER | DZ171 Aftercooler | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-INTEX | DZ171 Intake and Exhaust System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-FUSYS-FULTP | DZ171 Fuel Transfer Pump | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-FUSYS-FULTK | DZ171 Fuel Tank | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-FUSYS-FUINJ | DZ171 Fuel Injectors | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-FUSYS-FUHLF | DZ171 Fuel System Hoses, Lines and Fitt | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-FUSYS | DZ171 Fuel System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-COSYS-WTRPP | DZ171 Water Pump Engine | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-COSYS-THERM | DZ171 Thermostats/Regulators | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-COSYS-RADTR | DZ171 Radiator Engine | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-COSYS-CSHLF | DZ171 Cooling System Hoses, Lines and F | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-COSYS-COFAN | DZ171 Fan Cooling System | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -ENGINE-COSYS | DZ171 Engine Cooling System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ENGINE | DZ171 Engine Assembly, Caterpillar C27 | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-START-STRMR | DZ171 Starter Motor | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-START | DZ171 Electrical Starting System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-LIGHT | DZ171 Lighting Low Voltage | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-HARNS | DZ171 Electrical Harness | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-CONTL | DZ171 Electrical Controls Low Voltage | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-CHARG-BATTY | DZ171 Batteries | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-CHARG-ALTER | DZ171 Alternator 24V | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV-CHARG | DZ171 Charging System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -ELCTLV | DZ171 Electrical System Low Voltage 24V | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -COMMUN-RADIO | DZ171 Two Way Radio | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -COMMUN-FLMGT | DZ171 Fleet Management | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -COMMUN | DZ171 Communications | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -BRKSTR-STVLV | DZ171 Valve Hydraulic Steering | 67979 | 25809 | 5000
CCK-MP-DOZR-DZ171 -BRKSTR-STHLF | DZ171 Steering System Hoses Lines and F | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -BRKSTR-STCON | DZ171 Controls Steering | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -BRKSTR-SCABR | DZ171 Steering Clutch and Brake Assembl | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -BRKSTR-SCABL | DZ171 Steering Clutch and Brake Assembl | 67979 | 11227 | 5000
CCK-MP-DOZR-DZ171 -BRKSTR-HYSPP | DZ171 Pump Hydraulic Steering | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 -BRKSTR | DZ171 Brake and Steering System | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 | DZ171 Mechanical & Lube Services | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ171 | Caterpillar D10T Dozer, DZ171 | 67979 | 67979 | 5000
CCK-MP-DOZR-DZ170 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 54284 | 9464 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-PIVOT | DZ170 Pivot Shaft | 54263 | 23313 | 5000
CCK-MP-DOZR-DZ170 -TRNSYS-TRQUE | DZ170 Torque Converter | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -TRNSYS-TRPMP | DZ170 Pump Trans & Torque Converter Cha | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -TRNSYS-TROLC | DZ170 Oil Cooler Transmission | 54263 | 19857 | 5000
CCK-MP-DOZR-DZ170 -TRNSYS-TRANS-BEVEL | DZ170 Bevel Gear | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -TRNSYS-TRANS | DZ170 Transmission | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -TRNSYS | DZ170 Transmission System | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-TKFRR | DZ170 Track Frame R/H | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-TKFRL | DZ170 Track Frame L/H | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-LDSFR | DZ170 Rollers Load Single Flange Right | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-LDSFL | DZ170 Rollers Load Single Flange Left H | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-LDDFR | DZ170 Rollers Load Double Flange Right | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-LDDFL | DZ170 Rollers Load Double Flange Left H | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-IDRHR | DZ170 Idler Track R/H Rear | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-IDRHF | DZ170 Idler Track R/H Front | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-IDLHR | DZ170 Idler Track L/H Rear | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-IDLHF | DZ170 Idler Track L/H Front | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-ADJRH | DZ170 Track Adjuster R/H | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER-ADJLH | DZ170 Track Adjuster L/H | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-UNDER | DZ170 Undercarriage | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-STLAD-SLFXD | DZ170 Fixed Steps and Ladders | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-STLAD | DZ170 Steps and Ladders | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-RIPPR-RIGET | DZ170 Ripper Wear Elements (GET) | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-RIPPR | DZ170 Ripper | 54263 | 23313 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-PNLGU | DZ170 Panels and Guards | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-PLHAN | DZ170 Platforms and Handrails | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CHASS-TRNON | DZ170 Trunnions | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CHASS-ROPSS | DZ170 Roll Over Protective Structure | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CHASS-PUARM | DZ170 Push Arms | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CHASS-LNKGE | DZ170 Link Stabiliser | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CHASS-EQUAL | DZ170 Equaliser Bar | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CHASS | DZ170 Chassis | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN-SEATS | DZ170 Operators Seat | 54263 | 5339 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN-SBELT | DZ170 Seat Belt | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN-GLASS | DZ170 Glass | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN-CABPR | DZ170 Cabin Pressurisation System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN-CABES | DZ170 Cabin Entertainment System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN-CABCO | DZ170 Cabin Controls | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN-AIRCN | DZ170 Air Conditioning System | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-CABIN | DZ170 Operators Cabin | 54263 | 35925 | 5000
CCK-MP-DOZR-DZ170 -STRUCT-BLADE | DZ170 Blade | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -STRUCT | DZ170 Structure | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -MANGMT-UMMMC | DZ170 Mine Monitoring and Control | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -MANGMT-UMENG | DZ170 Engine Management System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -MANGMT | DZ170 Unit Management | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HYDPP-HYIPP | DZ170 Pump Hydraulic Implement | 54263 | 5339 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HYDPP-HYFPP | DZ170 Pump Hydraulic Fan | 54263 | 7185 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HYDPP | DZ170 Pumps Hydraulic | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDTNK | DZ170 Tank Hydraulic | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDOCO | DZ170 Oil Cooler Hydraulic | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDHLF | DZ170 Hydraulic System Hoses Lines Fitt | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-RTCYR | DZ170 Cylinder Ripper Tilt RH | 54263 | 150 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-RTCYL | DZ170 Cylinder Ripper Tilt LH | 54263 | 4295 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-RPUCY | DZ170 Cylinder Ripper Pin Puller | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-RLCYR | DZ170 Cylinder Ripper Lift RH | 54263 | 150 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-RLCYL | DZ170 Cylinder Ripper Lift LH | 54263 | 150 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BTCYR | DZ170 Cylinder Blade Tilt RH | 54263 | 162 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BTCYL | DZ170 Cylinder Blade Tilt LH | 54263 | 162 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BLCYR | DZ170 Cylinder Blade Lift RH | 54263 | 4295 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL-BLCYL | DZ170 Cylinder Blade Lift LH | 54263 | 6767 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCYL | DZ170 Cylinders Hydraulic | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCVL | DZ170 Implement Valves Hydraulic | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCON | DZ170 Implement Control Hydraulic | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS-HDCFM | DZ170 Fan Cooling Motor Hydraulic | 54263 | 1222 | 5000
CCK-MP-DOZR-DZ170 -HYDSYS | DZ170 Hydraulic System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -GRSYST-GRTNK | DZ170 Auto Lube Resevoir | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -GRSYST-GRINJ | DZ170 Auto Lube Injectors | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -GRSYST-ALHLF | DZ170 Auto Lube Hoses Lines Fittings | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -GRSYST-ALELC | DZ170 Auto Lube Electrical | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -GRSYST-ALCON | DZ170 Auto Lube Controller | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -GRSYST-ALBPP | DZ170 Auto Lube Pump | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -GRSYST | DZ170 Grease Lubrication System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -FRSUPP-FSMAN-EXTIN | DZ170 Hand Held Fire Extinguisher | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -FRSUPP-FSMAN | DZ170 Fire Suppression Manual | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -FRSUPP-FSAUT-FFOAM | DZ170 Fire Suppression Foam | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -FRSUPP-FSAUT | DZ170 Fire Suppression Automatic | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -FRSUPP-FSALM | DZ170 Fire System Alarm | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -FRSUPP | DZ170 Fire Suppression System | 54263 | 35925 | 5000
CCK-MP-DOZR-DZ170 -FDRSYS-TRKRH | DZ170 Track Assembly R/H | 54263 | 3674 | 5000
CCK-MP-DOZR-DZ170 -FDRSYS-TRKLH | DZ170 Track Assembly L/H | 54263 | 3674 | 5000
CCK-MP-DOZR-DZ170 -FDRSYS-SEGRH | DZ170 Segments R/H | 54263 | 24571 | 5000
CCK-MP-DOZR-DZ170 -FDRSYS-SEGLH | DZ170 Segments L/H | 54263 | 24571 | 5000
CCK-MP-DOZR-DZ170 -FDRSYS-FDRRH | DZ170 Final Drive R/H | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -FDRSYS-FDRLH | DZ170 Final Drive L/H | 54263 | 3166 | 5000
CCK-MP-DOZR-DZ170 -FDRSYS | DZ170 Final Drive System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-LUBSY-PREPP | DZ170 Oil Pump Pre-Lube Engine | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-LUBSY-OILPP | DZ170 Oil Pump Engine | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-LUBSY-ENOLC | DZ170 Oil Cooler Engine | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-LUBSY | DZ170 Engine Lubrication System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-INTEX-TBORH | DZ170 Turbocharger R/H | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-INTEX-TBOLH | DZ170 Turbocharger L/H | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-INTEX-EXHST | DZ170 Exhaust System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-INTEX-AIRFL | DZ170 Air Filtration System | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-INTEX-AFTER | DZ170 Aftercooler | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-INTEX | DZ170 Intake and Exhaust System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-FUSYS-FULTP | DZ170 Fuel Transfer Pump | 54263 | 5245 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-FUSYS-FULTK | DZ170 Fuel Tank | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-FUSYS-FUINJ | DZ170 Fuel Injectors | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-FUSYS-FUHLF | DZ170 Fuel System Hoses, Lines and Fitt | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-FUSYS | DZ170 Fuel System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-COSYS-WTRPP | DZ170 Water Pump Engine | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-COSYS-THERM | DZ170 Thermostats/Regulators | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-COSYS-RADTR | DZ170 Radiator Engine | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-COSYS-CSHLF | DZ170 Cooling System Hoses, Lines and F | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-COSYS-COFAN | DZ170 Fan Cooling System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE-COSYS | DZ170 Engine Cooling System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ENGINE | DZ170 Engine Assembly, Caterpillar C27 | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-START-STRMR | DZ170 Starter Motor | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-START | DZ170 Electrical Starting System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-LIGHT | DZ170 Lighting Low Voltage | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-HARNS | DZ170 Electrical Harness | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-CONTL | DZ170 Electrical Controls Low Voltage | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-CHARG-BATTY | DZ170 Batteries | 54263 | 12208 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-CHARG-ALTER | DZ170 Alternator 24V | 54263 | 5287 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV-CHARG | DZ170 Charging System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -ELCTLV | DZ170 Electrical System Low Voltage 24V | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -COMMUN-RADIO | DZ170 Two Way Radio | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -COMMUN-FLMGT | DZ170 Fleet Management | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -COMMUN | DZ170 Communications | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -BRKSTR-STVLV | DZ170 Valve Hydraulic Steering | 54263 | 23313 | 5000
CCK-MP-DOZR-DZ170 -BRKSTR-STHLF | DZ170 Steering System Hoses Lines and F | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -BRKSTR-STCON | DZ170 Controls Steering | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -BRKSTR-SCABR | DZ170 Steering Clutch and Brake Assembl | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -BRKSTR-SCABL | DZ170 Steering Clutch and Brake Assembl | 54263 | 15137 | 5000
CCK-MP-DOZR-DZ170 -BRKSTR-HYSPP | DZ170 Pump Hydraulic Steering | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 -BRKSTR | DZ170 Brake and Steering System | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 | DZ170 Mechanical & Lube Services | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ170 | Caterpillar D10T Dozer, DZ170 | 54263 | 54263 | 5000
CCK-MP-DOZR-DZ169 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 62039 | 8459 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-PIVOT | DZ169 Pivot Shaft | 62015 | 15030 | 5000
CCK-MP-DOZR-DZ169 -TRNSYS-TRQUE | DZ169 Torque Converter | 62015 | 9171 | 5000
CCK-MP-DOZR-DZ169 -TRNSYS-TRPMP | DZ169 Pump Trans & Torque Converter Cha | 62015 | 9171 | 5000
CCK-MP-DOZR-DZ169 -TRNSYS-TROLC | DZ169 Oil Cooler Transmission | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -TRNSYS-TRANS-BEVEL | DZ169 Bevel Gear | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -TRNSYS-TRANS | DZ169 Transmission | 62015 | 836 | 5000
CCK-MP-DOZR-DZ169 -TRNSYS | DZ169 Transmission System | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-TKFRR | DZ169 Track Frame R/H | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-TKFRL | DZ169 Track Frame L/H | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-LDSFR | DZ169 Rollers Load Single Flange Right | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-LDSFL | DZ169 Rollers Load Single Flange Left H | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-LDDFR | DZ169 Rollers Load Double Flange Right | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-LDDFL | DZ169 Rollers Load Double Flange Left H | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-IDRHR | DZ169 Idler Track R/H Rear | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-IDRHF | DZ169 Idler Track R/H Front | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-IDLHR | DZ169 Idler Track L/H Rear | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-IDLHF | DZ169 Idler Track L/H Front | 62015 | 29097 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-ADJRH | DZ169 Track Adjuster R/H | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER-ADJLH | DZ169 Track Adjuster L/H | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-UNDER | DZ169 Undercarriage | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-STLAD-SLFXD | DZ169 Fixed Steps and Ladders | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-STLAD | DZ169 Steps and Ladders | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-RIPPR-RIGET | DZ169 Ripper Wear Elements (GET) | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-RIPPR | DZ169 Ripper | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-PNLGU | DZ169 Panels and Guards | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-PLHAN | DZ169 Platforms and Handrails | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CHASS-TRNON | DZ169 Trunnions | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CHASS-ROPSS | DZ169 Roll Over Protective Structure | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CHASS-PUARM | DZ169 Push Arms | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CHASS-LNKGE | DZ169 Link Stabiliser | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CHASS-EQUAL | DZ169 Equaliser Bar | 62015 | 10301 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CHASS | DZ169 Chassis | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN-SEATS | DZ169 Operators Seat | 62015 | 11979 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN-SBELT | DZ169 Seat Belt | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN-GLASS | DZ169 Glass | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN-CABPR | DZ169 Cabin Pressurisation System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN-CABES | DZ169 Cabin Entertainment System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN-CABCO | DZ169 Cabin Controls | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN-AIRCN | DZ169 Air Conditioning System | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-CABIN | DZ169 Operators Cabin | 62015 | 22000 | 5000
CCK-MP-DOZR-DZ169 -STRUCT-BLADE | DZ169 Blade | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -STRUCT | DZ169 Structure | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -MANGMT-UMMMC | DZ169 Mine Monitoring and Control | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -MANGMT-UMENG | DZ169 Engine Management System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -MANGMT | DZ169 Unit Management | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HYDPP-HYIPP | DZ169 Pump Hydraulic Implement | 62015 | 5429 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HYDPP-HYFPP | DZ169 Pump Hydraulic Fan | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HYDPP | DZ169 Pumps Hydraulic | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDTNK | DZ169 Tank Hydraulic | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDOCO | DZ169 Oil Cooler Hydraulic | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDHLF | DZ169 Hydraulic System Hoses Lines Fitt | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-RTCYR | DZ169 Cylinder Ripper Tilt RH | 62015 | 8498 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-RTCYL | DZ169 Cylinder Ripper Tilt LH | 62015 | 11343 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-RPUCY | DZ169 Cylinder Ripper Pin Puller | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-RLCYR | DZ169 Cylinder Ripper Lift RH | 62015 | 7656 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-RLCYL | DZ169 Cylinder Ripper Lift LH | 62015 | 19197 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-BTCYR | DZ169 Cylinder Blade Tilt RH | 62015 | 12680 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-BTCYL | DZ169 Cylinder Blade Tilt LH | 62015 | 3033 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-BLCYR | DZ169 Cylinder Blade Lift RH | 62015 | 10794 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL-BLCYL | DZ169 Cylinder Blade Lift LH | 62015 | 8908 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCYL | DZ169 Cylinders Hydraulic | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCVL | DZ169 Implement Valves Hydraulic | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCON | DZ169 Implement Control Hydraulic | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS-HDCFM | DZ169 Fan Cooling Motor Hydraulic | 62015 | 293 | 5000
CCK-MP-DOZR-DZ169 -HYDSYS | DZ169 Hydraulic System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -GRSYST-GRTNK | DZ169 Auto Lube Resevoir | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -GRSYST-GRINJ | DZ169 Auto Lube Injectors | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -GRSYST-ALHLF | DZ169 Auto Lube Hoses Lines Fittings | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -GRSYST-ALELC | DZ169 Auto Lube Electrical | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -GRSYST-ALCON | DZ169 Auto Lube Controller | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -GRSYST-ALBPP | DZ169 Auto Lube Pump | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -GRSYST | DZ169 Grease Lubrication System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -FRSUPP-FSMAN-EXTIN | DZ169 Hand Held Fire Extinguisher | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -FRSUPP-FSMAN | DZ169 Fire Suppression Manual | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -FRSUPP-FSAUT-FFOAM | DZ169 Fire Suppression Foam | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -FRSUPP-FSAUT | DZ169 Fire Suppression Automatic | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -FRSUPP-FSALM | DZ169 Fire System Alarm | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -FRSUPP | DZ169 Fire Suppression System | 62015 | 30666 | 5000
CCK-MP-DOZR-DZ169 -FDRSYS-TRKRH | DZ169 Track Assembly R/H | 62015 | 17758 | 5000
CCK-MP-DOZR-DZ169 -FDRSYS-TRKLH | DZ169 Track Assembly L/H | 62015 | 17758 | 5000
CCK-MP-DOZR-DZ169 -FDRSYS-SEGRH | DZ169 Segments R/H | 62015 | 52341 | 5000
CCK-MP-DOZR-DZ169 -FDRSYS-SEGLH | DZ169 Segments L/H | 62015 | 52341 | 5000
CCK-MP-DOZR-DZ169 -FDRSYS-FDRRH | DZ169 Final Drive R/H | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -FDRSYS-FDRLH | DZ169 Final Drive L/H | 62015 | 1137 | 5000
CCK-MP-DOZR-DZ169 -FDRSYS | DZ169 Final Drive System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-LUBSY-PREPP | DZ169 Oil Pump Pre-Lube Engine | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-LUBSY-OILPP | DZ169 Oil Pump Engine | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-LUBSY-ENOLC | DZ169 Oil Cooler Engine | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-LUBSY | DZ169 Engine Lubrication System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-INTEX-TBORH | DZ169 Turbocharger R/H | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-INTEX-TBOLH | DZ169 Turbocharger L/H | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-INTEX-EXHST | DZ169 Exhaust System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-INTEX-AIRFL | DZ169 Air Filtration System | 62015 | 22000 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-INTEX-AFTER | DZ169 Aftercooler | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-INTEX | DZ169 Intake and Exhaust System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-FUSYS-FULTP | DZ169 Fuel Transfer Pump | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-FUSYS-FULTK | DZ169 Fuel Tank | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-FUSYS-FUINJ | DZ169 Fuel Injectors | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-FUSYS-FUHLF | DZ169 Fuel System Hoses, Lines and Fitt | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-FUSYS | DZ169 Fuel System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-COSYS-WTRPP | DZ169 Water Pump Engine | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-COSYS-THERM | DZ169 Thermostats/Regulators | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-COSYS-RADTR | DZ169 Radiator Engine | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-COSYS-CSHLF | DZ169 Cooling System Hoses, Lines and F | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-COSYS-COFAN | DZ169 Fan Cooling System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE-COSYS | DZ169 Engine Cooling System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ENGINE | DZ169 Engine Assembly, Caterpillar C27 | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-START-STRMR | DZ169 Starter Motor | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-START | DZ169 Electrical Starting System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-LIGHT | DZ169 Lighting Low Voltage | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-HARNS | DZ169 Electrical Harness | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-CONTL | DZ169 Electrical Controls Low Voltage | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-CHARG-BATTY | DZ169 Batteries | 62015 | 10783 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-CHARG-ALTER | DZ169 Alternator 24V | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV-CHARG | DZ169 Charging System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -ELCTLV | DZ169 Electrical System Low Voltage 24V | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -COMMUN-RADIO | DZ169 Two Way Radio | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -COMMUN-FLMGT | DZ169 Fleet Management | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -COMMUN | DZ169 Communications | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -BRKSTR-STVLV | DZ169 Valve Hydraulic Steering | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -BRKSTR-STHLF | DZ169 Steering System Hoses Lines and F | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -BRKSTR-STCON | DZ169 Controls Steering | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -BRKSTR-SCABR | DZ169 Steering Clutch and Brake Assembl | 62015 | 8044 | 5000
CCK-MP-DOZR-DZ169 -BRKSTR-SCABL | DZ169 Steering Clutch and Brake Assembl | 62015 | 1137 | 5000
CCK-MP-DOZR-DZ169 -BRKSTR-HYSPP | DZ169 Pump Hydraulic Steering | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 -BRKSTR | DZ169 Brake and Steering System | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ169 | DZ169 Mechanical & Lube Services | 62013 | 62013 | 5000
CCK-MP-DOZR-DZ169 | Caterpillar D10T Dozer, DZ169 | 62015 | 62015 | 5000
CCK-MP-DOZR-DZ014 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 64687 | 5273 | 5000
CCK-MP-DOZR-DZ014 -ELCTLV-CHARG-BATTY | DZ014 Battery | 64644 | 9172 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 34675 | 34675 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 28779 | 28779 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-FDRRH | Final Drive R/H | 32278 | 32278 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-FDRLH | Final Drive L/H | 30111 | 30111 | 5000
CCK-MP-DOZR-DZ014 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 64687 | 23459 | 5000
CCK-MP-DOZR-DZ014 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 40249 | 40249 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-PIVOT | Pivot Shaft | 64687 | 24170 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDTNK | Hydraulic Tank | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -TRNSYS-TRQUE | Torque Converter | 64687 | 9550 | 5000
CCK-MP-DOZR-DZ014 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -TRNSYS-TROLC | Oil Cooler Transmission | 64687 | 16308 | 5000
CCK-MP-DOZR-DZ014 -TRNSYS-TRANS-BEVEL | Bevel Gear | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -TRNSYS-TRANS | Transmission | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -TRNSYS | Transmission Drive Line | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-TKFRR | Track Frame R/H | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-TKFRL | Track Frame L/H | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 64687 | 18002 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 64687 | 24170 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 64687 | 24170 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 64687 | 24170 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-RIPPR | Ripper | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CHASS-TRNON | Trunnions | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CHASS-PUARM | Push Arms | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CHASS-PIVOT | Pivot Shaft | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CHASS-LNKGE | Link Stabiliser | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CHASS-EQUAL | Equaliser Bar | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CABIN-SEATS | Operators Seat | 64687 | 2402 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CABIN-SBELT | Seat Belt | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CABIN-AIRCN | Air Conditioning System | 64687 | 16308 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-CABIN | Operators Cabin | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -STRUCT-BLADE | Blade | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 64687 | 862 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-RTCYR | DZ014 Cylinder Ripper Tilt RH | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-RTCYL | DZ014 Cylinder Ripper Tilt LH | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-RLCYR | DZ014 Cylinder Ripper Lift RH | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-RLCYL | DZ014 Cylinder Ripper Lift LH | 64687 | 9227 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BTCYR | DZ014 Cylinder Blade Tilt RH | 64687 | 4406 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BTCYL | DZ014 Cylinder Blade Tilt LH | 64687 | 6028 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BLCYR | DZ014 Cylinder Blade Lift RH | 64687 | 6128 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCYL-BLCYL | DZ014 Cylinder Blade Lift LH | 64687 | 863 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCVL | Implement Valves Hydraulic | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCON | Implement Control Hydraulic | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 64687 | 56 | 5000
CCK-MP-DOZR-DZ014 -GRSYST-GRINJ | Auto Lube Injectors | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -GRSYST-ALCON | Auto Lube Controller | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -GRSYST-ALBPP | Auto Lube Pump | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-TRKRH | Track Assembly R/H | 64687 | 1094 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-TRKLH | Track Assembly L/H | 64687 | 1816 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-SEGRH | Segments R/H | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-SEGLH | Segments L/H | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-FDRRH | Final Drive R/H | 64687 | 4899 | 5000
CCK-MP-DOZR-DZ014 -FDRSYS-FDRLH | Final Drive L/H | 64687 | 4406 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 64687 | 47405 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 64687 | 16308 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-INTEX-TBORH | Turbocharger R/H | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-INTEX-AFTER | Aftercooler | 64687 | 16308 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-COSYS-WTRPP | Water Pump Engine | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-COSYS-THERM | Thermostats/Regulators | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-COSYS-RADTR | Radiator Coolant | 64687 | 30111 | 5100
CCK-MP-DOZR-DZ014 -ENGINE-COSYS-RADTR | Radiator Engine | 64687 | 2320 | 5000
CCK-MP-DOZR-DZ014 -ENGINE-COSYS-COFAN | Fan Cooling System | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -ENGINE | Engine Assembly, Caterpillar C27 | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ELCTLV-START-STRMR | Starter Motor | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -ELCTLV-CHARG-ALTER | Alternator 24V | 64687 | 3801 | 5000
CCK-MP-DOZR-DZ014 -BRKSTR-STVLV | Valve Hydraulic Steering | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 64687 | 4899 | 5000
CCK-MP-DOZR-DZ014 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 64687 | 9550 | 5000
CCK-MP-DOZR-DZ014 -BRKSTR-HYSPP | Pump Hydraulic Steering | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 | DZ014 Lubrication & Mechanical Services | 64687 | 64687 | 5000
CCK-MP-DOZR-DZ014 | Caterpillar D10T Dozer, DZ014 | 64687 | 64687 | 5000
CCK-MP-EXCV-EX7120 | R9400 Excavator EX7120 TRAVEL HOURS | 1973 | 1973 | 500
CCK-MP-HAUL-DT137 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84196 | 0 | 7400
CCK-MP-HAUL-DT137 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84196 | 0 | 7400
CCK-MP-HAUL-DT137 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84196 | 0 | 7400
CCK-MP-HAUL-DT137 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84196 | 0 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83108 | 0 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-SEATS | Operators Seat | 83059 | 0 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STOCO | Steering Oil Cooler | 88111 | 0 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 86608 | 0 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 86608 | 0 | 7400
CCK-MP-DRLL-DR3138-AIRSYS-ARTNK | DR3138 Receiver Tank | 14448 | 14448 | 5400
CCK-MP-DRLL-DR3138-TRAVEL-TRKRH | DR3138 Track Assembly RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-TRAVEL-TRKLH | DR3138 Track Assembly LH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-TRAVEL-SPRKR | DR3138 Sprocket RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-TRAVEL-SPRKL | DR3138 Sprocket LH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-TRAVEL-FDRRH | DR3138 Final Drive RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-TRAVEL-FDRLH | DR3138 Final Drive LH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF10 | DR3138 Roller Load Pos 10 S Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF09 | DR3138 Roller Load Pos 9 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF08 | DR3138 Roller Load Pos 8 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF07 | DR3138 Roller Load Pos 7 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF06 | DR3138 Roller Load Pos 6 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF05 | DR3138 Roller Load Pos 5 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF04 | DR3138 Roller Load Pos 4 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF03 | DR3138 Roller Load Pos 3 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF02 | DR3138 Roller Load Pos 2 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-RSF01 | DR3138 Roller Load Pos 1 Single Flange R | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-IDLRH | DR3138 Idler Track RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-CARRF | DR3138 Roller Carrier RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR-ADJGR | DR3138 Track Adjuster Grease RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRR | DR3138 Track Frame RH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF10 | DR3138 Roller Load Pos 10 S Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF09 | DR3138 Roller Load Pos 9 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF08 | DR3138 Roller Load Pos 8 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF07 | DR3138 Roller Load Pos 7 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF06 | DR3138 Roller Load Pos 6 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF05 | DR3138 Roller Load Pos 5 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF04 | DR3138 Roller Load Pos 4 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF03 | DR3138 Roller Load Pos 3 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF02 | DR3138 Roller Load Pos 2 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-RSF01 | DR3138 Roller Load Pos 1 Single Flange L | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-IDLLH | DR3138 Idler Track LH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-CARLF | DR3138 Roller Carrier LH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL-ADJGL | DR3138 Track Adjuster Grease LH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-TKFRL | DR3138 Track Frame LH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-CARAS-RMAGA | DR3138 Rod Magazine Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-CARAS-RGRPA | DR3138 Rod Gripper Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-CARAS | DR3138 Carousel Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-CABIN-SEATS | DR3138 Operators Seat | 14414 | 7858 | 5400
CCK-MP-DRLL-DR3138-STRUCT-CABIN-ACCOM | DR3138 Air Conditioning Compressor | 14414 | 7858 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-PWRHD | DR3138 Gearbox Power Head | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDMBA | DR3138 Feed Motor Brake Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDHDS | DR3138 Feed Chain Hose Drum Sprocket | 14414 | 7858 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDHDA | DR3138 Hose Drum Assembly | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHS | DR3138 Feed Chain Sprockets | 14414 | 7858 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHP | DR3138 Feed Chain Pulldown | 14414 | 7858 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-FDCHH | DR3138 Feed Chain Hoist | 14356 | 943 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-DSSAY | DR3138 Drill Steel Support Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-DMAST | DR3138 Mast | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BPERU | DR3138 Piston End Break Out Cylinder RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BPERL | DR3138 Piston End Break Out Cylinder RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BPELU | DR3138 Piston End Break Out Cylinder LH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BPELL | DR3138 Piston End Break Out Cylinder LH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BOTBL | DR3138 Breakout Table Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BMHDA | DR3138 Boom Head Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BMFHA | DR3138 Feed Holder Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BMASY | DR3138 Boom Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-STRUCT-BOOMS-BFEED | DR3138 Feed Beam Assembly | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-LUBSYS-DHDPP | DR3138 HECL Oil Pump | 14414 | 4212 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-PMPDR-COUPL | DR3138 Pump Drive Coupling | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HYDPP-MNPP4 | DR3138 Pump Hydraulic 4 & 5 | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HYDPP-MNPP3 | DR3138 Pump Hydraulic 3 | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HYDPP-MNPP2 | DR3138 Pump Hydraulic 2 | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HYDPP-MNPP1 | DR3138 Pump Hydraulic 1 | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDVLV-VVOST | DR3138 Valve Oscillation Track | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDVLV-VVOSR | DR3138 Valve Oscillation Relief | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDVLV-VVOCR | DR3138 Valve Over Centre | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDVLV-VVMBK | DR3138 Valve Main Block | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDTNK | DR3138 Tank Hydraulic | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MRTNR | DR3138 Motor Rotation RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MRTNL | DR3138 Motor Rotation LH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MPRPR | DR3138 Motor Propel RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MPRPL | DR3138 Motor Propel LH | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MFRCA | DR3138 Motor Fan Rad CAC Cooler Assy | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MFHCA | DR3138 Motor Fan Hyd Comp Cooler Assy | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDMOT-MFEED | DR3138 Motor Feed | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDHLF | DR3138 Hyd System Hose Lines & Fittings | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-TFCOR | DR3138 Cylinder Oscillation RH | 14403 | 4335 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-TFCOL | DR3138 Cylinder Oscillation LH | 14414 | 4335 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-RSFEC | DR3138 Cyl Rod Support Feed Extension | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-RMCTN | DR3138 Cylinder Rod Magazine Turning | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-RMCSU | DR3138 Cylinder Rod Magazine Securing Up | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-RMCSL | DR3138 Cylinder Rod Magazine Securing Lo | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-JLCYR | DR3138 Cylinder Jack levelling Rear | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-HASCU | DR3138 Cylinder Handling Arm Swing Upper | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-HASCL | DR3138 Cylinder Handling Arm Swing Lower | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-HACTN | DR3138 Cyl Rod Handling Arm Gripper Turn | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-HACGU | DR3138 Cyl Rod Handling Arm Gripper Up | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-HACGL | DR3138 Cyl Rod Handling Arm Gripper Lo | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-FDHCS | DR3138 Cylinder Feed Holder Swing | 14414 | 2853 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-FDDCR | DR3138 Cylinder Feed Dump RH | 14414 | 1483 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-FDDCL | DR3138 Cylinder Feed Dump LH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-FDCYE | DR3138 Cylinder Feed Extension | 14414 | 7799 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-DSCRH | DR3138 Cyl Drill Steel Support Lower RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-DSCLH | DR3138 Cyl Drill Steel Support Lower LH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BOTMC | DR3138 Cylinder Main Break Out Table | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BOTLR | DR3138 Cylinder Break Out Table Lower RH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BOTLL | DR3138 Cylinder Break Out Table Lower LH | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BOBRU | DR3138 Cyl Break Out Table Breaking RHU | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BOBRL | DR3138 Cyl Break Out Table Breaking RHL | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BOBLU | DR3138 Cyl Break Out Table Breaking LHU | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BOBLL | DR3138 Cyl Break Out Table Breaking LHL | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BMCYS | DR3138 Cylinder Boom Swing | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-HDCYL-BMCYH | DR3138 Cylinder Boom Lift | 14414 | 8511 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-COFAN-FCHCA | DR3138 Fan Hydraulic Compressor Cooling | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-HYDSYS-COFAN-FCECA | DR3138 Fan Engine CAC Cooling | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-GRSYST-RTLPP | DR3138 Rod Thread lube Pump | 14414 | 2620 | 5400
CCK-MP-DRLL-DR3138-GRSYST-ALPSV | DR3138 Auto lube Pump Safety Valve | 14414 | 2291 | 5400
CCK-MP-DRLL-DR3138-GRSYST-ALBPP | DR3138 Auto lube Pump | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-FRSUPP | DR3138 Fire Suppression System | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-ENGINE-INTEX-TBOP1 | DR3138 Turbocharger Engine | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-ENGINE-FUSYS-FULTK | DR3138 Fuel Tank Engine | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-ENGINE-FUSYS-FULPP | DR3138 Fuel Pump Engine | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-ENGINE-FUSYS-FULCO | DR3138 Fuel Cooler Engine | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-ENGINE-FUSYS-FUINJ | DR3138 Fuel Injectors Engine | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-ENGINE-FUSYS | DR3138 Engine Fuel System | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-ENGINE-COSYS-WTRPP | DR3138 Water pump Engine | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-ENGINE-COSYS-THERM | DR3138 Thermostats Regulators Engine | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-ENGINE | DR3138 Engine Assembly C15 | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-ELCTLV-START-STRMR | DR3138 Starter Motor Engine | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-ELCTLV-HARNS | DR3138 Wiring Harness | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-ELCTLV-CHARG-BATTY | DR3138 Batteries Engine | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-ELCTLV-CHARG-ALTER | DR3138 Alternator 24V | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-DSTSUP-WTTNK | DR3138 Water Tank | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-DSTSUP-WTRPP | DR3138 Pump Water Mist | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-COOLER-RADCA | DR3138 Cooler Radiator Charge Air | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-COOLER-HDOCO | DR3138 Cooler Hydraulic Compressor | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-VCSRL | DR3138 Air Compressor Safety Relief | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-VCOSP | DR3138 Air Compressor Oil Stop Valve | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-VCLOD | DR3138 Compressor Load Solenoid Valve | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-VCFLS | DR3138 Air Compressor Flushing Valves | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-VCBLW | DR3138 Air Compressor Blow Off Valve | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-VC34B | DR3138 34 bar Control Valves | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-PNHLF | DR3138 Air Hose Restraints | 14414 | 7858 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-PALUB | DR3138 Pump Air Lubrication | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR-COUPL | DR3138 Compressor Coupling | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138-AIRSYS-COMPR | DR3138 Main Air Compressor | 14414 | 3216 | 5400
CCK-MP-DRLL-DR3138 | Epiroc D65 XLF Drill DR3138 | 14414 | 14414 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-ARTNK | DR3137 Receiver Tank | 14235 | 10268 | 5400
CCK-MP-DRLL-DR3137-TRAVEL-TRKRH | DR3137 Track Assembly RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-TRAVEL-TRKLH | DR3137 Track Assembly LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-TRAVEL-SPRKR | DR3137 Sprocket RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-TRAVEL-SPRKL | DR3137 Sprocket LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-TRAVEL-FDRRH | DR3137 Final Drive RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-TRAVEL-FDRLH | DR3137 Final Drive LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF10 | DR3137 Roller Load Pos 10 S Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF09 | DR3137 Roller Load Pos 9 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF08 | DR3137 Roller Load Pos 8 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF07 | DR3137 Roller Load Pos 7 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF06 | DR3137 Roller Load Pos 6 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF05 | DR3137 Roller Load Pos 5 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF04 | DR3137 Roller Load Pos 4 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF03 | DR3137 Roller Load Pos 3 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF02 | DR3137 Roller Load Pos 2 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-RSF01 | DR3137 Roller Load Pos 1 Single Flange R | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-IDLRH | DR3137 Idler Track RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-CARRF | DR3137 Roller Carrier RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR-ADJGR | DR3137 Track Adjuster Grease RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRR | DR3137 Track Frame RH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF10 | DR3137 Roller Load Pos 10 S Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF09 | DR3137 Roller Load Pos 9 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF08 | DR3137 Roller Load Pos 8 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF07 | DR3137 Roller Load Pos 7 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF06 | DR3137 Roller Load Pos 6 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF05 | DR3137 Roller Load Pos 5 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF04 | DR3137 Roller Load Pos 4 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF03 | DR3137 Roller Load Pos 3 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF02 | DR3137 Roller Load Pos 2 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-RSF01 | DR3137 Roller Load Pos 1 Single Flange L | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-IDLLH | DR3137 Idler Track LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-CARLF | DR3137 Roller Carrier LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL-ADJGL | DR3137 Track Adjuster Grease LH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-TKFRL | DR3137 Track Frame LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-STRUCT-CARAS-RMAGA | DR3137 Rod Magazine Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-CARAS-RGRPA | DR3137 Rod Gripper Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-CARAS | DR3137 Carousel Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-CABIN-SEATS | DR3137 Operators Seat | 14232 | 4056 | 5400
CCK-MP-DRLL-DR3137-STRUCT-CABIN-ACCOM | DR3137 Air Conditioning Compressor | 14232 | 8625 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-PWRHD | DR3137 Gearbox Power Head | 14232 | 7186 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDMBA | DR3137 Feed Motor Brake Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDHDS | DR3137 Feed Chain Hose Drum Sprocket | 14232 | 8625 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDHDA | DR3137 Hose Drum Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHS | DR3137 Feed Chain Sprockets | 14232 | 8625 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHP | DR3137 Feed Chain Pulldown | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-FDCHH | DR3137 Feed Chain Hoist | 14232 | 1011 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-DSSAY | DR3137 Drill Steel Support Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-DMAST | DR3137 Mast | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BPERU | DR3137 Piston End Breakout Cyl RH Upper | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BPERL | DR3137 Piston End Breakout Cyl RH Lower | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BPELU | DR3137 Piston End Breakout Cyl LH Upper | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BPELL | DR3137 Piston End Breakout Cyl LH Lower | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BOTBL | DR3137 Breakout Table Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BMHDA | DR3137 Boom Head Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BMFHA | DR3137 Feed Holder Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BMASY | DR3137 Boom Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-STRUCT-BOOMS-BFEED | DR3137 Feed Beam Assembly | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-LUBSYS-DHDPP | DR3137 HECL Oil Pump | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-PMPDR-COUPL | DR3137 Pump Drive Coupling | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HYDPP-MNPP4 | DR3137 Pump Hydraulic 4 & 5 | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HYDPP-MNPP3 | DR3137 Pump Hydraulic 3 | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HYDPP-MNPP2 | DR3137 Pump Hydraulic 2 | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HYDPP-MNPP1 | DR3137 Pump Hydraulic 1 | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDVLV-VVOST | DR3137 Valve Oscillation Track | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDVLV-VVOSR | DR3137 Valve Oscillation Relief | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDVLV-VVOCR | DR3137 Valve Over Centre | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDVLV-VVMBK | DR3137 Valve Main Block | 14232 | 1891 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDTNK | DR3137 Tank Hydraulic | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MRTNR | DR3137 Motor Rotation RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MRTNL | DR3137 Motor Rotation LH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MPRPR | DR3137 Motor Propel RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MPRPL | DR3137 Motor Propel LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MFRCA | DR3137 Motor Fan Rad CAC Cooler Assy | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MFHCA | DR3137 Motor Fan Hyd Comp Cooler Assy | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDMOT-MFEED | DR3137 Motor Feed | 14232 | 4926 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDHLF | DR3137 Hyd System Hose Lines & Fittings | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-TFCOR | DR3137 Cylinder Oscillation RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-TFCOL | DR3137 Cylinder Oscillation LH | 14232 | 4968 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-RSFEC | DR3137 Cyl Rod Support Feed Extension | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-RMCTN | DR3137 Cylinder Rod Magazine Turning | 14232 | 1486 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-RMCSU | DR3137 Cylinder Rod Magazine Securing Up | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-RMCSL | DR3137 Cylinder Rod Magazine Securing Lo | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-JLCYR | DR3137 Cylinder Jack levelling Rear | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-HASCU | DR3137 Cylinder Handling Arm Swing Upper | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-HASCL | DR3137 Cylinder Handling Arm Swing Lower | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-HACTN | DR3137 Cyl Rod Handling Arm Gripper Turn | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-HACGU | DR3137 Cyl Rod Handling Arm Gripper Up | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-HACGL | DR3137 Cyl Rod Handling Arm Gripper Lo | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-FDHCS | DR3137 Cylinder Feed Holder Swing | 14232 | 4692 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-FDDCR | DR3137 Cylinder Feed Dump RH | 14232 | 1011 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-FDDCL | DR3137 Cylinder Feed Dump LH | 14232 | 1011 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-FDCYE | DR3137 Cylinder Feed Extension | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-DSCRH | DR3137 Cyl Drill Steel Support Lower RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-DSCLH | DR3137 Cyl Drill Steel Support Lower LH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BOTMC | DR3137 Cylinder Main Break Out Table | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BOTLR | DR3137 Cylinder Break Out Table Lower RH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BOTLL | DR3137 Cylinder Break Out Table Lower LH | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BOBRU | DR3137 Cyl Break Out Table Breaking RHU | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BOBRL | DR3137 Cyl Break Out Table Breaking RHL | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BOBLU | DR3137 Cyl Break Out Table Breaking LHU | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BOBLL | DR3137 Cyl Break Out Table Breaking LHL | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BMCYS | DR3137 Cylinder Boom Swing | 14232 | 875 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-HDCYL-BMCYH | DR3137 Cylinder Boom Lift | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-COFAN-FCHCA | DR3137 Fan Hydraulic Compressor Cooling | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-HYDSYS-COFAN-FCECA | DR3137 Fan Engine CAC Cooling | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-GRSYST-RTLPP | DR3137 Rod Thread lube Pump | 14232 | 2559 | 5400
CCK-MP-DRLL-DR3137-GRSYST-ALPSV | DR3137 Auto lube Pump Safety Valve | 14232 | 8625 | 5400
CCK-MP-DRLL-DR3137-GRSYST-ALBPP | DR3137 Auto lube Pump | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-FRSUPP | DR3137 Fire Suppression System | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-ENGINE-INTEX-TBOP1 | DR3137 Turbocharger Engine | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-ENGINE-FUSYS-FULTK | DR3137 Fuel Tank Engine | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-ENGINE-FUSYS-FULPP | DR3137 Fuel Pump Engine | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-ENGINE-FUSYS-FULCO | DR3137 Fuel Cooler Engine | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-ENGINE-FUSYS-FUINJ | DR3137 Fuel Injectors Engine | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-ENGINE-FUSYS | DR3137 Engine Fuel System | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-ENGINE-COSYS-WTRPP | DR3137 Water pump Engine | 14232 | 8625 | 5400
CCK-MP-DRLL-DR3137-ENGINE-COSYS-THERM | DR3137 Thermostats Engine | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-ENGINE | DR3137 Engine Assembly C15 | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-ELCTLV-START-STRMR | DR3137 Starter Motor Engine | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-ELCTLV-HARNS | DR3137 Wiring Harness | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-ELCTLV-CHARG-BATTY | DR3137 Batteries Engine | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-ELCTLV-CHARG-ALTER | DR3137 Alternator 24V | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-DSTSUP-WTTNK | DR3137 Water Tank | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-DSTSUP-WTRPP | DR3137 Pump Water Mist | 14232 | 7384 | 5400
CCK-MP-DRLL-DR3137-COOLER-RADCA | DR3137 Cooler Radiator Charge Air | 14232 | 2040 | 5400
CCK-MP-DRLL-DR3137-COOLER-HDOCO | DR3137 Cooler Hydraulic Compressor | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-VCSRL | DR3137 Air Compressor Safety Relief | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-VCOSP | DR3137 Air Compressor Oil Stop Valve | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-VCLOD | DR3137 Compressor Load Solenoid Valve | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-VCFLS | DR3137 Air Compressor Flushing Valves | 14232 | 2040 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-VCBLW | DR3137 Air Compressor Blow Off Valve | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-VC34B | DR3137 34 bar Control Valves | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-PNHLF | DR3137 Air Hose Restraints | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-PALUB | DR3137 Pump Air Lubrication | 14232 | 8625 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR-COUPL | DR3137 Compressor Coupling | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137-AIRSYS-COMPR | DR3137 Main Air Compressor | 14232 | 2835 | 5400
CCK-MP-DRLL-DR3137 | Epiroc D65 XLF Drill DR3137 | 14232 | 14232 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-ARTNK | DR3134 Receiver Tank | 16627 | 16627 | 5400
CCK-MP-DRLL-DR3134-TRAVEL-TRKRH | DR3134 Track Assembly RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-TRAVEL-TRKLH | DR3134 Track Assembly LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-TRAVEL-SPRKR | DR3134 Sprocket RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-TRAVEL-SPRKL | DR3134 Sprocket LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-TRAVEL-FDRRH | DR3134 Final Drive RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-TRAVEL-FDRLH | DR3134 Final Drive LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF10 | DR3134 Roller Load Pos 10 S Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF09 | DR3134 Roller Load Pos 9 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF08 | DR3134 Roller Load Pos 8 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF07 | DR3134 Roller Load Pos 7 Single Flange R | 16590 | 7567 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF06 | DR3134 Roller Load Pos 6 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF05 | DR3134 Roller Load Pos 5 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF04 | DR3134 Roller Load Pos 4 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF03 | DR3134 Roller Load Pos 3 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF02 | DR3134 Roller Load Pos 2 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-RSF01 | DR3134 Roller Load Pos 1 Single Flange R | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-IDLRH | DR3134 Idler Track RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-CARRF | DR3134 Roller Carrier RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR-ADJGR | DR3134 Track Adjuster Grease RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRR | DR3134 Track Frame RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF10 | DR3134 Roller Load Pos 10 S Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF09 | DR3134 Roller Load Pos 9 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF08 | DR3134 Roller Load Pos 8 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF07 | DR3134 Roller Load Pos 7 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF06 | DR3134 Roller Load Pos 6 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF05 | DR3134 Roller Load Pos 5 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF04 | DR3134 Roller Load Pos 4 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF03 | DR3134 Roller Load Pos 3 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF02 | DR3134 Roller Load Pos 2 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-RSF01 | DR3134 Roller Load Pos 1 Single Flange L | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-IDLLH | DR3134 Idler Track LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-CARLF | DR3134 Roller Carrier LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL-ADJGL | DR3134 Track Adjuster Grease LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-TKFRL | DR3134 Track Frame LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-STRUCT-CARAS-RMAGA | DR3134 Rod Magazine Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-CARAS-RGRPA | DR3134 Rod Gripper Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-CARAS | DR3134 Carousel Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-CABIN-SEATS | DR3134 Operators Seat | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-STRUCT-CABIN-ACCOM | DR3134 Air Conditioning Compressor | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-PWRHD | DR3134 Gearbox Power Head | 16590 | 5716 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDMBA | DR3134 Feed Motor Brake Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDHDS | DR3134 Feed Chain Hose Drum Sprocket | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDHDA | DR3134 Hose Drum Assembly | 16590 | 8396 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHS | DR3134 Feed Chain Sprockets | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHP | DR3134 Feed Chain Pulldown | 16590 | 567 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-FDCHH | DR3134 Feed Chain Hoist | 16590 | 3175 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-DSSAY | DR3134 Drill Steel Support Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-DMAST | DR3134 Mast | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BPERU | DR3134 Piston End Breakout Cyl RH Upper | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BPERL | DR3134 Piston End Breakout Cyl RH Lower | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BPELU | DR3134 Piston End Breakout Cyl LH Upper | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BPELL | DR3134 Piston End Breakout Cyl LH Lower | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BOTBL | DR3134 Breakout Table Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BMHDA | DR3134 Boom Head Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BMFHA | DR3134 Feed Holder Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BMASY | DR3134 Boom Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-STRUCT-BOOMS-BFEED | DR3134 Feed Beam Assembly | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-LUBSYS-DHDPP | DR3134 HECL Oil Pump | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-PMPDR-COUPL | DR3134 Pump Drive Coupling | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HYDPP-MNPP4 | DR3134 Pump Hydraulic 4 & 5 | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HYDPP-MNPP3 | DR3134 Pump Hydraulic 3 | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HYDPP-MNPP2 | DR3134 Pump Hydraulic 2 | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HYDPP-MNPP1 | DR3134 Pump Hydraulic 1 | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDVLV-VVOST | DR3134 Valve Oscillation Track | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDVLV-VVOSR | DR3134 Valve Oscillation Relief | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDVLV-VVOCR | DR3134 Valve Over Centre | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDVLV-VVMBK | DR3134 Valve Main Block | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDTNK | DR3134 Tank Hydraulic | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MRTNR | DR3134 Motor Rotation RH | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MRTNL | DR3134 Motor Rotation LH | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MPRPR | DR3134 Motor Propel RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MPRPL | DR3134 Motor Propel LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MFRCA | DR3134 Motor Fan Rad CAC Cooler Assy | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MFHCA | DR3134 Motor Fan Hyd Comp Cooler Assy | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDMOT-MFEED | DR3134 Motor Feed | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDHLF | DR3134 Hyd System Hose Lines & Fittings | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-TFCOR | DR3134 Cylinder Oscillation RH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-TFCOL | DR3134 Cylinder Oscillation LH | 16590 | 7605 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-RSFEC | DR3134 Cyl Rod Support Feed Extension | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-RMCTN | DR3134 Cylinder Rod Magazine Turning | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-RMCSU | DR3134 Cyl Rod Magazine Securing Upper | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-RMCSL | DR3134 Cyl Rod Magazine Securing Lower | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-JLCYR | DR3134 Cylinder Jack levelling Rear | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-HASCU | DR3134 Cylinder Handling Arm Swing Upper | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-HASCL | DR3134 Cylinder Handling Arm Swing Lower | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-HACTN | DR3134 Cyl Rod Handling Arm Gripper Turn | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-HACGU | DR3134 Cyl Rod Handling Arm Gripper Up | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-HACGL | DR3134 Cyl Rod Handling Arm Gripper Low | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-FDHCS | DR3134 Cylinder Feed Holder Swing | 16590 | 7567 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-FDDCR | DR3134 Cylinder Feed Dump RH | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-FDDCL | DR3134 Cylinder Feed Dump LH | 16590 | 3402 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-FDCYE | DR3134 Cylinder Feed Extension | 16590 | 2740 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-DSCRH | DR3134 Cyl Drill Steel Support Lower RH | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-DSCLH | DR3134 Cyl Drill Steel Support Lower LH | 16590 | 13815 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BOTMC | DR3134 Cylinder Main Break Out Table | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BOTLR | DR3134 Cylinder Break Out Table Lower RH | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BOTLL | DR3134 Cylinder Break Out Table LH Lower | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BOBRU | DR3134 Cyl Break Out Table Breaking RHU | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BOBRL | DR3134 Cyl Break Out Table Breaking RHL | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BOBLU | DR3134 Cyl Break Out Table Breaking LHU | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BOBLL | DR3134 Cyl Break Out Table Breaking LHL | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BMCYS | DR3134 Cylinder Boom Swing | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-HDCYL-BMCYH | DR3134 Cylinder Boom Lift | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-COFAN-FCHCA | DR3134 Fan Hydraulic Compressor Cooling | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-HYDSYS-COFAN-FCECA | DR3134 Fan Engine CAC Cooling | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-GRSYST-RTLPP | DR3134 Rod Thread lube Pump | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-GRSYST-ALPSV | DR3134 Auto lube Pump Safety Valve | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-GRSYST-ALBPP | DR3134 Auto lube Pump | 16590 | 970 | 5400
CCK-MP-DRLL-DR3134-FRSUPP | DR3134 Fire Suppression System | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-ENGINE-INTEX-TBOP1 | DR3134 Turbocharger Engine | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-ENGINE-FUSYS-FULTK | DR3134 Fuel Tank Engine | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-ENGINE-FUSYS-FULPP | DR3134 Fuel Pump Engine | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-ENGINE-FUSYS-FULCO | DR3134 Fuel Cooler Engine | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-ENGINE-FUSYS-FUINJ | DR3134 Fuel Injectors Engine | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-ENGINE-FUSYS | DR3134 Engine Fuel System | 16590 | 8745 | 5400
CCK-MP-DRLL-DR3134-ENGINE-COSYS-WTRPP | DR3134 Water pump Engine | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-ENGINE-COSYS-THERM | DR3134 Thermostats Regulators Engine | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-ENGINE | DR3134 Engine Assembly C15 | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-ELCTLV-START-STRMR | DR3134 Starter Motor Engine | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-ELCTLV-HARNS | DR3134 Wiring Harness | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-ELCTLV-CHARG-BATTY | DR3134 Batteries Engine | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-ELCTLV-CHARG-ALTER | DR3134 Alternator 24V | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-DSTSUP-WTTNK | DR3134 Water Tank | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-DSTSUP-WTRPP | DR3134 Pump Water Mist | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-COOLER-RADCA | DR3134 Cooler Radiator Charge Air | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-COOLER-HDOCO | DR3134 Cooler Hydraulic Compressor | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-VCSRL | DR3134 Air Compressor Safety Relief | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-VCOSP | DR3134 Air Compressor Oil Stop Valve | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-VCLOD | DR3134 Compressor Load Solenoid Valve | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-VCFLS | DR3134 Air Compressor Flushing Valves | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-VCBLW | DR3134 Air Compressor Blow Off Valve | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-VC34B | DR3134 34 bar Control Valves | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-PNHLF | DR3134 Air Hose Restraints | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-PALUB | DR3134 Pump Air Lubrication | 16590 | 5065 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR-COUPL | DR3134 Compressor Coupling | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134-AIRSYS-COMPR | DR3134 Main Air Compressor | 16590 | 5149 | 5400
CCK-MP-DRLL-DR3134 | Epiroc D65 XLF Drill DR3134 | 16590 | 16590 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-ARTNK | DR3133 Receiver Tank | 16273 | 10609 | 5400
CCK-MP-DRLL-DR3133-TRAVEL-TRKRH | DR3133 Track Assembly RH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-TRAVEL-TRKLH | DR3133 Track Assembly LH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-TRAVEL-SPRKR | DR3133 Sprocket RH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-TRAVEL-SPRKL | DR3133 Sprocket LH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-TRAVEL-FDRRH | DR3133 Final Drive RH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-TRAVEL-FDRLH | DR3133 Final Drive LH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF10 | DR3133 Roller Load Pos 10 S Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF09 | DR3133 Roller Load Pos 9 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF08 | DR3133 Roller Load Pos 8 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF07 | DR3133 Roller Load Pos 7 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF06 | DR3133 Roller Load Pos 6 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF05 | DR3133 Roller Load Pos 5 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF04 | DR3133 Roller Load Pos 4 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF03 | DR3133 Roller Load Pos 3 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF02 | DR3133 Roller Load Pos 2 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-RSF01 | DR3133 Roller Load Pos 1 Single Flange R | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-IDLRH | DR3133 Idler Track RH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-CARRF | DR3133 Roller Carrier RH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR-ADJGR | DR3133 Track Adjuster Grease RH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRR | DR3133 Track Frame RH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF10 | DR3133 Roller Load Pos 10 S Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF09 | DR3133 Roller Load Pos 9 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF08 | DR3133 Roller Load Pos 8 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF07 | DR3133 Roller Load Pos 7 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF06 | DR3133 Roller Load Pos 6 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF05 | DR3133 Roller Load Pos 5 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF04 | DR3133 Roller Load Pos 4 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF03 | DR3133 Roller Load Pos 3 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF02 | DR3133 Roller Load Pos 2 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-RSF01 | DR3133 Roller Load Pos 1 Single Flange L | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-IDLLH | DR3133 Idler Track LH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-CARLF | DR3133 Roller Carrier LH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL-ADJGL | DR3133 Track Adjuster Grease LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-TKFRL | DR3133 Track Frame LH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-STRUCT-CARAS-RMAGA | DR3133 Rod Magazine Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-CARAS-RGRPA | DR3133 Rod Gripper Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-CARAS | DR3133 Carousel Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-CABIN-SEATS | DR3133 Operators Seat | 16251 | 10110 | 5400
CCK-MP-DRLL-DR3133-STRUCT-CABIN-ACCOM | DR3133 Air Conditioning Compressor | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-PWRHD | DR3133 Gearbox Power Head | 16251 | 7735 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDMBA | DR3133 Feed Motor Brake Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDHDS | DR3133 Feed Chain Hose Drum Sprocket | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDHDA | DR3133 Hose Drum Assembly | 16251 | 8563 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHS | DR3133 Feed Chain Sprockets | 16251 | 2448 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHP | DR3133 Feed Chain Pulldown | 16251 | 1197 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-FDCHH | DR3133 Feed Chain Hoist | 16251 | 1197 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-DSSAY | DR3133 Drill Steel Support Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-DMAST | DR3133 Mast | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BPERU | DR3133 Piston End Break Out Cylinder RH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BPERL | DR3133 Piston End Break Out Cylinder RH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BPELU | DR3133 Piston End Break Out Cylinder LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BPELL | DR3133 Piston End Break Out Cylinder LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BOTBL | DR3133 Breakout Table Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BMHDA | DR3133 Boom Head Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BMFHA | DR3133 Feed Holder Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BMASY | DR3133 Boom Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-STRUCT-BOOMS-BFEED | DR3133 Feed Beam Assembly | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-LUBSYS-DHDPP | DR3133 HECL Oil Pump | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-PMPDR-COUPL | DR3133 Pump Drive Coupling | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HYDPP-MNPP4 | DR3133 Pump Hydraulic 4 & 5 | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HYDPP-MNPP3 | DR3133 Pump Hydraulic 3 | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HYDPP-MNPP2 | DR3133 Pump Hydraulic 2 | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HYDPP-MNPP1 | DR3133 Pump Hydraulic 1 | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDVLV-VVOST | DR3133 Valve Oscillation Track | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDVLV-VVOSR | DR3133 Valve Oscillation Relief | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDVLV-VVOCR | DR3133 Valve Over Centre | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDVLV-VVMBK | DR3133 Valve Main Block | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDTNK | DR3133 Tank Hydraulic | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MRTNR | DR3133 Motor Rotation RH | 16251 | 5715 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MRTNL | DR3133 Motor Rotation LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MPRPR | DR3133 Motor Propel RH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MPRPL | DR3133 Motor Propel LH | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MFRCA | DR3133 Motor Fan Rad CAC Cooler Assy | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MFHCA | DR3133 Motor Fan Hyd Comp Cooler Assy | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDMOT-MFEED | DR3133 Motor Feed | 16251 | 10609 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDHLF | DR3133 Hyd System Hose Lines & Fittings | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-TFCOR | DR3133 Cylinder Oscillation RH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-TFCOL | DR3133 Cylinder Oscillation LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-RSFEC | DR3133 Cyl Rod Support Feed Extension | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-RMCTN | DR3133 Cylinder Rod Magazine Turning | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-RMCSU | DR3133 Cylinder Rod Magazine Securing Up | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-RMCSL | DR3133 Cylinder Rod Magazine Securing Lo | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-JLCYR | DR3133 Cylinder Jack levelling Rear | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-HASCU | DR3133 Cylinder Handling Arm Swing Upper | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-HASCL | DR3133 Cylinder Handling Arm Swing Lower | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-HACTN | DR3133 Cyl Rod Handling Arm Gripper Turn | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-HACGU | DR3133 Cyl Rod Handling Arm Gripper Up | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-HACGL | DR3133 Cyl Rod Handling Arm Gripper Lo | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-FDHCS | DR3133 Cylinder Feed Holder Swing | 16251 | 8583 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-FDDCR | DR3133 Cylinder Feed Dump RH | 16251 | 2760 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-FDDCL | DR3133 Cylinder Feed Dump LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-FDCYE | DR3133 Cylinder Feed Extension | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-DSCRH | DR3133 Cyl Drill Steel Support Lower RH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-DSCLH | DR3133 Cyl Drill Steel Support Lower LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BOTMC | DR3133 Cylinder Main Break Out Table | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BOTLR | DR3133 Cylinder Break Out Table Lower RH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BOTLL | DR3133 Cylinder Break Out Table Lower LH | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BOBRU | DR3133 Cyl Break Out Table Breaking RHU | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BOBRL | DR3133 Cyl Break Out Table Breaking RHL | 16251 | 6175 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BOBLU | DR3133 Cyl Break Out Table Breaking LHU | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BOBLL | DR3133 Cyl Break Out Table Breaking LHL | 16251 | 2570 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BMCYS | DR3133 Cylinder Boom Swing | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-HDCYL-BMCYH | DR3133 Cylinder Boom Lift | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-COFAN-FCHCA | DR3133 Fan Hydraulic Compressor Cooling | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-HYDSYS-COFAN-FCECA | DR3133 Fan Engine CAC Cooling | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-GRSYST-RTLPP | DR3133 Rod Thread lube Pump | 16251 | 10110 | 5400
CCK-MP-DRLL-DR3133-GRSYST-ALPSV | DR3133 Auto lube Pump Safety Valve | 16251 | 4587 | 5400
CCK-MP-DRLL-DR3133-GRSYST-ALBPP | DR3133 Auto lube Pump | 16251 | 8583 | 5400
CCK-MP-DRLL-DR3133-FRSUPP | DR3133 Fire Suppression System | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-ENGINE-INTEX-TBOP1 | DR3133 Turbocharger Engine | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-ENGINE-FUSYS-FULTK | DR3133 Fuel Tank Engine | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-ENGINE-FUSYS-FULPP | DR3133 Fuel Pump Engine | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-ENGINE-FUSYS-FULCO | DR3133 Fuel Cooler Engine | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-ENGINE-FUSYS-FUINJ | DR3133 Fuel Injectors Engine | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-ENGINE-FUSYS | DR3133 Engine Fuel System | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-ENGINE-COSYS-WTRPP | DR3133 Water pump Engine | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-ENGINE-COSYS-THERM | DR3133 Thermostats Regulators Engine | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-ENGINE | DR3133 Engine Assembly C15 | 16251 | 4587 | 5400
CCK-MP-DRLL-DR3133-ELCTLV-START-STRMR | DR3133 Starter Motor Engine | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-ELCTLV-HARNS | DR3133 Wiring Harness | 16251 | 4587 | 5400
CCK-MP-DRLL-DR3133-ELCTLV-CHARG-BATTY | DR3133 Batteries Engine | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-ELCTLV-CHARG-ALTER | DR3133 Alternator 24V | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-DSTSUP-WTTNK | DR3133 Water Tank | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-DSTSUP-WTRPP | DR3133 Pump Water Mist | 16251 | 1685 | 5400
CCK-MP-DRLL-DR3133-COOLER-RADCA | DR3133 Cooler Radiator Charge Air | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-COOLER-HDOCO | DR3133 Cooler Hydraulic Compressor | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-VCSRL | DR3133 Air Compressor Safety Relief | 16251 | 10110 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-VCOSP | DR3133 Air Compressor Oil Stop Valve | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-VCLOD | DR3133 Compressor Load Solenoid Valve | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-VCFLS | DR3133 Air Compressor Flushing Valves | 16251 | 4824 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-VCBLW | DR3133 Air Compressor Blow Off Valve | 16251 | 4495 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-VC34B | DR3133 34 bar Control Valves | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-PNHLF | DR3133 Air Hose Restraints | 16251 | 16251 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-PALUB | DR3133 Pump Air Lubrication | 16251 | 10110 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR-COUPL | DR3133 Compressor Coupling | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133-AIRSYS-COMPR | DR3133 Main Air Compressor | 16251 | 4607 | 5400
CCK-MP-DRLL-DR3133 | Epiroc D65 XLF Drill DR3133 | 16251 | 16251 | 5400
CCK-MP-DRLL-DR2136-AIRSYS-ARTNK | DR2136 Receiver Tank | 13362 | 13362 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-TRKRH | Track Assembly Right Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-TRKLH | Track Assembly Left Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-TRBKR | Travel Brake Right Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-TRBKL | Travel Brake Left Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-SPRKR | Sprocket Right Hand | 13361 | 4130 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-SPRKL | Sprocket Left Hand | 13361 | 4373 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-FDRRH | Final Drive Right Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-TRAVEL-FDRLH | Final Drive Left Hand | 13361 | 4373 | 6700
CCK-MP-DRLL-DR2136-STRUCT-UNDER-EQUAL | Equaliser Bar | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF14 | Roller Load Pos 14 Single Flange CS | 13361 | 4130 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 13361 | 4130 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 13361 | 4130 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 13361 | 4130 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRR | Track Frame-Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF14 | Roller Load Pos 14 Single Flange NCS | 13361 | 8814 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-TKFRL | Track Frame-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 13361 | 3406 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 13361 | 2703 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 13361 | 2703 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-DSPAN | Deck Spanner | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-DMAST | Mast | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN-SEATS | Operators Seat | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN-AIRCN | Air Conditioning System | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-STRUCT-CABIN | Operators Cabin | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-LUBSYS-DHTNK | DHD Reservoir | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-LUBSYS-DHDPP | DHD Oil Pump | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-PMPDG | Pump Drive Gearbox | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDTNK | Tank Hydraulic | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 13361 | 1840 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 13361 | 4910 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 13361 | 7669 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 13361 | 8546 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End-Non Cab Side | 13361 | 5509 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-FDCYL | Cylinder Hoist Pulldown | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 13361 | 8077 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 13361 | 6120 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-GRSYST-RTTNK | Rod Thread Lube Reservoir | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-GRSYST-RTLPP | Rod Thread lube Pump | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-GRSYST-RTINJ | Rod Thread Grease Injector | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-GRSYST-GRTNK | Auto Lube Reservoir | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-GRSYST-GRINJ | Auto Lube Injectors | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-GRSYST-ALBPP | Auto lube Pump | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-FRSUPP | Fire Suppression System | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ENGINE-INTEX-EXHST | Exhaust System Engine | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE-COSYS-WTRPP | Water Pump Engine | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ENGINE-COSYS-RADTR | Radiator Engine | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ENGINE | Engine Assembly CAT C32 | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ELCTLV-START-STMRH | Starter Motor Engine Right | 13361 | 6120 | 6700
CCK-MP-DRLL-DR2136-ELCTLV-START-STMLH | Starter Motor Engine Left | 13361 | 6120 | 6700
CCK-MP-DRLL-DR2136-ELCTLV-HARNS | Wiring Harness | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ELCTLV-CHARG-BATTY | Batteries Engine | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ELCTLV-CHARG-ALTER | Alternator 24V | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-DSTSUP-WTRPP | Dynaset Water Pump | 13361 | 1577 | 6700
CCK-MP-DRLL-DR2136-DSTSUP-WTNKS | Water Tank Secondary | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-DSTSUP-WTNKP | Water Tank Primary | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-DSTSUP-WSHPP | Pump Wash Down | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-DSTSUP-WSHMT | Engine Wash Down | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-COOLER-HDOCO | Hydraulic Oil Cooler Core | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-COOLER-COOCO | Compressor Oil Cooler Core | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-COOLER | Cooler Module Assembly | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 13361 | 2706 | 6700
CCK-MP-DRLL-DR2136-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 13361 | 4800 | 6700
CCK-MP-DRLL-DR2136-AIRSYS-COMPR | Air Receiver Pressure Vessel | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-AIRSYS-COMPR | Main Air Compressor | 13361 | 8815 | 6700
CCK-MP-DRLL-DR2136-ADSYST-HARNC | ADS Harnesses & Connectors | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSPR | ADS HazTech | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSPO | ADS Global Positioning System | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSIS | ADS Instrumentation & Sensors | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST-ADSHW | ADS Hardware & Control System | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136-ADSYST | ADS Autonomous Rig Control System | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2136 | CAT MD6310 Drill DR2136 | 13361 | 13361 | 6700
CCK-MP-DRLL-DR2129-AIRSYS-ARTNK | DR2129 Receiver Tank | 18079 | 3352 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF14 | Roller Load Pos 14 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF14 | Roller Load Pos 14 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-UNDER-EQUAL | Equaliser Bar | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-DSTSUP-WTNKS | Water Tank Secondary | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-HARNC | ADS Harnesses & Connectors | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 18062 | 13815 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSPR | ADS HazTech | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSPO | ADS Global Positioning System | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSIS | ADS Instrumentation & Sensors | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ADSYST-ADSHW | ADS Hardware & Control System | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ELCTLV-HARNS | Wiring Harness | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-TRKRH | Track Assembly Right Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-TRKLH | Track Assembly Left Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-TRBKR | Travel Brake Right Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-TRBKL | Travel Brake Left Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-SPRKR | Sprocket Right Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-SPRKL | Sprocket Left Hand | 18062 | 9347 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-FDRRH | Final Drive Right Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-TRAVEL-FDRLH | Final Drive Left Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRR | Track Frame-Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 18062 | 15983 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-TKFRL | Track Frame-Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 18062 | 5521 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-DSPAN | Deck Spanner | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-DMAST | Mast | 18062 | 4985 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN-SEATS | Operators Seat | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN-AIRCN | Air Conditioning System | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN-ACCND | Air Conditioning Condenser | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-STRUCT-CABIN | Operators Cabin | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-PMPDG-DRSHT | Pump Drive Shaft | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-PMPDG | Pump Drive Gearbox | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 18062 | 3589 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 18062 | 4291 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDVLV-FLUVV | Valve-Relief Flushing | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDTNK | Tank Hydraulic | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 18062 | 13253 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 18057 | 1556 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End Non Cab Side | 18062 | 1556 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-FDCYL | Cylinder Hoist-Pulldown | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 18062 | 7084 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU-Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL-Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-GRSYST-RTTNK | Rod Thread Lube Reservoir | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-GRSYST-RTLPP | Rod Thread lube Pump | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-GRSYST-RTINJ | Rod Thread Grease Injector | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-GRSYST-GRTNK | Auto Lube Reservoir | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-GRSYST-GRINJ | Auto Lube Injectors | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-GRSYST-ALBPP | Auto lube Pump | 18062 | 11299 | 6800
CCK-MP-DRLL-DR2129-FRSUPP | Fire Suppression System | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ENGINE-INTEX-EXHST | Exhaust System Engine | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE-COSYS-WTRPP | Water Pump Engine | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ENGINE-COSYS-RADTR | Radiator Engine | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ENGINE | Engine Assembly CAT C32 | 18158 | 3449 | 6800
CCK-MP-DRLL-DR2129-ELCTLV-START-STMRH | Starter Motor Engine Right | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ELCTLV-START-STMLH | Starter Motor Engine Left | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-ELCTLV-CHARG-BATTY | Batteries Engine | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-ELCTLV-CHARG-ALTER | Alternator 24V | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-DSTSUP-WTNKP | Water Tank Primary | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-DSTSUP-WTRPP | Dynaset Water Pump | 18062 | 7100 | 6800
CCK-MP-DRLL-DR2129-DSTSUP-WSHPP | Pump Wash Down | 18062 | 3449 | 6800
CCK-MP-DRLL-DR2129-DSTSUP-WSHMT | Engine Wash Down | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-COOLER-HDOCO | Hydraulic Oil Cooler Core | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-COOLER-COOCO | Compressor Oil Cooler Core | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-COOLER | Cooler Module Assembly | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 18062 | 13204 | 6800
CCK-MP-DRLL-DR2129-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129-AIRSYS-COMPR | Main Air Compressor | 18062 | 320 | 6800
CCK-MP-DRLL-DR2129-ADSYST | ADS Autonomous Rig Control System | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2129 | CAT MD6310 Drill DR2129 | 18062 | 18062 | 6800
CCK-MP-DRLL-DR2128-AIRSYS-ARTNK | DR2128 Receiver Tank | 21693 | 21693 | 6800
CCK-MP-DRLL-DR2128-STRUCT-UNDER-EQUAL | Equaliser Bar | 21623 | 21623 | 6800
CCK-MP-DRLL-DR2128-DSTSUP-WTNKS | Water Tank Secondary | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-HARNC | ADS Harnesses & Connectors | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 21646 | 6175 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSPR | ADS HazTech | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSPO | ADS Global Positioning System | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 21646 | 11827 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSIS | ADS Instrumentation & Sensors | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ADSYST-ADSHW | ADS Hardware & Control System | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ELCTLV-HARNS | Wiring Harness | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-TRKRH | Track Assembly Right Hand | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-TRKLH | Track Assembly Left Hand | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-TRBKR | Travel Brake Right Hand | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-TRBKL | Travel Brake Left Hand | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-SPRKR | Sprocket Right Hand | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-SPRKL | Sprocket Left Hand | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-FDRRH | Final Drive Right Hand | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-TRAVEL-FDRLH | Final Drive Left Hand | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 21646 | 1400 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 21646 | 1400 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 21646 | 1400 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 21646 | 1400 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 21646 | 1309 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRR | Track Frame-Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 21646 | 1400 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 21646 | 1400 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 21646 | 1400 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-TKFRL | Track Frame-Non Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 21646 | 8615 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-DSPAN | Deck Spanner | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-DMAST | Mast | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN-SEATS | Operators Seat | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN-AIRCN | Air Conditioning System | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 21646 | 9264 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 21646 | 9264 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN-ACCND | Air Conditioning Condenser | 21646 | 9264 | 6800
CCK-MP-DRLL-DR2128-STRUCT-CABIN | Operators Cabin | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-PMPDG-DRSHT | Pump Drive Shaft | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-PMPDG | Pump Drive Gearbox | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 21646 | 79 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDVLV-FLUVV | Valve-Relief Flushing | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDTNK | Tank Hydraulic | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 21646 | 11817 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 21646 | 2226 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 21646 | 1516 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 21646 | 4602 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 21646 | 7977 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 21646 | 1486 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 21646 | 4602 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End Non Cab Side | 21646 | 2309 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-FDCYL | Cylinder Hoist-Pulldown | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU-Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL-Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 21646 | 6954 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-GRSYST-RTTNK | Rod Thread Lube Reservoir | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-GRSYST-RTLPP | Rod Thread lube Pump | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-GRSYST-RTINJ | Rod Thread Grease Injector | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-GRSYST-GRTNK | Auto Lube Reservoir | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-GRSYST-GRINJ | Auto Lube Injectors | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-GRSYST-ALBPP | Auto lube Pump | 21646 | 17905 | 6800
CCK-MP-DRLL-DR2128-FRSUPP | Fire Suppression System | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ENGINE-INTEX-EXHST | Exhaust System Engine | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE-COSYS-WTRPP | Water Pump Engine | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ENGINE-COSYS-RADTR | Radiator Engine | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ENGINE | Engine Assembly CAT C32 | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ELCTLV-START-STMRH | Starter Motor Engine Right | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ELCTLV-START-STMLH | Starter Motor Engine Left | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-ELCTLV-CHARG-BATTY | Batteries Engine | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-ELCTLV-CHARG-ALTER | Alternator 24V | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-DSTSUP-WTNKP | Water Tank Primary | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-DSTSUP-WTRPP | Dynaset Water Pump | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-DSTSUP-WSHPP | Pump Wash Down | 21646 | 3234 | 6800
CCK-MP-DRLL-DR2128-DSTSUP-WSHMT | Engine Wash Down | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-COOLER-HDOCO | Hydraulic Oil Cooler Core | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-COOLER-COOCO | Compressor Oil Cooler Core | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-COOLER | Cooler Module Assembly | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 21646 | 3367 | 6800
CCK-MP-DRLL-DR2128-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 21646 | 20951 | 6800
CCK-MP-DRLL-DR2128-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128-AIRSYS-COMPR | Main Air Compressor | 21646 | 6363 | 6800
CCK-MP-DRLL-DR2128-ADSYST | ARDVARC Autonomous Rig Control System | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2128 | CAT MD6310 Drill DR2128 | 21646 | 21646 | 6800
CCK-MP-DRLL-DR2113-AIRSYS-ARTNK | DR2113 Receiver Tank | 34054 | 3746 | 6800
CCK-MP-DRLL-DR2113-STRUCT-UNDER-EQUAL | Equaliser Bar | 33986 | 33986 | 6800
CCK-MP-DRLL-DR2113-DSTSUP-WTNKS | Water Tank Secondary | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ADSYST-HARNC | ADS Harnesses & Connectors | 34008 | 10800 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 34008 | 10800 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSPR | ADS HazTech | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSPO | ADS Global Positioning System | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSIS | ADS Instrumentation & Sensors | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 34008 | 10800 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-ADSYST-ADSHW | ADS Hardware & Control System | 34008 | 10800 | 6800
CCK-MP-DRLL-DR2113-ELCTLV-HARNS | Wiring Harness | 34008 | 16998 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 33987 | 12311 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-TRKRH | Track Assembly Right Hand | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-TRKLH | Track Assembly Left Hand | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-TRBKR | Travel Brake Right Hand | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-TRBKL | Travel Brake Left Hand | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-SPRKR | Sprocket Right Hand | 33987 | 2582 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-SPRKL | Sprocket Left Hand | 33987 | 2582 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-FDRRH | Final Drive Right Hand | 33987 | 2582 | 6800
CCK-MP-DRLL-DR2113-TRAVEL-FDRLH | Final Drive Left Hand | 33987 | 2582 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 33987 | 10801 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 33987 | 10801 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRR | Track Frame - Cab Side | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 33987 | 10801 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 33987 | 10801 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 33987 | 10801 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 33987 | 10801 | 6800
CCK-MP-DRLL-DR2113-STRUCT-TKFRL | Track Frame - Non Cab Side | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 33987 | 7786 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 33987 | 7867 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 33987 | 7867 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 33987 | 7867 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-DSPAN | Deck Spanner | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-DMAST | Mast | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 33987 | 10801 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN-SEATS | Operators Seat | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN-AIRCN | Air Conditioning System | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-STRUCT-CABIN | Operators Cabin | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ADSYST | ADS Autonomous Rig Control System | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 33987 | 2582 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-PMPDG | Pump Drive Gearbox | 33987 | 2582 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 33987 | 2582 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-MNPP2 | Main Pump - Cab Side | 33987 | 12311 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-MNPP1 | Main Pump - Non Cab Side | 33987 | 12311 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan - Cab Side | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan - Non Cab Side | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control - 4 Bank | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two - 4 Bank | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One - 6 Bank | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDTNK | Tank Hydraulic | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-MRTNR | Motor Rotation - Cab Side | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-MRTNL | Motor Rotation - Non Cab Side | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-MPRPR | Motor Travel - Cab Side | 33987 | 11590 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-MPRPL | Motor Travel - Non Cab Side | 33987 | 11590 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 33987 | 15927 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise - Cab Side | 33987 | 16998 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise - Non Cab Side | 33987 | 1834 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking - Cab Side | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking - Non Cab Side | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End - Cab Side | 33987 | 9499 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End - Cab Side | 33987 | 306 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End - Non Cab Side | 33987 | 22917 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End Non Cab Side | 33987 | 1040 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-FDCYL | Cylinder Hoist - Pulldown | 33987 | 16998 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 33987 | 18390 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 33987 | 18390 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU - Cab Side | 33987 | 18390 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 33987 | 18390 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL - Cab Side | 33987 | 18390 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 33987 | 18390 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 33987 | 18390 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 33987 | 20657 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 33987 | 10800 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-GRSYST-RTTNK | Rod Thread Lube Reservoir | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-GRSYST-RTLPP | Rod Thread lube Pump | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-GRSYST-RTINJ | Rod Thread Grease Injector | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-GRSYST-GRTNK | Auto Lube Reservoir | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-GRSYST-GRINJ | Auto Lube Injectors | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-GRSYST-ALBPP | Auto lube Pump | 33987 | 1040 | 6800
CCK-MP-DRLL-DR2113-FRSUPP | Fire Suppression System | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ENGINE-INTEX-EXHST | Exhaust System Engine | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 33987 | 16493 | 6800
CCK-MP-DRLL-DR2113-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 33987 | 16493 | 6800
CCK-MP-DRLL-DR2113-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ENGINE-COSYS-WTRPP | Water Pump Engine | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ENGINE-COSYS-RADTR | Radiator Engine | 33987 | 16493 | 6800
CCK-MP-DRLL-DR2113-ENGINE | Engine Assembly CAT C32 | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ELCTLV-START-STMRH | Starter Motor Engine Right | 33980 | 13861 | 6800
CCK-MP-DRLL-DR2113-ELCTLV-START-STMLH | Starter Motor Engine Left | 33987 | 13861 | 6800
CCK-MP-DRLL-DR2113-ELCTLV-CHARG-BATTY | Batteries Engine | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-ELCTLV-CHARG-ALTER | Alternator 24V | 33987 | 9239 | 6800
CCK-MP-DRLL-DR2113-DSTSUP-WSHMT | Engine Wash Down | 33987 | 4706 | 6800
CCK-MP-DRLL-DR2113-DSTSUP-WSHPP | Pump Wash Down | 33987 | 9462 | 6800
CCK-MP-DRLL-DR2113-DSTSUP-WTNKP | Water Tank Primary | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-DSTSUP-WTRPP | Dynaset Water Pump | 33987 | 306 | 6800
CCK-MP-DRLL-DR2113-COOLER-HDOCO | Hydraulic Oil Cooler Core | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-COOLER-COOCO | Compressor Oil Cooler Core | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-COOLER | Cooler Module Assembly | 33987 | 306 | 6800
CCK-MP-DRLL-DR2113-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 33987 | 33987 | 6800
CCK-MP-DRLL-DR2113-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2113-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 34008 | 11590 | 6800
CCK-MP-DRLL-DR2113-AIRSYS-COMPR | Main Air Compressor | 34008 | 548 | 6800
CCK-MP-DRLL-DR2113 | CAT MD6310 Drill DR2113 | 34008 | 34008 | 6800
CCK-MP-DRLL-DR2112-AIRSYS-ARTNK | DR2112 Receiver Tank | 34298 | 34298 | 6800
CCK-MP-DRLL-DR2112-STRUCT-UNDER-EQUAL | Equaliser Bar | 34230 | 34230 | 6800
CCK-MP-DRLL-DR2112-DSTSUP-WTNKS | Water Tank Secondary | 34249 | 10037 | 6800
CCK-MP-DRLL-DR2112-ADSYST-HARNC | ADS Harnesses & Connectors | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSPR | ADS HazTech | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSPO | ADS Global Positioning System | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSIS | ADS Instrumentation & Sensors | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 34252 | 2739 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 34252 | 2739 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ADSYST-ADSHW | ADS Hardware & Control System | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-ELCTLV-HARNS | Wiring Harness | 34252 | 34228 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 34249 | 10385 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 34249 | 10385 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 34249 | 11048 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 34249 | 10385 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 34249 | 10385 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 34249 | 10385 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 34249 | 10385 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 34249 | 10385 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-TRKRH | Track Assembly Right Hand | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-TRKLH | Track Assembly Left Hand | 34249 | 22114 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-TRBKR | Travel Brake Right Hand | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-TRBKL | Travel Brake Left Hand | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-SPRKR | Sprocket Right Hand | 34249 | 4197 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-SPRKL | Sprocket Left Hand | 34249 | 4197 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-FDRRH | Final Drive Right Hand | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-TRAVEL-FDRLH | Final Drive Left Hand | 34249 | 11924 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 34249 | 11324 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 34249 | 11324 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRR | Track Frame - Cab Side | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 34249 | 15978 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 34249 | 11326 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 34249 | 22131 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 34249 | 11326 | 6800
CCK-MP-DRLL-DR2112-STRUCT-TKFRL | Track Frame - Non Cab Side | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 34249 | 10345 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 34249 | 10345 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 34249 | 10345 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 34249 | 10345 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 34249 | 7741 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 34249 | 4691 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 34249 | 7741 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 34249 | 7741 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-DSPAN | Deck Spanner | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-DMAST | Mast | 34249 | 7732 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 34249 | 8288 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN-SEATS | Operators Seat | 34249 | 12444 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN-AIRCN | Air Conditioning System | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-STRUCT-CABIN | Operators Cabin | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ADSYST | ADS Autonomous Rig Control System | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 34249 | 2406 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-PMPDG | Pump Drive Gearbox | 34249 | 2739 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 34249 | 6803 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-MNPP2 | Main Pump - Cab Side | 34249 | 6803 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-MNPP1 | Main Pump - Non Cab Side | 34249 | 13155 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan - Cab Side | 34249 | 6803 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan - Non Cab Side | 34249 | 6803 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control - 4 Bank | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two - 4 Bank | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One - 6 Bank | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDTNK | Tank Hydraulic | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-MRTNR | Motor Rotation - Cab Side | 34249 | 19440 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-MRTNL | Motor Rotation - Non Cab Side | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-MPRPR | Motor Travel - Cab Side | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-MPRPL | Motor Travel - Non Cab Side | 34249 | 14251 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise - Cab Side | 34249 | 7731 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise - Non Cab Side | 34249 | 22682 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking - Cab Side | 34249 | 7732 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking - Non Cab Side | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End - Cab Side | 34249 | 22114 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End - Cab Side | 34249 | 2739 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End - Non Cab Side | 34249 | 1270 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End Non Cab Side | 34249 | 2981 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-FDCYL | Cylinder Hoist - Pulldown | 34249 | 10365 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 34249 | 21694 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 34249 | 21704 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 34249 | 22114 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 34249 | 22114 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU - Cab Side | 34249 | 16769 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 34249 | 16769 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL - Cab Side | 34249 | 16769 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 34249 | 16769 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 34249 | 22118 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 34249 | 20970 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-GRSYST-RTTNK | Rod Thread Lube Reservoir | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-GRSYST-RTLPP | Rod Thread lube Pump | 34249 | 28295 | 6800
CCK-MP-DRLL-DR2112-GRSYST-RTINJ | Rod Thread Grease Injector | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-GRSYST-GRTNK | Auto Lube Reservoir | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-GRSYST-GRINJ | Auto Lube Injectors | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-GRSYST-ALBPP | Auto lube Pump | 34249 | 13689 | 6800
CCK-MP-DRLL-DR2112-FRSUPP | Fire Suppression System | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ENGINE-INTEX-EXHST | Exhaust System Engine | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ENGINE-COSYS-WTRPP | Water Pump Engine | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ENGINE-COSYS-RADTR | Radiator Engine | 34249 | 2739 | 6800
CCK-MP-DRLL-DR2112-ENGINE | Engine Assembly CAT C32 | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ELCTLV-START-STMRH | Starter Motor Engine Right | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ELCTLV-START-STMLH | Starter Motor Engine Left | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-ELCTLV-CHARG-BATTY | Batteries Engine | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-ELCTLV-CHARG-ALTER | Alternator 24V | 34249 | 1582 | 6800
CCK-MP-DRLL-DR2112-DSTSUP-WSHMT | Engine Wash Down | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-DSTSUP-WSHPP | Pump Wash Down | 34249 | 9455 | 6800
CCK-MP-DRLL-DR2112-DSTSUP-WTNKP | Water Tank Primary | 34249 | 10037 | 6800
CCK-MP-DRLL-DR2112-DSTSUP-WTRPP | Dynaset Water Pump | 34249 | 11324 | 6800
CCK-MP-DRLL-DR2112-COOLER-HDOCO | Hydraulic Oil Cooler Core | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-COOLER-COOCO | Compressor Oil Cooler Core | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-COOLER | Cooler Module Assembly | 34249 | 2739 | 6800
CCK-MP-DRLL-DR2112-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 34249 | 34249 | 6800
CCK-MP-DRLL-DR2112-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2112-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 34252 | 3236 | 6800
CCK-MP-DRLL-DR2112-AIRSYS-COMPR | Main Air Compressor | 34252 | 10999 | 6800
CCK-MP-DRLL-DR2112 | CAT MD6310 Drill DR2112 | 34252 | 34252 | 6800
CCK-MP-DRLL-DR2111-AIRSYS-ARTNK | DR2111 Receiver Tank | 49465 | 49465 | 6800
CCK-MP-DRLL-DR2111-ELCTLV-HARNS-HARCO | Electrical Harness Control | 49417 | 49417 | 6800
CCK-MP-DRLL-DR2111-ADSYST-HARNC | ADS Harnesses & Connectors | 49417 | 4564 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 49417 | 6939 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 49417 | 19408 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSPR | ADS HazTech | 49417 | 45632 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSPO | ADS Global Positioning System | 49417 | 45632 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 49417 | 45632 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 49417 | 45632 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 49417 | 45632 | 6800
CCK-MP-DRLL-DR2111-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 49417 | 45632 | 6800
CCK-MP-DRLL-DR2111-ADSYST | Autonomous Drilling System | 49417 | 45632 | 6800
CCK-MP-DRLL-DR2111-ELCTLV-HARNS | Wiring Harness | 49417 | 49417 | 6800
CCK-MP-DRLL-DR2111-TRAVEL-TRKRH | DR2111 Track Assembly - Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-TRAVEL-TRKLH | DR2111 Track Assembly - Non Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-TRAVEL-SPRKR | DR2111 Sprocket - Cab Side | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-TRAVEL-SPRKL | DR2111 Sprocket - Non Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RSF04 | DR2111 Roller Load Pos 4 S Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RSF03 | DR2111 Roller Load Pos 3 S Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RSF02 | DR2111 Roller Load Pos 2 S Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RSF01 | DR2111 Roller Load Pos 1 S Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF13 | DR2111 Roller Load Pos 13 D Flange - CS | 49389 | 8360 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF12 | DR2111 Roller Load Pos 12 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF11 | DR2111 Roller Load Pos 11 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF10 | DR2111 Roller Load Pos 10 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF09 | DR2111 Roller Load Pos 9 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF08 | DR2111 Roller Load Pos 8 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF07 | DR2111 Roller Load Pos 7 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF06 | DR2111 Roller Load Pos 6 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-RDF05 | DR2111 Roller Load Pos 5 D Flange - CS | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-IDLRH | DR2111 Idler Track - Cab Side | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-CARRR | DR2111 Roller Carrier Rear - Cab Side | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-CARRM | DR2111 Roller Carrier Middle - Cab Side | 49389 | 8360 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-CARRF | DR2111 Roller Carrier Front - Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR | DR2111 Track Frame - Cab Side | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RSF04 | DR2111 Roller Load Pos 4 S Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RSF03 | DR2111 Roller Load Pos 3 S Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RSF02 | DR2111 Roller Load Pos 2 S Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RSF01 | DR2111 Roller Load Pos 1 S Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF13 | DR2111 Roller Load Pos 13 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF12 | DR2111 Roller Load Pos 12 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF11 | DR2111 Roller Load Pos 11 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF10 | DR2111 Roller Load Pos 10 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF09 | DR2111 Roller Load Pos 9 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF08 | DR2111 Roller Load Pos 8 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF07 | DR2111 Roller Load Pos 7 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF06 | DR2111 Roller Load Pos 6 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-RDF05 | DR2111 Roller Load Pos 5 D Flange - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-IDLLH | DR2111 Idler Track - Non Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-CARLR | DR2111 Roller Carrier Rear - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-CARLM | DR2111 Roller Carrier Middle - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-CARLF | DR2111 Roller Carrier Front - NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL | DR2111 Track Frame - Non Cab Side | 49393 | 8338 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-AFRME | DR2111 Tower A Frame | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-AIRSYS-EARCS-BDVVE | DR2111 Blowdown Valve | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-AIRSYS-EARCS-ACTBD | DR2111 Actuator Blowdown Valve | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-AIRSYS-EARCS-BFVVE | DR2111 Comp Butterfly Valve | 49393 | 22043 | 6800
CCK-MP-DRLL-DR2111-AIRSYS-EARCS-ACTBV | DR2111 Actuator Butterfly Valve | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-ENGINE-FUSYS-FULTK | Fuel Tank Mounting Bolts | 49393 | 11797 | 6800
CCK-MP-DRLL-DR2111-HYDSYS | DR2111 Hyraulic Tune | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SHULR | DR2111 Sheave Assy Up/Lower - Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SHULL | DR2111 Sheave Assy Up/Lower-Non Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER | DR2111 Tower | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-DSTSUP-WTRPP | DR2111 Pump Water Injection | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-GRSYST-RTLPP | DR2111 Rod Thread lube Pump | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-GRSYST-ALBPP | DR2111 Auto lube Pump | 49393 | 5207 | 6800
CCK-MP-DRLL-DR2111-LUBSYS-DHDPP | DR2111 DHD Oil Pump | 49393 | 36931 | 6800
CCK-MP-DRLL-DR2111-STRUCT-WINCH-WINRP | DR2111 Winch Rope | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-STRUCT-WINCH-WINSH | DR2111 Winch Sheaves | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-STRUCT-WINCH | DR2111 Winch Assembly | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-STRUCT-UNDER-YKOSC | DR2111 Yoke Oscillation | 49393 | 8374 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-BOFKA | DR2111 Breakout Fork Sliding Assembly | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-BOWRH | DR2111 Breakout Wrench Assy | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-CARAS | DR2111 Rod Changer / Carousel | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-RDSPT | DR2111 Rod support | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SCBTR | DR2111 Screw Jack Cable Tension R/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SCBTL | DR2111 Screw Jack Cable Tension L/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SHAUR | DR2111 Sheave Assembly Upper Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SHAUL | DR2111 Sheave Assembly Uppr Non Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SHALR | DR2111 Sheave Assembly Lower Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-SHALL | DR2111 Sheave Assembly Lowr Non Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-CSHAR | DR2111 Carriage Sheave Assembly Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-CSHAL | DR2111 Carriage Sheave Assy Non Cab Side | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-PBCBR | DR2111 Pullback Cable R/H | 49393 | 2876 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-PBCBL | DR2111 Pullback Cable L/H | 49393 | 2876 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-PDCBR | DR2111 Pulldown Cable R/H | 49393 | 2876 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-PDCBL | DR2111 Pulldown Cable L/H | 49393 | 2876 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TOWER-PWRHD | DR2111 Gearbox Power Head | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRR-ADJGR | DR2111 Track Adjuster Grease R/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-TKFRL-ADJGL | DR2111 Track Adjuster Grease L/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-STRUCT-CRANE | DR2111 Hiab Crane | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-STRUCT-CABIN-SEATS | DR2111 Operators Seat | 49393 | 11797 | 6800
CCK-MP-DRLL-DR2111-STRUCT-CABIN-ACCOM | DR2111 Air Conditioning Compressor | 49393 | 43134 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-COFAN-FCCAC | DR2111 Fan Cooling Charge Air Cooler | 49393 | 11797 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-COFAN-FCCMA | DR2111 Fan Cooling Cooler Module Assy | 49393 | 11797 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-ACONM | DR2111 Motor Hyd Air Con | 49393 | 43134 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MWINJ | DR2111 Motor Water Injection Pump | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MWINC | DR2111 Motor Winch | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MRTNR | DR2111 Hyd Motor Rotation CS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MRTNL | DR2111 Hyd Motor Rotation NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTR | DR2111 Mtr 4.9 CID ScrewJack Tension CS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MSJTL | DR2111 Mtr 4.9 CID ScrewJack Tension NCS | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MPRPR | DR2111 Motor Propel R/H | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MPRPL | DR2111 Motor Propel L/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MFCAC | DR2111 Motor Fan CAC Cooler | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDMOT-MFMCA | DR2111 Motor Fan Main Cooler Assy | 49393 | 1608 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VWIBR | DR2111 Winch Valve Brake Hyd | 49393 | 49393 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVTNC | DR2111 Valve Tension Cable | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDPC | DR2111 Valve Drill/Propel Control | 49393 | 26969 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDVR | DR2111 Valve Diverter RH | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDVL | DR2111 Valve Diverter LH | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVCNB | DR2111 Valve Counter Balance | 49393 | 11797 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVDCB | DR2111 Valve Dual Counter Balance | 49393 | 16543 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VV11S | DR2111 Valve Stacking 11 spool | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDVLV-VVS8S | DR2111 Valve Stacking 8 spool | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-CTCYR | DR2111 Cylinder Cable Tension R/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-CTCYL | DR2111 Cylinder Cable Tension L/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-FDCYR | DR2111 Cylinder Feed Hyd R/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-FDCYL | DR2111 Cylinder Feed Hyd L/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYRR | DR2111 Cylinder Jack Leg R/H/R | 49393 | 8373 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYLR | DR2111 Cylinder Jack Leg L/H/R | 49393 | 7634 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYRF | DR2111 Cylinder Jack Leg R/H/F | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-JCYLF | DR2111 Cylinder Jack Leg L/H/F | 49393 | 17919 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TACYR | DR2111 Cyl Tower Support Angle Lock R/H | 49393 | 16543 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TACYL | DR2111 Cyl Tower Support Angle Lock L/H | 49393 | 16543 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TLCYR | DR2111 Cylinder Tower locking R/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TLCYL | DR2111 Cylinder Tower locking L/H | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYR | DR2111 Cylinder Tower Raise R/H | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HDCYL-TRCYL | DR2111 Cylinder Tower Raise L/H | 49393 | 8364 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HYDPP-PRHDL | DR2111 Pump Self Revers Power Head Lube | 49393 | 8353 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HYDPP-MNPP3 | DR2111 Pump Hydraulic triple | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HYDPP-MNPP2 | "DR2111 Pump Hydraulic P7,9A CONT" | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-HYDPP-MNPP1 | "DR2111 Pump Hydraulic P7,9A CONT" | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-PMPDR-DRSHT | DR2111 Pump Drive Drive Shaft | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-HYDSYS-PMPDR | DR2111 Pump Drive Gearbox 3 Hole | 49393 | 4564 | 6800
CCK-MP-DRLL-DR2111-COOLER | DR2111 Cooler Module Assembley | 49417 | 11797 | 6800
CCK-MP-DRLL-DR2111-AIRSYS-COMPR-COUPL | DR2111 Compressor Coupling Ringfeeder | 49417 | 4564 | 6800
CCK-MP-DRLL-DR2111-AIRSYS-COMPR | DR2111 Main Air Compressor | 49417 | 11797 | 6800
CCK-MP-DRLL-DR2111-TRAVEL-FDRRH | DR2111 Final Drive R/H | 49417 | 8364 | 6800
CCK-MP-DRLL-DR2111-TRAVEL-FDRLH | DR2111 Final Drive L/H | 49417 | 8353 | 6800
CCK-MP-DRLL-DR2111-ELCTLV-START-STMRH | DR2111 Starter Motor Engine Right | 49387 | 4564 | 6800
CCK-MP-DRLL-DR2111-ELCTLV-START-STMLH | DR2111 Starter Motor Engine Left | 49387 | 4564 | 6800
CCK-MP-DRLL-DR2111-ELCTLV-CHARG-ALTER | DR2111 Alternator 24V | 49387 | 4470 | 6800
CCK-MP-DRLL-DR2111-ENGINE-FUSYS-FULCO | DR2111 Fuel Cooler Engine | 49417 | 11797 | 6800
CCK-MP-DRLL-DR2111-ENGINE-FUSYS-FUINJ | DR2111 Fuel Injectors Engine | 49387 | 4564 | 6800
CCK-MP-DRLL-DR2111-ENGINE-FUSYS-FULPP | DR2111 Fuel Pump Engine | 49387 | 4564 | 6800
CCK-MP-DRLL-DR2111-ENGINE-INTEX-CACAS | DR2111 Charge Air Cooler | 49417 | 11797 | 6800
CCK-MP-DRLL-DR2111-ENGINE-INTEX-TBOP2 | DR2111 Turbocharger Engine | 49387 | 4564 | 6800
CCK-MP-DRLL-DR2111-ENGINE-INTEX-TBOP1 | DR2111 Turbocharger Engine | 49387 | 4470 | 6800
CCK-MP-DRLL-DR2111-ENGINE-COSYS-THERM | DR2111 Thermostats/Regulators Engine | 49387 | 4564 | 6800
CCK-MP-DRLL-DR2111-ENGINE-COSYS-WTRPP | DR2111 Water pump Engine | 49387 | 4564 | 6800
CCK-MP-DRLL-DR2111-ENGINE | DR2111 Engine Assembly | 49411 | 11797 | 6800
CCK-MP-DRLL-DR2111 | Atlas Copco PV271HP Drill, DR2111 | 49417 | 49417 | 6800
CCK-MP-DRLL-DR2110-AIRSYS-ARTNK | DR2110 Receiver Tank | 54955 | 54955 | 6800
CCK-MP-DRLL-DR2110-ELCTLV-HARNS-HARCO | Electrical Harness Control | 54907 | 14230 | 6800
CCK-MP-DRLL-DR2110-ADSYST-HARNC | ADS Harnesses & Connectors | 54907 | 14230 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 54907 | 14230 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 54907 | 14238 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSPR | ADS HazTech | 54907 | 54751 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSPO | ADS Global Positioning System | 54907 | 54751 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 54907 | 54751 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 54907 | 14230 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 54907 | 14230 | 6800
CCK-MP-DRLL-DR2110-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 54907 | 54751 | 6800
CCK-MP-DRLL-DR2110-ADSYST | Autonomous Drilling System | 54907 | 54751 | 6800
CCK-MP-DRLL-DR2110-ELCTLV-HARNS | Wiring Harness | 54907 | 54907 | 6800
CCK-MP-DRLL-DR2110-TRAVEL-TRKRH | DR2110 Track Assembly - Cab Side | 54883 | 351 | 6800
CCK-MP-DRLL-DR2110-TRAVEL-TRKLH | DR2110 Track Assembly - Non Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-TRAVEL-SPRKR | DR2110 Sprocket - Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-TRAVEL-SPRKL | DR2110 Sprocket - Non Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RSF04 | DR2110 Roller Load Pos 4 S Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RSF03 | DR2110 Roller Load Pos 3 S Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RSF02 | DR2110 Roller Load Pos 2 S Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RSF01 | DR2110 Roller Load Pos 1 S Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF13 | DR2110 Roller Load Pos 13 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF12 | DR2110 Roller Load Pos 12 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF11 | DR2110 Roller Load Pos 11 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF10 | DR2110 Roller Load Pos 10 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF09 | DR2110 Roller Load Pos 9 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF08 | DR2110 Roller Load Pos 8 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF07 | DR2110 Roller Load Pos 7 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF06 | DR2110 Roller Load Pos 6 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-RDF05 | DR2110 Roller Load Pos 5 D Flange - CS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-IDLRH | DR2110 Idler Track - Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-CARRR | DR2110 Roller Carrier Rear - Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-CARRM | DR2110 Roller Carrier Middle - Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-CARRF | DR2110 Roller Carrier Front - Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR | DR2110 Track Frame - Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RSF04 | DR2110 Roller Load Pos 4 S Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RSF03 | DR2110 Roller Load Pos 3 S Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RSF02 | DR2110 Roller Load Pos 2 S Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RSF01 | DR2110 Roller Load Pos 1 S Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF13 | DR2110 Roller Load Pos 13 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF12 | DR2110 Roller Load Pos 12 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF11 | DR2110 Roller Load Pos 11 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF10 | DR2110 Roller Load Pos 10 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF09 | DR2110 Roller Load Pos 9 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF08 | DR2110 Roller Load Pos 8 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF07 | DR2110 Roller Load Pos 7 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF06 | DR2110 Roller Load Pos 6 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-RDF05 | DR2110 Roller Load Pos 5 D Flange - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-IDLLH | DR2110 Idler Track - Non Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-CARLR | DR2110 Roller Carrier Rear - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-CARLM | DR2110 Roller Carrier Middle - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-CARLF | DR2110 Roller Carrier Front - NCS | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL | DR2110 Track Frame - Non Cab Side | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-AFRME | DR2110 Tower A Frame | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-AIRSYS-EARCS-BDVVE | DR2110 Blowdown Valve | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-AIRSYS-EARCS-ACTBD | DR2110 Actuator Blowdown Valve | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-AIRSYS-EARCS-BFVVE | DR2110 Comp Butterfly Valve | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-AIRSYS-EARCS-ACTBV | DR2110 Actuator Butterfly Valve | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE-FUSYS-FULTK | Fuel Tank Mounting Bolts | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS | DR2110 Hyraulic Tune | 54883 | 22468 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SHULR | DR2110 Sheave Assy Up/Lower - Cab Side | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SHULL | DR2110 Sheave Assy Up/Lower-Non Cab Side | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER | DR2110 Tower | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-DSTSUP-WTRPP | DR2110 Pump Water Injection | 54883 | 11134 | 6800
CCK-MP-DRLL-DR2110-GRSYST-RTLPP | DR2110 Rod Thread lube Pump | 54883 | 11134 | 6800
CCK-MP-DRLL-DR2110-GRSYST-ALBPP | DR2110 Auto lube Pump | 54883 | 2172 | 6800
CCK-MP-DRLL-DR2110-LUBSYS-DHDPP | DR2110 DHD Oil Pump | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-STRUCT-WINCH-WINRP | DR2110 Winch Rope | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-STRUCT-WINCH-WINSH | DR2110 Winch Sheaves | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-STRUCT-WINCH | DR2110 Winch Assembly | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-STRUCT-UNDER-YKOSC | DR2110 Yoke Oscillation | 54883 | 20610 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-BOFKA | DR2110 Breakout Fork Sliding Assembly | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-BOWRH | DR2110 Breakout Wrench Assy | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-CARAS | DR2110 Rod Changer / Carousel | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-RDSPT | DR2110 Rod support | 54883 | 1072 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SCBTR | DR2110 Screw Jack Cable Tension R/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SCBTL | DR2110 Screw Jack Cable Tension L/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SHAUR | DR2110 Sheave Assembly Upper Cab Side | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SHAUL | DR2110 Sheave Assembly Uppr Non Cab Side | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SHALR | DR2110 Sheave Assembly Lower Cab Side | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-SHALL | DR2110 Sheave Assembly Lowr Non Cab Side | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-CSHAR | DR2110 Carriage Sheave Assembly Cab Side | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-CSHAL | DR2110 Carriage Sheave Assy Non Cab Side | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-PBCBR | DR2110 Pullback Cable R/H | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-PBCBL | DR2110 Pullback Cable L/H | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-PDCBR | DR2110 Pulldown Cable R/H | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-PDCBL | DR2110 Pulldown Cable L/H | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TOWER-PWRHD | DR2110 Gearbox Power Head | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRR-ADJGR | DR2110 Track Adjuster Grease R/H | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-STRUCT-TKFRL-ADJGL | DR2110 Track Adjuster Grease L/H | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-STRUCT-CRANE | DR2110 Hiab Crane | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-STRUCT-CABIN-SEATS | DR2110 Operators Seat | 54883 | 16796 | 6800
CCK-MP-DRLL-DR2110-STRUCT-CABIN-ACCOM | DR2110 Air Conditioning Compressor | 54883 | 24193 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-COFAN-FCCAC | DR2110 Fan Cooling Charge Air Cooler | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-COFAN-FCCMA | DR2110 Fan Cooling Cooler Module Assy | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-ACONM | DR2110 Motor Hyd Air Con | 54883 | 24193 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MWINJ | DR2110 Motor Water Injection Pump | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MWINC | DR2110 Motor Winch | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MRTNR | DR2110 Hyd Motor Rotation CS | 54883 | 9679 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MRTNL | DR2110 Hyd Motor Rotation NCS | 54883 | 9682 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MSJTR | DR2110 Mtr 4.9 CID ScrewJack Tension CS | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MSJTL | DR2110 Mtr 4.9 CID ScrewJack Tension NCS | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MPRPR | DR2110 Motor Propel R/H | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MPRPL | DR2110 Motor Propel L/H | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MFCAC | DR2110 Motor Fan CAC Cooler | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDMOT-MFMCA | DR2110 Motor Fan Main Cooler Assy | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VWIBR | DR2110 Winch Valve Brake Hyd | 54883 | 54883 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVTNC | DR2110 Valve Tension Cable | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDPC | DR2110 Valve Drill/Propel Control | 54883 | 14230 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDVR | DR2110 Valve Diverter RH | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDVL | DR2110 Valve Diverter LH | 54883 | 14238 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVCNB | DR2110 Valve Counter Balance | 54883 | 14230 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVDCB | DR2110 Valve Dual Counter Balance | 54883 | 11134 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VV11S | DR2110 Valve Stacking 11 spool | 54907 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDVLV-VVS8S | DR2110 Valve Stacking 8 spool | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-CTCYR | DR2110 Cylinder Cable Tension R/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-CTCYL | DR2110 Cylinder Cable Tension L/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-FDCYR | DR2110 Cylinder Feed Hyd R/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-FDCYL | DR2110 Cylinder Feed Hyd L/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYRR | DR2110 Cylinder Jack Leg R/H/R | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYLR | DR2110 Cylinder Jack Leg L/H/R | 54883 | 11134 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYRF | DR2110 Cylinder Jack Leg R/H/F | 54883 | 9679 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-JCYLF | DR2110 Cylinder Jack Leg L/H/F | 54883 | 11134 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TACYR | DR2110 Cyl Tower Support Angle Lock R/H | 54883 | 16796 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TACYL | DR2110 Cyl Tower Support Angle Lock L/H | 54883 | 18195 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TLCYR | DR2110 Cylinder Tower locking R/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TLCYL | DR2110 Cylinder Tower locking L/H | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TRCYR | DR2110 Cylinder Tower Raise R/H | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HDCYL-TRCYL | DR2110 Cylinder Tower Raise L/H | 54883 | 1949 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HYDPP-PRHDL | DR2110 Pump Self Revers Power Head Lube | 54883 | 11133 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HYDPP-MNPP3 | DR2110 Pump Hydraulic triple | 54883 | 1945 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HYDPP-MNPP2 | "DR2110 Pump Hydraulic P7,9A CONT" | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-HYDPP-MNPP1 | "DR2110 Pump Hydraulic P7,9A CONT" | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-PMPDR-DRSHT | DR2110 Pump Drive Drive Shaft | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-HYDSYS-PMPDR | DR2110 Pump Drive Gearbox 3 Hole | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-COOLER | DR2110 Cooler Module Assembley | 54883 | 1945 | 6800
CCK-MP-DRLL-DR2110-AIRSYS-COMPR-COUPL | DR2110 Compressor Coupling Ringfeeder | 54883 | 1945 | 6800
CCK-MP-DRLL-DR2110-AIRSYS-COMPR | DR2110 Main Air Compressor | 54907 | 1945 | 6800
CCK-MP-DRLL-DR2110-TRAVEL-FDRRH | DR2110 Final Drive R/H | 54907 | 12643 | 6800
CCK-MP-DRLL-DR2110-TRAVEL-FDRLH | DR2110 Final Drive L/H | 54907 | 14238 | 6800
CCK-MP-DRLL-DR2110-ELCTLV-START-STMRH | DR2110 Starter Motor Engine Right | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ELCTLV-START-STMLH | DR2110 Starter Motor Engine Left | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ELCTLV-CHARG-ALTER | DR2110 Alternator 24V | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE-FUSYS-FULCO | DR2110 Fuel Cooler Engine | 54907 | 20613 | 6800
CCK-MP-DRLL-DR2110-ENGINE-FUSYS-FUINJ | DR2110 Fuel Injectors Engine | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE-FUSYS-FULPP | DR2110 Fuel Pump Engine | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE-INTEX-CACAS | DR2110 Charge Air Cooler | 54907 | 14238 | 6800
CCK-MP-DRLL-DR2110-ENGINE-INTEX-TBOP2 | DR2110 Turbocharger Engine | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE-INTEX-TBOP1 | DR2110 Turbocharger Engine | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE-COSYS-THERM | DR2110 Thermostats/Regulators Engine | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE-COSYS-WTRPP | DR2110 Water pump Engine | 54883 | 5228 | 6800
CCK-MP-DRLL-DR2110-ENGINE | DR2110 Engine Assembly | 54907 | 5228 | 6800
CCK-MP-DRLL-DR2110 | Lubrication & Mechanical Services DR2110 | 54781 | 54781 | 6800
CCK-MP-DRLL-DR2110 | Atlas Copco PV271HP Drill, DR2110 | 54907 | 54907 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-ARTNK | DR2104 Receiver Tank | 77631 | 4834 | 6800
CCK-MP-DRLL-DR2104-ELCTLV-HARNS-HARCO | Electrical Harness Control | 77589 | 77589 | 6800
CCK-MP-DRLL-DR2104-ADSYST-HARNC | ADS Harnesses & Connectors | 77589 | 14943 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 77589 | 14977 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 77589 | 14977 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSPR | ADS HazTech | 77589 | 14943 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSPO | ADS Global Positioning System | 77589 | 59109 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 77589 | 14977 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 77589 | 14943 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 77589 | 14977 | 6800
CCK-MP-DRLL-DR2104-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 77589 | 14943 | 6800
CCK-MP-DRLL-DR2104-ADSYST | Autonomous Drilling System | 77589 | 59109 | 6800
CCK-MP-DRLL-DR2104-ELCTLV-HARNS | Wiring Harness | 77589 | 77589 | 6800
CCK-MP-DRLL-DR2104-TRAVEL-TRKRH | DR2104 Track Assembly - Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-TRAVEL-TRKLH | DR2104 Track Assembly - Non Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-TRAVEL-SPRKR | DR2104 Sprocket - Cab Side | 77566 | 15268 | 6800
CCK-MP-DRLL-DR2104-TRAVEL-SPRKL | DR2104 Sprocket - Non Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RSF04 | DR2104 Roller Load Pos 4 S Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RSF03 | DR2104 Roller Load Pos 3 S Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RSF02 | DR2104 Roller Load Pos 2 S Flange - CS | 77566 | 9567 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RSF01 | DR2104 Roller Load Pos 1 S Flange - CS | 77566 | 9567 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF13 | DR2104 Roller Load Pos 13 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF12 | DR2104 Roller Load Pos 12 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF11 | DR2104 Roller Load Pos 11 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF10 | DR2104 Roller Load Pos 10 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF09 | DR2104 Roller Load Pos 9 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF08 | DR2104 Roller Load Pos 8 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF07 | DR2104 Roller Load Pos 7 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF06 | DR2104 Roller Load Pos 6 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-RDF05 | DR2104 Roller Load Pos 5 D Flange - CS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-IDLRH | DR2104 Idler Track - Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-CARRR | DR2104 Roller Carrier Rear - Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-CARRM | DR2104 Roller Carrier Middle - Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-CARRF | DR2104 Roller Carrier Front - Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR | DR2104 Track Frame - Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RSF04 | DR2104 Roller Load Pos 4 S Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RSF03 | DR2104 Roller Load Pos 3 S Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RSF02 | DR2104 Roller Load Pos 2 S Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RSF01 | DR2104 Roller Load Pos 1 S Flange - NCS | 77566 | 9567 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF13 | DR2104 Roller Load Pos 13 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF12 | DR2104 Roller Load Pos 12 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF11 | DR2104 Roller Load Pos 11 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF10 | DR2104 Roller Load Pos 10 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF09 | DR2104 Roller Load Pos 9 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF08 | DR2104 Roller Load Pos 8 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF07 | DR2104 Roller Load Pos 7 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF06 | DR2104 Roller Load Pos 6 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-RDF05 | DR2104 Roller Load Pos 5 D Flange - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-IDLLH | DR2104 Idler Track - Non Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-CARLR | DR2104 Roller Carrier Rear - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-CARLM | DR2104 Roller Carrier Middle - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-CARLF | DR2104 Roller Carrier Front - NCS | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL | DR2104 Track Frame - Non Cab Side | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-AFRME | DR2104 Tower A Frame | 77566 | 24121 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-EARCS-BDVVE | DR2104 Blowdown Valve | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-EARCS-ACTBD | DR2104 Actuator Blowdown Valve | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-EARCS-BFVVE | DR2104 Comp Butterfly Valve | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-EARCS-ACTBV | DR2104 Actuator Butterfly Valve | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-FUSYS-FULTK | Fuel Tank Mounting Bolts | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS | DR2104 Hyraulic Tune | 77566 | 10891 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER | DR2104 Tower | 77566 | 34508 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-COMPR-ARTNK | DR2104 Compressor Safety Valve | 77566 | 14314 | 7400
CCK-MP-DRLL-DR2104-FRSUPP | DR2104 Fire Suppression System | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-DSTSUP-WTRPP | DR2104 Dynaset Water Pump | 77566 | 6258 | 6800
CCK-MP-DRLL-DR2104-GRSYST-RTLPP | DR2104 Rod Thread lube Pump | 77566 | 3376 | 6800
CCK-MP-DRLL-DR2104-GRSYST-ALBPP | DR2104 Auto lube Pump | 77566 | 11637 | 6800
CCK-MP-DRLL-DR2104-LUBSYS-DHDPP | DR2104 DHD Oil Pump | 77566 | 53446 | 6800
CCK-MP-DRLL-DR2104-STRUCT-WINCH-WINRP | DR2104 Winch Rope | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-STRUCT-WINCH-WINSH | DR2104 Winch Sheaves | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-STRUCT-WINCH | DR2104 Winch Assembly | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-STRUCT-UNDER-YKOSC | DR2104 Yoke Oscillation | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-BOFKA | DR2104 Breakout Fork Sliding Assembly | 77566 | 34520 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-BOWRH | DR2104 Breakout Wrench Assy | 77566 | 2314 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-CARAS | DR2104 Rod Changer / Carousel | 77566 | 4836 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-RDSPT | DR2104 Rod support | 77566 | 4898 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-SCBTR | DR2104 Screw Jack Cable Tension R/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-SCBTL | DR2104 Screw Jack Cable Tension L/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-SHAUR | DR2104 Sheave Assembly Upper R/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-SHAUL | DR2104 Sheave Assembly Upper L/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-SHALR | DR2104 Sheave Assembly Lower R/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-SHALL | DR2104 Sheave Assembly Lower L/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-CSHAR | DR2104 Carriage Sheave Assembly R/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-CSHAL | DR2104 Carriage Sheave Assembly L/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-PBCBR | DR2104 Pullback Cable R/H | 77566 | 10789 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-PBCBL | DR2104 Pullback Cable L/H | 77566 | 10808 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-PDCBR | DR2104 Pulldown Cable R/H | 77566 | 10808 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-PDCBL | DR2104 Pulldown Cable L/H | 77566 | 10808 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TOWER-PWRHD | DR2104 Gearbox Power Head | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRR-ADJGR | DR2104 Track Adjuster Grease R/H | 77566 | 51193 | 6800
CCK-MP-DRLL-DR2104-STRUCT-TKFRL-ADJGL | DR2104 Track Adjuster Grease L/H | 77566 | 51193 | 6800
CCK-MP-DRLL-DR2104-STRUCT-CRANE | DR2104 Hiab Crane | 77566 | 16712 | 6800
CCK-MP-DRLL-DR2104-STRUCT-CABIN-SEATS | DR2104 Operators Seat | 77566 | 9131 | 6800
CCK-MP-DRLL-DR2104-STRUCT-CABIN-ACCOM | DR2104 Air Conditioning Compressor | 77566 | 9567 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-COFAN-FCCAC | DR2104 Fan Cooling Charge Air Cooler | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-COFAN-FCCMA | DR2104 Fan Cooling Cooler Module Assy | 77566 | 34520 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-ACONM | DR2104 Motor Hyd Air Con | 77566 | 38979 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MWINJ | DR2104 Motor Water Injection Pump | 77566 | 60095 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MWINC | DR2104 Motor Winch | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MRTNR | DR2104 Hyd Motor Rotation CS | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MRTNL | DR2104 Hyd Motor Rotation NCS | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MSJTR | DR2104 Mtr 4.9 CID ScrewJack Tension CS | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MSJTL | DR2104 Mtr 4.9 CID ScrewJack Tension NCS | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MPRPR | DR2104 Motor Propel R/H | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MPRPL | DR2104 Motor Propel L/H | 77566 | 15348 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MFCAC | DR2104 Motor Fan CAC Cooler | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDMOT-MFMCA | DR2104 Motor Fan Main Cooler Assy | 77566 | 13825 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VWIBR | DR2104 Winch Valve Brake Hyd | 77566 | 77566 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VVTNC | DR2104 Valve Tension Cable | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VVDPC | DR2104 Valve Drill/Propel Control | 77566 | 28826 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VVDVR | DR2104 Valve Diverter RH | 77566 | 6442 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VVDVL | DR2104 Valve Diverter LH | 77566 | 6442 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VVCNB | DR2104 Valve Counter Balance | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VVDCB | DR2104 Valve Dual Counter Balance | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VV11S | DR2104 Valve Stacking 11 spool | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDVLV-VVS8S | DR2104 Valve Stacking 8 spool | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-CTCYR | DR2104 Cylinder Cable Tension R/H | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-CTCYL | DR2104 Cylinder Cable Tension L/H | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-FDCYR | DR2104 Cylinder Feed Hyd R/H | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-FDCYL | DR2104 Cylinder Feed Hyd L/H | 77566 | 549 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-JCYRR | DR2104 Cylinder Jack Leg R/H/R | 77566 | 4898 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-JCYLR | DR2104 Cylinder Jack Leg L/H/R | 77566 | 14087 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-JCYRF | DR2104 Cylinder Jack Leg R/H/F | 77566 | 4836 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-JCYLF | DR2104 Cylinder Jack Leg L/H/F | 77566 | 14087 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-TACYR | DR2104 Cyl Tower Support Angle Lock R/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-TACYL | DR2104 Cyl Tower Support Angle Lock L/H | 77566 | 14977 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-TLCYR | DR2104 Cylinder Tower locking R/H | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-TLCYL | DR2104 Cylinder Tower locking L/H | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-TRCYR | DR2104 Cylinder Tower Raise R/H | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HDCYL-TRCYL | DR2104 Cylinder Tower Raise L/H | 77566 | 4898 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HYDPP-PRHDL | DR2104 Pump Self Revers Power Head Lube | 77566 | 4834 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HYDPP-MNPP3 | DR2104 Pump Hydraulic triple | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HYDPP-MNPP2 | DR2104 Pump Hydraulic P7,9A CONT | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-HYDPP-MNPP1 | DR2104 Pump Hydraulic P7,9A CONT | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-PMPDR-DRSHT | DR2104 Pump Drive Drive Shaft | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-HYDSYS-PMPDR | DR2104 Pump Drive Gearbox 3 Hole | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-COOLER | DR2104 Cooler Module Assembley | 77566 | 1296 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-COMPR-COUPL | DR2104 Compressor Coupling Ringfeeder | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-AIRSYS-COMPR | DR2104 Main Air Compressor | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-TRAVEL-FDRRH | DR2104 Final Drive R/H | 77589 | 10168 | 6800
CCK-MP-DRLL-DR2104-TRAVEL-FDRLH | DR2104 Final Drive L/H | 77589 | 15348 | 6800
CCK-MP-DRLL-DR2104-ELCTLV-START-STMRH | DR2104 Starter Motor Engine Right | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ELCTLV-START-STMLH | DR2104 Starter Motor Engine Left | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ELCTLV-CHARG-ALTER | DR2104 Alternator 24V | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-FUSYS-FULCO | DR2104 Fuel Cooler Engine | 77589 | 24944 | 6800
CCK-MP-DRLL-DR2104-ENGINE-FUSYS-FUINJ | DR2104 Fuel Injectors Engine | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-FUSYS-FULPP | DR2104 Fuel Pump Engine | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-INTEX-CACAS | DR2104 Charge Air Cooler | 77589 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-INTEX-TBOP2 | DR2104 Turbocharger Engine | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-INTEX-TBOP1 | DR2104 Turbocharger Engine | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-COSYS-THERM | DR2104 Thermostats/Regulators Engine | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE-COSYS-WTRPP | DR2104 Water pump Engine | 77566 | 3577 | 6800
CCK-MP-DRLL-DR2104-ENGINE | DR2104 Engine Assembly | 77589 | 3577 | 6800
CCK-MP-DRLL-DR2104 | Lubrication & Mechanical Services DR2104 | 77589 | 77589 | 6800
CCK-MP-DRLL-DR2104 | Atlas Copco PV271HP Drill, DR2104 | 77589 | 77589 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-ARTNK | DR055 Receiver Tank | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-HARNS-HARCO | Electrical Harness Control | 64593 | 64593 | 6800
CCK-MP-DRLL-DR055 -ADSYST-HARNC | ADS Harnesses & Connectors | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSPR-LIDAR | ADS LiDAR System | 64593 | 14276 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSPR | ADS HazTech | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSPO | ADS Global Positioning System | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ADSYST | Autonomous Drilling System | 64593 | 35395 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-HARNS | Wiring Harness | 64593 | 64593 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-AFRME | DR055 Tower A Frame | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-EARCS-BDVVE | DR055 Blowdown Valve | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-EARCS-ACTBD | DR055 Actuator Blowdown Valve | 64569 | 10155 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-EARCS-BFVVE | DR055 Comp Butterfly Valve | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-EARCS-ACTBV | DR055 Actuator Butterfly Valve | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-TRKRH | DR055 Track Assembly - CS | 64569 | 11474 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-TRKLH | DR055 Track Assembly - NCS | 64569 | 6462 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-TRBKR | DR055 Travel Brake R/H | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-TRBKL | DR055 Travel Brake L/H | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-SPRKR | DR055 Sprocket - CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-SPRKL | DR055 Sprocket - NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -TRAVEL | DR055 Travel System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-WINCH-WIHLF | DR055 Winch System Hose Lines Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-UNDER | DR055 Undercarriage | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER | DR055 Tower | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 64569 | 14276 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 64569 | 14276 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 64569 | 14276 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF13 | Roller Load Pos 13 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF12 | Roller Load Pos 12 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF11 | Roller Load Pos 11 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF10 | Roller Load Pos 10 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF09 | Roller Load Pos 9 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF08 | Roller Load Pos 8 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF07 | Roller Load Pos 7 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF06 | Roller Load Pos 6 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-RDF05 | Roller Load Pos 5 Double Flange CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-IDLRH | DR055 Idler Track CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-CARRR | DR055 Roller Carrier Rear - CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-CARRM | DR055 Roller Carrier Middle - CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-CARRF | DR055 Roller Carrier Front - CS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR | DR055 Track Frame CS | 64569 | 1827 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF13 | Roller Load Pos 13 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF12 | Roller Load Pos 12 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF11 | Roller Load Pos 11 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF10 | Roller Load Pos 10 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF09 | Roller Load Pos 9 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF08 | Roller Load Pos 8 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF07 | Roller Load Pos 7 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF06 | Roller Load Pos 6 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-RDF05 | Roller Load Pos 5 Double Flange NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-IDLLH | DR055 Idler Track - NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-CARLR | DR055 Roller Carrier Rear - NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-CARLM | DR055 Roller Carrier Middle - NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-CARLF | DR055 Roller Carrier Front - NCS | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL | DR055 Track Frame - NCS | 64569 | 1827 | 6800
CCK-MP-DRLL-DR055 -STRUCT-STLAD-SLFXD | DR055 Fixed Steps and Ladders | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-STLAD-SLAUT | DR055 Automatic Access Systems | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-STLAD | DR055 Steps and ladders | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-PLHAN | DR055 Platforms and Hand Rails | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-DRSTR-SHSUB | DR055 ShockSub Foremost | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-DRSTR | DR055 Drill String | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-SBELT | DR055 Seat belt | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-GLASS | DR055 Glass | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-CABPR | DR055 Cabin Pressurisation System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-CABES | DR055 Cabin Entertainment System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-CABCO | DR055 Cabin Controls | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-AIRCN | DR055 Air Conditioning System | 64569 | 13121 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN | DR055 Operators Cabin | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT | DR055 Structure | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -MANGMT-UMMMC | DR055 Mine Monitoring and Control | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -MANGMT-UMENG | DR055 Engine Management System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -MANGMT-UMRIG | DR055 Board Control System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -MANGMT | DR055 Unit Management | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -LUBSYS-DHTNK | DR055 DHD Reservoir | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -LUBSYS-DHTMR | DR055 DHD Timer | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -LUBSYS-DHHLF | DR055 DHD Hose Lines & Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -LUBSYS-DHELC | DR055 DHD Electrical | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -LUBSYS | DR055 Lubrication System DHD | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HYDPP | DR055 Pumps Hydraulic | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV | DR055 Valves Hydraulic | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDTNK | DR055 Tank Hydraulic | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT | DR055 Motors Hydraulic | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDHLF | Hydraulic System Hose Lines Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-RSSCY | DR055 Cylinder Swing Rod Support | 64569 | 15370 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-RSCCY | DR055 Cylinder Rod Support Clamp | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-DSRCY | DR055 Cylinder Dust Skirt Raise | 64569 | 17524 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-CSCYU | DR055 Cylinder Carousel Swing Upper | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-CSCYL | DR055 Cylinder Carousel Swing Lower | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-CRTCY | Cylinder Carousel Rotation indexing | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-BWSCY | DR055 Cylinder Swing Breakout Wrench | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-BWRCY | DR055 Cylinder Rotate Breakout Wrench | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-BWCCY | DR055 Cylinder Clamp Breakout Wrench | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-BKOCY | DR055 Cylinder Breakout Fork | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL | DR055 Cylinders Hydraulic | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-COFAN | DR055 Fan Cooling | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -HYDSYS | DR055 Hydraulic Systems | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-RTTNK | DR055 Rod Thread Lube Reservoir | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-RTINJ | DR055 Rod Thread Grease Injector | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-RTHLF | Rod Thread Lube Hoses Line Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-RTELC | DR055 Rod Thread Lube Electrical | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-GRTNK | DR055 Auto Lube Reservoir | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-GRINJ | DR055 Auto Lube Injectors | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-ALHLF | DR055 Auto Lube Hoses Line Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-ALELC | DR055 Auto Lube Electrical | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST-ALCON | DR055 Auto Lube Controller | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -GRSYST | DR055 Grease lubrication System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -FRSUPP-FSMAN-EXTIN | DR055 Hand Held Fire Extinguisher | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -FRSUPP-FSMAN | DR055 Fire Suppression Manual | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -FRSUPP-FSAUT-FSHLF | DR055 Fire Sup Hose Lines Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -FRSUPP-FSAUT-FFOAM | DR055 Fire Suppression Foam | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -FRSUPP-FSAUT | Fire Suppression Automatic | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -FRSUPP-FSALM | Fire System Alarm | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -FRSUPP | Fire Suppression System | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -ENGINE-LUBSY | Engine Lubrication System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-INTEX-EXHST | Exhaust System Engine | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-INTEX | Engine Intake and Exhaust System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-FUSYS-FULTK | Fuel Tank Engine | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-FUSYS-FUHLF | Fuel System Hoses/Lines and Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-FUSYS | Engine Fuel System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-COSYS-CSHLF | Cooling System Hoses/Lines and Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ENGINE-COSYS | Engine Cooling System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-START | Electrical Starting System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-LIGHT | Lighting Low Voltage | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-CONTL | Electrical Controls Low Voltage | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-CHARG-BATTY | Batteries Engine | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-CHARG | Charging System | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -ELCTLV | Electrical System Low Voltage 24V | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -DSTSUP-WTTNK | Water Tank | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -DSTSUP-WTHLF | Water Inj System Hose Lines Fittings | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -DSTSUP-DSTSK | Dust Skirt | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -DSTSUP | Dust Suppresion | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -COOLER-RADTR | Radiator Core | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -COOLER-HDOCO | Hydraulic Oil Cooler Core | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -COOLER-COOCO | Compressor Oil Cooler Core | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -COMMUN-RADIO | Two Way Radio | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -COMMUN | Communications | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-COMPR-PNHLF | Pneumatic System Hoses Lines Fittings | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -AIRSYS | Air Systems | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -DSTSUP-WTRPP | DR055 Pump Water Injection | 64569 | 14276 | 6800
CCK-MP-DRLL-DR055 -GRSYST-RTLPP | DR055 Rod Thread lube Pump | 64569 | 6663 | 6800
CCK-MP-DRLL-DR055 -GRSYST-ALBPP | DR055 Auto lube Pump | 64569 | 11474 | 6800
CCK-MP-DRLL-DR055 -LUBSYS-DHDPP | DR055 DHD Oil Pump | 64569 | 55157 | 6800
CCK-MP-DRLL-DR055 -STRUCT-WINCH-WINRP | DR055 Winch Rope | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-WINCH-WINSH | DR055 Winch Sheaves | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-WINCH | DR055 Winch Assembly | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -STRUCT-UNDER-YKOSC | DR055 Yoke Oscillation | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-BOFKA | DR055 Breakout Fork Sliding Assembly | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-BOWRH | DR055 Breakout Wrench Assy | 64569 | 3965 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-CARAS | DR055 Rod Changer / Carousel | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-RDSPT | DR055 Rod support | 64569 | 13121 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-SCBTR | DR055 Screw Jack Cable Tension R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-SCBTL | DR055 Screw Jack Cable Tension L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-SHAUR | DR055 Sheave Assembly Upper R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-SHAUL | DR055 Sheave Assembly Upper L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-SHALR | DR055 Sheave Assembly Lower R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-SHALL | DR055 Sheave Assembly Lower L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-CSHAR | DR055 Carriage Sheave Assembly R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-CSHAL | DR055 Carriage Sheave Assembly L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-PBCBR | DR055 Pullback Cable R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-PBCBL | DR055 Pullback Cable L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-PDCBR | DR055 Pulldown Cable R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-PDCBL | DR055 Pulldown Cable L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TOWER-PWRHD | DR055 Gearbox Power Head | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRR-ADJGR | DR055 Track Adjuster Grease R/H | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-TKFRL-ADJGL | DR055 Track Adjuster Grease L/H | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CRANE | DR055 Hiab Crane | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-SEATS | DR055 Operators Seat | 64569 | 13103 | 6800
CCK-MP-DRLL-DR055 -STRUCT-CABIN-ACCOM | DR055 Air Conditioning Compressor | 64569 | 38112 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-COFAN-FCCAC | DR055 Fan Cooling Charge Air Cooler | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-COFAN-FCCMA | DR055 Fan Cooling Cooler Module Assy | 64593 | 3965 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-ACONM | DR055 Motor Hyd Air Con | 64569 | 35839 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MWINJ | DR055 Motor Water Injection Pump | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MWINC | DR055 Motor Winch | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MRTNR | DR055 Motor Rotation R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MRTNL | DR055 Motor Rotation L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MSJTR | DR055 Mtr 4.9 CID ScrewJack Tension R/H | 64569 | 13121 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MSJTL | DR055 Mtr 4.9 CID ScrewJack Tension L/H | 64569 | 13121 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MPRPR | DR055 Motor Propel R/H | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MPRPL | DR055 Motor Propel L/H | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MFCAC | DR055 Motor Fan CAC Cooler | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDMOT-MFMCA | DR055 Motor Fan Main Cooler Assy | 64593 | 3965 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VWIBR | DR055 Winch Valve Brake Hyd | 64569 | 64569 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVTNC | DR055 Valve Tension Cable | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDPC | DR055 Valve Drill/Propel Control | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDVR | DR055 Valve Diverter RH | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDVL | DR055 Valve Diverter LH | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVCNB | DR055 Valve Counter Balance | 64569 | 9560 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVDCB | DR055 Valve Dual Counter Balance | 64569 | 13103 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VV11S | DR055 Valve Stacking 11 spool | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDVLV-VVS8S | DR055 Valve Stacking 8 Spool | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-CTCYR | DR055 Cylinder Cable Tension R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-CTCYL | DR055 Cylinder Cable Tension L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-FDCYR | DR055 Cylinder Feed Hyd R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-FDCYL | DR055 Cylinder Feed Hyd L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYRR | DR055 Cylinder Jack Leg R/H/R | 64569 | 9560 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYLR | DR055 Cylinder Jack Leg L/H/R | 64569 | 11474 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYRF | DR055 Cylinder Jack Leg R/H/F | 64569 | 7492 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-JCYLF | DR055 Cylinder Jack Leg L/H/F | 64569 | 710 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TACYR | DR055 Cyl Tower Support Angle Lock R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TACYL | DR055 Cyl Tower Support Angle Lock L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TLCYR | DR055 Cylinder Tower locking R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TLCYL | DR055 Cylinder Tower locking L/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYR | DR055 Cylinder Tower Raise R/H | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HDCYL-TRCYL | DR055 Cylinder Tower Raise L/H | 64569 | 13121 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HYDPP-PRHDL | DR055 Pump Self Revers Power Head Lube | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HYDPP-MNPP3 | DR055 Pump Hydraulic triple | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HYDPP-MNPP2 | DR055 Pump Hydraulic P7,9A CONT | 64569 | 5664 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-HYDPP-MNPP1 | DR055 Pump Hydraulic P7,9A CONT | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-PMPDR-DRSHT | DR055 Pump Drive Drive Shaft | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -HYDSYS-PMPDR | DR055 Pump Drive Gearbox 3 Hole | 64569 | 10155 | 6800
CCK-MP-DRLL-DR055 -COOLER | DR055 Cooler Module Assembley | 64569 | 3965 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-COMPR-COUPL | DR055 Compressor Coupling Ringfeeder | 64569 | 3533 | 6800
CCK-MP-DRLL-DR055 -AIRSYS-COMPR | DR055 Main Air Compressor | 64569 | 10155 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-FDRRH | DR055 Final Drive R/H | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -TRAVEL-FDRLH | DR055 Final Drive L/H | 64569 | 23653 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-START-STMRH | DR055 Starter Motor Engine Right | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-START-STMLH | DR055 Starter Motor Engine Left | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ELCTLV-CHARG-ALTER | DR055 Alternator 24V | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE-FUSYS-FULCO | DR055 Fuel Cooler Engine | 64569 | 3965 | 6800
CCK-MP-DRLL-DR055 -ENGINE-FUSYS-FUINJ | DR055 Fuel Injectors Engine | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE-FUSYS-FULPP | DR055 Fuel Pump Engine | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE-INTEX-CACAS | DR055 Charge Air Cooler | 64569 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE-INTEX-TBOP2 | DR055 Turbocharger Engine | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE-INTEX-TBOP1 | DR055 Turbocharger Engine | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE-COSYS-THERM | DR055 Thermostats/Regulators Engine | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE-COSYS-WTRPP | DR055 Water pump Engine | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 -ENGINE | DR055 Engine Assembly | 64593 | 10155 | 6800
CCK-MP-DRLL-DR055 | Atlas Copco PV271HP Drill, DR055 | 64593 | 64593 | 6800
CCK-MP-EXCV-EX7145-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH Lift | 7526 | 0 | 6200
CCK-MP-HAUL-DT5490-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-TRAYS | Tray | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-CABIN | Operators Cabin | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 3000
CCK-MP-HAUL-DT5490-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 3000
CCK-MP-HAUL-DT5490 | DT5490 Liebherr T264 OHT | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-TRAYS | Tray | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-CABIN | Operators Cabin | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 3000
CCK-MP-HAUL-DT5489-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 3000
CCK-MP-HAUL-DT5489 | DT5489 Liebherr T264 OHT | 1 | 1 | 3000
CCK-MP-HAUL-DT5318-BRKSYS-BACCM | Accum Brake Rear | 21163 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BACCM | Accum Brake Front RH | 21163 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BACCM | Accum Brake Front LH | 21163 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STACC | Accum Steer Rear | 21163 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STACC | Accum Steer Middle | 21163 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STACC | Accum Steer Front | 21163 | 21163 | 7400
CCK-MP-HAUL-DT5318-AHSYST-HACAB-HATRU | Harness AHS to Truck | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ELCTLV-HARNS | Electrical Harness | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ELCTLV-LIGHT | DT5318 Lighting Low Voltage | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 44641 | 44641 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 44641 | 44641 | 7400
CCK-MP-HAUL-DT5318-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-TRNSYS-TRQUE | Torque Converter | 45240 | 14125 | 7400
CCK-MP-HAUL-DT5318-TRNSYS-TRPMP-TMCPP | Pump Transmission | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-TRNSYS-TROLC | Oil Cooler Transmission | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-TRNSYS-TRANS | Transmission | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRUCT-TRAYS | Tray | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-SUSPN | Suspension | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CHASS-LNKLU | Upper Tag Link | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CHASS-LNKLL | Lower Tag Link | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CHASS | Chassis | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-SEATS | Operators Seat | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-SBELT | Seat Belt | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-ELECT | Cabin Electrical System | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-AIRCN | Air Con Lines | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-AIRCN | Air Con Condenser | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 45240 | 27496 | 7400
CCK-MP-HAUL-DT5318-STRUCT-CABIN | Operators Cabin | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STOCO | Steering Oil Cooler | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STLTR-STBST | Ball Studs | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STLTR | Steering Linkages and Tie Rods | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STHMU | Steering HMU | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STHLF-STRHO | Steering System Hoses | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STCON-STWHL | Steering Wheel | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STCON-STCOL | Steering Column | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STACC-SACCR | Accumulator Steering Rear | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STACC-SACCM | Accumulator Steering Middle | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-STRSYS-STACC-SACCF | Accumulator Steering Front | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-MANGMT-UMTRN | Power Train Management System | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-MANGMT-UMMMC | Mine Monitoring and Control | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-MANGMT-UMENG | Engine Management System | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-TOWPP | Pump Towing | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-HOVLV | Valve Hoist | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-HOPMP | Pump Hoist & Brake | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-HDTNK | Tank Hydraulic | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-HDOCO | Oil Cooler Hydraulic | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-HYDSYS | Hydraulic System | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-GRSYST-GRTNK | Auto Lube Pump | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-GRSYST-GRINJ | Auto Lube Injectors | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-GRSYST-ALBPP | Auto Lube Pump | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-FRSUPP | Fire Suppression System | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-DRSHT | Transmission Drive Shaft | 45240 | 2794 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 45240 | 25711 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-DIFFL | Differential | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-ENGINE-PMPDR | Pump Drive | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ENGINE-LUBSY-OILPP | Oil Pump Engine | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ENGINE-INTEX-EXHST | Exhaust System | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-INTEX-AFTER | Aftercooler | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-FUSYS-FULIP | Fuel Injector Pump | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ENGINE-FUSYS-FUINJ | Fuel Injectors | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ENGINE-COSYS-WTRPP | Water Pump Engine | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE-COSYS-RADTR | Radiator Coolant | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-ENGINE-COSYS-RADTR | Radiator Engine | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ENGINE | Engine Assembly Caterpillar C175-16 | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ELCTLV-START-STMUP | Starter Motor Upper | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ELCTLV-START-STMLO | Starter Motor Lower | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-ELCTLV-CHARG-BATTY | Batteries | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-ELCTLV-CHARG-ALTER | Alternator 24V | 45240 | 6204 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-TCVLV | Valve Traction Control | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 45240 | 9085 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-PRKPP | Pump Park Brake Release | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-MERTR | Mechanical Retarder | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-HYFPP | Pump Brake Cooling | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BRVTR | Valve Brake Treadle | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BRVLV | Valve Brake | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 45240 | 21163 | 7400
CCK-MP-HAUL-DT5318 | DT5318 Lubrication & Mechanical Services | 44747 | 44747 | 7400
CCK-MP-HAUL-DT5318 | Caterpillar 793F Haul Truck DT5318 | 45240 | 45240 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STACC | Accum Steer Rear | 20480 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STACC | Accum Steer Middle | 20480 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STACC | Accum Steer Front | 20480 | 20480 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BACCM | Accum Brake Rear | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BACCM | Accum Brake Front RH | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BACCM | Accum Brake Front LH | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-AHSYST-HACAB-HATRU | Harness AHS to Truck | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ELCTLV-HARNS | Electrical Harness | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ELCTLV-LIGHT | DT5317 Lighting Low Voltage | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 44872 | 44872 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 44872 | 44872 | 7400
CCK-MP-HAUL-DT5317-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-TRNSYS-TRQUE | Torque Converter | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-TRNSYS-TRPMP-TMCPP | Pump Transmission | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-TRNSYS-TROLC | Oil Cooler Transmission | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-TRNSYS-TRANS | Transmission | 45576 | 9163 | 7400
CCK-MP-HAUL-DT5317-STRUCT-TRAYS | Tray | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 45576 | 2004 | 7400
CCK-MP-HAUL-DT5317-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRUCT-SUSPN | Suspension | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CHASS-LNKLU | Upper Tag Link | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CHASS-LNKLL | Lower Tag Link | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CHASS | Chassis | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-SEATS | Operators Seat | 45576 | 12321 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-SBELT | Seat Belt | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-ELECT | Cabin Electrical System | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-AIRCN | Air Con Lines | 45576 | 32701 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-AIRCN | Air Con Condenser | 45576 | 32701 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 45576 | 32701 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-CABIN | Operators Cabin | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 45576 | 2004 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 45576 | 4261 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STOCO | Steering Oil Cooler | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STLTR-STBST | Ball Studs | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STLTR | Steering Linkages and Tie Rods | 45576 | 10024 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STHMU | Steering HMU | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STHLF-STRHO | Steering System Hoses | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STCON-STWHL | Steering Wheel | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STCON-STCOL | Steering Column | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STACC-SACCR | Accumulator Steering Rear | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STACC-SACCM | Accumulator Steering Middle | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-STRSYS-STACC-SACCF | Accumulator Steering Front | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-MANGMT-UMTRN | Power Train Management System | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-MANGMT-UMMMC | Mine Monitoring and Control | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-MANGMT-UMENG | Engine Management System | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-TOWPP | Pump Towing | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-HOVLV | Valve Hoist | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-HOPMP | Pump Hoist & Brake | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-HDTNK | Tank Hydraulic | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-HDOCO | Oil Cooler Hydraulic | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 45556 | 20460 | 7400
CCK-MP-HAUL-DT5317-HYDSYS | Hydraulic System | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-GRSYST-GRTNK | Auto Lube Pump | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-GRSYST-GRINJ | Auto Lube Injectors | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-GRSYST-ALBPP | Auto Lube Pump | 45576 | 12321 | 7400
CCK-MP-HAUL-DT5317-FRSUPP | Fire Suppression System | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-DRSHT | Transmission Drive Shaft | 45576 | 9163 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-DIFFL | Differential | 45576 | 9163 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-ENGINE-PMPDR | Pump Drive | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-LUBSY-OILPP | Oil Pump Engine | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-INTEX-EXHST | Exhaust System | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-INTEX-AFTER | Aftercooler | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-FUSYS-FULIP | Fuel Injector Pump | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-ENGINE-FUSYS-FUINJ | Fuel Injectors | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-ENGINE-COSYS-WTRPP | Water Pump Engine | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE-COSYS-RADTR | Radiator Coolant | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-COSYS-RADTR | Radiator Engine | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-ENGINE | Engine Assembly Caterpillar C175-16 | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-ELCTLV-START-STMUP | Starter Motor Upper | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-ELCTLV-START-STMLO | Starter Motor Lower | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-ELCTLV-CHARG-BATTY | Batteries | 45576 | 18109 | 7400
CCK-MP-HAUL-DT5317-ELCTLV-CHARG-ALTER | Alternator 24V | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-TCVLV | Valve Traction Control | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 45576 | 8696 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-PRKPP | Pump Park Brake Release | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-MERTR | Mechanical Retarder | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-HYFPP | Pump Brake Cooling | 45576 | 20480 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BRVTR | Valve Brake Treadle | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BRVLV | Valve Brake | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317 | DT5317 Lubrication & Mechanical Services | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5317 | Caterpillar 793F Haul Truck DT5317 | 45576 | 45576 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STACC | Accum Steer Rear | 19566 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STACC | Accum Steer Middle | 19566 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STACC | Accum Steer Front | 19566 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BACCM | Accum Brake Rear | 19566 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BACCM | Accum Brake Front RH | 19566 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BACCM | Accum Brake Front LH | 19566 | 19566 | 7400
CCK-MP-HAUL-DT5316-AHSYST-HACAB-HATRU | Harness AHS to Truck | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ELCTLV-HARNS | Electrical Harness | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ELCTLV-LIGHT | DT5316 Lighting Low Voltage | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 44790 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 44790 | 19566 | 7400
CCK-MP-HAUL-DT5316-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-TRNSYS-TRQUE | Torque Converter | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-TRNSYS-TRPMP-TMCPP | Pump Transmission | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-TRNSYS-TROLC | Oil Cooler Transmission | 45108 | 25317 | 7400
CCK-MP-HAUL-DT5316-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-TRNSYS-TRANS | Transmission | 45108 | 15135 | 7400
CCK-MP-HAUL-DT5316-STRUCT-TRAYS | Tray | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 45108 | 24198 | 7400
CCK-MP-HAUL-DT5316-STRUCT-SUSPN | Suspension | 45108 | 35673 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CHASS-LNKLU | Upper Tag Link | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CHASS-LNKLL | Lower Tag Link | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CHASS | Chassis | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-SEATS | Operators Seat | 45108 | 10479 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-SBELT | Seat Belt | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-ELECT | Cabin Electrical System | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-AIRCN | Air Con Lines | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-AIRCN | Air Con Condenser | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 45108 | 30007 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRUCT-CABIN | Operators Cabin | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 45108 | 7788 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 45108 | 7788 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STOCO | Steering Oil Cooler | 45108 | 7861 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STLTR-STBST | Ball Studs | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STLTR | Steering Linkages and Tie Rods | 45108 | 30055 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STHMU | Steering HMU | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STHLF-STRHO | Steering System Hoses | 45108 | 7861 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STCON-STWHL | Steering Wheel | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STCON-STCOL | Steering Column | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STACC-SACCR | Accumulator Steering Rear | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STACC-SACCM | Accumulator Steering Middle | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-STRSYS-STACC-SACCF | Accumulator Steering Front | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-MANGMT-UMTRN | Power Train Management System | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-MANGMT-UMMMC | Mine Monitoring and Control | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-MANGMT-UMENG | Engine Management System | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-TOWPP | Pump Towing | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-HOVLV | Valve Hoist | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-HOPMP | Pump Hoist & Brake | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 45108 | 7788 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-HDTNK | Tank Hydraulic | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-HDOCO | Oil Cooler Hydraulic | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-HYDSYS | Hydraulic System | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-GRSYST-GRTNK | Auto Lube Pump | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-GRSYST-GRINJ | Auto Lube Injectors | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-GRSYST-ALBPP | Auto Lube Pump | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FRSUPP | Fire Suppression System | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 45108 | 926 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 45108 | 1608 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-DRSHT | Transmission Drive Shaft | 45108 | 5582 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-DIFFL | Differential | 45108 | 7861 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 45108 | 27566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-PMPDR | Pump Drive | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-LUBSY-OILPP | Oil Pump Engine | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-INTEX-EXHST | Exhaust System | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ENGINE-INTEX-AFTER | Aftercooler | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ENGINE-FUSYS-FULIP | Fuel Injector Pump | 45108 | 7861 | 7400
CCK-MP-HAUL-DT5316-ENGINE-FUSYS-FUINJ | Fuel Injectors | 45108 | 7788 | 7400
CCK-MP-HAUL-DT5316-ENGINE-COSYS-WTRPP | Water Pump Engine | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 45108 | 21322 | 7400
CCK-MP-HAUL-DT5316-ENGINE-COSYS-RADTR | Radiator Coolant | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-COSYS-RADTR | Radiator Engine | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 45108 | 3285 | 7400
CCK-MP-HAUL-DT5316-ENGINE | Engine Assembly Caterpillar C175-16 | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-ELCTLV-START-STMUP | Starter Motor Upper | 45108 | 7861 | 7400
CCK-MP-HAUL-DT5316-ELCTLV-START-STMLO | Starter Motor Lower | 45108 | 7861 | 7400
CCK-MP-HAUL-DT5316-ELCTLV-CHARG-BATTY | Batteries | 45108 | 21322 | 7400
CCK-MP-HAUL-DT5316-ELCTLV-CHARG-ALTER | Alternator 24V | 45108 | 7861 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-TCVLV | Valve Traction Control | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 45108 | 7788 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 45108 | 7788 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-PRKPP | Pump Park Brake Release | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-MERTR | Mechanical Retarder | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-HYFPP | Pump Brake Cooling | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BRVTR | Valve Brake Treadle | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BRVLV | Valve Brake | 45108 | 13925 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 45108 | 5582 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 45108 | 5582 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 45108 | 19566 | 7400
CCK-MP-HAUL-DT5316 | DT5316 Lubrication & Mechanical Services | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5316 | Caterpillar 793F Haul Truck DT5316 | 45108 | 45108 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STACC | Accum Steer Rear | 20546 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STACC | Accum Steer Middle | 20546 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STACC | Accum Steer Front | 20546 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BACCM | Accum Brake Rear | 20546 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BACCM | Accum Brake Front RH | 20546 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BACCM | Accum Brake Front LH | 20546 | 20546 | 7400
CCK-MP-HAUL-DT5315-AHSYST-HACAB-HATRU | Harness AHS to Truck | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ELCTLV-HARNS | Electrical Harness | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ELCTLV-LIGHT | DT5315 Lighting Low Voltage | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 44832 | 44832 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 44832 | 44832 | 7400
CCK-MP-HAUL-DT5315-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-TRNSYS-TRQUE | Torque Converter | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-TRNSYS-TRPMP-TMCPP | Pump Transmission | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-TRNSYS-TROLC | Oil Cooler Transmission | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 45392 | 25826 | 7400
CCK-MP-HAUL-DT5315-TRNSYS-TRANS | Transmission | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-STRUCT-TRAYS | Tray | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-SUSPN | Suspension | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CHASS-LNKLU | Upper Tag Link | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CHASS-LNKLL | Lower Tag Link | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CHASS | Chassis | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-SEATS | Operators Seat | 45392 | 2340 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-SBELT | Seat Belt | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-ELECT | Cabin Electrical System | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-AIRCN | Air Con Lines | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-AIRCN | Air Con Condenser | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 45392 | 24147 | 7400
CCK-MP-HAUL-DT5315-STRUCT-CABIN | Operators Cabin | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STOCO | Steering Oil Cooler | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 45392 | 11716 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STLTR-STBST | Ball Studs | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STLTR | Steering Linkages and Tie Rods | 45392 | 30138 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STHMU | Steering HMU | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STHLF-STRHO | Steering System Hoses | 45392 | 8351 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STCON-STWHL | Steering Wheel | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STCON-STCOL | Steering Column | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STACC-SACCR | Accumulator Steering Rear | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STACC-SACCM | Accumulator Steering Middle | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-STRSYS-STACC-SACCF | Accumulator Steering Front | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-MANGMT-UMTRN | Power Train Management System | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-MANGMT-UMMMC | Mine Monitoring and Control | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-MANGMT-UMENG | Engine Management System | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-TOWPP | Pump Towing | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-HOVLV | Valve Hoist | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-HOPMP | Pump Hoist & Brake | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-HDTNK | Tank Hydraulic | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-HDOCO | Oil Cooler Hydraulic | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-HYDSYS | Hydraulic System | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-GRSYST-GRTNK | Auto Lube Pump | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-GRSYST-GRINJ | Auto Lube Injectors | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-GRSYST-ALBPP | Auto Lube Pump | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-FRSUPP | Fire Suppression System | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 45392 | 2340 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-DRSHT | Transmission Drive Shaft | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 45392 | 16418 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 45392 | 16359 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 45392 | 25826 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-DIFFL | Differential | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 45392 | 8351 | 7400
CCK-MP-HAUL-DT5315-ENGINE-PMPDR | Pump Drive | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-LUBSY-OILPP | Oil Pump Engine | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-INTEX-EXHST | Exhaust System | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-INTEX-AFTER | Aftercooler | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-FUSYS-FULIP | Fuel Injector Pump | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-ENGINE-FUSYS-FUINJ | Fuel Injectors | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-ENGINE-COSYS-WTRPP | Water Pump Engine | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE-COSYS-RADTR | Radiator Coolant | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-COSYS-RADTR | Radiator Engine | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-ENGINE | Engine Assembly Caterpillar C175-16 | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-ELCTLV-START-STMUP | Starter Motor Upper | 45392 | 2935 | 7400
CCK-MP-HAUL-DT5315-ELCTLV-START-STMLO | Starter Motor Lower | 45392 | 2935 | 7400
CCK-MP-HAUL-DT5315-ELCTLV-CHARG-BATTY | Batteries | 45392 | 30138 | 7400
CCK-MP-HAUL-DT5315-ELCTLV-CHARG-ALTER | Alternator 24V | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-TCVLV | Valve Traction Control | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 45392 | 8391 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-PRKPP | Pump Park Brake Release | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-MERTR | Mechanical Retarder | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-HYFPP | Pump Brake Cooling | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BRVTR | Valve Brake Treadle | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BRVLV | Valve Brake | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 45392 | 16359 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 45392 | 16359 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 45392 | 20546 | 7400
CCK-MP-HAUL-DT5315 | DT5315 Lubrication & Mechanical Services | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5315 | Caterpillar 793F Haul Truck DT5315 | 45392 | 45392 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STACC | Accum Steer Rear | 29863 | 29863 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STACC | Accum Steer Middle | 22018 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STACC | Accum Steer Front | 22018 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BACCM | Accum Brake Rear | 22018 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BACCM | Accum Brake Front RH | 22018 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BACCM | Accum Brake Front LH | 22018 | 22018 | 7400
CCK-MP-HAUL-DT5314-AHSYST-HACAB-HATRU | Harness AHS to Truck | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ELCTLV-HARNS | Electrical Harness | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ELCTLV-LIGHT | DT5314 Lighting Low Voltage | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 45113 | 45113 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 45113 | 45113 | 7400
CCK-MP-HAUL-DT5314-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-TRNSYS-TRQUE | Torque Converter | 45898 | 950 | 7400
CCK-MP-HAUL-DT5314-TRNSYS-TRPMP-TMCPP | Pump Transmission | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-TRNSYS-TROLC | Oil Cooler Transmission | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-TRNSYS-TRANS | Transmission | 45898 | 950 | 7400
CCK-MP-HAUL-DT5314-STRUCT-TRAYS | Tray | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 45898 | 27054 | 7400
CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRUCT-SUSPN | Suspension | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CHASS-LNKLU | Upper Tag Link | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CHASS-LNKLL | Lower Tag Link | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CHASS | Chassis | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-SEATS | Operators Seat | 45898 | 13481 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-SBELT | Seat Belt | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-ELECT | Cabin Electrical System | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-AIRCN | Air Con Lines | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-AIRCN | Air Con Condenser | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-CABIN | Operators Cabin | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 45898 | 6943 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 45898 | 951 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 45898 | 6943 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STOCO | Steering Oil Cooler | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STLTR-STBST | Ball Studs | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STLTR | Steering Linkages and Tie Rods | 45898 | 1930 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STHMU | Steering HMU | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STHLF-STRHO | Steering System Hoses | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STCON-STWHL | Steering Wheel | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STCON-STCOL | Steering Column | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STACC-SACCR | Accumulator Steering Rear | 45898 | 29863 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STACC-SACCM | Accumulator Steering Middle | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-STRSYS-STACC-SACCF | Accumulator Steering Front | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-MANGMT-UMTRN | Power Train Management System | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-MANGMT-UMMMC | Mine Monitoring and Control | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-MANGMT-UMENG | Engine Management System | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-TOWPP | Pump Towing | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-HOVLV | Valve Hoist | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-HOPMP | Pump Hoist & Brake | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-HDTNK | Tank Hydraulic | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-HDOCO | Oil Cooler Hydraulic | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-HYDSYS | Hydraulic System | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-GRSYST-GRTNK | Auto Lube Pump | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-GRSYST-GRINJ | Auto Lube Injectors | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-GRSYST-ALBPP | Auto Lube Pump | 45898 | 14121 | 7400
CCK-MP-HAUL-DT5314-FRSUPP | Fire Suppression System | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 45898 | 1909 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 45898 | 950 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-DRSHT | Transmission Drive Shaft | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-DIFFL | Differential | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-ENGINE-PMPDR | Pump Drive | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-LUBSY-OILPP | Oil Pump Engine | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-INTEX-EXHST | Exhaust System | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-INTEX-AFTER | Aftercooler | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-FUSYS-FULIP | Fuel Injector Pump | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-ENGINE-FUSYS-FUINJ | Fuel Injectors | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-ENGINE-COSYS-WTRPP | Water Pump Engine | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE-COSYS-RADTR | Radiator Coolant | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-COSYS-RADTR | Radiator Engine | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-ENGINE | Engine Assembly Caterpillar C175-16 | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-ELCTLV-START-STMUP | Starter Motor Upper | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-ELCTLV-START-STMLO | Starter Motor Lower | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-ELCTLV-CHARG-BATTY | Batteries | 45898 | 20296 | 7400
CCK-MP-HAUL-DT5314-ELCTLV-CHARG-ALTER | Alternator 24V | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-TCVLV | Valve Traction Control | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 45898 | 9592 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-PRKPP | Pump Park Brake Release | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-MERTR | Mechanical Retarder | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-HYFPP | Pump Brake Cooling | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BRVTR | Valve Brake Treadle | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BRVLV | Valve Brake | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 45898 | 22018 | 7400
CCK-MP-HAUL-DT5314 | DT5314 Lubrication & Mechanical Services | 45768 | 45768 | 7400
CCK-MP-HAUL-DT5314 | Caterpillar 793F Haul Truck DT5314 | 45898 | 45898 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STACC | Accum Steer Rear | 19408 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STACC | Accum Steer Middle | 19408 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STACC | Accum Steer Front | 19408 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BACCM | Accum Brake Rear | 29131 | 29131 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BACCM | Accum Brake Front RH | 19408 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BACCM | Accum Brake Front LH | 19408 | 19408 | 7400
CCK-MP-HAUL-DT5313-AHSYST-HACAB-HATRU | Harness AHS to Truck | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ELCTLV-HARNS | Electrical Harness | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ELCTLV-LIGHT | DT5313 Lighting Low Voltage | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 44435 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 44435 | 19408 | 7400
CCK-MP-HAUL-DT5313-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-TRNSYS-TRQUE | Torque Converter | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-TRNSYS-TRPMP-TMCPP | Pump Transmission | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-TRNSYS-TROLC | Oil Cooler Transmission | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 44693 | 25140 | 7400
CCK-MP-HAUL-DT5313-TRNSYS-TRANS | Transmission | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-STRUCT-TRAYS | Tray | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 44693 | 6676 | 7400
CCK-MP-HAUL-DT5313-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-SUSPN | Suspension | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CHASS-LNKLU | Upper Tag Link | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CHASS-LNKLL | Lower Tag Link | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CHASS | Chassis | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-SEATS | Operators Seat | 44693 | 13322 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-SBELT | Seat Belt | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-ELECT | Cabin Electrical System | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-AIRCN | Air Con Lines | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-AIRCN | Air Con Condenser | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-CABIN | Operators Cabin | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 44693 | 1116 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 44693 | 14543 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STOCO | Steering Oil Cooler | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 44693 | 14543 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STLTR-STBST | Ball Studs | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STLTR | Steering Linkages and Tie Rods | 44693 | 14543 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STHMU | Steering HMU | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STHLF-STRHO | Steering System Hoses | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STCON-STWHL | Steering Wheel | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STCON-STCOL | Steering Column | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STACC-SACCR | Accumulator Steering Rear | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STACC-SACCM | Accumulator Steering Middle | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-STRSYS-STACC-SACCF | Accumulator Steering Front | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-MANGMT-UMTRN | Power Train Management System | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-MANGMT-UMMMC | Mine Monitoring and Control | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-MANGMT-UMENG | Engine Management System | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-TOWPP | Pump Towing | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-HOVLV | Valve Hoist | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-HOPMP | Pump Hoist & Brake | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 44693 | 27967 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 44693 | 27967 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-HDTNK | Tank Hydraulic | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-HDOCO | Oil Cooler Hydraulic | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-HYDSYS | Hydraulic System | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-GRSYST-GRTNK | Auto Lube Pump | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-GRSYST-GRINJ | Auto Lube Injectors | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-GRSYST-ALBPP | Auto Lube Pump | 44693 | 7599 | 7400
CCK-MP-HAUL-DT5313-FRSUPP | Fire Suppression System | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-DRSHT | Transmission Drive Shaft | 44693 | 25164 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 44693 | 25140 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-DIFFL | Differential | 44693 | 17171 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-ENGINE-PMPDR | Pump Drive | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-LUBSY-OILPP | Oil Pump Engine | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-INTEX-EXHST | Exhaust System | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-INTEX-AFTER | Aftercooler | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-FUSYS-FULIP | Fuel Injector Pump | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-ENGINE-FUSYS-FUINJ | Fuel Injectors | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-ENGINE-COSYS-WTRPP | Water Pump Engine | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE-COSYS-RADTR | Radiator Coolant | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-COSYS-RADTR | Radiator Engine | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-ENGINE | Engine Assembly Caterpillar C175-16 | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-ELCTLV-START-STMUP | Starter Motor Upper | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-ELCTLV-START-STMLO | Starter Motor Lower | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-ELCTLV-CHARG-BATTY | Batteries | 44693 | 16895 | 7400
CCK-MP-HAUL-DT5313-ELCTLV-CHARG-ALTER | Alternator 24V | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-TCVLV | Valve Traction Control | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-PRKPP | Pump Park Brake Release | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-MERTR | Mechanical Retarder | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-HYFPP | Pump Brake Cooling | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BRVTR | Valve Brake Treadle | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BRVLV | Valve Brake | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 44693 | 19408 | 7400
CCK-MP-HAUL-DT5313-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 44693 | 6773 | 7400
CCK-MP-HAUL-DT5313 | DT5313 Lubrication & Mechanical Services | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5313 | Caterpillar 793F Haul Truck DT5313 | 44693 | 44693 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STACC | Accum Steer Rear | 26550 | 26550 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STACC | Accum Steer Middle | 26550 | 26550 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STACC | Accum Steer Front | 26550 | 26550 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BACCM | Accum Brake Rear | 16634 | 16634 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BACCM | Accum Brake Front RH | 16634 | 16634 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BACCM | Accum Brake Front LH | 16634 | 16634 | 7400
CCK-MP-HAUL-DT5255-AHSYST-HACAB-HATRU | Harness AHS to Truck | 87580 | 56490 | 7400
CCK-MP-HAUL-DT5255-ELCTLV-HARNS | Electrical Harness | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-ELCTLV-LIGHT | DT5255 Lighting Low Voltage | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42970 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42970 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 87580 | 22547 | 7400
CCK-MP-HAUL-DT5255-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 87580 | 13477 | 7400
CCK-MP-HAUL-DT5255-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 87580 | 10729 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-STRUCT-SUSPN | Suspension | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STOCO | Steering Oil Cooler | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 87580 | 42298 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-ELECT | Cabin Electrical System | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN | Operators Cabin | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STHLF-STRHO | Steering System Hoses | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STLTR-STBST | Ball Studs | 87580 | 68761 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 87580 | 58488 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 87580 | 58488 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-TCVLV | Valve Traction Control | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CHASS-LNKLL | Lower Tag Link | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CHASS-LNKLU | Upper Tag Link | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE | Bearing Roll | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-TRNSYS-TRQUE | Torque Converter | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-TRNSYS-TRPMP-TMCPP | Pump Transmission | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 87580 | 289 | 7400
CCK-MP-HAUL-DT5255-TRNSYS-TROLC | Oil Cooler Transmission | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-TRNSYS-TRANS | Transmission | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRUCT-TRAYS | Tray | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 87580 | 21361 | 7400
CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 87580 | 25846 | 7400
CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 87580 | 25990 | 7400
CCK-MP-HAUL-DT5255-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 87580 | 25846 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CHASS | Chassis | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-SEATS | Operators Seat | 87580 | 10729 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-SBELT | Seat Belt | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-AIRCN | Air Con Lines | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-AIRCN | Air Con Condenser | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 87580 | 42298 | 7400
CCK-MP-HAUL-DT5255-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 87580 | 6100 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 87580 | 5564 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 87580 | 20163 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STLTR | Steering Linkages and Tie Rods | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STHMU | Steering HMU | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STCON-STWHL | Steering Wheel | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STCON-STCOL | Steering Column | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STACC-SACCR | Accumulator Steering Rear | 87580 | 26550 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STACC-SACCM | Accumulator Steering Middle | 87580 | 26550 | 7400
CCK-MP-HAUL-DT5255-STRSYS-STACC-SACCF | Accumulator Steering Front | 87580 | 26550 | 7400
CCK-MP-HAUL-DT5255-MANGMT-UMTRN | Power Train Management System | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-MANGMT-UMMMC | Mine Monitoring and Control | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-MANGMT-UMENG | Engine Management System | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-TOWPP | Pump Towing | 87580 | 24858 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-HOVLV | Valve Hoist | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-HOPMP | Pump Hoist & Brake | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87580 | 27012 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87580 | 27012 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-HDTNK | Tank Hydraulic | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-HYDSYS-HDOCO | Oil Cooler Hydraulic | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-HYDSYS | Hydraulic System | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-GRSYST-GRTNK | Auto Lube Pump | 87580 | 27546 | 7400
CCK-MP-HAUL-DT5255-GRSYST-GRINJ | Auto Lube Injectors | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-GRSYST-ALBPP | Auto Lube Pump | 87580 | 3331 | 7400
CCK-MP-HAUL-DT5255-FRSUPP | Fire Suppression System | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-DRSHT | Transmission Drive Shaft | 87580 | 354 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-DIFFL | Differential | 87580 | 11919 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87580 | 13068 | 7400
CCK-MP-HAUL-DT5255-ENGINE-PMPDR | Pump Drive | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-LUBSY-OILPP | Oil Pump Engine | 87580 | 42441 | 7400
CCK-MP-HAUL-DT5255-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 87580 | 42441 | 7400
CCK-MP-HAUL-DT5255-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-INTEX-EXHST | Exhaust System | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-ENGINE-INTEX-AFTER | Aftercooler | 87580 | 42441 | 7400
CCK-MP-HAUL-DT5255-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 87580 | 42441 | 7400
CCK-MP-HAUL-DT5255-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 87580 | 42441 | 7400
CCK-MP-HAUL-DT5255-ENGINE-FUSYS-FULIP | Fuel Injector Pump | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-FUSYS-FUINJ | Fuel Injectors | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-COSYS-WTRPP | Water Pump Engine | 87580 | 42441 | 7400
CCK-MP-HAUL-DT5255-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 87580 | 76061 | 7400
CCK-MP-HAUL-DT5255-ENGINE-COSYS-RADTR | Radiator Coolant | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-COSYS-RADTR | Radiator Engine | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-ENGINE | Engine Assembly Caterpillar C175-16 | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ELCTLV-START-STMUP | Starter Motor Upper | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ELCTLV-START-STMLO | Starter Motor Lower | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-ELCTLV-CHARG-BATTY | Batteries | 87580 | 17053 | 7400
CCK-MP-HAUL-DT5255-ELCTLV-CHARG-ALTER | Alternator 24V | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-PRKPP | Pump Park Brake Release | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-MERTR | Mechanical Retarder | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-HYFPP | Pump Brake Cooling | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BRVTR | Valve Brake Treadle | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BRVLV | Valve Brake | 87580 | 33228 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87580 | 8253 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 87580 | 16634 | 7400
CCK-MP-HAUL-DT5255 | DT5255 Lubrication & Mechanical Services | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5255 | Caterpillar 793F Haul Truck DT5255 | 87580 | 87580 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STACC | Accum Steer Rear | 35011 | 35011 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STACC | Accum Steer Middle | 35011 | 35011 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STACC | Accum Steer Front | 35011 | 35011 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BACCM | Accum Brake Rear | 34988 | 34988 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BACCM | Accum Brake Front RH | 58193 | 58193 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BACCM | Accum Brake Front LH | 35011 | 35011 | 7400
CCK-MP-HAUL-DT5202-AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 84306 | 53242 | 7400
CCK-MP-HAUL-DT5202-AHSYST-HACAB-HATRU | Harness AHS to Truck | 84333 | 53269 | 7400
CCK-MP-HAUL-DT5202-AHSYST-CTRLH-LIDAR | AHS Lidar | 84341 | 28652 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41509 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41509 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84333 | 7715 | 7400
CCK-MP-HAUL-DT5202-STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84333 | 15833 | 7400
CCK-MP-HAUL-DT5202-STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84333 | 7715 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84333 | 28520 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TRQUE | Torque Converter | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TRPMP-TMCPP | Pump Transmission | 84333 | 37387 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TRPMP | Pumps Transmission | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TROLC | Oil Cooler Transmission | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-TRNSYS-TRANS | Transmission | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-TRNSYS | Transmission System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-TRAYS | Tray | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-SUSPN | Suspension | 84333 | 48301 | 7400
CCK-MP-HAUL-DT5202-STRUCT-STLAD-SLFXD | Fixed Steps and Ladders | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-STLAD | Steps and Ladders | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-PNLGU | Panels and Guards | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-PLHAN | Platforms and Handrails | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CHASS-LNKLU | Upper Tag Link | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CHASS-LNKLL | Lower Tag Link | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CHASS | Chassis | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-SEATS | Operators Seat | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-SBELT | Seat Belt | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-GLASS | Glass | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-ELECT | Cabin Electrical System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-CABES | Cabin Entertainment System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-CABCO | Cabin Controls | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-AIRCN | Air Conditioning System | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRUCT-CABIN | Operators Cabin | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84333 | 15833 | 7400
CCK-MP-HAUL-DT5202-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84333 | 15833 | 7400
CCK-MP-HAUL-DT5202-STRUCT-AXLES | Axle Assembly Front | 84333 | 28520 | 7400
CCK-MP-HAUL-DT5202-STRUCT | Structure | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS-AHSEV | Valve Steering | 84306 | 84306 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STRCY | Cylinders Steering | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STOCO | Steering Oil Cooler | 84333 | 14587 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STLTR-STBST | Ball Studs | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STLTR | Steering Linkages and Tie Rods | 84333 | 33598 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STHMU | Steering HMU | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STHLF-STRHO | Steering System Hoses | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STHLF | Steering System Hoses Lines and Fittings | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STCON-STWHL | Steering Wheel | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STCON-STCOL | Steering Column | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STCON | Controls Steering | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STACC-SACCR | Accumulator Steering Rear | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STACC-SACCM | Accumulator Steering Middle | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STACC-SACCF | Accumulator Steering Front | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-STRSYS-STACC | Accumulators Steering | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-STRSYS | Steering System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-MANGMT-UMTRN | Power Train Management System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-MANGMT-UMMMC | Mine Monitoring and Control | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-MANGMT-UMENG | Engine Management System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-MANGMT | Unit Management | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-TOWPP | Pump Towing | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HOVLV | Valve Hoist | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HOPMP | Pump Hoist & Brake | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HOCYL | Cylinders Hoist | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HDTNK | Tank Hydraulic | 84333 | 57795 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HDOCO | Oil Cooler Hydraulic | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-HYDSYS | Hydraulic System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-GRSYST-GRTNK | Auto Lube Resevoir | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-GRSYST-GRINJ | Auto Lube Injectors | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-GRSYST-ALHLF | Auto Lube Hoses Lines Fittings | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-GRSYST-ALELC | Auto Lube Electrical | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-GRSYST-ALCON | Auto Lube Controller | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-GRSYST-ALBPP | Auto Lube Pump | 84333 | 6577 | 7400
CCK-MP-HAUL-DT5202-GRSYST | Grease Lubrication System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FRSUPP-FSMAN | Fire Suppression Manual | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FRSUPP-FSAUT | Fire Suppression Automatic | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FRSUPP-FSALM | Fire System Alarm | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FRSUPP | Fire Suppression System | 84333 | 53575 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-WHTYR | Wheels Tyres and Rims | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-FDRVE | Final Drives | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-DRSHT | Transmission Drive Shaft | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-DRLAX | Drive Line Axles | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-DIFFL | Differential | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-FDRSYS-AXLEC | Rear Axle Oil Cooling | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-FDRSYS | Final Drive System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84333 | 5510 | 7400
CCK-MP-HAUL-DT5202-ENGINE-PMPDR | Pump Drive | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-ENGINE-LUBSY-OILPP | Oil Pump Engine | 84333 | 53574 | 7400
CCK-MP-HAUL-DT5202-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84333 | 53574 | 7400
CCK-MP-HAUL-DT5202-ENGINE-LUBSY | Engine Lubrication System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX-EXHST | Exhaust System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX-AIRFL | Air Filtration System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX-AFTER | Aftercooler | 84333 | 53574 | 7400
CCK-MP-HAUL-DT5202-ENGINE-INTEX | Intake and Exhaust System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84333 | 53574 | 7400
CCK-MP-HAUL-DT5202-ENGINE-FUSYS-FULTK | Fuel Tank | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84333 | 53574 | 7400
CCK-MP-HAUL-DT5202-ENGINE-FUSYS-FULIP | Fuel Injection Pump | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-ENGINE-FUSYS-FUINJ | Fuel Injectors | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines and Fittings | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-FUSYS | Fuel System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-COSYS-WTRPP | Water Pump Engine | 84333 | 53574 | 7400
CCK-MP-HAUL-DT5202-ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84333 | 34700 | 7400
CCK-MP-HAUL-DT5202-ENGINE-COSYS-RADTR | Radiator Engine | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-ENGINE-COSYS-CSHLF | Cooling System Hoses Lines and Fittings | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84333 | 40680 | 7400
CCK-MP-HAUL-DT5202-ENGINE-COSYS-BELTS | Fan Belts Engine | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE-COSYS | Engine Cooling System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ENGINE | Engine Assembly Caterpillar C175-16 | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-START-STMUP | Starter Motor Upper | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-START-STMLO | Starter Motor Lower | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-START | Electrical Starting System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-LIGHT | DT5202 Lighting Low Voltage | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-HARNS | Electrical Harness | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-CONTL | Electrical Controls Low Voltage | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-CHARG-BATTY | Batteries | 84333 | 28520 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-CHARG-ALTER | Alternator 24V | 84333 | 975 | 7400
CCK-MP-HAUL-DT5202-ELCTLV-CHARG | Charging System | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-ELCTLV | Electrical System Low Voltage 24V | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-COMMUN-RADIO | Two Way Radio | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-COMMUN-FLMGT | Fleet Management | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-COMMUN | Communications | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-TCVLV | Valve Traction Control | 84333 | 34192 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84333 | 53529 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84333 | 53529 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SRVBK | Service Brake | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84333 | 15880 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84333 | 15880 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-SLACK | Brake Slack Adjusters | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-PRKPP | Pump Park Brake Release | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-MERTR | Mechanical Retarder | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-HYFPP | Pump Brake Cooling | 84333 | 16149 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BRVTR | Valve Brake Treadle | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BRVLV | Valve Brake | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84333 | 1995 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BROCO | Brake Oil Cooler | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 89142 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84333 | 13327 | 7400
CCK-MP-HAUL-DT5202-BRKSYS-BACCM | Brake Accumulators | 84333 | 84333 | 7400
CCK-MP-HAUL-DT5202-BRKSYS | Braking System | 84333 | 44953 | 7400
CCK-MP-HAUL-DT5202 | Caterpillar 793F Haul Truck DT5202 | 84333 | 84333 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STACC | Accum Steer Rear | 29074 | 29074 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STACC | Accum Steer Middle | 29074 | 29074 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STACC | Accum Steer Front | 29074 | 29074 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BACCM | Accum Brake Rear | 29074 | 29074 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BACCM | Accum Brake Front RH | 29074 | 29074 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BACCM | Accum Brake Front LH | 29074 | 29074 | 7400
CCK-MP-HAUL-DT223 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 54899 | 54899 | 7400
CCK-MP-HAUL-DT223 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ELCTLV-HARNS | Electrical Harness | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -AHSYST-CTRLH-LIDAR | AHS Lidar | 56283 | 46501 | 7400
CCK-MP-HAUL-DT223 -ELCTLV-LIGHT | DT223 Lighting Low Voltage | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43527 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43527 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 54920 | 32109 | 7400
CCK-MP-HAUL-DT223 -TRNSYS-TRQUE | Torque Converter | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 54920 | 52144 | 7400
CCK-MP-HAUL-DT223 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -TRNSYS-TROLC | Oil Cooler Transmission | 54920 | 13339 | 7400
CCK-MP-HAUL-DT223 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -TRNSYS-TRANS | Transmission | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-TRAYS | Tray | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-TRAYS | 793F Tray Wear. DT223 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CHASS-LNKLU | Upper Tag Link | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CHASS-LNKLL | Lower Tag Link | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CHASS | Chassis | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-SEATS | Operators Seat | 54920 | 24735 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-SBELT | Seat Belt | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-ELECT | Cabin Electrical System | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-AIRCN | Air Con Condenser | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-AIRCN | Air Con Lines | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-CABIN | Operators Cabin | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-AHSEV | Valve Steering | 54899 | 54899 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 54920 | 10976 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 54920 | 10976 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STOCO | Steering Oil Cooler | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STLTR-STBST | Ball Studs | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STLTR | Steering Linkages and Tie Rods | 54920 | 12085 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STHMU | Steering HMU | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STHLF-STRHO | Steering System Hoses | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STCON-STWHL | Steering Wheel | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STCON-STCOL | Steering Column | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRSYS-STACC-SACCF | Accumulator Steering Front | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -MANGMT-UMTRN | Power Train Management System | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -MANGMT-UMMMC | Mine Monitoring and Control | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -MANGMT-UMENG | Engine Management System | 122014 | 122014 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-TOWPP | Pump Towing | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-HOVLV | Valve Hoist | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-HOPMP | Pump Hoist & Brake | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-HDTNK | Tank Hydraulic | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -HYDSYS | Hydraulic System | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -GRSYST-GRTNK | Auto Lube Pump | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -GRSYST-GRINJ | Auto Lube Injectors | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -GRSYST-ALBPP | Auto Lube Pump | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -FRSUPP | Fire Suppression System | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 54920 | 2595 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 54920 | 6323 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-DRSHT | Transmission Drive Shaft | 54920 | 19882 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-DIFFL | Differential | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 54920 | 19069 | 7400
CCK-MP-HAUL-DT223 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-PMPDR | Pump Drive | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-INTEX-EXHST | Exhaust System | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE-INTEX-AFTER | Aftercooler | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-COSYS-WTRPP | Water Pump Engine | 54920 | 38862 | 7400
CCK-MP-HAUL-DT223 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE-COSYS-RADTR | Radiator Engine | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ENGINE-COSYS-RADTR | Radiator Coolant | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -ENGINE | Engine Assembly Caterpillar C175-16 | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ELCTLV-START-STMUP | Starter Motor Upper | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ELCTLV-START-STMLO | Starter Motor Lower | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -ELCTLV-CHARG-BATTY | Batteries | 54920 | 29074 | 7400
CCK-MP-HAUL-DT223 -ELCTLV-CHARG-ALTER | Alternator 24V | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-TCVLV | Valve Traction Control | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-PRKPP | Pump Park Brake Release | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-MERTR | Mechanical Retarder | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-HYFPP | Pump Brake Cooling | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BRVTR | Valve Brake Treadle | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BRVLV | Valve Brake | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 54920 | 3706 | 7400
CCK-MP-HAUL-DT223 -STRUCT-SUSPN | Suspension | 54920 | 54920 | 7400
CCK-MP-HAUL-DT223 | Caterpillar 793F Haul Truck DT223 | 54920 | 54920 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STACC | Accum Steer Rear | 28978 | 28978 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STACC | Accum Steer Middle | 28978 | 28978 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STACC | Accum Steer Front | 28978 | 28978 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BACCM | Accum Brake Rear | 28978 | 28978 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BACCM | Accum Brake Front RH | 28978 | 28978 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BACCM | Accum Brake Front LH | 28978 | 28978 | 7400
CCK-MP-HAUL-DT222 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 55708 | 55636 | 7400
CCK-MP-HAUL-DT222 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 55735 | 55663 | 7400
CCK-MP-HAUL-DT222 -ELCTLV-HARNS | Electrical Harness | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -AHSYST-CTRLH-LIDAR | AHS Lidar | 55708 | 29189 | 7400
CCK-MP-HAUL-DT222 -ELCTLV-LIGHT | DT222 Lighting Low Voltage | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42935 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42935 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -TRNSYS-TRQUE | Torque Converter | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -TRNSYS-TROLC | Oil Cooler Transmission | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -TRNSYS-TRANS | Transmission | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-TRAYS | Tray | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-TRAYS | 793F Tray Wear. DT222 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 55735 | 22120 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CHASS-LNKLU | Upper Tag Link | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CHASS-LNKLL | Lower Tag Link | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CHASS | Chassis | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-SEATS | Operators Seat | 55735 | 9457 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-SBELT | Seat Belt | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-ELECT | Cabin Electrical System | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-AIRCN | Air Con Condenser | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-AIRCN | Air Con Lines | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-CABIN | Operators Cabin | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 55735 | 3234 | 7400
CCK-MP-HAUL-DT222 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-AHSEV | Valve Steering | 55708 | 55708 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 55735 | 12092 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STOCO | Steering Oil Cooler | 55736 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STLTR-STBST | Ball Studs | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STLTR | Steering Linkages and Tie Rods | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STHMU | Steering HMU | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STHLF-STRHO | Steering System Hoses | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STCON-STWHL | Steering Wheel | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STCON-STCOL | Steering Column | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRSYS-STACC-SACCF | Accumulator Steering Front | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -MANGMT-UMTRN | Power Train Management System | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -MANGMT-UMMMC | Mine Monitoring and Control | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -MANGMT-UMENG | Engine Management System | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-TOWPP | Pump Towing | 55735 | 28733 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-HOVLV | Valve Hoist | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-HOPMP | Pump Hoist & Brake | 55735 | 1546 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-HDTNK | Tank Hydraulic | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -HYDSYS | Hydraulic System | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -GRSYST-GRTNK | Auto Lube Pump | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -GRSYST-GRINJ | Auto Lube Injectors | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -GRSYST-ALBPP | Auto Lube Pump | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -FRSUPP | Fire Suppression System | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 55735 | 9011 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 55735 | 11599 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-DRSHT | Transmission Drive Shaft | 55735 | 15829 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-DIFFL | Differential | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-PMPDR | Pump Drive | 55735 | 3987 | 7400
CCK-MP-HAUL-DT222 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-INTEX-EXHST | Exhaust System | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE-INTEX-AFTER | Aftercooler | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ENGINE-COSYS-WTRPP | Water Pump Engine | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -ENGINE-COSYS-RADTR | Radiator Engine | 55735 | 3987 | 7400
CCK-MP-HAUL-DT222 -ENGINE-COSYS-RADTR | Radiator Coolant | 55735 | 28978 | 7400
CCK-MP-HAUL-DT222 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -ENGINE | Engine Assembly Caterpillar C175-16 | 55735 | 3987 | 7400
CCK-MP-HAUL-DT222 -ELCTLV-START-STMUP | Starter Motor Upper | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ELCTLV-START-STMLO | Starter Motor Lower | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -ELCTLV-CHARG-BATTY | Batteries | 55735 | 39957 | 7400
CCK-MP-HAUL-DT222 -ELCTLV-CHARG-ALTER | Alternator 24V | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-TCVLV | Valve Traction Control | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-PRKPP | Pump Park Brake Release | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-MERTR | Mechanical Retarder | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-HYFPP | Pump Brake Cooling | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BRVTR | Valve Brake Treadle | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BRVLV | Valve Brake | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 55735 | 4006 | 7400
CCK-MP-HAUL-DT222 -STRUCT-SUSPN | Suspension | 55735 | 55735 | 7400
CCK-MP-HAUL-DT222 | Caterpillar 793F Haul Truck DT222 | 55735 | 55735 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STACC | Accum Steer Rear | 30334 | 30334 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STACC | Accum Steer Middle | 30334 | 30334 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STACC | Accum Steer Front | 30334 | 30334 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BACCM | Accum Brake Rear | 30334 | 30334 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BACCM | Accum Brake Front RH | 36715 | 36715 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BACCM | Accum Brake Front LH | 30334 | 30334 | 7400
CCK-MP-HAUL-DT221 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 57209 | 56956 | 7400
CCK-MP-HAUL-DT221 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 57237 | 56984 | 7400
CCK-MP-HAUL-DT221 -ELCTLV-HARNS | Electrical Harness | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -AHSYST-CTRLH-LIDAR | AHS Lidar | 57209 | 51058 | 7400
CCK-MP-HAUL-DT221 -ELCTLV-LIGHT | DT221 Lighting Low Voltage | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43818 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43818 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 57237 | 30334 | 7400
CCK-MP-HAUL-DT221 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 57237 | 30334 | 7400
CCK-MP-HAUL-DT221 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 57237 | 30334 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 57237 | 5640 | 7400
CCK-MP-HAUL-DT221 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 57237 | 36715 | 7400
CCK-MP-HAUL-DT221 -TRNSYS-TRQUE | Torque Converter | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -TRNSYS-TROLC | Oil Cooler Transmission | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 57237 | 20442 | 7400
CCK-MP-HAUL-DT221 -TRNSYS-TRANS | Transmission | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-TRAYS | Tray | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-TRAYS | 793F Tray Wear. DT221 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 57237 | 4057 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CHASS-LNKLU | Upper Tag Link | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CHASS-LNKLL | Lower Tag Link | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CHASS | Chassis | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-SEATS | Operators Seat | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-SBELT | Seat Belt | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-ELECT | Cabin Electrical System | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-AIRCN | Air Con Condenser | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-AIRCN | Air Con Lines | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-CABIN | Operators Cabin | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-AHSEV | Valve Steering | 57209 | 57209 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 57237 | 13199 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 57237 | 13199 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STOCO | Steering Oil Cooler | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STLTR-STBST | Ball Studs | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STLTR | Steering Linkages and Tie Rods | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STHMU | Steering HMU | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STHLF-STRHO | Steering System Hoses | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STCON-STWHL | Steering Wheel | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STCON-STCOL | Steering Column | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRSYS-STACC-SACCF | Accumulator Steering Front | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -MANGMT-UMTRN | Power Train Management System | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -MANGMT-UMMMC | Mine Monitoring and Control | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -MANGMT-UMENG | Engine Management System | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-TOWPP | Pump Towing | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-HOVLV | Valve Hoist | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-HOPMP | Pump Hoist & Brake | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-HDTNK | Tank Hydraulic | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -HYDSYS | Hydraulic System | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -GRSYST-GRTNK | Auto Lube Pump | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -GRSYST-GRINJ | Auto Lube Injectors | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -GRSYST-ALBPP | Auto Lube Pump | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -FRSUPP | Fire Suppression System | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-DRSHT | Transmission Drive Shaft | 57237 | 17825 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 57237 | 20442 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-DIFFL | Differential | 57237 | 16760 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 57237 | 2222 | 7400
CCK-MP-HAUL-DT221 -ENGINE-PMPDR | Pump Drive | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-INTEX-EXHST | Exhaust System | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE-INTEX-AFTER | Aftercooler | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-COSYS-WTRPP | Water Pump Engine | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 57237 | 25631 | 7400
CCK-MP-HAUL-DT221 -ENGINE-COSYS-RADTR | Radiator Engine | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ENGINE-COSYS-RADTR | Radiator Coolant | 57237 | 30334 | 7400
CCK-MP-HAUL-DT221 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -ENGINE | Engine Assembly Caterpillar C175-16 | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ELCTLV-START-STMUP | Starter Motor Upper | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ELCTLV-START-STMLO | Starter Motor Lower | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -ELCTLV-CHARG-BATTY | Batteries | 57237 | 30334 | 7400
CCK-MP-HAUL-DT221 -ELCTLV-CHARG-ALTER | Alternator 24V | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-TCVLV | Valve Traction Control | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-PRKPP | Pump Park Brake Release | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-MERTR | Mechanical Retarder | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-HYFPP | Pump Brake Cooling | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BRVTR | Valve Brake Treadle | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BRVLV | Valve Brake | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -STRUCT-SUSPN | Suspension | 57237 | 57237 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 57237 | 36715 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 57237 | 10386 | 7400
CCK-MP-HAUL-DT221 | Caterpillar 793F Haul Truck DT221 | 57237 | 57237 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STACC | Accum Steer Rear | 24548 | 24548 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STACC | Accum Steer Middle | 24548 | 24548 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STACC | Accum Steer Front | 24548 | 24548 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BACCM | Accum Brake Rear | 24548 | 24548 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BACCM | Accum Brake Front RH | 24548 | 24548 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BACCM | Accum Brake Front LH | 24548 | 24548 | 7400
CCK-MP-HAUL-DT161 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 80609 | 54425 | 7400
CCK-MP-HAUL-DT161 -ELCTLV-HARNS | Electrical Harness | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -ELCTLV-LIGHT | DT161 Lighting Low Voltage | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42689 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42689 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 80609 | 10780 | 7400
CCK-MP-HAUL-DT161 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 80609 | 12749 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STOCO | Steering Oil Cooler | 80609 | 11737 | 7400
CCK-MP-HAUL-DT161 -STRUCT-SUSPN | Suspension | 80609 | 49818 | 7400
CCK-MP-HAUL-DT161 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 80609 | 49818 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN-ELECT | Cabin Electrical System | 80604 | 80604 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN | Operators Cabin | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STHLF-STRHO | Steering System Hoses | 80609 | 8581 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -TRNSYS-TRQUE | Torque Converter | 80609 | 2649 | 7400
CCK-MP-HAUL-DT161 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 80609 | 52973 | 7400
CCK-MP-HAUL-DT161 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -TRNSYS-TROLC | Oil Cooler Transmission | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -TRNSYS-TRANS | Transmission | 80609 | 12241 | 7400
CCK-MP-HAUL-DT161 -STRUCT-TRAYS | Tray | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 80609 | 8581 | 7400
CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 80609 | 17509 | 7400
CCK-MP-HAUL-DT161 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CHASS | Chassis | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN-SEATS | Operators Seat | 80609 | 13960 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN-SBELT | Seat Belt | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN-AIRCN | Air Con Lines | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN-AIRCN | Air Con Condenser | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 80609 | 8581 | 7400
CCK-MP-HAUL-DT161 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 80609 | 5614 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 80609 | 8581 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 80609 | 13960 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 80609 | 13960 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STLTR | Steering Linkages and Tie Rods | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STHMU | Steering HMU | 80609 | 7381 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STCON-STWHL | Steering Wheel | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STCON-STCOL | Steering Column | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -STRSYS-STACC-SACCF | Accumulator Steering Front | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -MANGMT-UMTRN | Power Train Management System | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -MANGMT-UMMMC | Mine Monitoring and Control | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -MANGMT-UMENG | Engine Management System | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-TOWPP | Pump Towing | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-HOVLV | Valve Hoist | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-HOPMP | Pump Hoist & Brake | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-HDTNK | Tank Hydraulic | 80609 | 24548 | 7400
CCK-MP-HAUL-DT161 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -HYDSYS | Hydraulic System | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -GRSYST-GRTNK | Auto Lube Pump | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -GRSYST-GRINJ | Auto Lube Injectors | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -GRSYST-ALBPP | Auto Lube Pump | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -FRSUPP | Fire Suppression System | 80609 | 49818 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 114240 | 114240 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 80609 | 12221 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-DRSHT | Transmission Drive Shaft | 80609 | 13960 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-DIFFL | Differential | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 80609 | 16372 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-PMPDR | Pump Drive | 80609 | 9556 | 7400
CCK-MP-HAUL-DT161 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 80609 | 68404 | 7400
CCK-MP-HAUL-DT161 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-INTEX-EXHST | Exhaust System | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -ENGINE-INTEX-AFTER | Aftercooler | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 80609 | 68404 | 7400
CCK-MP-HAUL-DT161 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ENGINE-COSYS-WTRPP | Water Pump Engine | 80609 | 68404 | 7400
CCK-MP-HAUL-DT161 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -ENGINE-COSYS-RADTR | Radiator Coolant | 80609 | 68404 | 7400
CCK-MP-HAUL-DT161 -ENGINE-COSYS-RADTR | Radiator Engine | 80609 | 7381 | 7400
CCK-MP-HAUL-DT161 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 80609 | 43551 | 7400
CCK-MP-HAUL-DT161 -ENGINE | Engine Assembly Caterpillar C175-16 | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ELCTLV-START-STMUP | Starter Motor Upper | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ELCTLV-START-STMLO | Starter Motor Lower | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -ELCTLV-CHARG-BATTY | Batteries | 80609 | 16404 | 7400
CCK-MP-HAUL-DT161 -ELCTLV-CHARG-ALTER | Alternator 24V | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 80609 | 11737 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 80609 | 17509 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-PRKPP | Pump Park Brake Release | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-MERTR | Mechanical Retarder | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-HYFPP | Pump Brake Cooling | 80609 | 11737 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BRVTR | Valve Brake Treadle | 80609 | 80609 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BRVLV | Valve Brake | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 80609 | 17509 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 80609 | 17509 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 80609 | 1574 | 7400
CCK-MP-HAUL-DT161 | DT161 Lubrication & Mechanical Services | 80614 | 80614 | 7400
CCK-MP-HAUL-DT161 | Caterpillar 793F Haul Truck DT161 | 80609 | 80609 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STACC | Accum Steer Rear | 32389 | 32389 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STACC | Accum Steer Middle | 32389 | 32389 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STACC | Accum Steer Front | 32389 | 32389 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BACCM | Accum Brake Rear | 32389 | 32389 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BACCM | Accum Brake Front RH | 32389 | 32389 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BACCM | Accum Brake Front LH | 32389 | 32389 | 7400
CCK-MP-HAUL-DT160 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 85085 | 57441 | 7400
CCK-MP-HAUL-DT160 -ELCTLV-HARNS | Electrical Harness | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -ELCTLV-LIGHT | DT160 Lighting Low Voltage | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42539 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42539 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 85085 | 2673 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-SUSPN | Suspension | 85085 | 47498 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STOCO | Steering Oil Cooler | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 85085 | 57996 | 7400
CCK-MP-HAUL-DT160 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN-ELECT | Cabin Electrical System | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN | Operators Cabin | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STHLF-STRHO | Steering System Hoses | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -TRNSYS-TRQUE | Torque Converter | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 85085 | 35378 | 7400
CCK-MP-HAUL-DT160 -TRNSYS-TROLC | Oil Cooler Transmission | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -TRNSYS-TRANS | Transmission | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-TRAYS | Tray | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CHASS | Chassis | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN-SEATS | Operators Seat | 85085 | 16709 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN-SBELT | Seat Belt | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN-AIRCN | Air Con Lines | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN-AIRCN | Air Con Condenser | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 85037 | 13594 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 85085 | 13594 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STLTR | Steering Linkages and Tie Rods | 85085 | 32389 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STHMU | Steering HMU | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STCON-STWHL | Steering Wheel | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STCON-STCOL | Steering Column | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -STRSYS-STACC-SACCF | Accumulator Steering Front | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -MANGMT-UMTRN | Power Train Management System | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -MANGMT-UMMMC | Mine Monitoring and Control | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -MANGMT-UMENG | Engine Management System | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-TOWPP | Pump Towing | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-HOVLV | Valve Hoist | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-HOPMP | Pump Hoist & Brake | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 85085 | 23750 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 85085 | 23750 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-HDTNK | Tank Hydraulic | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -HYDSYS | Hydraulic System | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -GRSYST-GRTNK | Auto Lube Pump | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -GRSYST-GRINJ | Auto Lube Injectors | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -GRSYST-ALBPP | Auto Lube Pump | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -FRSUPP | Fire Suppression System | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 85085 | 20089 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 85085 | 15924 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-DRSHT | Transmission Drive Shaft | 85085 | 18309 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-DIFFL | Differential | 85085 | 13594 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 85085 | 20607 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 85085 | 2673 | 7400
CCK-MP-HAUL-DT160 -ENGINE-PMPDR | Pump Drive | 85085 | 10046 | 7400
CCK-MP-HAUL-DT160 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 85085 | 72701 | 7400
CCK-MP-HAUL-DT160 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-INTEX-EXHST | Exhaust System | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -ENGINE-INTEX-AFTER | Aftercooler | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 85085 | 57053 | 7400
CCK-MP-HAUL-DT160 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 85085 | 57053 | 7400
CCK-MP-HAUL-DT160 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-COSYS-WTRPP | Water Pump Engine | 85085 | 57053 | 7400
CCK-MP-HAUL-DT160 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 85085 | 32389 | 7400
CCK-MP-HAUL-DT160 -ENGINE-COSYS-RADTR | Radiator Coolant | 85085 | 32389 | 7400
CCK-MP-HAUL-DT160 -ENGINE-COSYS-RADTR | Radiator Engine | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -ENGINE | Engine Assembly Caterpillar C175-16 | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ELCTLV-START-STMUP | Starter Motor Upper | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ELCTLV-START-STMLO | Starter Motor Lower | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ELCTLV-CHARG-BATTY | Batteries | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -ELCTLV-CHARG-ALTER | Alternator 24V | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 85085 | 28041 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-PRKPP | Pump Park Brake Release | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-MERTR | Mechanical Retarder | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-HYFPP | Pump Brake Cooling | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BRVTR | Valve Brake Treadle | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BRVLV | Valve Brake | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 85085 | 19556 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 85085 | 19556 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 85085 | 7211 | 7400
CCK-MP-HAUL-DT160 | DT160 Lubrication & Mechanical Services | 85085 | 85085 | 7400
CCK-MP-HAUL-DT160 | Caterpillar 793F Haul Truck DT160 | 85085 | 85085 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STACC | Accum Steer Rear | 15586 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STACC | Accum Steer Middle | 15586 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STACC | Accum Steer Front | 15586 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BACCM | Accum Brake Rear | 15586 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BACCM | Accum Brake Front RH | 15586 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BACCM | Accum Brake Front LH | 15586 | 15586 | 7400
CCK-MP-HAUL-DT159 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 90235 | 54973 | 7400
CCK-MP-HAUL-DT159 -ELCTLV-HARNS | Electrical Harness | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -ELCTLV-LIGHT | DT159 Lighting Low Voltage | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42018 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42018 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 90235 | 1418 | 7400
CCK-MP-HAUL-DT159 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 90235 | 16874 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 90235 | 7642 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 90235 | 3442 | 7400
CCK-MP-HAUL-DT159 -STRUCT-SUSPN | Suspension | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STOCO | Steering Oil Cooler | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 90235 | 26756 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-ELECT | Cabin Electrical System | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN | Operators Cabin | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STHLF-STRHO | Steering System Hoses | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STLTR-STBST | Ball Studs | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 90235 | 55505 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-TCVLV | Valve Traction Control | 90235 | 64601 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CHASS-LNKLL | Lower Tag Link | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CHASS-LNKLU | Upper Tag Link | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -TRNSYS-TRQUE | Torque Converter | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 90235 | 55313 | 7400
CCK-MP-HAUL-DT159 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -TRNSYS-TROLC | Oil Cooler Transmission | 90235 | 13326 | 7400
CCK-MP-HAUL-DT159 -TRNSYS-TRANS | Transmission | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRUCT-TRAYS | Tray | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 90235 | 22947 | 7400
CCK-MP-HAUL-DT159 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 90235 | 1547 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CHASS | Chassis | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-SEATS | Operators Seat | 90235 | 18567 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-SBELT | Seat Belt | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-AIRCN | Air Con Lines | 90235 | 41100 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-AIRCN | Air Con Condenser | 90235 | 41100 | 7400
CCK-MP-HAUL-DT159 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 90235 | 41100 | 7400
CCK-MP-HAUL-DT159 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 90235 | 1418 | 7400
CCK-MP-HAUL-DT159 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 90235 | 1547 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 90235 | 3490 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STLTR | Steering Linkages and Tie Rods | 90235 | 41736 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STHMU | Steering HMU | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STCON-STWHL | Steering Wheel | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STCON-STCOL | Steering Column | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -STRSYS-STACC-SACCF | Accumulator Steering Front | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -MANGMT-UMTRN | Power Train Management System | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -MANGMT-UMMMC | Mine Monitoring and Control | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -MANGMT-UMENG | Engine Management System | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-TOWPP | Pump Towing | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-HOVLV | Valve Hoist | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-HOPMP | Pump Hoist & Brake | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-HDTNK | Tank Hydraulic | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -HYDSYS | Hydraulic System | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -GRSYST-GRTNK | Auto Lube Pump | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -GRSYST-GRINJ | Auto Lube Injectors | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -GRSYST-ALBPP | Auto Lube Pump | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -FRSUPP | Fire Suppression System | 90235 | 41100 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 90235 | 1418 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 90235 | 1418 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-DRSHT | Transmission Drive Shaft | 90235 | 20303 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-DIFFL | Differential | 90235 | 7642 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 90235 | 26756 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 90235 | 18811 | 7400
CCK-MP-HAUL-DT159 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 90235 | 5552 | 7400
CCK-MP-HAUL-DT159 -ENGINE-PMPDR | Pump Drive | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 90235 | 21571 | 7400
CCK-MP-HAUL-DT159 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 90235 | 52124 | 7400
CCK-MP-HAUL-DT159 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ENGINE-INTEX-EXHST | Exhaust System | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -ENGINE-INTEX-AFTER | Aftercooler | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 90235 | 5759 | 7400
CCK-MP-HAUL-DT159 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -ENGINE-COSYS-WTRPP | Water Pump Engine | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 90235 | 80269 | 7400
CCK-MP-HAUL-DT159 -ENGINE-COSYS-RADTR | Radiator Coolant | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -ENGINE-COSYS-RADTR | Radiator Engine | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 90235 | 64601 | 7400
CCK-MP-HAUL-DT159 -ENGINE | Engine Assembly Caterpillar C175-16 | 90235 | 26732 | 7400
CCK-MP-HAUL-DT159 -ELCTLV-START-STMUP | Starter Motor Upper | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -ELCTLV-START-STMLO | Starter Motor Lower | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -ELCTLV-CHARG-BATTY | Batteries | 90235 | 26756 | 7400
CCK-MP-HAUL-DT159 -ELCTLV-CHARG-ALTER | Alternator 24V | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 90235 | 8738 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 90235 | 8738 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-PRKPP | Pump Park Brake Release | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-MERTR | Mechanical Retarder | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-HYFPP | Pump Brake Cooling | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BRVTR | Valve Brake Treadle | 90235 | 90235 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BRVLV | Valve Brake | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 90235 | 1418 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 90235 | 1418 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 90235 | 15586 | 7400
CCK-MP-HAUL-DT159 | DT159 Lubrication & Mechanical Services | 90336 | 90336 | 7400
CCK-MP-HAUL-DT159 | Caterpillar 793F Haul Truck DT159 | 90235 | 90235 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STACC | Accum Steer Rear | 31285 | 31285 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STACC | Accum Steer Middle | 60869 | 60869 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STACC | Accum Steer Front | 31285 | 31285 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BACCM | Accum Brake Rear | 60869 | 60869 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BACCM | Accum Brake Front RH | 60869 | 60869 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BACCM | Accum Brake Front LH | 60869 | 60869 | 7400
CCK-MP-HAUL-DT158 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 85964 | 59723 | 7400
CCK-MP-HAUL-DT158 -ELCTLV-HARNS | Electrical Harness | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -ELCTLV-LIGHT | DT158 Lighting Low Voltage | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42918 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42918 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 85964 | 1034 | 7400
CCK-MP-HAUL-DT158 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STOCO | Steering Oil Cooler | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-SUSPN | Suspension | 85964 | 45664 | 7400
CCK-MP-HAUL-DT158 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 85964 | 33728 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN-ELECT | Cabin Electrical System | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN | Operators Cabin | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STHLF-STRHO | Steering System Hoses | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 85964 | 23229 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 85964 | 23229 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -TRNSYS-TRQUE | Torque Converter | 85964 | 7168 | 7400
CCK-MP-HAUL-DT158 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -TRNSYS-TROLC | Oil Cooler Transmission | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -TRNSYS-TRANS | Transmission | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-TRAYS | Tray | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 85964 | 20324 | 7400
CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 85964 | 12018 | 7400
CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 85964 | 8094 | 7400
CCK-MP-HAUL-DT158 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CHASS | Chassis | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN-SEATS | Operators Seat | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN-SBELT | Seat Belt | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN-AIRCN | Air Con Lines | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN-AIRCN | Air Con Condenser | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 85964 | 12018 | 7400
CCK-MP-HAUL-DT158 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 85964 | 22843 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 85964 | 409 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STLTR | Steering Linkages and Tie Rods | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STHMU | Steering HMU | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STCON-STWHL | Steering Wheel | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STCON-STCOL | Steering Column | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -STRSYS-STACC-SACCF | Accumulator Steering Front | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -MANGMT-UMTRN | Power Train Management System | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -MANGMT-UMMMC | Mine Monitoring and Control | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -MANGMT-UMENG | Engine Management System | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-TOWPP | Pump Towing | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-HOVLV | Valve Hoist | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-HOPMP | Pump Hoist & Brake | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 85964 | 23285 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-HDTNK | Tank Hydraulic | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -HYDSYS | Hydraulic System | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -GRSYST-GRTNK | Auto Lube Pump | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -GRSYST-GRINJ | Auto Lube Injectors | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -GRSYST-ALBPP | Auto Lube Pump | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FRSUPP | Fire Suppression System | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 85964 | 16304 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-DRSHT | Transmission Drive Shaft | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-DIFFL | Differential | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -ENGINE-PMPDR | Pump Drive | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 85964 | 33728 | 7400
CCK-MP-HAUL-DT158 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 85964 | 60187 | 7400
CCK-MP-HAUL-DT158 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 85964 | 60187 | 7400
CCK-MP-HAUL-DT158 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ENGINE-INTEX-EXHST | Exhaust System | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -ENGINE-INTEX-AFTER | Aftercooler | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 85964 | 60187 | 7400
CCK-MP-HAUL-DT158 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 85964 | 60187 | 7400
CCK-MP-HAUL-DT158 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ENGINE-COSYS-WTRPP | Water Pump Engine | 85964 | 60187 | 7400
CCK-MP-HAUL-DT158 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 85964 | 30229 | 7400
CCK-MP-HAUL-DT158 -ENGINE-COSYS-RADTR | Radiator Coolant | 85964 | 33728 | 7400
CCK-MP-HAUL-DT158 -ENGINE-COSYS-RADTR | Radiator Engine | 85964 | 33728 | 7400
CCK-MP-HAUL-DT158 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -ENGINE | Engine Assembly Caterpillar C175-16 | 85964 | 11614 | 7400
CCK-MP-HAUL-DT158 -ELCTLV-START-STMUP | Starter Motor Upper | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ELCTLV-START-STMLO | Starter Motor Lower | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -ELCTLV-CHARG-BATTY | Batteries | 85964 | 18924 | 7400
CCK-MP-HAUL-DT158 -ELCTLV-CHARG-ALTER | Alternator 24V | 85964 | 23196 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 85964 | 22843 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-PRKPP | Pump Park Brake Release | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-MERTR | Mechanical Retarder | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-HYFPP | Pump Brake Cooling | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BRVTR | Valve Brake Treadle | 85964 | 85964 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BRVLV | Valve Brake | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 85964 | 11104 | 7400
CCK-MP-HAUL-DT158 | DT158 Lubrication & Mechanical Services | 85330 | 85330 | 7400
CCK-MP-HAUL-DT158 | Caterpillar 793F Haul Truck DT158 | 85964 | 85964 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STACC | Accum Steer Rear | 29465 | 29465 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STACC | Accum Steer Middle | 51465 | 51465 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STACC | Accum Steer Front | 29465 | 29465 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BACCM | Accum Brake Rear | 29465 | 29465 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BACCM | Accum Brake Front RH | 29465 | 29465 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BACCM | Accum Brake Front LH | 29465 | 29465 | 7400
CCK-MP-HAUL-DT157 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83018 | 54766 | 7400
CCK-MP-HAUL-DT157 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83041 | 54789 | 7400
CCK-MP-HAUL-DT157 -ELCTLV-HARNS | Electrical Harness | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -AHSYST-CTRLH-LIDAR | AHS Lidar | 83019 | 228723 | 7400
CCK-MP-HAUL-DT157 -ELCTLV-LIGHT | DT157 Lighting Low Voltage | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41711 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41711 | 4183 | 7400
CCK-MP-HAUL-DT157 -AHSYST | Autonomous Haulage System | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 82954 | 22902 | 7400
CCK-MP-HAUL-DT157 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STOCO | Steering Oil Cooler | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-SUSPN | Suspension | 83026 | 51446 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83026 | 14033 | 7400
CCK-MP-HAUL-DT157 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83026 | 14033 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN | Operators Cabin | 83026 | 83026 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STHLF-STRHO | Steering System Hoses | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -TRNSYS-TRQUE | Torque Converter | 83026 | 15134 | 7400
CCK-MP-HAUL-DT157 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83026 | 83026 | 7400
CCK-MP-HAUL-DT157 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83026 | 83026 | 7400
CCK-MP-HAUL-DT157 -TRNSYS-TROLC | Oil Cooler Transmission | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -TRNSYS-TRANS | Transmission | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-TRAYS | Tray | 83026 | 83026 | 7400
CCK-MP-HAUL-DT157 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CHASS | Chassis | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN-SEATS | Operators Seat | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN-SBELT | Seat Belt | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN-AIRCN | Air Con Lines | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN-AIRCN | Air Con Condenser | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83041 | 861 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83041 | 11339 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83041 | 11339 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83041 | 22974 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STHMU | Steering HMU | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STCON-STWHL | Steering Wheel | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STCON-STCOL | Steering Column | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -MANGMT-UMTRN | Power Train Management System | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -MANGMT-UMMMC | Mine Monitoring and Control | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -MANGMT-UMENG | Engine Management System | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-TOWPP | Pump Towing | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-HOVLV | Valve Hoist | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-HOPMP | Pump Hoist & Brake | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-HDTNK | Tank Hydraulic | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -HYDSYS | Hydraulic System | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -GRSYST-GRTNK | Auto Lube Pump | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -GRSYST-GRINJ | Auto Lube Injectors | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -GRSYST-ALBPP | Auto Lube Pump | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -FRSUPP | Fire Suppression System | 83041 | 29465 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83041 | 1780 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83041 | 4138 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-DRSHT | Transmission Drive Shaft | 83041 | 8363 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-DIFFL | Differential | 83041 | 15134 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83041 | 51465 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83041 | 14090 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83041 | 15134 | 7400
CCK-MP-HAUL-DT157 -ENGINE-PMPDR | Pump Drive | 83041 | 9184 | 7400
CCK-MP-HAUL-DT157 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83026 | 46904 | 7400
CCK-MP-HAUL-DT157 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83026 | 46904 | 7400
CCK-MP-HAUL-DT157 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-INTEX-EXHST | Exhaust System | 83026 | 83026 | 7400
CCK-MP-HAUL-DT157 -ENGINE-INTEX-AFTER | Aftercooler | 83026 | 83026 | 7400
CCK-MP-HAUL-DT157 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83026 | 46904 | 7400
CCK-MP-HAUL-DT157 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83026 | 46904 | 7400
CCK-MP-HAUL-DT157 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83026 | 4183 | 7400
CCK-MP-HAUL-DT157 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83026 | 46904 | 7400
CCK-MP-HAUL-DT157 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 83026 | 29465 | 7400
CCK-MP-HAUL-DT157 -ENGINE-COSYS-RADTR | Radiator Coolant | 83041 | 29465 | 7400
CCK-MP-HAUL-DT157 -ENGINE-COSYS-RADTR | Radiator Engine | 83041 | 14033 | 7400
CCK-MP-HAUL-DT157 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -ENGINE | Engine Assembly Caterpillar C175-16 | 83041 | 15053 | 7400
CCK-MP-HAUL-DT157 -ELCTLV-START-STMUP | Starter Motor Upper | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -ELCTLV-START-STMLO | Starter Motor Lower | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -ELCTLV-CHARG-BATTY | Batteries | 83041 | 15388 | 7400
CCK-MP-HAUL-DT157 -ELCTLV-CHARG-ALTER | Alternator 24V | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-PRKPP | Pump Park Brake Release | 83041 | 33950 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-MERTR | Mechanical Retarder | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-HYFPP | Pump Brake Cooling | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BRVTR | Valve Brake Treadle | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BRVLV | Valve Brake | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 83041 | 14033 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83041 | 11359 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 83041 | 4183 | 7400
CCK-MP-HAUL-DT157 | DT157 Lubrication & Mechanical Services | 83041 | 83041 | 7400
CCK-MP-HAUL-DT157 | Caterpillar 793F Haul Truck DT157 | 83041 | 83041 | 7400
CCK-MP-HAUL-DT155 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 81407 | 55518 | 7400
CCK-MP-HAUL-DT155 -ELCTLV-HARNS | Electrical Harness | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -ELCTLV-LIGHT | DT155 Lighting Low Voltage | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 81407 | 10226 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STOCO | Steering Oil Cooler | 81407 | 8629 | 7400
CCK-MP-HAUL-DT155 -STRUCT-SUSPN | Suspension | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 81407 | 30632 | 7400
CCK-MP-HAUL-DT155 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 81407 | 30632 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN-ELECT | Cabin Electrical System | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN | Operators Cabin | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STHLF-STRHO | Steering System Hoses | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -TRNSYS-TRQUE | Torque Converter | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 81407 | 57067 | 7400
CCK-MP-HAUL-DT155 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -TRNSYS-TROLC | Oil Cooler Transmission | 81407 | 12608 | 7400
CCK-MP-HAUL-DT155 -TRNSYS-TRANS | Transmission | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-TRAYS | Tray | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CHASS | Chassis | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN-SEATS | Operators Seat | 81407 | 42 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN-SBELT | Seat Belt | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN-AIRCN | Air Con Lines | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN-AIRCN | Air Con Condenser | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 81407 | 1746 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 81407 | 12608 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 81407 | 8471 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STLTR | Steering Linkages and Tie Rods | 81407 | 30632 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STHMU | Steering HMU | 81407 | 23145 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STCON-STWHL | Steering Wheel | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STCON-STCOL | Steering Column | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -STRSYS-STACC-SACCF | Accumulator Steering Front | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -MANGMT-UMTRN | Power Train Management System | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -MANGMT-UMMMC | Mine Monitoring and Control | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -MANGMT-UMENG | Engine Management System | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-TOWPP | Pump Towing | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-HOVLV | Valve Hoist | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-HOPMP | Pump Hoist & Brake | 81407 | 30632 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-HDTNK | Tank Hydraulic | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -HYDSYS | Hydraulic System | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -GRSYST-GRTNK | Auto Lube Pump | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -GRSYST-GRINJ | Auto Lube Injectors | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -GRSYST-ALBPP | Auto Lube Pump | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FRSUPP | Fire Suppression System | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-DRSHT | Transmission Drive Shaft | 81407 | 10226 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-DIFFL | Differential | 81407 | 11450 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 81407 | 27996 | 7400
CCK-MP-HAUL-DT155 -ENGINE-PMPDR | Pump Drive | 81407 | 10315 | 7400
CCK-MP-HAUL-DT155 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 81407 | 50922 | 7400
CCK-MP-HAUL-DT155 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 81407 | 50922 | 7400
CCK-MP-HAUL-DT155 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-INTEX-EXHST | Exhaust System | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -ENGINE-INTEX-AFTER | Aftercooler | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 81407 | 50922 | 7400
CCK-MP-HAUL-DT155 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 81407 | 50922 | 7400
CCK-MP-HAUL-DT155 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-COSYS-WTRPP | Water Pump Engine | 81407 | 50953 | 7400
CCK-MP-HAUL-DT155 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 81407 | 30632 | 7400
CCK-MP-HAUL-DT155 -ENGINE-COSYS-RADTR | Radiator Coolant | 81407 | 30632 | 7400
CCK-MP-HAUL-DT155 -ENGINE-COSYS-RADTR | Radiator Engine | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -ENGINE | Engine Assembly Caterpillar C175-16 | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ELCTLV-START-STMUP | Starter Motor Upper | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ELCTLV-START-STMLO | Starter Motor Lower | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -ELCTLV-CHARG-BATTY | Batteries | 81407 | 30632 | 7400
CCK-MP-HAUL-DT155 -ELCTLV-CHARG-ALTER | Alternator 24V | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-PRKPP | Pump Park Brake Release | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-MERTR | Mechanical Retarder | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-HYFPP | Pump Brake Cooling | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BRVTR | Valve Brake Treadle | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BRVLV | Valve Brake | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 81407 | 1746 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 81407 | 1746 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 81407 | 5297 | 7400
CCK-MP-HAUL-DT155 | DT155 Lubrication & Mechanical Services | 81407 | 81407 | 7400
CCK-MP-HAUL-DT155 | Caterpillar 793F Haul Truck DT155 | 81407 | 81407 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STACC | Accum Steer Rear | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STACC | Accum Steer Middle | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STACC | Accum Steer Front | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BACCM | Accum Brake Rear | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BACCM | Accum Brake Front RH | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BACCM | Accum Brake Front LH | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84230 | 59719 | 7400
CCK-MP-HAUL-DT153 -ELCTLV-HARNS | Electrical Harness | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -ELCTLV-LIGHT | DT153 Lighting Low Voltage | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84230 | 130 | 7400
CCK-MP-HAUL-DT153 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84230 | 9760 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84230 | 2506 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84230 | 2424 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84230 | 2424 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STOCO | Steering Oil Cooler | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-SUSPN | Suspension | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84230 | 21906 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84230 | 21906 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN | Operators Cabin | 84230 | 61434 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STHLF-STRHO | Steering System Hoses | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STLTR-STBST | Ball Studs | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 84230 | 27608 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84230 | 27608 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-TCVLV | Valve Traction Control | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CHASS-LNKLL | Lower Tag Link | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CHASS-LNKLU | Upper Tag Link | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84230 | 27608 | 7400
CCK-MP-HAUL-DT153 -ENGINE | Bearing Roll | 84181 | 51293 | 7400
CCK-MP-HAUL-DT153 -TRNSYS-TRQUE | Torque Converter | 84230 | 7415 | 7400
CCK-MP-HAUL-DT153 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84230 | 70367 | 7400
CCK-MP-HAUL-DT153 -TRNSYS-TROLC | Oil Cooler Transmission | 84230 | 21949 | 7400
CCK-MP-HAUL-DT153 -TRNSYS-TRANS | Transmission | 84230 | 2506 | 7400
CCK-MP-HAUL-DT153 -STRUCT-TRAYS | Tray | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84230 | 26146 | 7400
CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CHASS | Chassis | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-SEATS | Operators Seat | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-SBELT | Seat Belt | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-AIRCN | Air Con Lines | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-AIRCN | Air Con Condenser | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84181 | 14402 | 7400
CCK-MP-HAUL-DT153 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84230 | 21882 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84230 | 21906 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STHMU | Steering HMU | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STCON-STWHL | Steering Wheel | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STCON-STCOL | Steering Column | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -MANGMT-UMTRN | Power Train Management System | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -MANGMT-UMMMC | Mine Monitoring and Control | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -MANGMT-UMENG | Engine Management System | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-TOWPP | Pump Towing | 84230 | 27608 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-HOVLV | Valve Hoist | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-HOPMP | Pump Hoist & Brake | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84230 | 27608 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84230 | 27608 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-HDTNK | Tank Hydraulic | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -HYDSYS | Hydraulic System | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -GRSYST-GRTNK | Auto Lube Pump | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -GRSYST-GRINJ | Auto Lube Injectors | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -GRSYST-ALBPP | Auto Lube Pump | 84230 | 7415 | 7400
CCK-MP-HAUL-DT153 -FRSUPP | Fire Suppression System | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84230 | 11477 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-DRSHT | Transmission Drive Shaft | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-DIFFL | Differential | 84230 | 2506 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -ENGINE-PMPDR | Pump Drive | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84230 | 75147 | 7400
CCK-MP-HAUL-DT153 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ENGINE-INTEX-EXHST | Exhaust System | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -ENGINE-INTEX-AFTER | Aftercooler | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84230 | 27680 | 7400
CCK-MP-HAUL-DT153 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84230 | 27680 | 7400
CCK-MP-HAUL-DT153 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84230 | 27680 | 7400
CCK-MP-HAUL-DT153 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84230 | 84181 | 7400
CCK-MP-HAUL-DT153 -ENGINE-COSYS-RADTR | Radiator Coolant | 84230 | 34787 | 7400
CCK-MP-HAUL-DT153 -ENGINE-COSYS-RADTR | Radiator Engine | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84230 | 61483 | 7400
CCK-MP-HAUL-DT153 -ENGINE | Engine Assembly Caterpillar C175-16 | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ELCTLV-START-STMUP | Starter Motor Upper | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ELCTLV-START-STMLO | Starter Motor Lower | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -ELCTLV-CHARG-BATTY | Batteries | 84230 | 22995 | 7400
CCK-MP-HAUL-DT153 -ELCTLV-CHARG-ALTER | Alternator 24V | 84230 | 1779 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-PRKPP | Pump Park Brake Release | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-MERTR | Mechanical Retarder | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-HYFPP | Pump Brake Cooling | 84230 | 21755 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BRVTR | Valve Brake Treadle | 84230 | 84230 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BRVLV | Valve Brake | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84230 | 13523 | 7400
CCK-MP-HAUL-DT153 | DT153 Lubrication & Mechanical Services | 84230 | 82870 | 7400
CCK-MP-HAUL-DT153 | Caterpillar 793F Haul Truck DT153 | 84230 | 84230 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STACC | Accum Steer Rear | 28267 | 28267 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STACC | Accum Steer Middle | 28267 | 28267 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STACC | Accum Steer Front | 21869 | 21869 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BACCM | Accum Brake Rear | 28267 | 28267 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BACCM | Accum Brake Front RH | 28267 | 28267 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BACCM | Accum Brake Front LH | 28267 | 28267 | 7400
CCK-MP-HAUL-DT151 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84301 | 54510 | 7400
CCK-MP-HAUL-DT151 -ELCTLV-HARNS | Electrical Harness | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -ELCTLV-LIGHT | DT151 Lighting Low Voltage | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43672 | 43672 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43672 | 1290 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84253 | 3168 | 7400
CCK-MP-HAUL-DT151 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84253 | 12362 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84253 | 3168 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84253 | 2068 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84253 | 2068 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STOCO | Steering Oil Cooler | 84253 | 9530 | 7400
CCK-MP-HAUL-DT151 -STRUCT-SUSPN | Suspension | 84253 | 44690 | 7400
CCK-MP-HAUL-DT151 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84253 | 43683 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84253 | 28267 | 7400
CCK-MP-HAUL-DT151 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84253 | 9280 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN | Operators Cabin | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STHLF-STRHO | Steering System Hoses | 84253 | 9530 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STLTR-STBST | Ball Studs | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-TCVLV | Valve Traction Control | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CHASS-LNKLL | Lower Tag Link | 84253 | 1290 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CHASS-LNKLU | Upper Tag Link | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -ENGINE | Bearing Roll | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -TRNSYS-TRQUE | Torque Converter | 84253 | 15853 | 7400
CCK-MP-HAUL-DT151 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -TRNSYS-TROLC | Oil Cooler Transmission | 84253 | 3168 | 7400
CCK-MP-HAUL-DT151 -TRNSYS-TRANS | Transmission | 84253 | 9530 | 7400
CCK-MP-HAUL-DT151 -STRUCT-TRAYS | Tray | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84253 | 28291 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CHASS | Chassis | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-SEATS | Operators Seat | 84253 | 12192 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-SBELT | Seat Belt | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-AIRCN | Air Con Lines | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-AIRCN | Air Con Condenser | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84253 | 21869 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84253 | 260 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84253 | 4338 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84253 | 9530 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84253 | 13409 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STHMU | Steering HMU | 84253 | 28327 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STCON-STWHL | Steering Wheel | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STCON-STCOL | Steering Column | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84301 | 28267 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84301 | 28267 | 7400
CCK-MP-HAUL-DT151 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84301 | 21869 | 7400
CCK-MP-HAUL-DT151 -MANGMT-UMTRN | Power Train Management System | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -MANGMT-UMMMC | Mine Monitoring and Control | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -MANGMT-UMENG | Engine Management System | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-TOWPP | Pump Towing | 84301 | 28267 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-HOVLV | Valve Hoist | 84301 | 28267 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-HOPMP | Pump Hoist & Brake | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84301 | 3400 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84301 | 28327 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-HDTNK | Tank Hydraulic | 84301 | 54538 | 7400
CCK-MP-HAUL-DT151 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -HYDSYS | Hydraulic System | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -GRSYST-GRTNK | Auto Lube Pump | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -GRSYST-GRINJ | Auto Lube Injectors | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -GRSYST-ALBPP | Auto Lube Pump | 84301 | 13358 | 7400
CCK-MP-HAUL-DT151 -FRSUPP | Fire Suppression System | 84301 | 43683 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84301 | 21869 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84301 | 21869 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-DRSHT | Transmission Drive Shaft | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-DIFFL | Differential | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84301 | 20384 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84301 | 21869 | 7400
CCK-MP-HAUL-DT151 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -ENGINE-PMPDR | Pump Drive | 84301 | 21869 | 7400
CCK-MP-HAUL-DT151 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84253 | 8936 | 7400
CCK-MP-HAUL-DT151 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84253 | 44785 | 7400
CCK-MP-HAUL-DT151 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84253 | 44785 | 7400
CCK-MP-HAUL-DT151 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84253 | 8936 | 7400
CCK-MP-HAUL-DT151 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84253 | 8936 | 7400
CCK-MP-HAUL-DT151 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84253 | 8936 | 7400
CCK-MP-HAUL-DT151 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84253 | 8936 | 7400
CCK-MP-HAUL-DT151 -ENGINE-INTEX-EXHST | Exhaust System | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -ENGINE-INTEX-AFTER | Aftercooler | 84253 | 84253 | 7400
CCK-MP-HAUL-DT151 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84253 | 44785 | 7400
CCK-MP-HAUL-DT151 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84253 | 44785 | 7400
CCK-MP-HAUL-DT151 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 84253 | 8936 | 7400
CCK-MP-HAUL-DT151 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84253 | 8936 | 7400
CCK-MP-HAUL-DT151 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84253 | 35534 | 7400
CCK-MP-HAUL-DT151 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84253 | 61323 | 7400
CCK-MP-HAUL-DT151 -ENGINE-COSYS-RADTR | Radiator Coolant | 84301 | 54538 | 7400
CCK-MP-HAUL-DT151 -ENGINE-COSYS-RADTR | Radiator Engine | 84301 | 3168 | 7400
CCK-MP-HAUL-DT151 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84301 | 45076 | 7400
CCK-MP-HAUL-DT151 -ENGINE | Engine Assembly Caterpillar C175-16 | 84301 | 8936 | 7400
CCK-MP-HAUL-DT151 -ELCTLV-START-STMUP | Starter Motor Upper | 84301 | 8936 | 7400
CCK-MP-HAUL-DT151 -ELCTLV-START-STMLO | Starter Motor Lower | 84301 | 8936 | 7400
CCK-MP-HAUL-DT151 -ELCTLV-CHARG-BATTY | Batteries | 84301 | 28327 | 7400
CCK-MP-HAUL-DT151 -ELCTLV-CHARG-ALTER | Alternator 24V | 84301 | 8936 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84301 | 56680 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84301 | 56680 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84301 | 56680 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84301 | 56680 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-PRKPP | Pump Park Brake Release | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-MERTR | Mechanical Retarder | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-HYFPP | Pump Brake Cooling | 84301 | 43683 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BRVTR | Valve Brake Treadle | 84301 | 84301 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BRVLV | Valve Brake | 84301 | 21869 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84301 | 3168 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84301 | 9530 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84301 | 28267 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84301 | 28267 | 7400
CCK-MP-HAUL-DT151 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84301 | 28267 | 7400
CCK-MP-HAUL-DT151 | DT151 Lubrication & Mechanical Services | 84331 | 84331 | 7400
CCK-MP-HAUL-DT151 | Caterpillar 793F Haul Truck DT151 | 84301 | 84301 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STACC | Accum Steer Rear | 60048 | 60048 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STACC | Accum Steer Middle | 60048 | 60048 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STACC | Accum Steer Front | 60048 | 60048 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BACCM | Accum Brake Rear | 31134 | 31134 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BACCM | Accum Brake Front RH | 60096 | 60096 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BACCM | Accum Brake Front LH | 31134 | 31134 | 7400
CCK-MP-HAUL-DT150 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 86656 | 58221 | 7400
CCK-MP-HAUL-DT150 -ELCTLV-HARNS | Electrical Harness | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -ELCTLV-LIGHT | DT150 Lighting Low Voltage | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42413 | 872 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42413 | 872 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 86608 | 3064 | 7400
CCK-MP-HAUL-DT150 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 86608 | 12300 | 7400
CCK-MP-HAUL-DT150 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 86608 | 6426 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 86608 | 2171 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STOCO | Steering Oil Cooler | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -STRUCT-SUSPN | Suspension | 86608 | 33066 | 7400
CCK-MP-HAUL-DT150 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 86608 | 33066 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 86608 | 33066 | 7400
CCK-MP-HAUL-DT150 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 86608 | 33066 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-ELECT | Cabin Electrical System | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN | Operators Cabin | 86608 | 33066 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STHLF-STRHO | Steering System Hoses | 86608 | 29495 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STLTR-STBST | Ball Studs | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 86608 | 26664 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 86608 | 49940 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-TCVLV | Valve Traction Control | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CHASS-LNKLL | Lower Tag Link | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CHASS-LNKLU | Upper Tag Link | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -ENGINE | Bearing Roll | 86608 | 78719 | 7400
CCK-MP-HAUL-DT150 -TRNSYS-TRQUE | Torque Converter | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 86608 | 55427 | 7400
CCK-MP-HAUL-DT150 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -TRNSYS-TROLC | Oil Cooler Transmission | 86608 | 6426 | 7400
CCK-MP-HAUL-DT150 -TRNSYS-TRANS | Transmission | 86608 | 14649 | 7400
CCK-MP-HAUL-DT150 -STRUCT-TRAYS | Tray | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 86608 | 6426 | 7400
CCK-MP-HAUL-DT150 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 86608 | 23907 | 7400
CCK-MP-HAUL-DT150 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 86608 | 2585 | 7400
CCK-MP-HAUL-DT150 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 86608 | 23907 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CHASS | Chassis | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-SEATS | Operators Seat | 86608 | 4191 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-SBELT | Seat Belt | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-AIRCN | Air Con Lines | 86656 | 49988 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-AIRCN | Air Con Condenser | 86608 | 49940 | 7400
CCK-MP-HAUL-DT150 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 86608 | 49940 | 7400
CCK-MP-HAUL-DT150 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 86608 | 12303 | 7400
CCK-MP-HAUL-DT150 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 86608 | 6426 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 86608 | 872 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 86608 | 6426 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STLTR | Steering Linkages and Tie Rods | 86608 | 12300 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STHMU | Steering HMU | 86608 | 33066 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STCON-STWHL | Steering Wheel | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STCON-STCOL | Steering Column | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 86608 | 60048 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 86608 | 60048 | 7400
CCK-MP-HAUL-DT150 -STRSYS-STACC-SACCF | Accumulator Steering Front | 86608 | 60048 | 7400
CCK-MP-HAUL-DT150 -MANGMT-UMTRN | Power Train Management System | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -MANGMT-UMMMC | Mine Monitoring and Control | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -MANGMT-UMENG | Engine Management System | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-TOWPP | Pump Towing | 86656 | 5319 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-HOVLV | Valve Hoist | 86656 | 31134 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-HOPMP | Pump Hoist & Brake | 86656 | 6426 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 86656 | 26544 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 86656 | 26544 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-HDTNK | Tank Hydraulic | 86656 | 33066 | 7400
CCK-MP-HAUL-DT150 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -HYDSYS | Hydraulic System | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -GRSYST-GRTNK | Auto Lube Pump | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -GRSYST-GRINJ | Auto Lube Injectors | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -GRSYST-ALBPP | Auto Lube Pump | 86656 | 5319 | 7400
CCK-MP-HAUL-DT150 -FRSUPP | Fire Suppression System | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 86656 | 20534 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 86656 | 5319 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-DRSHT | Transmission Drive Shaft | 86656 | 14622 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-DIFFL | Differential | 86656 | 6426 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 86656 | 45090 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 86656 | 6426 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 86656 | 5355 | 7400
CCK-MP-HAUL-DT150 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 86656 | 5355 | 7400
CCK-MP-HAUL-DT150 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 86656 | 14622 | 7400
CCK-MP-HAUL-DT150 -ENGINE-PMPDR | Pump Drive | 86656 | 10014 | 7400
CCK-MP-HAUL-DT150 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 86608 | 918 | 7400
CCK-MP-HAUL-DT150 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 86608 | 55857 | 7400
CCK-MP-HAUL-DT150 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 86608 | 26544 | 7400
CCK-MP-HAUL-DT150 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 86608 | 918 | 7400
CCK-MP-HAUL-DT150 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 86608 | 918 | 7400
CCK-MP-HAUL-DT150 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 86608 | 918 | 7400
CCK-MP-HAUL-DT150 -ENGINE-INTEX-EXHST | Exhaust System | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -ENGINE-INTEX-AFTER | Aftercooler | 86608 | 86608 | 7400
CCK-MP-HAUL-DT150 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 86608 | 26544 | 7400
CCK-MP-HAUL-DT150 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 86608 | 26544 | 7400
CCK-MP-HAUL-DT150 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 86608 | 918 | 7400
CCK-MP-HAUL-DT150 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 86608 | 918 | 7400
CCK-MP-HAUL-DT150 -ENGINE-COSYS-WTRPP | Water Pump Engine | 86608 | 26544 | 7400
CCK-MP-HAUL-DT150 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 86608 | 33066 | 7400
CCK-MP-HAUL-DT150 -ENGINE-COSYS-RADTR | Radiator Coolant | 86656 | 33066 | 7400
CCK-MP-HAUL-DT150 -ENGINE-COSYS-RADTR | Radiator Engine | 86656 | 6426 | 7400
CCK-MP-HAUL-DT150 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 86656 | 49988 | 7400
CCK-MP-HAUL-DT150 -ENGINE | Engine Assembly Caterpillar C175-16 | 86656 | 918 | 7400
CCK-MP-HAUL-DT150 -ELCTLV-START-STMUP | Starter Motor Upper | 86656 | 872 | 7400
CCK-MP-HAUL-DT150 -ELCTLV-START-STMLO | Starter Motor Lower | 86656 | 872 | 7400
CCK-MP-HAUL-DT150 -ELCTLV-CHARG-BATTY | Batteries | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -ELCTLV-CHARG-ALTER | Alternator 24V | 86656 | 872 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 86656 | 14622 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 86656 | 14622 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-PRKPP | Pump Park Brake Release | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-MERTR | Mechanical Retarder | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-HYFPP | Pump Brake Cooling | 86656 | 5355 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BRVTR | Valve Brake Treadle | 86656 | 86656 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BRVLV | Valve Brake | 86656 | 6426 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 86656 | 5355 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 86656 | 3064 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 86656 | 918 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 86656 | 31134 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 86656 | 60096 | 7400
CCK-MP-HAUL-DT150 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 86656 | 31134 | 7400
CCK-MP-HAUL-DT150 | DT150 Lubrication & Mechanical Services | 86024 | 86024 | 7400
CCK-MP-HAUL-DT150 | Caterpillar 793F Haul Truck DT150 | 86656 | 86656 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STACC | Accum Steer Rear | 31553 | 31553 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STACC | Accum Steer Middle | 31553 | 31553 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STACC | Accum Steer Front | 31553 | 31553 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BACCM | Accum Brake Rear | 31553 | 31553 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BACCM | Accum Brake Front RH | 31553 | 31553 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BACCM | Accum Brake Front LH | 31553 | 31553 | 7400
CCK-MP-HAUL-DT149 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 87258 | 57575 | 7400
CCK-MP-HAUL-DT149 -ELCTLV-HARNS | Electrical Harness | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -ELCTLV-LIGHT | DT149 Lighting Low Voltage | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43453 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43453 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 86975 | 13875 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STOCO | Steering Oil Cooler | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-SUSPN | Suspension | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 86975 | 31553 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-ELECT | Cabin Electrical System | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN | Operators Cabin | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STHLF-STRHO | Steering System Hoses | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STLTR-STBST | Ball Studs | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-TCVLV | Valve Traction Control | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CHASS-LNKLL | Lower Tag Link | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CHASS-LNKLU | Upper Tag Link | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE | Bearing Roll | 86975 | 31553 | 7400
CCK-MP-HAUL-DT149 -TRNSYS-TRQUE | Torque Converter | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -TRNSYS-TROLC | Oil Cooler Transmission | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -TRNSYS-TRANS | Transmission | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-TRAYS | Tray | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CHASS | Chassis | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-SEATS | Operators Seat | 86975 | 3465 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-SBELT | Seat Belt | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-AIRCN | Air Con Lines | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-AIRCN | Air Con Condenser | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 86975 | 13875 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 86975 | 17339 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 86975 | 17339 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 86975 | 23026 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STLTR | Steering Linkages and Tie Rods | 86975 | 31553 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STHMU | Steering HMU | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STCON-STWHL | Steering Wheel | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STCON-STCOL | Steering Column | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -STRSYS-STACC-SACCF | Accumulator Steering Front | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -MANGMT-UMTRN | Power Train Management System | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -MANGMT-UMMMC | Mine Monitoring and Control | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -MANGMT-UMENG | Engine Management System | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-TOWPP | Pump Towing | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-HOVLV | Valve Hoist | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-HOPMP | Pump Hoist & Brake | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-HDTNK | Tank Hydraulic | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -HYDSYS | Hydraulic System | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -GRSYST-GRTNK | Auto Lube Pump | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -GRSYST-GRINJ | Auto Lube Injectors | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -GRSYST-ALBPP | Auto Lube Pump | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -FRSUPP | Fire Suppression System | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-DRSHT | Transmission Drive Shaft | 87258 | 4012 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-DIFFL | Differential | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87258 | 31553 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87258 | 13875 | 7400
CCK-MP-HAUL-DT149 -ENGINE-PMPDR | Pump Drive | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 86975 | 78155 | 7400
CCK-MP-HAUL-DT149 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 86975 | 18542 | 7400
CCK-MP-HAUL-DT149 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-INTEX-EXHST | Exhaust System | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -ENGINE-INTEX-AFTER | Aftercooler | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 86975 | 86975 | 7400
CCK-MP-HAUL-DT149 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 86975 | 78155 | 7400
CCK-MP-HAUL-DT149 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 86975 | 9207 | 7400
CCK-MP-HAUL-DT149 -ENGINE-COSYS-WTRPP | Water Pump Engine | 86975 | 78155 | 7400
CCK-MP-HAUL-DT149 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 86975 | 15048 | 7400
CCK-MP-HAUL-DT149 -ENGINE-COSYS-RADTR | Radiator Coolant | 87258 | 31553 | 7400
CCK-MP-HAUL-DT149 -ENGINE-COSYS-RADTR | Radiator Engine | 87258 | 31553 | 7400
CCK-MP-HAUL-DT149 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -ENGINE | Engine Assembly Caterpillar C175-16 | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -ELCTLV-START-STMUP | Starter Motor Upper | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -ELCTLV-START-STMLO | Starter Motor Lower | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -ELCTLV-CHARG-BATTY | Batteries | 87258 | 18542 | 7400
CCK-MP-HAUL-DT149 -ELCTLV-CHARG-ALTER | Alternator 24V | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-PRKPP | Pump Park Brake Release | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-MERTR | Mechanical Retarder | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-HYFPP | Pump Brake Cooling | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BRVTR | Valve Brake Treadle | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BRVLV | Valve Brake | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 87258 | 9207 | 7400
CCK-MP-HAUL-DT149 | DT149 Lubrication & Mechanical Services | 87258 | 87258 | 7400
CCK-MP-HAUL-DT149 | Caterpillar 793F Haul Truck DT149 | 87258 | 87258 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STACC | Accum Steer Rear | 18023 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STACC | Accum Steer Middle | 18023 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STACC | Accum Steer Front | 18024 | 18024 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BACCM | Accum Brake Rear | 18024 | 18024 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BACCM | Accum Brake Front RH | 18024 | 18024 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BACCM | Accum Brake Front LH | 18024 | 18024 | 7400
CCK-MP-HAUL-DT148 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 85452 | 58751 | 7400
CCK-MP-HAUL-DT148 -ELCTLV-HARNS | Electrical Harness | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -ELCTLV-LIGHT | DT148 Lighting Low Voltage | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 85451 | 1970 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 85451 | 3245 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 85451 | 1970 | 7400
CCK-MP-HAUL-DT148 -STRUCT-SUSPN | Suspension | 85451 | 54845 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STOCO | Steering Oil Cooler | 85451 | 5379 | 7400
CCK-MP-HAUL-DT148 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN-ELECT | Cabin Electrical System | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN | Operators Cabin | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STHLF-STRHO | Steering System Hoses | 85451 | 1970 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 85451 | 27203 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-TCVLV | Valve Traction Control | 85451 | 62711 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 85451 | 24979 | 7400
CCK-MP-HAUL-DT148 -ENGINE | Bearing Roll | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -TRNSYS-TRQUE | Torque Converter | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 85451 | 47294 | 7400
CCK-MP-HAUL-DT148 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -TRNSYS-TROLC | Oil Cooler Transmission | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -TRNSYS-TRANS | Transmission | 85451 | 10451 | 7400
CCK-MP-HAUL-DT148 -STRUCT-TRAYS | Tray | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 85451 | 4882 | 7400
CCK-MP-HAUL-DT148 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CHASS | Chassis | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN-SEATS | Operators Seat | 85451 | 13242 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN-SBELT | Seat Belt | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN-AIRCN | Air Con Lines | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN-AIRCN | Air Con Condenser | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 85451 | 1974 | 7400
CCK-MP-HAUL-DT148 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 85451 | 1974 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 85451 | 1974 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STLTR | Steering Linkages and Tie Rods | 85451 | 1974 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STHMU | Steering HMU | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STCON-STWHL | Steering Wheel | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STCON-STCOL | Steering Column | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 85451 | 18023 | 7400
CCK-MP-HAUL-DT148 -STRSYS-STACC-SACCF | Accumulator Steering Front | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -MANGMT-UMTRN | Power Train Management System | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -MANGMT-UMMMC | Mine Monitoring and Control | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -MANGMT-UMENG | Engine Management System | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-TOWPP | Pump Towing | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-HOVLV | Valve Hoist | 85452 | 39953 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-HOPMP | Pump Hoist & Brake | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 85452 | 4882 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-HDTNK | Tank Hydraulic | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -HYDSYS | Hydraulic System | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -GRSYST-GRTNK | Auto Lube Pump | 85452 | 38392 | 7400
CCK-MP-HAUL-DT148 -GRSYST-GRINJ | Auto Lube Injectors | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -GRSYST-ALBPP | Auto Lube Pump | 85452 | 20768 | 7400
CCK-MP-HAUL-DT148 -FRSUPP | Fire Suppression System | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 85452 | 15062 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-DRSHT | Transmission Drive Shaft | 85452 | 7645 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-DIFFL | Differential | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -ENGINE-PMPDR | Pump Drive | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 85451 | 31535 | 7400
CCK-MP-HAUL-DT148 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 85451 | 31535 | 7400
CCK-MP-HAUL-DT148 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -ENGINE-INTEX-EXHST | Exhaust System | 85451 | 85451 | 7400
CCK-MP-HAUL-DT148 -ENGINE-INTEX-AFTER | Aftercooler | 85451 | 31535 | 7400
CCK-MP-HAUL-DT148 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 85451 | 31535 | 7400
CCK-MP-HAUL-DT148 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 85451 | 31535 | 7400
CCK-MP-HAUL-DT148 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 85451 | 6450 | 7400
CCK-MP-HAUL-DT148 -ENGINE-COSYS-WTRPP | Water Pump Engine | 85451 | 31535 | 7400
CCK-MP-HAUL-DT148 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 85451 | 60644 | 7400
CCK-MP-HAUL-DT148 -ENGINE-COSYS-RADTR | Radiator Coolant | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -ENGINE-COSYS-RADTR | Radiator Engine | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 85452 | 62711 | 7400
CCK-MP-HAUL-DT148 -ENGINE | Engine Assembly Caterpillar C175-16 | 85452 | 6450 | 7400
CCK-MP-HAUL-DT148 -ELCTLV-START-STMUP | Starter Motor Upper | 85452 | 6450 | 7400
CCK-MP-HAUL-DT148 -ELCTLV-START-STMLO | Starter Motor Lower | 85452 | 6450 | 7400
CCK-MP-HAUL-DT148 -ELCTLV-CHARG-BATTY | Batteries | 85452 | 31538 | 7400
CCK-MP-HAUL-DT148 -ELCTLV-CHARG-ALTER | Alternator 24V | 85452 | 6450 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 85452 | 61063 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 85452 | 11002 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 85452 | 11002 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-PRKPP | Pump Park Brake Release | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-MERTR | Mechanical Retarder | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-HYFPP | Pump Brake Cooling | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BRVTR | Valve Brake Treadle | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BRVLV | Valve Brake | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 85452 | 9949 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 85452 | 9949 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 85452 | 258 | 7400
CCK-MP-HAUL-DT148 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 85452 | 18024 | 7400
CCK-MP-HAUL-DT148 | DT148 Lubrication & Mechanical Services | 85452 | 85452 | 7400
CCK-MP-HAUL-DT148 | Caterpillar 793F Haul Truck DT148 | 85452 | 85452 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STACC | Accum Steer Rear | 31850 | 31850 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STACC | Accum Steer Middle | 31850 | 31850 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STACC | Accum Steer Front | 31850 | 31850 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BACCM | Accum Brake Rear | 31850 | 31850 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BACCM | Accum Brake Front RH | 31850 | 31850 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BACCM | Accum Brake Front LH | 31850 | 31850 | 7400
CCK-MP-HAUL-DT147 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84708 | 56175 | 7400
CCK-MP-HAUL-DT147 -ELCTLV-HARNS | Electrical Harness | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -ELCTLV-LIGHT | DT147 Lighting Low Voltage | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42471 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42471 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84659 | 31850 | 7400
CCK-MP-HAUL-DT147 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84659 | 700 | 7400
CCK-MP-HAUL-DT147 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84659 | 716 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STOCO | Steering Oil Cooler | 84659 | 16832 | 7400
CCK-MP-HAUL-DT147 -STRUCT-SUSPN | Suspension | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84659 | 31850 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84659 | 16832 | 7400
CCK-MP-HAUL-DT147 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84659 | 16832 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN | Operators Cabin | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STHLF-STRHO | Steering System Hoses | 84659 | 16832 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STLTR-STBST | Ball Studs | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-TCVLV | Valve Traction Control | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CHASS-LNKLL | Lower Tag Link | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CHASS-LNKLU | Upper Tag Link | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE | Bearing Roll | 84659 | 31850 | 7400
CCK-MP-HAUL-DT147 -TRNSYS-TRQUE | Torque Converter | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -TRNSYS-TROLC | Oil Cooler Transmission | 84659 | 16832 | 7400
CCK-MP-HAUL-DT147 -TRNSYS-TRANS | Transmission | 84659 | 716 | 7400
CCK-MP-HAUL-DT147 -STRUCT-TRAYS | Tray | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84659 | 3942 | 7400
CCK-MP-HAUL-DT147 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84659 | 19041 | 7400
CCK-MP-HAUL-DT147 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84659 | 16832 | 7400
CCK-MP-HAUL-DT147 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84659 | 19041 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CHASS | Chassis | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-SEATS | Operators Seat | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-SBELT | Seat Belt | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-AIRCN | Air Con Lines | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-AIRCN | Air Con Condenser | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84659 | 700 | 7400
CCK-MP-HAUL-DT147 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84659 | 19041 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84659 | 3326 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84659 | 16832 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STHMU | Steering HMU | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STCON-STWHL | Steering Wheel | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STCON-STCOL | Steering Column | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -MANGMT-UMTRN | Power Train Management System | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -MANGMT-UMMMC | Mine Monitoring and Control | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -MANGMT-UMENG | Engine Management System | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-TOWPP | Pump Towing | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-HOVLV | Valve Hoist | 84708 | 31850 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-HOPMP | Pump Hoist & Brake | 84708 | 16832 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-HDTNK | Tank Hydraulic | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -HYDSYS | Hydraulic System | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -GRSYST-GRTNK | Auto Lube Pump | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -GRSYST-GRINJ | Auto Lube Injectors | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -GRSYST-ALBPP | Auto Lube Pump | 84664 | 12913 | 7400
CCK-MP-HAUL-DT147 -FRSUPP | Fire Suppression System | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84708 | 20354 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-DRSHT | Transmission Drive Shaft | 84708 | 716 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-DIFFL | Differential | 84708 | 16832 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84708 | 21673 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84708 | 16832 | 7400
CCK-MP-HAUL-DT147 -ENGINE-PMPDR | Pump Drive | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84659 | 57822 | 7400
CCK-MP-HAUL-DT147 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-INTEX-EXHST | Exhaust System | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -ENGINE-INTEX-AFTER | Aftercooler | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84659 | 67897 | 7400
CCK-MP-HAUL-DT147 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84659 | 79468 | 7400
CCK-MP-HAUL-DT147 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84659 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84659 | 29129 | 7400
CCK-MP-HAUL-DT147 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84659 | 84659 | 7400
CCK-MP-HAUL-DT147 -ENGINE-COSYS-RADTR | Radiator Coolant | 84708 | 31850 | 7400
CCK-MP-HAUL-DT147 -ENGINE-COSYS-RADTR | Radiator Engine | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -ENGINE | Engine Assembly Caterpillar C175-16 | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -ELCTLV-START-STMUP | Starter Motor Upper | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -ELCTLV-START-STMLO | Starter Motor Lower | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -ELCTLV-CHARG-BATTY | Batteries | 84708 | 16832 | 7400
CCK-MP-HAUL-DT147 -ELCTLV-CHARG-ALTER | Alternator 24V | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84708 | 64655 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84708 | 64654 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84708 | 64655 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84708 | 64655 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-PRKPP | Pump Park Brake Release | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-MERTR | Mechanical Retarder | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-HYFPP | Pump Brake Cooling | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BRVTR | Valve Brake Treadle | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BRVLV | Valve Brake | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84708 | 21673 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84708 | 21673 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84708 | 12913 | 7400
CCK-MP-HAUL-DT147 | DT147 Lubrication & Mechanical Services | 84708 | 84708 | 7400
CCK-MP-HAUL-DT147 | Caterpillar 793F Haul Truck DT147 | 84708 | 84708 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STACC | Accum Steer Rear | 27168 | 27168 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STACC | Accum Steer Middle | 27168 | 27168 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STACC | Accum Steer Front | 27168 | 27168 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BACCM | Accum Brake Rear | 27723 | 27723 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BACCM | Accum Brake Front RH | 27723 | 27723 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BACCM | Accum Brake Front LH | 27723 | 27723 | 7400
CCK-MP-HAUL-DT146 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83108 | 54617 | 7400
CCK-MP-HAUL-DT146 -ELCTLV-HARNS | Electrical Harness | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -ELCTLV-LIGHT | DT146 Lighting Low Voltage | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42585 | 42585 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42585 | 42585 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 83062 | 16275 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83062 | 26 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STOCO | Steering Oil Cooler | 83062 | 990 | 7400
CCK-MP-HAUL-DT146 -STRUCT-SUSPN | Suspension | 83062 | 54979 | 7400
CCK-MP-HAUL-DT146 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83062 | 31809 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN | Operators Cabin | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STHLF-STRHO | Steering System Hoses | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 83062 | 51566 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 83062 | 51566 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE | Bearing Roll | 83062 | 31809 | 7400
CCK-MP-HAUL-DT146 -TRNSYS-TRQUE | Torque Converter | 83062 | 16890 | 7400
CCK-MP-HAUL-DT146 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83062 | 65710 | 7400
CCK-MP-HAUL-DT146 -TRNSYS-TROLC | Oil Cooler Transmission | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -TRNSYS-TRANS | Transmission | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRUCT-TRAYS | Tray | 83061 | 83061 | 7400
CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83062 | 16042 | 7400
CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83062 | 16107 | 7400
CCK-MP-HAUL-DT146 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 83062 | 20016 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CHASS | Chassis | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN-SEATS | Operators Seat | 83062 | 2282 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN-SBELT | Seat Belt | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN-AIRCN | Air Con Lines | 83062 | 31809 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN-AIRCN | Air Con Condenser | 83062 | 31809 | 7400
CCK-MP-HAUL-DT146 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 83062 | 31809 | 7400
CCK-MP-HAUL-DT146 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83061 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83061 | 16107 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83062 | 31809 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STHMU | Steering HMU | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STCON-STWHL | Steering Wheel | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STCON-STCOL | Steering Column | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83062 | 12458 | 7400
CCK-MP-HAUL-DT146 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -MANGMT-UMTRN | Power Train Management System | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -MANGMT-UMMMC | Mine Monitoring and Control | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -MANGMT-UMENG | Engine Management System | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-TOWPP | Pump Towing | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-HOVLV | Valve Hoist | 83108 | 31809 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-HOPMP | Pump Hoist & Brake | 83108 | 13849 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83108 | 24149 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83108 | 24149 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-HDTNK | Tank Hydraulic | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -HYDSYS | Hydraulic System | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -GRSYST-GRTNK | Auto Lube Pump | 83108 | 60398 | 7400
CCK-MP-HAUL-DT146 -GRSYST-GRINJ | Auto Lube Injectors | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -GRSYST-ALBPP | Auto Lube Pump | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -FRSUPP | Fire Suppression System | 83108 | 31809 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83108 | 15678 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83108 | 16116 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-DRSHT | Transmission Drive Shaft | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-DIFFL | Differential | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-PMPDR | Pump Drive | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83061 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83061 | 75386 | 7400
CCK-MP-HAUL-DT146 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 83061 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 83061 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 83061 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 83061 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-INTEX-EXHST | Exhaust System | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -ENGINE-INTEX-AFTER | Aftercooler | 83062 | 83062 | 7400
CCK-MP-HAUL-DT146 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83062 | 52558 | 7400
CCK-MP-HAUL-DT146 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83061 | 75386 | 7400
CCK-MP-HAUL-DT146 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 83061 | 990 | 7400
CCK-MP-HAUL-DT146 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83061 | 990 | 7400
CCK-MP-HAUL-DT146 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83061 | 75386 | 7400
CCK-MP-HAUL-DT146 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 83062 | 36331 | 7400
CCK-MP-HAUL-DT146 -ENGINE-COSYS-RADTR | Radiator Coolant | 83108 | 66584 | 7400
CCK-MP-HAUL-DT146 -ENGINE-COSYS-RADTR | Radiator Engine | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -ENGINE | Engine Assembly Caterpillar C175-16 | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -ELCTLV-START-STMUP | Starter Motor Upper | 83108 | 990 | 7400
CCK-MP-HAUL-DT146 -ELCTLV-START-STMLO | Starter Motor Lower | 83108 | 990 | 7400
CCK-MP-HAUL-DT146 -ELCTLV-CHARG-BATTY | Batteries | 83108 | 16928 | 7400
CCK-MP-HAUL-DT146 -ELCTLV-CHARG-ALTER | Alternator 24V | 83108 | 990 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83108 | 65756 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83108 | 65756 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-PRKPP | Pump Park Brake Release | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-MERTR | Mechanical Retarder | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-HYFPP | Pump Brake Cooling | 83108 | 16416 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BRVTR | Valve Brake Treadle | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BRVLV | Valve Brake | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83108 | 16275 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83108 | 16275 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 83108 | 12458 | 7400
CCK-MP-HAUL-DT146 | DT146 Lubrication & Mechanical Services | 83108 | 83108 | 7400
CCK-MP-HAUL-DT146 | Caterpillar 793F Haul Truck DT146 | 83108 | 83108 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STACC | Accum Steer Rear | 30720 | 30720 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STACC | Accum Steer Middle | 30720 | 30720 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STACC | Accum Steer Front | 30720 | 30720 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BACCM | Accum Brake Rear | 30720 | 30720 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BACCM | Accum Brake Front RH | 30720 | 30720 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BACCM | Accum Brake Front LH | 30720 | 30720 | 7400
CCK-MP-HAUL-DT143 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 88225 | 56507 | 7400
CCK-MP-HAUL-DT143 -ELCTLV-HARNS | Electrical Harness | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -ELCTLV-LIGHT | DT143 Lighting Low Voltage | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42172 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42172 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 88225 | 7566 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STOCO | Steering Oil Cooler | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-SUSPN | Suspension | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 88225 | 30720 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-ELECT | Cabin Electrical System | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN | Operators Cabin | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STHLF-STRHO | Steering System Hoses | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STLTR-STBST | Ball Studs | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-TCVLV | Valve Traction Control | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CHASS-LNKLL | Lower Tag Link | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CHASS-LNKLU | Upper Tag Link | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE | Bearing Roll | 88225 | 30720 | 7400
CCK-MP-HAUL-DT143 -TRNSYS-TRQUE | Torque Converter | 88225 | 20247 | 7400
CCK-MP-HAUL-DT143 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 88225 | 24063 | 7400
CCK-MP-HAUL-DT143 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 88225 | 24063 | 7400
CCK-MP-HAUL-DT143 -TRNSYS-TROLC | Oil Cooler Transmission | 88225 | 13924 | 7400
CCK-MP-HAUL-DT143 -TRNSYS-TRANS | Transmission | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-TRAYS | Tray | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 88225 | 16214 | 7400
CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 88225 | 15547 | 7400
CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 88225 | 15547 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CHASS | Chassis | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-SEATS | Operators Seat | 88225 | 6200 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-SBELT | Seat Belt | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-AIRCN | Air Con Lines | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-AIRCN | Air Con Condenser | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 88225 | 14631 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STLTR | Steering Linkages and Tie Rods | 88225 | 35974 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STHMU | Steering HMU | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STCON-STWHL | Steering Wheel | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STCON-STCOL | Steering Column | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -STRSYS-STACC-SACCF | Accumulator Steering Front | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -MANGMT-UMTRN | Power Train Management System | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -MANGMT-UMMMC | Mine Monitoring and Control | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -MANGMT-UMENG | Engine Management System | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-TOWPP | Pump Towing | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-HOVLV | Valve Hoist | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-HOPMP | Pump Hoist & Brake | 88225 | 1004 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 88225 | 22268 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 88225 | 22268 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-HDTNK | Tank Hydraulic | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -HYDSYS | Hydraulic System | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -GRSYST-GRTNK | Auto Lube Pump | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -GRSYST-GRINJ | Auto Lube Injectors | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -GRSYST-ALBPP | Auto Lube Pump | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FRSUPP | Fire Suppression System | 88225 | 30720 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-DRSHT | Transmission Drive Shaft | 88225 | 6845 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-DIFFL | Differential | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 88225 | 14631 | 7400
CCK-MP-HAUL-DT143 -ENGINE-PMPDR | Pump Drive | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 88225 | 56548 | 7400
CCK-MP-HAUL-DT143 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-INTEX-EXHST | Exhaust System | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -ENGINE-INTEX-AFTER | Aftercooler | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 88225 | 79101 | 7400
CCK-MP-HAUL-DT143 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 88225 | 325 | 7400
CCK-MP-HAUL-DT143 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 88225 | 325 | 7400
CCK-MP-HAUL-DT143 -ENGINE-COSYS-WTRPP | Water Pump Engine | 88225 | 79101 | 7400
CCK-MP-HAUL-DT143 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 88225 | 27075 | 7400
CCK-MP-HAUL-DT143 -ENGINE-COSYS-RADTR | Radiator Coolant | 88225 | 30720 | 7400
CCK-MP-HAUL-DT143 -ENGINE-COSYS-RADTR | Radiator Engine | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 88225 | 36017 | 7400
CCK-MP-HAUL-DT143 -ENGINE | Engine Assembly Caterpillar C175-16 | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ELCTLV-START-STMUP | Starter Motor Upper | 88210 | 325 | 7400
CCK-MP-HAUL-DT143 -ELCTLV-START-STMLO | Starter Motor Lower | 88225 | 325 | 7400
CCK-MP-HAUL-DT143 -ELCTLV-CHARG-BATTY | Batteries | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -ELCTLV-CHARG-ALTER | Alternator 24V | 88225 | 325 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-PRKPP | Pump Park Brake Release | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-MERTR | Mechanical Retarder | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-HYFPP | Pump Brake Cooling | 88225 | 8738 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BRVTR | Valve Brake Treadle | 88225 | 88225 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BRVLV | Valve Brake | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 88225 | 11934 | 7400
CCK-MP-HAUL-DT143 | DT143 Lubrication & Mechanical Services | 88238 | 88238 | 7400
CCK-MP-HAUL-DT143 | Caterpillar 793F Haul Truck DT143 | 88225 | 88225 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STACC | Accum Steer Rear | 27424 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STACC | Accum Steer Middle | 27424 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STACC | Accum Steer Front | 27424 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BACCM | Accum Brake Rear | 27424 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BACCM | Accum Brake Front RH | 27424 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BACCM | Accum Brake Front LH | 27424 | 27424 | 7400
CCK-MP-HAUL-DT142 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 87027 | 53383 | 7400
CCK-MP-HAUL-DT142 -ELCTLV-HARNS | Electrical Harness | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -ELCTLV-LIGHT | DT142 Lighting Low Voltage | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42471 | 42471 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42471 | 42471 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 87027 | 6635 | 7400
CCK-MP-HAUL-DT142 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 87027 | 13221 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 87027 | 11970 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STOCO | Steering Oil Cooler | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRUCT-SUSPN | Suspension | 87027 | 41684 | 7400
CCK-MP-HAUL-DT142 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 87027 | 53730 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-ELECT | Cabin Electrical System | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN | Operators Cabin | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STHLF-STRHO | Steering System Hoses | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STLTR-STBST | Ball Studs | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-TCVLV | Valve Traction Control | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CHASS-LNKLL | Lower Tag Link | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CHASS-LNKLU | Upper Tag Link | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE | Bearing Roll | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -TRNSYS-TRQUE | Torque Converter | 87027 | 3010 | 7400
CCK-MP-HAUL-DT142 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 87027 | 48028 | 7400
CCK-MP-HAUL-DT142 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -TRNSYS-TROLC | Oil Cooler Transmission | 87027 | 9824 | 7400
CCK-MP-HAUL-DT142 -TRNSYS-TRANS | Transmission | 87027 | 9824 | 7400
CCK-MP-HAUL-DT142 -STRUCT-TRAYS | Tray | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 87027 | 9824 | 7400
CCK-MP-HAUL-DT142 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 87027 | 11005 | 7400
CCK-MP-HAUL-DT142 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 87027 | 3010 | 7400
CCK-MP-HAUL-DT142 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 87027 | 13221 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CHASS | Chassis | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-SEATS | Operators Seat | 87027 | 32847 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-SBELT | Seat Belt | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-AIRCN | Air Con Lines | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-AIRCN | Air Con Condenser | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 87027 | 21161 | 7400
CCK-MP-HAUL-DT142 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 87027 | 13221 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 87027 | 3010 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 87027 | 872 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STLTR | Steering Linkages and Tie Rods | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STHMU | Steering HMU | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STCON-STWHL | Steering Wheel | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STCON-STCOL | Steering Column | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -STRSYS-STACC-SACCF | Accumulator Steering Front | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -MANGMT-UMTRN | Power Train Management System | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -MANGMT-UMMMC | Mine Monitoring and Control | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -MANGMT-UMENG | Engine Management System | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-TOWPP | Pump Towing | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-HOVLV | Valve Hoist | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-HOPMP | Pump Hoist & Brake | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87027 | 21177 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-HDTNK | Tank Hydraulic | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -HYDSYS | Hydraulic System | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -GRSYST-GRTNK | Auto Lube Pump | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -GRSYST-GRINJ | Auto Lube Injectors | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -GRSYST-ALBPP | Auto Lube Pump | 87027 | 11970 | 7400
CCK-MP-HAUL-DT142 -FRSUPP | Fire Suppression System | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87027 | 15647 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87027 | 15622 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-DRSHT | Transmission Drive Shaft | 87027 | 11970 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-DIFFL | Differential | 87027 | 11970 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87027 | 17423 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 87027 | 13221 | 7400
CCK-MP-HAUL-DT142 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87027 | 18705 | 7400
CCK-MP-HAUL-DT142 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-PMPDR | Pump Drive | 87027 | 8755 | 7400
CCK-MP-HAUL-DT142 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 87027 | 53730 | 7400
CCK-MP-HAUL-DT142 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-INTEX-EXHST | Exhaust System | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -ENGINE-INTEX-AFTER | Aftercooler | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 87027 | 57074 | 7400
CCK-MP-HAUL-DT142 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 87027 | 53730 | 7400
CCK-MP-HAUL-DT142 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 87027 | 15680 | 7400
CCK-MP-HAUL-DT142 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-COSYS-WTRPP | Water Pump Engine | 87027 | 53730 | 7400
CCK-MP-HAUL-DT142 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 87027 | 37088 | 7400
CCK-MP-HAUL-DT142 -ENGINE-COSYS-RADTR | Radiator Coolant | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-COSYS-RADTR | Radiator Engine | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 87027 | 53731 | 7400
CCK-MP-HAUL-DT142 -ENGINE | Engine Assembly Caterpillar C175-16 | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ELCTLV-START-STMUP | Starter Motor Upper | 87027 | 15680 | 7400
CCK-MP-HAUL-DT142 -ELCTLV-START-STMLO | Starter Motor Lower | 87027 | 15680 | 7400
CCK-MP-HAUL-DT142 -ELCTLV-CHARG-BATTY | Batteries | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -ELCTLV-CHARG-ALTER | Alternator 24V | 87027 | 5154 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87027 | 21161 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87027 | 18705 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87027 | 13221 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-PRKPP | Pump Park Brake Release | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-MERTR | Mechanical Retarder | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-HYFPP | Pump Brake Cooling | 87027 | 17423 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BRVTR | Valve Brake Treadle | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BRVLV | Valve Brake | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87027 | 22338 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87027 | 22338 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 87027 | 27424 | 7400
CCK-MP-HAUL-DT142 | DT142 Lubrication & Mechanical Services | 87027 | 87027 | 7400
CCK-MP-HAUL-DT142 | Caterpillar 793F Haul Truck DT142 | 87027 | 87027 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STACC | Accum Steer Rear | 27334 | 27334 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STACC | Accum Steer Middle | 27334 | 27334 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STACC | Accum Steer Front | 27334 | 27334 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BACCM | Accum Brake Rear | 17344 | 17344 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BACCM | Accum Brake Front RH | 17344 | 17344 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BACCM | Accum Brake Front LH | 17344 | 17344 | 7400
CCK-MP-HAUL-DT140 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 86767 | 53468 | 7400
CCK-MP-HAUL-DT140 -ELCTLV-HARNS | Electrical Harness | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -ELCTLV-LIGHT | DT140 Lighting Low Voltage | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41474 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41474 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 86767 | 888 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STOCO | Steering Oil Cooler | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-SUSPN | Suspension | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 86767 | 65688 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-ELECT | Cabin Electrical System | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN | Operators Cabin | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STHLF-STRHO | Steering System Hoses | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STLTR-STBST | Ball Studs | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-TCVLV | Valve Traction Control | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CHASS-LNKLL | Lower Tag Link | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CHASS-LNKLU | Upper Tag Link | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -ENGINE | Bearing Roll | 86695 | 31795 | 7400
CCK-MP-HAUL-DT140 -TRNSYS-TRQUE | Torque Converter | 86767 | 13213 | 7400
CCK-MP-HAUL-DT140 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 86767 | 65688 | 7400
CCK-MP-HAUL-DT140 -TRNSYS-TROLC | Oil Cooler Transmission | 86767 | 17833 | 7400
CCK-MP-HAUL-DT140 -TRNSYS-TRANS | Transmission | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-TRAYS | Tray | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 86767 | 11747 | 7400
CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 86767 | 17344 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CHASS | Chassis | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-SEATS | Operators Seat | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-SBELT | Seat Belt | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-AIRCN | Air Con Lines | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-AIRCN | Air Con Condenser | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 86767 | 10686 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 86767 | 10686 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STLTR | Steering Linkages and Tie Rods | 86767 | 27334 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STHMU | Steering HMU | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STCON-STWHL | Steering Wheel | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STCON-STCOL | Steering Column | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -STRSYS-STACC-SACCF | Accumulator Steering Front | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -MANGMT-UMTRN | Power Train Management System | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -MANGMT-UMMMC | Mine Monitoring and Control | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -MANGMT-UMENG | Engine Management System | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-TOWPP | Pump Towing | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-HOVLV | Valve Hoist | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-HOPMP | Pump Hoist & Brake | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-HDTNK | Tank Hydraulic | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 86767 | 56732 | 7400
CCK-MP-HAUL-DT140 -HYDSYS | Hydraulic System | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -GRSYST-GRTNK | Auto Lube Pump | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -GRSYST-GRINJ | Auto Lube Injectors | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -GRSYST-ALBPP | Auto Lube Pump | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -FRSUPP | Fire Suppression System | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 86767 | 12914 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-DRSHT | Transmission Drive Shaft | 86767 | 9442 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-DIFFL | Differential | 86767 | 8224 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 86767 | 8224 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 86767 | 8224 | 7400
CCK-MP-HAUL-DT140 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 86767 | 8224 | 7400
CCK-MP-HAUL-DT140 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 86767 | 9442 | 7400
CCK-MP-HAUL-DT140 -ENGINE-PMPDR | Pump Drive | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 86695 | 52598 | 7400
CCK-MP-HAUL-DT140 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 86695 | 52598 | 7400
CCK-MP-HAUL-DT140 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-INTEX-EXHST | Exhaust System | 86695 | 86695 | 7400
CCK-MP-HAUL-DT140 -ENGINE-INTEX-AFTER | Aftercooler | 86695 | 86695 | 7400
CCK-MP-HAUL-DT140 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 86695 | 86695 | 7400
CCK-MP-HAUL-DT140 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 86695 | 52598 | 7400
CCK-MP-HAUL-DT140 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-COSYS-WTRPP | Water Pump Engine | 86695 | 52598 | 7400
CCK-MP-HAUL-DT140 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 86695 | 86695 | 7400
CCK-MP-HAUL-DT140 -ENGINE-COSYS-RADTR | Radiator Coolant | 86767 | 75352 | 7400
CCK-MP-HAUL-DT140 -ENGINE-COSYS-RADTR | Radiator Engine | 86767 | 7327 | 7400
CCK-MP-HAUL-DT140 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 86767 | 42449 | 7400
CCK-MP-HAUL-DT140 -ENGINE | Engine Assembly Caterpillar C175-16 | 86695 | 7327 | 7400
CCK-MP-HAUL-DT140 -ELCTLV-START-STMUP | Starter Motor Upper | 86767 | 7327 | 7400
CCK-MP-HAUL-DT140 -ELCTLV-START-STMLO | Starter Motor Lower | 86767 | 7327 | 7400
CCK-MP-HAUL-DT140 -ELCTLV-CHARG-BATTY | Batteries | 86767 | 28233 | 7400
CCK-MP-HAUL-DT140 -ELCTLV-CHARG-ALTER | Alternator 24V | 86767 | 7327 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 86767 | 65688 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 86767 | 65688 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 86767 | 65688 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 86767 | 65688 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-PRKPP | Pump Park Brake Release | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-MERTR | Mechanical Retarder | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-HYFPP | Pump Brake Cooling | 86767 | 14972 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BRVTR | Valve Brake Treadle | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BRVLV | Valve Brake | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 86767 | 6817 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 86767 | 17344 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 86767 | 17344 | 7400
CCK-MP-HAUL-DT140 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 86767 | 17344 | 7400
CCK-MP-HAUL-DT140 | DT140 Lubrication & Mechanical Services | 86767 | 86767 | 7400
CCK-MP-HAUL-DT140 | Caterpillar 793F Haul Truck DT140 | 86767 | 86767 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STACC | Accum Steer Rear | 23396 | 23396 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STACC | Accum Steer Middle | 35790 | 35790 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STACC | Accum Steer Front | 35790 | 35790 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BACCM | Accum Brake Rear | 35790 | 35790 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BACCM | Accum Brake Front RH | 35790 | 35790 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BACCM | Accum Brake Front LH | 35790 | 35790 | 7400
CCK-MP-HAUL-DT138 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 82982 | 57031 | 7400
CCK-MP-HAUL-DT138 -ELCTLV-HARNS | Electrical Harness | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -ELCTLV-LIGHT | DT138 Lighting Low Voltage | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41630 | 41630 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41630 | 41630 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 82982 | 29498 | 7400
CCK-MP-HAUL-DT138 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 82982 | 10615 | 7400
CCK-MP-HAUL-DT138 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 82982 | 5976 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 82982 | 23396 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 82982 | 23396 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STOCO | Steering Oil Cooler | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRUCT-SUSPN | Suspension | 82982 | 35790 | 7400
CCK-MP-HAUL-DT138 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 82982 | 35327 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 82982 | 23314 | 7400
CCK-MP-HAUL-DT138 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 82982 | 23396 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-ELECT | Cabin Electrical System | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN | Operators Cabin | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STHLF-STRHO | Steering System Hoses | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STLTR-STBST | Ball Studs | 82982 | 47470 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 82982 | 23396 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 82982 | 23396 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-TCVLV | Valve Traction Control | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CHASS-LNKLL | Lower Tag Link | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CHASS-LNKLU | Upper Tag Link | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 82982 | 23314 | 7400
CCK-MP-HAUL-DT138 -ENGINE | Bearing Roll | 82982 | 35790 | 7400
CCK-MP-HAUL-DT138 -TRNSYS-TRQUE | Torque Converter | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -TRNSYS-TROLC | Oil Cooler Transmission | 82982 | 5976 | 7400
CCK-MP-HAUL-DT138 -TRNSYS-TRANS | Transmission | 82982 | 6438 | 7400
CCK-MP-HAUL-DT138 -STRUCT-TRAYS | Tray | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 82982 | 22553 | 7400
CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 82982 | 23314 | 7400
CCK-MP-HAUL-DT138 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CHASS | Chassis | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-SEATS | Operators Seat | 82982 | 7134 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-SBELT | Seat Belt | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-AIRCN | Air Con Lines | 82982 | 35790 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-AIRCN | Air Con Condenser | 82982 | 35790 | 7400
CCK-MP-HAUL-DT138 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 82982 | 5976 | 7400
CCK-MP-HAUL-DT138 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 82982 | 1829 | 7400
CCK-MP-HAUL-DT138 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 82982 | 4189 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STLTR | Steering Linkages and Tie Rods | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STHMU | Steering HMU | 82982 | 23396 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STCON-STWHL | Steering Wheel | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STCON-STCOL | Steering Column | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 82982 | 23396 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -STRSYS-STACC-SACCF | Accumulator Steering Front | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -MANGMT-UMTRN | Power Train Management System | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -MANGMT-UMMMC | Mine Monitoring and Control | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -MANGMT-UMENG | Engine Management System | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-TOWPP | Pump Towing | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-HOVLV | Valve Hoist | 82982 | 35790 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-HOPMP | Pump Hoist & Brake | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 82982 | 5976 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 82982 | 5976 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-HDTNK | Tank Hydraulic | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -HYDSYS | Hydraulic System | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -GRSYST-GRTNK | Auto Lube Pump | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -GRSYST-GRINJ | Auto Lube Injectors | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -GRSYST-ALBPP | Auto Lube Pump | 82982 | 5976 | 7400
CCK-MP-HAUL-DT138 -FRSUPP | Fire Suppression System | 82982 | 35790 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-DRSHT | Transmission Drive Shaft | 82982 | 5094 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-DIFFL | Differential | 82982 | 6438 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 82982 | 431 | 7400
CCK-MP-HAUL-DT138 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 82982 | 6028 | 7400
CCK-MP-HAUL-DT138 -ENGINE-PMPDR | Pump Drive | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 82982 | 57563 | 7400
CCK-MP-HAUL-DT138 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-INTEX-EXHST | Exhaust System | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -ENGINE-INTEX-AFTER | Aftercooler | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 82982 | 55645 | 7400
CCK-MP-HAUL-DT138 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 82982 | 55645 | 7400
CCK-MP-HAUL-DT138 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 82982 | 431 | 7400
CCK-MP-HAUL-DT138 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 82982 | 431 | 7400
CCK-MP-HAUL-DT138 -ENGINE-COSYS-WTRPP | Water Pump Engine | 82982 | 55645 | 7400
CCK-MP-HAUL-DT138 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 82982 | 22648 | 7400
CCK-MP-HAUL-DT138 -ENGINE-COSYS-RADTR | Radiator Coolant | 82982 | 35790 | 7400
CCK-MP-HAUL-DT138 -ENGINE-COSYS-RADTR | Radiator Engine | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 82982 | 31430 | 7400
CCK-MP-HAUL-DT138 -ENGINE | Engine Assembly Caterpillar C175-16 | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -ELCTLV-START-STMUP | Starter Motor Upper | 82982 | 431 | 7400
CCK-MP-HAUL-DT138 -ELCTLV-START-STMLO | Starter Motor Lower | 82982 | 431 | 7400
CCK-MP-HAUL-DT138 -ELCTLV-CHARG-BATTY | Batteries | 82982 | 22669 | 7400
CCK-MP-HAUL-DT138 -ELCTLV-CHARG-ALTER | Alternator 24V | 82982 | 431 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-PRKPP | Pump Park Brake Release | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-MERTR | Mechanical Retarder | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-HYFPP | Pump Brake Cooling | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BRVTR | Valve Brake Treadle | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BRVLV | Valve Brake | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 82982 | 13427 | 7400
CCK-MP-HAUL-DT138 | DT138 Lubrication & Mechanical Services | 82982 | 82982 | 7400
CCK-MP-HAUL-DT138 | Caterpillar 793F Haul Truck DT138 | 82982 | 82982 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STACC | Accum Steer Rear | 32285 | 32285 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STACC | Accum Steer Middle | 32285 | 32285 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STACC | Accum Steer Front | 32285 | 32285 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BACCM | Accum Brake Rear | 32285 | 32285 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BACCM | Accum Brake Front RH | 32285 | 32285 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BACCM | Accum Brake Front LH | 32285 | 32285 | 7400
CCK-MP-HAUL-DT137 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84196 | 56902 | 7400
CCK-MP-HAUL-DT137 -ELCTLV-HARNS | Electrical Harness | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -ELCTLV-LIGHT | DT137 Lighting Low Voltage | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42489 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42489 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84196 | 1006 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STOCO | Steering Oil Cooler | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-SUSPN | Suspension | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN | Operators Cabin | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STHLF-STRHO | Steering System Hoses | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STLTR-STBST | Ball Studs | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-TCVLV | Valve Traction Control | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CHASS-LNKLL | Lower Tag Link | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CHASS-LNKLU | Upper Tag Link | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -ENGINE | Bearing Roll | 84196 | 49397 | 7400
CCK-MP-HAUL-DT137 -TRNSYS-TRQUE | Torque Converter | 84196 | 15059 | 7400
CCK-MP-HAUL-DT137 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -TRNSYS-TROLC | Oil Cooler Transmission | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -TRNSYS-TRANS | Transmission | 84196 | 1006 | 7400
CCK-MP-HAUL-DT137 -STRUCT-TRAYS | Tray | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84196 | 5546 | 7400
CCK-MP-HAUL-DT137 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CHASS | Chassis | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-SEATS | Operators Seat | 84196 | 18714 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-SBELT | Seat Belt | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-AIRCN | Air Con Lines | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-AIRCN | Air Con Condenser | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84196 | 13819 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84196 | 143 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STHMU | Steering HMU | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STCON-STWHL | Steering Wheel | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STCON-STCOL | Steering Column | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -MANGMT-UMTRN | Power Train Management System | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -MANGMT-UMMMC | Mine Monitoring and Control | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -MANGMT-UMENG | Engine Management System | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-TOWPP | Pump Towing | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-HOVLV | Valve Hoist | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-HOPMP | Pump Hoist & Brake | 84196 | 10904 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-HDTNK | Tank Hydraulic | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -HYDSYS | Hydraulic System | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -GRSYST-GRTNK | Auto Lube Pump | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -GRSYST-GRINJ | Auto Lube Injectors | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -GRSYST-ALBPP | Auto Lube Pump | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -FRSUPP | Fire Suppression System | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84196 | 862 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84196 | 862 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-DRSHT | Transmission Drive Shaft | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-DIFFL | Differential | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84196 | 12732 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -ENGINE-PMPDR | Pump Drive | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84196 | 49397 | 7400
CCK-MP-HAUL-DT137 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84196 | 49397 | 7400
CCK-MP-HAUL-DT137 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84196 | 49397 | 7400
CCK-MP-HAUL-DT137 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-INTEX-EXHST | Exhaust System | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -ENGINE-INTEX-AFTER | Aftercooler | 84196 | 49397 | 7400
CCK-MP-HAUL-DT137 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 84196 | 12215 | 7400
CCK-MP-HAUL-DT137 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -ENGINE-COSYS-RADTR | Radiator Coolant | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -ENGINE-COSYS-RADTR | Radiator Engine | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -ENGINE | Engine Assembly Caterpillar C175-16 | 84196 | 26406 | 7400
CCK-MP-HAUL-DT137 -ELCTLV-START-STMUP | Starter Motor Upper | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -ELCTLV-START-STMLO | Starter Motor Lower | 84196 | 32285 | 7400
CCK-MP-HAUL-DT137 -ELCTLV-CHARG-BATTY | Batteries | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -ELCTLV-CHARG-ALTER | Alternator 24V | 84196 | 27954 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-PRKPP | Pump Park Brake Release | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-MERTR | Mechanical Retarder | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-HYFPP | Pump Brake Cooling | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BRVTR | Valve Brake Treadle | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BRVLV | Valve Brake | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84196 | 866 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84196 | 866 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84196 | 9757 | 7400
CCK-MP-HAUL-DT137 | DT137 Lubrication & Mechanical Services | 84196 | 84196 | 7400
CCK-MP-HAUL-DT137 | Caterpillar 793F Haul Truck DT137 | 84196 | 84196 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STACC | Accum Steer Rear | 29370 | 29370 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STACC | Accum Steer Middle | 14476 | 14476 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STACC | Accum Steer Front | 29370 | 29370 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BACCM | Accum Brake Rear | 29370 | 29370 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BACCM | Accum Brake Front RH | 29370 | 29370 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BACCM | Accum Brake Front LH | 29370 | 29370 | 7400
CCK-MP-HAUL-DT136 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 87780 | 54027 | 7400
CCK-MP-HAUL-DT136 -ELCTLV-HARNS | Electrical Harness | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -ELCTLV-LIGHT | DT136 Lighting Low Voltage | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42633 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42633 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 87780 | 6584 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STOCO | Steering Oil Cooler | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-SUSPN | Suspension | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 87780 | 29370 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-ELECT | Cabin Electrical System | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN | Operators Cabin | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STHLF-STRHO | Steering System Hoses | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STLTR-STBST | Ball Studs | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-TCVLV | Valve Traction Control | 87780 | 64659 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CHASS-LNKLL | Lower Tag Link | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CHASS-LNKLU | Upper Tag Link | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE | Bearing Roll | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -TRNSYS-TRQUE | Torque Converter | 87780 | 13860 | 7400
CCK-MP-HAUL-DT136 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 87780 | 40368 | 7400
CCK-MP-HAUL-DT136 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -TRNSYS-TROLC | Oil Cooler Transmission | 87780 | 9254 | 7400
CCK-MP-HAUL-DT136 -TRNSYS-TRANS | Transmission | 87780 | 9256 | 7400
CCK-MP-HAUL-DT136 -STRUCT-TRAYS | Tray | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 87780 | 13439 | 7400
CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 87780 | 13439 | 7400
CCK-MP-HAUL-DT136 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CHASS | Chassis | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-SEATS | Operators Seat | 87780 | 1767 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-SBELT | Seat Belt | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-AIRCN | Air Con Lines | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-AIRCN | Air Con Condenser | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STLTR | Steering Linkages and Tie Rods | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STHMU | Steering HMU | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STCON-STWHL | Steering Wheel | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STCON-STCOL | Steering Column | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 87780 | 14476 | 7400
CCK-MP-HAUL-DT136 -STRSYS-STACC-SACCF | Accumulator Steering Front | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -MANGMT-UMTRN | Power Train Management System | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -MANGMT-UMMMC | Mine Monitoring and Control | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -MANGMT-UMENG | Engine Management System | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-TOWPP | Pump Towing | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-HOVLV | Valve Hoist | 87780 | 15727 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-HOPMP | Pump Hoist & Brake | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-HDTNK | Tank Hydraulic | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -HYDSYS | Hydraulic System | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -GRSYST-GRTNK | Auto Lube Pump | 87780 | 37403 | 7400
CCK-MP-HAUL-DT136 -GRSYST-GRINJ | Auto Lube Injectors | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -GRSYST-ALBPP | Auto Lube Pump | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -FRSUPP | Fire Suppression System | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87780 | 20807 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-DRSHT | Transmission Drive Shaft | 87780 | 13954 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-DIFFL | Differential | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87780 | 16897 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87780 | 13954 | 7400
CCK-MP-HAUL-DT136 -ENGINE-PMPDR | Pump Drive | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 87780 | 51550 | 7400
CCK-MP-HAUL-DT136 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-INTEX-EXHST | Exhaust System | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -ENGINE-INTEX-AFTER | Aftercooler | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 87780 | 78823 | 7400
CCK-MP-HAUL-DT136 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-COSYS-WTRPP | Water Pump Engine | 87780 | 78823 | 7400
CCK-MP-HAUL-DT136 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -ENGINE-COSYS-RADTR | Radiator Coolant | 87780 | 24460 | 7400
CCK-MP-HAUL-DT136 -ENGINE-COSYS-RADTR | Radiator Engine | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 87780 | 47799 | 7400
CCK-MP-HAUL-DT136 -ENGINE | Engine Assembly Caterpillar C175-16 | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ELCTLV-START-STMUP | Starter Motor Upper | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ELCTLV-START-STMLO | Starter Motor Lower | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ELCTLV-CHARG-BATTY | Batteries | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -ELCTLV-CHARG-ALTER | Alternator 24V | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87780 | 64659 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87780 | 64659 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87780 | 64659 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87780 | 18275 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-PRKPP | Pump Park Brake Release | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-MERTR | Mechanical Retarder | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-HYFPP | Pump Brake Cooling | 87780 | 20793 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BRVTR | Valve Brake Treadle | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BRVLV | Valve Brake | 87780 | 39696 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87780 | 716 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87780 | 716 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 87780 | 11471 | 7400
CCK-MP-HAUL-DT136 | DT136 Lubrication & Mechanical Services | 87780 | 87780 | 7400
CCK-MP-HAUL-DT136 | Caterpillar 793F Haul Truck DT136 | 87780 | 87780 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STACC | Accum Steer Rear | 31127 | 31127 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STACC | Accum Steer Middle | 31127 | 31127 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STACC | Accum Steer Front | 31127 | 31127 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BACCM | Accum Brake Rear | 31127 | 31127 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BACCM | Accum Brake Front RH | 31127 | 31127 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BACCM | Accum Brake Front LH | 31127 | 31127 | 7400
CCK-MP-HAUL-DT135 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 82965 | 56164 | 7400
CCK-MP-HAUL-DT135 -ELCTLV-HARNS | Electrical Harness | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -ELCTLV-LIGHT | DT135 Lighting Low Voltage | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42170 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42170 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 82965 | 12819 | 7400
CCK-MP-HAUL-DT135 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 82965 | 15252 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 82965 | 1709 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STOCO | Steering Oil Cooler | 82941 | 12254 | 7400
CCK-MP-HAUL-DT135 -STRUCT-SUSPN | Suspension | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 82965 | 36862 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 82965 | 36862 | 7400
CCK-MP-HAUL-DT135 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 82965 | 36862 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN-ELECT | Cabin Electrical System | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN | Operators Cabin | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STHLF-STRHO | Steering System Hoses | 82965 | 12254 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE | Bearing Roll | 82965 | 31710 | 7400
CCK-MP-HAUL-DT135 -TRNSYS-TRQUE | Torque Converter | 82965 | 23080 | 7400
CCK-MP-HAUL-DT135 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -TRNSYS-TROLC | Oil Cooler Transmission | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -TRNSYS-TRANS | Transmission | 82965 | 7974 | 7400
CCK-MP-HAUL-DT135 -STRUCT-TRAYS | Tray | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 82965 | 12818 | 7400
CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CHASS | Chassis | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN-SEATS | Operators Seat | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN-SBELT | Seat Belt | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN-AIRCN | Air Con Lines | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN-AIRCN | Air Con Condenser | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 82965 | 12818 | 7400
CCK-MP-HAUL-DT135 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 82965 | 15252 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 82965 | 12254 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 82965 | 12254 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STLTR | Steering Linkages and Tie Rods | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STHMU | Steering HMU | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STCON-STWHL | Steering Wheel | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STCON-STCOL | Steering Column | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -STRSYS-STACC-SACCF | Accumulator Steering Front | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -MANGMT-UMTRN | Power Train Management System | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -MANGMT-UMMMC | Mine Monitoring and Control | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -MANGMT-UMENG | Engine Management System | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-TOWPP | Pump Towing | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-HOVLV | Valve Hoist | 82965 | 31127 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-HOPMP | Pump Hoist & Brake | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 82965 | 6150 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 82965 | 23752 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-HDTNK | Tank Hydraulic | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -HYDSYS | Hydraulic System | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -GRSYST-GRTNK | Auto Lube Pump | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -GRSYST-GRINJ | Auto Lube Injectors | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -GRSYST-ALBPP | Auto Lube Pump | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FRSUPP | Fire Suppression System | 82965 | 31127 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-DRSHT | Transmission Drive Shaft | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-DIFFL | Differential | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 82965 | 13334 | 7400
CCK-MP-HAUL-DT135 -ENGINE-PMPDR | Pump Drive | 82965 | 11119 | 7400
CCK-MP-HAUL-DT135 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 82965 | 52154 | 7400
CCK-MP-HAUL-DT135 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-INTEX-EXHST | Exhaust System | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -ENGINE-INTEX-AFTER | Aftercooler | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 82965 | 52154 | 7400
CCK-MP-HAUL-DT135 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 82965 | 52154 | 7400
CCK-MP-HAUL-DT135 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-COSYS-WTRPP | Water Pump Engine | 82965 | 75571 | 7400
CCK-MP-HAUL-DT135 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 82965 | 21425 | 7400
CCK-MP-HAUL-DT135 -ENGINE-COSYS-RADTR | Radiator Coolant | 82965 | 31127 | 7400
CCK-MP-HAUL-DT135 -ENGINE-COSYS-RADTR | Radiator Engine | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -ENGINE | Engine Assembly Caterpillar C175-16 | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ELCTLV-START-STMUP | Starter Motor Upper | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ELCTLV-START-STMLO | Starter Motor Lower | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -ELCTLV-CHARG-BATTY | Batteries | 82965 | 16747 | 7400
CCK-MP-HAUL-DT135 -ELCTLV-CHARG-ALTER | Alternator 24V | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-PRKPP | Pump Park Brake Release | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-MERTR | Mechanical Retarder | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-HYFPP | Pump Brake Cooling | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BRVTR | Valve Brake Treadle | 82965 | 82965 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BRVLV | Valve Brake | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 82965 | 8025 | 7400
CCK-MP-HAUL-DT135 | DT135 Lubrication & Mechanical Services | 83706 | 83706 | 7400
CCK-MP-HAUL-DT135 | Caterpillar 793F Haul Truck DT135 | 82965 | 82965 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STACC | Accum Steer Rear | 33489 | 33489 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STACC | Accum Steer Middle | 33489 | 33489 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STACC | Accum Steer Front | 33489 | 33489 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BACCM | Accum Brake Rear | 33489 | 33489 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BACCM | Accum Brake Front RH | 33489 | 33489 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BACCM | Accum Brake Front LH | 33489 | 33489 | 7400
CCK-MP-HAUL-DT130 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 85185 | 57120 | 7400
CCK-MP-HAUL-DT130 -ELCTLV-HARNS | Electrical Harness | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -ELCTLV-LIGHT | DT130 Lighting Low Voltage | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42434 | 15131 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42434 | 15131 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 85185 | 10692 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STOCO | Steering Oil Cooler | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-SUSPN | Suspension | 85185 | 52616 | 7400
CCK-MP-HAUL-DT130 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 85185 | 33489 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 85185 | 33489 | 7400
CCK-MP-HAUL-DT130 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-ELECT | Cabin Electrical System | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN | Operators Cabin | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STHLF-STRHO | Steering System Hoses | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STLTR-STBST | Ball Studs | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-TCVLV | Valve Traction Control | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CHASS-LNKLL | Lower Tag Link | 85185 | 15131 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CHASS-LNKLU | Upper Tag Link | 85185 | 15131 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE | Bearing Roll | 85185 | 49739 | 7400
CCK-MP-HAUL-DT130 -TRNSYS-TRQUE | Torque Converter | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -TRNSYS-TROLC | Oil Cooler Transmission | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -TRNSYS-TRANS | Transmission | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-TRAYS | Tray | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 85185 | 15131 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CHASS | Chassis | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-SEATS | Operators Seat | 85185 | 12955 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-SBELT | Seat Belt | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-AIRCN | Air Con Lines | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-AIRCN | Air Con Condenser | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 85185 | 19963 | 7400
CCK-MP-HAUL-DT130 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 85185 | 11817 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 85185 | 14144 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STLTR | Steering Linkages and Tie Rods | 85185 | 33489 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STHMU | Steering HMU | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STCON-STWHL | Steering Wheel | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STCON-STCOL | Steering Column | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -STRSYS-STACC-SACCF | Accumulator Steering Front | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -MANGMT-UMTRN | Power Train Management System | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -MANGMT-UMMMC | Mine Monitoring and Control | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -MANGMT-UMENG | Engine Management System | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-TOWPP | Pump Towing | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-HOVLV | Valve Hoist | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-HOPMP | Pump Hoist & Brake | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 85185 | 16330 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-HDTNK | Tank Hydraulic | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -HYDSYS | Hydraulic System | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -GRSYST-GRTNK | Auto Lube Pump | 85185 | 29643 | 7400
CCK-MP-HAUL-DT130 -GRSYST-GRINJ | Auto Lube Injectors | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -GRSYST-ALBPP | Auto Lube Pump | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -FRSUPP | Fire Suppression System | 85185 | 52956 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-DRSHT | Transmission Drive Shaft | 85185 | 10692 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-DIFFL | Differential | 85185 | 15131 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 85185 | 16330 | 7400
CCK-MP-HAUL-DT130 -ENGINE-PMPDR | Pump Drive | 85185 | 16330 | 7400
CCK-MP-HAUL-DT130 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83925 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83925 | 48479 | 7400
CCK-MP-HAUL-DT130 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83925 | 48479 | 7400
CCK-MP-HAUL-DT130 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 83925 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 83925 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 83925 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 83925 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-INTEX-EXHST | Exhaust System | 83925 | 83925 | 7400
CCK-MP-HAUL-DT130 -ENGINE-INTEX-AFTER | Aftercooler | 83925 | 48479 | 7400
CCK-MP-HAUL-DT130 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83925 | 48479 | 7400
CCK-MP-HAUL-DT130 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83925 | 48479 | 7400
CCK-MP-HAUL-DT130 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 83925 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83925 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83925 | 48479 | 7400
CCK-MP-HAUL-DT130 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 83925 | 83925 | 7400
CCK-MP-HAUL-DT130 -ENGINE-COSYS-RADTR | Radiator Coolant | 85185 | 60620 | 7400
CCK-MP-HAUL-DT130 -ENGINE-COSYS-RADTR | Radiator Engine | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -ENGINE | Engine Assembly Caterpillar C175-16 | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -ELCTLV-START-STMUP | Starter Motor Upper | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -ELCTLV-START-STMLO | Starter Motor Lower | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -ELCTLV-CHARG-BATTY | Batteries | 85185 | 33489 | 7400
CCK-MP-HAUL-DT130 -ELCTLV-CHARG-ALTER | Alternator 24V | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-PRKPP | Pump Park Brake Release | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-MERTR | Mechanical Retarder | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-HYFPP | Pump Brake Cooling | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BRVTR | Valve Brake Treadle | 85185 | 85185 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BRVLV | Valve Brake | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 85185 | 15131 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 85185 | 15131 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 85185 | 15131 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 85185 | 7959 | 7400
CCK-MP-HAUL-DT130 | DT130 Lubrication & Mechanical Services | 83925 | 83925 | 7400
CCK-MP-HAUL-DT130 | Caterpillar 793F Haul Truck DT130 | 85185 | 85185 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STACC | Accum Steer Rear | 27545 | 27545 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STACC | Accum Steer Middle | 27545 | 27545 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STACC | Accum Steer Front | 27545 | 27545 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BACCM | Accum Brake Rear | 27545 | 27545 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BACCM | Accum Brake Front RH | 27545 | 27545 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BACCM | Accum Brake Front LH | 27545 | 27545 | 7400
CCK-MP-HAUL-DT127 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83059 | 54690 | 7400
CCK-MP-HAUL-DT127 -ELCTLV-HARNS | Electrical Harness | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -ELCTLV-LIGHT | DT127 Lighting Low Voltage | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41427 | 41427 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41427 | 41427 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 83059 | 15222 | 7400
CCK-MP-HAUL-DT127 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83059 | 9436 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STOCO | Steering Oil Cooler | 83059 | 7188 | 7400
CCK-MP-HAUL-DT127 -STRUCT-SUSPN | Suspension | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -TRNSYS-TRQUE-TRQHO | Torque Converter Hoses | 83059 | 52365 | 7400
CCK-MP-HAUL-DT127 -TRNSYS-TRANS-TRNHO | Transmission Hoses | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN | Operators Cabin | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STHLF-STRHO | Steering System Hoses | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STLTR-STBST | Ball Studs | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-TCVLV | Valve Traction Control | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CHASS-LNKLL | Lower Tag Link | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CHASS-LNKLU | Upper Tag Link | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -ENGINE | Bearing Roll | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -TRNSYS-TRQUE | Torque Converter | 83059 | 7188 | 7400
CCK-MP-HAUL-DT127 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83059 | 51296 | 7400
CCK-MP-HAUL-DT127 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -TRNSYS-TROLC | Oil Cooler Transmission | 83059 | 14187 | 7400
CCK-MP-HAUL-DT127 -TRNSYS-TRANS | Transmission | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRUCT-TRAYS | Tray | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83059 | 18116 | 7400
CCK-MP-HAUL-DT127 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83059 | 12964 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CHASS | Chassis | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-SBELT | Seat Belt | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-AIRCN | Air Con Lines | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-AIRCN | Air Con Condenser | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83059 | 15300 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83059 | 11091 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83059 | 11091 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83059 | 29032 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STHMU | Steering HMU | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STCON-STWHL | Steering Wheel | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STCON-STCOL | Steering Column | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -MANGMT-UMTRN | Power Train Management System | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -MANGMT-UMMMC | Mine Monitoring and Control | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -MANGMT-UMENG | Engine Management System | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-TOWPP | Pump Towing | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-HOVLV | Valve Hoist | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-HOPMP | Pump Hoist & Brake | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-HDTNK | Tank Hydraulic | 83059 | 54690 | 7400
CCK-MP-HAUL-DT127 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -HYDSYS | Hydraulic System | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -GRSYST-GRTNK | Auto Lube Pump | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -GRSYST-GRINJ | Auto Lube Injectors | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -GRSYST-ALBPP | Auto Lube Pump | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FRSUPP | Fire Suppression System | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-DRSHT | Transmission Drive Shaft | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-DIFFL | Differential | 83059 | 9436 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-PMPDR | Pump Drive | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83059 | 74134 | 7400
CCK-MP-HAUL-DT127 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83059 | 56072 | 7400
CCK-MP-HAUL-DT127 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-INTEX-EXHST | Exhaust System | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -ENGINE-INTEX-AFTER | Aftercooler | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83059 | 74134 | 7400
CCK-MP-HAUL-DT127 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83059 | 74134 | 7400
CCK-MP-HAUL-DT127 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 83059 | 41532 | 7400
CCK-MP-HAUL-DT127 -ENGINE-COSYS-RADTR | Radiator Coolant | 83059 | 54690 | 7400
CCK-MP-HAUL-DT127 -ENGINE-COSYS-RADTR | Radiator Engine | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -ENGINE | Engine Assembly Caterpillar C175-16 | 83059 | 3460 | 7400
CCK-MP-HAUL-DT127 -ELCTLV-START-STMUP | Starter Motor Upper | 83059 | 16965 | 7400
CCK-MP-HAUL-DT127 -ELCTLV-START-STMLO | Starter Motor Lower | 83059 | 16965 | 7400
CCK-MP-HAUL-DT127 -ELCTLV-CHARG-BATTY | Batteries | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -ELCTLV-CHARG-ALTER | Alternator 24V | 83059 | 21718 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83059 | 61206 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83059 | 61206 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83059 | 61206 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83059 | 61206 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-PRKPP | Pump Park Brake Release | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-MERTR | Mechanical Retarder | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-HYFPP | Pump Brake Cooling | 83059 | 3455 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BRVTR | Valve Brake Treadle | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BRVLV | Valve Brake | 83059 | 27545 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 83059 | 2333 | 7400
CCK-MP-HAUL-DT127 | DT127 Lubrication & Mechanical Services | 83059 | 83059 | 7400
CCK-MP-HAUL-DT127 | Caterpillar 793F Haul Truck DT127 | 83059 | 83059 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STACC | Accum Steer Rear | 15402 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STACC | Accum Steer Middle | 15402 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STACC | Accum Steer Front | 15402 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BACCM | Accum Brake Rear | 15402 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BACCM | Accum Brake Front RH | 15402 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BACCM | Accum Brake Front LH | 15402 | 15402 | 7400
CCK-MP-HAUL-DT126 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 88657 | 56523 | 7400
CCK-MP-HAUL-DT126 -ELCTLV-HARNS | Electrical Harness | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -ELCTLV-LIGHT | DT126 Lighting Low Voltage | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43232 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43232 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 88657 | 1218 | 7400
CCK-MP-HAUL-DT126 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 88657 | 3048 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 88657 | 132 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 88657 | 2432 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -STRUCT-SUSPN | Suspension | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STOCO | Steering Oil Cooler | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 88657 | 39846 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 88657 | 39846 | 7400
CCK-MP-HAUL-DT126 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 88657 | 39846 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-ELECT | Cabin Electrical System | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN | Operators Cabin | 88657 | 1218 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STHLF-STRHO | Steering System Hoses | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STLTR-STBST | Ball Studs | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 88657 | 25809 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 88657 | 25790 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-TCVLV | Valve Traction Control | 88657 | 63919 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CHASS-LNKLL | Lower Tag Link | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CHASS-LNKLU | Upper Tag Link | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ENGINE | Bearing Roll | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -TRNSYS-TRQUE | Torque Converter | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 88657 | 69114 | 7400
CCK-MP-HAUL-DT126 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -TRNSYS-TROLC | Oil Cooler Transmission | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -TRNSYS-TRANS | Transmission | 88657 | 2432 | 7400
CCK-MP-HAUL-DT126 -STRUCT-TRAYS | Tray | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CHASS | Chassis | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-SEATS | Operators Seat | 88657 | 1218 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-SBELT | Seat Belt | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-AIRCN | Air Con Lines | 88657 | 54006 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-AIRCN | Air Con Condenser | 88657 | 63919 | 7400
CCK-MP-HAUL-DT126 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 88657 | 39846 | 7400
CCK-MP-HAUL-DT126 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 88657 | 3048 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 88657 | 7138 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 88657 | 7138 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STLTR | Steering Linkages and Tie Rods | 88657 | 132 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STHMU | Steering HMU | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STCON-STWHL | Steering Wheel | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STCON-STCOL | Steering Column | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -STRSYS-STACC-SACCF | Accumulator Steering Front | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -MANGMT-UMTRN | Power Train Management System | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -MANGMT-UMMMC | Mine Monitoring and Control | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -MANGMT-UMENG | Engine Management System | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-TOWPP | Pump Towing | 88657 | 54006 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-HOVLV | Valve Hoist | 88657 | 39846 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-HOPMP | Pump Hoist & Brake | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 88657 | 28279 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 88657 | 25780 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-HDTNK | Tank Hydraulic | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -HYDSYS | Hydraulic System | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -GRSYST-GRTNK | Auto Lube Pump | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -GRSYST-GRINJ | Auto Lube Injectors | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -GRSYST-ALBPP | Auto Lube Pump | 88657 | 14100 | 7400
CCK-MP-HAUL-DT126 -FRSUPP | Fire Suppression System | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 88657 | 2432 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 88657 | 2432 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-DRSHT | Transmission Drive Shaft | 88657 | 7138 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-DIFFL | Differential | 88657 | 2432 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 88657 | 25780 | 7400
CCK-MP-HAUL-DT126 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 88657 | 7775 | 7400
CCK-MP-HAUL-DT126 -ENGINE-PMPDR | Pump Drive | 88657 | 25790 | 7400
CCK-MP-HAUL-DT126 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 88657 | 62221 | 7400
CCK-MP-HAUL-DT126 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ENGINE-INTEX-EXHST | Exhaust System | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -ENGINE-INTEX-AFTER | Aftercooler | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 88657 | 63919 | 7400
CCK-MP-HAUL-DT126 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 88657 | 63919 | 7400
CCK-MP-HAUL-DT126 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -ENGINE-COSYS-WTRPP | Water Pump Engine | 88657 | 35265 | 7400
CCK-MP-HAUL-DT126 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -ENGINE-COSYS-RADTR | Radiator Coolant | 88657 | 78969 | 7400
CCK-MP-HAUL-DT126 -ENGINE-COSYS-RADTR | Radiator Engine | 88657 | 2432 | 7400
CCK-MP-HAUL-DT126 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 88657 | 36707 | 7400
CCK-MP-HAUL-DT126 -ENGINE | Engine Assembly Caterpillar C175-16 | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ELCTLV-START-STMUP | Starter Motor Upper | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -ELCTLV-START-STMLO | Starter Motor Lower | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -ELCTLV-CHARG-BATTY | Batteries | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -ELCTLV-CHARG-ALTER | Alternator 24V | 88657 | 2403 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-PRKPP | Pump Park Brake Release | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-MERTR | Mechanical Retarder | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-HYFPP | Pump Brake Cooling | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BRVTR | Valve Brake Treadle | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BRVLV | Valve Brake | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 88651 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 88657 | 15402 | 7400
CCK-MP-HAUL-DT126 | DT126 Lubrication & Mechanical Services | 88657 | 88657 | 7400
CCK-MP-HAUL-DT126 | Caterpillar 793F Haul Truck DT126 | 88657 | 88657 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STACC | Accum Steer Rear | 33202 | 33202 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STACC | Accum Steer Middle | 33202 | 33202 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STACC | Accum Steer Front | 33202 | 33202 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BACCM | Accum Brake Rear | 33202 | 33202 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BACCM | Accum Brake Front RH | 33202 | 33202 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BACCM | Accum Brake Front LH | 33202 | 33202 | 7400
CCK-MP-HAUL-DT100 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 87135 | 53844 | 7400
CCK-MP-HAUL-DT100 -ELCTLV-HARNS | Electrical Harness | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -ELCTLV-LIGHT | DT100 Lighting Low Voltage | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41858 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41858 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 87135 | 864 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 87135 | 5703 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STOCO | Steering Oil Cooler | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRUCT-SUSPN | Suspension | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-ELECT | Cabin Electrical System | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN | Operators Cabin | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STHLF-STRHO | Steering System Hoses | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STLTR-STBST | Ball Studs | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-TCVLV | Valve Traction Control | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CHASS-LNKLL | Lower Tag Link | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CHASS-LNKLU | Upper Tag Link | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE | Bearing Roll | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -TRNSYS-TRQUE | Torque Converter | 87135 | 17914 | 7400
CCK-MP-HAUL-DT100 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -TRNSYS-TROLC | Oil Cooler Transmission | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -TRNSYS-TRANS | Transmission | 87135 | 5195 | 7400
CCK-MP-HAUL-DT100 -STRUCT-TRAYS | Tray | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 87135 | 864 | 7400
CCK-MP-HAUL-DT100 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 87135 | 23110 | 7400
CCK-MP-HAUL-DT100 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CHASS | Chassis | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-SEATS | Operators Seat | 87135 | 19823 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-SBELT | Seat Belt | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-AIRCN | Air Con Lines | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-AIRCN | Air Con Condenser | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 87135 | 23110 | 7400
CCK-MP-HAUL-DT100 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 87135 | 14184 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 87135 | 864 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STLTR | Steering Linkages and Tie Rods | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STHMU | Steering HMU | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STCON-STWHL | Steering Wheel | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STCON-STCOL | Steering Column | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -STRSYS-STACC-SACCF | Accumulator Steering Front | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -MANGMT-UMTRN | Power Train Management System | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -MANGMT-UMMMC | Mine Monitoring and Control | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -MANGMT-UMENG | Engine Management System | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-TOWPP | Pump Towing | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-HOVLV | Valve Hoist | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-HOPMP | Pump Hoist & Brake | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-HDTNK | Tank Hydraulic | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -HYDSYS | Hydraulic System | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -GRSYST-GRTNK | Auto Lube Pump | 87135 | 67766 | 7400
CCK-MP-HAUL-DT100 -GRSYST-GRINJ | Auto Lube Injectors | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -GRSYST-ALBPP | Auto Lube Pump | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -FRSUPP | Fire Suppression System | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-DRSHT | Transmission Drive Shaft | 87135 | 17914 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-DIFFL | Differential | 87135 | 914 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87135 | 863 | 7400
CCK-MP-HAUL-DT100 -ENGINE-PMPDR | Pump Drive | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 87135 | 77896 | 7400
CCK-MP-HAUL-DT100 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-INTEX-EXHST | Exhaust System | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -ENGINE-INTEX-AFTER | Aftercooler | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 87135 | 55160 | 7400
CCK-MP-HAUL-DT100 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 87135 | 54114 | 7400
CCK-MP-HAUL-DT100 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-COSYS-WTRPP | Water Pump Engine | 87135 | 54114 | 7400
CCK-MP-HAUL-DT100 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -ENGINE-COSYS-RADTR | Radiator Coolant | 87135 | 33202 | 7400
CCK-MP-HAUL-DT100 -ENGINE-COSYS-RADTR | Radiator Engine | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 87135 | 49049 | 7400
CCK-MP-HAUL-DT100 -ENGINE | Engine Assembly Caterpillar C175-16 | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ELCTLV-START-STMUP | Starter Motor Upper | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ELCTLV-START-STMLO | Starter Motor Lower | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ELCTLV-CHARG-BATTY | Batteries | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -ELCTLV-CHARG-ALTER | Alternator 24V | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-PRKPP | Pump Park Brake Release | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-MERTR | Mechanical Retarder | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-HYFPP | Pump Brake Cooling | 87135 | 19314 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BRVTR | Valve Brake Treadle | 87135 | 87135 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BRVLV | Valve Brake | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87135 | 15281 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87135 | 15281 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 87135 | 12861 | 7400
CCK-MP-HAUL-DT100 | DT100 Lubrication & Mechanical Services | 85551 | 85551 | 7400
CCK-MP-HAUL-DT100 | Caterpillar 793F Haul Truck DT100 | 87135 | 87135 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STACC | Accum Steer Rear | 32853 | 32853 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STACC | Accum Steer Middle | 32853 | 32853 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STACC | Accum Steer Front | 32853 | 32853 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BACCM | Accum Brake Rear | 32853 | 32853 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BACCM | Accum Brake Front RH | 32853 | 32853 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BACCM | Accum Brake Front LH | 32853 | 32853 | 7400
CCK-MP-HAUL-DT099 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 87442 | 58445 | 7400
CCK-MP-HAUL-DT099 -ELCTLV-HARNS | Electrical Harness | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -ELCTLV-LIGHT | DT099 Lighting Low Voltage | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42476 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42476 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 87442 | 17201 | 7400
CCK-MP-HAUL-DT099 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STOCO | Steering Oil Cooler | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-SUSPN | Suspension | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 87442 | 32853 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 87442 | 14729 | 7400
CCK-MP-HAUL-DT099 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 87442 | 14731 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-ELECT | Cabin Electrical System | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN | Operators Cabin | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STHLF-STRHO | Steering System Hoses | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STLTR-STBST | Ball Studs | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-TCVLV | Valve Traction Control | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CHASS-LNKLL | Lower Tag Link | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CHASS-LNKLU | Upper Tag Link | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE | Bearing Roll | 87442 | 32853 | 7400
CCK-MP-HAUL-DT099 -TRNSYS-TRQUE | Torque Converter | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -TRNSYS-TROLC | Oil Cooler Transmission | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -TRNSYS-TRANS | Transmission | 87442 | 14731 | 7400
CCK-MP-HAUL-DT099 -STRUCT-TRAYS | Tray | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 87442 | 7956 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CHASS | Chassis | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-SEATS | Operators Seat | 87442 | 4777 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-SBELT | Seat Belt | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-AIRCN | Air Con Lines | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-AIRCN | Air Con Condenser | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 87442 | 17201 | 7400
CCK-MP-HAUL-DT099 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 87442 | 14731 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 87442 | 8961 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STLTR | Steering Linkages and Tie Rods | 87442 | 32853 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STHMU | Steering HMU | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STCON-STWHL | Steering Wheel | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STCON-STCOL | Steering Column | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -STRSYS-STACC-SACCF | Accumulator Steering Front | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -MANGMT-UMTRN | Power Train Management System | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -MANGMT-UMMMC | Mine Monitoring and Control | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -MANGMT-UMENG | Engine Management System | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-TOWPP | Pump Towing | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-HOVLV | Valve Hoist | 87442 | 32853 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-HOPMP | Pump Hoist & Brake | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87442 | 23283 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-HDTNK | Tank Hydraulic | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -HYDSYS | Hydraulic System | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -GRSYST-GRTNK | Auto Lube Pump | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -GRSYST-GRINJ | Auto Lube Injectors | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -GRSYST-ALBPP | Auto Lube Pump | 87442 | 14730 | 7400
CCK-MP-HAUL-DT099 -FRSUPP | Fire Suppression System | 87442 | 53489 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87442 | 19843 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-DRSHT | Transmission Drive Shaft | 87442 | 14731 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-DIFFL | Differential | 87442 | 14781 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87442 | 3410 | 7400
CCK-MP-HAUL-DT099 -ENGINE-PMPDR | Pump Drive | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 87442 | 76793 | 7400
CCK-MP-HAUL-DT099 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-INTEX-EXHST | Exhaust System | 87442 | 76903 | 7400
CCK-MP-HAUL-DT099 -ENGINE-INTEX-AFTER | Aftercooler | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 87442 | 76793 | 7400
CCK-MP-HAUL-DT099 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-COSYS-WTRPP | Water Pump Engine | 87442 | 76793 | 7400
CCK-MP-HAUL-DT099 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 87442 | 32853 | 7400
CCK-MP-HAUL-DT099 -ENGINE-COSYS-RADTR | Radiator Coolant | 87442 | 32853 | 7400
CCK-MP-HAUL-DT099 -ENGINE-COSYS-RADTR | Radiator Engine | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 87442 | 43951 | 7400
CCK-MP-HAUL-DT099 -ENGINE | Engine Assembly Caterpillar C175-16 | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ELCTLV-START-STMUP | Starter Motor Upper | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ELCTLV-START-STMLO | Starter Motor Lower | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -ELCTLV-CHARG-BATTY | Batteries | 87442 | 14729 | 7400
CCK-MP-HAUL-DT099 -ELCTLV-CHARG-ALTER | Alternator 24V | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87442 | 35935 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-PRKPP | Pump Park Brake Release | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-MERTR | Mechanical Retarder | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-HYFPP | Pump Brake Cooling | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BRVTR | Valve Brake Treadle | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BRVLV | Valve Brake | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 87442 | 10255 | 7400
CCK-MP-HAUL-DT099 | DT099 Lubrication & Mechanical Services | 87442 | 87442 | 7400
CCK-MP-HAUL-DT099 | Caterpillar 793F Haul Truck DT099 | 87442 | 87442 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STACC | Accum Steer Rear | 27705 | 27705 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STACC | Accum Steer Middle | 27705 | 27705 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STACC | Accum Steer Front | 27705 | 27705 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BACCM | Accum Brake Rear | 31770 | 31770 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BACCM | Accum Brake Front RH | 27705 | 27705 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BACCM | Accum Brake Front LH | 27705 | 27705 | 7400
CCK-MP-HAUL-DT097 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83804 | 55979 | 7400
CCK-MP-HAUL-DT097 -ELCTLV-HARNS | Electrical Harness | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -ELCTLV-LIGHT | DT097 Lighting Low Voltage | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42089 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42089 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 83804 | 642 | 7400
CCK-MP-HAUL-DT097 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83804 | 3219 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STOCO | Steering Oil Cooler | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-SUSPN | Suspension | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83804 | 33534 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83804 | 17425 | 7400
CCK-MP-HAUL-DT097 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83804 | 17427 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN | Operators Cabin | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STHLF-STRHO | Steering System Hoses | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STLTR-STBST | Ball Studs | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-TCVLV | Valve Traction Control | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CHASS-LNKLL | Lower Tag Link | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CHASS-LNKLU | Upper Tag Link | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE | Bearing Roll | 83732 | 33462 | 7400
CCK-MP-HAUL-DT097 -TRNSYS-TRQUE | Torque Converter | 83804 | 7897 | 7400
CCK-MP-HAUL-DT097 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83804 | 69471 | 7400
CCK-MP-HAUL-DT097 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -TRNSYS-TROLC | Oil Cooler Transmission | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -TRNSYS-TRANS | Transmission | 83804 | 17427 | 7400
CCK-MP-HAUL-DT097 -STRUCT-TRAYS | Tray | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83804 | 22486 | 7400
CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CHASS | Chassis | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-SEATS | Operators Seat | 83804 | 1377 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-SBELT | Seat Belt | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-AIRCN | Air Con Lines | 83804 | 33534 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-AIRCN | Air Con Condenser | 83804 | 33534 | 7400
CCK-MP-HAUL-DT097 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 83804 | 33534 | 7400
CCK-MP-HAUL-DT097 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83804 | 642 | 7400
CCK-MP-HAUL-DT097 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83804 | 1815 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83804 | 1815 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83804 | 22315 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STHMU | Steering HMU | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STCON-STWHL | Steering Wheel | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STCON-STCOL | Steering Column | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -MANGMT-UMTRN | Power Train Management System | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -MANGMT-UMMMC | Mine Monitoring and Control | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -MANGMT-UMENG | Engine Management System | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-TOWPP | Pump Towing | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-HOVLV | Valve Hoist | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-HOPMP | Pump Hoist & Brake | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83804 | 17428 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83804 | 22316 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-HDTNK | Tank Hydraulic | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -HYDSYS | Hydraulic System | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -GRSYST-GRTNK | Auto Lube Pump | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -GRSYST-GRINJ | Auto Lube Injectors | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -GRSYST-ALBPP | Auto Lube Pump | 83804 | 2994 | 7400
CCK-MP-HAUL-DT097 -FRSUPP | Fire Suppression System | 83804 | 56066 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83804 | 10189 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-DRSHT | Transmission Drive Shaft | 83804 | 15765 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-DIFFL | Differential | 83804 | 17427 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83804 | 51166 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-PMPDR | Pump Drive | 83804 | 22315 | 7400
CCK-MP-HAUL-DT097 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83804 | 53205 | 7400
CCK-MP-HAUL-DT097 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-INTEX-EXHST | Exhaust System | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -ENGINE-INTEX-AFTER | Aftercooler | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83804 | 53205 | 7400
CCK-MP-HAUL-DT097 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83804 | 53205 | 7400
CCK-MP-HAUL-DT097 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83804 | 74795 | 7400
CCK-MP-HAUL-DT097 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 83804 | 33534 | 7400
CCK-MP-HAUL-DT097 -ENGINE-COSYS-RADTR | Radiator Coolant | 83804 | 33534 | 7400
CCK-MP-HAUL-DT097 -ENGINE-COSYS-RADTR | Radiator Engine | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -ENGINE | Engine Assembly Caterpillar C175-16 | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ELCTLV-START-STMUP | Starter Motor Upper | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ELCTLV-START-STMLO | Starter Motor Lower | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -ELCTLV-CHARG-BATTY | Batteries | 83804 | 17428 | 7400
CCK-MP-HAUL-DT097 -ELCTLV-CHARG-ALTER | Alternator 24V | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-PRKPP | Pump Park Brake Release | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-MERTR | Mechanical Retarder | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-HYFPP | Pump Brake Cooling | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BRVTR | Valve Brake Treadle | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BRVLV | Valve Brake | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 83804 | 11742 | 7400
CCK-MP-HAUL-DT097 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 83756 | 11742 | 7400
CCK-MP-HAUL-DT097 | DT097 Lubrication & Mechanical Services | 83804 | 83804 | 7400
CCK-MP-HAUL-DT097 | Caterpillar 793F Haul Truck DT097 | 83804 | 83804 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STACC | Accum Steer Rear | 21836 | 21836 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STACC | Accum Steer Middle | 21836 | 21836 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STACC | Accum Steer Front | 21836 | 21836 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BACCM | Accum Brake Rear | 21836 | 21836 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BACCM | Accum Brake Front RH | 21836 | 21836 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BACCM | Accum Brake Front LH | 21836 | 21836 | 7400
CCK-MP-HAUL-DT095 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 88921 | 59269 | 7400
CCK-MP-HAUL-DT095 -ELCTLV-HARNS | Electrical Harness | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -ELCTLV-LIGHT | DT095 Lighting Low Voltage | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41798 | 41798 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41798 | 41798 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 88921 | 11408 | 7400
CCK-MP-HAUL-DT095 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 88921 | 10426 | 7400
CCK-MP-HAUL-DT095 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -STRUCT-SUSPN | Suspension | 88921 | 59461 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STOCO | Steering Oil Cooler | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 88921 | 47532 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-ELECT | Cabin Electrical System | 88921 | 49753 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN | Operators Cabin | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STHLF-STRHO | Steering System Hoses | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STLTR-STBST | Ball Studs | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-TCVLV | Valve Traction Control | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CHASS-LNKLL | Lower Tag Link | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CHASS-LNKLU | Upper Tag Link | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -ENGINE | Bearing Roll | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -TRNSYS-TRQUE | Torque Converter | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -TRNSYS-TROLC | Oil Cooler Transmission | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -TRNSYS-TRANS | Transmission | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -STRUCT-TRAYS | Tray | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CHASS | Chassis | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-SEATS | Operators Seat | 88921 | 3966 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-SBELT | Seat Belt | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-AIRCN | Air Con Lines | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-AIRCN | Air Con Condenser | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 88921 | 23253 | 7400
CCK-MP-HAUL-DT095 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 88921 | 17105 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 88921 | 12649 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 88921 | 12649 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STLTR | Steering Linkages and Tie Rods | 88921 | 33241 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STHMU | Steering HMU | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STCON-STWHL | Steering Wheel | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STCON-STCOL | Steering Column | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -STRSYS-STACC-SACCF | Accumulator Steering Front | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -MANGMT-UMTRN | Power Train Management System | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -MANGMT-UMMMC | Mine Monitoring and Control | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -MANGMT-UMENG | Engine Management System | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-TOWPP | Pump Towing | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-HOVLV | Valve Hoist | 88921 | 40108 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-HOPMP | Pump Hoist & Brake | 88921 | 3614 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 88921 | 4016 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-HDTNK | Tank Hydraulic | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -HYDSYS | Hydraulic System | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -GRSYST-GRTNK | Auto Lube Pump | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -GRSYST-GRINJ | Auto Lube Injectors | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -GRSYST-ALBPP | Auto Lube Pump | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -FRSUPP | Fire Suppression System | 88921 | 58628 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 88921 | 14281 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 88921 | 1836 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-DRSHT | Transmission Drive Shaft | 88921 | 9465 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-DIFFL | Differential | 88921 | 10426 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 88921 | 40108 | 7400
CCK-MP-HAUL-DT095 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 88921 | 10426 | 7400
CCK-MP-HAUL-DT095 -ENGINE-PMPDR | Pump Drive | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-INTEX-EXHST | Exhaust System | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -ENGINE-INTEX-AFTER | Aftercooler | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ENGINE-COSYS-WTRPP | Water Pump Engine | 88921 | 28299 | 7400
CCK-MP-HAUL-DT095 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -ENGINE-COSYS-RADTR | Radiator Coolant | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -ENGINE-COSYS-RADTR | Radiator Engine | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -ENGINE | Engine Assembly Caterpillar C175-16 | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ELCTLV-START-STMUP | Starter Motor Upper | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ELCTLV-START-STMLO | Starter Motor Lower | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -ELCTLV-CHARG-BATTY | Batteries | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -ELCTLV-CHARG-ALTER | Alternator 24V | 88921 | 3967 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 88921 | 9465 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 88921 | 9465 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-PRKPP | Pump Park Brake Release | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-MERTR | Mechanical Retarder | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-HYFPP | Pump Brake Cooling | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BRVTR | Valve Brake Treadle | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BRVLV | Valve Brake | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 88921 | 21880 | 7400
CCK-MP-HAUL-DT095 | DT095 Lubrication & Mechanical Services | 88921 | 88921 | 7400
CCK-MP-HAUL-DT095 | Caterpillar 793F Haul Truck DT095 | 88921 | 88921 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STACC | Accum Steer Rear | 15729 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STACC | Accum Steer Middle | 15729 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STACC | Accum Steer Front | 15729 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BACCM | Accum Brake Rear | 15729 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BACCM | Accum Brake Front RH | 15729 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BACCM | Accum Brake Front LH | 15729 | 15729 | 7400
CCK-MP-HAUL-DT094 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 88788 | 59280 | 7400
CCK-MP-HAUL-DT094 -ELCTLV-HARNS | Electrical Harness | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -ELCTLV-LIGHT | DT094 Lighting Low Voltage | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43007 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43007 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 88788 | 14444 | 7400
CCK-MP-HAUL-DT094 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 88788 | 3009 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-SUSPN | Suspension | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STOCO | Steering Oil Cooler | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 88788 | 30693 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-ELECT | Cabin Electrical System | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN | Operators Cabin | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STHLF-STRHO | Steering System Hoses | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STLTR-STBST | Ball Studs | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 88788 | 24241 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 88788 | 24241 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-TCVLV | Valve Traction Control | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CHASS-LNKLL | Lower Tag Link | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CHASS-LNKLU | Upper Tag Link | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 88788 | 24241 | 7400
CCK-MP-HAUL-DT094 -ENGINE | Bearing Roll | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -TRNSYS-TRQUE | Torque Converter | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -TRNSYS-TROLC | Oil Cooler Transmission | 88788 | 5404 | 7400
CCK-MP-HAUL-DT094 -TRNSYS-TRANS | Transmission | 88788 | 5404 | 7400
CCK-MP-HAUL-DT094 -STRUCT-TRAYS | Tray | 88788 | 88788 | 7300
CCK-MP-HAUL-DT094 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 88788 | 21945 | 7400
CCK-MP-HAUL-DT094 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 88788 | 3009 | 7400
CCK-MP-HAUL-DT094 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CHASS | Chassis | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-SEATS | Operators Seat | 88788 | 12373 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-SBELT | Seat Belt | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-AIRCN | Air Con Lines | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-AIRCN | Air Con Condenser | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 88788 | 4191 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STLTR | Steering Linkages and Tie Rods | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STHMU | Steering HMU | 88788 | 42099 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STCON-STWHL | Steering Wheel | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STCON-STCOL | Steering Column | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -STRSYS-STACC-SACCF | Accumulator Steering Front | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -MANGMT-UMTRN | Power Train Management System | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -MANGMT-UMMMC | Mine Monitoring and Control | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -MANGMT-UMENG | Engine Management System | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-TOWPP | Pump Towing | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-HOVLV | Valve Hoist | 88788 | 42099 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-HOPMP | Pump Hoist & Brake | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 88788 | 24241 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 88788 | 24241 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-HDTNK | Tank Hydraulic | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -HYDSYS | Hydraulic System | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -GRSYST-GRTNK | Auto Lube Pump | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -GRSYST-GRINJ | Auto Lube Injectors | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -GRSYST-ALBPP | Auto Lube Pump | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -FRSUPP | Fire Suppression System | 88788 | 37893 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-DRSHT | Transmission Drive Shaft | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-DIFFL | Differential | 88788 | 5404 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 88788 | 11570 | 7400
CCK-MP-HAUL-DT094 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 88788 | 24241 | 7400
CCK-MP-HAUL-DT094 -ENGINE-PMPDR | Pump Drive | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ENGINE-INTEX-EXHST | Exhaust System | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -ENGINE-INTEX-AFTER | Aftercooler | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ENGINE-COSYS-WTRPP | Water Pump Engine | 88788 | 50851 | 7400
CCK-MP-HAUL-DT094 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 88788 | 63889 | 7400
CCK-MP-HAUL-DT094 -ENGINE-COSYS-RADTR | Radiator Coolant | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -ENGINE-COSYS-RADTR | Radiator Engine | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 88788 | 63889 | 7400
CCK-MP-HAUL-DT094 -ENGINE | Engine Assembly Caterpillar C175-16 | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ELCTLV-START-STMUP | Starter Motor Upper | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -ELCTLV-START-STMLO | Starter Motor Lower | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -ELCTLV-CHARG-BATTY | Batteries | 88788 | 31228 | 7400
CCK-MP-HAUL-DT094 -ELCTLV-CHARG-ALTER | Alternator 24V | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 88788 | 23617 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 88788 | 245 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-PRKPP | Pump Park Brake Release | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-MERTR | Mechanical Retarder | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-HYFPP | Pump Brake Cooling | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BRVTR | Valve Brake Treadle | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BRVLV | Valve Brake | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 88788 | 3009 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 88788 | 3009 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 88788 | 15729 | 7400
CCK-MP-HAUL-DT094 | DT094 Lubrication & Mechanical Services | 88788 | 88788 | 7400
CCK-MP-HAUL-DT094 | Caterpillar 793F Haul Truck DT094 | 88788 | 88788 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STACC | Accum Steer Rear | 23814 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STACC | Accum Steer Middle | 23814 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STACC | Accum Steer Front | 23814 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BACCM | Accum Brake Rear | 23814 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BACCM | Accum Brake Front RH | 23814 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BACCM | Accum Brake Front LH | 23814 | 23814 | 7400
CCK-MP-HAUL-DT091 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83859 | 59368 | 7400
CCK-MP-HAUL-DT091 -ELCTLV-HARNS | Electrical Harness | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -ELCTLV-LIGHT | DT091 Lighting Low Voltage | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43953 | 43953 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43953 | 43953 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 83859 | 16663 | 7400
CCK-MP-HAUL-DT091 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 83859 | 15238 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STOCO | Steering Oil Cooler | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -STRUCT-SUSPN | Suspension | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN | Operators Cabin | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STHLF-STRHO | Steering System Hoses | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE | Bearing Roll | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -TRNSYS-TRQUE | Torque Converter | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83859 | 51764 | 7400
CCK-MP-HAUL-DT091 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -TRNSYS-TROLC | Oil Cooler Transmission | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -TRNSYS-TRANS | Transmission | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -STRUCT-TRAYS | Tray | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83859 | 23319 | 7400
CCK-MP-HAUL-DT091 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CHASS | Chassis | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN-SEATS | Operators Seat | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN-SBELT | Seat Belt | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN-AIRCN | Air Con Lines | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN-AIRCN | Air Con Condenser | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83859 | 16663 | 7400
CCK-MP-HAUL-DT091 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83859 | 15238 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83859 | 10692 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83859 | 6114 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STHMU | Steering HMU | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STCON-STWHL | Steering Wheel | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STCON-STCOL | Steering Column | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -MANGMT-UMTRN | Power Train Management System | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -MANGMT-UMMMC | Mine Monitoring and Control | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -MANGMT-UMENG | Engine Management System | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-TOWPP | Pump Towing | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-HOVLV | Valve Hoist | 83859 | 52433 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-HOPMP | Pump Hoist & Brake | 83859 | 12954 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83859 | 8499 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-HDTNK | Tank Hydraulic | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -HYDSYS | Hydraulic System | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -GRSYST-GRTNK | Auto Lube Pump | 83859 | 66034 | 7400
CCK-MP-HAUL-DT091 -GRSYST-GRINJ | Auto Lube Injectors | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -GRSYST-ALBPP | Auto Lube Pump | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -FRSUPP | Fire Suppression System | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83859 | 15032 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83859 | 12431 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-DRSHT | Transmission Drive Shaft | 83859 | 11975 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-DIFFL | Differential | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 83859 | 5241 | 7400
CCK-MP-HAUL-DT091 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83859 | 12875 | 7400
CCK-MP-HAUL-DT091 -ENGINE-PMPDR | Pump Drive | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83859 | 77304 | 7400
CCK-MP-HAUL-DT091 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83859 | 44017 | 7400
CCK-MP-HAUL-DT091 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-INTEX-EXHST | Exhaust System | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -ENGINE-INTEX-AFTER | Aftercooler | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83859 | 77304 | 7400
CCK-MP-HAUL-DT091 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 83859 | 11975 | 7400
CCK-MP-HAUL-DT091 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83859 | 11975 | 7400
CCK-MP-HAUL-DT091 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83859 | 77304 | 7400
CCK-MP-HAUL-DT091 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 83859 | 29506 | 7400
CCK-MP-HAUL-DT091 -ENGINE-COSYS-RADTR | Radiator Coolant | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ENGINE-COSYS-RADTR | Radiator Engine | 83859 | 4826 | 7400
CCK-MP-HAUL-DT091 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -ENGINE | Engine Assembly Caterpillar C175-16 | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -ELCTLV-START-STMUP | Starter Motor Upper | 83859 | 11975 | 7400
CCK-MP-HAUL-DT091 -ELCTLV-START-STMLO | Starter Motor Lower | 83859 | 11975 | 7400
CCK-MP-HAUL-DT091 -ELCTLV-CHARG-BATTY | Batteries | 83859 | 18444 | 7400
CCK-MP-HAUL-DT091 -ELCTLV-CHARG-ALTER | Alternator 24V | 83859 | 11975 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83859 | 10692 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83859 | 10692 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-PRKPP | Pump Park Brake Release | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-MERTR | Mechanical Retarder | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-HYFPP | Pump Brake Cooling | 83859 | 12875 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BRVTR | Valve Brake Treadle | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BRVLV | Valve Brake | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83859 | 10692 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83859 | 10692 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 83859 | 23814 | 7400
CCK-MP-HAUL-DT091 | DT091 Lubrication & Mechanical Services | 83859 | 83859 | 7400
CCK-MP-HAUL-DT091 | Caterpillar 793F Haul Truck DT091 | 83859 | 83859 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STACC | Accum Steer Rear | 29105 | 29105 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STACC | Accum Steer Middle | 29105 | 29105 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STACC | Accum Steer Front | 29105 | 29105 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BACCM | Accum Brake Rear | 29105 | 29105 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BACCM | Accum Brake Front RH | 29105 | 29105 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BACCM | Accum Brake Front LH | 29105 | 29105 | 7400
CCK-MP-HAUL-DT090 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 81670 | 54543 | 7400
CCK-MP-HAUL-DT090 -ELCTLV-HARNS | Electrical Harness | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -ELCTLV-LIGHT | DT090 Lighting Low Voltage | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41709 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41709 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 81670 | 18331 | 7400
CCK-MP-HAUL-DT090 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 81670 | 18170 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STOCO | Steering Oil Cooler | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-SUSPN | Suspension | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 81670 | 29126 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 81670 | 29126 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-ELECT | Cabin Electrical System | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN | Operators Cabin | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STHLF-STRHO | Steering System Hoses | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STLTR-STBST | Ball Studs | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-TCVLV | Valve Traction Control | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CHASS-LNKLL | Lower Tag Link | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CHASS-LNKLU | Upper Tag Link | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE | Bearing Roll | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -TRNSYS-TRQUE | Torque Converter | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -TRNSYS-TROLC | Oil Cooler Transmission | 81670 | 15228 | 7400
CCK-MP-HAUL-DT090 -TRNSYS-TRANS | Transmission | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-TRAYS | Tray | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 81670 | 631 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CHASS | Chassis | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-SEATS | Operators Seat | 81670 | 10666 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-SBELT | Seat Belt | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-AIRCN | Air Con Lines | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-AIRCN | Air Con Condenser | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 81670 | 631 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 81670 | 11697 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 81670 | 2498 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STLTR | Steering Linkages and Tie Rods | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STHMU | Steering HMU | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STCON-STWHL | Steering Wheel | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STCON-STCOL | Steering Column | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -STRSYS-STACC-SACCF | Accumulator Steering Front | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -MANGMT-UMTRN | Power Train Management System | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -MANGMT-UMMMC | Mine Monitoring and Control | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -MANGMT-UMENG | Engine Management System | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-TOWPP | Pump Towing | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-HOVLV | Valve Hoist | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-HOPMP | Pump Hoist & Brake | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-HDTNK | Tank Hydraulic | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -HYDSYS | Hydraulic System | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -GRSYST-GRTNK | Auto Lube Pump | 81670 | 65125 | 7400
CCK-MP-HAUL-DT090 -GRSYST-GRINJ | Auto Lube Injectors | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -GRSYST-ALBPP | Auto Lube Pump | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FRSUPP | Fire Suppression System | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-DRSHT | Transmission Drive Shaft | 81670 | 17019 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-DIFFL | Differential | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 81670 | 21807 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-PMPDR | Pump Drive | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 81669 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 81669 | 58817 | 7400
CCK-MP-HAUL-DT090 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 81669 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 81669 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 81669 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 81669 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-INTEX-EXHST | Exhaust System | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -ENGINE-INTEX-AFTER | Aftercooler | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 81670 | 58798 | 7400
CCK-MP-HAUL-DT090 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 81669 | 50360 | 7400
CCK-MP-HAUL-DT090 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 81669 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 81669 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-COSYS-WTRPP | Water Pump Engine | 81669 | 50360 | 7400
CCK-MP-HAUL-DT090 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 81670 | 29126 | 7400
CCK-MP-HAUL-DT090 -ENGINE-COSYS-RADTR | Radiator Coolant | 81670 | 29126 | 7400
CCK-MP-HAUL-DT090 -ENGINE-COSYS-RADTR | Radiator Engine | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -ENGINE | Engine Assembly Caterpillar C175-16 | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ELCTLV-START-STMUP | Starter Motor Upper | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ELCTLV-START-STMLO | Starter Motor Lower | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -ELCTLV-CHARG-BATTY | Batteries | 81670 | 4405 | 7400
CCK-MP-HAUL-DT090 -ELCTLV-CHARG-ALTER | Alternator 24V | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-PRKPP | Pump Park Brake Release | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-MERTR | Mechanical Retarder | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-HYFPP | Pump Brake Cooling | 81670 | 8305 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BRVTR | Valve Brake Treadle | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BRVLV | Valve Brake | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 81670 | 19847 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 81670 | 5994 | 7400
CCK-MP-HAUL-DT090 | DT090 Lubrication & Mechanical Services | 81670 | 81670 | 7400
CCK-MP-HAUL-DT090 | Caterpillar 793F Haul Truck DT090 | 81670 | 81670 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STACC | Accum Steer Rear | 36530 | 36530 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STACC | Accum Steer Middle | 36530 | 36530 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STACC | Accum Steer Front | 36530 | 36530 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BACCM | Accum Brake Rear | 36530 | 36530 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BACCM | Accum Brake Front RH | 36530 | 36530 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BACCM | Accum Brake Front LH | 36530 | 36530 | 7400
CCK-MP-HAUL-DT088 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 89037 | 58879 | 7400
CCK-MP-HAUL-DT088 -ELCTLV-HARNS | Electrical Harness | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -ELCTLV-LIGHT | DT088 Lighting Low Voltage | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42290 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42290 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 89037 | 17080 | 7400
CCK-MP-HAUL-DT088 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 89037 | 5930 | 7400
CCK-MP-HAUL-DT088 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 89037 | 7099 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -STRUCT-SUSPN | Suspension | 89037 | 52640 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STOCO | Steering Oil Cooler | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 89037 | 36530 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 89037 | 36530 | 7400
CCK-MP-HAUL-DT088 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-ELECT | Cabin Electrical System | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN | Operators Cabin | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STHLF-STRHO | Steering System Hoses | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STLTR-STBST | Ball Studs | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 89037 | 25051 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 89037 | 50219 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-TCVLV | Valve Traction Control | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CHASS-LNKLL | Lower Tag Link | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CHASS-LNKLU | Upper Tag Link | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 89037 | 50219 | 7400
CCK-MP-HAUL-DT088 -ENGINE | Bearing Roll | 89037 | 50219 | 7400
CCK-MP-HAUL-DT088 -TRNSYS-TRQUE | Torque Converter | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -TRNSYS-TROLC | Oil Cooler Transmission | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -TRNSYS-TRANS | Transmission | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-TRAYS | Tray | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 89037 | 17080 | 7400
CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CHASS | Chassis | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-SEATS | Operators Seat | 89037 | 4804 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-SBELT | Seat Belt | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-AIRCN | Air Con Lines | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-AIRCN | Air Con Condenser | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 89037 | 4765 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 89037 | 4765 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STLTR | Steering Linkages and Tie Rods | 89037 | 25027 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STHMU | Steering HMU | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STCON-STWHL | Steering Wheel | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STCON-STCOL | Steering Column | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -STRSYS-STACC-SACCF | Accumulator Steering Front | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -MANGMT-UMTRN | Power Train Management System | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -MANGMT-UMMMC | Mine Monitoring and Control | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -MANGMT-UMENG | Engine Management System | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-TOWPP | Pump Towing | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-HOVLV | Valve Hoist | 89037 | 36530 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-HOPMP | Pump Hoist & Brake | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-HDTNK | Tank Hydraulic | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -HYDSYS | Hydraulic System | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -GRSYST-GRTNK | Auto Lube Pump | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -GRSYST-GRINJ | Auto Lube Injectors | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -GRSYST-ALBPP | Auto Lube Pump | 89037 | 1086 | 7400
CCK-MP-HAUL-DT088 -FRSUPP | Fire Suppression System | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-DRSHT | Transmission Drive Shaft | 89037 | 18338 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-DIFFL | Differential | 89037 | 17080 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 89037 | 7099 | 7400
CCK-MP-HAUL-DT088 -ENGINE-PMPDR | Pump Drive | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 89037 | 25027 | 7400
CCK-MP-HAUL-DT088 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 89037 | 50219 | 7400
CCK-MP-HAUL-DT088 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 89037 | 50219 | 7400
CCK-MP-HAUL-DT088 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -ENGINE-INTEX-EXHST | Exhaust System | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -ENGINE-INTEX-AFTER | Aftercooler | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 89037 | 24979 | 7400
CCK-MP-HAUL-DT088 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -ENGINE-COSYS-WTRPP | Water Pump Engine | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -ENGINE-COSYS-RADTR | Radiator Coolant | 89037 | 36530 | 7400
CCK-MP-HAUL-DT088 -ENGINE-COSYS-RADTR | Radiator Engine | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 89037 | 61933 | 7400
CCK-MP-HAUL-DT088 -ENGINE | Engine Assembly Caterpillar C175-16 | 89037 | 24564 | 7400
CCK-MP-HAUL-DT088 -ELCTLV-START-STMUP | Starter Motor Upper | 89037 | 4804 | 7400
CCK-MP-HAUL-DT088 -ELCTLV-START-STMLO | Starter Motor Lower | 89037 | 4804 | 7400
CCK-MP-HAUL-DT088 -ELCTLV-CHARG-BATTY | Batteries | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -ELCTLV-CHARG-ALTER | Alternator 24V | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 89037 | 44407 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-PRKPP | Pump Park Brake Release | 89037 | 60321 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-MERTR | Mechanical Retarder | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-HYFPP | Pump Brake Cooling | 89037 | 19390 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BRVTR | Valve Brake Treadle | 89037 | 89037 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BRVLV | Valve Brake | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 89037 | 14711 | 7400
CCK-MP-HAUL-DT088 | DT088 Lubrication & Mechanical Services | 89147 | 89147 | 7400
CCK-MP-HAUL-DT088 | Caterpillar 793F Haul Truck DT088 | 89037 | 89037 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STACC | Accum Steer Rear | 31508 | 31508 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STACC | Accum Steer Middle | 31508 | 31508 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STACC | Accum Steer Front | 31508 | 31508 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BACCM | Accum Brake Rear | 31508 | 31508 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BACCM | Accum Brake Front RH | 31508 | 31508 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BACCM | Accum Brake Front LH | 31508 | 31508 | 7400
CCK-MP-HAUL-DT086 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 86846 | 56226 | 7400
CCK-MP-HAUL-DT086 -ELCTLV-HARNS | Electrical Harness | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -ELCTLV-LIGHT | DT086 Lighting Low Voltage | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 40543 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 40543 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 86822 | 8185 | 7400
CCK-MP-HAUL-DT086 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 86822 | 13482 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 86822 | 2258 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 86822 | 23853 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 86822 | 23853 | 7400
CCK-MP-HAUL-DT086 -STRUCT-SUSPN | Suspension | 86822 | 29968 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STOCO | Steering Oil Cooler | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 86822 | 34843 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-ELECT | Cabin Electrical System | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN | Operators Cabin | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STHLF-STRHO | Steering System Hoses | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STLTR-STBST | Ball Studs | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-TCVLV | Valve Traction Control | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CHASS-LNKLL | Lower Tag Link | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CHASS-LNKLU | Upper Tag Link | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -ENGINE | Bearing Roll | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -TRNSYS-TRQUE | Torque Converter | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 86822 | 55173 | 7400
CCK-MP-HAUL-DT086 -TRNSYS-TROLC | Oil Cooler Transmission | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -TRNSYS-TRANS | Transmission | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-TRAYS | Tray | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 86822 | 1074 | 7400
CCK-MP-HAUL-DT086 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 86822 | 18310 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CHASS | Chassis | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-SEATS | Operators Seat | 86822 | 14768 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-SBELT | Seat Belt | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-AIRCN | Air Con Lines | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-AIRCN | Air Con Condenser | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 86822 | 8185 | 7400
CCK-MP-HAUL-DT086 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 86822 | 13482 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 86822 | 8185 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STLTR | Steering Linkages and Tie Rods | 86846 | 23853 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STHMU | Steering HMU | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STCON-STWHL | Steering Wheel | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STCON-STCOL | Steering Column | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -STRSYS-STACC-SACCF | Accumulator Steering Front | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -MANGMT-UMTRN | Power Train Management System | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -MANGMT-UMMMC | Mine Monitoring and Control | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -MANGMT-UMENG | Engine Management System | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-TOWPP | Pump Towing | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-HOVLV | Valve Hoist | 86846 | 31508 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-HOPMP | Pump Hoist & Brake | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 86846 | 16971 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 86846 | 16971 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-HDTNK | Tank Hydraulic | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -HYDSYS | Hydraulic System | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -GRSYST-GRTNK | Auto Lube Pump | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -GRSYST-GRINJ | Auto Lube Injectors | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -GRSYST-ALBPP | Auto Lube Pump | 86846 | 5030 | 7400
CCK-MP-HAUL-DT086 -FRSUPP | Fire Suppression System | 86846 | 31508 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-DRSHT | Transmission Drive Shaft | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-DIFFL | Differential | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 86846 | 3219 | 7400
CCK-MP-HAUL-DT086 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 86846 | 2216 | 7400
CCK-MP-HAUL-DT086 -ENGINE-PMPDR | Pump Drive | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 86822 | 23949 | 7400
CCK-MP-HAUL-DT086 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-INTEX-EXHST | Exhaust System | 86822 | 86822 | 7400
CCK-MP-HAUL-DT086 -ENGINE-INTEX-AFTER | Aftercooler | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 86822 | 14283 | 7400
CCK-MP-HAUL-DT086 -ENGINE-COSYS-WTRPP | Water Pump Engine | 86822 | 24006 | 7400
CCK-MP-HAUL-DT086 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 86822 | 31508 | 7400
CCK-MP-HAUL-DT086 -ENGINE-COSYS-RADTR | Radiator Coolant | 86846 | 31508 | 7400
CCK-MP-HAUL-DT086 -ENGINE-COSYS-RADTR | Radiator Engine | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 86846 | 31508 | 7400
CCK-MP-HAUL-DT086 -ENGINE | Engine Assembly Caterpillar C175-16 | 86846 | 24006 | 7400
CCK-MP-HAUL-DT086 -ELCTLV-START-STMUP | Starter Motor Upper | 86846 | 10028 | 7400
CCK-MP-HAUL-DT086 -ELCTLV-START-STMLO | Starter Motor Lower | 86846 | 10028 | 7400
CCK-MP-HAUL-DT086 -ELCTLV-CHARG-BATTY | Batteries | 86846 | 15759 | 7400
CCK-MP-HAUL-DT086 -ELCTLV-CHARG-ALTER | Alternator 24V | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-PRKPP | Pump Park Brake Release | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-MERTR | Mechanical Retarder | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-HYFPP | Pump Brake Cooling | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BRVTR | Valve Brake Treadle | 86846 | 86846 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BRVLV | Valve Brake | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 86846 | 14283 | 7400
CCK-MP-HAUL-DT086 | DT086 Lubrication & Mechanical Services | 85454 | 85454 | 7400
CCK-MP-HAUL-DT086 | Caterpillar 793F Haul Truck DT086 | 86846 | 86846 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STACC | Accum Steer Front | 35900 | 35900 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STACC | Accum Steer Rear | 35900 | 35900 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STACC | Accum Steer Middle | 35900 | 35900 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BACCM | Accum Brake Rear | 35900 | 35900 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BACCM | Accum Brake Front RH | 35900 | 35900 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BACCM | Accum Brake Front LH | 35900 | 35900 | 7400
CCK-MP-HAUL-DT082 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84374 | 55080 | 7400
CCK-MP-HAUL-DT082 -ELCTLV-HARNS | Electrical Harness | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -ELCTLV-LIGHT | DT082 Lighting Low Voltage | 84734 | 84734 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42319 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42319 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84374 | 11504 | 7400
CCK-MP-HAUL-DT082 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84374 | 28 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84374 | 4829 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84374 | 26984 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84374 | 26984 | 7400
CCK-MP-HAUL-DT082 -STRUCT-SUSPN | Suspension | 84374 | 35900 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STOCO | Steering Oil Cooler | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84374 | 35900 | 7400
CCK-MP-HAUL-DT082 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84374 | 65857 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN | Operators Cabin | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STHLF-STRHO | Steering System Hoses | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STLTR-STBST | Ball Studs | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-TCVLV | Valve Traction Control | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CHASS-LNKLL | Lower Tag Link | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CHASS-LNKLU | Upper Tag Link | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE | Bearing Roll | 84374 | 35900 | 7400
CCK-MP-HAUL-DT082 -TRNSYS-TRQUE | Torque Converter | 84375 | 16213 | 7400
CCK-MP-HAUL-DT082 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84375 | 84375 | 7400
CCK-MP-HAUL-DT082 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84375 | 84375 | 7400
CCK-MP-HAUL-DT082 -TRNSYS-TROLC | Oil Cooler Transmission | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -TRNSYS-TRANS | Transmission | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-TRAYS | Tray | 84375 | 84375 | 7400
CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84375 | 22524 | 7400
CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84375 | 29 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84375 | 84375 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CHASS | Chassis | 84375 | 84375 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-SEATS | Operators Seat | 84375 | 1223 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-SBELT | Seat Belt | 84375 | 84375 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84375 | 84375 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-AIRCN | Air Con Lines | 84375 | 35900 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-AIRCN | Air Con Condenser | 84375 | 35900 | 7400
CCK-MP-HAUL-DT082 -STRUCT-CABIN-AIRCN | Air Conditioning System | 84375 | 35900 | 7400
CCK-MP-HAUL-DT082 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84375 | 29 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84375 | 558 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STHMU | Steering HMU | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STCON-STWHL | Steering Wheel | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STCON-STCOL | Steering Column | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -MANGMT-UMTRN | Power Train Management System | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -MANGMT-UMMMC | Mine Monitoring and Control | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -MANGMT-UMENG | Engine Management System | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-TOWPP | Pump Towing | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-HOVLV | Valve Hoist | 84374 | 35900 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-HOPMP | Pump Hoist & Brake | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-HDTNK | Tank Hydraulic | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -HYDSYS | Hydraulic System | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -GRSYST-GRTNK | Auto Lube Pump | 84374 | 27552 | 7400
CCK-MP-HAUL-DT082 -GRSYST-GRINJ | Auto Lube Injectors | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -GRSYST-ALBPP | Auto Lube Pump | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -FRSUPP | Fire Suppression System | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84374 | 57113 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84374 | 25964 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84374 | 25964 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-DRSHT | Transmission Drive Shaft | 84374 | 17432 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-DIFFL | Differential | 84374 | 17432 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-PMPDR | Pump Drive | 84374 | 21416 | 7400
CCK-MP-HAUL-DT082 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84374 | 75325 | 7400
CCK-MP-HAUL-DT082 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84375 | 75325 | 7400
CCK-MP-HAUL-DT082 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-INTEX-EXHST | Exhaust System | 84375 | 75325 | 7400
CCK-MP-HAUL-DT082 -ENGINE-INTEX-AFTER | Aftercooler | 84375 | 75325 | 7400
CCK-MP-HAUL-DT082 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84375 | 42800 | 7400
CCK-MP-HAUL-DT082 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84375 | 75325 | 7400
CCK-MP-HAUL-DT082 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84375 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84375 | 21370 | 7400
CCK-MP-HAUL-DT082 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84375 | 35900 | 7400
CCK-MP-HAUL-DT082 -ENGINE-COSYS-RADTR | Radiator Coolant | 84374 | 35900 | 7400
CCK-MP-HAUL-DT082 -ENGINE-COSYS-RADTR | Radiator Engine | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84374 | 45144 | 7400
CCK-MP-HAUL-DT082 -ENGINE | Engine Assembly Caterpillar C175-16 | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -ELCTLV-START-STMUP | Starter Motor Upper | 84374 | 11504 | 7400
CCK-MP-HAUL-DT082 -ELCTLV-START-STMLO | Starter Motor Lower | 84374 | 11504 | 7400
CCK-MP-HAUL-DT082 -ELCTLV-CHARG-BATTY | Batteries | 84374 | 18931 | 7400
CCK-MP-HAUL-DT082 -ELCTLV-CHARG-ALTER | Alternator 24V | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-PRKPP | Pump Park Brake Release | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-MERTR | Mechanical Retarder | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-HYFPP | Pump Brake Cooling | 84374 | 17432 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BRVTR | Valve Brake Treadle | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BRVLV | Valve Brake | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84374 | 25919 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84374 | 25919 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84374 | 13167 | 7400
CCK-MP-HAUL-DT082 | DT082 Lubrication & Mechanical Services | 84374 | 84374 | 7400
CCK-MP-HAUL-DT082 | Caterpillar 793F Haul Truck DT082 | 84374 | 84374 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STACC | Accum Steer Rear | 15544 | 15544 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STACC | Accum Steer Middle | 15544 | 15544 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STACC | Accum Steer Front | 15544 | 15544 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BACCM | Accum Brake Rear | 57072 | 57072 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BACCM | Accum Brake Front RH | 15616 | 15616 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BACCM | Accum Brake Front LH | 15616 | 15616 | 7400
CCK-MP-HAUL-DT058 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 87864 | 57496 | 7400
CCK-MP-HAUL-DT058 -ELCTLV-HARNS | Electrical Harness | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -ELCTLV-LIGHT | DT058 Lighting Low Voltage | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41980 | 41980 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41980 | 41980 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 87864 | 5769 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-SUSPN | Suspension | 87864 | 37682 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STOCO | Steering Oil Cooler | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN | Operators Cabin | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-ELECT | Cabin Electrical System | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STHLF-STRHO | Steering System Hoses | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STLTR-STBST | Ball Studs | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-TCVLV | Valve Traction Control | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CHASS-LNKLL | Lower Tag Link | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CHASS-LNKLU | Upper Tag Link | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 87864 | 7715 | 7400
CCK-MP-HAUL-DT058 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 87864 | 46342 | 7400
CCK-MP-HAUL-DT058 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 87864 | 7691 | 7400
CCK-MP-HAUL-DT058 -ENGINE | Bearing Roll | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -TRNSYS-TRQUE | Torque Converter | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 87864 | 68339 | 7400
CCK-MP-HAUL-DT058 -TRNSYS-TROLC | Oil Cooler Transmission | 87864 | 2167 | 7400
CCK-MP-HAUL-DT058 -TRNSYS-TRANS | Transmission | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-TRAYS | Tray | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 87864 | 22115 | 7400
CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 87864 | 15484 | 7400
CCK-MP-HAUL-DT058 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 87864 | 15616 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CHASS | Chassis | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-SEATS | Operators Seat | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-SBELT | Seat Belt | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-AIRCN | Air Con Lines | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-AIRCN | Air Con Condenser | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 87864 | 11626 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 87864 | 11626 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 87864 | 15676 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STLTR | Steering Linkages and Tie Rods | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STHMU | Steering HMU | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STCON-STWHL | Steering Wheel | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STCON-STCOL | Steering Column | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -STRSYS-STACC-SACCF | Accumulator Steering Front | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -MANGMT-UMTRN | Power Train Management System | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -MANGMT-UMMMC | Mine Monitoring and Control | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -MANGMT-UMENG | Engine Management System | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-TOWPP | Pump Towing | 87864 | 15484 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-HOVLV | Valve Hoist | 87864 | 46342 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-HOPMP | Pump Hoist & Brake | 87864 | 14260 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87864 | 26627 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87864 | 15616 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-HDTNK | Tank Hydraulic | 87864 | 15676 | 7400
CCK-MP-HAUL-DT058 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -HYDSYS | Hydraulic System | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -GRSYST-GRTNK | Auto Lube Pump | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -GRSYST-GRINJ | Auto Lube Injectors | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -GRSYST-ALBPP | Auto Lube Pump | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -FRSUPP | Fire Suppression System | 87864 | 46341 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87864 | 15616 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87864 | 6793 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-DRSHT | Transmission Drive Shaft | 87864 | 5769 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-DIFFL | Differential | 87864 | 7850 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87864 | 7850 | 7400
CCK-MP-HAUL-DT058 -ENGINE-PMPDR | Pump Drive | 87864 | 15616 | 7400
CCK-MP-HAUL-DT058 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 87865 | 52816 | 7400
CCK-MP-HAUL-DT058 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 87864 | 52816 | 7400
CCK-MP-HAUL-DT058 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-INTEX-EXHST | Exhaust System | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -ENGINE-INTEX-AFTER | Aftercooler | 87864 | 52816 | 7400
CCK-MP-HAUL-DT058 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 87864 | 52816 | 7400
CCK-MP-HAUL-DT058 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 87864 | 52816 | 7400
CCK-MP-HAUL-DT058 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 87865 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-COSYS-WTRPP | Water Pump Engine | 87865 | 52816 | 7400
CCK-MP-HAUL-DT058 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 87864 | 20481 | 7400
CCK-MP-HAUL-DT058 -ENGINE-COSYS-RADTR | Radiator Coolant | 87864 | 29310 | 7400
CCK-MP-HAUL-DT058 -ENGINE-COSYS-RADTR | Radiator Engine | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 87864 | 48423 | 7400
CCK-MP-HAUL-DT058 -ENGINE | Engine Assembly Caterpillar C175-16 | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -ELCTLV-START-STMUP | Starter Motor Upper | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -ELCTLV-START-STMLO | Starter Motor Lower | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -ELCTLV-CHARG-BATTY | Batteries | 87864 | 15676 | 7400
CCK-MP-HAUL-DT058 -ELCTLV-CHARG-ALTER | Alternator 24V | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87864 | 34446 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87864 | 15544 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-PRKPP | Pump Park Brake Release | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-MERTR | Mechanical Retarder | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-HYFPP | Pump Brake Cooling | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BRVTR | Valve Brake Treadle | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BRVLV | Valve Brake | 87864 | 15676 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87864 | 1976 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 87864 | 7715 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 87864 | 15616 | 7400
CCK-MP-HAUL-DT058 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 87864 | 15616 | 7400
CCK-MP-HAUL-DT058 | DT058 Lubrication & Mechanical Services | 87864 | 87864 | 7400
CCK-MP-HAUL-DT058 | Caterpillar 793F Haul Truck DT058 | 87864 | 87864 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STACC | Accum Steer Rear | 42363 | 42363 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STACC | Accum Steer Middle | 42363 | 42363 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STACC | Accum Steer Front | 42363 | 42363 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BACCM | Accum Brake Rear | 42363 | 42363 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BACCM | Accum Brake Front RH | 42363 | 42363 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BACCM | Accum Brake Front LH | 42363 | 42363 | 7400
CCK-MP-HAUL-DT057 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 91273 | 59310 | 7400
CCK-MP-HAUL-DT057 -ELCTLV-HARNS | Electrical Harness | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -ELCTLV-LIGHT | DT057 Lighting Low Voltage | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 42407 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 42407 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 91273 | 454 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 91273 | 3875 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 91273 | 22845 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 91273 | 22845 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STOCO | Steering Oil Cooler | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN | Operators Cabin | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-ELECT | Cabin Electrical System | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 91273 | 65170 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STHLF-STRHO | Steering System Hoses | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STLTR-STBST | Ball Studs | 91273 | 65170 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-TCVLV | Valve Traction Control | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CHASS-LNKLL | Lower Tag Link | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CHASS-LNKLU | Upper Tag Link | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 91273 | 42405 | 7400
CCK-MP-HAUL-DT057 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE | Bearing Roll | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -TRNSYS-TRQUE | Torque Converter | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -TRNSYS-TROLC | Oil Cooler Transmission | 91273 | 13167 | 7400
CCK-MP-HAUL-DT057 -TRNSYS-TRANS | Transmission | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-TRAYS | Tray | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CHASS | Chassis | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-SEATS | Operators Seat | 91273 | 2803 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-SBELT | Seat Belt | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-AIRCN | Air Con Lines | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-AIRCN | Air Con Condenser | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 91273 | 3867 | 7400
CCK-MP-HAUL-DT057 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 91273 | 454 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 91273 | 13167 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 91273 | 13167 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STLTR | Steering Linkages and Tie Rods | 91273 | 22845 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STHMU | Steering HMU | 91273 | 15565 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STCON-STWHL | Steering Wheel | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STCON-STCOL | Steering Column | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 91273 | 42405 | 7400
CCK-MP-HAUL-DT057 -STRSYS-STACC-SACCF | Accumulator Steering Front | 91273 | 42405 | 7400
CCK-MP-HAUL-DT057 -MANGMT-UMTRN | Power Train Management System | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -MANGMT-UMMMC | Mine Monitoring and Control | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -MANGMT-UMENG | Engine Management System | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-TOWPP | Pump Towing | 91273 | 15565 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-HOVLV | Valve Hoist | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-HOPMP | Pump Hoist & Brake | 91273 | 19382 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 91273 | 950 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-HDTNK | Tank Hydraulic | 91273 | 42405 | 7400
CCK-MP-HAUL-DT057 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -HYDSYS | Hydraulic System | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -GRSYST-GRTNK | Auto Lube Pump | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -GRSYST-GRINJ | Auto Lube Injectors | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -GRSYST-ALBPP | Auto Lube Pump | 91273 | 3875 | 7400
CCK-MP-HAUL-DT057 -FRSUPP | Fire Suppression System | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 91273 | 22845 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-DRSHT | Transmission Drive Shaft | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-DIFFL | Differential | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 91273 | 15567 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 91273 | 15565 | 7400
CCK-MP-HAUL-DT057 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-PMPDR | Pump Drive | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 91273 | 33326 | 7400
CCK-MP-HAUL-DT057 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 91273 | 33326 | 7400
CCK-MP-HAUL-DT057 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-INTEX-EXHST | Exhaust System | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -ENGINE-INTEX-AFTER | Aftercooler | 91273 | 33326 | 7400
CCK-MP-HAUL-DT057 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 91273 | 33326 | 7400
CCK-MP-HAUL-DT057 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 91273 | 33326 | 7400
CCK-MP-HAUL-DT057 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-COSYS-WTRPP | Water Pump Engine | 91273 | 33326 | 7400
CCK-MP-HAUL-DT057 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 91273 | 57285 | 7400
CCK-MP-HAUL-DT057 -ENGINE-COSYS-RADTR | Radiator Coolant | 91273 | 58459 | 7400
CCK-MP-HAUL-DT057 -ENGINE-COSYS-RADTR | Radiator Engine | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 91273 | 65170 | 7400
CCK-MP-HAUL-DT057 -ENGINE | Engine Assembly Caterpillar C175-16 | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ELCTLV-START-STMUP | Starter Motor Upper | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ELCTLV-START-STMLO | Starter Motor Lower | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -ELCTLV-CHARG-BATTY | Batteries | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -ELCTLV-CHARG-ALTER | Alternator 24V | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 91273 | 65170 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 91273 | 65170 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 91273 | 25464 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-PRKPP | Pump Park Brake Release | 91273 | 10672 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-MERTR | Mechanical Retarder | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-HYFPP | Pump Brake Cooling | 91273 | 22845 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BRVTR | Valve Brake Treadle | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BRVLV | Valve Brake | 91273 | 19382 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 91273 | 15567 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 91273 | 15565 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 91273 | 18727 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 91273 | 42405 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 91273 | 42405 | 7400
CCK-MP-HAUL-DT057 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 91273 | 42405 | 7400
CCK-MP-HAUL-DT057 | DT057 Lubrication & Mechanical Services | 91273 | 91273 | 7400
CCK-MP-HAUL-DT057 | Caterpillar 793F Haul Truck DT057 | 91273 | 91273 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STACC | Accum Steer Rear | 36020 | 36020 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STACC | Accum Steer Middle | 36020 | 36020 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STACC | Accum Steer Front | 36020 | 36020 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BACCM | Accum Brake Rear | 36020 | 36020 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BACCM | Accum Brake Front RH | 36020 | 36020 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BACCM | Accum Brake Front LH | 36020 | 36020 | 7400
CCK-MP-HAUL-DT056 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84421 | 55831 | 7400
CCK-MP-HAUL-DT056 -ELCTLV-HARNS | Electrical Harness | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -ELCTLV-LIGHT | DT056 Lighting Low Voltage | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 40857 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 40857 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84421 | 11711 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84421 | 25278 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84421 | 25278 | 7400
CCK-MP-HAUL-DT056 -STRUCT-SUSPN | Suspension | 84421 | 36020 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STOCO | Steering Oil Cooler | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN | Operators Cabin | 84421 | 19076 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84421 | 84421 | 7300
CCK-MP-HAUL-DT056 -STRSYS-STHLF-STRHO | Steering System Hoses | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STLTR-STBST | Ball Studs | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-TCVLV | Valve Traction Control | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CHASS-LNKLL | Lower Tag Link | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CHASS-LNKLU | Upper Tag Link | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84421 | 18034 | 7400
CCK-MP-HAUL-DT056 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84421 | 36020 | 7400
CCK-MP-HAUL-DT056 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84421 | 17941 | 7400
CCK-MP-HAUL-DT056 -ENGINE | Bearing Roll | 84421 | 36020 | 7400
CCK-MP-HAUL-DT056 -TRNSYS-TRQUE | Torque Converter | 84421 | 18034 | 7400
CCK-MP-HAUL-DT056 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84421 | 64678 | 7400
CCK-MP-HAUL-DT056 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84421 | 64673 | 7400
CCK-MP-HAUL-DT056 -TRNSYS-TROLC | Oil Cooler Transmission | 84421 | 4851 | 7400
CCK-MP-HAUL-DT056 -TRNSYS-TRANS | Transmission | 84421 | 8230 | 7400
CCK-MP-HAUL-DT056 -STRUCT-TRAYS | Tray | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CHASS | Chassis | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-SEATS | Operators Seat | 84421 | 10436 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-SBELT | Seat Belt | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-AIRCN | Air Con Lines | 84421 | 18034 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-AIRCN | Air Con Condenser | 84421 | 18034 | 7400
CCK-MP-HAUL-DT056 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 84421 | 18034 | 7400
CCK-MP-HAUL-DT056 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84421 | 17941 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84421 | 17941 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84421 | 20273 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STHMU | Steering HMU | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STCON-STWHL | Steering Wheel | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STCON-STCOL | Steering Column | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -MANGMT-UMTRN | Power Train Management System | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -MANGMT-UMMMC | Mine Monitoring and Control | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -MANGMT-UMENG | Engine Management System | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-TOWPP | Pump Towing | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-HOVLV | Valve Hoist | 84421 | 36020 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-HOPMP | Pump Hoist & Brake | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84421 | 23496 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84421 | 23496 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-HDTNK | Tank Hydraulic | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -HYDSYS | Hydraulic System | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -GRSYST-GRTNK | Auto Lube Pump | 84421 | 64299 | 7400
CCK-MP-HAUL-DT056 -GRSYST-GRINJ | Auto Lube Injectors | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -GRSYST-ALBPP | Auto Lube Pump | 84421 | 4851 | 7400
CCK-MP-HAUL-DT056 -FRSUPP | Fire Suppression System | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84421 | 18034 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84421 | 18034 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-DRSHT | Transmission Drive Shaft | 84421 | 4791 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-DIFFL | Differential | 84421 | 867 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84421 | 5642 | 7400
CCK-MP-HAUL-DT056 -ENGINE-PMPDR | Pump Drive | 84421 | 867 | 7400
CCK-MP-HAUL-DT056 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84421 | 12555 | 7400
CCK-MP-HAUL-DT056 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84421 | 36022 | 7400
CCK-MP-HAUL-DT056 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84421 | 36022 | 7400
CCK-MP-HAUL-DT056 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84421 | 12555 | 7400
CCK-MP-HAUL-DT056 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84421 | 12555 | 7400
CCK-MP-HAUL-DT056 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84421 | 12555 | 7400
CCK-MP-HAUL-DT056 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84421 | 12555 | 7400
CCK-MP-HAUL-DT056 -ENGINE-INTEX-EXHST | Exhaust System | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -ENGINE-INTEX-AFTER | Aftercooler | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84421 | 36022 | 7400
CCK-MP-HAUL-DT056 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84421 | 36022 | 7400
CCK-MP-HAUL-DT056 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 84421 | 867 | 7400
CCK-MP-HAUL-DT056 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84421 | 867 | 7400
CCK-MP-HAUL-DT056 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84421 | 36022 | 7400
CCK-MP-HAUL-DT056 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -ENGINE-COSYS-RADTR | Radiator Coolant | 84421 | 36020 | 7400
CCK-MP-HAUL-DT056 -ENGINE-COSYS-RADTR | Radiator Engine | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84421 | 36022 | 7400
CCK-MP-HAUL-DT056 -ENGINE | Engine Assembly Caterpillar C175-16 | 84421 | 12555 | 7400
CCK-MP-HAUL-DT056 -ELCTLV-START-STMUP | Starter Motor Upper | 84421 | 867 | 7400
CCK-MP-HAUL-DT056 -ELCTLV-START-STMLO | Starter Motor Lower | 84421 | 895 | 7400
CCK-MP-HAUL-DT056 -ELCTLV-CHARG-BATTY | Batteries | 84421 | 16344 | 7400
CCK-MP-HAUL-DT056 -ELCTLV-CHARG-ALTER | Alternator 24V | 84421 | 867 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84421 | 38798 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-PRKPP | Pump Park Brake Release | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-MERTR | Mechanical Retarder | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-HYFPP | Pump Brake Cooling | 84421 | 15542 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BRVTR | Valve Brake Treadle | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BRVLV | Valve Brake | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84421 | 17941 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84421 | 13282 | 7400
CCK-MP-HAUL-DT056 | DT056 Lubrication & Mechanical Services | 84421 | 84421 | 7400
CCK-MP-HAUL-DT056 | Caterpillar 793F Haul Truck DT056 | 84421 | 84421 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STACC | Accum Steer Rear | 30645 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STACC | Accum Steer Middle | 30645 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STACC | Accum Steer Front | 30645 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BACCM | Accum Brake Rear | 30645 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BACCM | Accum Brake Front RH | 30645 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BACCM | Accum Brake Front LH | 30645 | 30645 | 7400
CCK-MP-HAUL-DT055 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84122 | 56583 | 7400
CCK-MP-HAUL-DT055 -ELCTLV-HARNS | Electrical Harness | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -ELCTLV-LIGHT | DT055 Lighting Low Voltage | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 43145 | 43145 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 43145 | 43145 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 84122 | 4767 | 7400
CCK-MP-HAUL-DT055 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 84122 | 7332 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84122 | 9073 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -STRUCT-SUSPN | Suspension | 84122 | 34377 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STOCO | Steering Oil Cooler | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN | Operators Cabin | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STHLF-STRHO | Steering System Hoses | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STLTR-STBST | Ball Studs | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-TCVLV | Valve Traction Control | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CHASS-LNKLL | Lower Tag Link | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CHASS-LNKLU | Upper Tag Link | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE | Bearing Roll | 84122 | 54657 | 7400
CCK-MP-HAUL-DT055 -TRNSYS-TRQUE | Torque Converter | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -TRNSYS-TROLC | Oil Cooler Transmission | 84122 | 10235 | 7400
CCK-MP-HAUL-DT055 -TRNSYS-TRANS | Transmission | 84122 | 15848 | 7400
CCK-MP-HAUL-DT055 -STRUCT-TRAYS | Tray | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84122 | 4031 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CHASS | Chassis | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-SEATS | Operators Seat | 84122 | 7365 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-SBELT | Seat Belt | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84122 | 50726 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-AIRCN | Air Con Lines | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-AIRCN | Air Con Condenser | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84122 | 4767 | 7400
CCK-MP-HAUL-DT055 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84122 | 13600 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84122 | 2699 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84122 | 14732 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STHMU | Steering HMU | 84122 | 5992 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STCON-STWHL | Steering Wheel | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STCON-STCOL | Steering Column | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84122 | 12545 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84122 | 1498 | 7400
CCK-MP-HAUL-DT055 -MANGMT-UMTRN | Power Train Management System | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -MANGMT-UMMMC | Mine Monitoring and Control | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -MANGMT-UMENG | Engine Management System | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-TOWPP | Pump Towing | 84122 | 5992 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-HOVLV | Valve Hoist | 84122 | 5698 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-HOPMP | Pump Hoist & Brake | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84122 | 330 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84122 | 5883 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-HDTNK | Tank Hydraulic | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -HYDSYS | Hydraulic System | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -GRSYST-GRTNK | Auto Lube Pump | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -GRSYST-GRINJ | Auto Lube Injectors | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -GRSYST-ALBPP | Auto Lube Pump | 84122 | 15901 | 7400
CCK-MP-HAUL-DT055 -FRSUPP | Fire Suppression System | 84122 | 54399 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 84122 | 51039 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-DRSHT | Transmission Drive Shaft | 84122 | 2155 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-DIFFL | Differential | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84122 | 5883 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 84122 | 7096 | 7400
CCK-MP-HAUL-DT055 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-PMPDR | Pump Drive | 84122 | 21547 | 7400
CCK-MP-HAUL-DT055 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84122 | 21547 | 7400
CCK-MP-HAUL-DT055 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84122 | 54657 | 7400
CCK-MP-HAUL-DT055 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-INTEX-EXHST | Exhaust System | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -ENGINE-INTEX-AFTER | Aftercooler | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84122 | 54657 | 7400
CCK-MP-HAUL-DT055 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 84122 | 9073 | 7400
CCK-MP-HAUL-DT055 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84122 | 9073 | 7400
CCK-MP-HAUL-DT055 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84122 | 25774 | 7400
CCK-MP-HAUL-DT055 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-COSYS-RADTR | Radiator Coolant | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -ENGINE-COSYS-RADTR | Radiator Engine | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -ENGINE | Engine Assembly Caterpillar C175-16 | 84122 | 21547 | 7400
CCK-MP-HAUL-DT055 -ELCTLV-START-STMUP | Starter Motor Upper | 84122 | 9073 | 7400
CCK-MP-HAUL-DT055 -ELCTLV-START-STMLO | Starter Motor Lower | 84122 | 9073 | 7400
CCK-MP-HAUL-DT055 -ELCTLV-CHARG-BATTY | Batteries | 84122 | 5372 | 7400
CCK-MP-HAUL-DT055 -ELCTLV-CHARG-ALTER | Alternator 24V | 84122 | 9073 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-PRKPP | Pump Park Brake Release | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-MERTR | Mechanical Retarder | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-HYFPP | Pump Brake Cooling | 84122 | 7001 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BRVTR | Valve Brake Treadle | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BRVLV | Valve Brake | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 84122 | 13600 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84122 | 11329 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84122 | 13600 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 84122 | 30645 | 7400
CCK-MP-HAUL-DT055 | DT055 Lubrication & Mechanical Services | 84122 | 84122 | 7400
CCK-MP-HAUL-DT055 | Caterpillar 793F Haul Truck DT055 | 84122 | 84122 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STACC | Accum Steer Rear | 31799 | 31799 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STACC | Accum Steer Middle | 31799 | 31799 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STACC | Accum Steer Front | 31799 | 31799 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BACCM | Accum Brake Rear | 31799 | 31799 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BACCM | Accum Brake Front RH | 31799 | 31799 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BACCM | Accum Brake Front LH | 31799 | 31799 | 7400
CCK-MP-HAUL-DT054 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 88111 | 56674 | 7400
CCK-MP-HAUL-DT054 -ELCTLV-HARNS | Electrical Harness | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -ELCTLV-LIGHT | DT054 Lighting Low Voltage | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CHASS-LNKRU | Axle Tag Link RH Upper | 41997 | 41997 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CHASS-LNKRL | Axle Tag Link RH Lower | 41997 | 41997 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STLTR-STLAC | Steering Linkage Arm Centre | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRUCT-AXLES-FWBRH | Front Wheel Bearings R/H | 88110 | 4965 | 7400
CCK-MP-HAUL-DT054 -STRUCT-AXLES-FWBLH | Front Wheel Bearings L/H | 88110 | 6138 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 88111 | 1222 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRUCT-SUSPN | Suspension | 88111 | 50039 | 7400
CCK-MP-HAUL-DT054 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 88111 | 31799 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-ELECT | Cabin Electrical System | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN | Operators Cabin | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STHLF-STRHO | Steering System Hoses | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STLTR-STBST | Ball Studs | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BRHLF-CBRHO | Brake Cooling System Hoses | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BRHLF-BRHOS | Service Brake System Hoses | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-TCVLV | Valve Traction Control | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CHASS-LNKLL | Lower Tag Link | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CHASS-LNKLU | Upper Tag Link | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -ENGINE | Bearing Roll | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -TRNSYS-TRQUE | Torque Converter | 88111 | 22331 | 7400
CCK-MP-HAUL-DT054 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 88111 | 54531 | 7400
CCK-MP-HAUL-DT054 -TRNSYS-TROLC | Oil Cooler Transmission | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -TRNSYS-TRANS | Transmission | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -STRUCT-TRAYS | Tray | 88098 | 88098 | 7300
CCK-MP-HAUL-DT054 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CHASS-TRMNT | Tray Mount Assembly | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CHASS-AXLIK | Rear Axle Four Point Link | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CHASS | Chassis | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-SEATS | Operators Seat | 88111 | 768 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-SBELT | Seat Belt | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-AIRCN | Air Con Lines | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-AIRCN | Air Con Condenser | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 88111 | 18865 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 88111 | 2567 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STPMP | Pump Steering & Hydraulic Fan | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STLTR | Steering Linkages and Tie Rods | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STHMU | Steering HMU | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STCON-STWHL | Steering Wheel | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STCON-STCOL | Steering Column | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -STRSYS-STACC-SACCF | Accumulator Steering Front | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -MANGMT-UMTRN | Power Train Management System | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -MANGMT-UMMMC | Mine Monitoring and Control | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -MANGMT-UMENG | Engine Management System | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-TOWPP | Pump Towing | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-HOVLV | Valve Hoist | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-HOPMP | Pump Hoist & Brake | 88111 | 21219 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-HDTNK | Tank Hydraulic | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -HYDSYS | Hydraulic System | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -GRSYST-GRTNK | Auto Lube Pump | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -GRSYST-GRINJ | Auto Lube Injectors | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -GRSYST-ALBPP | Auto Lube Pump | 88111 | 5197 | 7400
CCK-MP-HAUL-DT054 -FRSUPP | Fire Suppression System | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 88111 | 15701 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-DRSHT | Transmission Drive Shaft | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-DIFFL | Differential | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYM02 | Axle Oil Cooler Fan Motor | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -ENGINE-PMPDR | Pump Drive | 88111 | 18897 | 7400
CCK-MP-HAUL-DT054 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-INTEX-TBORO | Turbocharger R/H Outer | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-INTEX-TBORI | Turbocharger R/H Inner | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-INTEX-TBOLO | Turbocharger L/H Outer | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-INTEX-TBOLI | Turbocharger L/H Inner | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-INTEX-EXHST | Exhaust System | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -ENGINE-INTEX-AFTER | Aftercooler | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-FUSYS-FULIP | Fuel Injector Pump | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-COSYS-WTRPP | Water Pump Engine | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ENGINE-COSYS-THERM | Electronic Engine Thermostat | 88111 | 31799 | 7400
CCK-MP-HAUL-DT054 -ENGINE-COSYS-RADTR | Radiator Coolant | 88111 | 31799 | 7400
CCK-MP-HAUL-DT054 -ENGINE-COSYS-RADTR | Radiator Engine | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -ENGINE-COSYS-COFAN | Cooling Fan & Motor | 88111 | 34527 | 7400
CCK-MP-HAUL-DT054 -ENGINE | Engine Assembly Caterpillar C175-16 | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ELCTLV-START-STMUP | Starter Motor Upper | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ELCTLV-START-STMLO | Starter Motor Lower | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -ELCTLV-CHARG-BATTY | Batteries | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -ELCTLV-CHARG-ALTER | Alternator 24V | 88111 | 21034 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-PRKPP | Pump Park Brake Release | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-MERTR | Mechanical Retarder | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-HYFPP | Pump Brake Cooling | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BRVTR | Valve Brake Treadle | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BRVLV | Valve Brake | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BROCO-HYMO1 | Brake Oil Cooling Motor | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 88111 | 15675 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BACCM-FRRGT | Brake Accumulator Front Right | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 -BRKSYS-BACCM-FRLFT | Brake Accumulator Front Left | 88111 | 6138 | 7400
CCK-MP-HAUL-DT054 | DT054 Lubrication & Mechanical Services | 88111 | 88111 | 7400
CCK-MP-HAUL-DT054 | Caterpillar 793F Haul Truck DT054 | 88111 | 88111 | 7400
CCK-MP-SUPP-WC3112-BRKSYS-BACCM | CAT 785D Brake Accumulator | 29590 | 29590 | 5500
CCK-MP-SUPP-WC3112-STRSYS-STACC | CAT 785D Steering Accumulator RH | 29590 | 29590 | 5500
CCK-MP-SUPP-WC3112-STRSYS-STACC | CAT 785D Steering Accumulator LH | 29590 | 29590 | 5500
CCK-MP-SUPP-WC3112-STRUCT-WTANK-WTPPM | Water Tank Pump & Motor | 30406 | 23217 | 5600
CCK-MP-SUPP-WC3112-STRUCT-WTANK-SPRAY | Water Tank Sprays | 30406 | 30406 | 5600
CCK-MP-SUPP-WC3112-STRUCT-WTANK-CANON | Water Tank Cannon | 30406 | 30406 | 5600
CCK-MP-SUPP-WC3112-STRUCT-WTANK | Water Tank | 30406 | 30406 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-TRNSYS-TRQUE | Torque Converter | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-TRNSYS-TRPMP-TMCPP | Pump Transmission | 52240 | 2198 | 5600
CCK-MP-SUPP-WC3112-TRNSYS-TRPMP-TCCPP | Pump TC/Park Brake Release/Scavenge | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-TRNSYS-TRPMP | Pumps Transmission | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-TRNSYS-TROLC | Oil Cooler Transmission | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-TRNSYS-TRANS | Transmission | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-TRNSYS | Transmission System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-SUSPN | Suspension Service | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-STLAD-SLFXD | Fixed Steps and Ladders | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-STLAD | Steps and Ladders | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-PNLGU | Panels and Guards | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-PLHAN | Platforms and Handrails | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CHASS-TAGLK | Tag Link | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CHASS-AFRME | A Frame | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CHASS | Chassis | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN-SEATS | Operators Seat | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN-SBELT | Seat Belt | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN-GLASS | Glass | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN-CABES | Cabin Entertainment System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN-CABCO | Cabin Controls | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN-AIRCN | Air Conditioning System | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-CABIN | Operators Cabin | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRUCT-AXLES | Axle Assembly Front | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRUCT | Structure | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STVLV | Valve Steering | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STTNK | Tank Steering | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 52240 | 2873 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 52240 | 2873 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STRCY | Cylinders Steering | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STPMP | Pump Steering | 52240 | 11771 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STOLC | Oil Cooler Steering | 52240 | 11669 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STLTR | Steering Linkages and Tie Rods | 52240 | 14062 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STHMU | Steering HMU | 52240 | 11771 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STHLF | Steering System Hoses Lines and Fittings | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STCON-STWHL | Steering Wheel | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STCON-STCOL | Steering Column | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STCON | Controls Steering | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STACC-SACRH | Accumulator Steering R/H Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STACC-SACLH | Accumulator Steering L/H Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-STRSYS-STACC | Accumulators Steering | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-STRSYS | Steering System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-PNEUMC-START | Pneumatic Starter Motor | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-PNEUMC-PNTNK | Air Tank | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-PNEUMC-PNHLF | Pneumatic System Hoses Lines Fittings | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-PNEUMC-BRVLR-SVBRF | Brake Air Relay Valve | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-PNEUMC-BRVLR-ARCRR | Auto Retard Control | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-PNEUMC-BRVLR | Brake Control Valves | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-PNEUMC-AIRDR | Air Drier | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-PNEUMC | Pneumatic System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-MANGMT-UMTRN | Power Train Management System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-MANGMT-UMMMC | Mine Monitoring and Control | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-MANGMT-UMENG | Engine Management System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-MANGMT | Unit Management | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-TOWPP | Pump Towing | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-HOVLV | Valve Hoist | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-HOPMP | Pump Hoist & Rear Brake Cooling | 52240 | 11771 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-HOCYL | Cylinders Hoist | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-HDTNK | Tank Hydraulic | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-HYDSYS | Hydraulic System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-GRSYST-GRTNK | Auto Lube Resevoir | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-GRSYST-GRINJ | Auto Lube Injectors | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-GRSYST-ALHLF | Auto Lube Hoses Lines Fittings | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-GRSYST-ALELC | Auto Lube Electrical | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-GRSYST-ALCON | Auto Lube Controller | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-GRSYST-ALBPP | Auto Lube Pump | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-GRSYST | Grease Lubrication System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FRSUPP-FSMAN | Fire Suppression Manual | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FRSUPP-FSAUT | Fire Suppression Automatic | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FRSUPP-FSALM | Fire System Alarm | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FRSUPP | Fire Suppression System | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-WHTYR | Wheels, Tyres and Rims | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-FDRVE | Final Drives | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-DRSHT | Drive Shaft, Transmission | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-DRLAX | Drive Line Axles | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-DIFFL | Differential | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-FDRSYS-AXLEC | Rear Axle Oil Cooling | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-FDRSYS | Final Drive System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-PMPDR-DRSHT | Drive Shaft, Pump Drive | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-PMPDR | Pump Drive | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 52240 | 23974 | 5600
CCK-MP-SUPP-WC3112-ENGINE-LUBSY-OILPP | Oil Pump Engine | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-LUBSY | Engine Lubrication System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX-TBORF | Turbocharger R/H Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX-EXHST | Exhaust System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX-AIRFL | Air Filtration System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX-AFTER | Aftercooler | 52240 | 10839 | 5600
CCK-MP-SUPP-WC3112-ENGINE-INTEX | Intake and Exhaust System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-FUSYS-FULTK | Fuel Tank | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-FUSYS-FUINJ | Fuel Injectors | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-FUSYS-FUHLF | Fuel System Hoses, Lines and Fittings | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-FUSYS | Fuel System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS-WTRPP | Water Pump Engine | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS-THERM | Thermostats/Regulators | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS-RADTR | Radiator Engine | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS-CSHLF | Cooling System Hoses, Lines and Fitting | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS-COFAN | Fan Cooling System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS-BELTS | Fan Belts Engine | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COSYS | Engine Cooling System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ENGINE-COMPR | Air Compressor | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ENGINE | Engine Assembly, Caterpillar 3512 | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ELCTLV-LIGHT | Lighting Low Voltage | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ELCTLV-HARNS | Electrical Harness | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ELCTLV-CONTL | Electrical Controls Low Voltage | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ELCTLV-CHARG-BATTY | Batteries | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ELCTLV-CHARG-ALTER | Alternator 24V | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-ELCTLV-CHARG | Charging System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-ELCTLV | Electrical System Low Voltage 24V | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-COMMUN-RADIO | Two Way Radio | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-COMMUN-FLMGT | Fleet Management | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-COMMUN | Communications | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SRVBK | Service Brake | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-SLACK | Brake Slack Adjusters | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-PRKPP | Pump Park Brake Release | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-MERTR | Mechanical Retarder | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRVTR | Valve Brake Treadle | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRVLV | Valve Brake | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRPMP | Pump Brake | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BROCO-BROCT | Brake Oil Cooler Top Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BROCO-BROCC | Brake Oil Cooler Rear Bottom Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BROCO | Brake Oil Cooler | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRCYL-ROTFR | Rotochamber Front | 52240 | 8166 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BRCYL | Brake Cylinders | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112-BRKSYS-BACCM | Brake Accumulator | 52240 | 8256 | 5600
CCK-MP-SUPP-WC3112-BRKSYS | Braking System | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3112 | Caterpillar 785D Water Truck, WC3112 | 52240 | 52240 | 5600
CCK-MP-SUPP-WC3111-BRKSYS-BACCM | CAT 785D Brake Accumulator | 14617 | 14617 | 5500
CCK-MP-SUPP-WC3111-STRSYS-STACC | CAT 785D Steering Accumulator RH | 14617 | 14617 | 5500
CCK-MP-SUPP-WC3111-STRSYS-STACC | CAT 785D Steering Accumulator LH | 11166 | 11166 | 5500
CCK-MP-SUPP-WC3111-STRUCT-WTANK-WTPPM | Water Tank Pump & Motor | 28968 | 28968 | 5600
CCK-MP-SUPP-WC3111-STRUCT-WTANK-SPRAY | Water Tank Sprays | 28968 | 28968 | 5600
CCK-MP-SUPP-WC3111-STRUCT-WTANK-CANON | Water Tank Cannon | 28968 | 28968 | 5600
CCK-MP-SUPP-WC3111-STRUCT-WTANK | Water Tank | 28968 | 28968 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-TRNSYS-TRQUE | Torque Converter | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-TRNSYS-TRPMP-TMCPP | Pump Transmission | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-TRNSYS-TRPMP-TCCPP | Pump TC/Park Brake Release/Scavenge | 51257 | 14617 | 5600
CCK-MP-SUPP-WC3111-TRNSYS-TRPMP | Pumps Transmission | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-TRNSYS-TROLC | Oil Cooler Transmission | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-TRNSYS-TRANS | Transmission | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-TRNSYS | Transmission System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 51257 | 11166 | 5600
CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRUCT-SUSPN | Suspension Service | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-STLAD-SLFXD | Fixed Steps and Ladders | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-STLAD | Steps and Ladders | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-PNLGU | Panels and Guards | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-PLHAN | Platforms and Handrails | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CHASS-TAGLK | Tag Link | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CHASS-AFRME | A Frame | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CHASS | Chassis | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN-SEATS | Operators Seat | 51257 | 1832 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN-SBELT | Seat Belt | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN-GLASS | Glass | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN-CABES | Cabin Entertainment System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN-CABCO | Cabin Controls | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN-AIRCN | Air Conditioning System | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRUCT-CABIN | Operators Cabin | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 51257 | 10741 | 5600
CCK-MP-SUPP-WC3111-STRUCT-AXLES | Axle Assembly Front | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRUCT | Structure | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STVLV | Valve Steering | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STTNK | Tank Steering | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 51257 | 14617 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STRCY | Cylinders Steering | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STPMP | Pump Steering | 51257 | 14617 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STOLC | Oil Cooler Steering | 51257 | 14617 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STLTR | Steering Linkages and Tie Rods | 51257 | 14617 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STHMU | Steering HMU | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STHLF | Steering System Hoses Lines and Fittings | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STCON-STWHL | Steering Wheel | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STCON-STCOL | Steering Column | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STCON | Controls Steering | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STACC-SACRH | Accumulator Steering R/H Front | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STACC-SACLH | Accumulator Steering L/H Front | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-STRSYS-STACC | Accumulators Steering | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-STRSYS | Steering System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-PNEUMC-START | Pneumatic Starter Motor | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-PNEUMC-PNTNK | Air Tank | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-PNEUMC-PNHLF | Pneumatic System Hoses Lines Fittings | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-PNEUMC-BRVLR-SVBRF | Brake Air Relay Valve | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-PNEUMC-BRVLR-ARCRR | Auto Retard Control | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-PNEUMC-BRVLR | Brake Control Valves | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-PNEUMC-AIRDR | Air Drier | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-PNEUMC | Pneumatic System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-MANGMT-UMTRN | Power Train Management System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-MANGMT-UMMMC | Mine Monitoring and Control | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-MANGMT-UMENG | Engine Management System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-MANGMT | Unit Management | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-TOWPP | Pump Towing | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-HOVLV | Valve Hoist | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-HOPMP | Pump Hoist & Rear Brake Cooling | 51257 | 14617 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-HOCYL | Cylinders Hoist | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-HDTNK | Tank Hydraulic | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-HYDSYS | Hydraulic System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-GRSYST-GRTNK | Auto Lube Resevoir | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-GRSYST-GRINJ | Auto Lube Injectors | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-GRSYST-ALHLF | Auto Lube Hoses Lines Fittings | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-GRSYST-ALELC | Auto Lube Electrical | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-GRSYST-ALCON | Auto Lube Controller | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-GRSYST-ALBPP | Auto Lube Pump | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-GRSYST | Grease Lubrication System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FRSUPP-FSMAN | Fire Suppression Manual | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FRSUPP-FSAUT | Fire Suppression Automatic | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FRSUPP-FSALM | Fire System Alarm | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FRSUPP | Fire Suppression System | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-WHTYR | Wheels Tyres & Rims | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-FDRVE | Final Drives | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-DRSHT | Drive Shaft - Transmission | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-DRLAX | Drive Line Axles | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-DIFFL | Differential | 51257 | 532 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-FDRSYS-AXLEC | Rear Axle Oil Cooling | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-FDRSYS | Final Drive System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-PMPDR-DRSHT | Drive Shaft - Pump Drive | 51257 | 9904 | 5600
CCK-MP-SUPP-WC3111-ENGINE-PMPDR | Pump Drive | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-LUBSY-OILPP | Oil Pump Engine | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-LUBSY | Engine Lubrication System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX-TBORF | Turbocharger R/H Front | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX-EXHST | Exhaust System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX-AIRFL | Air Filtration System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX-AFTER | Aftercooler | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-INTEX | Intake and Exhaust System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-FUSYS-FULTK | Fuel Tank | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-FUSYS-FUINJ | Fuel Injectors | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-FUSYS | Fuel System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS-WTRPP | Water Pump Engine | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS-THERM | Thermostats/Regulators | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS-RADTR | Radiator Engine | 51257 | 11941 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS-CSHLF | Cooling System Hoses Lines & Fittings | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS-COFAN | Fan Cooling System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS-BELTS | Fan Belts Engine | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COSYS | Engine Cooling System | 51257 | 51257 | 5600
CCK-MP-SUPP-WC3111-ENGINE-COMPR | Air Compressor | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ENGINE | Engine Assembly, Caterpillar 3512 | 51257 | 8333 | 5600
CCK-MP-SUPP-WC3111-ELCTLV-LIGHT | Lighting Low Voltage | 51257 | 51257 | 5600